## ag-grid
Id | Line No. | Rev. | Latest Rev. | PId | DN | Building | Floor | Insulation | Transmittal No. | Date Rec. | Spooling | Iss. to prefab | Prefab start | Welded | Prefab compl. | Sent to site | Del. to site | Install start | Install 50 | Install 90 | Install compl. | Length | Pipe class | Fluid | Latest location | Prefab Company | Install Company | Prefab remarks | Site remarks | As built | Test Pressure | Ped Cat | Ped Cat | IWP Number | Priority
35748 | ABP-7-701-004-80-SD | 3 | false | CH06822004-BD-PI-0495 | 80 | 5K | Riser | N/A | T01583 | 2023-09-28 |  | 2023-10-27 | 2023-11-05 |  | 2023-12-11 | 2023-12-15 | [5 empty] | 5.58 | 271 | 362 |  |  |  |  | NEW name of ISO; ABP-7-701-027-80-SD |  | 0 | SEP | SEP |  | 2
43535 | ABP-7-701-004-80-SD | 3 | false | CH06822004-BD-PI-0495 | 80 | 5K | Riser | N/A | T01583 | 2023-09-28 | [12 empty] | 271 | 362 | [6 empty] | 0 | SEP | SEP
43536 | ABP-7-701-004-80-SD | 3 | false | CH06822004-BD-PI-0495 | 80 | 5K | Riser | N/A | T01583 | 2023-09-28 | [12 empty] | 271 | 362 | [6 empty] | 0 | SEP | SEP
35749 | ABP-7-701-001-80-SD | 2 | false | CH06822004-BD-PI-0495 | 80 | 5K | Riser | N/A | T01583 | 2023-09-28 |  | 2023-10-27 | 2023-11-05 | 2023-11-19 | 2023-12-04 | 2023-12-05 |  | 2023-12-11 |  |  | 2024-01-12 | 6.2 | 271 | 362 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 2
35750 | ABP-7-701-001-80-SD | 2 | false | CH06822004-BD-PI-0495 | 80 | 5K | Riser | N/A | T01583 | 2023-09-28 |  | 2023-10-27 | 2023-11-06 | 2023-11-19 | 2023-12-04 | 2023-12-05 |  | 2024-02-05 |  |  | 2024-01-12 | 14.8 | 271 | 362 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 2
43469 | ABP-7-701-001-80-SD | 3 | true | CH06822004-BD-PI-0495 | 80 | 5K | Riser | N/A | T-078 | 2024-04-26 | [10 empty] | 2024-05-11 | 6.2 | 271 | 362 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
43470 | ABP-7-701-001-80-SD | 3 | true | CH06822004-BD-PI-0495 | 80 | 5K | Riser | N/A | T-078 | 2024-04-26 | [10 empty] | 2024-05-11 | 14.8 | 271 | 362 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
35751 | ABP-7-701-002-80-SD | 2 | false | CH06822004-BD-PI-0495 | 80 | 5K | Riser | N/A | T01583 | 2023-09-28 |  | 2023-10-27 | 2023-11-06 | 2023-11-14 | 2023-11-15 | 2023-11-21 |  | 2023-12-11 |  |  | 2024-01-09 | 19.8 | 271 | 362 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 2
43471 | ABP-7-701-002-80-SD | 3 | true | CH06822004-BD-PI-0495 | 80 | 5K | Riser | N/A | T-078 | 2024-04-26 | [10 empty] | 2024-05-11 | 19.8 | 271 | 362 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
35752 | ABP-7-701-003-80-SD | 2 | false | CH06822004-BD-PI-0495 | 80 | 5K | Riser | N/A | T01583 | 2023-09-28 |  | 2023-10-27 | 2023-11-05 |  | 2023-12-11 | 2023-12-15 | [5 empty] | 5.8 | 271 | 362 |  |  |  |  | NEW name of ISO; ABP-7-701-026-80-SD |  | 0 | SEP | SEP |  | 2
35753 | CIPV-2-300-506-40-SP | 2 | true | CH06822004-BD-PI-0523 | 40 | 5K | Riser | H3 | T01583 | 2023-09-28 |  | 2023-10-27 | 2023-11-05 | 2023-12-11 | 2023-12-11 | 2023-12-15 |  | 2024-01-08 |  |  | 2024-06-25 | 0.5 | 262 | 367 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 2
35754 | CIP-2-000-001-40-SP | 2 | true | CH06822004-BD-PI-0523 | 40 | 5K | Riser | H3 | T01583 | 2023-09-28 |  | 2023-10-27 | 2023-11-05 | 2023-12-11 | 2023-12-11 | 2023-12-15 |  | 2024-01-08 |  | 2024-03-23 | 2024-06-25 | 7.2 | 262 | 460 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 2
35755 | CO2F-7-600-002-25-SP1 | 2 | true | CH06822004-BD-PI-0449 | 25 | 5K | Riser | N/A | T01583 | 2023-09-28 |  | 2023-10-27 | 2023-11-09 | 2023-11-19 | 2023-12-04 | 2023-12-05 |  | 2023-12-10 |  | 2024-01-04 | 2024-02-13 | 7.3 | 264 | 369 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 2
35756 | CO2F-7-600-002-25-SP1 | 2 | true | CH06822004-BD-PI-0449 | 25 | 5K | Riser | N/A | T01583 | 2023-09-28 |  | 2023-10-27 | 2023-11-12 | 2023-11-19 | 2023-12-04 | 2023-12-05 |  | 2023-12-10 | 2023-12-18 | 2024-01-04 | 2024-01-23 | 6.1 | 264 | 369 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 2
35757 | CS-7-201-043-65-SP1 | 2 | false | CH06822004-BD-PI-1179 | 65 | 5K | Riser | H2 | T01583 | 2023-09-28 |  | 2023-10-27 | 2023-11-12 | 2023-12-04 | 2023-12-04 | 2023-12-05 |  | 2024-01-05 |  |  | 2024-01-23 | 6.8 | 264 | 371 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 2
35758 | CS-7-201-043-65-SP1 | 2 | false | CH06822004-BD-PI-1179 | 65 | 5K | Riser | H2 | T01583 | 2023-09-28 |  | 2023-10-27 | 2023-11-12 | 2023-11-19 | 2023-12-11 | 2023-12-15 |  | 2024-01-05 |  |  | 2024-01-23 | 8.3 | 264 | 371 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 2
35759 | CS-7-201-043-65-SP1 | 2 | false | CH06822004-BD-PI-1179 | 65 | 5K | Riser | H2 | T01583 | 2023-09-28 |  | 2023-10-27 | 2023-11-12 | 2023-11-19 | 2023-12-11 | 2023-12-15 |  | 2024-01-05 |  |  | 2024-01-23 | 5.2 | 264 | 371 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 2
43477 | CS-7-201-043-65-SP1 | 3 | true | CH06822004-BD-PI-1179 | 65 | 5K | Riser | H2 | T-047 | 2024-01-25 |  | 2023-10-27 | 2023-11-12 | 2023-12-04 | 2023-12-04 | 2023-12-05 |  | 2024-01-05 |  | 2024-02-06 | 2024-03-13 | 4.8 | 264 | 371 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
43478 | CS-7-201-043-65-SP1 | 3 | true | CH06822004-BD-PI-1179 | 65 | 5K | Riser | H2 | T-047 | 2024-01-25 |  | 2023-10-27 | 2023-11-12 | 2023-11-19 | 2023-12-11 | 2023-12-15 |  | 2024-01-05 |  | 2024-02-06 | 2024-02-12 | 9 | 264 | 371 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
43479 | CS-7-201-043-65-SP1 | 3 | true | CH06822004-BD-PI-1179 | 65 | 5K | Riser | H2 | T-047 | 2024-01-25 |  | 2023-10-27 | 2023-11-12 | 2023-11-19 | 2023-12-11 | 2023-12-15 |  | 2024-01-05 |  | 2024-02-06 | 2024-02-12 | 6.7 | 264 | 371 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
35760 | DK4-0-600-007-25-SD6 | 2 | false | CH06822004-BD-PI-0558 | 25 | 5K | Riser | H6 | T01583 | 2023-09-28 |  | 2023-10-27 | 2023-11-05 | 2023-11-14 | 2023-11-15 | 2023-11-21 |  | 2023-12-05 |  |  | 2023-12-12 | 1.4 | 261 | 375 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 2
35761 | DK4-0-600-007-25-SD6 | 2 | false | CH06822004-BD-PI-0558 | 25 | 5K | Riser | H6 | T01583 | 2023-09-28 |  | 2023-10-27 | 2023-11-05 | 2023-11-07 | 2023-11-08 | 2023-11-21 |  | 2023-12-05 |  |  | 2023-12-12 | 7 | 261 | 375 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 2
43825 | DK4-0-600-007-25-SD6 | 3 | true | CH06822004-BD-PI-0558 | 25 | 5K | Riser | H6 | T-048 | 2024-01-30 |  | 2023-10-27 | 2023-11-05 | 2023-11-14 | 2023-11-15 | 2023-11-21 |  | 2023-12-05 |  | 2024-01-12 | 2024-03-07 | 2.2 | 261 | 375 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
43826 | DK4-0-600-007-25-SD6 | 3 | true | CH06822004-BD-PI-0558 | 25 | 5K | Riser | H6 | T-048 | 2024-01-30 |  | 2023-10-27 | 2023-11-05 | 2023-11-07 | 2023-11-08 | 2023-11-21 |  | 2023-12-05 |  | 2024-01-31 | 2024-03-07 | 7 | 261 | 375 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
35762 | DKA-7-400-009-40-SD | 2 | true | CH06822004-BD-PI-1201 | 40 | 5K | Riser | H3 | T01583 | 2023-09-28 |  | 2023-10-27 | 2023-11-06 | 2023-11-19 | 2023-12-04 | 2023-12-05 |  | 2023-12-12 |  | 2023-12-18 | 2023-12-21 | 6.9 | 271 | 376 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 2
35763 | DKS-7-401-004-40-SD | 2 | true | CH06822004-BD-PI-0530 | 40 | 5K | Riser | H3 | T01583 | 2023-09-28 |  | 2023-10-27 | 2023-11-21 | 2023-12-04 | 2023-12-04 | 2023-12-05 |  | 2024-01-03 |  |  | 2024-01-12 | 1.1 | 271 | 378 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 2
35764 | DKS-7-401-004-40-SD | 2 | true | CH06822004-BD-PI-0530 | 40 | 5K | Riser | H3 | T01583 | 2023-09-28 |  | 2023-10-27 | 2023-11-05 |  | 2023-12-15 | 2023-12-15 |  | 2024-01-03 |  |  | 2024-01-12 | 5.6 | 271 | 378 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 2
35765 | DKS-7-401-004-40-SD | 2 | true | CH06822004-BD-PI-0530 | 40 | 5K | Riser | H3 | T01583 | 2023-09-28 |  | 2023-10-27 | 2023-11-21 |  | 2023-12-14 | 2023-12-15 |  | 2024-01-03 |  |  | 2024-01-15 | 5.9 | 271 | 378 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 2
35766 | DKS-7-401-004-40-SD | 2 | true | CH06822004-BD-PI-0530 | 40 | 5K | Riser | H3 | T01583 | 2023-09-28 |  | 2023-10-27 | 2023-11-05 |  | 2023-12-14 | 2023-12-15 |  | 2024-01-03 |  |  | 2024-01-12 | 5.7 | 271 | 378 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 2
35767 | DLF-7-834-005-50-SP1 | 2 | false | CH06822004-BD-PI-0537 | 50 | 5K | Riser | N/A | T01583 | 2023-09-28 |  | 2023-10-27 | 2023-11-14 | 2023-11-19 | 2023-12-13 | 2023-12-15 |  | 2024-01-05 |  |  |  | 5.8 | 264 | 380 | Jozef Kotul | [5 empty] | 0 | SEP | SEP |  | 2
35768 | DLF-7-834-005-50-SP1 | 2 | false | CH06822004-BD-PI-0537 | 50 | 5K | Riser | N/A | T01583 | 2023-09-28 |  | 2023-10-27 | 2023-11-09 | 2023-11-19 | 2023-12-04 | 2023-12-05 |  | 2024-01-05 |  |  |  | 6.6 | 264 | 380 | Jozef Kotul | [5 empty] | 0 | SEP | SEP |  | 2
35769 | DLF-7-834-005-50-SP1 | 2 | false | CH06822004-BD-PI-0537 | 50 | 5K | Riser | N/A | T01583 | 2023-09-28 |  | 2023-10-27 | 2023-11-05 | 2023-11-15 | 2023-11-15 | 2023-12-05 |  | 2024-01-05 |  |  |  | 0.3 | 264 | 380 | Jozef Kotul | [5 empty] | 0 | SEP | SEP |  | 2
35770 | DLF-7-834-005-50-SP1 | 2 | false | CH06822004-BD-PI-0537 | 50 | 5K | Riser | N/A | T01583 | 2023-09-28 |  | 2023-10-27 | 2023-11-09 | 2023-11-19 | 2023-12-13 | 2023-12-15 |  | 2024-01-05 |  |  |  | 5.9 | 264 | 380 | Jozef Kotul | [5 empty] | 0 | SEP | SEP |  | 2
42089 | DLF-7-834-005-50-SP1 | 3 | false | CH06822004-BD-PI-0537 | 50 | 5K | Riser | N/A | PEL-ZAU-T-037 | 2024-01-15 |  | 2023-10-27 | 2023-11-14 | 2023-11-19 | 2023-12-13 | 2023-12-15 |  | 2024-01-05 |  |  | 2024-01-23 | 5.8 | 264 | 380 | Virgil Frinculescu |  |  |  | Only TAG Names changed |  | 0 | SEP | SEP |  | 2
42090 | DLF-7-834-005-50-SP1 | 3 | false | CH06822004-BD-PI-0537 | 50 | 5K | Riser | N/A | PEL-ZAU-T-037 | 2024-01-15 |  | 2023-10-27 | 2023-11-09 | 2023-11-19 | 2023-12-04 | 2023-12-05 |  | 2024-01-05 |  |  | 2024-01-23 | 6.6 | 264 | 380 | Virgil Frinculescu |  |  |  | Only TAG Names changed |  | 0 | SEP | SEP |  | 2
42091 | DLF-7-834-005-50-SP1 | 3 | false | CH06822004-BD-PI-0537 | 50 | 5K | Riser | N/A | PEL-ZAU-T-037 | 2024-01-15 |  | 2023-10-27 | 2023-11-05 | 2023-11-15 | 2023-11-15 | 2023-12-05 |  | 2024-01-05 |  |  | 2024-01-23 | 0.3 | 264 | 380 | Virgil Frinculescu |  |  |  | Only TAG Names changed |  | 0 | SEP | SEP |  | 2
42092 | DLF-7-834-005-50-SP1 | 3 | false | CH06822004-BD-PI-0537 | 50 | 5K | Riser | N/A | PEL-ZAU-T-037 | 2024-01-15 |  | 2023-10-27 | 2023-11-09 | 2023-11-19 | 2023-12-13 | 2023-12-15 |  | 2024-01-05 |  |  | 2024-01-23 | 5.9 | 264 | 380 | Virgil Frinculescu |  |  |  | Only TAG Names changed |  | 0 | SEP | SEP |  | 2
45597 | DLF-7-834-005-50-SP1 | 4 | true | CH06822004-BD-PI-0537 | 50 | 5K | Riser | N/A | T-061 | 2024-03-08 |  | 2023-10-27 | 2023-11-14 | 2023-11-19 | 2023-12-13 | 2023-12-15 |  | 2024-03-14 |  | 2024-03-08 | 2024-03-25 | 5.8 | 264 | 380 | Virgil Frinculescu |  |  |  | New Tie-in for Manifold |  | 0 | SEP | SEP
45598 | DLF-7-834-005-50-SP1 | 4 | true | CH06822004-BD-PI-0537 | 50 | 5K | Riser | N/A | T-061 | 2024-03-08 |  | 2023-10-27 | 2023-11-09 | 2023-11-19 | 2023-12-04 | 2023-12-05 |  | 2024-01-05 |  | 2024-03-08 | 2024-03-14 | 6.6 | 264 | 380 | Virgil Frinculescu |  |  |  | New Tie-in for DLF Manifold |  | 0 | SEP | SEP
45599 | DLF-7-834-005-50-SP1 | 4 | true | CH06822004-BD-PI-0537 | 50 | 5K | Riser | N/A | T-061 | 2024-03-08 |  | 2023-10-27 | 2023-11-05 | 2023-11-15 | 2023-11-15 | 2023-12-05 |  | 2024-01-05 |  | 2024-03-08 | 2024-03-14 | 0.3 | 264 | 380 | Virgil Frinculescu |  |  |  | New Tie-in for DLF Manifold |  | 0 | SEP | SEP
45600 | DLF-7-834-005-50-SP1 | 4 | true | CH06822004-BD-PI-0537 | 50 | 5K | Riser | N/A | T-061 | 2024-03-08 |  | 2023-10-27 | 2023-11-09 | 2023-11-19 | 2023-12-13 | 2023-12-15 |  | 2024-01-05 |  | 2024-03-08 | 2024-03-14 | 5.9 | 264 | 380 | Virgil Frinculescu |  |  |  | New Tie-in for DLF Manifold |  | 0 | SEP | SEP
35771 | DLP-7-301-008-50-SP1 | 2 | true | CH06822004-BD-PI-0544 | 50 | 5K | Riser | N/A | T01583 | 2023-09-28 |  | 2023-10-27 | 2023-11-14 | 2023-11-19 | 2023-12-11 | 2023-12-15 |  | 2024-01-05 |  |  | 2024-01-31 | 12.8 | 264 | 382 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 2
35772 | GA-0-245-007-25-SD5 | 2 | false | CH06822004-BD-PI-0572 | 25 | 5K | Riser | N/A | T01583 | 2023-09-28 | [11 empty] | 9.4 | 260 | 386 | [6 empty] | 0 | SEP | SEP |  | 2
35773 | GA-0-245-007-25-SD5 | 2 | false | CH06822004-BD-PI-0572 | 25 | 5K | Riser | N/A | T01583 | 2023-09-28 |  | 2023-10-27 | 2023-11-19 | 2023-12-15 | 2023-12-15 | 2023-12-15 |  | 2024-01-08 |  |  | 2024-01-16 | 4.1 | 260 | 386 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 2
35774 | GA-0-245-007-25-SD5 | 2 | false | CH06822004-BD-PI-0572 | 25 | 5K | Riser | N/A | T01583 | 2023-09-28 |  | 2023-10-27 | 2023-11-19 | 2023-12-15 | 2023-12-15 | 2023-12-15 |  | 2024-01-08 |  |  | 2024-01-16 | 6.3 | 260 | 386 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 2
35775 | GA-0-245-007-25-SD5 | 2 | false | CH06822004-BD-PI-0572 | 25 | 5K | Riser | N/A | T01583 | 2023-09-28 |  | 2023-10-27 | 2023-11-19 |  | 2023-12-15 | 2023-12-15 |  | 2024-01-08 |  |  | 2024-01-16 | 4.2 | 260 | 386 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 2
43487 | GA-0-245-007-25-SD5 | 3 | true | CH06822004-BD-PI-0572 | 25 | 5K | Riser | N/A | T-047 | 2024-01-25 | [7 empty] | 2024-02-14 |  |  | 2024-02-29 | 2.8 | 260 | 386 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
43488 | GA-0-245-007-25-SD5 | 3 | true | CH06822004-BD-PI-0572 | 25 | 5K | Riser | N/A | T-047 | 2024-01-25 |  | 2023-10-27 | 2023-11-19 | 2023-12-15 | 2023-12-15 | 2023-12-15 |  | 2024-02-14 |  |  | 2024-02-22 | 4.2 | 260 | 386 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
43489 | GA-0-245-007-25-SD5 | 3 | true | CH06822004-BD-PI-0572 | 25 | 5K | Riser | N/A | T-047 | 2024-01-25 |  | 2023-10-27 | 2023-11-19 | 2023-12-15 | 2023-12-15 | 2023-12-15 |  | 2024-02-14 |  |  | 2024-02-26 | 5.8 | 260 | 386 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
43490 | GA-0-245-007-25-SD5 | 3 | true | CH06822004-BD-PI-0572 | 25 | 5K | Riser | N/A | T-047 | 2024-01-25 |  | 2023-10-27 | 2023-11-19 |  | 2023-12-15 | 2023-12-15 |  | 2024-02-14 |  |  | 2024-02-26 | 4.2 | 260 | 386 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
35776 | GR-0-244-002-80-SD5 | 2 | true | CH06822004-BD-PI-0565 | 80 | 5K | Riser | C3 | T01583 | 2023-09-28 |  | 2023-10-27 | 2023-11-04 | 2023-11-16 | 2023-11-17 | 2023-11-21 |  | 2023-12-05 |  |  | 2023-12-12 | 6.2 | 260 | 387 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 2
35777 | GR-0-244-002-80-SD5 | 2 | true | CH06822004-BD-PI-0565 | 80 | 5K | Riser | C3 | T01583 | 2023-09-28 |  | 2023-10-27 | 2023-11-07 | 2023-11-15 | 2023-11-16 | 2023-11-21 |  | 2023-12-05 | 2023-12-18 | 2024-01-04 | 2024-01-12 | 2.2 | 260 | 387 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 2
35778 | GR-0-244-002-80-SD5 | 2 | true | CH06822004-BD-PI-0565 | 80 | 5K | Riser | C3 | T01583 | 2023-09-28 |  | 2023-10-27 | 2023-11-04 | 2023-11-15 | 2023-11-16 | 2023-11-21 |  | 2023-12-05 |  |  | 2023-12-12 | 7.4 | 260 | 387 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 2
35779 | GR-0-244-002-80-SD5 | 2 | true | CH06822004-BD-PI-0565 | 80 | 5K | Riser | C3 | T01583 | 2023-09-28 |  | 2023-10-27 | 2023-11-04 | 2023-11-16 | 2023-11-17 | 2023-11-21 |  | 2023-12-05 |  |  | 2023-12-12 | 5.8 | 260 | 387 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 2
35780 | GV-0-244-003-80-SD5 | 2 | true | CH06822004-BD-PI-0565 | 80 | 5K | Riser | C3 | T01583 | 2023-09-28 |  | 2023-10-27 | 2023-11-12 | 2023-11-17 | 2023-11-19 | 2023-11-21 |  | 2023-12-05 | 2023-12-18 | 2024-01-04 | 2024-01-12 | 2.8 | 260 | 388 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 2
35781 | GV-0-244-003-80-SD5 | 2 | true | CH06822004-BD-PI-0565 | 80 | 5K | Riser | C3 | T01583 | 2023-09-28 |  | 2023-10-27 | 2023-11-12 | 2023-11-17 | 2023-11-19 | 2023-11-21 |  | 2023-12-05 |  | 2023-12-18 | 2024-01-05 | 6.2 | 260 | 388 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 2
35782 | GV-0-244-003-80-SD5 | 2 | true | CH06822004-BD-PI-0565 | 80 | 5K | Riser | C3 | T01583 | 2023-09-28 |  | 2023-10-27 | 2023-11-12 | 2023-11-17 | 2023-11-19 | 2023-11-21 |  | 2023-12-05 |  |  | 2023-12-12 | 11.8 | 260 | 388 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 2
35783 | GV-0-244-003-80-SD5 | 2 | true | CH06822004-BD-PI-0565 | 80 | 5K | Riser | C3 | T01583 | 2023-09-28 |  | 2023-10-27 | 2023-11-12 | 2023-11-17 | 2023-11-19 | 2023-11-21 |  | 2023-12-05 |  |  | 2023-12-12 | 1.4 | 260 | 388 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 2
35784 | GV-0-244-012-25-SD5 | 2 | false | CH06822004-BD-PI-0565 | 25 | 5K | Riser | C3 | T01583 | 2023-09-29 |  | 2023-10-28 | 2023-11-08 | 2023-11-18 | 2023-11-20 | 2023-11-22 |  | 2023-12-06 |  |  | 2023-12-18 | 0.7 | 260 | 388 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 2
35785 | GV-0-244-012-25-SD5 | 2 | false | CH06822004-BD-PI-0565 | 25 | 5K | Riser | C3 | T01583 | 2023-09-29 |  | 2023-10-28 | 2023-11-08 | 2023-11-18 | 2023-11-20 | 2023-11-22 |  | 2023-12-06 |  |  | 2024-02-07 | 0.2 | 260 | 388 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 2
41978 | GV-0-244-012-25-SD5 | 3 | true | CH06822004-BD-PI-0565 | 25 | 5K | Riser | C3 | PEL-ZAU-T-034 | 2024-01-12 |  | 2023-10-28 | 2023-11-08 | 2023-11-18 | 2023-11-20 | 2023-11-22 |  | 2023-12-06 |  | 2023-12-18 | 2024-03-05 | 0.8 | 260 | 388 | Virgil Frinculescu |  |  |  | Modificaiton of the Valve arrangement |  | 0 | SEP | SEP |  | 2
41979 | GV-0-244-012-25-SD5 | 3 | true | CH06822004-BD-PI-0565 | 25 | 5K | Riser | C3 | PEL-ZAU-T-034 | 2024-01-12 |  | 2023-10-28 | 2023-11-08 | 2023-11-18 | 2023-11-20 | 2023-11-22 |  | 2023-12-06 |  |  | 2024-02-07 | 0.2 | 260 | 388 | Virgil Frinculescu |  |  |  | No change |  | 0 | SEP | SEP |  | 2
35786 | HR-NT-0-212-002-100-CA | 2 | false | CH06822004-BD-PI-0579 | 100 | 5K | Riser | H1 | T01583 | 2023-09-28 | 2023-11-23 | 2023-11-23 | 2023-12-07 | 2023-12-13 | 2023-12-13 | 2023-12-15 |  | 2024-01-08 |  |  | 2024-02-07 | 0.5 | 249 | 389 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 2
35787 | HR-NT-0-212-002-100-CA | 2 | false | CH06822004-BD-PI-0579 | 100 | 5K | Riser | H1 | T01583 | 2023-09-28 | 2023-11-23 | 2023-11-23 | 2023-12-07 | 2023-12-13 | 2023-12-13 | 2023-12-15 |  | 2024-01-08 |  |  | 2024-01-23 | 0.3 | 249 | 389 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 2
35788 | HR-NT-0-212-002-100-CA | 2 | false | CH06822004-BD-PI-0579 | 100 | 5K | Riser | H1 | T01583 | 2023-09-28 | 2023-11-23 | 2023-11-23 | 2023-12-07 | 2023-12-13 | 2023-12-13 | 2023-12-15 |  | 2024-01-08 |  |  | 2024-01-26 | 9 | 249 | 389 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 2
48662 | HR-NT-0-212-002-100-CA | 3 | true | CH06822004-BD-PI-0579 | 100 | 5K | Riser | H1 | T-074 | 2024-04-15 | 2023-11-23 | 2023-11-23 | 2023-12-07 | 2023-12-13 | 2023-12-13 | 2023-12-15 |  | 2024-01-08 |  | 2024-04-15 | 2024-05-11 | 0.3 | 249 | 389 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48663 | HR-NT-0-212-002-100-CA | 3 | true | CH06822004-BD-PI-0579 | 100 | 5K | Riser | H1 | T-074 | 2024-04-15 | 2023-11-23 | 2023-11-23 | 2023-12-07 | 2023-12-13 | 2023-12-13 | 2023-12-15 |  | 2024-01-08 |  | 2024-04-15 | 2024-05-11 | 9 | 249 | 389 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48664 | HR-NT-0-212-002-100-CA | 3 | true | CH06822004-BD-PI-0579 | 100 | 5K | Riser | H1 | T-074 | 2024-04-15 | 2023-11-23 | 2023-11-23 | 2023-12-07 | 2023-12-13 | 2023-12-13 | 2023-12-15 |  | 2024-05-11 |  | 2024-04-15 | 2024-05-11 | 3.6 | 249 | 389 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48665 | HR-NT-0-212-002-100-CA | 3 | true | CH06822004-BD-PI-0579 | 100 | 5K | Riser | H1 | T-074 | 2024-04-15 | [10 empty] | 2024-05-11 | 0.5 | 249 | 389 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
35789 | HV-NT-0-212-003-100-CA | 2 | true | CH06822004-BD-PI-0579 | 100 | 5K | Riser | H1 | T01583 | 2023-09-28 | 2023-11-23 | 2023-11-23 | 2023-12-07 |  | 2023-12-15 | 2023-12-15 |  | 2024-01-08 |  |  | 2024-02-07 | 0.6 | 249 | 390 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 2
35790 | HV-NT-0-212-003-100-CA | 2 | true | CH06822004-BD-PI-0579 | 100 | 5K | Riser | H1 | T01583 | 2023-09-28 | 2023-11-23 | 2023-11-23 | 2023-12-07 | 2023-12-15 | 2023-12-15 | 2023-12-15 |  | 2024-01-08 |  |  | 2024-02-21 | 6.4 | 249 | 390 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 2
35791 | HV-NT-0-212-003-100-CA | 2 | true | CH06822004-BD-PI-0579 | 100 | 5K | Riser | H1 | T01583 | 2023-09-28 | 2023-11-23 | 2023-11-23 | 2023-12-07 | 2023-12-15 | 2023-12-15 | 2023-12-15 |  | 2024-01-08 |  |  | 2024-02-07 | 7 | 249 | 390 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 2
35792 | KKR-0-241-002-100-SD5 | 2 | true | CH06822004-BD-PI-0593 | 100 | 5K | Riser | C2 | T01583 | 2023-09-28 |  | 2023-10-27 | 2023-11-08 | 2023-11-17 | 2023-11-19 | 2023-11-21 |  | 2023-12-13 |  | 2024-01-04 | 2024-02-29 | 2.9 | 260 | 391 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 2
35793 | KKR-0-241-002-100-SD5 | 2 | true | CH06822004-BD-PI-0593 | 100 | 5K | Riser | C2 | T01583 | 2023-09-28 |  | 2023-10-27 | 2023-11-08 | 2023-11-17 | 2023-11-19 | 2023-11-21 |  | 2023-12-13 |  | 2024-01-04 | 2024-01-09 | 8.5 | 260 | 391 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 2
35794 | KKR-0-241-002-100-SD5 | 2 | true | CH06822004-BD-PI-0593 | 100 | 5K | Riser | C2 | T01583 | 2023-09-28 |  | 2023-10-27 | 2023-11-08 | 2023-11-17 | 2023-11-19 | 2023-11-21 |  | 2023-12-13 |  |  | 2024-01-09 | 0.4 | 260 | 391 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 2
35795 | KKR-0-241-002-100-SD5 | 2 | true | CH06822004-BD-PI-0593 | 100 | 5K | Riser | C2 | T01583 | 2023-09-28 |  | 2023-10-27 | 2023-11-06 | 2023-11-17 | 2023-11-19 | 2023-11-21 |  | 2023-12-13 |  |  | 2024-01-09 | 1.8 | 260 | 391 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 2
35796 | KKV-0-241-003-100-SD5 | 2 | true | CH06822004-BD-PI-0593 | 100 | 5K | Riser | C2 | T01583 | 2023-09-28 |  | 2023-10-27 | 2023-11-09 | 2023-11-13 | 2023-11-16 | 2023-11-21 |  | 2023-12-13 |  | 2024-01-04 | 2024-01-09 | 0.1 | 260 | 392 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 2
35797 | KKV-0-241-003-100-SD5 | 2 | true | CH06822004-BD-PI-0593 | 100 | 5K | Riser | C2 | T01583 | 2023-09-28 |  | 2023-10-27 | 2023-11-09 | 2023-11-13 | 2023-11-16 | 2023-11-21 |  | 2023-12-13 |  | 2024-01-04 | 2024-01-09 | 2.5 | 260 | 392 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 2
35798 | KKV-0-241-003-100-SD5 | 2 | true | CH06822004-BD-PI-0593 | 100 | 5K | Riser | C2 | T01583 | 2023-09-28 |  | 2023-10-27 | 2023-11-06 | 2023-11-13 | 2023-11-16 | 2023-11-21 |  | 2023-12-13 |  |  | 2024-01-09 | 1.8 | 260 | 392 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 2
35799 | KKV-0-241-003-100-SD5 | 2 | true | CH06822004-BD-PI-0593 | 100 | 5K | Riser | C2 | T01583 | 2023-09-28 |  | 2023-10-27 | 2023-11-07 | 2023-11-13 | 2023-11-16 | 2023-11-21 |  | 2023-12-13 |  | 2024-01-04 | 2024-01-09 | 8.4 | 260 | 392 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 2
38554 | KKV-0-241-003-100-SD5 | 2 | false | CH06822004-BD-PI-0593 | 100 | 5K | Riser | C2 | T01967 | 2023-11-11 |  | 2023-10-27 | 2023-11-07 | [8 empty] | 0.1 | 260 | 392 | [6 empty] | 0 | SEP | SEP |  | 2
38555 | KKV-0-241-003-100-SD5 | 2 | false | CH06822004-BD-PI-0593 | 100 | 5K | Riser | C2 | T01967 | 2023-11-11 |  | 2023-10-27 | 2023-11-07 | [8 empty] | 0.7 | 260 | 392 | [6 empty] | 0 | SEP | SEP |  | 2
38556 | KKV-0-241-003-100-SD5 | 2 | false | CH06822004-BD-PI-0593 | 100 | 5K | Riser | C2 | T01967 | 2023-11-11 |  | 2023-10-27 | 2023-11-04 | [8 empty] | 0.2 | 260 | 392 | [6 empty] | 0 | SEP | SEP |  | 2
38557 | KKV-0-241-003-100-SD5 | 2 | false | CH06822004-BD-PI-0593 | 100 | 5K | Riser | C2 | T01967 | 2023-11-11 |  | 2023-10-27 | 2023-11-07 | [8 empty] | 8.4 | 260 | 392 | [6 empty] | 0 | SEP | SEP |  | 2
35800 | KR-0-216-012-125-SD5 | 2 | false | CH06822004-BD-PI-0607 | 125 | 5K | Riser | C2 | T01583 | 2023-09-28 |  | 2023-10-27 | 2023-11-16 | 2023-11-19 | 2023-12-11 | 2023-12-15 |  | 2024-01-08 |  |  | 2024-02-07 | 1.9 | 260 | 393 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 2
35801 | KR-0-216-012-125-SD5 | 2 | false | CH06822004-BD-PI-0607 | 125 | 5K | Riser | C2 | T01583 | 2023-09-28 |  | 2023-10-27 | 2023-11-16 |  | 2023-12-15 | 2023-12-15 |  | 2024-01-08 |  |  | 2024-01-12 | 6.2 | 260 | 393 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 2
35802 | KR-0-216-012-125-SD5 | 2 | false | CH06822004-BD-PI-0607 | 125 | 5K | Riser | C2 | T01583 | 2023-09-28 |  | 2023-10-27 | 2023-11-16 | 2023-12-11 | 2023-12-11 | 2023-12-15 |  | 2024-01-08 |  |  | 2024-01-12 | 5.9 | 260 | 393 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 2
35803 | KR-0-216-012-125-SD5 | 2 | false | CH06822004-BD-PI-0607 | 125 | 5K | Riser | C2 | T01583 | 2023-09-28 |  | 2023-10-27 | 2023-11-16 |  | 2023-12-11 | 2023-12-15 |  | 2024-01-08 |  |  | 2024-01-12 | 6.2 | 260 | 393 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 2
35804 | KR-0-216-012-125-SD5 | 2 | false | CH06822004-BD-PI-0607 | 125 | 5K | Riser | C2 | T01583 | 2023-09-28 |  | 2023-10-27 | 2023-11-07 | 2023-11-19 | 2023-12-11 | 2023-12-15 |  | 2024-01-08 |  |  | 2024-01-12 | 1.3 | 260 | 393 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 2
41923 | KR-0-216-012-125-SD5 | 3 | false | CH06822004-BD-PI-0607 | 125 | 5K | Riser | C2 | PEL-ZAU-T-036 | 2024-01-12 |  | 2023-10-27 | 2023-11-16 | 2023-11-19 | 2023-12-11 | 2023-12-15 |  | 2024-01-08 |  |  |  | 1.9 | 260 | 393 |  |  |  |  | No change |  | 0 | SEP | SEP
41924 | KR-0-216-012-125-SD5 | 3 | false | CH06822004-BD-PI-0607 | 125 | 5K | Riser | C2 | PEL-ZAU-T-036 | 2024-01-12 |  | 2023-10-27 | 2023-11-16 |  | 2023-12-15 | 2023-12-15 |  | 2024-01-08 |  | 2024-01-12 |  | 6.2 | 260 | 393 |  |  |  |  | No change |  | 0 | SEP | SEP |  | 2
41925 | KR-0-216-012-125-SD5 | 3 | false | CH06822004-BD-PI-0607 | 125 | 5K | Riser | C2 | PEL-ZAU-T-036 | 2024-01-12 |  | 2023-10-27 | 2023-11-16 | 2023-12-11 | 2023-12-11 | 2023-12-15 |  | 2024-01-08 |  | 2024-01-12 |  | 5.9 | 260 | 393 |  |  |  |  | No change |  | 0 | SEP | SEP |  | 2
41926 | KR-0-216-012-125-SD5 | 3 | false | CH06822004-BD-PI-0607 | 125 | 5K | Riser | C2 | PEL-ZAU-T-036 | 2024-01-12 |  | 2023-10-27 | 2023-11-16 |  | 2023-12-11 | 2023-12-15 |  | 2024-01-08 |  | 2024-01-12 |  | 6.2 | 260 | 393 |  |  |  |  | Updated Pipe Lenghts DN25 |  | 0 | SEP | SEP |  | 2
41927 | KR-0-216-012-125-SD5 | 3 | false | CH06822004-BD-PI-0607 | 125 | 5K | Riser | C2 | PEL-ZAU-T-036 | 2024-01-12 |  | 2023-10-27 | 2023-11-07 | 2023-11-19 | 2023-12-11 | 2023-12-15 |  | 2024-01-08 |  | 2024-01-12 |  | 1.3 | 260 | 393 |  |  |  |  | No change |  | 0 | SEP | SEP |  | 2
43985 | KR-0-216-012-125-SD5 | 4 | true | CH06822004-BD-PI-0607 | 125 | 5K | Riser | C2 | T-051 | 2024-02-01 |  | 2023-10-27 | 2023-11-16 | 2023-11-19 | 2023-12-11 | 2023-12-15 |  | 2024-01-08 |  |  | 2024-03-06 | 1.9 | 260 | 393 | Virgil Frinculescu |  |  |  | No change. Latest rev. 4 is added to the w.map. |  | 0 | SEP | SEP
43986 | KR-0-216-012-125-SD5 | 4 | true | CH06822004-BD-PI-0607 | 125 | 5K | Riser | C2 | T-051 | 2024-02-01 |  | 2023-10-27 | 2023-11-16 |  | 2023-12-15 | 2023-12-15 |  | 2024-01-08 |  | 2024-01-12 | 2024-02-02 | 6.2 | 260 | 393 | Virgil Frinculescu |  |  |  | No change |  | 0 | SEP | SEP
43987 | KR-0-216-012-125-SD5 | 4 | true | CH06822004-BD-PI-0607 | 125 | 5K | Riser | C2 | T-051 | 2024-02-01 |  | 2023-10-27 | 2023-11-16 | 2023-12-11 | 2023-12-11 | 2023-12-15 |  | 2024-02-26 |  | 2024-01-12 | 2024-03-13 | 5.9 | 260 | 393 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
43988 | KR-0-216-012-125-SD5 | 4 | true | CH06822004-BD-PI-0607 | 125 | 5K | Riser | C2 | T-051 | 2024-02-01 |  | 2023-10-27 | 2023-11-16 |  | 2023-12-11 | 2023-12-15 |  | 2024-02-26 |  | 2024-01-12 | 2024-03-07 | 6.2 | 260 | 393 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
43989 | KR-0-216-012-125-SD5 | 4 | true | CH06822004-BD-PI-0607 | 125 | 5K | Riser | C2 | T-051 | 2024-02-01 |  | 2023-10-27 | 2023-11-07 | 2023-11-19 | 2023-12-11 | 2023-12-15 |  | 2024-01-08 |  | 2024-01-12 | 2024-02-02 | 1.3 | 260 | 393 | Virgil Frinculescu |  |  |  | No change |  | 0 | SEP | SEP
35805 | KV-0-216-003-125-SD5 | 2 | false | CH06822004-BD-PI-0607 | 125 | 5K | Riser | C2 | T01583 | 2023-09-28 |  | 2023-10-27 | 2023-11-13 | 2023-11-20 | 2023-11-21 | 2023-11-21 |  | 2023-12-12 | 2023-12-18 |  | 2024-02-06 | 6.4 | 260 | 394 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 2
35806 | KV-0-216-003-125-SD5 | 2 | false | CH06822004-BD-PI-0607 | 125 | 5K | Riser | C2 | T01583 | 2023-09-28 |  | 2023-10-27 | 2023-11-13 | 2023-11-20 | 2023-11-21 | 2023-11-21 |  | 2023-12-12 |  |  |  | 5.7 | 260 | 394 | Jozef Kotul |  |  | HOLD | HOLD |  | 0 | SEP | SEP |  | 2
35807 | KV-0-216-003-125-SD5 | 2 | false | CH06822004-BD-PI-0607 | 125 | 5K | Riser | C2 | T01583 | 2023-09-28 |  | 2023-10-27 | 2023-11-13 | 2023-11-20 | 2023-11-21 | 2023-11-21 |  | 2023-12-12 |  |  |  | 5.7 | 260 | 394 | Jozef Kotul | [5 empty] | 0 | SEP | SEP |  | 2
35808 | KV-0-216-003-125-SD5 | 2 | false | CH06822004-BD-PI-0607 | 125 | 5K | Riser | C2 | T01583 | 2023-09-28 |  | 2023-10-27 | 2023-11-13 | 2023-11-20 | 2023-11-21 | 2023-11-21 |  | 2023-12-12 |  |  | 2023-12-21 | 1.3 | 260 | 394 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 2
35809 | KV-0-216-003-125-SD5 | 2 | false | CH06822004-BD-PI-0607 | 125 | 5K | Riser | C2 | T01583 | 2023-09-28 |  | 2023-10-27 | 2023-11-13 | 2023-11-20 | 2023-11-21 | 2023-11-21 |  | 2023-12-12 |  |  | 2024-01-09 | 2.3 | 260 | 394 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 2
43992 | KV-0-216-003-125-SD5 | 3 | true | CH06822004-BD-PI-0607 | 125 | 5K | Riser | C2 | T-051 | 2024-02-01 |  | 2023-10-27 | 2023-11-13 | 2023-11-20 | 2023-11-21 | 2023-11-21 |  | 2023-12-12 | 2023-12-18 |  | 2024-02-06 | 6.4 | 260 | 394 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
43993 | KV-0-216-003-125-SD5 | 3 | true | CH06822004-BD-PI-0607 | 125 | 5K | Riser | C2 | T-051 | 2024-02-01 |  | 2023-10-27 | 2023-11-13 | 2023-11-20 | 2023-11-21 | 2023-11-21 |  | 2024-02-26 |  |  | 2024-03-13 | 5.7 | 260 | 394 | Virgil Frinculescu |  |  |  | Latest rev. 3 is added to the w.map. |  | 0 | SEP | SEP
43994 | KV-0-216-003-125-SD5 | 3 | true | CH06822004-BD-PI-0607 | 125 | 5K | Riser | C2 | T-051 | 2024-02-01 |  | 2023-10-27 | 2023-11-13 | 2023-11-20 | 2023-11-21 | 2023-11-21 |  | 2024-02-26 |  |  | 2024-03-13 | 5.7 | 260 | 394 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
43995 | KV-0-216-003-125-SD5 | 3 | true | CH06822004-BD-PI-0607 | 125 | 5K | Riser | C2 | T-051 | 2024-02-01 |  | 2023-10-27 | 2023-11-13 | 2023-11-20 | 2023-11-21 | 2023-11-21 |  | 2023-12-12 |  | 2024-02-01 | 2024-02-02 | 1.3 | 260 | 394 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
43996 | KV-0-216-003-125-SD5 | 3 | true | CH06822004-BD-PI-0607 | 125 | 5K | Riser | C2 | T-051 | 2024-02-01 |  | 2023-10-27 | 2023-11-13 | 2023-11-20 | 2023-11-21 | 2023-11-21 |  | 2023-12-12 |  | 2024-02-01 | 2024-02-02 | 2.3 | 260 | 394 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
35810 | N2F-7-500-002-25-SP1 | 2 | true | CH06822004-BD-PI-0457 | 25 | 5K | Riser | N/A | T01583 | 2023-09-28 |  | 2023-10-27 | 2023-11-05 | 2023-11-15 | 2023-11-15 | 2023-12-05 |  | 2023-12-10 |  | 2024-01-04 | 2024-01-23 | 7.3 | 264 | 396 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 2
35811 | N2F-7-500-002-25-SP1 | 2 | true | CH06822004-BD-PI-0457 | 25 | 5K | Riser | N/A | T01583 | 2023-09-28 |  | 2023-10-27 | 2023-11-05 | 2023-11-14 | 2023-11-14 | 2023-12-05 |  | 2023-12-10 | 2023-12-18 | 2024-01-04 | 2024-01-26 | 6.3 | 264 | 396 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 2
35812 | O2F-7-400-002-25-SP1 | 2 | true | CH06822004-BD-PI-0465 | 25 | 5K | Riser | N/A | T01583 | 2023-09-28 |  | 2023-10-27 | 2023-11-09 | 2023-11-19 | 2023-12-04 | 2023-12-05 |  | 2023-12-10 |  | 2024-01-04 | 2024-01-23 | 6.1 | 264 | 458 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 2
35813 | O2F-7-400-002-25-SP1 | 2 | true | CH06822004-BD-PI-0465 | 25 | 5K | Riser | N/A | T01583 | 2023-09-28 |  | 2023-10-27 | 2023-11-09 | 2023-11-19 | 2023-12-04 | 2023-12-05 |  | 2023-12-10 | 2023-12-18 | 2024-01-04 | 2024-01-23 | 7.3 | 264 | 458 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 2
35814 | US4-0-244-001-50-SD6 | 2 | false | CH06822004-BD-PI-0586 | 50 | 5K | Riser | H5 | T01583 | 2023-09-29 |  | 2023-10-28 | 2023-11-08 | 2023-11-08 | 2023-11-13 | 2023-11-22 |  | 2023-12-14 |  | 2023-12-18 | 2024-01-12 | 7.1 | 261 | 410 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 2
35815 | US4-0-244-001-50-SD6 | 2 | false | CH06822004-BD-PI-0586 | 50 | 5K | Riser | H5 | T01583 | 2023-09-29 |  | 2023-10-28 | 2023-11-06 | 2023-11-20 | 2023-11-21 | 2023-11-22 |  | 2023-12-14 |  |  | 2024-01-12 | 0.7 | 261 | 410 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 2
35816 | US4-0-244-001-50-SD6 | 2 | false | CH06822004-BD-PI-0586 | 50 | 5K | Riser | H5 | T01583 | 2023-09-29 |  | 2023-10-28 | 2023-11-06 | 2023-11-20 | 2023-11-21 | 2023-11-22 |  | 2023-12-14 |  |  | 2024-01-12 | 6.9 | 261 | 410 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 2
35817 | US4-0-244-001-50-SD6 | 2 | false | CH06822004-BD-PI-0586 | 50 | 5K | Riser | H5 | T01583 | 2023-09-28 |  | 2023-10-27 | 2023-11-15 | 2023-12-10 | 2023-12-10 | 2023-12-15 |  | 2024-01-05 |  | 2024-01-26 |  | 7.8 | 261 | 410 | Jozef Kotul | [5 empty] | 0 | SEP | SEP |  | 2
35818 | US4-0-244-001-50-SD6 | 2 | false | CH06822004-BD-PI-0586 | 50 | 5K | Riser | H5 | T01583 | 2023-09-28 | [11 empty] | 4.3 | 261 | 410 |  |  |  |  | HOLD |  | 0 | SEP | SEP |  | 2
35819 | US4-0-244-001-50-SD6 | 2 | false | CH06822004-BD-PI-0586 | 50 | 5K | Riser | H5 | T01583 | 2023-09-28 |  | 2023-10-27 | 2023-11-15 | 2023-12-10 | 2023-12-10 | 2023-12-15 | [5 empty] | 0 | 261 | 410 | [6 empty] | 0 | SEP | SEP |  | 2
45146 | US4-0-244-001-50-SD6 | 3 | true | CH06822004-BD-PI-0586 | 50 | 5K | Riser | H5 | T-058 | 2024-02-28 |  | 2023-10-28 | 2023-11-08 | 2023-11-08 | 2023-11-13 | 2023-11-22 |  | 2023-12-14 |  | 2023-12-18 | 2024-03-05 | 7.1 | 261 | 410 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45147 | US4-0-244-001-50-SD6 | 3 | true | CH06822004-BD-PI-0586 | 50 | 5K | Riser | H5 | T-058 | 2024-02-28 |  | 2023-10-28 | 2023-11-06 | 2023-11-20 | 2023-11-21 | 2023-11-22 |  | 2024-03-05 |  | 2024-02-28 | 2024-03-11 | 1.1 | 261 | 410 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45148 | US4-0-244-001-50-SD6 | 3 | true | CH06822004-BD-PI-0586 | 50 | 5K | Riser | H5 | T-058 | 2024-02-28 |  | 2023-10-28 | 2023-11-06 | 2023-11-20 | 2023-11-21 | 2023-11-22 |  | 2023-12-14 |  | 2024-02-28 | 2024-03-05 | 6.6 | 261 | 410 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45149 | US4-0-244-001-50-SD6 | 3 | true | CH06822004-BD-PI-0586 | 50 | 5K | Riser | H5 | T-058 | 2024-02-28 |  | 2023-10-27 | 2023-11-15 | 2023-12-10 | 2023-12-10 | 2023-12-15 |  | 2024-03-05 |  | 2024-01-26 | 2024-03-13 | 7.8 | 261 | 410 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45150 | US4-0-244-001-50-SD6 | 3 | true | CH06822004-BD-PI-0586 | 50 | 5K | Riser | H5 | T-058 | 2024-02-28 | [7 empty] | 2024-03-05 |  |  | 2024-03-13 | 3.3 | 261 | 410 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45151 | US4-0-244-001-50-SD6 | 3 | true | CH06822004-BD-PI-0586 | 50 | 5K | Riser | H5 | T-058 | 2024-02-28 |  | 2023-10-27 | 2023-11-15 | 2023-12-10 | 2023-12-10 | 2023-12-15 |  | 2024-03-05 |  |  | 2024-03-13 | 0 | 261 | 410 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
35820 | US4-0-244-011-15-SD6 | 2 | false | CH06822004-BD-PI-0586 | 15 | 5K | Riser | H5 | T01583 | 2023-09-28 | [11 empty] | 1.1 | 261 | 410 |  |  |  |  | HOLD |  | 0 | SEP | SEP |  | 2
45156 | US4-0-244-011-15-SD6 | 3 | true | CH06822004-BD-PI-0586 | 15 | 5K | Riser | H5 | T-058 | 2024-02-28 | [7 empty] | 2024-03-13 |  |  | 2024-03-20 | 5.9 | 261 | 410 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45157 | US4-0-244-011-15-SD6 | 3 | true | CH06822004-BD-PI-0586 | 15 | 5K | Riser | H5 | T-058 | 2024-02-28 | [7 empty] | 2024-03-13 |  | 2024-03-23 | 2024-07-10 | 0.8 | 261 | 410 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45158 | US4-0-244-011-15-SD6 | 3 | true | CH06822004-BD-PI-0586 | 15 | 5K | Riser | H5 | T-058 | 2024-02-28 | [7 empty] | 2024-03-13 | 2024-03-23 |  | 2024-06-18 | 7.3 | 261 | 410 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45159 | US4-0-244-011-15-SD6 | 3 | true | CH06822004-BD-PI-0586 | 15 | 5K | Riser | H5 | T-058 | 2024-02-28 | [7 empty] | 2024-03-13 |  |  | 2024-07-10 | 2.7 | 261 | 410 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
35821 | WAA-7-931-002-150-SD | 2 | false | CH06822004-BD-PI-0635 | 150 | 5K | Riser | H3 | T01583 | 2023-09-28 | 2023-10-17 | 2023-10-17 | 2023-10-30 | 2023-10-30 | 2023-11-05 | 2023-11-07 |  | 2023-11-21 | 2023-12-18 | 2024-01-04 | 2024-01-26 | 12.8 | 271 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
35822 | WAA-7-931-002-150-SD | 2 | false | CH06822004-BD-PI-0635 | 150 | 5K | Riser | H3 | T01583 | 2023-09-28 | 2023-10-17 | 2023-10-17 | 2023-10-30 | 2023-10-31 | 2023-11-05 | 2023-11-07 |  | 2023-11-21 |  |  | 2024-01-26 | 0.4 | 271 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
35823 | WAA-7-931-002-150-SD | 2 | false | CH06822004-BD-PI-0635 | 150 | 5K | Riser | H3 | T01583 | 2023-09-28 | 2023-10-17 | 2023-10-17 | 2023-10-30 | 2023-10-31 | 2023-11-05 | 2023-11-07 |  | 2023-11-21 | 2023-12-18 | 2024-01-04 | 2024-01-26 | 6.2 | 271 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
43532 | WAA-7-931-002-150-SD | 3 | true | CH06822004-BD-PI-0635 | 150 | 5K | Riser | H3 | T-047 | 2024-01-25 | 2023-10-17 | 2023-10-17 | 2023-10-30 | 2023-10-30 | 2023-11-05 | 2023-11-07 |  | 2023-11-21 | 2023-12-18 | 2024-01-04 | 2024-01-29 | 12.8 | 271 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
43533 | WAA-7-931-002-150-SD | 3 | true | CH06822004-BD-PI-0635 | 150 | 5K | Riser | H3 | T-047 | 2024-01-25 | 2023-10-17 | 2023-10-17 | 2023-10-30 | 2023-10-31 | 2023-11-05 | 2023-11-07 |  | 2023-11-21 |  | 2024-03-23 | 2024-01-26 | 0.5 | 271 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
43534 | WAA-7-931-002-150-SD | 3 | true | CH06822004-BD-PI-0635 | 150 | 5K | Riser | H3 | T-047 | 2024-01-25 | 2023-10-17 | 2023-10-17 | 2023-10-30 | 2023-10-31 | 2023-11-05 | 2023-11-07 |  | 2024-01-31 | 2023-12-18 | 2024-01-04 | 2024-02-26 | 5.9 | 271 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
35824 | WAA-7-931-052-100-SD | 2 | false | CH06822004-BD-PI-0635 | 100 | 5K | Riser | H3 | T01583 | 2023-09-28 | 2023-10-17 | 2023-10-17 | 2023-10-29 | 2023-10-31 | 2023-11-05 | 2023-11-07 |  | 2023-11-21 | 2023-11-30 |  | 2023-12-05 | 18.3 | 271 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
35825 | WAA-7-931-052-100-SD | 2 | false | CH06822004-BD-PI-0635 | 100 | 5K | Riser | H3 | T01583 | 2023-09-28 | 2023-10-17 | 2023-10-17 | 2023-10-29 | 2023-10-30 | 2023-11-05 | 2023-11-07 |  | 2023-11-21 | 2023-11-30 | 2024-03-23 |  | 1.5 | 271 | 411 | Attila Henter | [5 empty] | 0 | SEP | SEP |  | 1
35826 | WAA-7-931-052-100-SD | 2 | false | CH06822004-BD-PI-0635 | 100 | 5K | Riser | H3 | T01583 | 2023-09-28 | 2023-10-17 | 2023-10-17 | 2023-10-29 | 2023-11-05 | 2023-11-05 | 2023-11-07 |  | 2023-11-21 |  |  | 2024-01-26 | 0.8 | 271 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
51889 | WAA-7-931-052-100-SD | 3 | true | CH06822004-BD-PI-0635 | 100 | 5K | Riser | H3 | T-083 | 2024-05-21 | 2023-10-17 | 2023-10-17 | 2023-10-29 | 2023-10-31 | 2023-11-05 | 2023-11-07 |  | 2023-11-21 | 2023-11-30 | 2024-05-21 | 2024-06-13 | 18.1 | 271 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
51890 | WAA-7-931-052-100-SD | 3 | true | CH06822004-BD-PI-0635 | 100 | 5K | Riser | H3 | T-083 | 2024-05-21 | 2023-10-17 | 2023-10-17 | 2023-10-29 | 2023-10-30 | 2023-11-05 | 2023-11-07 |  | 2023-11-21 | 2023-11-30 | 2024-03-23 | 2024-06-19 | 1.3 | 271 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
51891 | WAA-7-931-052-100-SD | 3 | true | CH06822004-BD-PI-0635 | 100 | 5K | Riser | H3 | T-083 | 2024-05-21 | 2023-10-17 | 2023-10-17 | 2023-10-29 | 2023-11-05 | 2023-11-05 | 2023-11-07 |  | 2023-11-21 |  | 2024-05-21 | 2024-06-27 | 0.4 | 271 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
35827 | WAA-7-931-053-15-SD | 2 | false | CH06822004-BD-PI-0635 | 15 | 5K | Riser | H3 | T01583 | 2023-09-28 | [11 empty] | 0.65 | 271 | 411 | [6 empty] | 0 | SEP | SEP |  | 2
42110 | WAA-7-931-053-15-SD | 3 | true | CH06822004-BD-PI-0635 | 15 | 5K | Riser | H3 | PEL-ZAU-T-038 | 2024-01-15 | 2024-01-25 | 2024-01-25 | 2024-01-31 |  | 2024-02-05 | 2024-02-16 |  | 2024-02-21 |  |  | 2024-03-22 | 0.6 | 271 | 411 | Virgil Frinculescu |  |  |  | Line released from HOLD for ZRO to prefab |  | 0 | SEP | SEP |  | 2
35828 | WAA-7-931-054-150-SD | 2 | false | CH06822004-BD-PI-0635 | 150 | 5K | Riser | H3 | T01583 | 2023-09-28 | [11 empty] | 1.3 | 271 | 411 | [6 empty] | 0 | SEP | SEP |  | 2
42111 | WAA-7-931-054-150-SD | 3 | true | CH06822004-BD-PI-0635 | 150 | 5K | Riser | H3 | PEL-ZAU-T-038 | 2024-01-15 | 2024-01-25 | 2024-01-25 | 2024-02-01 |  | 2024-02-05 | 2024-02-16 |  | 2024-02-21 |  |  | 2024-03-21 | 1.2 | 271 | 411 | Virgil Frinculescu |  |  |  | Line released from HOLD for ZRO to prefab |  | 0 | SEP | SEP |  | 2
35829 | WAA-7-931-055-15-SD | 2 | false | CH06822004-BD-PI-0635 | 15 | 5K | Riser | H3 | T01583 | 2023-09-28 | [11 empty] | 0.61 | 271 | 411 | [6 empty] | 0 | SEP | SEP |  | 2
42112 | WAA-7-931-055-15-SD | 3 | true | CH06822004-BD-PI-0635 | 15 | 5K | Riser | H3 | PEL-ZAU-T-038 | 2024-01-15 | 2024-01-25 | 2024-01-25 | 2024-01-31 |  | 2024-02-05 | 2024-02-16 |  | 2024-02-21 |  |  | 2024-03-21 | 0.7 | 271 | 411 | Virgil Frinculescu |  |  |  | Line released from HOLD for ZRO to prefab |  | 0 | SEP | SEP |  | 2
35830 | WAA-7-931-056-100-SD | 2 | false | CH06822004-BD-PI-0635 | 100 | 5K | Riser | H3 | T01583 | 2023-09-28 | [11 empty] | 1 | 271 | 411 | [6 empty] | 0 | SEP | SEP |  | 2
42113 | WAA-7-931-056-100-SD | 3 | true | CH06822004-BD-PI-0635 | 100 | 5K | Riser | H3 | PEL-ZAU-T-038 | 2024-01-15 | 2024-01-25 | 2024-01-25 | 2024-01-31 |  | 2024-02-05 | 2024-02-16 |  | 2024-02-21 |  |  | 2024-03-21 | 1.1 | 271 | 411 | Virgil Frinculescu |  |  |  | Line released from HOLD for ZRO to prefab |  | 0 | SEP | SEP |  | 2
35831 | WAA-7-931-057-100-SD | 2 | false | CH06822004-BD-PI-0635 | 100 | 5K | Riser | H3 | T01583 | 2023-09-28 | 2023-10-17 | 2023-10-17 | 2023-10-27 | 2023-12-04 | 2023-12-04 | 2023-12-05 | [5 empty] | 5.6 | 271 | 411 | [6 empty] | 0 | SEP | SEP |  | 1
47537 | WAA-7-931-057-100-SD | 3 | true | CH06822004-BD-PI-0635 | 100 | 5K | Riser | H3 | T-068 | 2024-04-03 | 2023-10-17 | 2023-10-17 | 2023-10-27 | 2023-12-04 | 2023-12-04 | 2023-12-05 |  | 2024-05-23 |  |  | 2024-06-18 | 5.6 | 271 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
35832 | WAA-7-931-058-150-SD | 2 | false | CH06822004-BD-PI-0635 | 150 | 5K | Riser | H3 | T01583 | 2023-09-28 | 2023-10-17 | 2023-10-17 | 2023-10-27 |  | 2023-12-13 | 2023-12-15 | [5 empty] | 5.6 | 271 | 411 | [6 empty] | 0 | SEP | SEP |  | 1
47538 | WAA-7-931-058-150-SD | 3 | true | CH06822004-BD-PI-0635 | 150 | 5K | Riser | H3 | T-068 | 2024-04-03 | 2023-10-17 | 2023-10-17 | 2023-10-27 |  | 2023-12-13 | 2023-12-15 |  | 2024-05-23 |  |  | 2024-06-18 | 5.6 | 271 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
35833 | WAI-7-201-001-150-SD | 2 | true | CH06822004-BD-PI-0642 | 150 | 5K | Riser | N/A | T01583 | 2023-09-28 |  | 2023-10-27 | 2023-11-02 | 2023-11-15 | 2023-11-16 | 2023-11-21 |  | 2023-12-10 |  | 2023-12-18 | 2024-02-28 | 6 | 271 | 413 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 2
35834 | WAI-7-201-001-150-SD | 2 | true | CH06822004-BD-PI-0642 | 150 | 5K | Riser | N/A | T01583 | 2023-09-28 |  | 2023-10-27 | 2023-11-01 | 2023-11-15 | 2023-11-16 | 2023-11-21 |  | 2023-12-10 | 2023-12-18 |  | 2024-02-28 | 13.9 | 271 | 413 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 2
35835 | WAI-7-201-003-150-SD | 2 | false | CH06822004-BD-PI-0642 | 150 | 5K | Riser | N/A | T01583 | 2023-09-28 | [11 empty] | 5.8 | 271 | 413 |  |  |  | New Name WAI-7-201-083-150-SD | New Name WAI-7-201-083-150-SD |  | 0 | SEP | SEP |  | 2
35836 | WAI-7-201-022-20-SD | 2 | false | CH06822004-BD-PI-0642 | 20 | 5K | Riser | N/A | T01583 | 2023-09-28 |  | 2023-10-27 | 2023-11-05 | 2023-11-19 | 2023-12-15 | 2023-12-15 |  | 2024-01-08 |  |  |  | 4.8 | 271 | 413 | Attila Henter | [5 empty] | 0 | SEP | SEP |  | 2
42043 | WAI-7-201-022-20-SD | 3 | true | CH06822004-BD-PI-0642 | 20 | 5K | Riser | N/A | PEL-ZAU-T-031 | 2024-01-12 |  | 2023-10-27 | 2023-11-05 | 2023-11-19 | 2023-12-15 | 2023-12-15 |  | 2024-01-29 |  |  | 2024-04-17 | 4.8 | 271 | 413 | Virgil Frinculescu |  |  |  | No change |  | 0 | SEP | SEP |  | 2
35837 | WAI-7-201-032-20-SD | 2 | true | CH06822004-BD-PI-0642 | 20 | 5K | Riser | N/A | T01583 | 2023-09-28 |  | 2023-10-27 | 2023-11-05 | 2023-11-19 | 2023-12-04 | 2023-12-05 |  | 2023-12-10 |  |  | 2024-01-09 | 3.3 | 271 | 413 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 2
35838 | WAI-7-201-033-25-SD | 2 | true | CH06822004-BD-PI-0642 | 25 | 5K | Riser | N/A | T01583 | 2023-09-28 |  | 2023-10-27 | 2023-11-06 | 2023-11-19 | 2023-12-04 | 2023-12-05 |  | 2023-12-10 |  |  | 2024-01-09 | 2.8 | 271 | 413 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 2
35839 | WAI-7-201-034-20-SD | 2 | true | CH06822004-BD-PI-0642 | 20 | 5K | Riser | N/A | T01583 | 2023-09-28 |  | 2023-10-27 | 2023-11-11 | 2023-11-19 | 2023-12-04 | 2023-12-05 |  | 2023-12-10 |  |  | 2024-01-12 | 1 | 271 | 413 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 2
35840 | WAI-7-201-035-20-SD | 2 | false | CH06822004-BD-PI-0642 | 20 | 5K | Riser | N/A | T01583 | 2023-09-28 |  | 2023-10-27 | 2023-11-05 | 2023-11-19 | 2023-12-04 | 2023-12-05 |  | 2023-12-10 |  |  | 2024-01-12 | 6.7 | 271 | 413 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 2
42053 | WAI-7-201-035-20-SD | 3 | true | CH06822004-BD-PI-0642 | 20 | 5K | Riser | N/A | PEL-ZAU-T-031 | 2024-01-12 |  | 2023-10-27 | 2023-11-05 | 2023-11-19 | 2023-12-04 | 2023-12-05 |  | 2023-12-10 |  | 2024-01-12 | 2024-03-05 | 6.7 | 271 | 413 | Virgil Frinculescu |  |  |  | Updated Pipe Lenghts DN20 |  | 0 | SEP | SEP |  | 2
35841 | WAI-7-201-036-20-SD | 2 | true | CH06822004-BD-PI-0642 | 20 | 5K | Riser | N/A | T01583 | 2023-09-28 |  | 2023-10-27 | 2023-11-11 | 2023-11-19 | 2023-12-04 | 2023-12-05 |  | 2023-12-10 |  |  | 2024-01-09 | 4.8 | 271 | 413 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 2
35842 | WFIA-7-105-013-32-SP1 | 2 | true | CH06822004-BD-PI-0473 | 32 | 5K | Riser | H3 | T01583 | 2023-09-28 |  | 2023-10-27 | 2023-11-05 | 2023-11-15 | 2023-11-15 | 2023-12-05 |  | 2024-01-08 |  |  | 2024-01-23 | 2.2 | 264 | 416 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 2
35843 | WFIA-7-105-015-40-SP1 | 2 | true | CH06822004-BD-PI-0473 | 40 | 5K | Riser | H3 | T01583 | 2023-09-28 |  | 2023-10-27 | 2023-11-09 | 2023-12-11 | 2023-12-11 | 2023-12-15 |  | 2024-01-08 |  |  | 2024-01-12 | 9.2 | 264 | 416 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 2
35844 | DKS-7-401-022-15-SD | 1 | true | CH06822004-BD-PI-1179 | 15 | 5K | OG1 | H3 | T02031 | 2023-09-29 |  | 2023-10-27 | 2023-11-06 | 2023-11-19 | 2023-12-04 | 2023-12-05 |  | 2024-01-08 |  |  | 2024-01-23 | 2.2 | 271 | 378 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 2
35845 | WAA-7-931-044-100-SD | 1 | true | CH06822004-BD-PI-0635 | 100 | 5K | OG1 | H3 | T02031 | 2023-09-29 |  | 2023-10-23 | 2023-10-29 | 2023-11-15 | 2023-11-16 | 2023-11-21 |  | 2023-11-30 | 2023-12-18 |  | 2024-01-09 | 9 | 271 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
35846 | WAA-7-931-045-65-SD | 1 | true | CH06822004-BD-PI-0635 | 65 | 5K | OG1 | H3 | T02031 | 2023-09-29 |  | 2023-10-23 | 2023-10-28 | 2023-10-29 | 2023-10-30 | 2023-11-05 |  | 2023-11-30 | 2023-12-18 |  | 2024-01-12 | 6.6 | 271 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
35847 | WAA-7-931-046-65-SD | 1 | false | CH06822004-BD-PI-0635 | 65 | 5K | OG1 | H3 | T02031 | 2023-09-29 |  | 2023-10-23 | 2023-10-28 | 2023-10-29 | 2023-10-29 | 2023-11-05 |  | 2023-11-30 |  |  | 2024-01-23 | 1.8 | 271 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
42109 | WAA-7-931-046-65-SD | 2 | true | CH06822004-BD-PI-0635 | 65 | 5K | OG1 | H3 | PEL-ZAU-T-038 | 2024-01-15 |  | 2023-10-23 | 2023-10-28 | 2023-10-29 | 2023-10-29 | 2023-11-05 |  | 2024-02-12 |  |  | 2024-02-13 | 1.8 | 271 | 411 | Virgil Frinculescu |  |  |  | Main DN65 Pipe to be modified (lengthend) |  | 0 | SEP | SEP
35848 | WAA-7-931-047-65-SD | 1 | true | CH06822004-BD-PI-0635 | 65 | 5K | OG1 | H3 | T02031 | 2023-09-29 |  | 2023-10-23 | 2023-10-28 | 2023-10-29 | 2023-10-30 | 2023-11-05 |  | 2023-11-30 | 2023-12-18 |  | 2024-01-12 | 8.8 | 271 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
35849 | WAA-7-931-048-65-SD | 1 | true | CH06822004-BD-PI-0635 | 65 | 5K | OG1 | H3 | T02031 | 2023-09-29 |  | 2023-10-23 | 2023-10-28 | 2023-10-29 | 2023-10-30 | 2023-11-05 |  | 2023-11-30 |  |  | 2024-01-09 | 0.8 | 271 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
35850 | WAA-7-931-049-65-SD | 1 | true | CH06822004-BD-PI-0635 | 65 | 5K | OG1 | H3 | T02031 | 2023-09-29 |  | 2023-10-23 | 2023-10-30 | 2023-10-29 | 2023-11-15 | 2023-11-21 |  | 2023-11-30 | 2023-12-18 |  | 2024-01-09 | 7.8 | 271 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
35851 | WAA-7-931-050-65-SD | 1 | true | CH06822004-BD-PI-0635 | 65 | 5K | OG1 | H3 | T02031 | 2023-09-29 |  | 2023-10-23 | 2023-11-02 | 2023-11-11 | 2023-11-14 | 2023-11-21 |  | 2023-11-30 |  |  | 2024-01-09 | 0.4 | 271 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
35852 | DKS-7-401-006-32-SD | 1 | false | CH06822004-BD-PI-0530 | 32 | 5K | OG2 | H3 | T02032 | 2023-09-29 |  | 2023-10-22 | 2023-10-29 | 2023-10-29 | 2023-10-30 | 2023-11-21 |  | 2024-01-03 |  |  | 2024-02-06 | 8.7 | 271 | 378 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
35853 | DKS-7-401-006-32-SD | 1 | false | CH06822004-BD-PI-0530 | 32 | 5K | OG2 | H3 | T02032 | 2023-09-29 |  | 2023-10-22 | 2023-11-11 | 2023-11-19 | 2023-12-04 | 2023-12-05 |  | 2024-01-03 |  |  | 2024-02-08 | 9.9 | 271 | 378 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
42412 | DKS-7-401-006-32-SD | 2 | true | CH06822004-BD-PI-0530 | 32 | 5K | OG2 | H3 | PEL-ZAU-T-040 | 2024-01-17 |  | 2023-10-22 | 2023-10-29 | 2023-10-29 | 2023-10-30 | 2023-11-21 |  | 2024-01-24 |  |  | 2024-03-05 | 8.7 | 271 | 378 | Virgil Frinculescu |  |  |  | Latest Revision added to the folder "00_All Isometrics" |  | 0 | SEP | SEP
42413 | DKS-7-401-006-32-SD | 2 | true | CH06822004-BD-PI-0530 | 32 | 5K | OG2 | H3 | PEL-ZAU-T-040 | 2024-01-17 |  | 2023-10-22 | 2023-11-11 | 2023-11-19 | 2023-12-04 | 2023-12-05 |  | 2024-01-24 |  |  | 2024-02-08 | 9.9 | 271 | 378 | Virgil Frinculescu |  |  |  | Latest Revision added to the folder "00_All Isometrics" |  | 0 | SEP | SEP
35854 | DKS-7-401-021-15-SD | 1 | true | CH06822004-BD-PI-0530 | 15 | 5K | OG2 | H3 | T02032 | 2023-09-29 |  | 2023-10-22 | 2023-11-05 | 2023-11-13 | 2023-11-15 | 2023-11-21 |  | 2024-01-03 |  |  | 2024-01-23 | 5.6 | 271 | 378 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
35855 | DKS-7-401-029-32-SD | 1 | true | CH06822004-BD-PI-0530 | 32 | 5K | OG2 | H3 | T02032 | 2023-09-29 | 2023-10-16 | 2023-10-22 | 2023-11-11 | 2023-11-19 | 2023-12-04 | 2023-12-05 |  | 2024-01-03 |  |  | 2024-02-06 | 4.2 | 271 | 378 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
35856 | DKA-7-400-006-40-SD | 1 | true | CH06822004-BD-PI-1201 | 40 | 5K | EG | H3 | T02030 | 2023-09-28 |  | 2023-10-22 | 2023-11-03 | 2023-11-04 | 2023-11-08 | 2023-11-21 |  | 2023-12-03 |  |  | 2024-01-09 | 7.1 | 271 | 376 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
35857 | DKA-7-400-008-40-SD | 1 | true | CH06822004-BD-PI-1201 | 40 | 5K | EG | H3 | T02030 | 2023-09-28 |  | 2023-10-22 | 2023-10-31 | 2023-11-19 | 2023-11-21 | 2023-11-21 |  | 2023-12-03 |  |  | 2024-01-23 | 5.1 | 271 | 376 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
35858 | DKA-7-400-015-32-SD | 1 | true | CH06822004-BD-PI-1201 | 32 | 5K | EG | H3 | T02030 | 2023-09-28 |  | 2023-10-22 | 2023-11-11 | 2023-11-17 | 2023-11-19 | 2023-11-21 |  | 2023-12-03 |  |  | 2023-12-11 | 4.6 | 271 | 376 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
35859 | DKA-7-400-016-25-SD | 1 | true | CH06822004-BD-PI-1201 | 25 | 5K | EG | H3 | T02030 | 2023-09-28 |  | 2023-10-22 | 2023-11-21 | 2023-12-04 | 2023-12-04 | 2023-12-05 |  | 2023-12-10 |  | 2024-01-05 | 2024-01-23 | 1 | 271 | 376 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
35860 | DKA-7-400-017-25-SD | 1 | true | CH06822004-BD-PI-1201 | 25 | 5K | EG | H3 | T02030 | 2023-09-28 |  | 2023-10-22 | 2023-11-03 | 2023-11-07 | 2023-11-08 | 2023-11-21 |  | 2023-12-03 |  | 2023-12-18 | 2024-01-23 | 1 | 271 | 376 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
35861 | DKA-7-400-018-25-SD | 1 | true | CH06822004-BD-PI-1201 | 25 | 5K | EG | H3 | T02030 | 2023-09-28 |  | 2023-10-22 | 2023-11-03 | 2023-11-05 | 2023-11-06 | 2023-11-21 |  | 2023-12-03 |  | 2023-12-18 | 2024-07-05 | 1.9 | 271 | 376 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
35862 | DKA-7-400-019-25-SD | 1 | true | CH06822004-BD-PI-1201 | 25 | 5K | EG | H3 | T02030 | 2023-09-28 |  | 2023-10-22 | 2023-11-03 | 2023-11-05 | 2023-11-06 | 2023-11-21 |  | 2023-12-03 |  |  | 2024-07-05 | 1 | 271 | 376 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
35863 | DKA-7-400-020-25-SD | 1 | true | CH06822004-BD-PI-1201 | 25 | 5K | EG | H3 | T02030 | 2023-09-28 |  | 2023-10-22 | 2023-11-03 | 2023-11-05 | 2023-11-06 | 2023-11-21 |  | 2023-12-03 |  |  | 2024-01-25 | 2.5 | 271 | 376 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
35864 | DKA-7-400-021-25-SD | 1 | true | CH06822004-BD-PI-1201 | 25 | 5K | EG | H3 | T02030 | 2023-09-28 |  | 2023-10-22 | 2023-11-03 | 2023-11-05 | 2023-11-06 | 2023-11-21 |  | 2023-12-03 |  |  | 2024-01-09 | 1.7 | 271 | 376 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
35865 | DKA-7-400-022-25-SD | 1 | true | CH06822004-BD-PI-1201 | 25 | 5K | EG | H3 | T02030 | 2023-09-28 |  | 2023-10-22 | 2023-11-21 | 2023-12-04 | 2023-12-04 | 2023-12-05 |  | 2023-12-10 |  |  | 2024-07-05 | 2.5 | 271 | 376 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
35866 | DKA-7-400-022-25-SD | 1 | true | CH06822004-BD-PI-1201 | 25 | 5K | EG | H3 | T02030 | 2023-09-28 |  | 2023-10-22 | 2023-11-01 | 2023-12-04 | 2023-12-04 | 2023-12-05 |  | 2023-12-10 |  |  | 2024-01-09 | 4 | 271 | 376 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
35867 | DKA-7-400-051-25-SD | 1 | true | CH06822004-BD-PI-1201 | 25 | 5K | EG | H3 | T02030 | 2023-09-28 |  | 2023-10-22 | 2023-11-05 | 2023-11-08 | 2023-11-12 | 2023-11-21 |  | 2023-12-03 |  |  | 2023-12-10 | 5 | 271 | 376 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
35868 | DKS-7-401-036-15-SD | 1 | true | CH06822004-BD-PI-0530 | 15 | 5K | EG | H3 | T02030 | 2023-09-28 |  | 2023-10-27 | 2023-11-06 | 2023-11-19 | 2023-12-04 | 2023-12-05 |  | 2024-01-08 |  |  | 2024-01-23 | 2 | 271 | 378 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 2
35869 | DKS-7-401-044-25-SD | 1 | true | CH06822004-BD-PI-0530 | 25 | 5K | EG | H3 | T02030 | 2023-09-28 |  | 2023-10-22 | 2023-11-03 | 2023-11-05 | 2023-11-06 | 2023-11-21 |  | 2023-11-27 |  |  | 2023-12-10 | 2.1 | 271 | 378 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
35870 | DKS-7-401-055-25-SD | 1 | true | CH06822004-BD-PI-0530 | 25 | 5K | EG | H3 | T02030 | 2023-09-28 |  | 2023-10-22 | 2023-11-08 | 2023-11-17 | 2023-11-15 | 2023-11-21 |  | 2023-11-27 | 2023-11-30 | 2024-01-05 | 2024-01-29 | 3.9 | 271 | 378 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
35871 | DKS-7-401-057-25-SD | 1 | true | CH06822004-BD-PI-0530 | 25 | 5K | EG | H3 | T02030 | 2023-09-28 |  | 2023-10-22 | 2023-11-08 | 2023-11-06 | 2023-11-15 | 2023-11-21 |  | 2023-11-27 |  | 2023-12-18 | 2024-01-26 | 3.2 | 271 | 378 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
35872 | DKS-7-401-059-25-SD | 1 | true | CH06822004-BD-PI-0530 | 25 | 5K | EG | H3 | T02030 | 2023-09-28 |  | 2023-10-22 | 2023-11-03 | 2023-11-06 | 2023-11-08 | 2023-11-21 |  | 2023-11-27 |  | 2023-11-30 | 2024-01-26 | 7.3 | 271 | 378 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
35873 | WAA-7-931-006-40-SD | 1 | false | CH06822004-BD-PI-0635 | 40 | 5K | EG | H3 | T02030 | 2023-09-28 |  | 2023-10-22 | 2023-10-31 | 2023-11-06 | 2023-11-06 | 2023-11-21 |  | 2023-11-26 |  |  | 2024-01-09 | 5.5 | 271 | 411 | Virgil Frinculescu |  |  | New ISO WAA-7-931-006-65-SD | New ISO WAA-7-931-006-65-SD |  | 0 | SEP | SEP |  | 1
35874 | WAA-7-931-007-100-SD | 1 | false | CH06822004-BD-PI-0635 | 100 | 5K | EG | H3 | T02030 | 2023-09-28 |  | 2023-10-22 | 2023-11-19 | 2023-11-19 | 2023-11-20 | 2023-11-21 |  | 2023-11-26 |  |  | 2023-12-05 | 8.4 | 271 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
35875 | WAA-7-931-007-100-SD | 1 | false | CH06822004-BD-PI-0635 | 100 | 5K | EG | H3 | T02030 | 2023-09-28 |  | 2023-10-22 | 2023-11-03 | 2023-11-19 | 2023-11-20 | 2023-11-21 |  | 2023-11-26 | 2023-11-30 |  | 2024-01-09 | 6.2 | 271 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
42097 | WAA-7-931-007-100-SD | 2 | true | CH06822004-BD-PI-0635 | 100 | 5K | EG | H3 | PEL-ZAU-T-038 | 2024-01-15 |  | 2023-10-22 | 2023-11-19 | 2023-11-19 | 2023-11-20 | 2023-11-21 |  | 2023-11-26 |  | 2023-12-04 | 2024-02-14 | 8.4 | 271 | 411 | Virgil Frinculescu |  |  |  | No Change |  | 0 | SEP | SEP |  | 1
42098 | WAA-7-931-007-100-SD | 2 | true | CH06822004-BD-PI-0635 | 100 | 5K | EG | H3 | PEL-ZAU-T-038 | 2024-01-15 |  | 2023-10-22 | 2023-11-03 | 2023-11-19 | 2023-11-20 | 2023-11-21 |  | 2023-11-26 | 2023-11-30 |  | 2024-02-14 | 6.2 | 271 | 411 | Virgil Frinculescu |  |  |  | Change already performed after RFI answer |  | 0 | SEP | SEP
35876 | WAA-7-931-009-80-SD | 1 | true | CH06822004-BD-PI-0635 | 80 | 5K | EG | H3 | T02030 | 2023-09-28 |  | 2023-10-22 | 2023-11-11 | 2023-11-19 | 2023-12-04 | 2023-12-05 |  | 2023-12-10 |  | 2023-12-18 | 2024-01-09 | 8.2 | 271 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
35877 | WAA-7-931-010-100-SD | 1 | true | CH06822004-BD-PI-0635 | 100 | 5K | EG | H3 | T02030 | 2023-09-28 |  | 2023-10-22 | 2023-11-03 | 2023-11-15 | 2023-11-16 | 2023-11-21 |  | 2023-11-26 |  | 2023-11-30 | 2023-12-05 | 7.8 | 271 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
35878 | WAA-7-931-011-100-SD | 1 | true | CH06822004-BD-PI-0635 | 100 | 5K | EG | H3 | T02030 | 2023-09-28 |  | 2023-10-22 | 2023-10-31 | 2023-11-15 | 2023-11-16 | 2023-11-21 |  | 2023-11-26 |  | 2023-11-30 | 2023-12-05 | 8.6 | 271 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
35879 | WAA-7-931-012-80-SD | 1 | true | CH06822004-BD-PI-0635 | 80 | 5K | EG | H3 | T02030 | 2023-09-28 |  | 2023-10-22 | 2023-11-12 | 2023-11-15 | 2023-11-16 | 2023-11-21 |  | 2023-11-26 | 2023-11-30 |  | 2023-12-05 | 6.2 | 271 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
35880 | WAA-7-931-013-100-SD | 1 | true | CH06822004-BD-PI-0635 | 100 | 5K | EG | H3 | T02030 | 2023-09-28 |  | 2023-10-22 | 2023-10-31 | 2023-11-15 | 2023-11-16 | 2023-11-21 |  | 2023-11-26 | 2023-11-30 |  | 2023-12-05 | 6.8 | 271 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
35881 | WAA-7-931-014-40-SD | 1 | true | CH06822004-BD-PI-0635 | 40 | 5K | EG | H3 | T02030 | 2023-09-28 |  | 2023-10-22 | 2023-11-05 | 2023-11-11 | 2023-11-14 | 2023-11-21 |  | 2023-11-27 |  |  | 2023-12-10 | 4.7 | 271 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
35882 | WAA-7-931-015-65-SD | 1 | true | CH06822004-BD-PI-0635 | 65 | 5K | EG | H3 | T02030 | 2023-09-28 |  | 2023-10-22 | 2023-11-01 | 2023-11-10 | 2023-11-14 | 2023-11-21 |  | 2023-11-27 |  |  | 2023-12-11 | 1.6 | 271 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
35883 | WAA-7-931-016-65-SD | 1 | true | CH06822004-BD-PI-0635 | 65 | 5K | EG | H3 | T02030 | 2023-09-28 |  | 2023-10-22 | 2023-10-31 | 2023-11-19 | 2023-11-16 | 2023-11-21 |  | 2023-11-27 |  |  | 2023-12-10 | 4 | 271 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
35884 | WAA-7-931-017-65-SD | 1 | false | CH06822004-BD-PI-0635 | 65 | 5K | EG | H3 | T02030 | 2023-09-28 |  | 2023-10-22 | 2023-10-27 | 2023-10-28 | 2023-10-28 | 2023-11-05 |  | 2023-11-12 |  |  | 2023-12-11 | 4.6 | 271 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
42099 | WAA-7-931-017-65-SD | 2 | true | CH06822004-BD-PI-0635 | 65 | 5K | EG | H3 | PEL-ZAU-T-038 | 2024-01-15 |  | 2023-10-22 | 2023-10-27 | 2023-10-28 | 2023-10-28 | 2023-11-05 |  | 2023-11-12 |  | 2023-12-10 | 2024-02-08 | 4.7 | 271 | 411 | Virgil Frinculescu |  |  |  | Main DN65 Pipe to be modified |  | 0 | SEP | SEP |  | 1
35885 | WAA-7-931-018-65-SD | 1 | true | CH06822004-BD-PI-0635 | 65 | 5K | EG | H3 | T02030 | 2023-09-28 |  | 2023-10-22 | 2023-10-29 | 2023-10-29 | 2023-10-29 | 2023-11-05 |  | 2023-11-12 |  |  | 2023-12-11 | 1.6 | 271 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
35886 | WAA-7-931-019-40-SD | 1 | false | CH06822004-BD-PI-0635 | 40 | 5K | EG | H3 | T02030 | 2023-09-28 |  | 2023-10-22 | 2023-11-02 | 2023-11-07 | 2023-11-12 | 2023-11-21 |  | 2023-11-27 |  | 2023-12-18 |  | 0.5 | 271 | 411 | Attila Henter | [5 empty] | 0 | SEP | SEP |  | 1
42100 | WAA-7-931-019-40-SD | 2 | true | CH06822004-BD-PI-0635 | 40 | 5K | EG | H3 | PEL-ZAU-T-038 | 2024-01-15 |  | 2023-10-22 | 2023-11-02 | 2023-11-07 | 2023-11-12 | 2023-11-21 |  | 2023-11-27 |  | 2023-12-18 | 2024-02-22 | 0.5 | 271 | 411 | Virgil Frinculescu |  |  |  | Main DN40 Pipe to be modified (shortend) |  | 0 | SEP | SEP
35887 | WAA-7-931-020-25-SD | 1 | false | CH06822004-BD-PI-0635 | 25 | 5K | EG | H3 | T02030 | 2023-09-28 |  | 2023-10-22 | 2023-11-01 | 2023-11-05 | 2023-11-06 | 2023-11-21 |  | 2023-11-27 |  | 2023-12-18 |  | 1.3 | 271 | 411 | Attila Henter | [5 empty] | 0 | SEP | SEP |  | 1
42101 | WAA-7-931-020-25-SD | 2 | true | CH06822004-BD-PI-0635 | 25 | 5K | EG | H3 | PEL-ZAU-T-038 | 2024-01-15 |  | 2023-10-22 | 2023-11-01 | 2023-11-05 | 2023-11-06 | 2023-11-21 |  | 2023-11-27 |  | 2023-12-18 | 2024-02-20 | 1.4 | 271 | 411 | Virgil Frinculescu |  |  |  | Main DN25 Pipe to be modified (shortend) |  | 0 | SEP | SEP
35888 | WAA-7-931-021-65-SD | 1 | true | CH06822004-BD-PI-0635 | 65 | 5K | EG | H3 | T02030 | 2023-09-28 |  | 2023-10-22 | 2023-10-29 | 2023-10-30 | 2023-10-30 | 2023-11-05 |  | 2023-11-12 |  | 2023-12-18 | 2024-01-09 | 2.8 | 271 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
35889 | WAA-7-931-022-40-SD | 1 | true | CH06822004-BD-PI-0635 | 40 | 5K | EG | H3 | T02030 | 2023-09-28 |  | 2023-10-22 | 2023-10-27 | 2023-10-28 | 2023-10-28 | 2023-11-05 |  | 2023-11-12 | 2023-12-18 |  | 2024-01-09 | 8.7 | 271 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
35890 | WAA-7-931-023-40-SD | 1 | false | CH06822004-BD-PI-0635 | 40 | 5K | EG | H3 | T02030 | 2023-09-28 |  | 2023-10-22 | 2023-10-29 | 2023-10-31 | 2023-11-08 | 2023-11-21 |  | 2023-11-27 | 2023-11-30 |  | 2024-01-09 | 0.7 | 271 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
42102 | WAA-7-931-023-40-SD | 2 | true | CH06822004-BD-PI-0635 | 40 | 5K | EG | H3 | PEL-ZAU-T-038 | 2024-01-15 |  | 2023-10-22 | 2023-10-29 | 2023-10-31 | 2023-11-08 | 2023-11-21 |  | 2023-11-27 | 2023-11-30 |  | 2024-01-09 | 0.6 | 271 | 411 | Virgil Frinculescu |  |  |  | Connection on Drain changed |  | 0 | SEP | SEP |  | 1
35891 | WAA-7-931-024-50-SD | 1 | true | CH06822004-BD-PI-0635 | 50 | 5K | EG | H3 | T02030 | 2023-09-28 |  | 2023-10-22 | 2023-10-28 | 2023-10-29 | 2023-10-29 | 2023-12-05 |  | 2023-12-10 | 2023-12-18 |  | 2024-01-30 | 4.3 | 271 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
35892 | WAA-7-931-025-25-SD | 1 | true | CH06822004-BD-PI-0635 | 25 | 5K | EG | H3 | T02030 | 2023-09-28 |  | 2023-10-22 | 2023-11-01 | 2023-11-07 | 2023-11-08 | 2023-11-21 |  | 2023-11-27 |  | 2024-01-05 | 2024-01-26 | 0.6 | 271 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
35893 | WAA-7-931-026-65-SD | 1 | true | CH06822004-BD-PI-0635 | 65 | 5K | EG | H3 | T02030 | 2023-09-28 |  | 2023-10-22 | 2023-11-12 | 2023-11-19 | 2023-12-15 | 2023-12-15 |  | 2024-01-08 |  |  | 2024-01-23 | 0.5 | 271 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
35894 | WAA-7-931-027-40-SD | 1 | false | CH06822004-BD-PI-0635 | 40 | 5K | EG | H3 | T02030 | 2023-09-28 |  | 2023-10-22 | 2023-10-27 | 2023-10-28 | 2023-10-28 | 2023-11-05 |  | 2023-11-12 | 2023-12-18 |  | 2024-01-09 | 8.4 | 271 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
42103 | WAA-7-931-027-40-SD | 2 | true | CH06822004-BD-PI-0635 | 40 | 5K | EG | H3 | PEL-ZAU-T-038 | 2024-01-15 |  | 2023-10-22 | 2023-10-27 | 2023-10-28 | 2023-10-28 | 2023-11-05 |  | 2023-11-12 | 2023-12-18 |  | 2024-01-09 | 8.3 | 271 | 411 | Virgil Frinculescu |  |  |  | Connection on Drain changed |  | 0 | SEP | SEP |  | 1
35895 | WAA-7-931-028-40-SD | 1 | false | CH06822004-BD-PI-0635 | 40 | 5K | EG | H3 | T02030 | 2023-09-28 |  | 2023-10-22 | 2023-10-29 | 2023-10-30 | 2023-10-31 | 2023-11-05 |  | 2023-11-12 | 2023-11-30 |  | 2024-01-09 | 3.3 | 271 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
42104 | WAA-7-931-028-40-SD | 2 | true | CH06822004-BD-PI-0635 | 40 | 5K | EG | H3 | PEL-ZAU-T-038 | 2024-01-15 |  | 2023-10-22 | 2023-10-29 | 2023-10-30 | 2023-10-31 | 2023-11-05 |  | 2023-11-12 | 2023-11-30 |  | 2024-01-09 | 3.3 | 271 | 411 | Virgil Frinculescu |  |  |  | Connection on Drain changed |  | 0 | SEP | SEP |  | 1
35896 | WAA-7-931-029-65-SD | 1 | true | CH06822004-BD-PI-0635 | 65 | 5K | EG | H3 | T02030 | 2023-09-28 |  | 2023-10-22 | 2023-10-29 | 2023-10-28 | 2023-11-19 | 2023-11-21 |  | 2023-11-27 |  |  | 2023-12-10 | 7.5 | 271 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
35897 | WAA-7-931-030-40-SD | 1 | false | CH06822004-BD-PI-0635 | 40 | 5K | EG | H3 | T02030 | 2023-09-28 |  | 2023-10-22 | 2023-10-31 | 2023-11-19 | 2023-12-04 | 2023-12-05 |  | 2023-12-10 |  |  | 2023-12-21 | 4.5 | 271 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
42105 | WAA-7-931-030-40-SD | 2 | true | CH06822004-BD-PI-0635 | 40 | 5K | EG | H3 | PEL-ZAU-T-038 | 2024-01-15 |  | 2023-10-22 | 2023-10-31 | 2023-11-19 | 2023-12-04 | 2023-12-05 |  | 2023-12-10 |  |  | 2023-12-21 | 4.4 | 271 | 411 | Virgil Frinculescu |  |  |  | Connection on Drain changed |  | 0 | SEP | SEP |  | 1
35898 | WAA-7-931-031-65-SD | 1 | true | CH06822004-BD-PI-0635 | 65 | 5K | EG | H3 | T02030 | 2023-09-28 |  | 2023-10-22 | 2023-10-30 | 2023-11-19 | 2023-12-14 | 2023-12-15 |  |  |  |  | 2023-12-21 | 0.6 | 271 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
35899 | WAA-7-931-032-65-SD | 1 | true | CH06822004-BD-PI-0635 | 65 | 5K | EG | H3 | T02030 | 2023-09-28 |  | 2023-10-22 | 2023-10-28 | 2023-10-30 | 2023-10-30 | 2023-11-21 |  | 2023-11-27 | 2023-12-18 |  | 2024-01-05 | 5.5 | 271 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
35900 | WAA-7-931-033-40-SD | 1 | false | CH06822004-BD-PI-0635 | 40 | 5K | EG | H3 | T02030 | 2023-09-28 |  |  | 2023-10-31 | 2023-11-08 | 2023-11-09 | 2023-11-21 |  | 2023-11-27 | 2023-11-30 | 2023-12-18 | 2024-01-09 | 0.7 | 271 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
42106 | WAA-7-931-033-40-SD | 2 | true | CH06822004-BD-PI-0635 | 40 | 5K | EG | H3 | PEL-ZAU-T-038 | 2024-01-15 |  |  | 2023-10-31 | 2023-11-08 | 2023-11-09 | 2023-11-21 |  | 2023-11-27 | 2023-11-30 | 2023-12-18 | 2024-01-09 | 0.6 | 271 | 411 | Virgil Frinculescu |  |  |  | Connection on Drain changed |  | 0 | SEP | SEP |  | 1
35901 | WAA-7-931-034-40-SD | 1 | false | CH06822004-BD-PI-0635 | 40 | 5K | EG | H3 | T02030 | 2023-09-28 |  |  | 2023-10-27 | 2023-10-28 | 2023-10-28 | 2023-11-05 |  | 2023-11-12 |  |  | 2024-01-09 | 4.6 | 271 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
42107 | WAA-7-931-034-40-SD | 2 | true | CH06822004-BD-PI-0635 | 40 | 5K | EG | H3 | PEL-ZAU-T-038 | 2024-01-15 |  |  | 2023-10-27 | 2023-10-28 | 2023-10-28 | 2023-11-05 |  | 2023-11-12 |  |  | 2024-01-09 | 4.6 | 271 | 411 | Virgil Frinculescu |  |  |  | Connection on Drain changed |  | 0 | SEP | SEP |  | 1
35902 | WAA-7-931-035-40-SD | 1 | false | CH06822004-BD-PI-0635 | 40 | 5K | EG | H3 | T02030 | 2023-09-28 |  |  | 2023-10-31 | 2023-11-19 | 2023-11-21 | 2023-11-21 |  | 2023-11-27 |  | 2023-11-30 | 2024-01-09 | 3.7 | 271 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
42108 | WAA-7-931-035-40-SD | 2 | true | CH06822004-BD-PI-0635 | 40 | 5K | EG | H3 | PEL-ZAU-T-038 | 2024-01-15 |  |  | 2023-10-31 | 2023-11-19 | 2023-11-21 | 2023-11-21 |  | 2023-11-27 |  | 2023-11-30 | 2024-01-09 | 3.6 | 271 | 411 | Virgil Frinculescu |  |  |  | Connection on Drain changed |  | 0 | SEP | SEP |  | 1
35903 | WAA-7-931-036-65-SD | 1 | true | CH06822004-BD-PI-0635 | 65 | 5K | EG | H3 | T02030 | 2023-09-28 |  |  | 2023-10-31 | 2023-11-20 | 2023-11-21 | 2023-11-21 |  | 2023-11-27 |  |  | 2023-12-05 | 1.1 | 271 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
35904 | WAA-7-931-037-65-SD | 1 | true | CH06822004-BD-PI-0635 | 65 | 5K | EG | H3 | T02030 | 2023-09-28 |  |  | 2023-10-31 | 2023-11-19 | 2023-12-11 | 2023-12-15 |  | 2024-01-03 |  |  | 2024-01-09 | 0.9 | 271 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
35905 | WAA-7-931-038-65-SD | 1 | true | CH06822004-BD-PI-0635 | 65 | 5K | EG | H3 | T02030 | 2023-09-28 |  |  | 2023-11-05 | 2023-11-19 | 2023-12-14 | 2023-12-15 |  | 2024-01-03 |  |  | 2024-01-09 | 7.9 | 271 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
35906 | WAA-7-931-040-50-SD | 1 | true | CH06822004-BD-PI-0635 | 50 | 5K | EG | H3 | T02030 | 2023-09-28 |  | 2023-10-22 | 2023-10-31 | 2023-12-04 | 2023-12-04 | 2023-12-05 |  | 2023-12-10 |  |  | 2023-12-18 | 8.7 | 271 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
35907 | WAA-7-931-040-50-SD | 1 | true | CH06822004-BD-PI-0635 | 50 | 5K | EG | H3 | T02030 | 2023-09-28 |  | 2023-10-22 | 2023-10-28 | 2023-10-29 | 2023-10-30 | 2023-12-05 |  | 2023-12-10 |  |  | 2023-12-18 | 3.1 | 271 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
35908 | WAA-7-931-041-32-SD | 1 | false | CH06822004-BD-PI-0635 | 32 | 5K | EG | H3 | T02030 | 2023-09-28 |  | 2023-10-22 | 2023-11-11 | 2023-11-19 | 2023-11-21 | 2023-11-21 |  | 2023-11-27 |  |  |  | 6.7 | 271 | 411 | Attila Henter | [5 empty] | 0 | SEP | SEP |  | 1
44597 | WAA-7-931-041-32-SD | 2 | true | CH06822004-BD-PI-0635 | 32 | 5K | EG | H3 | T-058 | 2024-01-17 |  | 2023-10-22 | 2023-11-11 | 2023-11-19 | 2023-11-21 | 2023-11-21 |  | 2023-11-27 |  |  | 2024-03-05 | 6.7 | 271 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
35909 | WAA-7-931-042-32-SD | 1 | true | CH06822004-BD-PI-0635 | 32 | 5K | EG | H3 | T02030 | 2023-09-28 |  | 2023-10-22 | 2023-10-29 | 2023-10-30 | 2023-10-31 | 2023-11-21 |  | 2023-11-27 |  |  | 2024-03-05 | 1.1 | 271 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
35910 | WAA-7-931-057-40-SD | 1 | true | CH06822004-BD-PI-0635 | 40 | 5K | EG | H3 | T02030 | 2023-09-28 |  | 2023-10-22 | 2023-10-29 | 2023-10-30 | 2023-10-30 | 2023-11-05 |  | 2023-11-12 |  |  | 2023-12-11 | 2.2 | 271 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
35911 | WAA-7-931-058-25-SD | 1 | true | CH06822004-BD-PI-0635 | 25 | 5K | EG | H3 | T02030 | 2023-09-28 |  | 2023-10-22 | 2023-10-29 | 2023-10-30 | 2023-10-30 | 2023-11-05 |  | 2023-11-12 | 2023-12-18 |  | 2024-01-09 | 2.4 | 271 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
35912 | WAI-7-201-026-25-SD | 1 | false | CH06822004-BD-PI-0642 | 25 | 5K | EG | H3 | T02030 | 2023-09-28 |  | 2023-10-23 | 2023-11-03 | 2023-11-07 | 2023-11-12 | 2023-11-21 |  | 2023-12-05 |  | 2023-12-18 | 2024-01-29 | 5.5 | 271 | 413 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
35913 | WAI-7-201-026-25-SD | 1 | false | CH06822004-BD-PI-0642 | 25 | 5K | EG | H3 | T02030 | 2023-09-28 |  | 2023-10-23 | 2023-11-03 | 2023-11-15 | 2023-11-15 | 2023-11-21 |  | 2023-12-05 |  |  | 2023-12-11 | 11.1 | 271 | 413 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
42046 | WAI-7-201-026-25-SD | 2 | true | CH06822004-BD-PI-0642 | 25 | 5K | EG | H3 | PEL-ZAU-T-031 | 2024-01-12 |  | 2023-10-23 | 2023-11-03 | 2023-11-07 | 2023-11-12 | 2023-11-21 |  | 2023-12-05 |  | 2023-12-18 | 2024-01-29 | 5.5 | 271 | 413 | Virgil Frinculescu |  |  |  | No change |  | 0 | SEP | SEP |  | 1
42047 | WAI-7-201-026-25-SD | 2 | true | CH06822004-BD-PI-0642 | 25 | 5K | EG | H3 | PEL-ZAU-T-031 | 2024-01-12 |  | 2023-10-23 | 2023-11-03 | 2023-11-15 | 2023-11-15 | 2023-11-21 |  | 2023-12-05 |  | 2023-12-10 | 2024-03-05 | 10.9 | 271 | 413 | Virgil Frinculescu |  |  |  | no major change |  | 0 | SEP | SEP |  | 1
35914 | WAI-7-201-028-32-SD | 1 | false | CH06822004-BD-PI-0642 | 32 | 5K | EG | H3 | T02030 | 2023-09-28 |  | 2023-10-23 | 2023-11-11 | 2023-11-19 | 2023-12-04 | 2023-12-05 |  | 2023-12-10 |  | 2023-12-18 |  | 7.6 | 271 | 413 | Attila Henter | [5 empty] | 0 | SEP | SEP |  | 1
35915 | WAI-7-201-028-32-SD | 1 | false | CH06822004-BD-PI-0642 | 32 | 5K | EG | H3 | T02030 | 2023-09-28 |  | 2023-10-23 | 2023-11-12 | 2023-11-19 | 2023-12-04 | 2023-12-05 |  | 2023-12-10 |  | 2023-12-18 |  | 7.8 | 271 | 413 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
42048 | WAI-7-201-028-32-SD | 2 | false | CH06822004-BD-PI-0642 | 32 | 5K | EG | H3 | PEL-ZAU-T-031 | 2024-01-12 |  | 2023-10-23 | 2023-11-11 | 2023-11-19 | 2023-12-04 | 2023-12-05 |  | 2023-12-10 |  | 2023-12-18 |  | 7.6 | 271 | 413 |  |  |  |  | No change |  | 0 | SEP | SEP |  | 1
42049 | WAI-7-201-028-32-SD | 2 | false | CH06822004-BD-PI-0642 | 32 | 5K | EG | H3 | PEL-ZAU-T-031 | 2024-01-12 |  | 2023-10-23 | 2023-11-12 | 2023-11-19 | 2023-12-04 | 2023-12-05 |  | 2023-12-10 |  | 2023-12-18 |  | 7.7 | 271 | 413 |  |  |  |  | no major change |  | 0 | SEP | SEP |  | 1
44928 | WAI-7-201-028-32-SD | 3 | true | CH06822004-BD-PI-0642 | 32 | 5K | EG | H3 | T-057 | 2024-02-22 | [7 empty] | 2024-02-27 |  |  | 2024-03-05 | 7.6 | 271 | 413 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
44929 | WAI-7-201-028-32-SD | 3 | true | CH06822004-BD-PI-0642 | 32 | 5K | EG | H3 | T-057 | 2024-02-22 | [7 empty] | 2024-02-27 |  |  | 2024-03-05 | 7.6 | 271 | 413 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
35916 | WAI-7-201-030-25-SD | 1 | false | CH06822004-BD-PI-0642 | 25 | 5K | EG | H3 | T02030 | 2023-09-28 |  | 2023-10-23 | 2023-11-01 | 2023-11-07 | 2023-11-08 | 2023-11-21 |  | 2023-12-05 |  |  | 2023-12-18 | 7.2 | 271 | 413 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
35917 | WAI-7-201-030-25-SD | 1 | false | CH06822004-BD-PI-0642 | 25 | 5K | EG | H3 | T02030 | 2023-09-28 |  | 2023-10-23 | 2023-11-01 | 2023-11-07 | 2023-11-08 | 2023-11-21 |  | 2023-12-05 |  |  | 2023-12-18 | 5.1 | 271 | 413 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
42051 | WAI-7-201-030-25-SD | 2 | true | CH06822004-BD-PI-0642 | 25 | 5K | EG | H3 | PEL-ZAU-T-031 | 2024-01-12 |  | 2023-10-23 | 2023-11-01 | 2023-11-07 | 2023-11-08 | 2023-11-21 |  | 2023-12-05 |  | 2023-12-18 | 2024-03-05 | 7.2 | 271 | 413 | Virgil Frinculescu |  |  |  | No change |  | 0 | SEP | SEP |  | 1
42052 | WAI-7-201-030-25-SD | 2 | true | CH06822004-BD-PI-0642 | 25 | 5K | EG | H3 | PEL-ZAU-T-031 | 2024-01-12 |  | 2023-10-23 | 2023-11-01 | 2023-11-07 | 2023-11-08 | 2023-11-21 |  | 2023-12-05 |  | 2023-12-18 | 2024-03-05 | 4.9 | 271 | 413 | Virgil Frinculescu |  |  |  | Updated Pipe Lenghts DN25 |  | 0 | SEP | SEP |  | 1
35927 | HR-NT-0-212-004-40-CA | 1 | false | CH06822004-BD-PI-0579 | 40 | 5K | OG2 | H3 | T01579 | 2023-09-30 |  | 2023-11-06 | 2023-12-07 | 2023-12-13 | 2023-12-13 | 2023-12-15 |  | 2024-01-10 |  |  | 2024-02-22 | 22.7 | 249 | 389 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 3
35928 | HR-NT-0-212-004-40-CA | 1 | false | CH06822004-BD-PI-0579 | 40 | 5K | OG2 | H3 | T01579 | 2023-09-30 |  | 2023-11-06 | 2023-12-07 | 2023-12-15 | 2023-12-15 | 2023-12-15 |  | 2024-01-10 |  |  |  | 1.3 | 249 | 389 | Attila Henter |  |  |  | New ISO issued just for information, FIX point changed (14.02.2024) |  | 0 | SEP | SEP |  | 3
48464 | HR-NT-0-212-004-40-CA | 3 | true | CH06822004-BD-PI-0579 | 40 | 5K | OG2 | H3 | T-073 | 2024-04-11 | [9 empty] | 2024-04-12 | 2024-04-24 | 22.7 | 249 | 389 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48465 | HR-NT-0-212-004-40-CA | 3 | true | CH06822004-BD-PI-0579 | 40 | 5K | OG2 | H3 | T-073 | 2024-04-11 | [10 empty] | 2024-04-24 | 1.3 | 249 | 389 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
35929 | HV-NT-0-212-005-40-CA | 1 | false | CH06822004-BD-PI-0579 | 40 | 5K | OG2 | H3 | T01579 | 2023-09-30 |  | 2023-11-06 | 2023-12-07 | 2023-12-13 | 2023-12-13 | 2023-12-15 |  | 2024-01-10 |  |  | 2024-07-08 | 2.1 | 249 | 390 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 3
35930 | HV-NT-0-212-005-40-CA | 1 | false | CH06822004-BD-PI-0579 | 40 | 5K | OG2 | H3 | T01579 | 2023-09-30 |  | 2023-11-06 | 2023-12-07 | 2023-12-13 | 2023-12-13 | 2023-12-15 |  | 2024-01-10 |  |  | 2024-02-22 | 24.3 | 249 | 390 | Virgil Frinculescu |  |  |  | New ISO issued just for information, FIX point changed (14.02.2024) |  | 0 | SEP | SEP |  | 3
48466 | HV-NT-0-212-005-40-CA | 2 | true | CH06822004-BD-PI-0579 | 40 | 5K | OG2 | H3 | T-073 | 2024-04-11 | [10 empty] | 2024-07-08 | 1.9 | 249 | 390 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48467 | HV-NT-0-212-005-40-CA | 2 | true | CH06822004-BD-PI-0579 | 40 | 5K | OG2 | H3 | T-073 | 2024-04-11 | [10 empty] | 2024-07-08 | 0.7 | 249 | 390 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48468 | HV-NT-0-212-005-40-CA | 2 | true | CH06822004-BD-PI-0579 | 40 | 5K | OG2 | H3 | T-073 | 2024-04-11 | [10 empty] | 2024-04-24 | 23.9 | 249 | 390 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
35931 | KR-0-216-004-65-SD5 | 1 | false | CH06822004-BD-PI-0607 | 65 | 5K | OG2 | C2 | T01579 | 2023-09-30 |  | 2023-11-06 | 2023-11-11 | 2023-11-15 | 2023-11-16 | 2023-11-21 |  | 2024-01-05 |  |  |  | 23.3 | 260 | 393 | Jozef Kotul |  |  |  | The new revision was released on 1.2.2023. Diameter changed |  | 0 | SEP | SEP |  | 3
35932 | KR-0-216-004-65-SD5 | 1 | false | CH06822004-BD-PI-0607 | 65 | 5K | OG2 | C2 | T01579 | 2023-09-30 |  | 2023-11-06 | 2023-11-11 | 2023-11-15 | 2023-11-16 | 2023-11-21 |  | 2024-01-05 |  |  |  | 1.2 | 260 | 393 | Jozef Kotul |  |  |  | The new revision was released on 1.2.2023. Diameter changed |  | 0 | SEP | SEP |  | 3
35933 | KR-0-216-035-20-SD5 | 1 | true | CH06822004-BD-PI-0607 | 20 | 5K | OG2 | C2 | T01579 | 2023-09-30 |  | 2023-11-06 | 2023-11-15 | 2023-11-19 | 2023-12-04 | 2023-12-05 |  | 2024-01-05 |  |  | 2024-03-25 | 0.4 | 260 | 393 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 3
35934 | KV-0-216-005-65-SD5 | 1 | false | CH06822004-BD-PI-0607 | 65 | 5K | OG2 | C2 | T01579 | 2023-09-30 |  | 2023-11-06 | 2023-11-11 | 2023-11-15 | 2023-11-19 | 2023-11-21 |  | 2024-01-05 |  |  |  | 1.5 | 260 | 394 | Jozef Kotul |  |  |  | The new revision was released on 1.2.2023. Diameter changed |  | 0 | SEP | SEP |  | 3
35935 | KV-0-216-005-65-SD5 | 1 | false | CH06822004-BD-PI-0607 | 65 | 5K | OG2 | C2 | T01579 | 2023-09-30 |  | 2023-11-06 | 2023-11-11 | 2023-11-16 | 2023-11-17 | 2023-11-21 |  | 2024-01-05 |  |  |  | 23.3 | 260 | 394 | Jozef Kotul |  |  |  | The new revision was released on 1.2.2023. Diameter changed |  | 0 | SEP | SEP |  | 3
35936 | KV-0-216-040-20-SD5 | 1 | true | CH06822004-BD-PI-0607 | 20 | 5K | OG2 | C2 | T01579 | 2023-09-30 |  | 2023-11-06 | 2023-11-15 | 2023-11-15 | 2023-11-19 | 2023-11-21 |  | 2024-01-05 |  |  | 2024-03-22 | 0.9 | 260 | 394 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 3
35937 | DKS-7-401-005-32-SD | 2 | true | CH06822004-BD-PI-0530 | 32 | 5K | OG2 | H3 | T01579 | 2023-09-30 |  | 2023-10-22 | 2023-10-29 | 2023-10-30 | 2023-10-31 | 2023-11-21 |  | 2023-12-03 |  | 2023-12-18 | 2024-01-12 | 18.7 | 271 | 378 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
35938 | DK4-0-600-002-25-SD6 | 1 | true | CH06822004-BD-PI-0558 | 25 | 5K | EG | H6 | T01577 | 2023-10-13 |  | 2023-10-22 | 2023-10-30 | 2023-11-04 | 2023-11-08 | 2023-11-21 |  | 2024-01-10 |  |  | 2024-01-23 | 12.2 | 261 | 375 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
35939 | DK4-0-600-002-25-SD6 | 1 | true | CH06822004-BD-PI-0558 | 25 | 5K | EG | H6 | T01577 | 2023-10-13 |  | 2023-10-22 | 2023-10-30 | 2023-11-19 | 2023-12-11 | 2023-12-15 |  | 2024-01-10 |  |  | 2024-01-23 | 5 | 261 | 375 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
35940 | DKA-7-400-050-25-SD | 1 | true | CH06822004-BD-PI-1201 | 25 | 5K | EG | H3 | T01577 | 2023-10-13 |  | 2023-10-22 | 2023-10-31 | 2023-11-08 | 2023-11-12 | 2023-11-21 |  | 2023-12-04 |  | 2023-12-18 | 2024-01-25 | 11.1 | 271 | 376 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
35942 | DKS-7-401-008-32-SD | 1 | true | CH06822004-BD-PI-0530 | 32 | 5K | EG | H3 | T01577 | 2023-10-14 |  | 2023-10-22 | 2023-10-29 | 2023-10-30 | 2023-10-30 | 2023-11-21 |  | 2023-12-05 |  | 2023-12-18 | 2024-01-23 | 5.1 | 271 | 378 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
35943 | DLF-7-831-003-25-SP1 | 1 | false | CH06822004-BD-PI-0537 | 25 | 5K | EG | N/A | T01577 | 2023-10-14 |  | 2023-11-06 | 2023-11-17 | 2023-11-19 | 2023-11-19 | 2023-12-15 |  | 2024-01-17 |  |  | 2024-01-26 | 10.8 | 264 | 380 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 3
35944 | DLF-7-831-003-25-SP1 | 1 | false | CH06822004-BD-PI-0537 | 25 | 5K | EG | N/A | T01577 | 2023-10-14 |  | 2023-11-06 | 2023-11-17 | 2023-11-19 | 2023-11-19 | 2023-12-15 |  | 2024-01-17 |  |  | 2024-01-26 | 3.1 | 264 | 380 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 3
45590 | DLF-7-831-003-25-SP1 | 2 | true | CH06822004-BD-PI-0537 | 25 | 5K | EG | N/A | T-061 | 2024-03-07 |  | 2023-11-06 | 2023-11-17 | 2023-11-19 | 2023-11-19 | 2023-12-15 |  | 2024-01-17 |  | 2024-03-08 | 2024-03-12 | 10.8 | 264 | 380 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45591 | DLF-7-831-003-25-SP1 | 2 | true | CH06822004-BD-PI-0537 | 25 | 5K | EG | N/A | T-061 | 2024-03-07 |  | 2023-11-06 | 2023-11-17 | 2023-11-19 | 2023-11-19 | 2023-12-15 |  | 2024-03-19 |  | 2024-03-08 | 2024-03-22 | 3 | 264 | 380 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
35945 | DLF-7-831-004-25-SP1 | 1 | false | CH06822004-BD-PI-0537 | 25 | 5K | EG | N/A | T01577 | 2023-10-14 |  | 2023-11-06 | 2023-11-17 | 2023-11-19 | 2023-11-19 | 2023-12-15 |  | 2024-01-17 |  |  | 2024-01-26 | 15.1 | 264 | 380 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 3
35946 | DLF-7-831-004-25-SP1 | 1 | false | CH06822004-BD-PI-0537 | 25 | 5K | EG | N/A | T01577 | 2023-10-14 |  | 2023-11-06 | 2023-11-13 | 2023-11-19 | 2023-12-07 | 2023-12-15 |  | 2024-01-17 |  |  | 2024-01-26 | 3.3 | 264 | 380 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 3
45592 | DLF-7-831-004-25-SP1 | 2 | true | CH06822004-BD-PI-0537 | 25 | 5K | EG | N/A | T-061 | 2024-03-07 |  | 2023-11-06 | 2023-11-17 | 2023-11-19 | 2023-11-19 | 2023-12-15 |  | 2024-03-19 |  | 2024-03-08 | 2024-03-22 | 11.6 | 264 | 380 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45593 | DLF-7-831-004-25-SP1 | 2 | true | CH06822004-BD-PI-0537 | 25 | 5K | EG | N/A | T-061 | 2024-03-07 |  | 2023-11-06 | 2023-11-13 | 2023-11-19 | 2023-12-07 | 2023-12-15 |  | 2024-01-17 |  | 2024-03-08 | 2024-03-12 | 6.7 | 264 | 380 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
35947 | KR-0-216-002-40-SD5 | 1 | false | CH06822004-BD-PI-0607 | 40 | 5K | EG | C2 | T01577 | 2023-10-14 |  | 2023-11-06 | 2023-11-12 | 2023-12-04 | 2023-12-04 | 2023-12-05 |  | 2024-01-11 |  |  |  | 2.3 | 260 | 393 | Jozef Kotul | [5 empty] | 0 | SEP | SEP |  | 3
42093 | KR-0-216-002-40-SD5 | 2 | true | CH06822004-BD-PI-0607 | 40 | 5K | EG | C2 | PEL-ZAU-T-039 | 2024-01-16 |  | 2023-11-06 | 2023-11-12 | 2023-12-04 | 2023-12-04 | 2023-12-05 |  | 2024-01-11 |  | 2024-02-07 | 2024-02-15 | 2.4 | 260 | 393 | Virgil Frinculescu |  |  |  | Updated Positions of Thermowells etc. |  | 0 | SEP | SEP |  | 3
35948 | KR-0-216-033-20-SD5 | 1 | true | CH06822004-BD-PI-0607 | 20 | 5K | EG | C2 | T01577 | 2023-10-14 |  | 2023-11-06 | 2023-11-12 | 2023-11-19 | 2023-12-07 | 2023-12-15 |  | 2024-01-11 |  |  | 2024-01-26 | 0.2 | 260 | 393 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 3
35949 | KV-0-216-032-40-SD5 | 1 | false | CH06822004-BD-PI-0607 | 40 | 5K | EG | C2 | T01577 | 2023-10-14 |  | 2023-11-06 | 2023-11-12 | 2023-11-22 | 2023-12-07 | 2023-12-15 |  | 2024-01-24 |  |  | 2024-01-26 | 2.6 | 260 | 394 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 3
42094 | KV-0-216-032-40-SD5 | 2 | true | CH06822004-BD-PI-0607 | 40 | 5K | EG | C2 | PEL-ZAU-T-039 | 2024-01-16 |  | 2023-11-06 | 2023-11-12 | 2023-11-22 | 2023-12-07 | 2023-12-15 |  | 2024-01-24 |  |  | 2024-01-26 | 2.7 | 260 | 394 | Virgil Frinculescu |  |  |  | Updated Positions of Thermowells etc. |  | 0 | SEP | SEP |  | 3
35950 | KV-0-216-034-20-SD5 | 1 | true | CH06822004-BD-PI-0607 | 20 | 5K | EG | C2 | T01577 | 2023-10-14 |  | 2023-11-06 | 2023-11-12 | 2023-11-19 | 2023-12-07 | 2023-12-15 |  | 2024-01-24 |  |  | 2024-01-26 | 0.2 | 260 | 394 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 3
35951 | NaOHP-6-601-001-25-SP | 1 | true | CH06822004-BD-PI-0614 | 25 | 5K | EG | N/A | T01577 | 2023-10-14 |  | 2023-11-06 | 2023-11-16 | 2023-11-19 | 2023-12-15 | 2023-12-15 |  | 2024-01-17 |  |  | 2024-01-26 | 8.7 | 262 | 398 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 3
35952 | NaOHP-6-601-013-25-SP | 1 | true | CH06822004-BD-PI-0614 | 25 | 5K | EG | N/A | T01577 | 2023-10-14 |  | 2023-11-06 | 2023-11-17 | 2023-11-19 | 2024-01-09 | 2024-01-12 |  | 2024-01-17 |  | 2024-02-07 | 2024-06-25 | 6.1 | 262 | 398 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 3
35953 | NaOHP-6-601-013-25-SP | 1 | true | CH06822004-BD-PI-0614 | 25 | 5K | EG | N/A | T01577 | 2023-10-14 |  | 2023-11-06 | 2023-11-17 |  | 2024-01-09 | 2024-01-12 |  | 2024-01-17 |  | 2024-02-07 | 2024-06-19 | 19.8 | 262 | 398 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 3
35954 | WAA-7-931-005-150-SD | 1 | false | CH06822004-BD-PI-0635 | 150 | 5K | EG | H3 | T01577 | 2023-10-14 | 2023-10-17 | 2023-10-17 | 2023-10-31 | 2023-10-30 | 2023-11-05 | 2023-11-07 |  | 2023-11-12 | 2023-11-30 |  | 2023-12-21 | 3.2 | 271 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
35955 | WAA-7-931-005-150-SD | 1 | false | CH06822004-BD-PI-0635 | 150 | 5K | EG | H3 | T01577 | 2023-10-14 | 2023-10-17 | 2023-10-17 | 2023-10-31 | 2023-10-30 | 2023-11-05 | 2023-11-07 |  | 2023-11-12 |  | 2023-12-18 | 2024-01-26 | 11.7 | 271 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
35956 | WAA-7-931-005-150-SD | 1 | false | CH06822004-BD-PI-0635 | 150 | 5K | EG | H3 | T01577 | 2023-10-14 | 2023-10-17 | 2023-10-17 | 2023-10-31 | 2023-10-30 | 2023-11-05 | 2023-11-07 |  | 2023-11-12 | 2023-11-30 |  | 2024-01-23 | 2 | 271 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
43311 | WAA-7-931-005-150-SD | 3 | true | CH06822004-BD-PI-0635 | 150 | 5K | EG | H3 | T-067 | 2024-03-27 | [9 empty] | 2024-02-21 | 2024-02-29 | 3.1 | 271 | 411 | Virgil Frinculescu |  |  |  | Revision not via IDF but Redlined |  | 0 | SEP | SEP
43312 | WAA-7-931-005-150-SD | 3 | true | CH06822004-BD-PI-0635 | 150 | 5K | EG | H3 | T-067 | 2024-03-27 | [7 empty] | 2024-01-29 |  |  | 2024-02-20 | 11.3 | 271 | 411 | Virgil Frinculescu |  |  |  | Revision not via IDF but Redlined |  | 0 | SEP | SEP
43313 | WAA-7-931-005-150-SD | 3 | true | CH06822004-BD-PI-0635 | 150 | 5K | EG | H3 | T-067 | 2024-03-27 | [7 empty] | 2024-01-29 |  |  | 2024-02-20 | 2 | 271 | 411 | Virgil Frinculescu |  |  |  | Revision not via IDF but Redlined |  | 0 | SEP | SEP
35957 | WAA-7-931-008-150-SD | 1 | false | CH06822004-BD-PI-0635 | 150 | 5K | EG | H3 | T01577 | 2023-10-14 | 2023-10-17 | 2023-10-17 | 2023-10-31 | 2023-10-30 | 2023-11-05 | 2023-11-07 |  | 2023-11-12 |  |  | 2023-12-05 | 1.7 | 271 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
35958 | WAA-7-931-008-150-SD | 1 | false | CH06822004-BD-PI-0635 | 150 | 5K | EG | H3 | T01577 | 2023-10-14 | 2023-10-17 | 2023-10-17 | 2023-10-31 | 2023-10-30 | 2023-11-05 | 2023-11-07 |  | 2023-11-12 | 2023-11-30 |  |  | 15.3 | 271 | 411 | Jozef Kotul |  |  |  | Revision not via IDF but Redlined |  | 0 | SEP | SEP |  | 1
35959 | WAA-7-931-008-150-SD | 1 | false | CH06822004-BD-PI-0635 | 150 | 5K | EG | H3 | T01577 | 2023-10-14 | 2023-10-17 | 2023-10-17 | 2023-10-31 | 2023-10-30 | 2023-11-05 | 2023-11-07 |  | 2023-11-12 |  | 2023-11-30 | 2024-01-09 | 2.4 | 271 | 411 | Virgil Frinculescu |  |  |  | Revision not via IDF but Redlined |  | 0 | SEP | SEP |  | 1
35960 | WAA-7-931-008-150-SD | 1 | false | CH06822004-BD-PI-0635 | 150 | 5K | EG | H3 | T01577 | 2023-10-14 | 2023-10-17 | 2023-10-17 | 2023-10-31 | 2023-10-30 | 2023-11-05 | 2023-11-07 |  | 2023-11-12 |  | 2023-11-30 | 2023-12-21 | 3.9 | 271 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
35961 | WAA-7-931-008-150-SD | 1 | false | CH06822004-BD-PI-0635 | 150 | 5K | EG | H3 | T01577 | 2023-10-14 | 2023-10-17 | 2023-10-17 | 2023-10-31 | 2023-10-30 | 2023-11-05 | 2023-11-07 |  | 2023-11-12 |  | 2023-11-30 | 2024-01-09 | 3.9 | 271 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
35962 | WAA-7-931-008-150-SD | 1 | false | CH06822004-BD-PI-0635 | 150 | 5K | EG | H3 | T01577 | 2023-10-14 | 2023-10-17 | 2023-10-17 | 2023-10-31 | 2023-10-30 | 2023-11-05 | 2023-11-07 |  | 2023-11-12 |  | 2023-11-30 | 2023-12-10 | 9 | 271 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
35963 | WAA-7-931-008-150-SD | 1 | false | CH06822004-BD-PI-0635 | 150 | 5K | EG | H3 | T01577 | 2023-10-14 | 2023-10-17 | 2023-10-17 | 2023-10-29 | 2023-10-30 | 2023-10-31 | 2023-11-05 |  | 2023-11-12 | 2023-11-30 |  | 2023-12-21 | 6.6 | 271 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
43025 | WAA-7-931-008-150-SD | 3 | true | CH06822004-BD-PI-0635 | 150 | 5K | EG | H3 | T-067 | 2024-03-27 | [9 empty] | 2023-11-30 | 2024-03-05 | 3.9 | 271 | 411 | Virgil Frinculescu |  |  |  | Revision not via IDF but Redlined |  | 0 | SEP | SEP
43298 | WAA-7-931-008-150-SD | 3 | true | CH06822004-BD-PI-0635 | 150 | 5K | EG | H3 | T-067 | 2024-03-27 | [9 empty] | 2023-11-30 | 2024-03-05 | 4 | 271 | 411 | Virgil Frinculescu |  |  |  | Revision not via IDF but Redlined |  | 0 | SEP | SEP
43299 | WAA-7-931-008-150-SD | 3 | true | CH06822004-BD-PI-0635 | 150 | 5K | EG | H3 | T-067 | 2024-03-27 | [9 empty] | 2023-11-30 | 2024-03-05 | 8.9 | 271 | 411 | Virgil Frinculescu |  |  |  | Revision not via IDF but Redlined |  | 0 | SEP | SEP
43300 | WAA-7-931-008-150-SD | 3 | true | CH06822004-BD-PI-0635 | 150 | 5K | EG | H3 | T-067 | 2024-03-27 | [9 empty] | 2023-12-15 | 2024-03-05 | 6.6 | 271 | 411 | Virgil Frinculescu |  |  |  | Revision not via IDF but Redlined |  | 0 | SEP | SEP
43314 | WAA-7-931-008-150-SD | 3 | true | CH06822004-BD-PI-0635 | 150 | 5K | EG | H3 | T-067 | 2024-03-27 | [10 empty] | 2024-02-12 | 1.7 | 271 | 411 | Virgil Frinculescu |  |  |  | Revision not via IDF but Redlined |  | 0 | SEP | SEP
43315 | WAA-7-931-008-150-SD | 3 | true | CH06822004-BD-PI-0635 | 150 | 5K | EG | H3 | T-067 | 2024-03-27 | [8 empty] | 2023-11-30 |  | 2024-03-05 | 2.4 | 271 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
43316 | WAA-7-931-008-150-SD | 3 | true | CH06822004-BD-PI-0635 | 150 | 5K | EG | H3 | T-067 | 2024-03-27 | [9 empty] | 2024-02-07 | 2024-02-12 | 2.4 | 271 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
35964 | WAA-7-931-039-50-SD | 1 | true | CH06822004-BD-PI-0635 | 50 | 5K | EG | H3 | T01577 | 2023-10-14 | 2023-10-17 | 2023-10-17 | 2023-10-29 | 2023-10-29 | 2023-10-29 | 2023-11-05 |  | 2023-11-12 | 2023-11-30 |  | 2024-01-09 | 19.4 | 271 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
35965 | WFIA-7-105-012-32-SP1 | 1 | true | CH06822004-BD-PI-0473 | 32 | 5K | EG | H3 | T01577 | 2023-10-14 |  | 2023-11-06 | 2023-11-22 |  | 2023-12-20 | 2024-01-12 |  | 2024-01-17 |  |  | 2024-01-23 | 16.7 | 264 | 416 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 3
35966 | CS-7-201-002-40-SP1 | 2 | false | CH06822004-BD-PI-1179 | 40 | 5K | EG | H2 | T01577 | 2023-10-14 |  | 2023-11-06 | 2023-12-15 |  | 2024-01-09 |  |  | 2024-01-17 |  |  |  | 0.9 | 264 | 371 | Jozef Kotul | [5 empty] | 0 | SEP | SEP |  | 3
43472 | CS-7-201-002-40-SP1 | 3 | true | CH06822004-BD-PI-1179 | 40 | 5K | EG | H2 | T-047 | 2024-01-25 |  | 2023-11-06 | 2023-12-15 |  | 2024-01-09 |  |  | 2024-01-17 |  |  | 2024-07-10 | 6 | 264 | 371 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
35967 | CSL-7-201-003-40-SP1 | 2 | false | CH06822004-BD-PI-1179 | 40 | 5K | EG | H2 | T01577 | 2023-10-14 |  | 2023-11-06 | 2023-12-13 |  | 2023-12-20 | 2024-01-12 |  | 2024-01-17 |  |  |  | 3.5 | 264 | 373 | Jozef Kotul | [5 empty] | 0 | SEP | SEP |  | 3
35968 | CSL-7-201-003-40-SP1 | 2 | false | CH06822004-BD-PI-1179 | 40 | 5K | EG | H2 | T01577 | 2023-10-14 |  | 2023-11-06 | 2023-12-13 |  | 2023-12-20 | 2024-01-12 |  | 2024-01-17 |  | 2024-02-07 |  | 8 | 264 | 373 | Jozef Kotul | [5 empty] | 0 | SEP | SEP |  | 3
35969 | CSL-7-201-003-40-SP1 | 2 | false | CH06822004-BD-PI-1179 | 40 | 5K | EG | H2 | T01577 | 2023-10-14 |  | 2023-11-06 | 2023-12-12 | 2023-12-14 | 2023-12-15 | 2023-12-15 |  | 2024-01-17 |  |  | 2024-02-07 | 2 | 264 | 373 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 3
35970 | CSL-7-201-003-40-SP1 | 2 | false | CH06822004-BD-PI-1179 | 40 | 5K | EG | H2 | T01577 | 2023-10-14 |  | 2023-11-06 | 2023-12-12 | 2023-12-14 | 2023-12-14 | 2023-12-15 |  | 2024-01-17 |  | 2024-01-26 |  | 2.7 | 264 | 373 | Jozef Kotul | [5 empty] | 0 | SEP | SEP |  | 3
43480 | CSL-7-201-003-40-SP1 | 3 | true | CH06822004-BD-PI-1179 | 40 | 5K | EG | H2 | T-047 | 2024-01-25 |  | 2023-11-06 | 2023-12-13 |  | 2023-12-20 | 2024-01-12 |  | 2024-01-30 | 2024-02-07 |  | 2024-07-11 | 1.7 | 264 | 373 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
43481 | CSL-7-201-003-40-SP1 | 3 | true | CH06822004-BD-PI-1179 | 40 | 5K | EG | H2 | T-047 | 2024-01-25 |  | 2023-11-06 | 2023-12-13 |  | 2023-12-20 | 2024-01-12 |  | 2024-01-30 |  | 2024-02-07 | 2024-04-18 | 5.9 | 264 | 373 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
43482 | CSL-7-201-003-40-SP1 | 3 | true | CH06822004-BD-PI-1179 | 40 | 5K | EG | H2 | T-047 | 2024-01-25 |  | 2023-11-06 | 2023-12-12 | 2023-12-14 | 2023-12-15 | 2023-12-15 |  | 2024-01-30 |  |  | 2024-02-07 | 2.8 | 264 | 373 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
43483 | CSL-7-201-003-40-SP1 | 3 | true | CH06822004-BD-PI-1179 | 40 | 5K | EG | H2 | T-047 | 2024-01-25 |  | 2023-11-06 | 2023-12-12 | 2023-12-14 | 2023-12-14 | 2023-12-15 |  | 2024-01-30 |  | 2024-02-07 | 2024-04-15 | 6.1 | 264 | 373 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
35971 | CSL-7-201-004-40-SP1 | 2 | true | CH06822004-BD-PI-1179 | 40 | 5K | EG | H2 | T01577 | 2023-10-14 |  | 2023-11-06 | 2023-12-13 |  | 2023-12-20 | 2024-01-12 |  | 2024-01-17 |  |  | 2024-01-26 | 9.2 | 264 | 373 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 3
35972 | CSL-7-201-004-40-SP1 | 2 | true | CH06822004-BD-PI-1179 | 40 | 5K | EG | H2 | T01577 | 2023-10-14 |  | 2023-11-06 | 2023-12-12 | 2023-12-14 | 2023-12-14 | 2023-12-15 |  | 2024-01-17 |  |  | 2024-01-26 | 2.5 | 264 | 373 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 3
35973 | CSL-7-201-004-40-SP1 | 2 | true | CH06822004-BD-PI-1179 | 40 | 5K | EG | H2 | T01577 | 2023-10-14 |  | 2023-11-06 | 2023-12-13 |  | 2023-12-20 | 2024-01-12 |  | 2024-01-17 |  | 2024-02-07 | 2024-04-10 | 8.3 | 264 | 373 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 3
35974 | CSL-7-201-004-40-SP1 | 2 | true | CH06822004-BD-PI-1179 | 40 | 5K | EG | H2 | T01577 | 2023-10-14 |  | 2023-11-06 | 2023-12-12 | 2023-12-14 | 2023-12-14 | 2023-12-15 |  | 2024-01-17 |  | 2024-02-07 | 2024-04-10 | 2.5 | 264 | 373 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 3
35975 | CSL-7-201-004-40-SP1 | 2 | true | CH06822004-BD-PI-1179 | 40 | 5K | EG | H2 | T01577 | 2023-10-14 |  | 2023-11-06 | 2023-12-13 |  | 2023-12-20 | 2024-01-12 |  | 2024-01-17 |  | 2024-02-07 | 2024-04-10 | 6 | 264 | 373 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 3
43897 | CSL-7-201-004-40-SP1 | 3 | false | CH06822004-BD-PI-1179 | 40 | 5K | EG | H2 | T-050 | 2024-01-31 |  | 2023-11-06 | 2023-12-13 |  | 2023-12-20 | 2024-01-12 |  | 2024-01-17 |  | 2024-01-31 |  | 11.7 | 264 | 373 |  |  |  |  | Issued for Information |  | 0 | SEP | SEP
43898 | CSL-7-201-004-40-SP1 | 3 | false | CH06822004-BD-PI-1179 | 40 | 5K | EG | H2 | T-050 | 2024-01-31 |  | 2023-11-06 | 2023-12-12 | 2023-12-14 | 2023-12-14 | 2023-12-15 |  | 2024-01-17 |  | 2024-01-31 |  | 2.7 | 264 | 373 |  |  |  |  | Issued for Information |  | 0 | SEP | SEP
43899 | CSL-7-201-004-40-SP1 | 3 | false | CH06822004-BD-PI-1179 | 40 | 5K | EG | H2 | T-050 | 2024-01-31 |  | 2023-11-06 | 2023-12-13 |  | 2023-12-20 | 2024-01-12 |  | 2024-01-17 |  | 2024-01-26 |  | 8.2 | 264 | 373 |  |  |  |  | Issued for Information |  | 0 | SEP | SEP
43900 | CSL-7-201-004-40-SP1 | 3 | false | CH06822004-BD-PI-1179 | 40 | 5K | EG | H2 | T-050 | 2024-01-31 |  | 2023-11-06 | 2023-12-12 | 2023-12-14 | 2023-12-14 | 2023-12-15 |  | 2024-01-17 |  | 2024-01-26 |  | 6 | 264 | 373 |  |  |  |  | Issued for Information |  | 0 | SEP | SEP
43901 | CSL-7-201-004-40-SP1 | 0 | false | CH06822004-BD-PI-1179 | 40 | 5K | EG | H2 | T-050 | 2024-01-31 |  | 2023-11-06 | 2023-12-13 |  | 2023-12-20 | 2024-01-12 |  | 2024-01-17 |  | 2024-01-26 |  | 6 | 264 | 373 |  |  |  |  | DELETED ISO´s PAGE |  | 0 | SEP | SEP
35976 | DKA-7-400-005-40-SD | 2 | false | CH06822004-BD-PI-1201 | 40 | 5K | EG | H3 | T01577 | 2023-10-14 |  | 2023-10-22 | 2023-10-31 | 2023-11-04 | 2023-11-08 | 2023-11-21 |  | 2023-12-04 |  |  | 2024-01-25 | 1.6 | 271 | 376 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
35977 | DKA-7-400-005-40-SD | 2 | false | CH06822004-BD-PI-1201 | 40 | 5K | EG | H3 | T01577 | 2023-10-14 |  | 2023-10-22 | 2023-10-31 | 2023-12-10 | 2023-12-10 | 2023-12-15 |  | 2024-01-17 |  |  | 2024-01-25 | 20 | 271 | 376 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
35978 | DKA-7-400-005-40-SD | 2 | false | CH06822004-BD-PI-1201 | 40 | 5K | EG | H3 | T01577 | 2023-10-14 |  | 2023-10-22 | 2023-11-02 | 2023-11-11 | 2023-11-14 | 2023-11-21 |  | 2023-12-04 |  |  | 2024-01-25 | 4.8 | 271 | 376 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
43256 | DKA-7-400-005-40-SD | 3 | true | CH06822004-BD-PI-1201 | 40 | 5K | EG | H3 | PEL-ZAU-T-044 | 2024-01-19 |  | 2023-10-22 | 2023-10-31 | 2023-11-04 | 2023-11-08 | 2023-11-21 |  | 2023-12-04 |  |  | 2024-01-25 | 1.5 | 271 | 376 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
43257 | DKA-7-400-005-40-SD | 3 | true | CH06822004-BD-PI-1201 | 40 | 5K | EG | H3 | PEL-ZAU-T-044 | 2024-01-19 |  | 2023-10-22 | 2023-10-31 | 2023-12-10 | 2023-12-10 | 2023-12-15 |  | 2024-01-17 |  |  | 2024-01-25 | 20 | 271 | 376 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
43258 | DKA-7-400-005-40-SD | 3 | true | CH06822004-BD-PI-1201 | 40 | 5K | EG | H3 | PEL-ZAU-T-044 | 2024-01-19 |  | 2023-10-22 | 2023-11-02 | 2023-11-11 | 2023-11-14 | 2023-11-21 |  | 2023-12-04 |  |  | 2024-01-25 | 4.8 | 271 | 376 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
35979 | DKS-7-401-007-32-SD | 2 | true | CH06822004-BD-PI-0530 | 32 | 5K | EG | H3 | T01577 | 2023-10-14 |  | 2023-10-22 | 2023-10-31 | 2023-11-06 | 2023-11-15 | 2023-11-21 |  | 2023-11-27 | 2023-11-30 |  | 2023-12-10 | 16.1 | 271 | 378 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
35980 | DLP-7-301-002-40-SP1 | 2 | false | CH06822004-BD-PI-0544 | 40 | 5K | EG | N/A | T01577 | 2023-10-14 |  | 2023-11-06 | 2023-12-15 |  | 2024-01-09 | 2024-01-12 |  | 2024-01-17 | 2024-02-07 |  |  | 4.2 | 264 | 382 | Jozef Kotul | [5 empty] | 0 | SEP | SEP |  | 3
35981 | DLP-7-301-002-40-SP1 | 2 | false | CH06822004-BD-PI-0544 | 40 | 5K | EG | N/A | T01577 | 2023-10-14 |  | 2023-11-06 | 2023-12-15 |  | 2024-01-09 | 2024-01-12 |  | 2024-01-17 |  |  | 2024-01-26 | 11.1 | 264 | 382 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 3
35982 | DLP-7-301-002-40-SP1 | 2 | false | CH06822004-BD-PI-0544 | 40 | 5K | EG | N/A | T01577 | 2023-10-14 |  | 2023-11-06 | 2023-12-12 |  | 2023-12-20 | 2024-01-12 |  | 2024-01-17 |  |  | 2024-01-31 | 14.7 | 264 | 382 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 3
43902 | DLP-7-301-002-40-SP1 | 3 | true | CH06822004-BD-PI-0544 | 40 | 5K | EG | N/A | T-058 | 2024-02-28 |  | 2023-11-06 | 2023-12-15 |  | 2024-01-09 | 2024-01-12 |  | 2024-01-17 |  |  | 2024-03-13 | 4.2 | 264 | 382 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
43903 | DLP-7-301-002-40-SP1 | 3 | true | CH06822004-BD-PI-0544 | 40 | 5K | EG | N/A | T-058 | 2024-02-28 |  | 2023-11-06 | 2023-12-15 |  | 2024-01-09 | 2024-01-12 |  | 2024-01-17 |  | 2024-01-31 | 2024-03-05 | 14.8 | 264 | 382 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
43904 | DLP-7-301-002-40-SP1 | 3 | true | CH06822004-BD-PI-0544 | 40 | 5K | EG | N/A | T-058 | 2024-02-28 |  | 2023-11-06 | 2023-12-12 |  | 2023-12-20 | 2024-01-12 |  | 2024-01-17 |  | 2024-01-31 | 2024-03-05 | 10.8 | 264 | 382 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
35983 | KR-0-216-038-40-SD5 | 2 | false | CH06822004-BD-PI-0607 | 40 | 5K | EG | C2 | T01577 | 2023-10-14 |  | 2023-11-06 | 2023-11-16 | 2023-11-19 | 2023-12-10 | 2023-12-15 |  | 2024-01-15 |  |  |  | 14 | 260 | 393 | Attila Henter | [5 empty] | 0 | SEP | SEP |  | 3
35984 | KR-0-216-038-40-SD5 | 2 | false | CH06822004-BD-PI-0607 | 40 | 5K | EG | C2 | T01577 | 2023-10-14 |  | 2023-11-06 | 2023-11-16 | 2023-11-19 | 2023-12-07 | 2023-12-15 |  | 2024-01-15 |  |  |  | 3 | 260 | 393 | Attila Henter | [5 empty] | 0 | SEP | SEP |  | 3
35985 | KR-0-216-038-40-SD5 | 2 | false | CH06822004-BD-PI-0607 | 40 | 5K | EG | C2 | T01577 | 2023-10-14 |  | 2023-11-06 | 2023-11-16 | 2023-11-19 | 2023-12-07 | 2023-12-15 |  | 2024-01-15 |  |  |  | 2.3 | 260 | 393 | Attila Henter | [5 empty] | 0 | SEP | SEP |  | 3
41931 | KR-0-216-038-40-SD5 | 3 | true | CH06822004-BD-PI-0607 | 40 | 5K | EG | C2 | PEL-ZAU-T-036 | 2024-01-12 |  | 2023-11-06 | 2023-11-16 | 2023-11-19 | 2023-12-10 | 2023-12-15 |  | 2024-02-01 |  | 2024-02-09 | 2024-02-15 | 14 | 260 | 393 | Virgil Frinculescu |  |  |  | Updated Positions of Thermowells etc. |  | 0 | SEP | SEP |  | 3
41932 | KR-0-216-038-40-SD5 | 3 | true | CH06822004-BD-PI-0607 | 40 | 5K | EG | C2 | PEL-ZAU-T-036 | 2024-01-12 |  | 2023-11-06 | 2023-11-16 | 2023-11-19 | 2023-12-07 | 2023-12-15 |  | 2024-02-01 |  |  | 2024-02-07 | 3 | 260 | 393 | Virgil Frinculescu |  |  |  | No change |  | 0 | SEP | SEP |  | 3
41933 | KR-0-216-038-40-SD5 | 3 | true | CH06822004-BD-PI-0607 | 40 | 5K | EG | C2 | PEL-ZAU-T-036 | 2024-01-12 |  | 2023-11-06 | 2023-11-16 | 2023-11-19 | 2023-12-07 | 2023-12-15 |  | 2024-02-01 |  | 2024-02-09 | 2024-02-20 | 2.4 | 260 | 393 | Virgil Frinculescu |  |  |  | Updated Pipe Lenghts DN20 |  | 0 | SEP | SEP |  | 3
35986 | KR-0-216-039-40-SD5 | 2 | false | CH06822004-BD-PI-0607 | 40 | 5K | EG | C2 | T01577 | 2023-10-14 |  | 2023-11-06 | 2023-11-12 | 2023-11-19 | 2023-12-11 | 2024-01-12 |  | 2024-01-18 |  |  |  | 1.6 | 260 | 393 | Attila Henter | [5 empty] | 0 | SEP | SEP |  | 3
35987 | KR-0-216-039-40-SD5 | 2 | false | CH06822004-BD-PI-0607 | 40 | 5K | EG | C2 | T01577 | 2023-10-14 |  | 2023-11-06 | 2023-11-12 | 2023-11-19 | 2023-12-10 | 2024-01-12 |  | 2024-01-18 |  |  |  | 2.6 | 260 | 393 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 3
35988 | KR-0-216-039-40-SD5 | 2 | false | CH06822004-BD-PI-0607 | 40 | 5K | EG | C2 | T01577 | 2023-10-14 |  | 2023-11-06 | 2023-11-12 | 2023-11-19 | 2023-12-10 | 2024-01-12 |  | 2024-01-18 |  |  |  | 10.7 | 260 | 393 | Attila Henter | [5 empty] | 0 | SEP | SEP |  | 3
35989 | KR-0-216-039-40-SD5 | 2 | false | CH06822004-BD-PI-0607 | 40 | 5K | EG | C2 | T01577 | 2023-10-14 |  | 2023-11-06 | 2023-11-12 | 2023-11-19 | 2023-12-19 | 2024-01-12 |  | 2024-01-18 |  |  |  | 8.8 | 260 | 393 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 3
41934 | KR-0-216-039-40-SD5 | 3 | true | CH06822004-BD-PI-0607 | 40 | 5K | EG | C2 | PEL-ZAU-T-036 | 2024-01-12 |  | 2023-11-06 | 2023-11-12 | 2023-11-19 | 2023-12-11 | 2024-01-12 |  | 2024-01-18 |  |  | 2024-02-13 | 1.5 | 260 | 393 | Virgil Frinculescu |  |  |  | Updated Positions of Thermowells etc. |  | 0 | SEP | SEP |  | 3
41935 | KR-0-216-039-40-SD5 | 3 | true | CH06822004-BD-PI-0607 | 40 | 5K | EG | C2 | PEL-ZAU-T-036 | 2024-01-12 |  | 2023-11-06 | 2023-11-12 | 2023-11-19 | 2023-12-10 | 2024-01-12 |  | 2024-01-18 |  |  | 2024-02-08 | 2.6 | 260 | 393 | Virgil Frinculescu |  |  |  | No change |  | 0 | SEP | SEP |  | 3
41936 | KR-0-216-039-40-SD5 | 3 | true | CH06822004-BD-PI-0607 | 40 | 5K | EG | C2 | PEL-ZAU-T-036 | 2024-01-12 |  | 2023-11-06 | 2023-11-12 | 2023-11-19 | 2023-12-10 | 2024-01-12 |  | 2024-01-18 |  |  | 2024-02-07 | 10.7 | 260 | 393 | Virgil Frinculescu |  |  |  | No change |  | 0 | SEP | SEP |  | 3
41937 | KR-0-216-039-40-SD5 | 3 | true | CH06822004-BD-PI-0607 | 40 | 5K | EG | C2 | PEL-ZAU-T-036 | 2024-01-12 |  | 2023-11-06 | 2023-11-12 | 2023-11-19 | 2023-12-19 | 2024-01-12 |  | 2024-01-18 |  |  | 2024-02-07 | 8.8 | 260 | 393 | Virgil Frinculescu |  |  |  | No change |  | 0 | SEP | SEP |  | 3
35990 | KV-0-216-036-40-SD5 | 2 | false | CH06822004-BD-PI-0607 | 40 | 5K | EG | C2 | T01577 | 2023-10-14 |  | 2023-11-06 | 2023-11-16 | 2023-11-19 | 2023-12-20 | 2024-01-12 |  | 2024-01-18 |  |  |  | 15.3 | 260 | 394 | Attila Henter | [5 empty] | 0 | SEP | SEP |  | 3
35991 | KV-0-216-036-40-SD5 | 2 | false | CH06822004-BD-PI-0607 | 40 | 5K | EG | C2 | T01577 | 2023-10-14 |  | 2023-11-06 | 2023-11-16 | 2023-11-19 | 2023-12-11 | 2024-01-12 |  | 2024-01-18 |  |  |  | 3.8 | 260 | 394 | Attila Henter | [5 empty] | 0 | SEP | SEP |  | 3
41875 | KV-0-216-036-40-SD5 | 3 | true | CH06822004-BD-PI-0607 | 40 | 5K | EG | C2 | PEL-ZAU-T-035 | 2024-01-13 |  | 2023-11-06 | 2023-11-16 | 2023-11-19 | 2023-12-20 | 2024-01-12 |  | 2024-01-18 |  |  | 2024-02-07 | 15.3 | 260 | 394 | Virgil Frinculescu |  |  |  | No change |  | 0 | SEP | SEP |  | 3
41876 | KV-0-216-036-40-SD5 | 3 | true | CH06822004-BD-PI-0607 | 40 | 5K | EG | C2 | PEL-ZAU-T-035 | 2024-01-13 |  | 2023-11-06 | 2023-11-16 | 2023-11-19 | 2023-12-11 | 2024-01-12 |  | 2024-01-18 |  |  | 2024-02-07 | 3.8 | 260 | 394 | Virgil Frinculescu |  |  |  | Updated Positions of Thermowells etc. |  | 0 | SEP | SEP |  | 3
35992 | KV-0-216-037-40-SD5 | 2 | false | CH06822004-BD-PI-0607 | 40 | 5K | EG | C2 | T01577 | 2023-10-14 |  | 2023-11-06 | 2023-11-10 | 2023-11-19 | 2023-12-07 | 2024-01-12 |  | 2024-01-18 |  |  | 2024-02-08 | 7.9 | 260 | 394 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 3
35993 | KV-0-216-037-40-SD5 | 2 | false | CH06822004-BD-PI-0607 | 40 | 5K | EG | C2 | T01577 | 2023-10-14 |  | 2023-11-06 | 2023-11-10 | 2023-11-19 | 2023-12-07 | 2024-01-12 |  | 2024-01-18 |  |  |  | 11.3 | 260 | 394 | Attila Henter | [5 empty] | 0 | SEP | SEP |  | 3
35994 | KV-0-216-037-40-SD5 | 2 | false | CH06822004-BD-PI-0607 | 40 | 5K | EG | C2 | T01577 | 2023-10-14 |  | 2023-11-06 | 2023-11-10 | 2023-11-19 | 2023-12-20 | 2024-01-12 |  | 2024-01-18 |  |  |  | 4.2 | 260 | 394 | Attila Henter | [5 empty] | 0 | SEP | SEP |  | 3
35995 | KV-0-216-037-40-SD5 | 2 | false | CH06822004-BD-PI-0607 | 40 | 5K | EG | C2 | T01577 | 2023-10-14 |  | 2023-11-06 | 2023-11-12 | 2023-11-19 | 2023-12-10 | 2024-01-12 |  | 2024-01-18 |  |  |  | 2.1 | 260 | 394 | Attila Henter | [5 empty] | 0 | SEP | SEP |  | 3
41877 | KV-0-216-037-40-SD5 | 3 | true | CH06822004-BD-PI-0607 | 40 | 5K | EG | C2 | PEL-ZAU-T-035 | 2024-01-13 |  | 2023-11-06 | 2023-11-10 | 2023-11-19 | 2023-12-07 | 2024-01-12 |  | 2024-01-18 |  |  | 2024-02-08 | 7.9 | 260 | 394 | Virgil Frinculescu |  |  |  | No change |  | 0 | SEP | SEP |  | 3
41878 | KV-0-216-037-40-SD5 | 3 | true | CH06822004-BD-PI-0607 | 40 | 5K | EG | C2 | PEL-ZAU-T-035 | 2024-01-13 |  | 2023-11-06 | 2023-11-10 | 2023-11-19 | 2023-12-07 | 2024-01-12 |  | 2024-01-18 |  | 2024-02-09 | 2024-02-09 | 11.3 | 260 | 394 | Virgil Frinculescu |  |  |  | No change |  | 0 | SEP | SEP |  | 3
41879 | KV-0-216-037-40-SD5 | 3 | true | CH06822004-BD-PI-0607 | 40 | 5K | EG | C2 | PEL-ZAU-T-035 | 2024-01-13 |  | 2023-11-06 | 2023-11-10 | 2023-11-19 | 2023-12-20 | 2024-01-12 |  | 2024-01-18 |  |  | 2024-02-07 | 4.2 | 260 | 394 | Virgil Frinculescu |  |  |  | No change |  | 0 | SEP | SEP |  | 3
41880 | KV-0-216-037-40-SD5 | 3 | true | CH06822004-BD-PI-0607 | 40 | 5K | EG | C2 | PEL-ZAU-T-035 | 2024-01-13 |  | 2023-11-06 | 2023-11-12 | 2023-11-19 | 2023-12-10 | 2024-01-12 |  | 2024-01-18 |  |  | 2024-02-13 | 2.3 | 260 | 394 | Virgil Frinculescu |  |  |  | Connection line from Supply to Retun has changed. |  | 0 | SEP | SEP |  | 3
36703 | ABP-7-701-005-65-SD | 1 | true | CH06822004-BD-PI-0495 | 65 | 5K | OG1 | N/A | T01578 | 2023-10-01 |  | 2023-11-06 | 2023-11-10 | 2023-11-17 | 2023-11-19 | 2023-11-21 |  | 2024-01-08 |  |  | 2024-01-23 | 5.8 | 271 | 362 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 3
36704 | ABP-7-701-005-65-SD | 1 | true | CH06822004-BD-PI-0495 | 65 | 5K | OG1 | N/A | T01578 | 2023-10-01 |  | 2023-11-06 | 2023-11-10 | 2023-11-16 | 2023-11-16 | 2023-11-21 |  | 2024-01-08 |  |  | 2024-01-23 | 10.8 | 271 | 362 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 3
36705 | ABP-7-701-005-65-SD | 1 | true | CH06822004-BD-PI-0495 | 65 | 5K | OG1 | N/A | T01578 | 2023-10-01 |  | 2023-11-06 | 2023-11-10 | 2023-11-16 | 2023-11-17 | 2023-11-21 |  | 2024-01-08 |  |  | 2024-01-23 | 4.5 | 271 | 362 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 3
36706 | ABP-7-701-014-65-SD | 1 | true | CH06822004-BD-PI-0495 | 65 | 5K | OG1 | N/A | T01578 | 2023-10-01 |  | 2023-11-06 | 2023-11-16 | 2023-11-19 | 2024-01-05 | 2024-01-12 |  | 2024-02-01 |  |  | 2024-02-09 | 3.5 | 271 | 362 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 3
36707 | ABP-7-701-014-65-SD | 1 | true | CH06822004-BD-PI-0495 | 65 | 5K | OG1 | N/A | T01578 | 2023-10-01 |  | 2023-11-06 | 2023-11-16 | 2023-11-19 | 2024-01-05 | 2024-01-12 |  | 2024-02-01 |  | 2024-02-07 | 2024-02-09 | 17 | 271 | 362 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 3
36708 | CIP-2-000-011-40-SP | 1 | true | CH06822004-BD-PI-0523 | 40 | 5K | OG1 | H3 | T01578 | 2023-10-01 |  | 2023-11-06 | 2023-12-12 | 2023-12-14 | 2023-12-14 | 2023-12-15 |  | 2024-01-11 |  |  | 2024-01-23 | 3.2 | 262 | 460 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 3
36709 | CIP-2-000-011-40-SP | 1 | true | CH06822004-BD-PI-0523 | 40 | 5K | OG1 | H3 | T01578 | 2023-10-01 |  | 2023-11-06 | 2023-12-15 |  | 2023-12-20 | 2024-01-12 |  | 2024-01-16 |  | 2024-01-26 | 2024-02-06 | 25.3 | 262 | 460 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 3
36710 | CO2F-7-600-003-25-SP1 | 1 | false | CH06822004-BD-PI-0449 | 25 | 5K | OG1 | N/A | T01578 | 2023-10-01 |  | 2023-11-06 | 2023-11-16 | 2023-12-06 | 2023-12-07 | 2023-12-15 |  | 2024-01-11 |  |  |  | 5 | 264 | 369 | Jozef Kotul | [5 empty] | 0 | SEP | SEP |  | 3
36711 | CO2F-7-600-003-25-SP1 | 1 | false | CH06822004-BD-PI-0449 | 25 | 5K | OG1 | N/A | T01578 | 2023-10-01 |  | 2023-11-06 | 2023-11-15 |  | 2024-01-12 | 2024-01-12 |  | 2024-01-16 |  |  | 2024-01-26 | 17.9 | 264 | 369 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 3
36712 | CO2F-7-600-003-25-SP1 | 1 | false | CH06822004-BD-PI-0449 | 25 | 5K | OG1 | N/A | T01578 | 2023-10-01 |  | 2023-11-06 | 2023-11-17 | 2023-12-07 | 2023-12-07 | 2023-12-15 |  | 2024-01-10 |  |  | 2024-01-23 | 13.3 | 264 | 369 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 3
42570 | CO2F-7-600-003-25-SP1 | 2 | true | CH06822004-BD-PI-0449 | 25 | 5K | OG1 | N/A | PEL-ZAU-T-043 | 2024-01-19 |  | 2023-11-06 | 2023-11-16 | 2023-12-06 | 2023-12-07 | 2023-12-15 |  | 2024-01-31 | 2024-02-07 |  | 2024-06-27 | 5 | 264 | 369 | Virgil Frinculescu |  |  |  | Updated Positions of Thermowells etc. |  | 0 | SEP | SEP
42571 | CO2F-7-600-003-25-SP1 | 2 | true | CH06822004-BD-PI-0449 | 25 | 5K | OG1 | N/A | PEL-ZAU-T-043 | 2024-01-19 |  | 2023-11-06 | 2023-11-15 |  | 2024-01-12 | 2024-01-12 |  | 2024-01-29 |  |  | 2024-02-08 | 17.9 | 264 | 369 | Virgil Frinculescu |  |  |  | No change |  | 0 | SEP | SEP
42572 | CO2F-7-600-003-25-SP1 | 2 | true | CH06822004-BD-PI-0449 | 25 | 5K | OG1 | N/A | PEL-ZAU-T-043 | 2024-01-19 |  | 2023-11-06 | 2023-11-17 | 2023-12-07 | 2023-12-07 | 2023-12-15 |  | 2024-01-10 |  |  | 2024-02-01 | 13.3 | 264 | 369 | Virgil Frinculescu |  |  |  | No change |  | 0 | SEP | SEP
36713 | DLF-7-831-005-25-SP1 | 1 | true | CH06822004-BD-PI-0537 | 25 | 5K | OG1 | N/A | T01578 | 2023-10-01 |  | 2023-11-06 | 2023-11-15 | 2023-11-19 | 2023-12-07 | 2023-12-15 |  | 2024-01-11 |  |  | 2024-02-06 | 3.7 | 264 | 380 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 3
36714 | DLF-7-831-005-25-SP1 | 1 | true | CH06822004-BD-PI-0537 | 25 | 5K | OG1 | N/A | T01578 | 2023-10-01 |  | 2023-11-06 | 2023-11-16 | 2023-11-19 | 2023-12-07 | 2023-12-15 |  | 2024-01-11 |  |  | 2024-01-23 | 12.9 | 264 | 380 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 3
36715 | DLF-7-831-006-25-SP1 | 1 | false | CH06822004-BD-PI-0537 | 25 | 5K | OG1 | N/A | T01578 | 2023-10-01 |  | 2023-11-06 | 2023-11-16 | 2023-11-19 | 2023-12-07 | 2023-12-15 |  | 2024-01-09 |  |  | 2024-01-26 | 4 | 264 | 380 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 3
36716 | DLF-7-831-006-25-SP1 | 1 | false | CH06822004-BD-PI-0537 | 25 | 5K | OG1 | N/A | T01578 | 2023-10-01 |  | 2023-11-06 | 2023-11-16 | 2023-11-19 | 2023-12-07 | 2023-12-15 |  | 2024-01-09 |  |  | 2024-01-15 | 17.7 | 264 | 380 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 3
45594 | DLF-7-831-006-25-SP1 | 3 | false | CH06822004-BD-PI-0537 | 25 | 5K | OG1 | N/A | T-061 | 2024-03-08 |  | 2023-11-06 | 2023-11-16 | 2023-11-19 | 2023-12-07 | 2023-12-15 |  | 2024-01-09 |  | 2024-03-08 | 2024-03-12 | 11.6 | 264 | 380 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45595 | DLF-7-831-006-25-SP1 | 3 | false | CH06822004-BD-PI-0537 | 25 | 5K | OG1 | N/A | T-061 | 2024-03-08 |  | 2023-11-06 | 2023-11-16 | 2023-11-19 | 2023-12-07 | 2023-12-15 |  | 2024-03-14 |  | 2024-03-08 | 2024-03-21 | 9.8 | 264 | 380 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
50532 | DLF-7-831-006-25-SP1 | 4 | true | CH06822004-BD-PI-0537 | 25 | 5K | OG1 | N/A | T-081 | 2024-05-13 |  | 2023-11-06 | 2023-11-16 | 2023-11-19 | 2023-12-07 | 2023-12-15 |  | 2024-01-09 |  | 2024-05-13 | 2024-05-15 | 11.6 | 264 | 380 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
50533 | DLF-7-831-006-25-SP1 | 4 | true | CH06822004-BD-PI-0537 | 25 | 5K | OG1 | N/A | T-081 | 2024-05-13 |  | 2023-11-06 | 2023-11-16 | 2023-11-19 | 2023-12-07 | 2023-12-15 |  | 2024-03-14 |  | 2024-05-13 | 2024-05-29 | 9.7 | 264 | 380 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
36717 | EtOHP-6-701-001-25-SP | 1 | false | CH06822004-BD-PI-0473 | 25 | 5K | OG1 | N/A | T01578 | 2023-10-01 |  | 2023-11-06 | 2023-11-16 | 2023-11-19 | 2023-12-07 | 2023-12-15 |  | 2024-01-10 |  | 2024-02-07 |  | 25.9 | 262 | 384 | Jozef Kotul | [5 empty] | 0 | SEP | SEP |  | 3
49852 | EtOHP-6-701-001-25-SP | 2 | true | CH06822004-BD-PI-0473 | 25 | 5K | OG1 | N/A | T-078 | 2024-04-26 | [9 empty] | 2024-05-15 | 2024-05-23 | 25.6 | 262 | 384 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
36718 | KR-0-216-003-50-SD5 | 1 | false | CH06822004-BD-PI-0607 | 50 | 5K | OG1 | C2 | T01578 | 2023-10-01 |  | 2023-11-06 | 2023-11-16 | 2023-11-19 | 2023-12-06 | 2023-12-15 |  | 2024-01-11 |  |  |  | 3.2 | 260 | 393 | Jozef Kotul | [5 empty] | 0 | SEP | SEP |  | 3
41917 | KR-0-216-003-50-SD5 | 2 | true | CH06822004-BD-PI-0607 | 50 | 5K | OG1 | C2 | PEL-ZAU-T-036 | 2024-01-12 |  | 2023-11-06 | 2023-11-16 | 2023-11-19 | 2023-12-06 | 2023-12-15 |  | 2024-01-18 |  | 2024-02-07 | 2024-06-06 | 3.2 | 260 | 393 | Virgil Frinculescu |  |  |  | Updated Positions of Thermowells etc. |  | 0 | SEP | SEP |  | 3
36719 | KR-0-216-034-20-SD5 | 1 | true | CH06822004-BD-PI-0607 | 20 | 5K | OG1 | C2 | T01578 | 2023-10-01 |  | 2023-11-06 | 2023-11-08 | 2023-11-19 | 2023-12-06 | 2023-12-15 |  | 2024-01-11 |  |  | 2024-01-26 | 0.1 | 260 | 393 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 3
36720 | KV-0-216-004-50-SD5 | 1 | false | CH06822004-BD-PI-0607 | 50 | 5K | OG1 | C2 | T01578 | 2023-10-01 |  | 2023-11-06 | 2023-11-08 | 2023-11-19 | 2023-12-06 | 2023-12-15 |  | 2024-01-18 |  |  |  | 3.5 | 260 | 394 | Attila Henter | [5 empty] | 0 | SEP | SEP |  | 3
41865 | KV-0-216-004-50-SD5 | 2 | true | CH06822004-BD-PI-0607 | 50 | 5K | OG1 | C2 | PEL-ZAU-T-035 | 2024-01-13 |  | 2023-11-06 | 2023-11-08 | 2023-11-19 | 2023-12-06 | 2023-12-15 |  | 2024-01-18 |  | 2024-02-07 | 2024-06-06 | 3.3 | 260 | 394 | Virgil Frinculescu |  |  |  | Updated Positions of Thermowells etc. |  | 0 | SEP | SEP |  | 5
36721 | KV-0-216-039-20-SD5 | 1 | true | CH06822004-BD-PI-0607 | 20 | 5K | OG1 | C2 | T01578 | 2023-10-01 | 2023-11-08 | 2023-11-06 | 2023-11-10 | 2023-11-19 | 2023-12-06 | 2023-12-15 |  | 2024-01-18 |  |  | 2024-02-06 | 0.1 | 260 | 394 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 3
36722 | N2F-7-500-003-025-SP1 | 1 | true | CH06822004-BD-PI-0457 | 25 | 5K | OG1 | N/A | T01578 | 2023-10-01 |  | 2023-11-06 | 2023-11-19 | 2023-11-19 | 2023-12-20 | 2024-01-12 |  | 2024-01-16 | 2024-02-07 |  | 2024-06-27 | 5.3 | 264 | 396 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 3
36723 | N2F-7-500-003-025-SP1 | 1 | true | CH06822004-BD-PI-0457 | 25 | 5K | OG1 | N/A | T01578 | 2023-10-01 |  | 2023-11-06 | 2023-11-19 | 2023-11-19 | 2024-01-12 | 2024-01-12 |  | 2024-01-16 |  |  | 2024-01-26 | 13 | 264 | 396 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 3
36724 | N2F-7-500-003-025-SP1 | 1 | true | CH06822004-BD-PI-0457 | 25 | 5K | OG1 | N/A | T01578 | 2023-10-01 |  | 2023-11-06 | 2023-11-15 | 2023-11-19 | 2023-12-07 | 2023-12-15 |  | 2024-01-10 |  |  | 2024-01-23 | 17.6 | 264 | 396 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 3
36725 | O2F-7-400-003-25-SP1 | 1 | false | CH06822004-BD-PI-0465 | 25 | 5K | OG1 | N/A | T01578 | 2023-10-01 |  | 2023-11-06 | 2023-11-15 | 2023-11-19 | 2023-12-07 | 2023-12-15 |  | 2024-01-11 |  |  |  | 5.1 | 264 | 458 | Jozef Kotul | [5 empty] | 0 | SEP | SEP |  | 3
36726 | O2F-7-400-003-25-SP1 | 1 | false | CH06822004-BD-PI-0465 | 25 | 5K | OG1 | N/A | T01578 | 2023-10-01 |  | 2023-11-06 | 2023-11-15 | 2023-11-19 | 2023-12-07 | 2024-01-12 |  | 2024-01-16 |  |  | 2024-01-26 | 13.5 | 264 | 458 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 3
36727 | O2F-7-400-003-25-SP1 | 1 | false | CH06822004-BD-PI-0465 | 25 | 5K | OG1 | N/A | T01578 | 2023-10-01 |  | 2023-11-06 | 2023-11-15 | 2023-11-19 | 2023-12-07 | 2023-12-15 |  | 2024-01-10 |  |  | 2024-01-23 | 17.3 | 264 | 458 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 3
43909 | O2F-7-400-003-25-SP1 | 2 | true | CH06822004-BD-PI-0465 | 25 | 5K | OG1 | N/A | T-050 | 2024-01-31 |  | 2023-11-06 | 2023-11-15 | 2023-11-19 | 2023-12-07 | 2023-12-15 |  | 2024-02-01 | 2024-02-07 |  | 2024-06-27 | 5.1 | 264 | 458 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
43910 | O2F-7-400-003-25-SP1 | 2 | true | CH06822004-BD-PI-0465 | 25 | 5K | OG1 | N/A | T-050 | 2024-01-31 |  | 2023-11-06 | 2023-11-15 | 2023-11-19 | 2023-12-07 | 2024-01-12 |  | 2024-01-16 |  | 2024-01-31 | 2024-02-01 | 13.5 | 264 | 458 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
43911 | O2F-7-400-003-25-SP1 | 2 | true | CH06822004-BD-PI-0465 | 25 | 5K | OG1 | N/A | T-050 | 2024-01-31 |  | 2023-11-06 | 2023-11-15 | 2023-11-19 | 2023-12-07 | 2023-12-15 |  | 2024-01-10 |  | 2024-01-31 | 2024-02-01 | 17.3 | 264 | 458 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
36728 | US4-0-244-009-15-SD6 | 1 | false | CH06822004-BD-PI-0586 | 15 | 5K | OG1 | H5 | T01578 | 2023-10-01 |  | 2023-11-06 | 2023-11-09 | 2023-11-19 | 2023-12-10 | 2023-12-15 | [5 empty] | 0.3 | 261 | 410 | [6 empty] | 0 | SEP | SEP |  | 3
43834 | US4-0-244-009-15-SD6 | 2 | true | CH06822004-BD-PI-0586 | 15 | 5K | OG1 | H5 | T-048 | 2024-01-30 |  | 2023-11-06 | 2023-11-09 | 2023-11-19 | 2023-12-10 | 2023-12-15 |  | 2024-02-07 |  |  | 2024-02-29 | 1.1 | 261 | 410 | Virgil Frinculescu |  |  |  | Latest rev. 2 is added to the w.map. |  | 0 | SEP | SEP
36729 | WAA-7-931-043-100-SD | 1 | true | CH06822004-BD-PI-0635 | 100 | 5K | OG1 | H3 | T01578 | 2023-10-01 |  | 2023-10-23 | 2023-10-31 | 2023-11-15 | 2023-11-16 | 2023-11-21 |  | 2023-11-30 | 2023-12-18 |  | 2024-01-09 | 14.8 | 271 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
36730 | WAA-7-931-043-100-SD | 1 | true | CH06822004-BD-PI-0635 | 100 | 5K | OG1 | H3 | T01578 | 2023-10-01 |  | 2023-10-23 | 2023-11-03 | 2023-11-15 | 2023-11-16 | 2023-11-21 |  | 2023-11-30 |  |  | 2024-01-09 | 7.7 | 271 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
36731 | WAA-7-931-051-50-SD | 1 | true | CH06822004-BD-PI-0635 | 50 | 5K | OG1 | H3 | T01578 | 2023-10-01 |  | 2023-10-23 | 2023-11-05 | 2023-11-11 | 2023-11-14 | 2023-11-21 |  | 2023-11-30 | 2023-12-18 |  | 2024-01-16 | 9.7 | 271 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
36732 | WAA-7-931-051-50-SD | 1 | true | CH06822004-BD-PI-0635 | 50 | 5K | OG1 | H3 | T01578 | 2023-10-01 |  | 2023-10-23 | 2023-11-05 | 2023-11-06 | 2023-11-06 | 2023-12-05 |  | 2023-12-12 |  |  | 2024-01-16 | 5.6 | 271 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
36733 | CS-7-201-006-50-SP1 | 2 | false | CH06822004-BD-PI-1179 | 50 | 5K | OG1 | H2 | T01578 | 2023-10-01 |  | 2023-11-06 | 2023-12-15 |  | 2024-01-12 | 2024-01-12 |  | 2024-01-16 |  |  |  | 0.7 | 264 | 371 | Jozef Kotul | [5 empty] | 0 | SEP | SEP |  | 3
43473 | CS-7-201-006-50-SP1 | 3 | true | CH06822004-BD-PI-1179 | 50 | 5K | OG1 | H2 | T-047 | 2024-01-25 |  | 2023-11-06 | 2023-12-15 |  | 2024-01-12 | 2024-01-12 |  | 2024-01-30 |  |  | 2024-07-10 | 0.3 | 264 | 371 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
36734 | CSL-7-201-007-50-SP1 | 2 | false | CH06822004-BD-PI-1179 | 50 | 5K | OG1 | H2 | T01578 | 2023-10-01 |  | 2023-11-06 | 2023-11-20 | 2023-11-19 | 2024-01-12 | 2024-01-12 |  | 2024-01-16 |  |  |  | 5.6 | 264 | 373 | Jozef Kotul | [5 empty] | 0 | SEP | SEP |  | 3
36735 | CSL-7-201-007-50-SP1 | 2 | false | CH06822004-BD-PI-1179 | 50 | 5K | OG1 | H2 | T01578 | 2023-10-01 |  | 2023-11-06 | 2023-11-20 | 2023-11-19 | 2023-12-14 | 2023-12-15 |  | 2024-01-11 |  |  | 2024-01-23 | 7.7 | 264 | 373 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 3
36736 | CSL-7-201-007-50-SP1 | 2 | false | CH06822004-BD-PI-1179 | 50 | 5K | OG1 | H2 | T01578 | 2023-10-01 |  | 2023-11-06 | 2023-11-20 | 2023-11-19 | 2023-12-20 | 2024-01-12 |  | 2024-01-16 |  |  | 2024-01-23 | 6.3 | 264 | 373 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 3
43484 | CSL-7-201-007-50-SP1 | 3 | true | CH06822004-BD-PI-1179 | 50 | 5K | OG1 | H2 | T-047 | 2024-01-25 |  | 2023-11-06 | 2023-11-20 | 2023-11-19 | 2024-01-12 | 2024-01-12 |  | 2024-01-31 | 2024-02-07 |  | 2024-07-15 | 3.5 | 264 | 373 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
43485 | CSL-7-201-007-50-SP1 | 3 | true | CH06822004-BD-PI-1179 | 50 | 5K | OG1 | H2 | T-047 | 2024-01-25 |  | 2023-11-06 | 2023-11-20 | 2023-11-19 | 2023-12-14 | 2023-12-15 |  | 2024-01-11 |  |  | 2024-02-08 | 9.9 | 264 | 373 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
43486 | CSL-7-201-007-50-SP1 | 3 | true | CH06822004-BD-PI-1179 | 50 | 5K | OG1 | H2 | T-047 | 2024-01-25 |  | 2023-11-06 | 2023-11-20 | 2023-11-19 | 2023-12-20 | 2024-01-12 |  | 2024-01-16 |  |  | 2024-02-08 | 6.3 | 264 | 373 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
36737 | DLP-7-301-005-40-SP1 | 2 | false | CH06822004-BD-PI-0544 | 40 | 5K | OG1 | N/A | T01578 | 2023-10-01 |  | 2023-11-06 | 2023-12-15 |  | 2023-12-20 | 2024-01-12 |  | 2024-01-16 | 2024-02-07 |  |  | 2.5 | 264 | 382 | Jozef Kotul |  |  |  | NEW ISO released just for information. OLD revision need to redline acc. to new ISO |  | 0 | SEP | SEP |  | 3
36738 | DLP-7-301-005-40-SP1 | 2 | false | CH06822004-BD-PI-0544 | 40 | 5K | OG1 | N/A | T01578 | 2023-10-01 |  | 2023-11-06 | 2023-12-15 |  | 2023-12-20 | 2024-01-12 |  | 2024-01-16 |  |  | 2024-02-06 | 19.7 | 264 | 382 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 3
36739 | DLP-7-301-005-40-SP1 | 2 | false | CH06822004-BD-PI-0544 | 40 | 5K | OG1 | N/A | T01578 | 2023-10-01 |  | 2023-11-06 | 2023-12-15 |  | 2023-12-20 | 2024-01-12 |  | 2024-01-16 |  |  | 2024-01-23 | 13.2 | 264 | 382 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 3
43905 | DLP-7-301-005-40-SP1 | 3 | true | CH06822004-BD-PI-0544 | 40 | 5K | OG1 | N/A | T-058 | 2024-02-28 |  | 2023-11-06 | 2023-12-15 |  | 2023-12-20 | 2024-01-12 |  | 2024-01-16 |  |  | 2024-03-11 | 2.6 | 264 | 382 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
43906 | DLP-7-301-005-40-SP1 | 3 | true | CH06822004-BD-PI-0544 | 40 | 5K | OG1 | N/A | T-050 | 2024-01-31 |  | 2023-11-06 | 2023-12-15 |  | 2023-12-20 | 2024-01-12 |  | 2024-01-16 |  |  | 2024-04-16 | 19.7 | 264 | 382 | Virgil Frinculescu |  |  |  | Issued for Information |  | 0 | SEP | SEP
43907 | DLP-7-301-005-40-SP1 | 3 | true | CH06822004-BD-PI-0544 | 40 | 5K | OG1 | N/A | T-058 | 2024-02-28 |  | 2023-11-06 | 2023-12-15 |  | 2023-12-20 | 2024-01-12 |  | 2024-01-16 |  | 2024-01-31 | 2024-03-05 | 13.2 | 264 | 382 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
36740 | GR-0-244-003-80-SD5 | 2 | false | CH06822004-BD-PI-0565 | 80 | 5K | OG1 | C3 | T01578 | 2023-10-01 |  | 2023-11-06 | 2023-11-16 | 2023-11-19 | 2023-12-04 | 2023-12-05 |  | 2024-01-26 |  |  |  | 2 | 260 | 387 | Jozef Kotul | [5 empty] | 0 | SEP | SEP |  | 3
36741 | GR-0-244-003-80-SD5 | 2 | false | CH06822004-BD-PI-0565 | 80 | 5K | OG1 | C3 | T01578 | 2023-10-01 |  | 2023-11-06 | 2023-11-16 | 2023-12-12 | 2023-12-12 | 2024-01-12 |  | 2024-01-26 |  |  |  | 10.5 | 260 | 387 | Jozef Kotul | [5 empty] | 0 | SEP | SEP |  | 3
36742 | GR-0-244-003-80-SD5 | 2 | false | CH06822004-BD-PI-0565 | 80 | 5K | OG1 | C3 | T01578 | 2023-10-01 |  | 2023-11-06 | 2023-11-16 | 2023-12-13 | 2023-12-13 | 2024-01-12 |  | 2024-01-26 |  |  |  | 11 | 260 | 387 | Jozef Kotul | [5 empty] | 0 | SEP | SEP |  | 3
36743 | GR-0-244-003-80-SD5 | 2 | false | CH06822004-BD-PI-0565 | 80 | 5K | OG1 | C3 | T01578 | 2023-10-01 |  | 2023-11-06 | 2023-11-16 | 2023-11-19 | 2024-01-05 | 2024-01-12 |  | 2024-01-26 |  |  |  | 9.7 | 260 | 387 | Jozef Kotul | [5 empty] | 0 | SEP | SEP |  | 3
36744 | GR-0-244-003-80-SD5 | 2 | false | CH06822004-BD-PI-0565 | 80 | 5K | OG1 | C3 | T01578 | 2023-10-01 |  | 2023-11-06 | 2023-11-16 | 2023-11-19 | 2023-12-13 | 2024-01-12 |  | 2024-01-26 |  |  |  | 1.1 | 260 | 387 | Jozef Kotul | [5 empty] | 0 | SEP | SEP |  | 3
36745 | GR-0-244-003-80-SD5 | 2 | false | CH06822004-BD-PI-0565 | 80 | 5K | OG1 | C3 | T01578 | 2023-10-01 |  | 2023-11-06 | 2023-11-16 | 2023-12-12 | 2023-12-12 | 2024-01-12 |  | 2024-01-26 |  |  |  | 3.9 | 260 | 387 | Jozef Kotul | [5 empty] | 0 | SEP | SEP |  | 3
41957 | GR-0-244-003-80-SD5 | 3 | true | CH06822004-BD-PI-0565 | 80 | 5K | OG1 | C3 | PEL-ZAU-T-034 | 2024-01-12 |  | 2023-11-06 | 2023-11-16 | 2023-11-19 | 2023-12-04 | 2023-12-05 |  | 2024-01-26 |  | 2024-02-07 | 2024-02-09 | 2.1 | 260 | 387 | Virgil Frinculescu |  |  |  | Updated Positions of Thermowells etc. |  | 0 | SEP | SEP |  | 3
41958 | GR-0-244-003-80-SD5 | 3 | true | CH06822004-BD-PI-0565 | 80 | 5K | OG1 | C3 | PEL-ZAU-T-034 | 2024-01-12 |  | 2023-11-06 | 2023-11-16 | 2023-12-12 | 2023-12-12 | 2024-01-12 |  | 2024-01-26 |  | 2024-02-07 | 2024-02-09 | 10.5 | 260 | 387 | Virgil Frinculescu |  |  |  | No change |  | 0 | SEP | SEP |  | 3
41959 | GR-0-244-003-80-SD5 | 3 | true | CH06822004-BD-PI-0565 | 80 | 5K | OG1 | C3 | PEL-ZAU-T-034 | 2024-01-12 |  | 2023-11-06 | 2023-11-16 | 2023-12-13 | 2023-12-13 | 2024-01-12 |  | 2024-01-26 |  | 2024-02-07 | 2024-02-09 | 11 | 260 | 387 | Virgil Frinculescu |  |  |  | No change |  | 0 | SEP | SEP |  | 3
41960 | GR-0-244-003-80-SD5 | 3 | true | CH06822004-BD-PI-0565 | 80 | 5K | OG1 | C3 | PEL-ZAU-T-034 | 2024-01-12 |  | 2023-11-06 | 2023-11-16 | 2023-11-19 | 2024-01-05 | 2024-01-12 |  | 2024-01-26 |  | 2024-02-07 | 2024-05-02 | 9.7 | 260 | 387 | Virgil Frinculescu |  |  |  | No change |  | 0 | SEP | SEP |  | 3
41961 | GR-0-244-003-80-SD5 | 3 | true | CH06822004-BD-PI-0565 | 80 | 5K | OG1 | C3 | PEL-ZAU-T-034 | 2024-01-12 |  | 2023-11-06 | 2023-11-16 | 2023-11-19 | 2023-12-13 | 2024-01-12 |  | 2024-01-26 |  | 2024-02-07 | 2024-02-09 | 1.2 | 260 | 387 | Virgil Frinculescu |  |  |  | Updated Pipe Lenghts DN20 |  | 0 | SEP | SEP |  | 3
41962 | GR-0-244-003-80-SD5 | 3 | true | CH06822004-BD-PI-0565 | 80 | 5K | OG1 | C3 | PEL-ZAU-T-034 | 2024-01-12 |  | 2023-11-06 | 2023-11-16 | 2023-12-12 | 2023-12-12 | 2024-01-12 |  | 2024-01-26 |  | 2024-02-07 | 2024-06-06 | 3.9 | 260 | 387 | Virgil Frinculescu |  |  |  | Updated Positions of Thermowells etc. |  | 0 | SEP | SEP |  | 3
36746 | GV-0-244-004-80-SD5 | 2 | false | CH06822004-BD-PI-0565 | 80 | 5K | OG1 | C3 | T01578 | 2023-10-01 |  | 2023-11-06 | 2023-11-16 | 2023-11-19 | 2023-12-06 | 2023-12-15 |  | 2024-01-26 |  |  | 2024-06-06 | 3.2 | 260 | 388 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 3
36747 | GV-0-244-004-80-SD5 | 2 | false | CH06822004-BD-PI-0565 | 80 | 5K | OG1 | C3 | T01578 | 2023-10-01 |  | 2023-11-06 | 2023-11-16 | 2023-11-19 | 2024-01-06 | 2024-01-12 |  | 2024-01-26 |  |  |  | 12.3 | 260 | 388 | Jozef Kotul | [5 empty] | 0 | SEP | SEP |  | 3
36748 | GV-0-244-004-80-SD5 | 2 | false | CH06822004-BD-PI-0565 | 80 | 5K | OG1 | C3 | T01578 | 2023-10-01 |  | 2023-11-06 | 2023-11-16 | 2023-11-19 | 2023-12-06 | 2024-01-12 |  | 2024-01-26 |  |  |  | 0.8 | 260 | 388 | Jozef Kotul | [5 empty] | 0 | SEP | SEP |  | 3
36749 | GV-0-244-004-80-SD5 | 2 | false | CH06822004-BD-PI-0565 | 80 | 5K | OG1 | C3 | T01578 | 2023-10-01 |  | 2023-11-06 | 2023-11-16 | 2023-11-19 | 2023-12-06 | 2023-12-15 |  | 2024-01-10 |  |  |  | 12.7 | 260 | 388 | Attila Henter | [5 empty] | 0 | SEP | SEP |  | 3
36750 | GV-0-244-004-80-SD5 | 2 | false | CH06822004-BD-PI-0565 | 80 | 5K | OG1 | C3 | T01578 | 2023-10-01 |  | 2023-11-06 | 2023-11-16 | 2023-11-19 | 2023-12-06 | 2023-12-15 |  | 2024-01-26 |  |  | 2024-01-16 | 7.5 | 260 | 388 | Jozef Kotul | [5 empty] | 0 | SEP | SEP |  | 3
36751 | GV-0-244-004-80-SD5 | 2 | false | CH06822004-BD-PI-0565 | 80 | 5K | OG1 | C3 | T01578 | 2023-10-01 |  | 2023-11-06 | 2023-11-16 | 2023-11-19 | 2023-12-06 | 2023-12-15 |  | 2024-01-26 |  |  | 2024-01-16 | 1.4 | 260 | 388 | Jozef Kotul | [5 empty] | 0 | SEP | SEP |  | 3
36752 | GV-0-244-004-80-SD5 | 2 | false | CH06822004-BD-PI-0565 | 80 | 5K | OG1 | C3 | T01578 | 2023-10-01 |  | 2023-11-06 | 2023-11-16 | 2023-11-19 | 2023-12-06 | 2023-12-15 |  | 2024-01-26 |  |  | 2024-01-16 | 0.1 | 260 | 388 | Jozef Kotul | [5 empty] | 0 | SEP | SEP |  | 3
41971 | GV-0-244-004-80-SD5 | 3 | true | CH06822004-BD-PI-0565 | 80 | 5K | OG1 | C3 | PEL-ZAU-T-034 | 2024-01-12 |  | 2023-11-06 | 2023-11-16 | 2023-11-19 | 2023-12-06 | 2023-12-15 |  | 2024-01-26 | 2024-02-07 |  | 2024-02-09 | 3.2 | 260 | 388 | Virgil Frinculescu |  |  |  | Updated Positions of Thermowells etc. + Line to be cut back |  | 0 | SEP | SEP |  | 3
41972 | GV-0-244-004-80-SD5 | 3 | true | CH06822004-BD-PI-0565 | 80 | 5K | OG1 | C3 | PEL-ZAU-T-034 | 2024-01-12 |  | 2023-11-06 | 2023-11-16 | 2023-11-19 | 2024-01-06 | 2024-01-12 |  | 2024-01-26 |  | 2024-02-07 | 2024-05-08 | 12.2 | 260 | 388 | Virgil Frinculescu |  |  |  | No change |  | 0 | SEP | SEP |  | 3
41973 | GV-0-244-004-80-SD5 | 3 | true | CH06822004-BD-PI-0565 | 80 | 5K | OG1 | C3 | PEL-ZAU-T-034 | 2024-01-12 |  | 2023-11-06 | 2023-11-16 | 2023-11-19 | 2023-12-06 | 2024-01-12 |  | 2024-01-26 |  | 2024-02-07 | 2024-02-09 | 0.8 | 260 | 388 | Virgil Frinculescu |  |  |  | Main Line got longer DN80 |  | 0 | SEP | SEP |  | 3
41974 | GV-0-244-004-80-SD5 | 3 | true | CH06822004-BD-PI-0565 | 80 | 5K | OG1 | C3 | PEL-ZAU-T-034 | 2024-01-12 |  | 2023-11-06 | 2023-11-16 | 2023-11-19 | 2023-12-06 | 2023-12-15 |  | 2024-01-26 |  | 2024-02-07 | 2024-02-09 | 12.7 | 260 | 388 | Virgil Frinculescu |  |  |  | No change |  | 0 | SEP | SEP |  | 3
41975 | GV-0-244-004-80-SD5 | 3 | true | CH06822004-BD-PI-0565 | 80 | 5K | OG1 | C3 | PEL-ZAU-T-034 | 2024-01-12 |  | 2023-11-06 | 2023-11-16 | 2023-11-19 | 2023-12-06 | 2023-12-15 |  | 2024-01-26 |  | 2024-01-16 | 2024-02-09 | 7.5 | 260 | 388 | Virgil Frinculescu |  |  |  | No change |  | 0 | SEP | SEP |  | 3
41976 | GV-0-244-004-80-SD5 | 3 | true | CH06822004-BD-PI-0565 | 80 | 5K | OG1 | C3 | PEL-ZAU-T-034 | 2024-01-12 |  | 2023-11-06 | 2023-11-16 | 2023-11-19 | 2023-12-06 | 2023-12-15 |  | 2024-01-26 |  | 2024-02-07 | 2024-02-09 | 1.4 | 260 | 388 | Virgil Frinculescu |  |  |  | Modificaiton of the Valve arrangement |  | 0 | SEP | SEP |  | 3
41977 | GV-0-244-004-80-SD5 | 3 | true | CH06822004-BD-PI-0565 | 80 | 5K | OG1 | C3 | PEL-ZAU-T-034 | 2024-01-12 |  | 2023-11-06 | 2023-11-16 | 2023-11-19 | 2023-12-06 | 2023-12-15 |  | 2024-01-26 |  | 2024-01-16 | 2024-02-09 | 0.1 | 260 | 388 | Virgil Frinculescu |  |  |  | No change |  | 0 | SEP | SEP |  | 3
36753 | KR-0-216-036-50-SD5 | 2 | false | CH06822004-BD-PI-0607 | 50 | 5K | OG1 | C2 | T01578 | 2023-10-01 |  | 2023-11-06 | 2023-11-08 | 2023-11-19 | 2023-12-19 | 2024-01-12 |  | 2024-01-18 |  |  | 2024-01-29 | 3.2 | 260 | 393 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 3
36754 | KR-0-216-036-50-SD5 | 2 | false | CH06822004-BD-PI-0607 | 50 | 5K | OG1 | C2 | T01578 | 2023-10-01 |  | 2023-11-06 | 2023-11-08 | 2023-11-19 | 2023-12-13 | 2024-01-12 |  | 2024-01-18 |  |  | 2024-01-29 | 5 | 260 | 393 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 3
36755 | KR-0-216-036-50-SD5 | 2 | false | CH06822004-BD-PI-0607 | 50 | 5K | OG1 | C2 | T01578 | 2023-10-01 |  | 2023-11-06 | 2023-11-08 | 2023-11-19 | 2023-12-19 | 2024-01-12 |  | 2024-01-18 |  |  | 2024-01-29 | 15.9 | 260 | 393 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 3
41928 | KR-0-216-036-50-SD5 | 3 | true | CH06822004-BD-PI-0607 | 50 | 5K | OG1 | C2 | PEL-ZAU-T-036 | 2024-01-12 |  | 2023-11-06 | 2023-11-08 | 2023-11-19 | 2023-12-19 | 2024-01-12 |  | 2024-01-18 |  |  | 2024-01-29 | 2.8 | 260 | 393 | Virgil Frinculescu |  |  |  | Updated Positions of Thermowells etc. |  | 0 | SEP | SEP |  | 3
41929 | KR-0-216-036-50-SD5 | 3 | true | CH06822004-BD-PI-0607 | 50 | 5K | OG1 | C2 | PEL-ZAU-T-036 | 2024-01-12 |  | 2023-11-06 | 2023-11-08 | 2023-11-19 | 2023-12-13 | 2024-01-12 |  | 2024-01-18 |  |  | 2024-01-29 | 5.4 | 260 | 393 | Virgil Frinculescu |  |  |  | No change |  | 0 | SEP | SEP |  | 3
41930 | KR-0-216-036-50-SD5 | 3 | true | CH06822004-BD-PI-0607 | 50 | 5K | OG1 | C2 | PEL-ZAU-T-036 | 2024-01-12 |  | 2023-11-06 | 2023-11-08 | 2023-11-19 | 2023-12-19 | 2024-01-12 |  | 2024-01-18 |  |  | 2024-01-29 | 15.9 | 260 | 393 | Virgil Frinculescu |  |  |  | No change |  | 0 | SEP | SEP |  | 3
36756 | KR-0-216-040-50-SD5 | 2 | false | CH06822004-BD-PI-0607 | 50 | 5K | OG1 | C2 | T01578 | 2023-10-01 |  | 2023-11-06 | 2023-11-12 |  | 2023-12-19 | 2024-01-12 |  | 2024-01-18 |  |  |  | 1.1 | 260 | 393 | Attila Henter | [5 empty] | 0 | SEP | SEP |  | 3
36757 | KR-0-216-040-50-SD5 | 2 | false | CH06822004-BD-PI-0607 | 50 | 5K | OG1 | C2 | T01578 | 2023-10-01 |  | 2023-11-06 | 2023-11-12 | 2023-11-19 | 2023-12-20 | 2024-01-12 |  | 2024-01-18 |  |  |  | 3.4 | 260 | 393 | Attila Henter | [5 empty] | 0 | SEP | SEP |  | 3
36758 | KR-0-216-040-50-SD5 | 2 | false | CH06822004-BD-PI-0607 | 50 | 5K | OG1 | C2 | T01578 | 2023-10-01 |  | 2023-11-06 | 2023-11-12 | 2023-11-19 | 2023-12-20 | 2024-01-12 |  | 2024-01-18 |  |  |  | 8.1 | 260 | 393 | Attila Henter | [5 empty] | 0 | SEP | SEP |  | 3
36759 | KR-0-216-040-50-SD5 | 2 | false | CH06822004-BD-PI-0607 | 50 | 5K | OG1 | C2 | T01578 | 2023-10-01 |  | 2023-11-06 | 2023-11-12 | 2023-11-19 | 2023-12-19 | 2024-01-12 |  | 2024-01-18 |  |  |  | 8.9 | 260 | 393 | Attila Henter | [5 empty] | 0 | SEP | SEP |  | 3
41938 | KR-0-216-040-50-SD5 | 3 | true | CH06822004-BD-PI-0607 | 50 | 5K | OG1 | C2 | PEL-ZAU-T-036 | 2024-01-12 |  | 2023-11-06 | 2023-11-12 |  | 2023-12-19 | 2024-01-12 |  | 2024-01-18 | 2024-02-07 | 2024-02-09 | 2024-02-20 | 1 | 260 | 393 | Virgil Frinculescu |  |  |  | Updated Positions of Thermowells etc. + Extra Pipe DN20 |  | 0 | SEP | SEP |  | 3
41939 | KR-0-216-040-50-SD5 | 3 | true | CH06822004-BD-PI-0607 | 50 | 5K | OG1 | C2 | PEL-ZAU-T-036 | 2024-01-12 |  | 2023-11-06 | 2023-11-12 | 2023-11-19 | 2023-12-20 | 2024-01-12 |  | 2024-01-18 | 2024-02-07 | 2024-02-09 | 2024-02-12 | 3 | 260 | 393 | Virgil Frinculescu |  |  |  | No change |  | 0 | SEP | SEP |  | 3
41940 | KR-0-216-040-50-SD5 | 3 | true | CH06822004-BD-PI-0607 | 50 | 5K | OG1 | C2 | PEL-ZAU-T-036 | 2024-01-12 |  | 2023-11-06 | 2023-11-12 | 2023-11-19 | 2023-12-20 | 2024-01-12 |  | 2024-01-18 |  | 2024-02-09 | 2024-02-12 | 5.8 | 260 | 393 | Virgil Frinculescu |  |  |  | No change |  | 0 | SEP | SEP |  | 3
41941 | KR-0-216-040-50-SD5 | 3 | true | CH06822004-BD-PI-0607 | 50 | 5K | OG1 | C2 | PEL-ZAU-T-036 | 2024-01-12 |  | 2023-11-06 | 2023-11-12 | 2023-11-19 | 2023-12-19 | 2024-01-12 |  | 2024-01-18 | 2024-02-07 | 2024-02-09 | 2024-02-12 | 12.2 | 260 | 393 | Virgil Frinculescu |  |  |  | No change |  | 0 | SEP | SEP |  | 3
36760 | KV-0-216-035-50-SD5 | 2 | false | CH06822004-BD-PI-0607 | 50 | 5K | OG1 | C2 | T01578 | 2023-10-01 |  | 2023-11-06 | 2023-11-08 | 2023-11-19 | 2023-12-11 | 2023-12-15 |  | 2024-01-10 |  |  |  | 16.7 | 260 | 394 | Attila Henter | [5 empty] | 0 | SEP | SEP |  | 3
36761 | KV-0-216-035-50-SD5 | 2 | false | CH06822004-BD-PI-0607 | 50 | 5K | OG1 | C2 | T01578 | 2023-10-01 |  | 2023-11-06 | 2023-11-08 | 2023-11-19 | 2023-12-11 | 2023-12-15 |  | 2024-01-10 |  |  | 2024-01-26 | 5.2 | 260 | 394 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 3
36762 | KV-0-216-035-50-SD5 | 2 | false | CH06822004-BD-PI-0607 | 50 | 5K | OG1 | C2 | T01578 | 2023-10-01 |  | 2023-11-06 | 2023-11-08 | 2023-11-19 | 2023-12-11 | 2023-12-15 |  | 2024-01-10 |  |  |  | 3.4 | 260 | 394 | Attila Henter | [5 empty] | 0 | SEP | SEP |  | 3
41871 | KV-0-216-035-50-SD5 | 3 | true | CH06822004-BD-PI-0607 | 50 | 5K | OG1 | C2 | PEL-ZAU-T-035 | 2024-01-13 |  | 2023-11-06 | 2023-11-08 | 2023-11-19 | 2023-12-11 | 2023-12-15 |  | 2024-01-10 |  |  | 2024-01-26 | 18.8 | 260 | 394 | Virgil Frinculescu |  |  |  | No change |  | 0 | SEP | SEP |  | 3
41872 | KV-0-216-035-50-SD5 | 3 | true | CH06822004-BD-PI-0607 | 50 | 5K | OG1 | C2 | PEL-ZAU-T-035 | 2024-01-13 |  | 2023-11-06 | 2023-11-08 | 2023-11-19 | 2023-12-11 | 2023-12-15 |  | 2024-01-10 |  |  | 2024-01-26 | 3.5 | 260 | 394 | Virgil Frinculescu |  |  |  | No change |  | 0 | SEP | SEP |  | 3
41873 | KV-0-216-035-50-SD5 | 3 | true | CH06822004-BD-PI-0607 | 50 | 5K | OG1 | C2 | PEL-ZAU-T-035 | 2024-01-13 |  | 2023-11-06 | 2023-11-08 | 2023-11-19 | 2023-12-11 | 2023-12-15 |  | 2024-01-10 |  |  | 2024-03-05 | 2.8 | 260 | 394 | Virgil Frinculescu |  |  |  | Updated Positions of Thermowells etc. |  | 0 | SEP | SEP |  | 3
41874 | KV-0-216-035-50-SD5 | 3 | true | CH06822004-BD-PI-0607 | 50 | 5K | OG1 | C2 | PEL-ZAU-T-035 | 2024-01-13 | [7 empty] | 2024-01-10 |  | 2024-02-07 | 2024-02-26 | 2.3 | 260 | 394 | Virgil Frinculescu |  |  |  | The Butterfly & Regulation valve must be moved. |  | 0 | SEP | SEP |  | 3
36763 | KV-0-216-038-50-SD5 | 2 | false | CH06822004-BD-PI-0607 | 50 | 5K | OG1 | C2 | T01578 | 2023-10-01 |  | 2023-11-06 | 2023-11-08 | 2023-11-19 | 2023-12-11 | 2023-12-15 |  | 2024-01-18 |  |  | 2024-02-07 | 7.2 | 260 | 394 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 3
36764 | KV-0-216-038-50-SD5 | 2 | false | CH06822004-BD-PI-0607 | 50 | 5K | OG1 | C2 | T01578 | 2023-10-01 |  | 2023-11-06 | 2023-11-08 | 2023-11-19 | 2023-12-12 | 2024-01-12 |  | 2024-01-18 |  |  | 2024-02-07 | 7.6 | 260 | 394 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 3
36765 | KV-0-216-038-50-SD5 | 2 | false | CH06822004-BD-PI-0607 | 50 | 5K | OG1 | C2 | T01578 | 2023-10-01 |  | 2023-11-06 | 2023-11-08 | 2023-11-19 | 2023-12-19 | 2024-01-12 |  | 2024-01-18 |  |  | 2024-02-07 | 5.4 | 260 | 394 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 3
36766 | KV-0-216-038-50-SD5 | 2 | false | CH06822004-BD-PI-0607 | 50 | 5K | OG1 | C2 | T01578 | 2023-10-01 |  | 2023-11-06 | 2023-11-10 | 2023-11-19 | 2023-12-01 | 2024-01-12 |  | 2024-01-18 |  |  | 2024-02-07 | 3.1 | 260 | 394 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 3
36767 | KV-0-216-038-50-SD5 | 2 | false | CH06822004-BD-PI-0607 | 50 | 5K | OG1 | C2 | T01578 | 2023-10-01 |  | 2023-11-06 | 2023-11-08 | 2023-11-19 | 2023-12-19 | 2024-01-12 |  | 2024-01-18 |  |  | 2024-02-07 | 1.1 | 260 | 394 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 3
41881 | KV-0-216-038-50-SD5 | 3 | true | CH06822004-BD-PI-0607 | 50 | 5K | OG1 | C2 | PEL-ZAU-T-035 | 2024-01-13 |  | 2023-11-06 | 2023-11-08 | 2023-11-19 | 2023-12-11 | 2023-12-15 |  | 2024-01-18 |  |  | 2024-02-07 | 7.2 | 260 | 394 | Virgil Frinculescu |  |  |  | No change |  | 0 | SEP | SEP |  | 3
41882 | KV-0-216-038-50-SD5 | 3 | true | CH06822004-BD-PI-0607 | 50 | 5K | OG1 | C2 | PEL-ZAU-T-035 | 2024-01-13 |  | 2023-11-06 | 2023-11-08 | 2023-11-19 | 2023-12-12 | 2024-01-12 |  | 2024-01-18 |  |  | 2024-02-07 | 7.6 | 260 | 394 | Virgil Frinculescu |  |  |  | No change |  | 0 | SEP | SEP |  | 3
41883 | KV-0-216-038-50-SD5 | 3 | true | CH06822004-BD-PI-0607 | 50 | 5K | OG1 | C2 | PEL-ZAU-T-035 | 2024-01-13 |  | 2023-11-06 | 2023-11-08 | 2023-11-19 | 2023-12-19 | 2024-01-12 |  | 2024-01-18 |  |  | 2024-02-07 | 5.4 | 260 | 394 | Virgil Frinculescu |  |  |  | No change |  | 0 | SEP | SEP |  | 3
41884 | KV-0-216-038-50-SD5 | 3 | true | CH06822004-BD-PI-0607 | 50 | 5K | OG1 | C2 | PEL-ZAU-T-035 | 2024-01-13 |  | 2023-11-06 | 2023-11-10 | 2023-11-19 | 2023-12-01 | 2024-01-12 |  | 2024-01-18 |  |  | 2024-02-07 | 3.1 | 260 | 394 | Virgil Frinculescu |  |  |  | No change |  | 0 | SEP | SEP |  | 3
41885 | KV-0-216-038-50-SD5 | 3 | true | CH06822004-BD-PI-0607 | 50 | 5K | OG1 | C2 | PEL-ZAU-T-035 | 2024-01-13 |  | 2023-11-06 | 2023-11-08 | 2023-11-19 | 2023-12-19 | 2024-01-12 |  | 2024-01-18 |  |  | 2024-02-07 | 1.1 | 260 | 394 | Virgil Frinculescu |  |  |  | The Butterfly & Regulation valve must be moved. |  | 0 | SEP | SEP |  | 3
36768 | US4-0-244-007-15-SD6 | 2 | false | CH06822004-BD-PI-0586 | 15 | 5K | OG1 | H5 | T01578 | 2023-10-01 |  | 2023-11-06 | 2023-11-12 | 2023-11-19 | 2023-12-20 | 2024-01-12 |  | 2024-02-07 | 2024-02-13 |  |  | 0.3 | 261 | 410 | Jozef Kotul | [5 empty] | 0 | SEP | SEP |  | 3
45367 | US4-0-244-007-15-SD6 | 3 | true | CH06822004-BD-PI-0586 | 15 | 5K | OG1 | H5 | T-060 | 2024-03-05 |  | 2023-11-06 | 2023-11-12 | 2023-11-19 | 2023-12-20 | 2024-01-12 |  | 2024-03-22 | 2024-02-13 |  | 2024-04-12 | 3.6 | 261 | 410 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45368 | US4-0-244-007-15-SD6 | 3 | true | CH06822004-BD-PI-0586 | 15 | 5K | OG1 | H5 | T-060 | 2024-03-05 | [7 empty] | 2024-03-22 |  |  | 2024-04-12 | 3.3 | 261 | 410 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
36769 | US4-0-244-004-32-SD6 | 2 | false | CH06822004-BD-PI-0586 | 32 | 5K | OG1 | H5 | T01578 | 2023-10-01 |  | 2023-11-06 | 2023-11-09 | 2023-11-19 | 2023-12-11 | 2024-01-12 |  | 2024-01-31 |  |  |  | 4.2 | 261 | 410 | Jozef Kotul | [5 empty] | 0 | SEP | SEP |  | 3
36770 | US4-0-244-004-32-SD6 | 2 | false | CH06822004-BD-PI-0586 | 32 | 5K | OG1 | H5 | T01578 | 2023-10-01 |  | 2023-11-06 | 2023-11-09 | 2023-11-19 | 2023-12-20 | 2024-01-12 |  | 2024-01-31 |  |  |  | 10.6 | 261 | 410 | Jozef Kotul | [5 empty] | 0 | SEP | SEP |  | 3
43832 | US4-0-244-004-32-SD6 | 3 | true | CH06822004-BD-PI-0586 | 32 | 5K | OG1 | H5 | T-048 | 2024-01-30 |  | 2023-11-06 | 2023-11-09 | 2023-11-19 | 2023-12-11 | 2024-01-12 |  | 2024-02-07 |  | 2024-03-23 | 2024-05-29 | 13.9 | 261 | 410 | Virgil Frinculescu |  |  |  | Latest rev. 3 is added to the w.map. |  | 0 | SEP | SEP
43833 | US4-0-244-004-32-SD6 | 3 | true | CH06822004-BD-PI-0586 | 32 | 5K | OG1 | H5 | T-048 | 2024-01-30 |  | 2023-11-06 | 2023-11-09 | 2023-11-19 | 2023-12-20 | 2024-01-12 |  | 2024-02-07 |  |  | 2024-07-10 | 3.2 | 261 | 410 | Virgil Frinculescu |  |  |  | Latest rev. 3 is added to the w.map. |  | 0 | SEP | SEP
36936 | ABP-7-701-012-80-SD | 1 | true | CH06822004-BD-PI-0495 | 80 | 5K | UG | N/A | T02043 | 2023-10-02 | [7 empty] | 2024-04-25 |  |  | 2024-05-07 | 7.9 | 271 | 362 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 0
36937 | ABP-7-701-013-80-SD | 1 | false | CH06822004-BD-PI-0495 | 80 | 5K | UG | N/A | T02043 | 2023-10-02 | [11 empty] | 6.1 | 271 | 362 |  |  |  |  | NEW ISO released just for information. OLD revision need to redline acc. to new ISO |  | 0 | SEP | SEP |  | 0
43465 | ABP-7-701-013-80-SD | 2 | true | CH06822004-BD-PI-0495 | 80 | 5K | UG | N/A | T-078 | 2024-04-26 | [7 empty] | 2024-05-08 |  |  | 2024-05-11 | 6.1 | 271 | 362 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
43468 | ABP-7-701-013-80-SD | 2 | false | CH06822004-BD-PI-0495 | 80 | 5K | UG | N/A | T-047 | 2024-01-25 | [12 empty] | 271 | 362 | [6 empty] | 0 | SEP | SEP
36938 | CO2F-7-600-001-25-SP1 | 1 | true | CH06822004-BD-PI-0449 | 25 | 5K | UG | N/A | T02043 | 2023-10-02 |  |  | 2023-11-22 | [7 empty] | 2024-01-31 | 3.1 | 264 | 369 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 0
37056 | CO2F-7-600-001-25-SP1 | 1 | true | CH06822004-BD-PI-0449 | 25 | 5K | UG | N/A | T02043 | 2023-10-02 |  |  | 2023-11-22 | [7 empty] | 2023-12-10 | 35.3 | 264 | 369 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 0
37057 | CO2F-7-600-001-25-SP1 | 1 | true | CH06822004-BD-PI-0449 | 25 | 5K | UG | N/A | T02043 | 2023-10-02 |  |  | 2023-11-22 | [7 empty] | 2023-12-18 | 11.7 | 264 | 369 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 0
36941 | CS-7-201-001-65-SP1 | 1 | true | CH06822004-BD-PI-1179 | 65 | 5K | UG | H2 | T02043 | 2023-10-02 | [7 empty] | 2024-02-12 | 2024-03-23 |  | 2024-07-16 | 5.6 | 264 | 371 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 0
36942 | CS-7-201-001-65-SP1 | 1 | true | CH06822004-BD-PI-1179 | 65 | 5K | UG | H2 | T02043 | 2023-10-02 | [7 empty] | 2024-02-12 |  |  | 2024-02-26 | 23.7 | 264 | 371 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 0
36943 | CS-7-201-001-65-SP1 | 1 | true | CH06822004-BD-PI-1179 | 65 | 5K | UG | H2 | T02043 | 2023-10-02 | [7 empty] | 2024-02-12 | 2024-03-23 |  | 2024-03-27 | 7.3 | 264 | 371 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 0
36944 | CS-7-201-001-65-SP1 | 1 | true | CH06822004-BD-PI-1179 | 65 | 5K | UG | H2 | T02043 | 2023-10-02 | [7 empty] | 2024-02-12 |  |  | 2024-02-29 | 11.1 | 264 | 371 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 0
36945 | CS-7-201-001-65-SP1 | 1 | true | CH06822004-BD-PI-1179 | 65 | 5K | UG | H2 | T02043 | 2023-10-02 | [7 empty] | 2024-02-12 |  |  | 2024-03-05 | 11.2 | 264 | 371 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 0
36946 | CS-7-201-001-65-SP1 | 1 | true | CH06822004-BD-PI-1179 | 65 | 5K | UG | H2 | T02043 | 2023-10-02 | [7 empty] | 2024-02-12 |  |  | 2024-03-25 | 1.1 | 264 | 371 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 0
36947 | DK4-0-600-001-25-SD6 | 1 | true | CH06822004-BD-PI-0558 | 25 | 5K | UG | H2 | T02043 | 2023-10-02 | [7 empty] | 2024-01-16 |  |  | 2024-02-06 | 6.1 | 261 | 375 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 0
36948 | DK4-0-600-003-25-SD6 | 1 | true | CH06822004-BD-PI-0558 | 25 | 5K | UG | H2 | T02043 | 2023-10-02 | [7 empty] | 2024-01-15 |  |  | 2024-01-26 | 4.3 | 261 | 375 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 0
36949 | DK4-0-600-008-15-SD6 | 1 | true | CH06822004-BD-PI-0558 | 15 | 5K | UG | H2 | T02043 | 2023-10-02 | [7 empty] | 2024-01-15 |  |  | 2024-02-23 | 2.6 | 261 | 375 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 0
36950 | DK4-0-600-008-15-SD6 | 1 | true | CH06822004-BD-PI-0558 | 15 | 5K | UG | H2 | T02043 | 2023-10-02 | [7 empty] | 2024-01-15 |  |  | 2024-02-23 | 5.9 | 261 | 375 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 0
36951 | DKA-7-400-002-40-SD | 1 | true | CH06822004-BD-PI-1201 | 40 | 5K | UG | H3 | T02043 | 2023-10-02 | [7 empty] | 2024-02-06 |  |  | 2024-02-15 | 10.7 | 271 | 376 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 0
36952 | DKA-7-400-001-40-SD | 1 | true | CH06822004-BD-PI-1201 | 40 | 5K | UG | H3 | T02043 | 2023-10-02 | [7 empty] | 2024-02-06 |  |  | 2024-02-09 | 17.5 | 271 | 376 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 0
36953 | DKA-7-400-001-40-SD | 1 | true | CH06822004-BD-PI-1201 | 40 | 5K | UG | H3 | T02043 | 2023-10-02 | [7 empty] | 2024-02-06 |  |  | 2024-02-09 | 7.5 | 271 | 376 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 0
36954 | DKA-7-400-001-40-SD | 1 | true | CH06822004-BD-PI-1201 | 40 | 5K | UG | H3 | T02043 | 2023-10-02 | [7 empty] | 2024-02-06 |  |  | 2024-02-13 | 10.2 | 271 | 376 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 0
36955 | DKA-7-400-001-40-SD | 1 | true | CH06822004-BD-PI-1201 | 40 | 5K | UG | H3 | T02043 | 2023-10-02 | [7 empty] | 2024-02-06 |  |  | 2024-02-13 | 8.7 | 271 | 376 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 0
36956 | DKA-7-400-003-25-SD | 1 | true | CH06822004-BD-PI-1201 | 25 | 5K | UG | H3 | T02043 | 2023-10-02 | [7 empty] | 2024-02-06 |  |  | 2024-07-05 | 9 | 271 | 376 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 0
36957 | DKA-7-400-003-25-SD | 1 | true | CH06822004-BD-PI-1201 | 25 | 5K | UG | H3 | T02043 | 2023-10-02 | [7 empty] | 2024-02-06 |  |  | 2024-03-05 | 5.3 | 271 | 376 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 0
36958 | DKA-7-400-003-25-SD | 1 | true | CH06822004-BD-PI-1201 | 25 | 5K | UG | H3 | T02043 | 2023-10-02 | [7 empty] | 2024-02-06 |  |  | 2024-03-05 | 5.7 | 271 | 376 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 0
36959 | DKA-7-400-004-25-SD | 1 | true | CH06822004-BD-PI-1201 | 25 | 5K | UG | H3 | T02043 | 2023-10-02 | [7 empty] | 2024-02-06 |  |  | 2024-02-20 | 5.6 | 271 | 376 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 0
36960 | DKA-7-400-007-25-SD | 1 | true | CH06822004-BD-PI-1201 | 25 | 5K | UG | H3 | T02043 | 2023-10-02 | [7 empty] | 2024-02-06 |  |  | 2024-02-28 | 10.9 | 271 | 376 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 0
36961 | DKA-7-400-007-25-SD | 1 | true | CH06822004-BD-PI-1201 | 25 | 5K | UG | H3 | T02043 | 2023-10-02 | [7 empty] | 2024-02-06 |  |  | 2024-02-23 | 6.1 | 271 | 376 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 0
36962 | DKS-7-401-001-40-SD | 1 | false |  | 40 | 5K | UG | H3 | T02043 | 2023-10-02 | [11 empty] | 3.7 | 271 | 378 |  | 130 |  | HOLD | HOLD |  | 0 | SEP | SEP |  | 0
43871 | DKS-7-401-001-40-SD | 2 | true |  | 40 | 5K | UG | H3 | T-049 | 2024-01-31 | [7 empty] | 2024-02-14 |  |  | 2024-03-19 | 6.5 | 271 | 378 | Virgil Frinculescu | 130 |  |  |  |  | 0 | SEP | SEP
36963 | DKS-7-401-002-32-SD | 1 | false |  | 32 | 5K | UG | H3 | T02043 | 2023-10-02 | [11 empty] | 2.3 | 271 | 378 |  | 130 |  |  |  |  | 0 | SEP | SEP |  | 0
36964 | DKS-7-401-002-32-SD | 1 | false |  | 32 | 5K | UG | H3 | T02043 | 2023-10-02 | [11 empty] | 6.5 | 271 | 378 |  | 130 |  |  |  |  | 0 | SEP | SEP |  | 0
36965 | DKS-7-401-002-32-SD | 1 | false |  | 32 | 5K | UG | H3 | T02043 | 2023-10-02 | [11 empty] | 10.2 | 271 | 378 |  | 130 |  |  |  |  | 0 | SEP | SEP |  | 0
36966 | DKS-7-401-002-32-SD | 1 | false |  | 32 | 5K | UG | H3 | T02043 | 2023-10-02 | [11 empty] | 7.3 | 271 | 378 |  | 130 |  |  |  |  | 0 | SEP | SEP |  | 0
36967 | DKS-7-401-002-32-SD | 1 | false |  | 32 | 5K | UG | H3 | T02043 | 2023-10-02 | [11 empty] | 11.5 | 271 | 378 |  | 130 |  | HOLD | HOLD |  | 0 | SEP | SEP |  | 0
43872 | DKS-7-401-002-32-SD | 2 | true |  | 32 | 5K | UG | H3 | T-049 | 2024-01-31 | [7 empty] | 2024-02-14 |  |  | 2024-03-20 | 2.3 | 271 | 378 | Virgil Frinculescu | 130 |  |  |  |  | 0 | SEP | SEP
43873 | DKS-7-401-002-32-SD | 2 | true |  | 32 | 5K | UG | H3 | T-049 | 2024-01-31 | [7 empty] | 2024-02-14 |  |  | 2024-03-20 | 6.5 | 271 | 378 | Virgil Frinculescu | 130 |  |  |  |  | 0 | SEP | SEP
43874 | DKS-7-401-002-32-SD | 2 | true |  | 32 | 5K | UG | H3 | T-049 | 2024-01-31 | [7 empty] | 2024-02-14 |  |  | 2024-03-20 | 10.2 | 271 | 378 | Virgil Frinculescu | 130 |  |  |  |  | 0 | SEP | SEP
43875 | DKS-7-401-002-32-SD | 2 | true |  | 32 | 5K | UG | H3 | T-049 | 2024-01-31 | [7 empty] | 2024-02-14 |  |  | 2024-03-20 | 7.3 | 271 | 378 | Virgil Frinculescu | 130 |  |  |  |  | 0 | SEP | SEP
43876 | DKS-7-401-002-32-SD | 2 | true |  | 32 | 5K | UG | H3 | T-049 | 2024-01-31 | [7 empty] | 2024-02-14 |  |  | 2024-03-19 | 9.7 | 271 | 378 | Virgil Frinculescu | 130 |  |  |  |  | 0 | SEP | SEP
36968 | DKS-7-401-003-32-SD | 1 | false |  | 32 | 5K | UG | H3 | T02043 | 2023-10-02 | [11 empty] | 4 | 271 | 378 | [6 empty] | 0 | SEP | SEP |  | 0
36969 | DKS-7-401-003-32-SD | 1 | false |  | 32 | 5K | UG | H3 | T02043 | 2023-10-02 | [11 empty] | 10.4 | 271 | 378 | [6 empty] | 0 | SEP | SEP |  | 0
42409 | DKS-7-401-003-32-SD | 2 | true |  | 32 | 5K | UG | H3 | PEL-ZAU-T-040 | 2024-01-17 | [7 empty] | 2024-02-14 |  |  | 2024-03-14 | 2.8 | 271 | 378 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
42410 | DKS-7-401-003-32-SD | 2 | true |  | 32 | 5K | UG | H3 | PEL-ZAU-T-040 | 2024-01-17 | [7 empty] | 2024-02-14 |  |  | 2024-03-14 | 8.6 | 271 | 378 | Virgil Frinculescu |  |  |  | Latest Revision added to the folder "00_All Isometrics" |  | 0 | SEP | SEP
42411 | DKS-7-401-003-32-SD | 2 | true |  | 32 | 5K | UG | H3 | PEL-ZAU-T-040 | 2024-01-17 | [7 empty] | 2024-02-14 |  |  | 2024-03-05 | 6.7 | 271 | 378 | Virgil Frinculescu |  |  |  | Latest Revision added to the folder "00_All Isometrics" |  | 0 | SEP | SEP
36970 | DKS-7-401-011-15-SD | 1 | false |  | 15 | 5K | UG | H3 | T02043 | 2023-10-02 | [11 empty] | 1.2 | 271 | 378 |  | 130 |  | HOLD | HOLD |  | 0 | SEP | SEP |  | 0
43877 | DKS-7-401-011-15-SD | 2 | true |  | 15 | 5K | UG | H3 | T-049 | 2024-01-31 | [7 empty] | 2024-02-14 |  |  | 2024-04-03 | 0.6 | 271 | 378 | Virgil Frinculescu | 130 |  |  |  |  | 0 | SEP | SEP
36971 | DKS-7-401-012-15-SD | 1 | false |  | 15 | 5K | UG | H3 | T02043 | 2023-10-02 | [11 empty] | 5.2 | 271 | 378 | [6 empty] | 0 | SEP | SEP |  | 0
42414 | DKS-7-401-012-15-SD | 2 | true |  | 15 | 5K | UG | H3 | PEL-ZAU-T-040 | 2024-01-17 | [7 empty] | 2024-02-14 |  |  | 2024-03-19 | 14.6 | 271 | 378 | Virgil Frinculescu |  |  |  | Latest Revision added to the folder "00_All Isometrics" |  | 0 | SEP | SEP
36972 | DKS-7-401-013-15-SD | 1 | false |  | 15 | 5K | UG | H3 | T02043 | 2023-10-02 | [11 empty] | 5.1 | 271 | 378 | [6 empty] | 0 | SEP | SEP |  | 0
42415 | DKS-7-401-013-15-SD | 2 | true |  | 15 | 5K | UG | H3 | PEL-ZAU-T-040 | 2024-01-17 | [7 empty] | 2024-02-14 |  |  | 2024-03-14 | 3.4 | 271 | 378 | Virgil Frinculescu |  |  |  | Latest Revision added to the folder "00_All Isometrics" |  | 0 | SEP | SEP
36973 | DLF-7-831-001-50-SP1 | 1 | false | CH06822004-BD-PI-0537 | 50 | 5K | UG | N/A | T02043 | 2023-10-02 |  |  | 2023-11-22 | [8 empty] | 0.2 | 264 | 380 | Jozef Kotul | [5 empty] | 0 | SEP | SEP |  | 0
36974 | DLF-7-831-001-50-SP1 | 1 | false | CH06822004-BD-PI-0537 | 50 | 5K | UG | N/A | T02043 | 2023-10-02 |  |  | 2023-11-22 | [7 empty] | 2024-02-06 | 1.4 | 264 | 380 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 0
36975 | DLF-7-831-001-50-SP1 | 1 | false | CH06822004-BD-PI-0537 | 50 | 5K | UG | N/A | T02043 | 2023-10-02 |  |  | 2023-11-22 | [7 empty] | 2024-02-06 | 29.8 | 264 | 380 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 0
36976 | DLF-7-831-001-50-SP1 | 1 | false | CH06822004-BD-PI-0537 | 50 | 5K | UG | N/A | T02043 | 2023-10-02 |  |  | 2023-11-22 | [7 empty] | 2024-01-31 | 12.5 | 264 | 380 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 0
42076 | DLF-7-831-001-50-SP1 | 2 | false | CH06822004-BD-PI-0537 | 50 | 5K | UG | N/A | PEL-ZAU-T-037 | 2024-01-15 |  |  | 2023-11-22 |  |  |  |  | 2024-01-31 | 2024-03-23 |  |  | 0.4 | 264 | 380 | Jozef Kotul |  |  |  | not prefabricated ==> No impact |  | 0 | SEP | SEP |  | 0
42077 | DLF-7-831-001-50-SP1 | 2 | false | CH06822004-BD-PI-0537 | 50 | 5K | UG | N/A | PEL-ZAU-T-037 | 2024-01-15 |  |  | 2023-11-22 |  |  |  |  | 2024-01-31 |  |  | 2024-02-06 | 1.2 | 264 | 380 | Virgil Frinculescu |  |  |  | not prefabricated ==> No impact |  | 0 | SEP | SEP |  | 0
42078 | DLF-7-831-001-50-SP1 | 2 | false | CH06822004-BD-PI-0537 | 50 | 5K | UG | N/A | PEL-ZAU-T-037 | 2024-01-15 |  |  | 2023-11-22 |  |  |  |  | 2024-01-31 |  | 2024-01-05 | 2024-02-06 | 29.1 | 264 | 380 | Virgil Frinculescu |  |  |  | Minor change |  | 0 | SEP | SEP |  | 0
42079 | DLF-7-831-001-50-SP1 | 2 | false | CH06822004-BD-PI-0537 | 50 | 5K | UG | N/A | PEL-ZAU-T-037 | 2024-01-15 |  |  | 2023-11-22 |  |  |  |  | 2024-01-31 |  |  | 2024-01-31 | 12.5 | 264 | 380 | Virgil Frinculescu |  |  |  | No change |  | 0 | SEP | SEP |  | 0
51885 | DLF-7-831-001-50-SP1 | 3 | true | CH06822004-BD-PI-0537 | 50 | 5K | UG | N/A | T-083 | 2024-05-21 |  |  | 2023-11-22 |  |  |  |  | 2024-01-31 | 2024-03-23 |  | 2024-05-25 | 0.4 | 264 | 380 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
51886 | DLF-7-831-001-50-SP1 | 3 | true | CH06822004-BD-PI-0537 | 50 | 5K | UG | N/A | T-083 | 2024-05-21 |  |  | 2023-11-22 |  |  |  |  | 2024-01-31 |  | 2024-05-21 | 2024-05-22 | 1.2 | 264 | 380 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
51887 | DLF-7-831-001-50-SP1 | 3 | true | CH06822004-BD-PI-0537 | 50 | 5K | UG | N/A | T-083 | 2024-05-21 |  |  | 2023-11-22 |  |  |  |  | 2024-01-31 |  | 2024-05-21 | 2024-05-22 | 29.1 | 264 | 380 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
51888 | DLF-7-831-001-50-SP1 | 3 | true | CH06822004-BD-PI-0537 | 50 | 5K | UG | N/A | T-083 | 2024-05-21 |  |  | 2023-11-22 |  |  |  |  | 2024-01-31 |  | 2024-05-21 | 2024-05-22 | 12.5 | 264 | 380 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
36977 | DLP-7-301-005-50-SP1 | 1 | true | CH06822004-BD-PI-0544 | 50 | 5K | UG | N/A | T02043 | 2023-10-02 |  |  | 2023-11-22 | [7 empty] | 2024-01-23 | 3.4 | 264 | 382 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 0
36978 | DLP-7-301-005-50-SP1 | 1 | true | CH06822004-BD-PI-0544 | 50 | 5K | UG | N/A | T02043 | 2023-10-02 |  |  | 2023-11-22 | [7 empty] | 2024-01-05 | 30.8 | 264 | 382 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 0
36979 | DLP-7-301-005-50-SP1 | 1 | true | CH06822004-BD-PI-0544 | 50 | 5K | UG | N/A | T02043 | 2023-10-02 |  |  | 2023-11-22 | [7 empty] | 2024-01-23 | 12.9 | 264 | 382 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 0
36980 | GV-0-244-002-80-SD5 | 1 | false | CH06822004-BD-PI-0565 | 80 | 5K | UG | C3 | T02043 | 2023-10-02 |  |  | 2023-11-22 | [8 empty] | 0.5 | 260 | 388 | Attila Henter | [5 empty] | 0 | SEP | SEP |  | 0
36981 | GV-0-244-002-80-SD5 | 1 | false | CH06822004-BD-PI-0565 | 80 | 5K | UG | C3 | T02043 | 2023-10-02 |  |  | 2023-11-22 | [8 empty] | 0.5 | 260 | 388 | Attila Henter | [5 empty] | 0 | SEP | SEP |  | 0
36985 | GV-0-244-002-80-SD5 | 1 | false | CH06822004-BD-PI-0565 | 80 | 5K | UG | C3 | T02043 | 2023-10-02 |  |  | 2023-11-22 | [8 empty] | 4.8 | 260 | 388 | Attila Henter | [5 empty] | 0 | SEP | SEP |  | 0
36986 | GV-0-244-002-80-SD5 | 1 | false | CH06822004-BD-PI-0565 | 80 | 5K | UG | C3 | T02043 | 2023-10-02 |  |  | 2023-11-22 | [8 empty] | 23.1 | 260 | 388 | Attila Henter | [5 empty] | 0 | SEP | SEP |  | 0
36987 | GV-0-244-002-80-SD5 | 1 | false | CH06822004-BD-PI-0565 | 80 | 5K | UG | C3 | T02043 | 2023-10-02 |  |  | 2023-11-22 | [8 empty] | 11.8 | 260 | 388 | Attila Henter | [5 empty] | 0 | SEP | SEP |  | 0
36988 | GV-0-244-002-80-SD5 | 1 | false | CH06822004-BD-PI-0565 | 80 | 5K | UG | C3 | T02043 | 2023-10-02 |  |  | 2023-11-22 | [5 empty] | 2023-12-18 |  |  | 29.5 | 260 | 388 | Attila Henter | [5 empty] | 0 | SEP | SEP |  | 0
41963 | GV-0-244-002-80-SD5 | 2 | true | CH06822004-BD-PI-0565 | 80 | 5K | UG | C3 | PEL-ZAU-T-034 | 2024-01-12 |  |  | 2023-11-22 | [7 empty] | 2024-03-20 | 1 | 260 | 388 | Virgil Frinculescu |  |  |  | Modification from other ISOs |  | 0 | SEP | SEP
41964 | GV-0-244-002-80-SD5 | 2 | true | CH06822004-BD-PI-0565 | 80 | 5K | UG | C3 | PEL-ZAU-T-034 | 2024-01-12 |  |  | 2023-11-22 | [7 empty] | 2024-02-26 | 4 | 260 | 388 | Virgil Frinculescu |  |  |  | Updated Positions of Thermowells etc. |  | 0 | SEP | SEP
41965 | GV-0-244-002-80-SD5 | 2 | true | CH06822004-BD-PI-0565 | 80 | 5K | UG | C3 | PEL-ZAU-T-034 | 2024-01-12 |  |  | 2023-11-22 | [7 empty] | 2024-03-20 | 1 | 260 | 388 | Virgil Frinculescu |  |  |  | Modification from other ISOs |  | 0 | SEP | SEP
41966 | GV-0-244-002-80-SD5 | 2 | true | CH06822004-BD-PI-0565 | 80 | 5K | UG | C3 | PEL-ZAU-T-034 | 2024-01-12 |  |  | 2023-11-22 | [7 empty] | 2024-02-23 | 14.2 | 260 | 388 | Virgil Frinculescu |  |  |  | Extra Vent Valve to be installed |  | 0 | SEP | SEP
41967 | GV-0-244-002-80-SD5 | 2 | true | CH06822004-BD-PI-0565 | 80 | 5K | UG | C3 | PEL-ZAU-T-034 | 2024-01-12 |  |  | 2023-11-22 | [7 empty] | 2024-05-22 | 10.2 | 260 | 388 | Virgil Frinculescu |  |  |  | Extra Drain Valve to be installed |  | 0 | SEP | SEP
41968 | GV-0-244-002-80-SD5 | 2 | true | CH06822004-BD-PI-0565 | 80 | 5K | UG | C3 | PEL-ZAU-T-034 | 2024-01-12 |  |  | 2023-11-22 | [5 empty] | 2023-12-18 |  | 2024-05-22 | 5 | 260 | 388 | Virgil Frinculescu |  |  |  | No change |  | 0 | SEP | SEP
41969 | GV-0-244-002-80-SD5 | 2 | true | CH06822004-BD-PI-0565 | 80 | 5K | UG | C3 | PEL-ZAU-T-034 | 2024-01-12 | [10 empty] | 2024-02-23 | 28.1 | 260 | 388 | Virgil Frinculescu |  |  |  | No change |  | 0 | SEP | SEP |  | 0
41970 | GV-0-244-002-80-SD5 | 2 | true | CH06822004-BD-PI-0565 | 80 | 5K | UG | C3 | PEL-ZAU-T-034 | 2024-01-12 | [10 empty] | 2024-05-24 | 8.3 | 260 | 388 | Virgil Frinculescu |  |  |  | Updated Positions of Thermowells etc. |  | 0 | SEP | SEP |  | 0
36982 | GV-0-244-001-80-SD5 | 1 | false | CH06822004-BD-PI-0565 | 80 | 5K | UG | C3 | T02043 | 2023-10-02 |  |  | 2023-11-22 | [8 empty] | 0.4 | 260 | 388 | Attila Henter | [5 empty] | 0 | SEP | SEP |  | 0
45529 | GV-0-244-001-80-SD5 | 2 | true | CH06822004-BD-PI-0565 | 80 | 5K | UG | C3 | T-061 | 2024-03-07 |  |  | 2023-11-22 |  |  |  |  | 2024-03-07 |  | 2024-03-26 | 2024-05-24 | 0.7 | 260 | 388 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
36983 | GR-0-244-001-80-SD5 | 1 | false | CH06822004-BD-PI-0565 | 80 | 5K | UG | C3 | T02043 | 2023-10-02 |  |  | 2023-11-22 | [8 empty] | 8.9 | 260 | 387 | Attila Henter | [5 empty] | 0 | SEP | SEP |  | 0
36984 | GR-0-244-001-80-SD5 | 1 | false | CH06822004-BD-PI-0565 | 80 | 5K | UG | C3 | T02043 | 2023-10-02 |  |  | 2023-11-22 | [5 empty] | 2023-12-18 |  |  | 29.2 | 260 | 387 | Attila Henter | [5 empty] | 0 | SEP | SEP |  | 0
41953 | GR-0-244-001-80-SD5 | 2 | true | CH06822004-BD-PI-0565 | 80 | 5K | UG | C3 | PEL-ZAU-T-034 | 2024-01-12 |  |  | 2023-11-22 | [7 empty] | 2024-02-23 | 29.8 | 260 | 387 | Virgil Frinculescu |  |  |  | Updated Positions of Thermowells etc. |  | 0 | SEP | SEP |  | 0
41954 | GR-0-244-001-80-SD5 | 2 | true | CH06822004-BD-PI-0565 | 80 | 5K | UG | C3 | PEL-ZAU-T-034 | 2024-01-12 |  |  | 2023-11-22 | [5 empty] | 2023-12-18 |  | 2024-03-05 | 8.5 | 260 | 387 | Virgil Frinculescu |  |  |  | Extra Drain Valve to be installed |  | 0 | SEP | SEP |  | 0
36989 | KR-0-216-001-125-SD5 | 1 | false | CH06822004-BD-PI-0607 | 125 | 5K | UG | C2 | T02043 | 2023-10-02 | [7 empty] | 2023-12-06 |  |  |  | 5.8 | 260 | 393 | [6 empty] | 0 | SEP | SEP |  | 0
36990 | KR-0-216-001-125-SD5 | 1 | false | CH06822004-BD-PI-0607 | 125 | 5K | UG | C2 | T02043 | 2023-10-02 | [7 empty] | 2023-12-06 |  |  |  | 18.7 | 260 | 393 | [6 empty] | 0 | SEP | SEP |  | 0
36991 | KR-0-216-001-125-SD5 | 1 | false | CH06822004-BD-PI-0607 | 125 | 5K | UG | C2 | T02043 | 2023-10-02 | [7 empty] | 2023-12-06 |  |  |  | 5.1 | 260 | 393 | [6 empty] | 0 | SEP | SEP |  | 0
36992 | KR-0-216-001-125-SD5 | 1 | false | CH06822004-BD-PI-0607 | 125 | 5K | UG | C2 | T02043 | 2023-10-02 | [7 empty] | 2023-12-06 |  |  |  | 21.8 | 260 | 393 | [6 empty] | 0 | SEP | SEP |  | 0
43453 | KR-0-216-001-125-SD5 | 3 | true | CH06822004-BD-PI-0607 | 125 | 5K | UG | C2 | T-079 | 2024-04-26 | [7 empty] | 2024-01-26 | 2024-03-26 |  | 2024-04-26 | 5.8 | 260 | 393 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
43454 | KR-0-216-001-125-SD5 | 3 | true | CH06822004-BD-PI-0607 | 125 | 5K | UG | C2 | T-079 | 2024-04-26 | [7 empty] | 2024-01-26 |  | 2024-03-26 | 2024-04-23 | 18.7 | 260 | 393 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
43455 | KR-0-216-001-125-SD5 | 3 | true | CH06822004-BD-PI-0607 | 125 | 5K | UG | C2 | T-079 | 2024-04-26 | [7 empty] | 2024-01-26 |  | 2024-03-26 | 2024-04-12 | 5.1 | 260 | 393 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
43456 | KR-0-216-001-125-SD5 | 3 | true | CH06822004-BD-PI-0607 | 125 | 5K | UG | C2 | T-079 | 2024-04-04 | [7 empty] | 2024-01-26 | 2024-03-26 |  | 2024-04-30 | 19 | 260 | 393 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
43457 | KR-0-216-001-125-SD5 | 3 | true | CH06822004-BD-PI-0607 | 125 | 5K | UG | C2 | T-079 | 2024-04-26 | [7 empty] | 2024-01-26 | 2024-03-26 |  | 2024-06-06 | 3 | 260 | 393 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
36993 | KV-0-216-001-100-SD5 | 1 | false | CH06822004-BD-PI-0607 | 100 | 5K | UG | C2 | T02043 | 2023-10-02 | [11 empty] | 0.5 | 260 | 394 | [6 empty] | 0 | SEP | SEP |  | 0
41864 | KV-0-216-001-100-SD5 | 2 | true | CH06822004-BD-PI-0607 | 100 | 5K | UG | C2 | PEL-ZAU-T-035 | 2024-01-13 | [10 empty] | 2024-05-24 | 0.5 | 260 | 394 | Virgil Frinculescu |  |  |  | Connection to Pumps and Equipment changed. |  | 0 | SEP | SEP |  | 0
36994 | KV-0-216-002-125-SD5 | 1 | false | CH06822004-BD-PI-0607 | 125 | 5K | UG | C2 | T02043 | 2023-10-02 | [7 empty] | 2023-12-06 |  |  |  | 0.3 | 260 | 394 | [6 empty] | 0 | SEP | SEP |  | 0
36995 | KV-0-216-002-125-SD5 | 1 | false | CH06822004-BD-PI-0607 | 125 | 5K | UG | C2 | T02043 | 2023-10-02 | [7 empty] | 2023-12-06 | 2023-12-18 |  | 2024-03-21 | 3.4 | 260 | 394 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 0
36996 | KV-0-216-002-125-SD5 | 1 | false | CH06822004-BD-PI-0607 | 125 | 5K | UG | C2 | T02043 | 2023-10-02 | [7 empty] | 2023-12-06 | 2023-12-18 |  | 2024-03-21 | 13.3 | 260 | 394 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 0
36997 | KV-0-216-002-125-SD5 | 1 | false | CH06822004-BD-PI-0607 | 125 | 5K | UG | C2 | T02043 | 2023-10-02 | [7 empty] | 2023-12-06 |  |  |  | 16.9 | 260 | 394 | [6 empty] | 0 | SEP | SEP |  | 0
36998 | KV-0-216-002-125-SD5 | 1 | false | CH06822004-BD-PI-0607 | 125 | 5K | UG | C2 | T02043 | 2023-10-02 | [7 empty] | 2023-12-06 |  |  |  | 2.4 | 260 | 394 | Gruppe_Test | [5 empty] | 0 | SEP | SEP |  | 0
36999 | KV-0-216-002-125-SD5 | 1 | false | CH06822004-BD-PI-0607 | 125 | 5K | UG | C2 | T02043 | 2023-10-02 | [7 empty] | 2023-12-06 |  |  |  | 5.4 | 260 | 394 | [6 empty] | 0 | SEP | SEP |  | 0
43452 | KV-0-216-002-125-SD5 | 3 | true | CH06822004-BD-PI-0607 | 125 | 5K | UG | C2 | T-079 | 2024-04-04 | [7 empty] | 2024-01-26 | 2024-03-26 |  | 2024-04-29 | 5.4 | 260 | 394 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
43458 | KV-0-216-002-125-SD5 | 3 | true | CH06822004-BD-PI-0607 | 125 | 5K | UG | C2 | T-079 | 2024-04-26 | [7 empty] | 2024-01-26 |  |  | 2024-04-26 | 0.2 | 260 | 394 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
43459 | KV-0-216-002-125-SD5 | 3 | true | CH06822004-BD-PI-0607 | 125 | 5K | UG | C2 | T-079 | 2024-04-26 | [7 empty] | 2024-01-26 |  | 2024-03-26 | 2024-06-26 | 3.3 | 260 | 394 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
43460 | KV-0-216-002-125-SD5 | 3 | true | CH06822004-BD-PI-0607 | 125 | 5K | UG | C2 | T-079 | 2024-04-26 | [7 empty] | 2024-01-26 |  | 2024-03-26 | 2024-06-26 | 13.3 | 260 | 394 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
43461 | KV-0-216-002-125-SD5 | 3 | true | CH06822004-BD-PI-0607 | 125 | 5K | UG | C2 | T-079 | 2024-04-26 | [7 empty] | 2024-01-26 |  | 2024-03-26 | 2024-04-03 | 16.9 | 260 | 394 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
43462 | KV-0-216-002-125-SD5 | 3 | true | CH06822004-BD-PI-0607 | 125 | 5K | UG | C2 | T-079 | 2024-04-26 | [7 empty] | 2024-01-26 |  | 2024-03-26 | 2024-04-26 | 2.4 | 260 | 394 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
37000 | N2F-7-500-001-25-SP1 | 1 | true | CH06822004-BD-PI-0457 | 25 | 5K | UG | N/A | T02043 | 2023-10-02 |  |  | 2023-11-22 | [7 empty] | 2024-01-31 | 4.9 | 264 | 396 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 0
37001 | N2F-7-500-001-25-SP1 | 1 | true | CH06822004-BD-PI-0457 | 25 | 5K | UG | N/A | T02043 | 2023-10-02 |  |  | 2023-11-22 | [7 empty] | 2023-12-10 | 35.3 | 264 | 396 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 0
37002 | N2F-7-500-001-25-SP1 | 1 | true | CH06822004-BD-PI-0457 | 25 | 5K | UG | N/A | T02043 | 2023-10-02 |  |  | 2023-11-22 | [7 empty] | 2023-12-18 | 11.9 | 264 | 396 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 0
37003 | O2F-7-400-001-25-SP1 | 1 | true |  | 25 | 5K | UG | N/A | T02043 | 2023-10-02 |  |  | 2023-11-22 | [7 empty] | 2024-01-31 | 1.8 | 264 | 458 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 0
37004 | O2F-7-400-001-25-SP1 | 1 | true |  | 25 | 5K | UG | N/A | T02043 | 2023-10-02 |  |  | 2023-11-22 | [7 empty] | 2023-12-10 | 36.9 | 264 | 458 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 0
37005 | O2F-7-400-001-25-SP1 | 1 | true |  | 25 | 5K | UG | N/A | T02043 | 2023-10-02 |  |  | 2023-11-22 | [7 empty] | 2023-12-18 | 12.1 | 264 | 458 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 0
37006 | US4-0-244-002-50-SD6 | 1 | false | CH06822004-BD-PI-0586 | 50 | 5K | UG | H2 | T02043 | 2023-10-02 | [7 empty] | 2024-01-11 |  |  |  | 1.7 | 261 | 410 | Attila Henter | 130 | 130 | HOLD | HOLD |  | 0 | SEP | SEP |  | 0
37007 | US4-0-244-002-50-SD6 | 1 | false | CH06822004-BD-PI-0586 | 50 | 5K | UG | H2 | T02043 | 2023-10-02 | [7 empty] | 2024-02-08 |  |  | 2024-01-25 | 8 | 261 | 410 | Virgil Frinculescu | 130 | 130 |  |  |  | 0 | SEP | SEP |  | 0
37008 | US4-0-244-002-50-SD6 | 1 | false | CH06822004-BD-PI-0586 | 50 | 5K | UG | H2 | T02043 | 2023-10-02 | [7 empty] | 2024-02-08 |  |  | 2024-01-25 | 20.5 | 261 | 410 | Virgil Frinculescu | 130 | 130 |  |  |  | 0 | SEP | SEP |  | 0
37009 | US4-0-244-002-50-SD6 | 1 | false | CH06822004-BD-PI-0586 | 50 | 5K | UG | H2 | T02043 | 2023-10-02 | [7 empty] | 2024-02-08 |  |  | 2024-01-25 | 10.7 | 261 | 410 | Virgil Frinculescu | 130 | 130 |  |  |  | 0 | SEP | SEP |  | 0
37010 | US4-0-244-002-50-SD6 | 1 | false | CH06822004-BD-PI-0586 | 50 | 5K | UG | H2 | T02043 | 2023-10-02 | [7 empty] | 2024-02-08 |  |  | 2024-01-25 | 6.2 | 261 | 410 | Virgil Frinculescu | 130 | 130 |  |  |  | 0 | SEP | SEP |  | 0
43827 | US4-0-244-002-50-SD6 | 2 | true | CH06822004-BD-PI-0586 | 50 | 5K | UG | H2 | T-048 | 2024-01-30 | [7 empty] | 2024-02-08 |  | 2024-02-06 | 2024-05-23 | 1 | 261 | 410 | Virgil Frinculescu | 130 | 130 |  |  |  | 0 | SEP | SEP
43828 | US4-0-244-002-50-SD6 | 2 | true | CH06822004-BD-PI-0586 | 50 | 5K | UG | H2 | T-048 | 2024-01-30 | [7 empty] | 2024-02-08 |  | 2024-02-06 | 2024-07-05 | 0.7 | 261 | 410 | Virgil Frinculescu | 130 | 130 |  |  |  | 0 | SEP | SEP
43829 | US4-0-244-002-50-SD6 | 2 | true | CH06822004-BD-PI-0586 | 50 | 5K | UG | H2 | T-048 | 2024-01-30 | [7 empty] | 2024-02-08 |  | 2024-02-06 | 2024-02-08 | 8 | 261 | 410 | Virgil Frinculescu | 130 | 130 |  |  |  | 0 | SEP | SEP
43830 | US4-0-244-002-50-SD6 | 2 | true | CH06822004-BD-PI-0586 | 50 | 5K | UG | H2 | T-048 | 2024-01-30 | [7 empty] | 2024-02-08 |  | 2024-02-06 | 2024-02-08 | 20.5 | 261 | 410 | Virgil Frinculescu | 130 | 130 |  |  |  | 0 | SEP | SEP
43831 | US4-0-244-002-50-SD6 | 2 | true | CH06822004-BD-PI-0586 | 50 | 5K | UG | H2 | T-048 | 2024-01-30 | [7 empty] | 2024-02-08 |  | 2024-02-06 | 2024-02-08 | 10.7 | 261 | 410 | Virgil Frinculescu | 130 | 130 |  |  |  | 0 | SEP | SEP
43835 | US4-0-244-002-50-SD6 | 2 | true | CH06822004-BD-PI-0586 | 50 | 5K | UG | H2 | T-048 | 2024-01-30 | [7 empty] | 2024-02-08 |  | 2024-02-06 | 2024-02-08 | 6.2 | 261 | 410 | Virgil Frinculescu | 130 | 130 |  |  |  | 0 | SEP | SEP
37011 | US4-0-244-003-15-SD6 | 1 | true | CH06822004-BD-PI-0586 | 15 | 5K | UG | H2 | T02043 | 2023-10-02 | [7 empty] | 2024-01-11 |  |  | 2024-02-06 | 4.3 | 261 | 410 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 0
37012 | US4-0-244-008-25-SD6 | 1 | true | CH06822004-BD-PI-0586 | 25 | 5K | UG | H2 | T02043 | 2023-10-02 | [7 empty] | 2024-01-11 |  |  | 2024-01-26 | 5.2 | 261 | 410 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 0
37013 | WA_EtOH-7-500-001-50-SD | 1 | false | CH06822004-BD-PI-1212 | 50 | 5K | UG | N/A | T02043 | 2023-10-02 | [11 empty] | 3.4 | 271 | 412 | [6 empty] | 0 | SEP | SEP |  | 0
37014 | WA_EtOH-7-500-001-50-SD | 1 | false | CH06822004-BD-PI-1212 | 50 | 5K | UG | N/A | T02043 | 2023-10-02 | [11 empty] | 15.1 | 271 | 412 | [6 empty] | 0 | SEP | SEP |  | 0
37015 | WA_EtOH-7-500-001-50-SD | 1 | false | CH06822004-BD-PI-1212 | 50 | 5K | UG | N/A | T02043 | 2023-10-02 | [11 empty] | 6.9 | 271 | 412 | [6 empty] | 0 | SEP | SEP |  | 0
43266 | WA_EtOH-7-500-001-50-SD | 2 | true | CH06822004-BD-PI-1212 | 50 | 5K | UG | N/A | PEL-ZAU-T-044 | 2024-01-19 | [7 empty] | 2024-03-20 |  |  | 2024-04-08 | 1.9 | 271 | 412 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
43267 | WA_EtOH-7-500-001-50-SD | 2 | true | CH06822004-BD-PI-1212 | 50 | 5K | UG | N/A | PEL-ZAU-T-044 | 2024-01-19 | [7 empty] | 2024-03-20 |  |  | 2024-04-08 | 7.8 | 271 | 412 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
43268 | WA_EtOH-7-500-001-50-SD | 2 | true | CH06822004-BD-PI-1212 | 50 | 5K | UG | N/A | PEL-ZAU-T-044 | 2024-01-19 | [7 empty] | 2024-03-20 |  |  | 2024-04-08 | 12.1 | 271 | 412 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
43269 | WA_EtOH-7-500-001-50-SD | 2 | true | CH06822004-BD-PI-1212 | 50 | 5K | UG | N/A | PEL-ZAU-T-044 | 2024-01-19 | [7 empty] | 2024-03-20 |  |  | 2024-04-08 | 3.4 | 271 | 412 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 0
37016 | WA_EtOH-7-500-002-50-SD | 1 | false | CH06822004-BD-PI-1212 | 50 | 5K | UG | N/A | T02043 | 2023-10-02 | [11 empty] | 9.5 | 271 | 412 | [6 empty] | 0 | SEP | SEP |  | 0
37017 | WA_EtOH-7-500-002-50-SD | 1 | false | CH06822004-BD-PI-1212 | 50 | 5K | UG | N/A | T02043 | 2023-10-02 | [11 empty] | 4.9 | 271 | 412 | [6 empty] | 0 | SEP | SEP |  | 0
37018 | WA_EtOH-7-500-002-50-SD | 1 | false | CH06822004-BD-PI-1212 | 50 | 5K | UG | N/A | T02043 | 2023-10-02 | [11 empty] | 7.5 | 271 | 412 | [6 empty] | 0 | SEP | SEP |  | 0
37019 | WA_EtOH-7-500-002-50-SD | 1 | false | CH06822004-BD-PI-1212 | 50 | 5K | UG | N/A | T02043 | 2023-10-02 | [11 empty] | 8.1 | 271 | 412 | [6 empty] | 0 | SEP | SEP |  | 0
43270 | WA_EtOH-7-500-002-50-SD | 2 | true | CH06822004-BD-PI-1212 | 50 | 5K | UG | N/A | PEL-ZAU-T-044 | 2024-01-19 | [7 empty] | 2024-03-20 |  |  | 2024-04-26 | 0.7 | 271 | 412 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
43271 | WA_EtOH-7-500-002-50-SD | 2 | true | CH06822004-BD-PI-1212 | 50 | 5K | UG | N/A | PEL-ZAU-T-044 | 2024-01-19 | [7 empty] | 2024-03-20 |  |  | 2024-04-26 | 9 | 271 | 412 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
43272 | WA_EtOH-7-500-002-50-SD | 2 | true | CH06822004-BD-PI-1212 | 50 | 5K | UG | N/A | PEL-ZAU-T-044 | 2024-01-19 | [7 empty] | 2024-03-20 |  |  | 2024-04-26 | 6.7 | 271 | 412 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
43273 | WA_EtOH-7-500-002-50-SD | 2 | true | CH06822004-BD-PI-1212 | 50 | 5K | UG | N/A | PEL-ZAU-T-044 | 2024-01-19 | [7 empty] | 2024-03-20 |  |  | 2024-04-26 | 5.4 | 271 | 412 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
43274 | WA_EtOH-7-500-002-50-SD | 2 | true | CH06822004-BD-PI-1212 | 50 | 5K | UG | N/A | PEL-ZAU-T-044 | 2024-01-19 | [7 empty] | 2024-03-20 |  |  | 2024-04-26 | 8.1 | 271 | 412 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 0
37020 | WAA-7-931-001-150-SD | 1 | false | CH06822004-BD-PI-0635 | 150 | 5K | UG | H3 | T02043 | 2023-10-02 | [7 empty] | 2023-12-06 |  |  |  | 1.8 | 271 | 411 | [6 empty] | 0 | SEP | SEP |  | 0
37021 | WAA-7-931-001-150-SD | 1 | false | CH06822004-BD-PI-0635 | 150 | 5K | UG | H3 | T02043 | 2023-10-02 | [7 empty] | 2023-12-06 |  |  |  | 18.4 | 271 | 411 | [6 empty] | 0 | SEP | SEP |  | 0
37022 | WAA-7-931-001-150-SD | 1 | false | CH06822004-BD-PI-0635 | 150 | 5K | UG | H3 | T02043 | 2023-10-02 | [7 empty] | 2023-12-06 |  |  |  | 6.5 | 271 | 411 | [6 empty] | 0 | SEP | SEP |  | 0
43301 | WAA-7-931-001-150-SD | 3 | true | CH06822004-BD-PI-0635 | 150 | 5K | UG | H3 | T-076 | 2024-04-24 | [7 empty] | 2024-02-06 |  |  | 2024-04-10 | 11 | 271 | 411 | Virgil Frinculescu |  |  |  | Revision not via IDF but Redlined |  | 0 | SEP | SEP
43302 | WAA-7-931-001-150-SD | 3 | true | CH06822004-BD-PI-0635 | 150 | 5K | UG | H3 | T-076 | 2024-04-24 | [7 empty] | 2024-02-06 |  |  | 2024-04-08 | 9.1 | 271 | 411 | Virgil Frinculescu |  |  |  | Revision not via IDF but Redlined |  | 0 | SEP | SEP
43310 | WAA-7-931-001-150-SD | 3 | true | CH06822004-BD-PI-0635 | 150 | 5K | UG | H3 | T-076 | 2024-04-24 | [7 empty] | 2024-02-06 |  |  | 2024-04-03 | 6.5 | 271 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
37023 | WAA-7-931-003-100-SD | 1 | false | CH06822004-BD-PI-0635 | 100 | 5K | UG | H3 | T02043 | 2023-10-02 | [7 empty] | 2023-12-06 |  |  |  | 5.2 | 271 | 411 | [6 empty] | 0 | SEP | SEP |  | 0
42095 | WAA-7-931-003-100-SD | 2 | true | CH06822004-BD-PI-0635 | 100 | 5K | UG | H3 | PEL-ZAU-T-038 | 2024-01-15 | [7 empty] | 2024-02-06 |  |  | 2024-03-11 | 5.2 | 271 | 411 | Virgil Frinculescu |  |  |  | Main DN100 Pipe to be modified |  | 0 | SEP | SEP |  | 0
37024 | WAA-7-931-004-25-SD | 1 | false | CH06822004-BD-PI-0635 | 25 | 5K | UG | H3 | T02043 | 2023-10-02 | [11 empty] | 17 | 271 | 411 | [6 empty] | 0 | SEP | SEP |  | 0
42115 | WAA-7-931-004-25-SD | 2 | false | CH06822004-BD-PI-0635 | 25 | 5K | UG | H3 | PEL-ZAU-T-038 | 2024-01-15 | [11 empty] | 17 | 271 | 411 |  |  |  |  | Line got deleted |  | 0 | SEP | SEP |  | 0
37025 | WAI-7-201-003-40-SD | 1 | false |  | 40 | 5K | UG | N/A | T02043 | 2023-10-02 | [11 empty] | 10.6 | 271 | 413 | [6 empty] | 0 | SEP | SEP |  | 0
37026 | WAI-7-201-003-40-SD | 1 | false |  | 40 | 5K | UG | N/A | T02043 | 2023-10-02 | [11 empty] | 9 | 271 | 413 | [6 empty] | 0 | SEP | SEP |  | 0
37027 | WAI-7-201-003-40-SD | 1 | false |  | 40 | 5K | UG | N/A | T02043 | 2023-10-02 | [11 empty] | 4.7 | 271 | 413 | [6 empty] | 0 | SEP | SEP |  | 0
37028 | WAI-7-201-004-80-SD | 1 | false | CH06822004-BD-PI-0642 | 80 | 5K | UG | N/A | T02043 | 2023-10-02 | [11 empty] | 3.5 | 271 | 413 | [6 empty] | 0 | SEP | SEP |  | 0
42073 | WAI-7-201-004-80-SD | 2 | false | CH06822004-BD-PI-0642 | 80 | 5K | UG | N/A | PEL-ZAU-T-031 | 2024-01-12 | [11 empty] | 3.5 | 271 | 413 |  |  |  |  | ISO got deleted. |  | 0 | SEP | SEP |  | 0
37029 | WAI-7-201-005-40-SD | 1 | false | CH06822004-BD-PI-0642 | 40 | 5K | UG | N/A | T02043 | 2023-10-02 | [11 empty] | 4 | 271 | 413 | [6 empty] | 0 | SEP | SEP |  | 0
42032 | WAI-7-201-005-40-SD | 2 | true | CH06822004-BD-PI-0642 | 40 | 5K | UG | N/A | PEL-ZAU-T-031 | 2024-01-12 | [7 empty] | 2024-02-06 |  |  | 2024-04-03 | 4 | 271 | 413 | Virgil Frinculescu |  |  |  | Connection to Drain changed no Impact |  | 0 | SEP | SEP |  | 0
37030 | WAI-7-201-007-65-SD | 1 | true | CH06822004-BD-PI-0642 | 65 | 5K | UG | N/A | T02043 | 2023-10-02 | [7 empty] | 2024-02-06 |  |  | 2024-04-25 | 7.6 | 271 | 413 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 0
37031 | WAI-7-201-008-150-SD | 1 | false | CH06822004-BD-PI-0642 | 150 | 5K | UG | N/A | T02043 | 2023-10-02 | [11 empty] | 5.9 | 271 | 413 | [6 empty] | 0 | SEP | SEP |  | 0
42034 | WAI-7-201-008-150-SD | 2 | false | CH06822004-BD-PI-0642 | 150 | 5K | UG | N/A | PEL-ZAU-T-031 | 2024-01-12 | [7 empty] | 2024-02-06 |  |  | 2024-03-14 | 0.6 | 271 | 413 | Virgil Frinculescu |  |  |  | No Prefabrication = No Impact |  | 0 | SEP | SEP |  | 0
42035 | WAI-7-201-008-150-SD | 2 | false | CH06822004-BD-PI-0642 | 150 | 5K | UG | N/A | PEL-ZAU-T-031 | 2024-01-12 | [7 empty] | 2024-02-06 |  |  |  | 5.8 | 271 | 413 | Attila Henter |  |  |  | No Prefabrication = No Impact |  | 0 | SEP | SEP |  | 0
43262 | WAI-7-201-008-150-SD | 3 | true | CH06822004-BD-PI-0642 | 150 | 5K | UG | N/A | T-078 | 2024-04-26 | [10 empty] | 2024-03-14 | 0.6 | 271 | 413 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
43265 | WAI-7-201-008-150-SD | 3 | true | CH06822004-BD-PI-0642 | 150 | 5K | UG | N/A | T-078 | 2024-04-26 | [7 empty] | 2024-02-06 |  |  | 2024-03-14 | 5.8 | 271 | 413 | Virgil Frinculescu |  |  |  | supports have been added |  | 0 | SEP | SEP
37032 | WAI-7-201-009-65-SD | 1 | false | CH06822004-BD-PI-0642 | 65 | 5K | UG | N/A | T02043 | 2023-10-02 | [11 empty] | 4.7 | 271 | 413 | [6 empty] | 0 | SEP | SEP |  | 0
42036 | WAI-7-201-009-65-SD | 2 | true | CH06822004-BD-PI-0642 | 65 | 5K | UG | N/A | PEL-ZAU-T-031 | 2024-01-12 | [7 empty] | 2024-02-06 |  |  | 2024-03-20 | 4.7 | 271 | 413 | Virgil Frinculescu |  |  |  | Updated Pipe Lenghts DN65 |  | 0 | SEP | SEP |  | 0
37033 | WAI-7-201-011-65-SD | 1 | true | CH06822004-BD-PI-0642 | 65 | 5K | UG | N/A | T02043 | 2023-10-02 | [7 empty] | 2024-02-06 |  |  | 2024-03-22 | 3.7 | 271 | 413 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 0
37034 | WAI-7-201-012-65-SD | 1 | true | CH06822004-BD-PI-0642 | 65 | 5K | UG | N/A | T02043 | 2023-10-02 | [7 empty] | 2024-02-06 |  |  | 2024-03-22 | 2.5 | 271 | 413 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 0
37035 | WAI-7-201-013-25-SD | 1 | false | CH06822004-BD-PI-0642 | 25 | 5K | UG | N/A | T02043 | 2023-10-02 | [11 empty] | 4.7 | 271 | 413 | [6 empty] | 0 | SEP | SEP |  | 0
42037 | WAI-7-201-013-25-SD | 2 | true | CH06822004-BD-PI-0642 | 25 | 5K | UG | N/A | PEL-ZAU-T-031 | 2024-01-12 | [7 empty] | 2024-02-06 |  |  | 2024-03-19 | 4.5 | 271 | 413 | Virgil Frinculescu |  |  |  | Completly new DN |  | 0 | SEP | SEP |  | 0
37036 | WAI-7-201-014-25-SD | 1 | false | CH06822004-BD-PI-0642 | 25 | 5K | UG | N/A | T02043 | 2023-10-02 | [11 empty] | 1.8 | 271 | 413 | [6 empty] | 0 | SEP | SEP |  | 0
42038 | WAI-7-201-014-25-SD | 2 | true | CH06822004-BD-PI-0642 | 25 | 5K | UG | N/A | PEL-ZAU-T-031 | 2024-01-12 | [7 empty] | 2024-02-06 |  |  | 2024-04-03 | 2.8 | 271 | 413 | Virgil Frinculescu |  |  |  | New routing of ISO |  | 0 | SEP | SEP |  | 0
37037 | WAI-7-201-016-65-SD | 1 | true | CH06822004-BD-PI-0642 | 65 | 5K | UG | N/A | T02043 | 2023-10-02 | [7 empty] | 2024-02-06 |  |  | 2024-03-14 | 0.3 | 271 | 413 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 0
37038 | WAI-7-201-017-40-SD | 1 | false | CH06822004-BD-PI-0642 | 40 | 5K | UG | N/A | T02043 | 2023-10-02 | [11 empty] | 13 | 271 | 413 | [6 empty] | 0 | SEP | SEP |  | 0
42039 | WAI-7-201-017-40-SD | 2 | true | CH06822004-BD-PI-0642 | 40 | 5K | UG | N/A | PEL-ZAU-T-031 | 2024-01-12 | [7 empty] | 2024-02-06 |  |  | 2024-04-05 | 12.9 | 271 | 413 | Virgil Frinculescu |  |  |  | Connection to Drain changed no Impact |  | 0 | SEP | SEP |  | 0
37039 | WAI-7-201-018-40-SD | 1 | false | CH06822004-BD-PI-0642 | 40 | 5K | UG | N/A | T02043 | 2023-10-02 | [11 empty] | 0.1 | 271 | 413 | [6 empty] | 0 | SEP | SEP |  | 0
42040 | WAI-7-201-018-40-SD | 2 | true | CH06822004-BD-PI-0642 | 40 | 5K | UG | N/A | PEL-ZAU-T-031 | 2024-01-12 | [7 empty] | 2024-02-06 |  |  | 2024-04-05 | 0.2 | 271 | 413 | Virgil Frinculescu |  |  |  | New routing of ISO |  | 0 | SEP | SEP |  | 0
37040 | WAI-7-201-019-40-SD | 1 | false | CH06822004-BD-PI-0642 | 40 | 5K | UG | N/A | T02043 | 2023-10-02 | [11 empty] | 0.1 | 271 | 413 | [6 empty] | 0 | SEP | SEP |  | 0
42041 | WAI-7-201-019-40-SD | 2 | true | CH06822004-BD-PI-0642 | 40 | 5K | UG | N/A | PEL-ZAU-T-031 | 2024-01-12 | [7 empty] | 2024-02-06 |  |  | 2024-04-05 | 0.7 | 271 | 413 | Virgil Frinculescu |  |  |  | New routing of ISO |  | 0 | SEP | SEP |  | 0
37041 | WAI-7-201-021-25-SD | 1 | false | CH06822004-BD-PI-0642 | 25 | 5K | UG | N/A | T02043 | 2023-10-02 | [11 empty] | 7.2 | 271 | 413 | [6 empty] | 0 | SEP | SEP |  | 0
42042 | WAI-7-201-021-25-SD | 2 | true | CH06822004-BD-PI-0642 | 25 | 5K | UG | N/A | PEL-ZAU-T-031 | 2024-01-12 | [7 empty] | 2024-02-06 |  |  | 2024-04-03 | 7.3 | 271 | 413 | Virgil Frinculescu |  |  |  | Height change of Isometric no bigger impact |  | 0 | SEP | SEP |  | 0
37042 | WAI-7-201-024-40-SD | 1 | false | CH06822004-BD-PI-0642 | 40 | 5K | UG | N/A | T02043 | 2023-10-02 | [11 empty] | 16.7 | 271 | 413 | [6 empty] | 0 | SEP | SEP |  | 0
37043 | WAI-7-201-029-100-SD | 1 | false | CH06822004-BD-PI-0642 | 100 | 5K | UG | N/A | T02043 | 2023-10-02 | [11 empty] | 3.5 | 271 | 413 | [6 empty] | 0 | SEP | SEP |  | 0
42050 | WAI-7-201-029-100-SD | 2 | false | CH06822004-BD-PI-0642 | 100 | 5K | UG | N/A | PEL-ZAU-T-031 | 2024-01-12 | [7 empty] | 2024-02-06 |  |  |  | 3.6 | 271 | 413 | Attila Henter |  |  |  | Updated Pipe Lenghts DN100 |  | 0 | SEP | SEP |  | 0
43275 | WAI-7-201-029-100-SD | 3 | true | CH06822004-BD-PI-0642 | 100 | 5K | UG | N/A | T-078 | 2024-04-26 | [7 empty] | 2024-02-06 |  |  | 2024-06-20 | 3.6 | 271 | 413 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
37044 | WAI-7-201-037-100-SD | 1 | false | CH06822004-BD-PI-0642 | 100 | 5K | UG | N/A | T02043 | 2023-10-02 | [11 empty] | 0.5 | 271 | 413 | [6 empty] | 0 | SEP | SEP |  | 0
42054 | WAI-7-201-037-100-SD | 2 | false | CH06822004-BD-PI-0642 | 100 | 5K | UG | N/A | PEL-ZAU-T-031 | 2024-01-12 | [7 empty] | 2024-02-06 |  |  |  | 0.2 | 271 | 413 | Attila Henter |  |  |  | No Prefabrication = No Impact |  | 0 | SEP | SEP |  | 0
43297 | WAI-7-201-037-100-SD | 3 | true | CH06822004-BD-PI-0642 | 100 | 5K | UG | N/A | Email.19.Jan.2024 | 2024-01-19 | [7 empty] | 2024-02-06 |  |  | 2024-06-20 | 0.2 | 271 | 413 | Virgil Frinculescu |  |  |  | support has been removed |  | 0 | SEP | SEP
37045 | WAI-7-201-038-65-SD | 1 | true | CH06822004-BD-PI-0642 | 65 | 5K | UG | N/A | T02043 | 2023-10-02 | [7 empty] | 2024-02-06 |  |  | 2024-04-05 | 4.5 | 271 | 413 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 0
37046 | WAI-7-201-039-150-SD | 1 | false | CH06822004-BD-PI-0642 | 150 | 5K | UG | N/A | T02043 | 2023-10-02 | [11 empty] | 0.2 | 271 | 413 | [6 empty] | 0 | SEP | SEP |  | 0
42055 | WAI-7-201-039-150-SD | 2 | true | CH06822004-BD-PI-0642 | 150 | 5K | UG | N/A | PEL-ZAU-T-031 | 2024-01-12 | [7 empty] | 2024-02-06 |  |  | 2024-06-20 | 0.2 | 271 | 413 | Virgil Frinculescu |  |  |  | No Prefabrication = No Impact |  | 0 | SEP | SEP |  | 0
37047 | WAI-7-201-040-25-SD | 1 | false | CH06822004-BD-PI-0642 | 25 | 5K | UG | N/A | T02043 | 2023-10-02 | [11 empty] | 0.1 | 271 | 413 | [6 empty] | 0 | SEP | SEP |  | 0
42056 | WAI-7-201-040-25-SD | 2 | true | CH06822004-BD-PI-0642 | 25 | 5K | UG | N/A | PEL-ZAU-T-031 | 2024-01-12 | [7 empty] | 2024-02-06 |  |  | 2024-04-11 | 0.1 | 271 | 413 | Virgil Frinculescu |  |  |  | No Prefabrication = No Impact |  | 0 | SEP | SEP |  | 0
37048 | WAI-7-201-041-25-SD | 1 | false | CH06822004-BD-PI-0642 | 25 | 5K | UG | N/A | T02043 | 2023-10-02 | [11 empty] | 1.4 | 271 | 413 | [6 empty] | 0 | SEP | SEP |  | 0
42057 | WAI-7-201-041-25-SD | 2 | true | CH06822004-BD-PI-0642 | 25 | 5K | UG | N/A | PEL-ZAU-T-031 | 2024-01-12 | [7 empty] | 2024-02-06 |  |  | 2024-03-13 | 1.3 | 271 | 413 | Virgil Frinculescu |  |  |  | Partly New routing of ISO |  | 0 | SEP | SEP |  | 0
37049 | WAI-7-201-042-25-SD | 1 | false | CH06822004-BD-PI-0642 | 25 | 5K | UG | N/A | T02043 | 2023-10-02 | [11 empty] | 0.4 | 271 | 413 | [6 empty] | 0 | SEP | SEP |  | 0
42058 | WAI-7-201-042-25-SD | 2 | true | CH06822004-BD-PI-0642 | 25 | 5K | UG | N/A | PEL-ZAU-T-031 | 2024-01-12 | [7 empty] | 2024-02-06 |  |  | 2024-04-05 | 3.2 | 271 | 413 | Virgil Frinculescu |  |  |  | New routing of ISO |  | 0 | SEP | SEP |  | 0
37050 | WAI-7-201-043-25-SD | 1 | false | CH06822004-BD-PI-0642 | 25 | 5K | UG | N/A | T02043 | 2023-10-02 | [11 empty] | 0.3 | 271 | 413 | [6 empty] | 0 | SEP | SEP |  | 0
42059 | WAI-7-201-043-25-SD | 2 | true | CH06822004-BD-PI-0642 | 25 | 5K | UG | N/A | PEL-ZAU-T-031 | 2024-01-12 | [7 empty] | 2024-02-06 |  |  | 2024-04-08 | 4.2 | 271 | 413 | Virgil Frinculescu |  |  |  | New routing of ISO |  | 0 | SEP | SEP |  | 0
37051 | WAI-7-201-044-25-SD | 1 | false | CH06822004-BD-PI-0642 | 25 | 5K | UG | N/A | T02043 | 2023-10-02 | [11 empty] | 3.8 | 271 | 413 | [6 empty] | 0 | SEP | SEP |  | 0
42060 | WAI-7-201-044-25-SD | 2 | true | CH06822004-BD-PI-0642 | 25 | 5K | UG | N/A | PEL-ZAU-T-031 | 2024-01-12 | [7 empty] | 2024-02-06 |  |  | 2024-03-19 | 1.5 | 271 | 413 | Virgil Frinculescu |  |  |  | No Prefabrication = No Impact (slightly routing change) |  | 0 | SEP | SEP |  | 0
37052 | WAI-7-201-045-25-SD | 1 | true | CH06822004-BD-PI-0642 | 25 | 5K | UG | N/A | T02043 | 2023-10-02 | [7 empty] | 2024-02-06 |  |  | 2024-04-03 | 5.4 | 271 | 413 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 0
37053 | WAI-7-201-046-100-SD | 1 | false | CH06822004-BD-PI-0642 | 100 | 5K | UG | N/A | T02043 | 2023-10-02 | [11 empty] | 7 | 271 | 413 |  | 126 |  | HOLD | HOLD |  | 0 | SEP | SEP |  | 0
42061 | WAI-7-201-046-100-SD | 2 | false | CH06822004-BD-PI-0642 | 100 | 5K | UG | N/A | PEL-ZAU-T-031 | 2024-01-12 | [7 empty] | 2024-02-06 |  |  |  | 6.5 | 271 | 413 | Attila Henter | 126 |  | HOLD | No Prefabrication = No Impact (extra branches) |  | 0 | SEP | SEP |  | 0
43255 | WAI-7-201-046-100-SD | 3 | true | CH06822004-BD-PI-0642 | 100 | 5K | UG | N/A | T-078 | 2024-04-26 | [7 empty] | 2024-02-06 |  |  | 2024-03-22 | 6.5 | 271 | 413 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP
37054 | WAI-7-201-048-100-SD | 1 | false | CH06822004-BD-PI-0642 | 100 | 5K | UG | N/A | T02043 | 2023-10-02 | [11 empty] | 0.6 | 271 | 413 | [6 empty] | 0 | SEP | SEP |  | 0
42062 | WAI-7-201-048-100-SD | 2 | true | CH06822004-BD-PI-0642 | 100 | 5K | UG | N/A | PEL-ZAU-T-031 | 2024-01-12 | [7 empty] | 2024-02-06 |  |  | 2024-06-20 | 0.7 | 271 | 413 | Virgil Frinculescu |  |  |  | No Prefabrication = No Impact (slightly routing change) |  | 0 | SEP | SEP |  | 0
37055 | WAI-7-201-049-100-SD | 1 | false | CH06822004-BD-PI-0642 | 100 | 5K | UG | N/A | T02043 | 2023-10-02 | [11 empty] | 8.2 | 271 | 413 |  |  |  |  | HOLD |  | 0 | SEP | SEP |  | 0
42063 | WAI-7-201-049-100-SD | 2 | true | CH06822004-BD-PI-0642 | 100 | 5K | UG | N/A | PEL-ZAU-T-031 | 2024-01-12 | [7 empty] | 2024-02-06 |  |  | 2024-03-14 | 3.5 | 271 | 413 | Virgil Frinculescu |  |  |  | No change |  | 0 | SEP | SEP |  | 0
42064 | WAI-7-201-049-100-SD | 2 | true | CH06822004-BD-PI-0642 | 100 | 5K | UG | N/A | PEL-ZAU-T-031 | 2024-01-12 | [7 empty] | 2024-02-06 |  |  | 2024-03-14 | 4.5 | 271 | 413 | Virgil Frinculescu |  |  |  | No Prefabrication = No Impact (extra branches) |  | 0 | SEP | SEP |  | 0
37153 | DKS-7-401-056-25-SD | 1 | true | CH06822004-BD-PI-0530 | 25 | 5K | EG | H3 | T02030 | 2023-10-02 |  | 2023-10-22 | 2023-10-29 | 2023-10-31 | 2023-11-08 | 2023-11-21 |  | 2023-11-27 |  |  | 2023-12-05 | 9.1 | 271 | 378 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
37154 | DKS-7-401-058-25-SD | 1 | true | CH06822004-BD-PI-0530 | 25 | 5K | EG | H3 | T02030 | 2023-10-02 |  | 2023-10-22 | 2023-10-29 | 2023-10-30 | 2023-10-31 | 2023-11-21 |  | 2023-11-27 | 2023-11-30 | 2023-12-18 | 2024-01-29 | 1.7 | 271 | 378 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 1
38497 | CS-7-201-008-40-SP1 | 2 | false | CH06822004-BD-PI-1179 | 40 | 5K | OG3 | H2 | T01967 | 2023-11-11 | 2023-12-04 | 2023-12-04 | 2024-01-16 | 2024-01-25 | 2024-01-25 | 2024-02-02 |  | 2024-02-06 |  |  |  | 24.3 | 264 | 371 | Jozef Kotul | [5 empty] | 0 | SEP | SEP |  | 5
38498 | CS-7-201-008-40-SP1 | 2 | false | CH06822004-BD-PI-1179 | 40 | 5K | OG3 | H2 | T01967 | 2023-11-11 | 2023-12-04 | 2023-12-04 | 2024-01-16 | 2024-01-29 | 2024-01-30 | 2024-02-02 |  | 2024-02-06 |  |  |  | 4.7 | 264 | 371 | Jozef Kotul | [5 empty] | 0 | SEP | SEP |  | 5
38499 | CS-7-201-008-40-SP1 | 2 | false | CH06822004-BD-PI-1179 | 40 | 5K | OG3 | H2 | T01967 | 2023-11-11 | 2023-12-04 | 2023-12-04 | 2024-01-16 | 2024-01-25 | 2024-01-25 | 2024-02-02 |  | 2024-02-06 |  |  |  | 2.4 | 264 | 371 | Jozef Kotul | [5 empty] | 0 | SEP | SEP |  | 5
43474 | CS-7-201-008-40-SP1 | 3 | true | CH06822004-BD-PI-1179 | 40 | 5K | OG3 | H2 | T-047 | 2024-01-25 | 2023-12-04 | 2023-12-04 | 2024-01-16 | 2024-01-25 | 2024-01-25 |  |  | 2024-02-06 |  | 2024-03-23 | 2024-06-27 | 24 | 264 | 371 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
43475 | CS-7-201-008-40-SP1 | 3 | true | CH06822004-BD-PI-1179 | 40 | 5K | OG3 | H2 | T-047 | 2024-01-25 | 2023-12-04 | 2023-12-04 | 2024-01-16 |  | 2024-01-30 |  |  | 2024-02-06 |  |  | 2024-02-26 | 11 | 264 | 371 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
43476 | CS-7-201-008-40-SP1 | 3 | true | CH06822004-BD-PI-1179 | 40 | 5K | OG3 | H2 | T-047 | 2024-01-25 | 2023-12-04 | 2023-12-04 | 2024-01-16 | 2024-01-25 | 2024-01-25 |  |  | 2024-02-06 |  |  | 2024-03-19 | 1.6 | 264 | 371 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
38500 | CS-7-201-044-15-SP1 | 2 | false | CH06822004-BD-PI-1179 | 15 | 5K | OG3 | H2 | T01967 | 2023-11-11 | 2023-12-04 | 2023-12-04 | 2024-01-10 | 2024-01-12 | 2024-01-13 | 2024-02-02 |  | 2024-02-06 |  |  |  | 6.3 | 264 | 371 | Jozef Kotul |  |  | HOLD |  |  | 0 | SEP | SEP |  | 5
38501 | CS-7-201-045-15-SP1 | 2 | true | CH06822004-BD-PI-1179 | 15 | 5K | OG3 | H2 | T01967 | 2023-11-11 | 2023-12-04 | 2023-12-04 | 2024-01-10 | 2024-01-12 | 2024-01-12 | 2024-02-02 |  | 2024-02-06 |  |  |  | 6.3 | 264 | 371 | Jozef Kotul |  |  |  | HOLD |  | 0 | SEP | SEP |  | 5
38502 | DKS-7-401-020-15-SD | 2 | true |  | 15 | 5K | OG3 | H3 | T01967 | 2023-11-11 | 2023-11-23 | 2023-11-23 | 2024-01-05 | 2024-01-25 | 2024-01-25 | 2024-02-02 |  | 2024-02-08 |  |  | 2024-02-12 | 1.7 | 271 | 378 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 5
38503 | HR-NT-0-212-001-100-CA | 2 | false | CH06822004-BD-PI-0579 | 100 | 5K | OG3 | H1 | T01967 | 2023-11-11 | 2023-11-23 | 2023-11-23 | 2023-12-18 |  | 2024-01-15 | [6 empty] | 18.2 | 249 | 389 | [6 empty] | 0 | SEP | SEP |  | 5
38504 | HR-NT-0-212-001-100-CA | 2 | false | CH06822004-BD-PI-0579 | 100 | 5K | OG3 | H1 | T01967 | 2023-11-11 | 2023-11-23 | 2023-11-23 | 2023-12-18 |  | 2024-01-15 | [6 empty] | 18.5 | 249 | 389 | [6 empty] | 0 | SEP | SEP |  | 5
38505 | HR-NT-0-212-001-100-CA | 2 | false | CH06822004-BD-PI-0579 | 100 | 5K | OG3 | H1 | T01967 | 2023-11-11 | 2023-11-23 | 2023-11-23 | 2023-12-18 | 2024-01-15 | [7 empty] | 7.1 | 249 | 389 | [6 empty] | 0 | SEP | SEP |  | 5
41847 | HR-NT-0-212-001-100-CA | 3 | true | CH06822004-BD-PI-0579 | 100 | 5K | OG3 | H1 | PEL-ZAU-T-032 | 2024-01-12 | 2024-01-15 | 2023-11-20 | 2024-01-18 | 2024-01-29 | 2024-02-01 | 2024-02-02 |  | 2024-02-09 |  |  | 2024-03-19 | 18.2 | 249 | 389 | Virgil Frinculescu |  |  | No change |  |  | 0 | SEP | SEP |  | 5
41848 | HR-NT-0-212-001-100-CA | 3 | true | CH06822004-BD-PI-0579 | 100 | 5K | OG3 | H1 | PEL-ZAU-T-032 | 2024-01-12 | 2024-01-15 | 2023-11-20 | 2024-01-18 | 2024-01-25 | 2024-01-25 | 2024-02-02 |  | 2024-02-09 |  | 2024-03-23 | 2024-06-06 | 18.5 | 249 | 389 | Virgil Frinculescu |  |  | Updated Positions of Thermowells etc. |  |  | 0 | SEP | SEP |  | 5
41849 | HR-NT-0-212-001-100-CA | 3 | true | CH06822004-BD-PI-0579 | 100 | 5K | OG3 | H1 | PEL-ZAU-T-032 | 2024-01-12 | 2024-01-15 | 2023-11-20 | 2024-01-18 | 2024-01-29 | 2024-02-02 |  |  | 2024-02-09 |  | 2024-03-23 | 2024-07-18 | 7.1 | 249 | 389 | Virgil Frinculescu |  |  | Updated Positions of Thermowells etc. |  |  | 0 | SEP | SEP |  | 5
38506 | HR-NT-0-212-003-100-CA | 2 | false | CH06822004-BD-PI-0579 | 100 | 5K | OG3 | H1 | T01967 | 2023-11-11 | 2023-11-23 | 2023-11-23 | 2023-12-12 | 2024-01-15 | [7 empty] | 0.9 | 249 | 389 | [6 empty] | 0 | SEP | SEP |  | 5
38507 | HR-NT-0-212-003-100-CA | 2 | false | CH06822004-BD-PI-0579 | 100 | 5K | OG3 | H1 | T01967 | 2023-11-11 | 2023-11-23 | 2023-11-23 | 2023-12-12 | 2024-01-15 | [7 empty] | 2.1 | 249 | 389 | [6 empty] | 0 | SEP | SEP |  | 5
38508 | HR-NT-0-212-003-100-CA | 2 | false | CH06822004-BD-PI-0579 | 100 | 5K | OG3 | H1 | T01967 | 2023-11-11 | 2023-11-23 | 2023-11-23 | 2023-12-12 |  | 2024-01-15 | [6 empty] | 11 | 249 | 389 | [6 empty] | 0 | SEP | SEP |  | 5
38509 | HR-NT-0-212-003-100-CA | 2 | false | CH06822004-BD-PI-0579 | 100 | 5K | OG3 | H1 | T01967 | 2023-11-11 | 2023-11-23 | 2023-11-23 | 2023-12-12 |  | 2024-01-15 | [6 empty] | 6.8 | 249 | 389 | [6 empty] | 0 | SEP | SEP |  | 5
41850 | HR-NT-0-212-003-100-CA | 3 | true | CH06822004-BD-PI-0579 | 100 | 5K | OG3 | H1 | PEL-ZAU-T-032 | 2024-01-12 | 2024-01-15 | 2023-11-20 | 2024-01-18 | 2024-01-29 | 2024-02-01 | 2024-02-02 |  | 2024-02-09 |  |  | 2024-02-23 | 1 | 249 | 389 | Virgil Frinculescu |  |  | No effect as Prefab didn´t start |  |  | 0 | SEP | SEP |  | 5
41851 | HR-NT-0-212-003-100-CA | 3 | true | CH06822004-BD-PI-0579 | 100 | 5K | OG3 | H1 | PEL-ZAU-T-032 | 2024-01-12 | 2024-01-15 | 2023-11-20 | 2024-01-18 | 2024-01-30 | 2024-02-01 | 2024-02-02 |  | 2024-02-09 |  |  | 2024-02-23 | 2.1 | 249 | 389 | Virgil Frinculescu |  |  | Updated Positions of Thermowells etc. |  |  | 0 | SEP | SEP |  | 5
41852 | HR-NT-0-212-003-100-CA | 3 | true | CH06822004-BD-PI-0579 | 100 | 5K | OG3 | H1 | PEL-ZAU-T-032 | 2024-01-12 | 2024-01-15 | 2023-11-20 | 2024-01-18 | 2024-01-29 | 2024-02-01 | 2024-02-02 |  | 2024-02-09 |  |  | 2024-02-26 | 11 | 249 | 389 | Virgil Frinculescu |  |  | No change |  |  | 0 | SEP | SEP |  | 5
41853 | HR-NT-0-212-003-100-CA | 3 | true | CH06822004-BD-PI-0579 | 100 | 5K | OG3 | H1 | PEL-ZAU-T-032 | 2024-01-12 | 2024-01-15 | 2023-11-20 | 2024-01-18 | 2024-01-29 | 2024-02-01 | 2024-02-02 |  | 2024-02-09 |  | 2024-04-30 | 2024-06-06 | 6.8 | 249 | 389 | Virgil Frinculescu |  |  | Updated Positions of Thermowells etc. |  |  | 0 | SEP | SEP |  | 5
38510 | HR-NT-0-212-005-20-CA | 2 | true | CH06822004-BD-PI-0579 | 20 | 5K | OG3 | H1 | T01967 | 2023-11-11 | 2023-11-23 | 2023-11-23 | 2024-01-10 | 2024-01-29 | 2024-02-01 | 2024-02-02 |  | 2024-02-09 |  |  | 2024-02-22 | 0.7 | 249 | 389 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 5
38511 | HR-NT-0-212-006-50-CA | 2 | false | CH06822004-BD-PI-0579 | 50 | 5K | OG3 | H1 | T01967 | 2023-11-11 | 2023-11-23 | 2023-11-23 | 2024-01-26 | 2024-02-01 | 2024-02-01 | 2024-02-02 |  | 2024-02-13 |  |  | 2024-02-22 | 12.1 | 249 | 389 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 5
44745 | HR-NT-0-212-006-50-CA | 4 | true | CH06822004-BD-PI-0579 | 50 | 5K | OG3 | H1 | T-055 | 2024-02-16 | 2023-11-23 | 2023-11-23 | 2024-01-26 | 2024-02-01 | 2024-02-01 | 2024-02-02 |  | 2024-02-13 |  | 2024-03-23 | 2024-06-26 | 11.9 | 249 | 389 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
38512 | HR-NT-0-212-007-50-CA | 2 | false | CH06822004-BD-PI-0579 | 50 | 5K | OG3 | H1 | T01967 | 2023-11-11 | 2023-11-23 | 2023-11-23 | 2024-01-04 |  | 2024-01-15 | 2024-02-02 |  | 2024-02-13 |  |  | 2024-02-22 | 6.4 | 249 | 389 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 5
44746 | HR-NT-0-212-007-50-CA | 4 | true | CH06822004-BD-PI-0579 | 50 | 5K | OG3 | H1 | T-055 | 2024-02-16 | 2023-11-23 | 2023-11-23 | 2024-01-04 |  | 2024-01-15 | 2024-02-02 |  | 2024-02-13 |  | 2024-03-23 | 2024-06-25 | 6.4 | 249 | 389 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
38513 | HR-NT-0-212-008-40-CA | 2 | false | CH06822004-BD-PI-0579 | 40 | 5K | OG3 | H1 | T01967 | 2023-11-11 | 2023-11-23 | 2023-11-23 | 2024-01-10 |  | 2024-01-15 | 2024-02-02 |  | 2024-02-13 |  |  | 2024-02-22 | 7.1 | 249 | 389 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 5
44747 | HR-NT-0-212-008-40-CA | 4 | true | CH06822004-BD-PI-0579 | 40 | 5K | OG3 | H1 | T-055 | 2024-02-16 | 2023-11-23 | 2023-11-23 | 2024-01-10 |  | 2024-01-15 | 2024-02-02 |  | 2024-02-13 |  |  | 2024-03-07 | 7.2 | 249 | 389 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
38514 | HR-NT-0-212-009-65-CA | 2 | true | CH06822004-BD-PI-0579 | 65 | 5K | OG3 | H1 | T01967 | 2023-11-11 | 2023-11-23 | 2023-11-23 | 2024-01-04 |  | 2024-01-15 | 2024-02-02 |  | 2024-02-21 |  |  | 2024-02-28 | 13.9 | 249 | 389 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 5
38515 | HR-NT-0-212-010-40-CA | 2 | false | CH06822004-BD-PI-0579 | 40 | 5K | OG3 | H1 | T01967 | 2023-11-11 | 2023-11-23 | 2023-11-23 | 2024-01-10 | 2024-01-29 | 2024-02-01 | 2024-02-02 |  | 2024-02-21 |  |  |  | 5.8 | 249 | 389 | Attila Henter | [5 empty] | 0 | SEP | SEP |  | 5
38516 | HR-NT-0-212-010-40-CA | 2 | false | CH06822004-BD-PI-0579 | 40 | 5K | OG3 | H1 | T01967 | 2023-11-11 | 2023-11-23 | 2023-11-23 | 2024-01-10 | 2024-01-29 | 2024-02-01 | 2024-02-02 |  | 2024-02-21 |  |  |  | 8.5 | 249 | 389 | Attila Henter | [5 empty] | 0 | SEP | SEP |  | 5
44748 | HR-NT-0-212-010-40-CA | 4 | true | CH06822004-BD-PI-0579 | 40 | 5K | OG3 | H1 | T-055 | 2024-02-16 | 2023-11-23 | 2023-11-23 | 2024-01-10 | 2024-01-29 | 2024-02-01 | 2024-02-02 |  |  |  |  | 2024-03-07 | 5.8 | 249 | 389 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
44749 | HR-NT-0-212-010-40-CA | 4 | true | CH06822004-BD-PI-0579 | 40 | 5K | OG3 | H1 | T-055 | 2024-02-16 | 2023-11-23 | 2023-11-23 | 2024-01-10 | 2024-01-29 | 2024-02-01 | 2024-02-02 |  |  |  |  | 2024-03-05 | 8.5 | 249 | 389 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
38517 | HR-NT-0-212-011-40-CA | 2 | false | CH06822004-BD-PI-0579 | 40 | 5K | OG3 | H1 | T01967 | 2023-11-11 | 2023-11-23 | 2023-11-23 | 2024-01-10 | 2024-01-29 | 2024-02-01 | 2024-02-02 |  | 2024-02-21 |  |  |  | 13.6 | 249 | 389 | Attila Henter | [5 empty] | 0 | SEP | SEP |  | 5
44750 | HR-NT-0-212-011-40-CA | 4 | true | CH06822004-BD-PI-0579 | 40 | 5K | OG3 | H1 | T-055 | 2024-02-16 | 2023-11-23 | 2023-11-23 | 2024-01-10 | 2024-01-29 | 2024-02-01 | 2024-02-02 |  |  |  |  | 2024-03-07 | 13.7 | 249 | 389 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
38518 | HV-NT-0-212-001-100-CA | 2 | false | CH06822004-BD-PI-0579 | 100 | 5K | OG3 | H1 | T01967 | 2023-11-11 | 2023-11-23 | 2023-11-23 | 2023-12-12 | 2024-01-15 | [7 empty] | 1.1 | 249 | 390 | [6 empty] | 0 | SEP | SEP |  | 5
38519 | HV-NT-0-212-001-100-CA | 2 | false | CH06822004-BD-PI-0579 | 100 | 5K | OG3 | H1 | T01967 | 2023-11-11 | 2023-11-23 | 2023-11-23 | 2023-12-11 | 2023-12-13 | 2023-12-13 | [6 empty] | 0.7 | 249 | 390 | [6 empty] | 0 | SEP | SEP |  | 5
38521 | HV-NT-0-212-001-100-CA | 2 | false | CH06822004-BD-PI-0579 | 100 | 5K | OG3 | H1 | T01967 | 2023-11-11 | [12 empty] | 249 | 390 | [6 empty] | 0 | SEP | SEP |  | 5
41854 | HV-NT-0-212-001-100-CA | 3 | true | CH06822004-BD-PI-0579 | 100 | 5K | OG3 | H1 | PEL-ZAU-T-032 | 2024-01-12 | 2024-01-15 | 2023-11-20 | 2023-12-12 | 2024-01-30 | 2024-02-01 | 2024-02-02 |  | 2024-02-21 |  |  | 2024-03-13 | 1.1 | 249 | 390 | Virgil Frinculescu |  |  | No change |  |  | 0 | SEP | SEP |  | 5
41855 | HV-NT-0-212-001-100-CA | 3 | true | CH06822004-BD-PI-0579 | 100 | 5K | OG3 | H1 | PEL-ZAU-T-032 | 2024-01-12 | 2024-01-15 | 2023-11-20 | 2023-12-11 | 2023-12-13 | 2023-12-13 | 2024-02-02 |  | 2024-02-21 |  |  | 2024-03-13 | 0.7 | 249 | 390 | Virgil Frinculescu |  |  | Stub In /PI removed --> No data from prefab |  |  | 0 | SEP | SEP |  | 5
38522 | HV-NT-0-212-002-100-CA | 2 | false | CH06822004-BD-PI-0579 | 100 | 5K | OG3 | H1 | T01967 | 2023-11-11 | 2023-11-23 | 2023-11-23 | 2023-12-12 | 2024-01-15 | [7 empty] | 0.3 | 249 | 390 | [6 empty] | 0 | SEP | SEP |  | 5
38523 | HV-NT-0-212-002-100-CA | 2 | false | CH06822004-BD-PI-0579 | 100 | 5K | OG3 | H1 | T01967 | 2023-11-11 | 2023-11-23 | 2023-11-23 | 2023-12-12 | 2024-01-15 | [7 empty] | 0.3 | 249 | 390 | [6 empty] | 0 | SEP | SEP |  | 5
38524 | HV-NT-0-212-002-100-CA | 2 | false | CH06822004-BD-PI-0579 | 100 | 5K | OG3 | H1 | T01967 | 2023-11-11 | 2023-11-23 | 2023-11-23 | 2023-12-12 |  | 2024-01-15 | [6 empty] | 18.5 | 249 | 390 | [6 empty] | 0 | SEP | SEP |  | 5
38525 | HV-NT-0-212-002-100-CA | 2 | false | CH06822004-BD-PI-0579 | 100 | 5K | OG3 | H1 | T01967 | 2023-11-11 | 2023-11-23 | 2023-11-23 | 2023-12-12 |  | 2024-01-15 | [6 empty] | 17.8 | 249 | 390 | [6 empty] | 0 | SEP | SEP |  | 5
41856 | HV-NT-0-212-002-100-CA | 3 | true | CH06822004-BD-PI-0579 | 100 | 5K | OG3 | H1 | PEL-ZAU-T-032 | 2024-01-12 | 2024-01-15 | 2023-11-20 | 2024-01-18 | 2024-01-29 | 2024-02-01 | 2024-02-02 |  | 2024-02-09 |  |  | 2024-03-13 | 0.3 | 249 | 390 | Virgil Frinculescu |  |  | No change |  |  | 0 | SEP | SEP |  | 5
41857 | HV-NT-0-212-002-100-CA | 3 | true | CH06822004-BD-PI-0579 | 100 | 5K | OG3 | H1 | PEL-ZAU-T-032 | 2024-01-12 | 2024-01-15 | 2023-11-20 | 2024-01-18 | 2024-01-29 | 2024-02-01 | 2024-02-02 |  | 2024-02-09 |  |  | 2024-03-13 | 0.3 | 249 | 390 | Virgil Frinculescu |  |  | No change |  |  | 0 | SEP | SEP |  | 5
41858 | HV-NT-0-212-002-100-CA | 3 | true | CH06822004-BD-PI-0579 | 100 | 5K | OG3 | H1 | PEL-ZAU-T-032 | 2024-01-12 | 2024-01-15 | 2023-11-20 | 2024-01-18 | 2024-01-29 | 2024-02-01 | 2024-02-02 |  | 2024-02-09 |  | 2024-03-23 | 2024-06-06 | 18.5 | 249 | 390 | Virgil Frinculescu |  |  | Updated Positions of Thermowells etc. |  |  | 0 | SEP | SEP |  | 5
41859 | HV-NT-0-212-002-100-CA | 3 | true | CH06822004-BD-PI-0579 | 100 | 5K | OG3 | H1 | PEL-ZAU-T-032 | 2024-01-12 | 2024-01-15 | 2023-11-20 | 2024-01-18 | 2024-01-29 | 2024-02-01 | 2024-02-02 |  | 2024-02-09 |  |  | 2024-03-19 | 17.8 | 249 | 390 | Virgil Frinculescu |  |  | No change |  |  | 0 | SEP | SEP |  | 5
38526 | HV-NT-0-212-004-100-CA | 2 | false | CH06822004-BD-PI-0579 | 100 | 5K | OG3 | H1 | T01967 | 2023-11-11 | 2023-11-23 | 2023-11-23 | 2023-12-18 |  | 2024-01-15 | [6 empty] | 7.6 | 249 | 390 | [6 empty] | 0 | SEP | SEP |  | 5
38527 | HV-NT-0-212-004-100-CA | 2 | false | CH06822004-BD-PI-0579 | 100 | 5K | OG3 | H1 | T01967 | 2023-11-11 | 2023-11-23 | 2023-11-23 | 2023-12-18 |  | 2024-01-15 | [6 empty] | 9.6 | 249 | 390 | [6 empty] | 0 | SEP | SEP |  | 5
38528 | HV-NT-0-212-004-100-CA | 2 | false | CH06822004-BD-PI-0579 | 100 | 5K | OG3 | H1 | T01967 | 2023-11-11 | 2023-11-23 | 2023-11-23 | 2023-12-18 | 2024-01-15 | [7 empty] | 4.8 | 249 | 390 | [6 empty] | 0 | SEP | SEP |  | 5
38529 | HV-NT-0-212-004-100-CA | 2 | false | CH06822004-BD-PI-0579 | 100 | 5K | OG3 | H1 | T01967 | 2023-11-11 | 2023-11-23 | 2023-11-23 | 2023-12-18 |  | 2024-01-15 | [6 empty] | 0.2 | 249 | 390 | [6 empty] | 0 | SEP | SEP |  | 5
41860 | HV-NT-0-212-004-100-CA | 3 | true | CH06822004-BD-PI-0579 | 100 | 5K | OG3 | H1 | PEL-ZAU-T-032 | 2024-01-12 | 2024-01-15 | 2023-11-20 | 2024-01-18 | 2024-01-29 | 2024-02-01 | 2024-02-02 |  | 2024-02-09 |  | 2024-04-30 | 2024-06-06 | 7.6 | 249 | 390 | Virgil Frinculescu |  |  | Updated Positions of Thermowells etc. |  |  | 0 | SEP | SEP |  | 5
41861 | HV-NT-0-212-004-100-CA | 3 | true | CH06822004-BD-PI-0579 | 100 | 5K | OG3 | H1 | PEL-ZAU-T-032 | 2024-01-12 | 2024-01-15 | 2023-11-20 | 2024-01-18 | 2024-01-29 | 2024-02-01 | 2024-02-02 |  | 2024-02-09 |  |  | 2024-02-23 | 9.6 | 249 | 390 | Virgil Frinculescu |  |  | No change |  |  | 0 | SEP | SEP |  | 5
41862 | HV-NT-0-212-004-100-CA | 3 | true | CH06822004-BD-PI-0579 | 100 | 5K | OG3 | H1 | PEL-ZAU-T-032 | 2024-01-12 | 2024-01-15 | 2023-11-20 | 2024-01-18 | 2024-01-29 | 2024-02-01 | 2024-02-02 |  | 2024-02-09 |  |  | 2024-02-23 | 4.8 | 249 | 390 | Virgil Frinculescu |  |  | Updated Positions of Thermowells etc. |  |  | 0 | SEP | SEP |  | 5
41863 | HV-NT-0-212-004-100-CA | 3 | true | CH06822004-BD-PI-0579 | 100 | 5K | OG3 | H1 | PEL-ZAU-T-032 | 2024-01-12 | 2024-01-15 | 2023-11-20 | 2024-01-18 | 2024-01-29 | 2024-02-01 | 2024-02-02 |  | 2024-02-09 |  |  | 2024-02-23 | 0.2 | 249 | 390 | Virgil Frinculescu |  |  | No change |  |  | 0 | SEP | SEP |  | 5
38530 | HV-NT-0-212-006-20-CA | 2 | true | CH06822004-BD-PI-0579 | 20 | 5K | OG3 | H1 | T01967 | 2023-11-11 | 2023-11-23 | 2023-11-23 | 2024-01-09 | 2024-01-29 | 2024-02-01 | 2024-02-02 |  | 2024-02-09 |  |  | 2024-02-22 | 0.7 | 249 | 390 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 5
38531 | HV-NT-0-212-007-50-CA | 2 | false | CH06822004-BD-PI-0579 | 50 | 5K | OG3 | H1 | T01967 | 2023-11-11 | 2023-11-23 | 2023-11-23 | 2024-01-26 | 2024-01-30 | 2024-02-01 | 2024-02-02 |  | 2024-02-13 |  |  | 2024-02-22 | 11.3 | 249 | 390 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 5
45240 | HV-NT-0-212-007-50-CA | 3 | true | CH06822004-BD-PI-0579 | 50 | 5K | OG3 | H1 | T-059 | 2024-02-28 | 2023-11-23 | 2023-11-23 | 2024-01-26 | 2024-01-30 | 2024-02-01 | 2024-02-02 |  | 2024-02-13 |  | 2024-02-29 | 2024-06-27 | 11.5 | 249 | 390 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
38532 | HV-NT-0-212-008-50-CA | 2 | false | CH06822004-BD-PI-0579 | 50 | 5K | OG3 | H1 | T01967 | 2023-11-11 | 2023-11-23 | 2023-11-23 | 2024-01-04 | 2024-01-15 | 2024-02-01 | 2024-02-02 |  | 2024-02-13 |  |  | 2024-02-22 | 5.8 | 249 | 390 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 5
45241 | HV-NT-0-212-008-50-CA | 3 | true | CH06822004-BD-PI-0579 | 50 | 5K | OG3 | H1 | T-059 | 2024-02-28 | 2023-11-23 | 2023-11-23 | 2024-01-04 | 2024-01-15 | 2024-02-01 | 2024-02-02 |  | 2024-02-13 |  | 2024-02-29 | 2024-06-27 | 5.8 | 249 | 390 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
38533 | HV-NT-0-212-009-40-CA | 2 | false | CH06822004-BD-PI-0579 | 40 | 5K | OG3 | H1 | T01967 | 2023-11-11 | 2023-11-23 | 2023-11-23 | 2024-01-09 | 2024-01-30 | 2024-02-01 | 2024-02-02 |  | 2024-02-13 |  |  | 2024-02-23 | 6.7 | 249 | 390 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 5
45242 | HV-NT-0-212-009-40-CA | 3 | true | CH06822004-BD-PI-0579 | 40 | 5K | OG3 | H1 | T-059 | 2024-02-28 | 2023-11-23 | 2023-11-23 | 2024-01-09 | 2024-01-30 | 2024-02-01 | 2024-02-02 |  | 2024-02-13 |  | 2024-02-29 | 2024-03-07 | 6.8 | 249 | 390 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
38534 | HV-NT-0-212-010-65-CA | 2 | true | CH06822004-BD-PI-0579 | 65 | 5K | OG3 | H1 | T01967 | 2023-11-11 | 2023-11-23 | 2023-11-23 | 2024-01-04 |  | 2024-01-15 | 2024-02-02 |  | 2024-02-21 |  |  | 2024-02-28 | 20.7 | 249 | 390 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 5
38535 | HV-NT-0-212-011-40-CA | 2 | false | CH06822004-BD-PI-0579 | 40 | 5K | OG3 | H1 | T01967 | 2023-11-11 | 2023-11-23 | 2023-11-23 | 2024-01-09 | 2024-01-30 | 2024-02-01 | 2024-02-02 |  | 2024-02-21 |  |  |  | 12.3 | 249 | 390 | Attila Henter | [5 empty] | 0 | SEP | SEP |  | 5
45243 | HV-NT-0-212-011-40-CA | 3 | true | CH06822004-BD-PI-0579 | 40 | 5K | OG3 | H1 | T-059 | 2024-02-28 | 2023-11-23 | 2023-11-23 | 2024-01-09 | 2024-01-30 | 2024-02-01 | 2024-02-02 |  | 2024-02-21 |  |  | 2024-03-07 | 12.4 | 249 | 390 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
38536 | HV-NT-0-212-012-40-CA | 2 | false | CH06822004-BD-PI-0579 | 40 | 5K | OG3 | H1 | T01967 | 2023-11-11 | 2023-11-23 | 2023-11-23 | 2024-01-09 | 2024-01-30 | 2024-02-01 | 2024-02-02 |  | 2024-02-21 |  |  |  | 12.7 | 249 | 390 | Attila Henter | [5 empty] | 0 | SEP | SEP |  | 5
45244 | HV-NT-0-212-012-40-CA | 3 | true | CH06822004-BD-PI-0579 | 40 | 5K | OG3 | H1 | T-059 | 2024-02-28 | 2023-11-23 | 2023-11-23 | 2024-01-09 | 2024-01-30 | 2024-02-01 | 2024-02-02 |  | 2024-02-21 |  |  | 2024-03-07 | 12.8 | 249 | 390 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
38537 | KKR-0-241-001-100-SD5 | 2 | false | CH06822004-BD-PI-0593 | 100 | 5K | OG3 | C2 | T01967 | 2023-11-11 | 2023-11-21 | 2023-11-21 | 2023-12-06 |  | 2024-01-10 | 2024-01-12 |  | 2024-01-25 |  |  | 2024-02-07 | 6.7 | 260 | 391 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 5
38538 | KKR-0-241-001-100-SD5 | 2 | false | CH06822004-BD-PI-0593 | 100 | 5K | OG3 | C2 | T01967 | 2023-11-11 | 2023-11-21 | 2023-11-21 | 2023-12-06 |  | 2024-01-10 | 2024-01-12 |  | 2024-01-25 |  |  |  | 11.8 | 260 | 391 | Attila Henter | [5 empty] | 0 | SEP | SEP |  | 5
38539 | KKR-0-241-001-100-SD5 | 2 | false | CH06822004-BD-PI-0593 | 100 | 5K | OG3 | C2 | T01967 | 2023-11-11 | 2023-11-21 | 2023-11-21 | 2023-12-06 |  | 2024-01-10 | 2024-01-12 |  | 2024-01-25 |  |  |  | 20.7 | 260 | 391 | Attila Henter | [5 empty] | 0 | SEP | SEP |  | 5
38540 | KKR-0-241-001-100-SD5 | 2 | false | CH06822004-BD-PI-0593 | 100 | 5K | OG3 | C2 | T01967 | 2023-11-11 | 2023-11-21 | 2023-11-21 | 2023-12-06 |  | 2024-01-10 | 2024-01-12 |  | 2024-01-25 |  |  |  | 9.8 | 260 | 391 | Attila Henter | [5 empty] | 0 | SEP | SEP |  | 5
38541 | KKR-0-241-001-100-SD5 | 2 | false | CH06822004-BD-PI-0593 | 100 | 5K | OG3 | C2 | T01967 | 2023-11-11 | 2023-11-21 | 2023-11-21 | 2023-12-06 |  | 2024-01-10 | 2024-01-12 |  | 2024-01-25 |  |  |  | 4.9 | 260 | 391 | Attila Henter | [5 empty] | 0 | SEP | SEP |  | 5
38542 | KKR-0-241-001-100-SD5 | 2 | false | CH06822004-BD-PI-0593 | 100 | 5K | OG3 | C2 | T01967 | 2023-11-11 | 2023-11-21 | 2023-11-21 | 2023-12-06 |  | 2024-01-10 | 2024-01-12 |  | 2024-01-25 |  |  |  | 3.1 | 260 | 391 | Attila Henter | [5 empty] | 0 | SEP | SEP |  | 5
41886 | KKR-0-241-001-100-SD5 | 3 | true | CH06822004-BD-PI-0593 | 100 | 5K | OG3 | C2 | PEL-ZAU-T-033 | 2024-01-12 | 2023-11-21 | 2023-11-21 | 2023-12-06 |  | 2024-01-10 | 2024-01-12 |  | 2024-01-25 |  |  | 2024-02-07 | 6.7 | 260 | 391 | Virgil Frinculescu |  |  |  | No change |  | 0 | SEP | SEP |  | 5
41887 | KKR-0-241-001-100-SD5 | 3 | true | CH06822004-BD-PI-0593 | 100 | 5K | OG3 | C2 | PEL-ZAU-T-033 | 2024-01-12 | 2023-11-21 | 2023-11-21 | 2023-12-06 |  | 2024-01-10 | 2024-01-12 |  | 2024-01-25 |  |  | 2024-02-26 | 11.8 | 260 | 391 | Virgil Frinculescu |  |  |  | No change |  | 0 | SEP | SEP |  | 5
41888 | KKR-0-241-001-100-SD5 | 3 | true | CH06822004-BD-PI-0593 | 100 | 5K | OG3 | C2 | PEL-ZAU-T-033 | 2024-01-12 | 2023-11-21 | 2023-11-21 | 2023-12-06 |  | 2024-01-10 | 2024-01-12 |  | 2024-01-25 |  |  | 2024-02-26 | 16.2 | 260 | 391 | Virgil Frinculescu |  |  |  | No change |  | 0 | SEP | SEP |  | 5
41889 | KKR-0-241-001-100-SD5 | 3 | true | CH06822004-BD-PI-0593 | 100 | 5K | OG3 | C2 | PEL-ZAU-T-033 | 2024-01-12 | 2023-11-21 | 2023-11-21 | 2023-12-06 |  | 2024-01-10 | 2024-01-12 |  | 2024-01-25 |  | 2024-04-30 | 2024-05-24 | 14.3 | 260 | 391 | Virgil Frinculescu |  |  |  | No change |  | 0 | SEP | SEP |  | 5
41890 | KKR-0-241-001-100-SD5 | 3 | true | CH06822004-BD-PI-0593 | 100 | 5K | OG3 | C2 | PEL-ZAU-T-033 | 2024-01-12 | 2023-11-21 | 2023-11-21 | 2023-12-06 |  | 2024-01-10 | 2024-01-12 |  | 2024-01-25 |  | 2024-05-11 | 2024-05-24 | 4.9 | 260 | 391 | Virgil Frinculescu |  |  |  | No change |  | 0 | SEP | SEP |  | 5
41891 | KKR-0-241-001-100-SD5 | 3 | true | CH06822004-BD-PI-0593 | 100 | 5K | OG3 | C2 | PEL-ZAU-T-033 | 2024-01-12 | 2023-11-21 | 2023-11-21 | 2023-12-06 |  | 2024-01-10 | 2024-01-12 |  | 2024-01-25 | 2024-04-30 |  | 2024-05-24 | 3.1 | 260 | 391 | Virgil Frinculescu |  |  |  | Updated Positions of Thermowells etc. |  | 0 | SEP | SEP |  | 5
38543 | KKR-0-241-003-100-SD5 | 2 | false | CH06822004-BD-PI-0593 | 100 | 5K | OG3 | C2 | T01967 | 2023-11-11 | 2023-11-21 | 2023-11-21 | 2023-12-11 |  | 2024-01-10 | 2024-01-12 | [5 empty] | 0.1 | 260 | 391 | [6 empty] | 0 | SEP | SEP |  | 5
38544 | KKR-0-241-003-100-SD5 | 2 | false | CH06822004-BD-PI-0593 | 100 | 5K | OG3 | C2 | T01967 | 2023-11-11 | 2023-11-21 | 2023-11-21 | 2023-11-23 |  | 2024-01-10 | 2024-01-12 | [5 empty] | 2.3 | 260 | 391 | [6 empty] | 0 | SEP | SEP |  | 5
38545 | KKR-0-241-008-65-SD5 | 2 | true | CH06822004-BD-PI-0593 | 65 | 5K | OG3 | C2 | T01967 | 2023-11-11 | 2023-11-21 | 2023-11-21 | 2023-12-15 |  | 2024-01-10 | 2024-01-12 |  | 2024-02-27 |  |  | 2024-03-07 | 2.5 | 260 | 391 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 5
38546 | KKR-0-241-009-65-SD5 | 2 | true | CH06822004-BD-PI-0593 | 65 | 5K | OG3 | C2 | T01967 | 2023-11-11 | 2023-11-21 | 2023-11-21 | 2023-12-15 |  | 2024-01-10 | 2024-01-12 |  | 2024-02-27 |  |  | 2024-03-07 | 3 | 260 | 391 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 5
38547 | KKV-0-241-001-080-SD5 | 2 | false | CH06822004-BD-PI-0593 | 100 | 5K | OG3 | C2 | T01967 | 2023-11-11 | 2023-11-21 | 2023-11-21 | 2023-12-07 |  | 2023-12-20 | 2024-01-12 | [5 empty] | 0.9 | 260 | 392 | [6 empty] | 0 | SEP | SEP |  | 5
43463 | KKV-0-241-001-080-SD5 | 4 | true | CH06822004-BD-PI-0593 | 100 | 5K | OG3 | C2 | T-046 | 2024-01-25 | [5 empty] | 2024-02-12 |  | 2024-03-07 |  | 2024-04-30 | 2024-05-24 | 0.7 | 260 | 392 | Virgil Frinculescu |  |  |  | OLD ID and Line No.: 38547_KKV-0-241-001-100-SD5 |  | 0 | SEP | SEP
38548 | KKV-0-241-002-100-SD5 | 2 | false | CH06822004-BD-PI-0593 | 100 | 5K | OG3 | C2 | T01967 | 2023-11-11 | 2023-11-21 | 2023-11-21 | 2023-11-23 |  | 2023-12-20 | 2024-01-12 |  | 2024-01-25 |  |  |  | 12.8 | 260 | 392 | Attila Henter | [5 empty] | 0 | SEP | SEP |  | 5
38549 | KKV-0-241-002-100-SD5 | 2 | false | CH06822004-BD-PI-0593 | 100 | 5K | OG3 | C2 | T01967 | 2023-11-11 | 2023-11-21 | 2023-11-21 | 2023-11-23 |  | 2023-12-20 | 2024-01-12 |  | 2024-01-25 |  |  |  | 9.3 | 260 | 392 | Attila Henter | [5 empty] | 0 | SEP | SEP |  | 5
38550 | KKV-0-241-002-100-SD5 | 2 | false | CH06822004-BD-PI-0593 | 100 | 5K | OG3 | C2 | T01967 | 2023-11-11 | 2023-11-21 | 2023-11-21 | 2023-11-23 |  | 2023-12-20 | 2024-01-12 |  | 2024-01-25 |  |  |  | 13.8 | 260 | 392 | Attila Henter | [5 empty] | 0 | SEP | SEP |  | 5
38551 | KKV-0-241-002-100-SD5 | 2 | false | CH06822004-BD-PI-0593 | 100 | 5K | OG3 | C2 | T01967 | 2023-11-11 | 2023-11-21 | 2023-11-21 | 2023-11-23 |  | 2023-12-20 | 2024-01-12 |  | 2024-01-25 |  |  |  | 11.8 | 260 | 392 | Attila Henter | [5 empty] | 0 | SEP | SEP |  | 5
38552 | KKV-0-241-002-100-SD5 | 2 | false | CH06822004-BD-PI-0593 | 100 | 5K | OG3 | C2 | T01967 | 2023-11-11 | 2023-11-21 | 2023-11-21 | 2023-11-23 |  | 2023-12-20 | 2024-01-12 |  | 2024-01-25 |  |  | 2024-02-06 | 3.8 | 260 | 392 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 5
38553 | KKV-0-241-002-100-SD5 | 2 | false | CH06822004-BD-PI-0593 | 100 | 5K | OG3 | C2 | T01967 | 2023-11-11 | 2023-11-21 | 2023-11-21 | 2023-11-23 |  | 2023-12-20 | 2024-01-12 |  | 2024-01-25 |  |  | 2024-02-06 | 4.1 | 260 | 392 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 5
38916 | KKV-0-241-002-100-SD5 | 3 | false | CH06822004-BD-PI-0593 | 100 | 5K | OG3 | C2 | T02261 | 2023-11-20 | [11 empty] | 0.4 | 260 | 392 | [6 empty] | 0 | SEP | SEP |  | 5
38917 | KKV-0-241-002-100-SD5 | 3 | false | CH06822004-BD-PI-0593 | 100 | 5K | OG3 | C2 | T02261 | 2023-11-20 | [11 empty] | 23.1 | 260 | 392 | [6 empty] | 0 | SEP | SEP |  | 5
38918 | KKV-0-241-002-100-SD5 | 3 | false | CH06822004-BD-PI-0593 | 100 | 5K | OG3 | C2 | T02261 | 2023-11-20 | [11 empty] | 9.3 | 260 | 392 | [6 empty] | 0 | SEP | SEP |  | 5
38919 | KKV-0-241-002-100-SD5 | 3 | false | CH06822004-BD-PI-0593 | 100 | 5K | OG3 | C2 | T02261 | 2023-11-20 | [11 empty] | 13.8 | 260 | 392 | [6 empty] | 0 | SEP | SEP |  | 5
38920 | KKV-0-241-002-100-SD5 | 3 | false | CH06822004-BD-PI-0593 | 100 | 5K | OG3 | C2 | T02261 | 2023-11-20 | [11 empty] | 11.8 | 260 | 392 | [6 empty] | 0 | SEP | SEP |  | 5
38921 | KKV-0-241-002-100-SD5 | 3 | false | CH06822004-BD-PI-0593 | 100 | 5K | OG3 | C2 | T02261 | 2023-11-20 | [11 empty] | 3.8 | 260 | 392 | [6 empty] | 0 | SEP | SEP |  | 5
38922 | KKV-0-241-002-100-SD5 | 3 | false | CH06822004-BD-PI-0593 | 100 | 5K | OG3 | C2 | T02261 | 2023-11-20 | [11 empty] | 4.1 | 260 | 392 | [6 empty] | 0 | SEP | SEP |  | 5
41900 | KKV-0-241-002-100-SD5 | 4 | true | CH06822004-BD-PI-0593 | 100 | 5K | OG3 | C2 | PEL-ZAU-T-033 | 2024-01-12 | 2023-11-20 | 2023-11-20 | 2023-11-22 | 2023-12-01 | 2023-12-20 | 2024-01-12 |  | 2024-01-25 |  |  | 2024-03-21 | 0.4 | 260 | 392 | Virgil Frinculescu |  |  |  | No change |  | 0 | SEP | SEP |  | 5
41901 | KKV-0-241-002-100-SD5 | 4 | true | CH06822004-BD-PI-0593 | 100 | 5K | OG3 | C2 | PEL-ZAU-T-033 | 2024-01-12 | 2023-11-20 | 2023-11-20 | 2023-11-22 | 2023-12-01 | 2023-12-20 | 2024-01-12 |  | 2024-01-25 | 2024-04-30 | 2024-05-11 | 2024-05-24 | 13.1 | 260 | 392 | Virgil Frinculescu |  |  |  | No change |  | 0 | SEP | SEP |  | 5
41902 | KKV-0-241-002-100-SD5 | 4 | true | CH06822004-BD-PI-0593 | 100 | 5K | OG3 | C2 | PEL-ZAU-T-033 | 2024-01-12 | 2023-11-20 | 2023-11-20 | 2023-11-22 | 2023-12-01 | 2023-12-20 | 2024-01-12 |  | 2024-01-25 |  |  | 2024-02-20 | 9.3 | 260 | 392 | Virgil Frinculescu |  |  |  | No change |  | 0 | SEP | SEP |  | 5
41903 | KKV-0-241-002-100-SD5 | 4 | true | CH06822004-BD-PI-0593 | 100 | 5K | OG3 | C2 | PEL-ZAU-T-033 | 2024-01-12 | 2023-11-20 | 2023-11-20 | 2023-11-22 | 2023-12-01 | 2023-12-20 | 2024-01-12 |  | 2024-01-25 |  |  | 2024-02-15 | 13.8 | 260 | 392 | Virgil Frinculescu |  |  |  | No change |  | 0 | SEP | SEP |  | 5
41904 | KKV-0-241-002-100-SD5 | 4 | true | CH06822004-BD-PI-0593 | 100 | 5K | OG3 | C2 | PEL-ZAU-T-033 | 2024-01-12 | 2023-11-20 | 2023-11-20 | 2023-11-22 | 2023-12-01 | 2023-12-20 | 2024-01-12 |  | 2024-01-25 |  |  | 2024-02-12 | 11.8 | 260 | 392 | Virgil Frinculescu |  |  |  | No change |  | 0 | SEP | SEP |  | 5
41905 | KKV-0-241-002-100-SD5 | 4 | true | CH06822004-BD-PI-0593 | 100 | 5K | OG3 | C2 | PEL-ZAU-T-033 | 2024-01-12 | 2023-11-20 | 2023-11-20 | 2023-11-22 | 2023-12-01 | 2023-12-20 | 2024-01-12 |  | 2024-01-25 |  |  | 2024-02-06 | 3.8 | 260 | 392 | Virgil Frinculescu |  |  |  | No change |  | 0 | SEP | SEP |  | 5
41906 | KKV-0-241-002-100-SD5 | 4 | true | CH06822004-BD-PI-0593 | 100 | 5K | OG3 | C2 | PEL-ZAU-T-033 | 2024-01-12 | 2023-11-20 | 2023-11-20 | 2023-11-22 | 2023-12-01 | 2023-12-20 | 2024-01-12 |  | 2024-01-25 |  |  | 2024-02-06 | 4.1 | 260 | 392 | Virgil Frinculescu |  |  |  | No change |  | 0 | SEP | SEP |  | 5
38558 | KKV-0-241-008-65-SD5 | 2 | false | CH06822004-BD-PI-0593 | 65 | 5K | OG3 | C2 | T01967 | 2023-11-11 | 2023-11-21 | 2023-11-21 | 2023-12-11 | 2024-01-12 | 2024-01-16 | 2024-01-19 | [5 empty] | 2.7 | 260 | 392 | [6 empty] | 0 | SEP | SEP |  | 5
38559 | KKV-0-241-008-65-SD5 | 2 | false | CH06822004-BD-PI-0593 | 65 | 5K | OG3 | C2 | T01967 | 2023-11-11 | 2023-11-21 | 2023-11-21 | 2023-12-11 | 2024-01-12 | 2024-01-16 | 2024-01-19 | [5 empty] | 0.6 | 260 | 392 | [6 empty] | 0 | SEP | SEP |  | 5
38560 | KKV-0-241-009-65-SD5 | 2 | true | CH06822004-BD-PI-0593 | 65 | 5K | OG3 | C2 | T01967 | 2023-11-11 | 2023-11-21 | 2023-11-21 | 2023-12-12 | 2024-01-12 | 2024-01-16 | 2024-01-19 |  | 2024-02-27 |  |  | 2024-03-07 | 2.3 | 260 | 392 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 5
38561 | KKV-0-241-010-65-SD5 | 2 | true | CH06822004-BD-PI-0593 | 65 | 5K | OG3 | C2 | T01967 | 2023-11-11 | 2023-11-21 | 2023-11-21 | 2023-12-12 | 2024-01-12 | 2024-01-16 | 2024-01-19 |  | 2024-02-27 |  |  | 2024-03-07 | 1.8 | 260 | 392 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 5
38562 | KR-0-216-005-100-SD5 | 2 | false | CH06822004-BD-PI-0607 | 100 | 5K | OG3 | C2 | T01967 | 2023-11-11 |  | 2023-11-20 | 2023-11-22 |  | 2023-12-19 | 2024-01-12 |  | 2024-01-30 |  |  |  | 0.7 | 260 | 393 | Martin Kovacic | [5 empty] | 0 | SEP | SEP |  | 5
38563 | KR-0-216-005-100-SD5 | 2 | false | CH06822004-BD-PI-0607 | 100 | 5K | OG3 | C2 | T01967 | 2023-11-11 |  | 2023-11-20 | 2023-11-22 |  | 2023-12-19 | 2024-01-12 |  | 2024-01-30 |  |  |  | 2.9 | 260 | 393 | Martin Kovacic | [5 empty] | 0 | SEP | SEP |  | 5
38564 | KR-0-216-005-100-SD5 | 2 | false | CH06822004-BD-PI-0607 | 100 | 5K | OG3 | C2 | T01967 | 2023-11-11 |  | 2023-11-20 | 2023-11-22 |  | 2024-01-18 | 2024-01-19 |  | 2024-01-30 |  |  |  | 5.2 | 260 | 393 | Martin Kovacic | [5 empty] | 0 | SEP | SEP |  | 5
38565 | KR-0-216-005-100-SD5 | 2 | false | CH06822004-BD-PI-0607 | 100 | 5K | OG3 | C2 | T01967 | 2023-11-11 |  | 2023-11-20 | 2023-11-22 |  | 2024-01-18 | 2024-01-19 |  | 2024-01-30 |  |  |  | 9.7 | 260 | 393 | Martin Kovacic | [5 empty] | 0 | SEP | SEP |  | 5
38566 | KR-0-216-005-100-SD5 | 2 | false | CH06822004-BD-PI-0607 | 100 | 5K | OG3 | C2 | T01967 | 2023-11-11 |  | 2023-11-20 | 2023-11-22 |  | 2024-01-18 | 2024-01-19 |  | 2024-01-30 |  |  |  | 7.7 | 260 | 393 | Martin Kovacic | [5 empty] | 0 | SEP | SEP |  | 5
41918 | KR-0-216-005-100-SD5 | 3 | true | CH06822004-BD-PI-0607 | 100 | 5K | OG3 | C2 | PEL-ZAU-T-036 | 2024-01-12 |  | 2023-11-20 | 2023-11-22 |  | 2023-12-19 | 2024-01-12 |  | 2024-01-30 |  |  | 2024-02-09 | 0.8 | 260 | 393 | Virgil Frinculescu |  |  |  | Updated Pipe Lenghts DN20 |  | 0 | SEP | SEP |  | 5
41919 | KR-0-216-005-100-SD5 | 3 | true | CH06822004-BD-PI-0607 | 100 | 5K | OG3 | C2 | PEL-ZAU-T-036 | 2024-01-12 |  | 2023-11-20 | 2023-11-22 |  | 2023-12-19 | 2024-01-12 |  | 2024-01-30 |  |  | 2024-02-09 | 2.9 | 260 | 393 | Virgil Frinculescu |  |  |  | Updated Positions of Thermowells etc. |  | 0 | SEP | SEP |  | 5
41920 | KR-0-216-005-100-SD5 | 3 | true | CH06822004-BD-PI-0607 | 100 | 5K | OG3 | C2 | PEL-ZAU-T-036 | 2024-01-12 |  | 2023-11-20 | 2023-11-22 |  |  |  |  | 2024-01-30 |  |  | 2024-02-09 | 5.2 | 260 | 393 | Virgil Frinculescu |  |  |  | No change |  | 0 | SEP | SEP |  | 5
41921 | KR-0-216-005-100-SD5 | 3 | true | CH06822004-BD-PI-0607 | 100 | 5K | OG3 | C2 | PEL-ZAU-T-036 | 2024-01-12 |  | 2023-11-20 | 2023-11-22 |  | 2024-01-18 | 2024-01-19 |  | 2024-01-30 |  |  | 2024-02-09 | 9.2 | 260 | 393 | Virgil Frinculescu |  |  |  | No change |  | 0 | SEP | SEP |  | 5
41922 | KR-0-216-005-100-SD5 | 3 | true | CH06822004-BD-PI-0607 | 100 | 5K | OG3 | C2 | PEL-ZAU-T-036 | 2024-01-12 |  | 2023-11-20 | 2023-11-22 |  | 2024-01-18 | 2024-01-19 |  | 2024-01-30 |  | 2024-03-23 | 2024-05-21 | 7.7 | 260 | 393 | Virgil Frinculescu |  |  |  | Updated Positions of Thermowells etc. |  | 0 | SEP | SEP |  | 5
38567 | KR-0-216-025-40-SD5 | 2 | false | CH06822004-BD-PI-0607 | 40 | 5K | OG3 | C2 | T01967 | 2023-11-11 |  | 2023-11-20 | 2023-11-22 |  | 2023-12-06 | 2023-12-15 |  | 2024-02-12 |  |  | 2024-02-15 | 11.7 | 260 | 393 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 5
44751 | KR-0-216-025-40-SD5 | 4 | true | CH06822004-BD-PI-0607 | 40 | 5K | OG3 | C2 | T-055 | 2024-02-16 |  | 2023-11-20 | 2023-11-22 |  | 2023-12-06 | 2023-12-15 |  | 2024-03-08 |  | 2024-02-15 | 2024-03-25 | 11.8 | 260 | 393 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
38568 | KR-0-216-026-40-SD5 | 2 | false | CH06822004-BD-PI-0607 | 40 | 5K | OG3 | C2 | T01967 | 2023-11-11 |  | 2023-11-20 | 2023-11-22 | 2023-12-06 | 2023-12-06 | 2023-12-15 |  | 2024-02-12 |  |  | 2024-02-15 | 12.1 | 260 | 393 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 5
44752 | KR-0-216-026-40-SD5 | 4 | true | CH06822004-BD-PI-0607 | 40 | 5K | OG3 | C2 | T-055 | 2024-02-16 |  | 2023-11-20 | 2023-11-22 | 2023-12-06 | 2023-12-06 | 2023-12-15 |  | 2024-03-08 |  | 2024-02-15 | 2024-03-25 | 12.2 | 260 | 393 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
38569 | KR-0-216-027-65-SD5 | 2 | false | CH06822004-BD-PI-0607 | 65 | 5K | OG3 | C2 | T01967 | 2023-11-11 |  | 2023-11-20 | 2023-12-15 | 2024-01-12 | 2024-01-26 | 2024-02-02 |  | 2024-02-12 |  |  | 2024-02-23 | 9.5 | 260 | 393 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 5
45245 | KR-0-216-027-65-SD5 | 3 | true | CH06822004-BD-PI-0607 | 65 | 5K | OG3 | C2 | T-059 | 2024-02-28 |  | 2023-11-20 | 2023-12-15 | 2024-01-12 | 2024-01-26 | 2024-02-02 |  | 2024-03-07 |  | 2024-02-29 | 2024-06-24 | 9.5 | 260 | 393 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
38570 | KR-0-216-028-65-SD5 | 2 | false | CH06822004-BD-PI-0607 | 65 | 5K | OG3 | C2 | T01967 | 2023-11-11 |  | 2023-11-20 | 2023-12-15 | 2024-01-12 | 2024-01-26 | 2024-02-02 |  | 2024-02-12 |  |  | 2024-02-20 | 6.3 | 260 | 393 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 5
45246 | KR-0-216-028-65-SD5 | 3 | true | CH06822004-BD-PI-0607 | 65 | 5K | OG3 | C2 | T-059 | 2024-02-28 |  | 2023-11-20 | 2023-12-15 | 2024-01-12 | 2024-01-26 | 2024-02-02 |  | 2024-03-08 |  | 2024-02-29 | 2024-06-24 | 6.3 | 260 | 393 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
38571 | KR-0-216-029-40-SD5 | 2 | false | CH06822004-BD-PI-0607 | 40 | 5K | OG3 | C2 | T01967 | 2023-11-11 |  | 2023-11-20 | 2023-11-22 |  | 2023-12-04 | 2023-12-05 |  | 2024-02-12 |  |  | 2024-02-20 | 7.7 | 260 | 393 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 5
45247 | KR-0-216-029-40-SD5 | 3 | true | CH06822004-BD-PI-0607 | 40 | 5K | OG3 | C2 | T-059 | 2024-02-28 |  | 2023-11-20 | 2023-11-22 |  | 2023-12-04 | 2023-12-05 |  | 2024-03-08 |  | 2024-02-29 | 2024-03-25 | 7.8 | 260 | 393 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
38572 | KR-0-216-030-32-SD5 | 2 | false | CH06822004-BD-PI-0607 | 32 | 5K | OG3 | C2 | T01967 | 2023-11-11 |  | 2023-11-20 | 2023-12-11 |  | 2024-01-05 | 2024-01-12 | [5 empty] | 18 | 260 | 393 |  |  |  |  | This routing is deleted, and the new routing is under ID 43991 |  | 0 | SEP | SEP |  | 5
38573 | KR-0-216-030-32-SD5 | 2 | false | CH06822004-BD-PI-0607 | 32 | 5K | OG3 | C2 | T01967 | 2023-11-11 |  | 2023-11-20 | 2023-12-11 |  | 2024-01-05 | 2024-01-12 | [5 empty] | 13.1 | 260 | 393 |  |  |  |  | This routing is deleted, and the new routing is under ID 43991 |  | 0 | SEP | SEP |  | 5
43990 | KR-0-216-030-32-SD5 | 3 | false | CH06822004-BD-PI-0607 | 32 | 5K | OG3 | C2 | T-051 | 2024-02-01 |  | 2023-11-20 | 2023-12-11 |  | 2024-01-05 | 2024-01-12 | [5 empty] | 0.3 | 260 | 393 |  |  |  |  | DELETED |  | 0 | SEP | SEP
43991 | KR-0-216-030-32-SD5 | 3 | true | CH06822004-BD-PI-0607 | 32 | 5K | OG3 | C2 | T-051 | 2024-02-01 |  | 2023-11-20 | 2023-12-11 |  | 2024-01-05 | 2024-01-12 |  | 2024-02-12 |  |  | 2024-02-15 | 0.3 | 260 | 393 | Virgil Frinculescu |  |  |  | Latest rev. 3 is added to the w.map. |  | 0 | SEP | SEP
38574 | KR-0-216-032-20-SD5 | 2 | true | CH06822004-BD-PI-0607 | 20 | 5K | OG3 | C2 | T01967 | 2023-11-11 |  | 2023-11-20 | 2023-11-29 | 2024-01-12 | 2024-01-18 | 2024-01-19 |  | 2024-02-01 |  |  | 2024-02-09 | 0.2 | 260 | 393 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 5
38575 | KV-0-216-006-100-SD5 | 2 | false | CH06822004-BD-PI-0607 | 100 | 5K | OG3 | C2 | T01967 | 2023-11-11 |  | 2023-11-20 | 2023-11-22 |  | 2024-01-18 | 2024-01-19 |  | 2024-01-31 |  |  |  | 7.4 | 260 | 394 | Jozef Kotul | [5 empty] | 0 | SEP | SEP |  | 5
38576 | KV-0-216-006-100-SD5 | 2 | false | CH06822004-BD-PI-0607 | 100 | 5K | OG3 | C2 | T01967 | 2023-11-11 |  | 2023-11-20 | 2023-11-22 |  | 2024-01-18 | 2024-01-19 |  | 2024-01-31 |  |  |  | 9.4 | 260 | 394 | Jozef Kotul | [5 empty] | 0 | SEP | SEP |  | 5
38577 | KV-0-216-006-100-SD5 | 2 | false | CH06822004-BD-PI-0607 | 100 | 5K | OG3 | C2 | T01967 | 2023-11-11 |  | 2023-11-20 | 2023-11-22 |  | 2024-01-18 | 2024-01-19 |  | 2024-01-31 |  |  |  | 4.9 | 260 | 394 | Jozef Kotul | [5 empty] | 0 | SEP | SEP |  | 5
38578 | KV-0-216-006-100-SD5 | 2 | false | CH06822004-BD-PI-0607 | 100 | 5K | OG3 | C2 | T01967 | 2023-11-11 |  | 2023-11-20 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2023-12-05 |  | 2024-01-31 |  |  |  | 2.6 | 260 | 394 | Jozef Kotul | [5 empty] | 0 | SEP | SEP |  | 5
38579 | KV-0-216-006-100-SD5 | 2 | false | CH06822004-BD-PI-0607 | 100 | 5K | OG3 | C2 | T01967 | 2023-11-11 |  | 2023-11-20 | 2023-11-22 | 2023-12-10 | 2023-12-10 | 2024-01-12 |  | 2024-01-31 |  |  |  | 0.3 | 260 | 394 | Jozef Kotul | [5 empty] | 0 | SEP | SEP |  | 5
41866 | KV-0-216-006-100-SD5 | 3 | true | CH06822004-BD-PI-0607 | 100 | 5K | OG3 | C2 | PEL-ZAU-T-035 | 2024-01-13 |  | 2023-11-20 | 2023-11-22 |  |  |  |  | 2024-01-31 |  | 2024-03-23 | 2024-05-23 | 7.4 | 260 | 394 | Virgil Frinculescu |  |  |  | Updated Positions of Thermowells etc. + Stub In Changed |  | 0 | SEP | SEP |  | 5
41867 | KV-0-216-006-100-SD5 | 3 | true | CH06822004-BD-PI-0607 | 100 | 5K | OG3 | C2 | PEL-ZAU-T-035 | 2024-01-13 |  | 2023-11-20 | 2023-11-22 |  |  |  |  | 2024-01-31 |  |  | 2024-02-09 | 8.9 | 260 | 394 | Virgil Frinculescu |  |  |  | No change |  | 0 | SEP | SEP |  | 5
41868 | KV-0-216-006-100-SD5 | 3 | false | CH06822004-BD-PI-0607 | 100 | 5K | OG3 | C2 | PEL-ZAU-T-035 | 2024-01-13 |  | 2023-11-20 | 2023-11-22 |  |  |  |  | 2024-01-31 |  |  | 2024-02-09 | 4.9 | 260 | 394 | Virgil Frinculescu |  |  |  | No change |  | 0 | SEP | SEP |  | 5
41869 | KV-0-216-006-100-SD5 | 3 | true | CH06822004-BD-PI-0607 | 100 | 5K | OG3 | C2 | PEL-ZAU-T-035 | 2024-01-13 |  | 2023-11-20 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2023-12-05 |  | 2024-01-31 |  |  | 2024-02-09 | 2.6 | 260 | 394 | Virgil Frinculescu |  |  |  | Updated Positions of Thermowells etc. |  | 0 | SEP | SEP |  | 5
41870 | KV-0-216-006-100-SD5 | 3 | true | CH06822004-BD-PI-0607 | 100 | 5K | OG3 | C2 | PEL-ZAU-T-035 | 2024-01-13 |  | 2023-11-20 | 2023-11-22 | 2023-12-10 | 2023-12-10 | 2024-01-12 |  | 2024-01-31 |  |  | 2024-02-09 | 0.3 | 260 | 394 | Virgil Frinculescu |  |  |  | No change |  | 0 | SEP | SEP |  | 5
38580 | KV-0-216-026-40-SD5 | 2 | false | CH06822004-BD-PI-0607 | 40 | 5K | OG3 | C2 | T01967 | 2023-11-11 |  | 2023-11-20 | 2023-11-23 |  | 2023-12-20 | 2024-01-12 |  | 2024-02-12 |  |  | 2024-02-15 | 13 | 260 | 394 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 5
45248 | KV-0-216-026-40-SD5 | 3 | true | CH06822004-BD-PI-0607 | 40 | 5K | OG3 | C2 | T-059 | 2024-02-28 |  | 2023-11-20 | 2023-11-23 |  | 2023-12-20 | 2024-01-12 |  | 2024-03-08 |  | 2024-02-29 | 2024-03-25 | 13.1 | 260 | 394 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
38581 | KV-0-216-027-40-SD5 | 2 | false | CH06822004-BD-PI-0607 | 40 | 5K | OG3 | C2 | T01967 | 2023-11-11 |  | 2023-11-20 | 2023-11-23 |  | 2024-01-05 | 2024-01-12 |  | 2024-02-12 |  |  | 2024-02-15 | 12.6 | 260 | 394 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 5
45249 | KV-0-216-027-40-SD5 | 3 | true | CH06822004-BD-PI-0607 | 40 | 5K | OG3 | C2 | T-059 | 2024-02-28 |  | 2023-11-20 | 2023-11-23 |  | 2024-01-05 | 2024-01-12 |  | 2024-03-08 |  | 2024-02-29 | 2024-03-25 | 12.7 | 260 | 394 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
38582 | KV-0-216-028-65-SD5 | 2 | false | CH06822004-BD-PI-0607 | 65 | 5K | OG3 | C2 | T01967 | 2023-11-11 |  | 2023-11-20 | 2023-12-15 |  | 2024-01-05 | 2024-01-12 |  | 2024-02-12 |  |  | 2024-02-23 | 10 | 260 | 394 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 5
45250 | KV-0-216-028-65-SD5 | 3 | true | CH06822004-BD-PI-0607 | 65 | 5K | OG3 | C2 | T-059 | 2024-02-28 |  | 2023-11-20 | 2023-12-15 |  | 2024-01-05 | 2024-01-12 |  | 2024-03-07 |  | 2024-02-29 | 2024-06-24 | 10 | 260 | 394 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
38583 | KV-0-216-029-65-SD5 | 2 | false | CH06822004-BD-PI-0607 | 65 | 5K | OG3 | C2 | T01967 | 2023-11-11 |  | 2023-11-20 | 2023-12-15 | 2024-01-12 | 2024-01-26 | 2024-02-02 |  | 2024-02-12 |  |  | 2024-02-20 | 6.5 | 260 | 394 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 5
45251 | KV-0-216-029-65-SD5 | 3 | true | CH06822004-BD-PI-0607 | 65 | 5K | OG3 | C2 | T-059 | 2024-02-28 |  | 2023-11-20 | 2023-12-15 | 2024-01-12 | 2024-01-26 | 2024-02-02 |  | 2024-03-08 |  | 2024-02-29 | 2024-06-24 | 6.5 | 260 | 394 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
38584 | KV-0-216-030-40-SD5 | 2 | false | CH06822004-BD-PI-0607 | 40 | 5K | OG3 | C2 | T01967 | 2023-11-11 |  | 2023-11-20 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2023-12-05 |  | 2024-02-12 |  |  | 2024-02-20 | 8 | 260 | 394 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 5
45252 | KV-0-216-030-40-SD5 | 3 | true | CH06822004-BD-PI-0607 | 40 | 5K | OG3 | C2 | T-059 | 2024-02-28 |  | 2023-11-20 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2023-12-05 |  | 2024-03-08 |  | 2024-02-29 | 2024-03-25 | 10 | 260 | 394 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
38585 | KV-0-216-031-32-SD5 | 2 | false | CH06822004-BD-PI-0607 | 32 | 5K | OG3 | C2 | T01967 | 2023-11-11 |  | 2023-11-20 | 2023-12-10 |  | 2024-01-05 | 2024-01-12 |  | 2024-02-12 |  |  |  | 9.2 | 260 | 394 | Jozef Kotul |  |  |  | This routing is deleted and the new routing is under ID 44000 |  | 0 | SEP | SEP |  | 5
38586 | KV-0-216-031-32-SD5 | 2 | false | CH06822004-BD-PI-0607 | 32 | 5K | OG3 | C2 | T01967 | 2023-11-11 |  | 2023-11-20 | 2023-12-10 |  | 2024-01-05 | 2024-01-12 |  | 2024-02-12 |  |  | 2024-02-15 | 22.3 | 260 | 394 | Virgil Frinculescu |  |  |  | This routing is deleted and the new routing is under ID 44000 |  | 0 | SEP | SEP |  | 5
43999 | KV-0-216-031-32-SD5 | 2 | false | CH06822004-BD-PI-0607 | 32 | 5K | OG3 | C2 | T-051 | 2024-02-01 |  | 2023-11-20 | 2023-12-10 |  | 2024-01-05 | 2024-01-12 | [5 empty] | 0.4 | 260 | 394 |  |  |  |  | DELETED |  | 0 | SEP | SEP
44000 | KV-0-216-031-32-SD5 | 3 | true | CH06822004-BD-PI-0607 | 32 | 5K | OG3 | C2 | T-051 | 2024-02-01 |  | 2023-11-20 | 2023-12-10 |  | 2024-01-05 | 2024-01-12 |  | 2024-02-12 |  |  | 2024-02-15 | 0.4 | 260 | 394 | Virgil Frinculescu |  |  |  | Latest rev. 3 is added to the w.map. |  | 0 | SEP | SEP
38587 | KV-0-216-033-20-SD5 | 2 | true | CH06822004-BD-PI-0607 | 20 | 5K | OG3 | C2 | T01967 | 2023-11-11 |  | 2023-11-20 | 2023-12-11 |  | 2024-01-18 | 2024-01-19 |  | 2024-02-01 |  |  | 2024-02-09 | 0.2 | 260 | 394 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 5
39163 | ABP-7-701-004-65-SD | 2 | true | CH06822004-BD-PI-0495 | 65 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-11-28 | 2023-11-28 | 2023-12-18 |  | 2023-12-20 | 2024-01-12 |  | 2024-04-09 |  |  | 2024-04-12 | 1.2 | 271 | 362 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
43464 | ABP-7-701-004-65-SD | 3 | false | CH06822004-BD-PI-0495 | 65 | 5K | OG1 | N/A | T-047 | 2024-01-25 | 2023-11-28 | 2023-11-28 | 2023-12-18 |  | 2023-12-20 | 2024-01-12 | [5 empty] | 1.2 | 271 | 362 |  |  |  |  | Issued for information |  | 0 | SEP | SEP
39164 | ABP-7-701-010-65-SD | 2 | true | CH06822004-BD-PI-0495 | 65 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-11-28 | 2023-11-28 | 2023-12-18 |  | 2023-12-20 | 2024-01-12 |  | 2024-02-01 |  |  | 2024-02-06 | 0.7 | 271 | 362 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39165 | ABP-7-701-011-65-SD | 2 | true | CH06822004-BD-PI-0495 | 65 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-11-28 | 2023-11-28 | 2023-12-18 | 2024-01-12 | 2024-01-16 | 2024-01-19 |  | 2024-04-09 |  |  | 2024-05-01 | 1.1 | 271 | 362 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39166 | ABP-7-701-016-32-SD1 | 2 | true | CH06822004-BD-PI-0495 | 32 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-11-28 | 2023-11-28 | 2024-01-16 | 2024-01-25 | 2024-01-25 | 2024-02-02 |  | 2024-04-09 |  |  | 2024-04-24 | 6.9 | 258 | 362 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39167 | ABP-7-701-017-32-SD1 | 2 | true | CH06822004-BD-PI-0495 | 32 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-11-28 | 2023-11-28 | 2024-01-16 | 2024-01-25 | 2024-01-25 | 2024-02-02 |  | 2024-04-09 |  |  | 2024-04-24 | 4.2 | 258 | 362 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39168 | ABP-7-701-018-32-SD1 | 2 | true | CH06822004-BD-PI-0495 | 32 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-11-28 | 2023-11-28 | 2024-01-16 | 2024-01-25 | 2024-01-25 | 2024-02-02 |  | 2024-04-09 |  |  | 2024-04-23 | 2.6 | 258 | 362 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39169 | ABP-7-701-019-15-SD1 | 2 | true | CH06822004-BD-PI-0495 | 15 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-11-28 | 2023-11-28 | 2024-01-17 | 2024-01-26 | 2024-01-29 | 2024-02-02 |  | 2024-04-09 |  |  | 2024-04-15 | 2.5 | 258 | 362 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39170 | ABP-7-701-020-15-SD1 | 2 | true | CH06822004-BD-PI-0495 | 15 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-11-28 | 2023-11-28 | 2024-01-17 | 2024-01-25 | 2024-01-25 | 2024-02-02 |  | 2024-04-09 |  |  | 2024-04-15 | 3.9 | 258 | 362 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39171 | ABP-7-701-021-15-SD1 | 2 | true | CH06822004-BD-PI-0495 | 15 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-11-28 | 2023-11-28 | 2024-01-17 | 2024-01-30 | 2024-02-02 | 2024-02-02 |  | 2024-03-19 |  |  | 2024-03-25 | 5.4 | 258 | 362 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39172 | ABP-7-701-022-15-SD1 | 2 | true | CH06822004-BD-PI-0495 | 15 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-11-28 | 2023-11-28 | 2024-01-17 | 2024-01-25 | 2024-01-25 | 2024-02-02 |  | 2024-03-19 |  |  | 2024-04-25 | 2.8 | 258 | 362 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39173 | ABP-7-701-023-15-SD1 | 2 | true | CH06822004-BD-PI-0495 | 15 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-11-28 | 2023-11-28 | 2024-01-17 | 2024-01-25 | 2024-01-25 | 2024-02-02 |  | 2024-04-09 |  |  | 2024-04-12 | 6.1 | 258 | 362 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39174 | ABP-7-701-024-15-SD1 | 2 | true | CH06822004-BD-PI-0495 | 15 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-11-28 | 2023-11-28 | 2024-01-17 | 2024-01-25 | 2024-01-25 | 2024-02-02 |  | 2024-04-09 |  |  | 2024-04-12 | 6.8 | 258 | 362 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39175 | ABP-7-701-025-15-SD1 | 2 | true | Not in latest LineList from 20231115 | 15 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-11-28 | 2023-11-28 | 2024-01-17 | 2024-01-25 | 2024-01-25 | 2024-02-02 |  | 2024-04-09 |  |  | 2024-04-12 | 8.6 | 258 | 362 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39176 | ABP-7-701-025-15-SD1 | 2 | true | Not in latest LineList from 20231115 | 15 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-11-28 | 2023-11-28 | 2024-01-17 |  | 2024-02-02 | 2024-02-02 |  | 2024-04-09 |  |  | 2024-04-12 | 6.1 | 258 | 362 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39177 | CO2F-7-600-004-25-SP1 | 2 | true | CH06822004-BD-PI-0449 | 25 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-08 | 2024-01-25 | 2024-01-25 | 2024-02-02 |  | 2024-02-06 |  |  | 2024-02-12 | 10.9 | 264 | 369 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39178 | CO2F-7-600-004-25-SP1 | 2 | true | CH06822004-BD-PI-0449 | 25 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-08 | 2024-01-12 | 2024-01-12 | 2024-01-19 |  | 2024-02-06 |  |  | 2024-03-22 | 5.3 | 264 | 369 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39179 | CO2F-7-600-004-25-SP1 | 2 | true | CH06822004-BD-PI-0449 | 25 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-08 | 2024-01-12 | 2024-01-16 | 2024-01-19 |  | 2024-02-06 |  |  | 2024-02-15 | 17.3 | 264 | 369 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39180 | CO2F-7-600-005-25-SP1 | 2 | false | CH06822004-BD-PI-0449 | 25 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-08 | 2024-01-12 | 2024-01-16 | 2024-01-19 |  | 2024-02-06 |  |  |  | 8.3 | 264 | 369 | Jozef Kotul | [5 empty] | 0 | SEP | SEP |  | 4
39181 | CO2F-7-600-005-25-SP1 | 2 | false | CH06822004-BD-PI-0449 | 25 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2023-12-20 |  | 2024-01-16 | 2024-01-19 |  | 2024-02-06 |  |  |  | 5 | 264 | 369 | Jozef Kotul | [5 empty] | 0 | SEP | SEP |  | 4
42574 | CO2F-7-600-005-25-SP1 | 3 | true | CH06822004-BD-PI-0449 | 25 | 5K | OG1 | N/A | PEL-ZAU-T-043 | 2024-01-19 | 2023-12-04 | 2023-12-04 | 2024-01-08 | 2024-01-12 | 2024-01-16 |  |  | 2024-02-06 |  |  | 2024-02-20 | 8.3 | 264 | 369 | Virgil Frinculescu |  |  |  | No change |  | 0 | SEP | SEP
42575 | CO2F-7-600-005-25-SP1 | 3 | true | CH06822004-BD-PI-0449 | 25 | 5K | OG1 | N/A | PEL-ZAU-T-043 | 2024-01-19 | 2023-12-04 | 2023-12-04 | 2023-12-20 |  | 2024-01-16 |  |  | 2024-02-06 |  |  | 2024-02-23 | 5 | 264 | 369 | Virgil Frinculescu |  |  |  | Updated Positions of Thermowells etc. |  | 0 | SEP | SEP
39182 | CO2F-7-600-006-15-SP1 | 2 | true | CH06822004-BD-PI-0449 | 15 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-09 | 2024-01-12 | 2024-01-16 | 2024-01-19 |  | 2024-02-07 | 2024-03-23 |  | 2024-06-13 | 9.2 | 264 | 369 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39183 | CO2F-7-600-007-15-SP | 2 | true | CH06822004-BD-PI-0449 | 15 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-05 | 2024-01-25 | 2024-01-25 | 2024-02-02 |  | 2024-03-20 |  |  | 2024-06-05 | 1 | 262 | 369 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39184 | CO2F-7-600-011-15-SP | 2 | true | CH06822004-BD-PI-0449 | 15 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-05 | 2024-01-12 | 2024-01-13 | 2024-01-19 |  | 2024-03-20 |  |  | 2024-06-05 | 1 | 262 | 369 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39185 | CO2F-7-600-012-15-SP | 2 | true | CH06822004-BD-PI-0449 | 15 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-05 | 2024-01-12 | 2024-01-12 | 2024-01-19 |  | 2024-02-01 |  |  | 2024-05-21 | 2.5 | 262 | 369 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39186 | CO2F-7-600-013-15-SP | 2 | true | CH06822004-BD-PI-0449 | 15 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-05 | 2024-01-12 | 2024-01-13 | 2024-01-19 |  | 2024-02-01 |  | 2024-03-23 | 2024-05-15 | 4.5 | 262 | 369 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39187 | CO2F-7-600-014-15-SP | 2 | true | CH06822004-BD-PI-0449 | 15 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-08 | 2024-01-12 | 2024-01-13 | 2024-01-19 |  | 2024-03-20 |  |  | 2024-05-11 | 1 | 262 | 369 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39188 | CO2F-7-600-015-15-SP | 2 | true | CH06822004-BD-PI-0449 | 15 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-10 |  | 2024-01-16 | 2024-01-19 |  | 2024-03-20 |  |  | 2024-05-11 | 0.6 | 262 | 369 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39189 | CO2F-7-600-016-15-SP | 2 | true | CH06822004-BD-PI-0449 | 15 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-08 | 2024-01-25 | 2024-01-25 | 2024-02-02 |  | 2024-03-20 |  |  | 2024-04-24 | 1 | 262 | 369 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39190 | CO2F-7-600-017-15-SP | 2 | true | CH06822004-BD-PI-0449 | 15 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-05 | 2024-01-25 | 2024-01-25 | 2024-02-02 |  | 2024-03-20 |  |  | 2024-04-24 | 0.3 | 262 | 369 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39191 | CO2F-7-600-018-15-SP | 2 | true | CH06822004-BD-PI-0449 | 15 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-05 | 2024-01-12 | 2024-01-12 | 2024-01-19 |  | 2024-03-20 |  |  | 2024-04-23 | 2.2 | 262 | 369 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39192 | CO2F-7-600-021-25-SP1 | 2 | true | Not in latest LineList from 20231115 | 25 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-09 |  | 2024-01-16 | 2024-01-19 |  | 2024-03-19 |  |  | 2024-04-03 | 5.6 | 264 | 369 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39193 | DLF-7-831-002-25-SP1 | 2 | false | CH06822004-BD-PI-0537 | 25 | 5K | EG | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-09 | 2024-01-12 | 2024-01-16 | 2024-01-19 |  | 2024-01-26 |  |  |  | 10.1 | 264 | 380 | Technical office | [5 empty] | 0 | SEP | SEP |  | 4
45353 | DLF-7-831-002-25-SP1 | 3 | true | CH06822004-BD-PI-0537 | 25 | 5K | EG | N/A | T-060 | 2024-03-05 | 2023-12-04 | 2023-12-04 | 2024-01-09 | 2024-01-12 | 2024-01-16 | 2024-01-19 |  | 2024-04-03 |  |  | 2024-04-15 | 2.6 | 264 | 380 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45354 | DLF-7-831-002-25-SP1 | 3 | true | CH06822004-BD-PI-0537 | 25 | 5K | EG | N/A | T-060 | 2024-03-05 | [7 empty] | 2024-04-03 |  |  | 2024-04-15 | 4.1 | 264 | 380 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
39194 | DLF-7-831-007-25-SP1 | 2 | false | CH06822004-BD-PI-0537 | 25 | 5K | EG | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-09 | 2024-01-12 | 2024-01-16 | 2024-01-19 | [5 empty] | 9.2 | 264 | 380 | [6 empty] | 0 | SEP | SEP |  | 4
39195 | DLF-7-831-007-25-SP1 | 2 | false | CH06822004-BD-PI-0537 | 25 | 5K | EG | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-09 | 2024-01-12 | 2024-01-16 | 2024-01-19 | [5 empty] | 5.9 | 264 | 380 | [6 empty] | 0 | SEP | SEP |  | 4
42080 | DLF-7-831-007-25-SP1 | 3 | true | CH06822004-BD-PI-0537 | 25 | 5K | EG | N/A | PEL-ZAU-T-037 | 2024-01-15 | 2023-12-04 | 2023-12-04 | 2024-01-09 | 2024-01-12 | 2024-01-16 |  |  | 2024-02-13 |  |  | 2024-03-05 | 9.2 | 264 | 380 | Virgil Frinculescu |  |  |  | No change |  | 0 | SEP | SEP
42081 | DLF-7-831-007-25-SP1 | 3 | true | CH06822004-BD-PI-0537 | 25 | 5K | EG | N/A | PEL-ZAU-T-037 | 2024-01-15 | 2023-12-04 | 2023-12-04 | 2024-01-09 | 2024-01-12 | 2024-01-16 |  |  | 2024-02-13 |  |  | 2024-03-05 | 5.9 | 264 | 380 | Virgil Frinculescu |  |  |  | Updated Positions of Thermowells etc. |  | 0 | SEP | SEP
39196 | DLF-7-831-008-25-SP1 | 2 | false | CH06822004-BD-PI-0537 | 25 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-09 | 2024-01-12 | 2024-01-16 | 2024-01-19 |  | 2024-02-06 |  |  |  | 10 | 264 | 380 | Jozef Kotul | [5 empty] | 0 | SEP | SEP |  | 4
39197 | DLF-7-831-008-25-SP1 | 2 | false | CH06822004-BD-PI-0537 | 25 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-09 | 2024-01-30 | 2024-01-30 | 2024-02-02 |  | 2024-02-06 |  |  |  | 8.1 | 264 | 380 | Jozef Kotul | [5 empty] | 0 | SEP | SEP |  | 4
39198 | DLF-7-831-008-25-SP1 | 2 | false | CH06822004-BD-PI-0537 | 25 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-09 | 2024-01-31 | 2024-01-31 | 2024-02-02 |  | 2024-02-06 |  |  |  | 9.3 | 264 | 380 | Jozef Kotul | [5 empty] | 0 | SEP | SEP |  | 4
39199 | DLF-7-831-008-25-SP1 | 2 | false | CH06822004-BD-PI-0537 | 25 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-09 | 2024-01-26 | 2024-01-29 | 2024-02-02 |  | 2024-02-06 |  |  |  | 8.4 | 264 | 380 | Jozef Kotul | [5 empty] | 0 | SEP | SEP |  | 4
39200 | DLF-7-831-008-25-SP1 | 2 | false | CH06822004-BD-PI-0537 | 25 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-09 | 2024-01-26 | 2024-01-29 | 2024-02-02 |  | 2024-02-06 |  |  |  | 3.9 | 264 | 380 | Jozef Kotul | [5 empty] | 0 | SEP | SEP |  | 4
42082 | DLF-7-831-008-25-SP1 | 3 | true | CH06822004-BD-PI-0537 | 25 | 5K | OG1 | N/A | PEL-ZAU-T-037 | 2024-01-15 | 2023-12-04 | 2023-12-04 | 2024-01-09 | 2024-01-12 | 2024-01-16 |  |  | 2024-02-06 |  |  | 2024-02-12 | 10 | 264 | 380 | Virgil Frinculescu |  |  |  | No change |  | 0 | SEP | SEP |  | 4
42083 | DLF-7-831-008-25-SP1 | 3 | true | CH06822004-BD-PI-0537 | 25 | 5K | OG1 | N/A | PEL-ZAU-T-037 | 2024-01-15 | 2023-12-04 | 2023-12-04 | 2024-01-09 | 2024-01-30 | 2024-01-30 |  |  | 2024-02-06 |  |  | 2024-02-13 | 8.1 | 264 | 380 | Virgil Frinculescu |  |  |  | No change |  | 0 | SEP | SEP |  | 4
42084 | DLF-7-831-008-25-SP1 | 3 | true | CH06822004-BD-PI-0537 | 25 | 5K | OG1 | N/A | PEL-ZAU-T-037 | 2024-01-15 | 2023-12-04 | 2023-12-04 | 2024-01-09 |  |  |  |  | 2024-02-06 |  |  | 2024-02-20 | 9.3 | 264 | 380 | Virgil Frinculescu |  |  |  | No change |  | 0 | SEP | SEP |  | 4
42085 | DLF-7-831-008-25-SP1 | 3 | true | CH06822004-BD-PI-0537 | 25 | 5K | OG1 | N/A | PEL-ZAU-T-037 | 2024-01-15 | 2023-12-04 | 2023-12-04 | 2024-01-09 | 2024-01-26 | 2024-01-29 |  |  | 2024-02-06 |  |  | 2024-02-22 | 8.4 | 264 | 380 | Virgil Frinculescu |  |  |  | No change |  | 0 | SEP | SEP |  | 4
42086 | DLF-7-831-008-25-SP1 | 3 | true | CH06822004-BD-PI-0537 | 25 | 5K | OG1 | N/A | PEL-ZAU-T-037 | 2024-01-15 | 2023-12-04 | 2023-12-04 | 2024-01-09 | 2024-01-26 | 2024-01-29 |  |  | 2024-02-06 |  |  | 2024-02-23 | 3.9 | 264 | 380 | Virgil Frinculescu |  |  |  | Updated Positions of Thermowells etc. |  | 0 | SEP | SEP |  | 4
39201 | DLF-7-831-009-15-SP1 | 2 | false | CH06822004-BD-PI-0537 | 15 | 5K | EG | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-05 | 2024-01-12 | 2024-01-13 | 2024-01-19 |  | 2024-01-26 |  |  |  | 2.3 | 264 | 380 | Jozef Kotul | [5 empty] | 0 | SEP | SEP |  | 4
50179 | DLF-7-831-009-15-SP1 | 4 | true | CH06822004-BD-PI-0537 | 15 | 5K | EG | N/A | T-080 | 2024-05-01 | [7 empty] | 2024-06-18 |  |  | 2024-05-30 | 5.1 | 264 | 380 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
39202 | DLF-7-831-010-15-SP1 | 2 | false | CH06822004-BD-PI-0537 | 15 | 5K | EG | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-03 | 2024-01-12 | 2024-01-12 | 2024-01-19 | [5 empty] | 3.6 | 264 | 380 | [6 empty] | 0 | SEP | SEP |  | 4
45355 | DLF-7-831-010-15-SP1 | 3 | true | CH06822004-BD-PI-0537 | 15 | 5K | EG | N/A | T-060 | 2024-03-05 | 2023-12-04 | 2023-12-04 | 2024-01-03 | 2024-01-12 | 2024-01-12 | 2024-01-19 |  | 2024-04-03 |  |  | 2024-04-15 | 3.7 | 264 | 380 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
39203 | DLF-7-831-011-15-SP1 | 2 | false | CH06822004-BD-PI-0537 | 15 | 5K | EG | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-10 | 2024-01-25 | 2024-01-25 | 2024-02-02 | [5 empty] | 3.6 | 264 | 380 | [6 empty] | 0 | SEP | SEP |  | 4
45356 | DLF-7-831-011-15-SP1 | 3 | true | CH06822004-BD-PI-0537 | 15 | 5K | EG | N/A | T-060 | 2024-03-05 | 2023-12-04 | 2023-12-04 | 2024-01-10 | 2024-01-25 | 2024-01-25 | 2024-02-02 |  | 2024-04-03 |  |  | 2024-04-15 | 3.7 | 264 | 380 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
39204 | DLF-7-831-012-15-SP1 | 2 | false | CH06822004-BD-PI-0537 | 15 | 5K | EG | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-03 | 2024-01-12 | 2024-01-12 | 2024-01-19 | [5 empty] | 1.9 | 264 | 380 | [6 empty] | 0 | SEP | SEP |  | 4
45357 | DLF-7-831-012-15-SP1 | 3 | true | CH06822004-BD-PI-0537 | 15 | 5K | EG | N/A | T-060 | 2024-03-05 | 2023-12-04 | 2023-12-04 | 2024-01-03 | 2024-01-12 | 2024-01-12 | 2024-01-19 |  | 2024-04-03 |  |  | 2024-04-15 | 1.7 | 264 | 380 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
39205 | DLF-7-831-013-15-SP1 | 2 | true | CH06822004-BD-PI-0537 | 15 | 5K | EG | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-03 | 2024-01-12 | 2024-01-16 | 2024-01-19 |  | 2024-02-14 |  |  | 2024-03-05 | 2.4 | 264 | 380 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39206 | DLF-7-831-014-15-SP1 | 2 | true | CH06822004-BD-PI-0537 | 15 | 5K | EG | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-03 | 2024-01-12 | 2024-01-16 | 2024-01-19 |  | 2024-02-14 |  |  | 2024-03-05 | 3.5 | 264 | 380 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39207 | DLF-7-831-015-15-SP1 | 2 | true | CH06822004-BD-PI-0537 | 15 | 5K | EG | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-03 | 2024-01-12 | 2024-01-12 | 2024-01-19 |  | 2024-02-14 |  |  | 2024-03-05 | 2.4 | 264 | 380 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39208 | DLF-7-831-016-15-SP1 | 2 | true | CH06822004-BD-PI-0537 | 15 | 5K | EG | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-03 | 2024-01-12 | 2024-01-12 | 2024-01-19 |  | 2024-02-14 |  |  | 2024-03-05 | 2.6 | 264 | 380 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39209 | DLF-7-831-017-15-SP1 | 2 | true | CH06822004-BD-PI-0537 | 15 | 5K | EG | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-03 | 2024-01-12 | 2024-01-12 | 2024-01-19 |  | 2024-02-14 |  |  | 2024-03-05 | 3.3 | 264 | 380 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39210 | DLF-7-831-018-15-SP1 | 2 | true | CH06822004-BD-PI-0537 | 15 | 5K | EG | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-10 | 2024-01-25 | 2024-01-25 | 2024-02-02 |  | 2024-02-27 |  |  | 2024-03-05 | 3.3 | 264 | 380 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39211 | DLF-7-831-020-15-SP1 | 2 | true | CH06822004-BD-PI-0537 | 15 | 5K | EG | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-03 | 2024-01-12 | 2024-01-13 | 2024-01-19 |  | 2024-02-28 |  |  | 2024-03-05 | 2.4 | 264 | 380 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39212 | DLF-7-831-021-15-SP1 | 2 | true | CH06822004-BD-PI-0537 | 15 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-03 | 2024-01-12 | 2024-01-13 | 2024-01-19 |  | 2024-02-01 |  |  | 2024-04-23 | 2.2 | 264 | 380 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39213 | DLF-7-831-022-15-SP1 | 2 | true | CH06822004-BD-PI-0537 | 15 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-03 | 2024-01-12 | 2024-01-12 | 2024-01-19 |  | 2024-02-01 |  | 2024-03-23 | 2024-04-17 | 4.3 | 264 | 380 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39214 | DLF-7-831-023-15-SP1 | 2 | true | CH06822004-BD-PI-0537 | 15 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-09 |  | 2024-01-16 | 2024-01-19 |  | 2024-03-19 |  |  | 2024-03-27 | 5.7 | 264 | 380 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39215 | DLF-7-831-024-15-SP1 | 2 | true | CH06822004-BD-PI-0537 | 15 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-03 | 2024-01-12 | 2024-01-12 | 2024-01-19 |  | 2024-03-20 |  |  | 2024-03-27 | 1.5 | 264 | 380 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39216 | DLF-7-831-025-15-SP1 | 2 | true | CH06822004-BD-PI-0537 | 15 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-03 | 2024-01-12 | 2024-01-12 | 2024-01-19 |  | 2024-03-19 |  |  | 2024-03-26 | 1.4 | 264 | 380 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39217 | DLF-7-831-026-15-SP1 | 2 | false | CH06822004-BD-PI-0537 | 15 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-10 |  | 2024-01-19 | 2024-01-19 | [5 empty] | 2.1 | 264 | 380 | [6 empty] | 0 | SEP | SEP |  | 4
42087 | DLF-7-831-026-15-SP1 | 3 | true | CH06822004-BD-PI-0537 | 15 | 5K | OG1 | N/A | PEL-ZAU-T-037 | 2024-01-15 | 2023-12-04 | 2023-12-04 | 2024-01-10 |  | 2024-01-19 | 2024-01-19 |  | 2024-03-20 |  |  | 2024-03-26 | 2.1 | 264 | 380 | Virgil Frinculescu |  |  |  | Reducer has been changed out. |  | 0 | SEP | SEP |  | 4
39218 | DLF-7-831-027-15-SP1 | 2 | false | CH06822004-BD-PI-0537 | 15 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-09 | 2024-01-12 | 2024-01-16 | 2024-01-19 |  | 2024-02-08 |  |  |  | 4 | 264 | 380 | Jozef Kotul | [5 empty] | 0 | SEP | SEP |  | 4
42088 | DLF-7-831-027-15-SP1 | 3 | true | CH06822004-BD-PI-0537 | 15 | 5K | OG1 | N/A | PEL-ZAU-T-037 | 2024-01-15 | 2023-12-04 | 2023-12-04 | 2024-01-09 | 2024-01-12 | 2024-01-16 | 2024-01-19 |  | 2024-02-08 | 2024-03-23 |  | 2024-04-05 | 4 | 264 | 380 | Virgil Frinculescu |  |  |  | Reducer has been changed out. |  | 0 | SEP | SEP |  | 4
39219 | DLF-7-831-028-15-SP1 | 2 | true | CH06822004-BD-PI-0537 | 15 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-03 | 2024-01-12 | 2024-01-15 | 2024-01-19 |  | 2024-03-20 |  |  | 2024-03-27 | 5.2 | 264 | 380 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39220 | DLF-7-831-030-15-SP1 | 2 | true | CH06822004-BD-PI-0537 | 15 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-10 | 2024-01-25 | 2024-01-25 | 2024-02-02 |  | 2024-03-20 |  |  | 2024-04-24 | 2.7 | 264 | 380 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39221 | DLF-7-831-031-15-SP1 | 2 | true | CH06822004-BD-PI-0537 | 15 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-04 | 2024-01-12 | 2024-01-13 | 2024-01-19 |  | 2024-03-20 |  |  | 2024-04-06 | 1.2 | 264 | 380 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39222 | DLF-7-831-032-15-SP1 | 2 | true | CH06822004-BD-PI-0537 | 15 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-04 | 2024-01-12 | 2024-01-13 | 2024-01-19 |  | 2024-03-20 |  |  | 2024-04-24 | 0.5 | 264 | 380 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39223 | DLF-7-831-033-15-SP1 | 2 | true | CH06822004-BD-PI-0537 | 15 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-10 | 2024-01-25 | 2024-01-25 | 2024-02-02 |  | 2024-03-20 |  |  | 2024-04-04 | 1.5 | 264 | 380 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39224 | DLF-7-831-034-15-SP1 | 2 | true | CH06822004-BD-PI-0537 | 15 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-04 | 2024-01-12 | 2024-01-12 | 2024-01-19 |  | 2024-03-20 |  |  | 2024-04-04 | 1.7 | 264 | 380 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
48274 | DLF-7-831-034-15-SP1 | 1 | true | CH06822004-BD-PI-0537 | 15 | 5K | OG1 | N/A | T-069 | 2024-04-05 | 2023-12-04 | 2023-12-04 | 2024-01-04 | 2024-01-12 | 2024-01-12 | 2024-01-19 |  | 2024-05-21 | 2024-05-11 | 2024-04-10 | 2024-08-21 | 8.7 | 264 | 380 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
39225 | DLF-7-831-035-15-SP1_1 | 2 | true | CH06822004-BD-PI-0537 | 15 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-03 | 2024-01-12 | 2024-01-12 | 2024-01-19 |  | 2024-03-20 |  |  | 2024-04-04 | 1.7 | 264 | 380 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
48275 | DLF-7-831-035-15-SP1_1 | 1 | true | CH06822004-BD-PI-0537 | 15 | 5K | OG1 | N/A | T-069 | 2024-04-05 | 2023-12-04 | 2023-12-04 | 2024-01-03 | 2024-01-12 | 2024-01-12 | 2024-01-19 |  | 2024-04-26 |  | 2024-04-10 | 2024-05-11 | 5.6 | 264 | 380 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48276 | DLF-7-831-035-15-SP1_1 | 1 | true | CH06822004-BD-PI-0537 | 15 | 5K | OG1 | N/A | T-069 | 2024-04-05 | [7 empty] | 2024-05-21 |  | 2024-05-25 | 2024-06-04 | 3.3 | 264 | 380 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
39226 | DLF-7-831-036-15-SP1_1 | 2 | true | CH06822004-BD-PI-0537 | 15 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-04 | 2024-01-12 | 2024-01-12 | 2024-01-19 |  | 2024-03-20 |  |  | 2024-04-04 | 2 | 264 | 380 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
48277 | DLF-7-831-036-15-SP1_1 | 1 | true | CH06822004-BD-PI-0537 | 15 | 5K | OG1 | N/A | T-069 | 2024-04-05 | 2023-12-04 | 2023-12-04 | 2024-01-04 | 2024-01-12 | 2024-01-12 | 2024-01-19 |  | 2024-05-21 |  | 2024-04-10 | 2024-08-28 | 3.7 | 264 | 380 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48278 | DLF-7-831-036-15-SP1_1 | 1 | true | CH06822004-BD-PI-0537 | 15 | 5K | OG1 | N/A | T-069 | 2024-04-05 | [7 empty] | 2024-05-21 | 2024-08-24 |  | 2024-09-05 | 2.4 | 264 | 380 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
39227 | DLF-7-831-040-15-SP1 | 2 | true | CH06822004-BD-PI-0537 | 15 | 5K | EG | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-05 | 2024-01-12 | 2024-01-15 | 2024-01-19 |  | 2024-02-13 |  |  | 2024-02-29 | 4 | 264 | 380 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39228 | DLF-7-831-045-25-SP1 | 2 | true | CH06822004-BD-PI-0537 | 25 | 5K | EG | N/A | T02294 | 2023-11-22 | 2023-11-28 | 2023-11-28 | 2024-01-04 | 2024-01-26 | 2024-01-29 | 2024-02-02 |  | 2024-02-13 |  |  | 2024-02-26 | 6.7 | 264 | 380 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39229 | DLF-7-831-045-25-SP1 | 2 | true | CH06822004-BD-PI-0537 | 25 | 5K | EG | N/A | T02294 | 2023-11-22 | 2023-11-28 | 2023-11-28 | 2024-01-04 | 2024-01-26 | 2024-01-29 | 2024-02-02 |  | 2024-02-13 |  |  | 2024-03-05 | 12 | 264 | 380 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39230 | DLF-7-831-045-25-SP1 | 2 | true | CH06822004-BD-PI-0537 | 25 | 5K | EG | N/A | T02294 | 2023-11-22 | 2023-11-28 | 2023-11-28 | 2024-01-04 | 2024-01-26 | 2024-01-29 | 2024-02-02 |  | 2024-02-13 |  |  | 2024-03-05 | 4.4 | 264 | 380 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39231 | DLP-7-301-003-15-SP1 | 2 | true | CH06822004-BD-PI-0544 | 15 | 5K | EG | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-08 | 2024-01-12 | 2024-01-16 | 2024-01-19 |  | 2024-02-13 |  |  | 2024-03-05 | 10.8 | 264 | 382 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39232 | DLP-7-301-003-15-SP1 | 2 | true | CH06822004-BD-PI-0544 | 15 | 5K | EG | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-23 | 2024-01-25 | 2024-01-25 | 2024-02-02 |  | 2024-02-13 |  |  | 2024-03-05 | 6.5 | 264 | 382 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39233 | DLP-7-301-004-40-SP1 | 2 | false | CH06822004-BD-PI-0544 | 40 | 5K | EG | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-08 | 2024-01-12 | 2024-01-16 | 2024-01-19 |  | 2024-01-26 |  |  |  | 7.5 | 264 | 382 | Jozef Kotul | [5 empty] | 0 | SEP | SEP |  | 4
39234 | DLP-7-301-004-40-SP1 | 2 | false | CH06822004-BD-PI-0544 | 40 | 5K | EG | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-08 |  | 2024-01-16 | 2024-01-19 |  | 2024-01-26 |  |  |  | 4.6 | 264 | 382 | Jozef Kotul | [5 empty] | 0 | SEP | SEP |  | 4
39235 | DLP-7-301-004-40-SP1 | 2 | false | CH06822004-BD-PI-0544 | 40 | 5K | EG | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-16 | 2024-01-30 | 2024-01-30 | 2024-02-02 |  | 2024-02-13 |  |  |  | 9.8 | 264 | 382 | Jozef Kotul | [5 empty] | 0 | SEP | SEP |  | 4
39236 | DLP-7-301-004-40-SP1 | 2 | false | CH06822004-BD-PI-0544 | 40 | 5K | EG | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-16 | 2024-01-25 | 2024-01-25 | 2024-02-02 |  | 2024-02-13 |  |  |  | 5.3 | 264 | 382 | Jozef Kotul | [5 empty] | 0 | SEP | SEP |  | 4
43551 | DLP-7-301-004-40-SP1 | 3 | true | CH06822004-BD-PI-0544 | 40 | 5K | EG | N/A | T-078 | 2024-04-26 | 2023-12-04 | 2023-12-04 | 2024-01-08 | 2024-01-12 | 2024-01-16 | 2024-01-19 |  | 2024-01-26 |  |  | 2024-02-20 | 7.3 | 264 | 382 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
43552 | DLP-7-301-004-40-SP1 | 3 | true | CH06822004-BD-PI-0544 | 40 | 5K | EG | N/A | T-078 | 2024-04-26 | 2023-12-04 | 2023-12-04 | 2024-01-08 |  | 2024-01-16 | 2024-01-19 |  | 2024-01-26 |  |  | 2024-02-20 | 4.6 | 264 | 382 | Virgil Frinculescu |  |  |  | Latest rev. 3 is added to the w.map. |  | 0 | SEP | SEP
43553 | DLP-7-301-004-40-SP1 | 3 | true | CH06822004-BD-PI-0544 | 40 | 5K | EG | N/A | T-078 | 2024-04-26 | 2023-12-04 | 2023-12-04 | 2024-01-16 | 2024-01-30 | 2024-01-30 | 2024-02-02 |  |  |  |  | 2024-02-26 | 9.8 | 264 | 382 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
43554 | DLP-7-301-004-40-SP1 | 3 | true | CH06822004-BD-PI-0544 | 40 | 5K | EG | N/A | T-078 | 2024-04-26 | 2023-12-04 | 2023-12-04 | 2024-01-16 | 2024-01-25 | 2024-01-25 | 2024-02-02 |  |  |  |  | 2024-03-05 | 5.3 | 264 | 382 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
39237 | DLP-7-301-006-40-SP1 | 2 | false | CH06822004-BD-PI-0544 | 40 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-16 |  | 2024-02-02 | 2024-02-02 |  | 2024-02-06 |  |  | 2024-02-09 | 3.8 | 264 | 382 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39238 | DLP-7-301-006-40-SP1 | 2 | false | CH06822004-BD-PI-0544 | 40 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-16 | 2024-01-30 | 2024-01-30 | 2024-02-02 |  | 2024-02-06 |  |  | 2024-02-12 | 9.3 | 264 | 382 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39239 | DLP-7-301-006-40-SP1 | 2 | false | CH06822004-BD-PI-0544 | 40 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-08 | 2024-01-12 | 2024-01-13 | 2024-01-19 |  | 2024-02-06 |  |  | 2024-03-26 | 2.4 | 264 | 382 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39240 | DLP-7-301-006-40-SP1 | 2 | false | CH06822004-BD-PI-0544 | 40 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-16 |  | 2024-02-02 | 2024-02-02 |  | 2024-02-06 |  | 2024-03-23 | 2024-04-17 | 5.9 | 264 | 382 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39241 | DLP-7-301-006-40-SP1 | 2 | false | CH06822004-BD-PI-0544 | 40 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-08 |  | 2024-02-02 | 2024-02-02 |  | 2024-02-06 |  | 2024-03-23 | 2024-04-17 | 12.4 | 264 | 382 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
50182 | DLP-7-301-006-40-SP1 | 3 | true | CH06822004-BD-PI-0544 | 40 | 5K | OG1 | N/A | T-080 | 2024-05-01 | 2023-12-04 | 2023-12-04 | 2024-01-16 |  | 2024-02-02 | 2024-02-02 |  | 2024-02-06 |  | 2024-05-01 | 2024-05-22 | 3.8 | 264 | 382 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
50183 | DLP-7-301-006-40-SP1 | 3 | true | CH06822004-BD-PI-0544 | 40 | 5K | OG1 | N/A | T-080 | 2024-05-01 | 2023-12-04 | 2023-12-04 | 2024-01-16 | 2024-01-30 | 2024-01-30 | 2024-02-02 |  | 2024-02-06 |  | 2024-05-01 | 2024-05-22 | 9.3 | 264 | 382 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
50184 | DLP-7-301-006-40-SP1 | 3 | true | CH06822004-BD-PI-0544 | 40 | 5K | OG1 | N/A | T-080 | 2024-05-01 | 2023-12-04 | 2023-12-04 | 2024-01-08 | 2024-01-12 | 2024-01-13 | 2024-01-19 |  | 2024-02-06 |  | 2024-05-01 | 2024-05-22 | 2.4 | 264 | 382 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
50185 | DLP-7-301-006-40-SP1 | 3 | true | CH06822004-BD-PI-0544 | 40 | 5K | OG1 | N/A | T-080 | 2024-05-01 | 2023-12-04 | 2023-12-04 | 2024-01-16 |  | 2024-02-02 | 2024-02-02 |  | 2024-02-06 |  | 2024-05-01 | 2024-05-22 | 5.9 | 264 | 382 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
50186 | DLP-7-301-006-40-SP1 | 3 | true | CH06822004-BD-PI-0544 | 40 | 5K | OG1 | N/A | T-080 | 2024-05-01 | 2023-12-04 | 2023-12-04 | 2024-01-08 |  | 2024-02-02 | 2024-02-02 |  | 2024-02-06 |  | 2024-05-01 | 2024-05-22 | 3.9 | 264 | 382 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
50187 | DLP-7-301-006-40-SP1 | 3 | true | CH06822004-BD-PI-0544 | 40 | 5K | OG1 | N/A | T-080 | 2024-05-01 | [7 empty] | 2024-05-22 |  |  | 2024-06-26 | 8.4 | 264 | 382 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
39242 | DLP-7-301-007-15-SP1 | 2 | true | CH06822004-BD-PI-0544 | 15 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-23 | 2024-01-25 | 2024-01-25 | 2024-02-02 |  | 2024-02-06 |  |  | 2024-02-22 | 7.7 | 264 | 382 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39243 | DLP-7-301-007-15-SP1 | 2 | true | CH06822004-BD-PI-0544 | 15 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-23 | 2024-01-25 | 2024-01-25 | 2024-02-02 |  | 2024-02-06 |  |  | 2024-02-23 | 5 | 264 | 382 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39244 | DLP-7-301-009-15-SP1 | 2 | true | CH06822004-BD-PI-0544 | 15 | 5K | EG | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-06 | 2024-01-12 | 2024-01-13 | 2024-01-19 |  | 2024-02-28 |  |  | 2024-03-05 | 0.8 | 264 | 382 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39245 | DLP-7-301-010-15-SP | 2 | true | CH06822004-BD-PI-0544 | 15 | 5K | EG | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-10 |  | 2024-01-10 | 2024-01-12 |  | 2024-04-04 |  |  | 2024-04-06 | 1.1 | 262 | 382 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39246 | DLP-7-301-011-15-SP | 2 | true | CH06822004-BD-PI-0544 | 15 | 5K | EG | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-10 |  | 2024-01-10 | 2024-01-12 |  | 2024-04-04 |  |  | 2024-04-06 | 1.2 | 262 | 382 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39247 | DLP-7-301-012-15-SP | 2 | true | CH06822004-BD-PI-0544 | 15 | 5K | EG | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-06 | 2024-01-25 | 2024-01-25 | 2024-02-02 |  | 2024-04-04 |  |  | 2024-04-06 | 1.5 | 262 | 382 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39248 | DLP-7-301-013-15-SP | 2 | true | CH06822004-BD-PI-0544 | 15 | 5K | EG | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-05 | 2024-01-12 | 2024-01-12 | 2024-01-19 |  | 2024-04-04 |  |  | 2024-04-08 | 1.3 | 262 | 382 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39249 | DLP-7-301-014-15-SP | 2 | true | CH06822004-BD-PI-0544 | 15 | 5K | EG | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-10 |  | 2024-01-10 | 2024-01-12 |  | 2024-04-04 |  |  | 2024-04-08 | 1 | 264 | 382 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39250 | DLP-7-301-015-15-SP1 | 2 | false | CH06822004-BD-PI-0544 | 15 | 5K | EG | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-16 | 2024-01-26 | 2024-01-29 | 2024-02-02 | [5 empty] | 3.7 | 264 | 382 | [6 empty] | 0 | SEP | SEP |  | 4
39251 | DLP-7-301-015-15-SP1 | 2 | false | CH06822004-BD-PI-0544 | 15 | 5K | EG | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-16 | 2024-01-30 | 2024-01-30 | 2024-02-02 | [5 empty] | 5.3 | 264 | 382 | [6 empty] | 0 | SEP | SEP |  | 4
45358 | DLP-7-301-015-15-SP1 | 3 | true | CH06822004-BD-PI-0544 | 15 | 5K | EG | N/A | T-060 | 2024-03-05 | 2023-12-04 | 2023-12-04 | 2024-01-16 | 2024-01-26 | 2024-01-29 | 2024-02-02 |  | 2024-04-03 |  |  | 2024-04-15 | 6.5 | 264 | 382 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45359 | DLP-7-301-015-15-SP1 | 3 | true | CH06822004-BD-PI-0544 | 15 | 5K | EG | N/A | T-060 | 2024-03-05 | 2023-12-04 | 2023-12-04 | 2024-01-16 | 2024-01-30 | 2024-01-30 | 2024-02-02 |  | 2024-04-03 |  |  | 2024-04-15 | 2.6 | 264 | 382 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
39252 | DLP-7-301-016-15-SP | 2 | true | CH06822004-BD-PI-0544 | 15 | 5K | EG | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-10 |  | 2024-01-10 | 2024-01-12 |  | 2024-04-04 |  |  | 2024-04-12 | 1.1 | 262 | 382 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39253 | DLP-7-301-017-15-SP | 2 | true | CH06822004-BD-PI-0544 | 15 | 5K | EG | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-10 |  | 2024-01-10 | 2024-01-12 |  | 2024-04-04 |  |  | 2024-04-09 | 1 | 262 | 382 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39254 | DLP-7-301-018-15-SP | 2 | true | CH06822004-BD-PI-0544 | 15 | 5K | EG | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-06 | 2024-01-12 | 2024-01-15 |  |  | 2024-04-04 |  |  | 2024-04-08 | 1 | 264 | 382 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39255 | DLP-7-301-019-15-SP | 2 | true | CH06822004-BD-PI-0544 | 15 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-10 |  | 2024-01-10 | 2024-01-12 |  | 2024-03-20 |  |  | 2024-05-07 | 0.7 | 262 | 382 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39256 | DLP-7-301-020-15-SP | 2 | true | CH06822004-BD-PI-0544 | 15 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-06 | 2024-01-12 | 2024-01-15 | 2024-01-19 |  | 2024-03-20 |  |  | 2024-05-07 | 0.8 | 262 | 382 | Virgil Frinculescu |  |  |  | NEW ISO released just for information. OLD revision need to redline acc. to new ISO |  | 0 | SEP | SEP |  | 4
43908 | DLP-7-301-020-15-SP | 3 | false | CH06822004-BD-PI-0544 | 15 | 5K | OG1 | N/A | T-050 | 2024-01-31 | 2023-12-04 | 2023-12-04 | 2024-01-06 | 2024-01-12 | 2024-01-15 | 2024-01-19 | [5 empty] | 0.8 | 262 | 382 |  |  |  |  | Issued for Information |  | 0 | SEP | SEP
39257 | DLP-7-301-021-15-SP1 | 2 | true | CH06822004-BD-PI-0544 | 15 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-18 |  | 2024-02-02 | 2024-02-02 |  | 2024-03-19 |  |  | 2024-04-03 | 4.6 | 264 | 382 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39258 | DLP-7-301-022-15-SP | 2 | true | CH06822004-BD-PI-0544 | 15 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-06 | 2024-01-12 | 2024-01-13 | 2024-01-19 |  | 2024-03-20 |  |  | 2024-05-07 | 1 | 262 | 382 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39259 | DLP-7-301-023-15-SP1 | 2 | true | CH06822004-BD-PI-0544 | 15 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-06 | 2024-01-12 | 2024-01-13 | 2024-01-19 |  | 2024-02-01 |  |  | 2024-04-29 | 0.8 | 264 | 382 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39260 | DLP-7-301-024-15-SP1 | 2 | true | CH06822004-BD-PI-0544 | 15 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-06 | 2024-01-12 | 2024-01-13 | 2024-01-19 |  | 2024-02-01 |  |  | 2024-02-08 | 3.3 | 264 | 382 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39261 | DLP-7-301-025-15-SP | 2 | true | CH06822004-BD-PI-0544 | 15 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-10 |  | 2024-01-10 | 2024-01-12 |  | 2024-03-20 |  |  | 2024-04-18 | 1 | 262 | 382 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39262 | DLP-7-301-026-15-SP | 2 | true | CH06822004-BD-PI-0544 | 15 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-06 | 2024-01-12 | 2024-01-13 | 2024-01-19 |  | 2024-03-20 |  |  | 2024-04-18 | 0.8 | 262 | 382 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39263 | DLP-7-301-027-20-SP | 2 | true | CH06822004-BD-PI-0544 | 20 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-11-28 | 2023-11-28 | 2023-12-08 | 2023-12-14 | 2023-12-14 | 2023-12-15 |  | 2024-03-20 |  |  | 2024-04-25 | 1.1 | 262 | 382 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39264 | DLP-7-301-028-20-SP | 2 | true | CH06822004-BD-PI-0544 | 20 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-11-28 | 2023-11-28 | 2023-12-08 | 2023-12-14 | 2023-12-14 | 2023-12-15 |  | 2024-03-20 |  |  | 2024-04-25 | 0.3 | 262 | 382 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39265 | DLP-7-301-029-20-SP | 2 | true | CH06822004-BD-PI-0544 | 20 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-11-28 | 2023-11-28 | 2024-01-30 |  | 2024-02-02 | 2024-02-02 |  | 2024-03-20 |  |  | 2024-04-25 | 2.1 | 262 | 382 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39266 | DLP-7-301-038-15-SP | 2 | true | CH06822004-BD-PI-0544 | 15 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-10 |  | 2024-01-10 | 2024-01-12 |  | 2024-03-20 |  |  | 2024-04-29 | 1 | 264 | 382 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39267 | DLP-7-301-039-15-SP | 2 | true | CH06822004-BD-PI-0544 | 15 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-06 | 2024-01-12 | 2024-01-13 | 2024-01-19 |  | 2024-03-20 |  |  | 2024-05-07 | 1 | 262 | 382 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39268 | DLP-7-301-044-15-SP | 2 | true | CH06822004-BD-PI-0544 | 15 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-10 |  | 2024-01-10 | 2024-01-12 |  | 2024-02-01 |  | 2024-03-23 | 2024-04-29 | 1 | 262 | 382 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39269 | DLP-7-301-045-15-SP | 2 | true | CH06822004-BD-PI-0544 | 15 | 5K | EG | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-10 | 2024-01-25 | 2024-01-25 | 2024-02-02 |  | 2024-04-04 |  |  | 2024-04-06 | 1.7 | 262 | 382 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39270 | DLP-7-301-046-15-SP | 2 | true | CH06822004-BD-PI-0544 | 15 | 5K | EG | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-10 |  | 2024-01-10 | 2024-01-12 |  | 2024-04-04 |  |  | 2024-04-15 | 0.9 | 262 | 382 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39271 | DLP-7-301-047-15-SP1 | 2 | true | CH06822004-BD-PI-0544 | 15 | 5K | EG | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-05 | 2024-01-12 | 2024-01-12 | 2024-01-19 |  | 2024-02-13 |  |  | 2024-02-29 | 3.1 | 264 | 382 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39272 | DLP-7-301-048-15-SP1 | 2 | true | CH06822004-BD-PI-0544 | 15 | 5K | EG | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-10 | 2024-01-25 | 2024-01-25 | 2024-02-02 |  | 2024-02-16 |  |  | 2024-03-05 | 2.6 | 264 | 382 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39273 | KR-0-216-015-40-SD5 | 2 | true | CH06822004-BD-PI-0607 | 40 | 5K | OG1 | C2 | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-08 | 2024-01-25 | 2024-01-25 | 2024-02-02 |  | 2024-03-27 |  |  | 2024-04-05 | 6.5 | 260 | 393 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39274 | KR-0-216-015-40-SD5 | 2 | true | CH06822004-BD-PI-0607 | 40 | 5K | OG1 | C2 | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-08 | 2024-01-25 | 2024-01-25 | 2024-02-02 |  | 2024-03-27 |  |  | 2024-04-05 | 9.2 | 260 | 393 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39275 | KR-0-216-041-15-SD5 | 2 | false | CH06822004-BD-PI-0607 | 15 | 5K | OG1 | C2 | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-15 | 2024-01-26 | 2024-01-30 | 2024-02-02 | [5 empty] | 1.8 | 260 | 393 | [6 empty] | 0 | SEP | SEP |  | 4
41942 | KR-0-216-041-15-SD5 | 3 | true | CH06822004-BD-PI-0607 | 15 | 5K | OG1 | C2 | PEL-ZAU-T-036 | 2024-01-12 | 2023-12-04 | 2023-12-04 | 2024-01-15 | 2024-01-26 | 2024-01-30 | 2024-02-02 |  | 2024-04-04 |  |  | 2024-04-24 | 1.8 | 260 | 393 | Virgil Frinculescu |  |  |  | No Mat. Change only Regulation Valve moved |  | 0 | SEP | SEP |  | 4
39276 | KR-0-216-042-15-SD5 | 2 | false | CH06822004-BD-PI-0607 | 15 | 5K | OG1 | C2 | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-15 | 2024-01-26 | 2024-01-30 | 2024-02-02 | [5 empty] | 1.7 | 260 | 393 | [6 empty] | 0 | SEP | SEP |  | 4
41943 | KR-0-216-042-15-SD5 | 3 | true | CH06822004-BD-PI-0607 | 15 | 5K | OG1 | C2 | PEL-ZAU-T-036 | 2024-01-12 | 2023-12-04 | 2023-12-04 | 2024-01-15 |  | 2024-01-30 | 2024-02-02 |  | 2024-04-04 |  |  | 2024-04-24 | 1.7 | 260 | 393 | Virgil Frinculescu |  |  |  | Updated Position of the Redulation Valve. |  | 0 | SEP | SEP |  | 4
39277 | KR-0-216-043-15-SD5 | 2 | false | CH06822004-BD-PI-0607 | 15 | 5K | OG1 | C2 | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-15 | 2024-01-29 | 2024-01-30 | 2024-02-02 |  |  |  |  | 2024-04-12 | 2.1 | 260 | 393 | [6 empty] | 0 | SEP | SEP |  | 4
41944 | KR-0-216-043-15-SD5 | 3 | true | CH06822004-BD-PI-0607 | 15 | 5K | OG1 | C2 | PEL-ZAU-T-036 | 2024-01-12 | 2023-12-04 | 2023-12-04 | 2024-01-15 | 2024-01-29 | 2024-01-30 | 2024-02-02 |  | 2024-04-04 |  |  | 2024-04-15 | 2.1 | 260 | 393 | Virgil Frinculescu |  |  |  | No Mat. Change only Regulation Valve moved |  | 0 | SEP | SEP |  | 4
39278 | KV-0-216-016-40-SD5 | 2 | true | CH06822004-BD-PI-0607 | 40 | 5K | OG1 | C2 | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-08 | 2024-01-25 | 2024-01-25 | 2024-02-02 |  | 2024-04-02 |  |  | 2024-04-06 | 9 | 260 | 394 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39279 | KV-0-216-016-40-SD5 | 2 | true | CH06822004-BD-PI-0607 | 40 | 5K | OG1 | C2 | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-08 | 2024-01-25 | 2024-01-25 | 2024-02-02 |  | 2024-04-02 |  |  | 2024-04-06 | 6.6 | 260 | 394 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39280 | KV-0-216-041-15-SD5 | 2 | true | CH06822004-BD-PI-0607 | 15 | 5K | OG1 | C2 | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-08 |  | 2024-01-22 | 2024-02-02 |  | 2024-04-02 |  |  | 2024-04-24 | 2 | 260 | 394 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39281 | KV-0-216-042-15-SD5 | 2 | true | CH06822004-BD-PI-0607 | 15 | 5K | OG1 | C2 | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-08 | 2024-01-25 | 2024-01-25 | 2024-02-02 |  | 2024-04-02 |  |  | 2024-04-24 | 1.9 | 260 | 394 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39282 | KV-0-216-043-15-SD5 | 2 | true | CH06822004-BD-PI-0607 | 15 | 5K | OG1 | C2 | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-08 | 2024-01-26 | 2024-01-26 | 2024-02-02 |  | 2024-04-02 |  |  | 2024-04-24 | 2.5 | 260 | 394 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39283 | N2F-7-500-004-025-SP1 | 2 | true | CH06822004-BD-PI-0457 | 25 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-11-28 | 2023-11-28 | 2024-01-08 |  | 2024-02-02 | 2024-02-02 |  | 2024-02-06 |  | 2024-03-23 | 2024-04-17 | 16.4 | 264 | 396 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39284 | N2F-7-500-004-025-SP1 | 2 | true | CH06822004-BD-PI-0457 | 25 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-11-28 | 2023-11-28 | 2023-12-20 |  | 2024-01-09 | 2024-01-12 |  | 2024-02-06 |  |  | 2024-03-21 | 5 | 264 | 396 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39285 | N2F-7-500-004-025-SP1 | 2 | true | CH06822004-BD-PI-0457 | 25 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-11-28 | 2023-11-28 | 2024-01-08 |  | 2024-02-02 | 2024-02-02 |  | 2024-02-06 |  | 2024-03-23 | 2024-04-17 | 12.2 | 264 | 396 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39286 | N2F-7-500-005-025-SP1 | 2 | true | CH06822004-BD-PI-0457 | 25 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-11-28 | 2023-11-28 | 2023-12-08 | 2023-12-14 | 2023-12-14 | 2023-12-15 |  | 2024-02-06 |  |  | 2024-02-22 | 8.1 | 264 | 396 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39287 | N2F-7-500-005-025-SP1 | 2 | true | CH06822004-BD-PI-0457 | 25 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-11-28 | 2023-11-28 | 2023-12-08 | 2023-12-14 | 2023-12-14 | 2023-12-15 |  | 2024-02-06 |  |  | 2024-02-23 | 5 | 264 | 396 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39288 | N2F-7-500-007-015-SP | 2 | true | CH06822004-BD-PI-0457 | 15 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-05 | 2024-01-12 | 2024-01-12 | 2024-01-19 |  | 2024-02-01 |  |  | 2024-05-21 | 2.5 | 262 | 396 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39289 | N2F-7-500-008-015-SP | 2 | true | CH06822004-BD-PI-0457 | 15 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-05 | 2024-01-12 | 2024-01-12 | 2024-01-19 |  | 2024-02-01 |  | 2024-03-23 | 2024-05-15 | 4.3 | 262 | 396 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39290 | N2F-7-500-009-15-SP | 2 | true | Not in latest LineList from 20231115 | 15 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-10 |  | 2024-01-10 | 2024-01-12 |  | 2024-03-20 |  |  | 2024-04-29 | 1 | 262 | 396 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39291 | N2F-7-500-010-15-SP | 2 | true | Not in latest LineList from 20231115 | 15 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-05 | 2024-01-12 | 2024-01-13 | 2024-01-19 |  | 2024-03-20 |  |  | 2024-04-29 | 0.8 | 262 | 396 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39292 | N2F-7-500-011-20-SP | 2 | true | Not in latest LineList from 20231115 | 20 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-11-28 | 2023-11-28 | 2024-01-08 | 2024-01-25 | 2024-01-25 | 2024-02-02 |  | 2024-03-20 |  |  | 2024-05-29 | 2.1 | 262 | 396 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39293 | N2F-7-500-012-20-SP | 2 | true | Not in latest LineList from 20231115 | 20 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-11-28 | 2023-11-28 | 2023-12-08 | 2023-12-14 | 2023-12-14 | 2023-12-15 |  | 2024-03-20 |  |  | 2024-05-29 | 0.3 | 262 | 396 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39294 | N2F-7-500-013-20-SP | 2 | true | Not in latest LineList from 20231115 | 20 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-11-28 | 2023-11-28 | 2024-01-08 | 2024-01-25 | 2024-01-25 | 2024-02-02 |  | 2024-03-20 |  |  | 2024-05-08 | 1 | 262 | 396 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39295 | O2F-7-400-004-25-SP1 | 2 | true | CH06822004-BD-PI-0465 | 25 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-11-28 | 2023-11-28 | 2023-12-18 |  | 2023-12-20 | 2024-01-12 |  | 2024-01-26 |  |  | 2024-02-13 | 15.8 | 264 | 458 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39296 | O2F-7-400-004-25-SP1 | 2 | true | CH06822004-BD-PI-0465 | 25 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-11-28 | 2023-11-28 | 2023-12-18 |  | 2023-12-20 | 2024-01-12 |  | 2024-01-26 |  |  | 2024-03-22 | 4.9 | 264 | 458 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39297 | O2F-7-400-004-25-SP1 | 2 | true | CH06822004-BD-PI-0465 | 25 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-11-28 | 2023-11-28 | 2023-12-18 |  | 2023-12-20 | 2024-01-12 |  | 2024-01-26 |  |  | 2024-02-20 | 12.7 | 264 | 458 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39299 | O2F-7-400-005-25-SP1 | 2 | false | CH06822004-BD-PI-0465 | 25 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-11-28 | 2023-11-28 | 2023-12-08 | 2023-12-14 | 2023-12-14 | 2023-12-15 |  | 2024-01-26 |  |  |  | 8 | 264 | 458 | Jozef Kotul | [5 empty] | 0 | SEP | SEP |  | 4
39300 | O2F-7-400-005-25-SP1 | 2 | false | CH06822004-BD-PI-0465 | 25 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-11-28 | 2023-11-28 | 2023-12-08 | 2023-12-14 | 2023-12-14 | 2023-12-15 |  | 2024-01-26 |  |  |  | 5 | 264 | 458 | Jozef Kotul | [5 empty] | 0 | SEP | SEP |  | 4
43912 | O2F-7-400-005-25-SP1 | 3 | true | CH06822004-BD-PI-0465 | 25 | 5K | OG1 | N/A | T-050 | 2024-01-31 | 2023-11-28 | 2023-11-28 | 2023-12-08 | 2023-12-14 | 2023-12-14 | 2023-12-15 |  | 2024-01-26 |  |  | 2024-02-22 | 8 | 264 | 458 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
43913 | O2F-7-400-005-25-SP1 | 3 | true | CH06822004-BD-PI-0465 | 25 | 5K | OG1 | N/A | T-050 | 2024-01-31 | 2023-11-28 | 2023-11-28 | 2023-12-08 | 2023-12-14 | 2023-12-14 | 2023-12-15 |  | 2024-01-26 |  |  | 2024-02-23 | 5 | 264 | 458 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
39301 | O2F-7-400-007-15-SP | 2 | true | Not in latest LineList from 20231115 | 15 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-05 | 2024-01-12 | 2024-01-12 | 2024-01-19 |  | 2024-02-01 |  |  | 2024-05-08 | 2.1 | 262 | 458 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39302 | O2F-7-400-008-15-SP | 2 | true | Not in latest LineList from 20231115 | 15 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-05 | 2024-01-12 | 2024-01-15 | 2024-01-19 |  | 2024-02-01 |  | 2024-03-23 | 2024-04-29 | 4.4 | 262 | 458 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39303 | O2F-7-400-009-15-SP | 2 | true | Not in latest LineList from 20231115 | 15 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-05 | 2024-01-12 | 2024-01-13 | 2024-01-19 |  | 2024-03-20 |  |  | 2024-04-18 | 1 | 262 | 458 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39304 | O2F-7-400-010-15-SP | 2 | true | Not in latest LineList from 20231115 | 15 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-10 |  | 2024-01-16 | 2024-01-19 |  | 2024-03-20 |  |  | 2024-04-23 | 0.6 | 262 | 458 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39305 | O2F-7-400-011-15-SP | 2 | true | Not in latest LineList from 20231115 | 15 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-30 |  | 2024-02-02 | 2024-02-02 |  | 2024-03-20 |  |  | 2024-05-08 | 0.9 | 262 | 458 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39306 | O2F-7-400-012-15-SP | 2 | true | Not in latest LineList from 20231115 | 15 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-05 | 2024-01-12 | 2024-01-12 | 2024-01-19 |  | 2024-03-20 |  |  | 2024-05-08 | 0.3 | 262 | 458 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39307 | O2F-7-400-013-15-SP | 2 | true | Not in latest LineList from 20231115 | 15 | 5K | OG1 | N/A | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-30 |  | 2024-02-02 | 2024-02-02 |  | 2024-03-20 |  |  | 2024-06-04 | 2.1 | 262 | 458 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39308 | TMG-2-017-004-25-SD | 2 | true | CH06822004-BD-PI-1432 | 25 | 5K | EG | H3 | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-08 | 2024-01-12 | 2024-01-16 | 2024-01-19 |  | 2024-02-12 |  |  | 2024-04-16 | 5.5 | 271 | 500 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39309 | TMG-2-003-003-25-SD | 2 | true | CH06822004-BD-PI-1467 | 25 | 5K | OG1 | H3 | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-08 | 2024-01-12 | 2024-01-16 | 2024-01-19 |  | 2024-02-01 |  |  | 2024-05-23 | 2.3 | 271 | 500 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39310 | TMG-2-003-004-25-SD | 2 | true | CH06822004-BD-PI-1467 | 25 | 5K | OG1 | H3 | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-08 | 2024-01-12 | 2024-01-16 | 2024-01-19 |  | 2024-02-01 |  |  | 2024-05-23 | 2 | 271 | 500 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39311 | TMG-2-007-003-25-SD | 2 | true | CH06822004-BD-PI-1468 | 25 | 5K | OG1 | H3 | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-04 | 2024-01-12 | 2024-01-16 | 2024-01-19 |  | 2024-02-01 |  |  | 2024-02-12 | 2.3 | 271 | 500 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39312 | TMG-2-007-003-25-SD | 2 | true | CH06822004-BD-PI-1468 | 25 | 5K | OG1 | H3 | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-04 | 2024-01-12 | 2024-01-15 | 2024-01-19 |  | 2024-02-01 |  |  | 2024-05-23 | 1.9 | 271 | 500 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39313 | TMG-2-007-004-25-SD | 2 | true | CH06822004-BD-PI-1468 | 25 | 5K | OG1 | H3 | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-08 | 2024-01-12 | 2024-01-16 | 2024-01-19 |  | 2024-02-01 |  |  | 2024-05-23 | 4.5 | 271 | 500 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39314 | TMG-2-008-003-25-SD | 2 | true | CH06822004-BD-PI-1469 | 25 | 5K | OG1 | H3 | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-04 | 2024-01-12 | 2024-01-15 | 2024-01-19 |  | 2024-02-01 |  |  | 2024-04-03 | 2.2 | 271 | 500 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39315 | TMG-2-008-003-25-SD | 2 | true | CH06822004-BD-PI-1469 | 25 | 5K | OG1 | H3 | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-04 | 2024-01-12 | 2024-01-16 | 2024-01-19 |  | 2024-02-01 |  |  | 2024-03-22 | 3 | 271 | 500 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39316 | TMG-2-008-004-25-SD | 2 | true | CH06822004-BD-PI-1469 | 25 | 5K | OG1 | H3 | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-08 |  | 2024-01-16 | 2024-01-19 |  | 2024-02-01 |  |  | 2024-04-08 | 2.2 | 271 | 500 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39317 | TMG-2-008-004-25-SD | 2 | true | CH06822004-BD-PI-1469 | 25 | 5K | OG1 | H3 | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-08 | 2024-01-25 | 2024-01-25 | 2024-02-02 |  | 2024-03-20 |  |  | 2024-04-08 | 2.8 | 271 | 500 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39318 | TMG-2-010-003-25-SD | 2 | true | CH06822004-BD-PI-1470 | 25 | 5K | OG1 | H3 | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-08 |  | 2024-01-16 | 2024-01-19 |  | 2024-02-01 |  |  | 2024-04-04 | 8.4 | 271 | 500 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39319 | TMG-2-010-004-25-SD | 2 | true | CH06822004-BD-PI-1470 | 25 | 5K | OG1 | H3 | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-08 |  | 2024-01-22 | 2024-02-02 |  | 2024-03-20 |  |  | 2024-04-04 | 8.4 | 271 | 500 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39320 | TMG-2-010-009-25-SD | 2 | true | CH06822004-BD-PI-1471 | 25 | 5K | OG1 | H3 | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-08 | 2024-01-25 | 2024-01-25 | 2024-02-02 |  | 2024-03-20 |  |  | 2024-04-04 | 6.7 | 271 | 500 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39321 | TMG-2-010-009-25-SD | 2 | true | CH06822004-BD-PI-1471 | 25 | 5K | OG1 | H3 | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-08 | 2024-01-26 | 2024-01-26 | 2024-02-02 |  | 2024-03-20 |  |  | 2024-04-04 | 1.5 | 271 | 500 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39322 | TMG-2-010-010-25-SD | 2 | true | CH06822004-BD-PI-1471 | 25 | 5K | OG1 | H3 | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-08 | 2024-01-26 | 2024-01-30 | 2024-02-02 |  | 2024-03-20 |  |  | 2024-04-04 | 1.8 | 271 | 500 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39323 | TMG-2-010-010-25-SD | 2 | true | CH06822004-BD-PI-1471 | 25 | 5K | OG1 | H3 | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-08 | 2024-01-26 | 2024-01-26 | 2024-02-02 |  | 2024-03-20 |  |  | 2024-04-04 | 6.3 | 271 | 500 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39324 | TMG-2-010-015-25-SD | 2 | true | CH06822004-BD-PI-1315 | 25 | 5K | OG1 | H3 | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-08 | 2024-01-25 | 2024-01-25 | 2024-02-02 |  | 2024-03-20 |  |  | 2024-04-05 | 5.2 | 271 | 500 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39325 | TMG-2-010-015-25-SD | 2 | true | CH06822004-BD-PI-1315 | 25 | 5K | OG1 | H3 | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-08 | 2024-01-25 | 2024-01-25 | 2024-02-02 |  | 2024-03-20 |  |  | 2024-04-05 | 7.3 | 271 | 500 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39326 | TMG-2-010-016-25-SD | 2 | true | CH06822004-BD-PI-1315 | 25 | 5K | OG1 | H3 | T02294 | 2023-11-22 | 2023-11-28 | 2023-11-28 | 2023-12-14 | 2024-01-12 | 2024-01-17 | 2024-01-19 |  | 2024-03-20 |  |  | 2024-04-05 | 7 | 271 | 500 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39327 | TMG-2-010-016-25-SD | 2 | true | CH06822004-BD-PI-1315 | 25 | 5K | OG1 | H3 | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2023-12-14 | 2024-01-12 | 2024-01-25 | 2024-02-02 |  | 2024-03-20 |  |  | 2024-04-05 | 4.9 | 271 | 500 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39328 | TMG-2-011-003-25-SD | 2 | true | CH06822004-BD-PI-1472 | 25 | 5K | OG1 | H3 | T02294 | 2023-11-22 | 2023-11-28 | 2023-11-28 | 2024-01-08 | 2024-01-25 | 2024-01-25 | 2024-02-02 |  | 2024-03-20 |  |  | 2024-04-09 | 2.8 | 271 | 500 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39329 | TMG-2-011-003-25-SD | 2 | true | CH06822004-BD-PI-1472 | 25 | 5K | OG1 | H3 | T02294 | 2023-11-22 | 2023-11-28 | 2023-11-28 | 2024-01-08 |  | 2024-01-17 | 2024-01-19 |  | 2024-03-20 |  |  | 2024-04-09 | 2.3 | 271 | 500 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39330 | TMG-2-011-004-25-SD | 2 | true | CH06822004-BD-PI-1472 | 25 | 5K | OG1 | H3 | T02294 | 2023-11-22 | 2023-11-28 | 2023-11-28 | 2023-12-19 | 2024-01-12 | 2024-01-16 | 2024-01-19 |  | 2024-03-20 |  |  | 2024-04-24 | 2.6 | 271 | 500 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39331 | TMG-2-011-004-25-SD | 2 | true | CH06822004-BD-PI-1472 | 25 | 5K | OG1 | H3 | T02294 | 2023-11-22 | 2023-11-28 | 2023-11-28 | 2023-12-19 | 2024-01-12 | 2024-01-25 | 2024-02-02 |  | 2024-03-20 |  |  | 2024-04-23 | 2.9 | 271 | 500 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39332 | TMG-2-011-009-25-SD | 2 | true | CH06822004-BD-PI-1473 | 25 | 5K | OG1 | H3 | T02294 | 2023-11-22 | 2023-11-28 | 2023-11-28 | 2024-01-03 | 2024-01-12 | 2024-01-25 | 2024-02-02 |  | 2024-03-20 |  |  | 2024-04-23 | 2.9 | 271 | 500 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39333 | TMG-2-011-009-25-SD | 2 | true | CH06822004-BD-PI-1473 | 25 | 5K | OG1 | H3 | T02294 | 2023-11-22 | 2023-11-28 | 2023-11-28 | 2024-01-03 | 2024-01-12 | 2024-01-18 | 2024-01-19 |  | 2024-03-20 |  |  | 2024-04-24 | 1.9 | 271 | 500 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39344 | TMG-2-011-010-25-SD | 2 | true | CH06822004-BD-PI-1473 | 25 | 5K | OG1 | H3 | T02294 | 2023-11-22 | 2023-11-28 | 2023-11-28 | 2024-01-03 | 2024-01-12 | 2024-01-16 | 2024-01-19 |  | 2024-03-20 |  |  | 2024-04-23 | 2 | 271 | 500 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39345 | TMG-2-011-010-25-SD | 2 | true | CH06822004-BD-PI-1473 | 25 | 5K | OG1 | H3 | T02294 | 2023-11-22 | 2023-11-28 | 2023-11-28 | 2024-01-03 | 2024-01-12 | 2024-01-16 | 2024-01-19 |  | 2024-03-20 |  |  | 2024-04-23 | 2.9 | 271 | 500 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39346 | TMG-2-011-015-25-SD | 2 | true | CH06822004-BD-PI-1322 | 25 | 5K | OG1 | H3 | T02294 | 2023-11-22 | 2023-11-28 | 2023-11-28 | 2023-12-13 |  | 2024-01-05 | 2024-01-12 |  | 2024-03-20 |  |  | 2024-04-09 | 1.4 | 271 | 500 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39347 | TMG-2-011-016-25-SD | 2 | true | CH06822004-BD-PI-1322 | 25 | 5K | OG1 | H3 | T02294 | 2023-11-22 | 2023-11-28 | 2023-11-28 | 2024-01-08 |  | 2024-01-17 | 2024-01-19 |  | 2024-03-20 |  |  | 2024-04-09 | 1.3 | 271 | 500 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39348 | TMG-2-012-001-25-SD | 2 | true | CH06822004-BD-PI-1513 | 25 | 5K | EG | H3 | T02294 | 2023-11-22 | 2023-11-28 | 2023-11-28 | 2023-12-20 | 2024-01-12 | 2024-01-18 | 2024-01-19 |  | 2024-02-15 |  |  | 2024-04-16 | 5.4 | 271 | 500 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39349 | TMG-2-012-003-25-SD | 2 | true | CH06822004-BD-PI-1513 | 25 | 5K | OG1 | H3 | T02294 | 2023-11-22 | 2023-11-28 | 2023-11-28 | 2024-01-08 | 2024-01-12 | 2024-01-25 | 2024-02-02 |  | 2024-03-20 |  |  | 2024-04-08 | 4.1 | 271 | 500 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39350 | TMG-2-012-004-25-SD | 2 | true | CH06822004-BD-PI-1513 | 25 | 5K | OG1 | H3 | T02294 | 2023-11-22 | 2023-11-28 | 2023-11-28 | 2024-01-16 | 2024-01-17 | 2024-01-22 | 2024-02-02 |  | 2024-03-20 |  |  | 2024-04-08 | 3.6 | 271 | 500 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39351 | TMG-2-012-006-25-SD | 2 | true | CH06822004-BD-PI-1514 | 25 | 5K | EG | H3 | T02294 | 2023-11-22 | 2023-11-28 | 2023-11-28 | 2023-12-20 | 2024-01-12 | 2024-01-26 | 2024-02-02 |  | 2024-02-15 |  |  | 2024-04-16 | 4.9 | 271 | 500 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39352 | TMG-2-012-009-25-SD | 2 | true | CH06822004-BD-PI-1514 | 25 | 5K | OG1 | H3 | T02294 | 2023-11-22 | 2023-11-28 | 2023-11-28 | 2023-12-14 | 2024-01-26 | 2024-01-30 | 2024-02-02 |  | 2024-03-20 |  |  | 2024-04-08 | 3.6 | 271 | 500 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39353 | TMG-2-012-010-25-SD | 2 | true | CH06822004-BD-PI-1514 | 25 | 5K | OG1 | H3 | T02294 | 2023-11-22 | 2023-11-28 | 2023-11-28 | 2023-12-20 | 2024-01-12 | 2024-01-25 | 2024-02-02 |  | 2024-03-20 |  |  | 2024-04-08 | 3.5 | 271 | 500 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39354 | TMG-2-013-003-25-SD | 2 | true | CH06822004-BD-PI-1329 | 25 | 5K | EG | H3 | T02294 | 2023-11-22 | 2023-11-28 | 2023-11-28 | 2024-01-08 |  | 2024-01-17 | 2024-01-19 |  | 2024-02-15 |  |  | 2024-02-23 | 2.8 | 271 | 500 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39355 | TMG-2-013-003-25-SD | 2 | true | CH06822004-BD-PI-1329 | 25 | 5K | EG | H3 | T02294 | 2023-11-22 | 2023-11-28 | 2023-11-28 | 2024-01-08 |  | 2024-01-22 | 2024-02-02 |  | 2024-02-15 |  |  | 2024-04-16 | 3.6 | 271 | 500 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39356 | TMG-2-013-004-25-SD | 2 | true | CH06822004-BD-PI-1329 | 25 | 5K | EG | H3 | T02294 | 2023-11-22 | 2023-11-28 | 2023-11-28 | 2024-01-03 | 2024-01-12 | 2024-01-15 | 2024-01-19 |  | 2024-02-15 |  |  | 2024-04-16 | 3.3 | 271 | 500 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39357 | TMG-2-013-004-25-SD | 2 | true | CH06822004-BD-PI-1329 | 25 | 5K | EG | H3 | T02294 | 2023-11-22 | 2023-11-28 | 2023-11-28 | 2024-01-03 | 2024-01-12 | 2024-01-16 | 2024-01-19 |  | 2024-02-15 |  |  | 2024-02-23 | 3.2 | 271 | 500 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39358 | TMG-2-014-003-25-SD | 2 | true | CH06822004-BD-PI-1336 | 25 | 5K | EG | H3 | T02294 | 2023-11-22 | 2023-11-28 | 2023-11-28 | 2023-12-11 | 2024-01-12 | 2024-01-17 | 2024-01-19 |  | 2024-02-15 |  |  | 2024-04-16 | 4.8 | 271 | 500 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39359 | TMG-2-014-004-25-SD | 2 | true | CH06822004-BD-PI-1336 | 25 | 5K | EG | H3 | T02294 | 2023-11-22 | 2023-11-28 | 2023-11-28 | 2023-12-11 | 2024-01-12 | 2024-01-25 | 2024-02-02 |  | 2024-02-15 |  |  | 2024-04-16 | 4.9 | 271 | 500 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39360 | TMG-2-015-003-25-SD | 2 | true | CH06822004-BD-PI-1343 | 25 | 5K | EG | H3 | T02294 | 2023-11-22 | 2023-11-28 | 2023-11-28 | 2023-12-11 | 2024-01-12 | 2024-01-17 | 2024-01-19 |  | 2024-02-15 |  |  | 2024-04-16 | 2.5 | 271 | 500 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39361 | TMG-2-015-004-25-SD | 2 | true | CH06822004-BD-PI-1343 | 25 | 5K | EG | H3 | T02294 | 2023-11-22 | 2023-11-28 | 2023-11-28 | 2023-12-12 | 2024-01-12 | 2024-01-17 | 2024-01-19 |  | 2024-02-15 |  |  | 2024-04-16 | 2.8 | 271 | 500 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39362 | TMG-2-016-003-25-SD | 2 | true | CH06822004-BD-PI-1357 | 25 | 5K | EG | H3 | T02294 | 2023-11-22 | 2023-12-04 | 2023-12-04 | 2024-01-08 | 2024-01-26 | 2024-01-26 | 2024-02-02 |  | 2024-02-12 |  |  | 2024-04-16 | 4.5 | 271 | 500 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39363 | TMG-2-016-004-25-SD | 2 | true | CH06822004-BD-PI-1357 | 25 | 5K | EG | H3 | T02294 | 2023-11-22 | 2023-11-28 | 2023-11-28 | 2023-12-14 | 2024-01-12 | 2024-01-26 | 2024-02-02 |  | 2024-02-12 |  |  | 2024-04-16 | 4.4 | 271 | 500 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
39364 | TMG-2-017-003-25-SD | 2 | true | CH06822004-BD-PI-1432 | 25 | 5K | EG | H3 | T02294 | 2023-11-22 | 2023-11-28 | 2023-11-28 | 2023-12-12 | 2024-01-12 | 2024-01-17 | 2024-01-19 |  | 2024-02-12 |  |  | 2024-04-16 | 5.3 | 271 | 500 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP |  | 4
40186 | KV-0-216-007-25-SD5 | 2 | true |  | 25 | 5K | EG | C2 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-11 | 2024-01-12 | 2024-01-18 | 2024-01-19 |  | 2024-02-01 |  |  | 2024-02-07 | 2.2 | 260 | 394 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40187 | KV-0-216-008-25-SD5 | 2 | true |  | 25 | 5K | EG | C2 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-15 | 2024-01-25 | 2024-01-25 | 2024-02-02 |  | 2024-02-15 |  |  | 2024-02-28 | 2.2 | 260 | 394 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40188 | KV-0-216-009-25-SD5 | 2 | true |  | 25 | 5K | EG | C2 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-11 | 2024-01-25 | 2024-01-25 | 2024-02-02 |  | 2024-02-15 |  |  | 2024-02-28 | 2.8 | 260 | 394 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40189 | KV-0-216-010-25-SD5 | 2 | true |  | 25 | 5K | EG | C2 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-11 | 2024-01-12 | 2024-01-17 | 2024-01-19 |  | 2024-02-01 |  |  | 2024-02-07 | 2.3 | 260 | 394 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40190 | KV-0-216-013-25-SD5 | 2 | true |  | 25 | 5K | EG | C2 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-15 | 2024-01-25 | 2024-01-25 | 2024-02-02 |  | 2024-02-15 |  |  | 2024-04-26 | 3.7 | 260 | 394 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40191 | KV-0-216-014-25-SD5 | 2 | true |  | 25 | 5K | EG | C2 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-15 | 2024-01-25 | 2024-01-25 | 2024-02-02 |  | 2024-02-15 |  |  | 2024-02-28 | 2.2 | 260 | 394 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40192 | KR-0-216-031-25-SD5 | 2 | true |  | 25 | 5K | EG | C2 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-11 | 2024-01-12 | 2024-01-17 | 2024-01-19 |  | 2024-02-01 |  |  | 2024-02-07 | 1.8 | 260 | 393 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40193 | KR-0-216-006-25-SD5 | 2 | true |  | 25 | 5K | EG | C2 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-11 |  | 2024-01-23 | 2024-02-02 |  | 2024-02-15 |  |  | 2024-02-20 | 1.8 | 260 | 393 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40194 | KR-0-216-007-25-SD5 | 2 | true |  | 25 | 5K | EG | C2 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-25 | 2024-01-29 | 2024-01-29 | 2024-02-02 |  | 2024-02-15 |  |  | 2024-02-28 | 1.9 | 260 | 393 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40195 | KR-0-216-008-25-SD5 | 2 | true |  | 25 | 5K | EG | C2 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-15 |  | 2024-01-23 | 2024-02-02 |  | 2024-02-15 |  |  | 2024-02-28 | 2.4 | 260 | 393 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40196 | KR-0-216-009-25-SD5 | 2 | true |  | 25 | 5K | EG | C2 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-11 | 2024-01-12 | 2024-01-18 | 2024-01-19 |  | 2024-02-01 |  |  | 2024-02-07 | 2 | 260 | 393 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40197 | KR-0-216-013-25-SD5 | 2 | true |  | 25 | 5K | EG | C2 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-11 |  | 2024-01-23 | 2024-02-02 |  | 2024-02-15 |  |  | 2024-04-26 | 3.3 | 260 | 393 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40198 | TMG-2-017-006-25-SD | 2 | true |  | 25 | 5K | EG | H3 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-10 | 2024-01-26 | 2024-01-26 | 2024-02-02 |  | 2024-02-12 |  |  | 2024-02-15 | 5 | 271 | 500 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40199 | TMG-2-012-013-25-SD | 2 | true |  | 25 | 5K | EG | H3 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-08 |  | 2024-01-23 | 2024-02-02 |  | 2024-02-15 |  |  | 2024-02-23 | 2.2 | 271 | 500 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40200 | TMG-2-012-013-25-SD | 2 | true |  | 25 | 5K | EG | H3 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-08 | 2024-01-25 | 2024-01-25 | 2024-02-02 |  | 2024-02-15 |  |  | 2024-02-23 | 4.7 | 271 | 500 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40201 | TMG-2-012-018-25-SD | 2 | true |  | 25 | 5K | EG | H3 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-10 |  | 2024-01-17 | 2024-01-19 |  | 2024-02-15 |  |  | 2024-03-05 | 5.2 | 271 | 500 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40202 | TMG-2-013-001-25-SD | 2 | true |  | 25 | 5K | EG | H3 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-10 |  | 2024-01-23 | 2024-02-02 |  | 2024-02-15 |  |  | 2024-02-28 | 2.3 | 271 | 500 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40203 | TMG-2-013-001-25-SD | 2 | true |  | 25 | 5K | EG | H3 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-10 |  | 2024-01-23 | 2024-02-02 |  | 2024-02-15 |  |  | 2024-02-29 | 5.3 | 271 | 500 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40204 | TMG-2-013-006-25-SD | 2 | true |  | 25 | 5K | EG | H3 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-10 |  | 2024-01-22 | 2024-02-02 |  | 2024-02-15 |  |  | 2024-03-05 | 5.5 | 271 | 500 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40205 | TMG-2-014-001-25-SD | 2 | true |  | 25 | 5K | EG | H3 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-10 | 2024-01-12 | 2024-01-22 | 2024-02-02 |  | 2024-02-12 |  |  | 2024-02-20 | 5.8 | 271 | 500 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40206 | TMG-2-014-006-25-SD | 2 | true |  | 25 | 5K | EG | H3 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-08 | 2024-01-25 | 2024-01-25 | 2024-02-02 |  | 2024-02-12 |  |  | 2024-02-20 | 4.4 | 271 | 500 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40207 | TMG-2-015-001-25-SD | 2 | true |  | 25 | 5K | EG | H3 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-10 | 2024-01-25 | 2024-01-25 | 2024-02-02 |  | 2024-02-12 |  |  | 2024-02-20 | 6.8 | 271 | 500 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40208 | TMG-2-015-001-25-SD | 2 | true |  | 25 | 5K | EG | H3 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-10 | 2024-01-25 | 2024-01-25 | 2024-02-02 |  | 2024-02-12 |  |  | 2024-02-20 | 1.9 | 271 | 500 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40209 | TMG-2-015-006-25-SD | 2 | true |  | 25 | 5K | EG | H3 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-08 | 2024-01-25 | 2024-01-25 | 2024-02-02 |  | 2024-02-12 |  |  | 2024-02-20 | 6.8 | 271 | 500 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40210 | TMG-2-016-001-25-SD | 2 | true |  | 25 | 5K | EG | H3 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-10 | 2024-01-25 | 2024-01-25 | 2024-02-02 |  | 2024-02-12 |  |  | 2024-02-26 | 7.3 | 271 | 500 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40211 | TMG-2-016-001-25-SD | 2 | true |  | 25 | 5K | EG | H3 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-10 | 2024-01-25 | 2024-01-25 | 2024-02-02 |  | 2024-02-12 |  |  | 2024-02-26 | 1.9 | 271 | 500 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40212 | TMG-2-016-006-25-SD | 2 | true |  | 25 | 5K | EG | H3 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-10 | 2024-01-12 | 2024-01-17 | 2024-01-19 |  | 2024-02-12 |  |  | 2024-02-15 | 7.4 | 271 | 500 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40213 | TMG-2-017-001-25-SD | 2 | true |  | 25 | 5K | EG | H3 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-08 | 2024-01-25 | 2024-01-25 | 2024-02-02 |  | 2024-02-12 |  |  | 2024-02-15 | 1.6 | 271 | 500 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40214 | TMG-2-017-001-25-SD | 2 | true |  | 25 | 5K | EG | H3 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-08 | 2024-01-25 | 2024-01-25 | 2024-02-02 |  | 2024-02-12 |  |  | 2024-02-15 | 4.9 | 271 | 500 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40215 | GV-0-244-011-32-SD5 | 2 | true |  | 32 | 5K | OG1 | C3 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-08 | 2024-01-12 | 2024-01-15 | 2024-01-19 |  | 2024-02-22 |  |  | 2024-03-05 | 3.1 | 260 | 388 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40216 | GV-0-244-006-32-SD5 | 2 | true |  | 32 | 5K | OG1 | C3 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-09 |  | 2024-01-18 | 2024-01-19 |  | 2024-02-22 |  |  | 2024-03-05 | 3 | 260 | 388 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40217 | GV-0-244-007-32-SD5 | 2 | true |  | 32 | 5K | OG1 | C3 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-09 |  | 2024-01-17 | 2024-01-19 |  | 2024-02-22 |  |  | 2024-03-05 | 2.5 | 260 | 388 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40218 | GV-0-244-008-32-SD5 | 2 | true |  | 32 | 5K | OG1 | C3 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-09 | 2024-01-12 | 2024-01-23 | 2024-02-02 |  | 2024-02-22 |  |  | 2024-03-05 | 3 | 260 | 388 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40219 | GV-0-244-009-32-SD5 | 2 | true |  | 32 | 5K | OG1 | C3 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-09 | 2024-01-25 | 2024-01-25 | 2024-02-02 |  | 2024-02-22 |  |  | 2024-03-05 | 2.5 | 260 | 388 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40220 | GV-0-244-010-32-SD5 | 2 | true |  | 32 | 5K | OG1 | C3 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-09 |  | 2024-01-17 |  |  | 2024-02-22 |  |  | 2024-03-05 | 2.6 | 260 | 388 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40221 | GR-0-244-010-32-SD5 | 2 | true |  | 32 | 5K | OG1 | C3 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-09 | 2024-01-12 | 2024-01-16 | 2024-01-19 |  | 2024-02-22 |  |  | 2024-03-05 | 3 | 260 | 387 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40222 | GR-0-244-005-32-SD5 | 2 | true |  | 32 | 5K | OG1 | C3 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-09 | 2024-01-12 | 2024-01-16 | 2024-01-19 |  | 2024-02-22 |  |  | 2024-03-05 | 2.7 | 260 | 387 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40223 | GR-0-244-006-32-SD5 | 2 | true |  | 32 | 5K | OG1 | C3 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-09 | 2024-01-12 | 2024-01-15 | 2024-01-19 |  | 2024-02-22 |  |  | 2024-03-05 | 2.2 | 260 | 387 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40224 | GR-0-244-007-32-SD5 | 2 | true |  | 32 | 5K | OG1 | C3 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-09 | 2024-01-12 | 2024-01-16 | 2024-01-19 |  | 2024-02-22 |  |  | 2024-03-05 | 2.9 | 260 | 387 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40225 | GR-0-244-008-32-SD5 | 2 | true |  | 32 | 5K | OG1 | C3 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-09 | 2024-01-12 | 2024-01-15 | 2024-01-19 |  | 2024-02-22 |  |  | 2024-03-05 | 2.2 | 260 | 387 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40226 | GR-0-244-009-32-SD5 | 2 | true |  | 32 | 5K | OG1 | C3 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-09 | 2024-01-12 | 2024-01-15 | 2024-01-19 |  | 2024-02-22 |  |  | 2024-03-05 | 2.4 | 260 | 387 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40227 | KV-0-216-015-15-SD5 | 2 | true |  | 15 | 5K | OG1 | C2 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-09 | 2024-01-12 | 2024-01-17 | 2024-01-19 |  | 2024-02-01 |  |  | 2024-02-12 | 2.5 | 260 | 394 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40228 | KV-0-216-018-15-SD5 | 2 | true |  | 15 | 5K | OG1 | C2 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-08 | 2024-01-12 | 2024-01-17 | 2024-01-19 |  | 2024-02-01 |  |  | 2024-02-12 | 4 | 260 | 394 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40229 | KV-0-216-019-15-SD5 | 2 | true |  | 15 | 5K | OG1 | C2 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-08 | 2024-01-12 | 2024-01-17 | 2024-01-19 |  | 2024-02-01 |  |  | 2024-02-12 | 2.5 | 260 | 394 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40230 | KV-0-216-022-15-SD5 | 2 | true |  | 15 | 5K | OG1 | C2 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-09 | 2024-01-12 | 2024-01-17 | 2024-01-19 |  | 2024-02-01 |  |  | 2024-02-12 | 3.2 | 260 | 394 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40231 | KV-0-216-023-15-SD5 | 2 | true |  | 15 | 5K | OG1 | C2 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-08 | 2024-01-12 | 2024-01-17 | 2024-01-19 |  | 2024-02-01 |  |  | 2024-02-09 | 4.5 | 260 | 394 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40232 | KR-0-216-014-15-SD5 | 2 | true |  | 15 | 5K | OG1 | C2 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-08 | 2024-01-12 | 2024-01-17 | 2024-01-19 |  | 2024-02-01 |  |  | 2024-02-13 | 2.2 | 260 | 393 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40233 | KR-0-216-017-15-SD5 | 2 | true |  | 15 | 5K | OG1 | C2 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-10 | 2024-01-12 | 2024-01-15 | 2024-01-19 |  | 2024-02-01 |  |  | 2024-02-13 | 3.7 | 260 | 393 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40234 | KR-0-216-018-15-SD5 | 2 | true |  | 15 | 5K | OG1 | C2 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-08 | 2024-01-12 | 2024-01-17 | 2024-01-19 |  | 2024-02-01 |  |  | 2024-02-13 | 2.2 | 260 | 393 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40235 | KR-0-216-021-15-SD5 | 2 | true |  | 15 | 5K | OG1 | C2 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-10 | 2024-01-12 | 2024-01-15 | 2024-01-19 |  | 2024-02-01 |  |  | 2024-02-13 | 2.9 | 260 | 393 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40236 | KR-0-216-022-15-SD5 | 2 | true |  | 15 | 5K | OG1 | C2 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-10 | 2024-01-12 | 2024-01-15 | 2024-01-19 |  | 2024-02-01 |  |  | 2024-02-09 | 3.8 | 260 | 393 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40237 | TMG-2-012-016-25-SD | 2 | true |  | 25 | 5K | OG1 | H3 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-22 | 2024-01-29 | 2024-01-29 | 2024-02-02 |  | 2024-03-05 |  |  | 2024-03-14 | 6.2 | 271 | 500 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40238 | TMG-2-003-001-25-SD | 2 | false |  | 25 | 5K | OG1 | H3 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-22 | 2024-01-29 | 2024-01-30 | 2024-02-02 | [5 empty] | 3.3 | 271 | 500 |  | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40239 | TMG-2-003-001-25-SD | 2 | false |  | 25 | 5K | OG1 | H3 | T02400 | 2023-12-13 | [11 empty] | 5.5 | 271 | 500 |  | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
43259 | TMG-2-003-001-25-SD | 3 | true |  | 25 | 5K | OG1 | H3 | PEL-ZAU-T-044 | 2024-01-19 | 2023-12-20 | 2023-12-20 | 2024-01-22 | 2024-01-29 | 2024-01-30 | 2024-02-02 |  | 2024-03-05 |  |  | 2024-03-14 | 3.3 | 271 | 500 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP
43260 | TMG-2-003-001-25-SD | 3 | true |  | 25 | 5K | OG1 | H3 | PEL-ZAU-T-044 | 2024-01-19 | 2024-02-05 | 2024-02-05 | 2024-02-06 |  | 2024-02-12 | 2024-02-16 |  | 2024-03-05 |  |  | 2024-03-11 | 4.9 | 271 | 500 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
43261 | TMG-2-003-001-25-SD | 3 | true |  | 25 | 5K | OG1 | H3 | PEL-ZAU-T-044 | 2024-01-19 | 2024-02-05 | 2024-02-05 | 2024-02-06 |  | 2024-02-12 | 2024-02-16 |  | 2024-03-05 |  |  | 2024-04-16 | 3 | 271 | 500 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40240 | TMG-2-003-006-25-SD | 2 | false |  | 25 | 5K | OG1 | H3 | T02400 | 2023-12-13 | [11 empty] | 6.8 | 271 | 500 |  | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
43263 | TMG-2-003-006-25-SD | 3 | true |  | 25 | 5K | OG1 | H3 | PEL-ZAU-T-044 | 2024-01-19 | 2024-02-05 | 2024-02-05 | 2024-02-06 |  | 2024-02-12 | 2024-02-16 |  | 2024-03-20 |  |  | 2024-04-16 | 3.2 | 271 | 500 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
43264 | TMG-2-003-006-25-SD | 3 | true |  | 25 | 5K | OG1 | H3 | PEL-ZAU-T-044 | 2024-01-19 | 2024-02-05 | 2024-02-05 | 2024-02-06 |  | 2024-02-12 | 2024-02-16 |  | 2024-03-20 |  |  | 2024-04-08 | 6 | 271 | 500 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40241 | TMG-2-007-001-25-SD | 2 | true |  | 25 | 5K | OG1 | H3 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-11 | 2024-01-25 | 2024-01-25 | 2024-02-02 |  |  |  |  | 2024-02-28 | 4.6 | 271 | 500 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40242 | TMG-2-007-001-25-SD | 2 | true |  | 25 | 5K | OG1 | H3 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-11 | 2024-01-29 | 2024-01-29 | 2024-02-02 |  |  |  |  | 2024-02-28 | 2.2 | 271 | 500 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40243 | TMG-2-007-006-25-SD | 2 | true |  | 25 | 5K | OG1 | H3 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-22 | 2024-01-29 | 2024-01-29 | 2024-02-02 |  |  |  |  | 2024-02-28 | 4.5 | 271 | 500 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40244 | TMG-2-008-001-25-SD | 2 | true |  | 25 | 5K | OG1 | H3 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-12 |  | 2024-01-22 | 2024-02-02 |  | 2024-03-05 |  |  | 2024-03-14 | 4.8 | 271 | 500 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40245 | TMG-2-008-001-25-SD | 2 | true |  | 25 | 5K | OG1 | H3 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-12 |  | 2024-01-22 | 2024-02-02 |  | 2024-03-05 |  |  | 2024-03-19 | 2.2 | 271 | 500 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40246 | TMG-2-008-006-25-SD | 2 | true |  | 25 | 5K | OG1 | H3 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-22 | 2024-01-29 | 2024-01-29 | 2024-02-02 |  | 2024-03-05 |  |  | 2024-03-14 | 4.7 | 271 | 500 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40247 | TMG-2-010-001-25-SD | 2 | true |  | 25 | 5K | OG1 | H3 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-12 | 2024-01-26 | 2024-01-26 | 2024-02-02 |  | 2024-02-12 |  |  | 2024-02-26 | 2.4 | 271 | 500 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40248 | TMG-2-010-001-25-SD | 2 | true |  | 25 | 5K | OG1 | H3 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-12 | 2024-01-25 | 2024-01-25 | 2024-02-02 |  | 2024-02-12 |  |  | 2024-02-22 | 17.5 | 271 | 500 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40249 | TMG-2-010-006-25-SD | 2 | true |  | 25 | 5K | OG1 | H3 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-10 | 2024-01-26 | 2024-01-26 | 2024-02-02 |  | 2024-02-12 |  |  | 2024-03-05 | 17.5 | 271 | 500 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40250 | TMG-2-010-007-25-SD | 2 | true |  | 25 | 5K | OG1 | H3 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-12 | 2024-01-26 | 2024-01-26 | 2024-02-02 |  | 2024-02-12 |  |  | 2024-02-20 | 11.4 | 271 | 500 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40251 | TMG-2-010-007-25-SD | 2 | true |  | 25 | 5K | OG1 | H3 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-12 | 2024-01-26 | 2024-01-26 | 2024-02-02 |  | 2024-02-12 |  |  | 2024-02-22 | 2.1 | 271 | 500 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40252 | TMG-2-010-012-25-SD | 2 | true |  | 25 | 5K | OG1 | H3 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-10 | 2024-01-12 | 2024-01-23 | 2024-02-02 |  | 2024-02-12 |  |  | 2024-02-20 | 10.8 | 271 | 500 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40253 | TMG-2-010-013-25-SD | 2 | true |  | 25 | 5K | OG1 | H3 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-12 | 2024-01-29 | 2024-01-30 | 2024-02-02 |  | 2024-03-05 |  |  | 2024-03-14 | 2.6 | 271 | 500 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40254 | TMG-2-010-013-25-SD | 2 | true |  | 25 | 5K | OG1 | H3 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-12 | 2024-01-29 | 2024-01-30 | 2024-02-02 |  | 2024-03-05 |  |  | 2024-03-14 | 10.6 | 271 | 500 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40255 | TMG-2-010-018-25-SD | 2 | true |  | 25 | 5K | OG1 | H3 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-11 | 2024-01-29 | 2024-01-29 | 2024-02-02 |  | 2024-03-05 |  |  | 2024-03-14 | 2.6 | 271 | 500 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40256 | TMG-2-010-018-25-SD | 2 | true |  | 25 | 5K | OG1 | H3 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-11 | 2024-01-26 | 2024-01-29 | 2024-02-02 |  | 2024-03-05 |  |  | 2024-03-14 | 8.4 | 271 | 500 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40257 | TMG-2-011-001-25-SD | 2 | true |  | 25 | 5K | OG1 | H3 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-10 | 2024-01-26 | 2024-01-26 | 2024-02-02 |  | 2024-02-12 |  |  | 2024-02-26 | 2.4 | 271 | 500 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40258 | TMG-2-011-001-25-SD | 2 | true |  | 25 | 5K | OG1 | H3 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-10 | 2024-01-25 | 2024-01-25 | 2024-02-02 |  | 2024-02-12 |  |  | 2024-02-26 | 8.7 | 271 | 500 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40259 | TMG-2-011-006-25-SD | 2 | true |  | 25 | 5K | OG1 | H3 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-10 |  | 2024-01-16 | 2024-01-19 |  | 2024-02-12 |  |  | 2024-02-26 | 9 | 271 | 500 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40260 | TMG-2-011-007-25-SD | 2 | true |  | 25 | 5K | OG1 | H3 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-10 |  | 2024-01-17 | 2024-01-19 |  | 2024-02-12 |  |  | 2024-02-23 | 4.4 | 271 | 500 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40261 | TMG-2-011-007-25-SD | 2 | true |  | 25 | 5K | OG1 | H3 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-10 |  | 2024-01-17 | 2024-01-19 |  | 2024-02-12 |  |  | 2024-02-23 | 1.4 | 271 | 500 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40262 | TMG-2-011-012-25-SD | 2 | true |  | 25 | 5K | OG1 | H3 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-22 | 2024-01-29 | 2024-01-30 | 2024-02-02 |  | 2024-02-12 |  |  | 2024-02-23 | 4.5 | 271 | 500 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40263 | TMG-2-011-013-25-SD | 2 | true |  | 25 | 5K | OG1 | H3 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-12 | 2024-01-26 | 2024-01-26 | 2024-02-02 |  | 2024-03-05 |  |  | 2024-03-14 | 2.9 | 271 | 500 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40264 | TMG-2-011-013-25-SD | 2 | true |  | 25 | 5K | OG1 | H3 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-12 |  | 2024-01-18 | 2024-01-19 |  | 2024-03-05 |  |  | 2024-03-14 | 2.1 | 271 | 500 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40265 | TMG-2-011-013-25-SD | 2 | true |  | 25 | 5K | OG1 | H3 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-12 | 2024-01-29 | 2024-01-29 | 2024-02-02 |  | 2024-03-05 |  |  | 2024-03-14 | 13.2 | 271 | 500 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40266 | TMG-2-011-018-25-SD | 2 | true |  | 25 | 5K | OG1 | H3 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-10 | 2024-01-26 | 2024-01-26 | 2024-02-02 |  | 2024-03-05 |  |  | 2024-03-11 | 13.1 | 271 | 500 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40267 | TMG-2-011-018-25-SD | 2 | true |  | 25 | 5K | OG1 | H3 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-10 | 2024-01-25 | 2024-01-25 | 2024-02-02 |  | 2024-03-05 |  |  | 2024-03-20 | 2.8 | 271 | 500 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40268 | TMG-2-012-007-25-SD | 2 | true |  | 25 | 5K | OG1 | H3 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-22 | 2024-01-29 | 2024-01-29 | 2024-02-02 |  | 2024-03-05 |  |  | 2024-03-19 | 2.6 | 271 | 500 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40269 | TMG-2-012-007-25-SD | 2 | true |  | 25 | 5K | OG1 | H3 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-22 | 2024-01-29 | 2024-01-29 | 2024-02-02 |  | 2024-03-05 |  |  | 2024-03-19 | 10.8 | 271 | 500 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40270 | TMG-2-012-012-25-SD | 2 | true |  | 25 | 5K | OG1 | H3 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-22 | 2024-01-29 | 2024-01-29 | 2024-02-02 |  | 2024-03-05 |  |  | 2024-03-14 | 11.1 | 271 | 500 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40271 | TMG-2-012-015-25-SD | 2 | true |  | 25 | 5K | OG1 | H3 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-15 |  | 2024-01-22 | 2024-02-02 |  | 2024-03-05 |  |  | 2024-03-14 | 6.6 | 271 | 500 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
40272 | TMG-2-012-015-25-SD | 2 | true |  | 25 | 5K | OG1 | H3 | T02400 | 2023-12-13 | 2023-12-20 | 2023-12-20 | 2024-01-15 |  | 2024-01-22 | 2024-02-02 |  | 2024-03-05 |  |  | 2024-03-14 | 1.4 | 271 | 500 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP |  | 4
41892 | KKR-0-241-003-80-SD5 | 3 | true | CH06822004-BD-PI-0593 | 80 | 5K | OG3 | C2 | PEL-ZAU-T-033 | 2024-01-12 |  | 2023-11-20 | 2023-12-11 |  | 2024-01-10 | 2024-01-12 |  | 2024-02-27 |  |  | 2024-03-07 | 0.1 | 260 | 392 | Virgil Frinculescu |  |  |  | No change + old ISO 38543 |  | 0 | SEP | SEP |  | 5
41893 | KKR-0-241-003-80-SD5 | 3 | true | CH06822004-BD-PI-0593 | 80 | 5K | OG3 | C2 | PEL-ZAU-T-033 | 2024-01-12 |  | 2023-11-20 | 2023-11-23 | 2024-01-10 | 2024-01-10 | 2024-01-12 |  | 2024-02-27 |  |  | 2024-06-06 | 2.3 | 260 | 392 | Virgil Frinculescu |  |  |  | Updated Positions of Thermowells etc. + old ISO 38544 |  | 0 | SEP | SEP |  | 5
41907 | KKV-0-241-008-80-SD5 | 3 | true | CH06822004-BD-PI-0593 | 80 | 5K | OG3 | C2 | PEL-ZAU-T-033 | 2024-01-12 |  | 2023-11-20 | 2023-12-11 | 2024-01-12 | 2024-01-16 |  |  | 2024-02-27 |  |  | 2024-06-06 | 2.6 | 260 | 392 | Virgil Frinculescu |  |  |  | Updated Positions of Thermowells etc. |  | 0 | SEP | SEP |  | 5
41908 | KKV-0-241-008-80-SD5 | 3 | true | CH06822004-BD-PI-0593 | 80 | 5K | OG3 | C2 | PEL-ZAU-T-033 | 2024-01-12 |  | 2023-11-20 | 2023-12-11 | 2024-01-12 | 2024-01-16 |  |  | 2024-02-27 |  |  | 2024-03-11 | 0.7 | 260 | 392 | Virgil Frinculescu |  |  |  | Length changes in DN20 |  | 0 | SEP | SEP |  | 5
42030 | WAI-7-201-003-50-SD | 2 | true |  | 50 | 5K | UG | H3 | PEL-ZAU-T-031 | 2024-01-12 | [10 empty] | 2024-03-13 | 11.1 | 271 | 413 | Virgil Frinculescu |  |  | old name WAI-7-201-003-40-SD | Completly new DN |  | 0 | SEP | SEP
42031 | WAI-7-201-003-50-SD | 2 | true |  | 50 | 5K | UG | H3 | PEL-ZAU-T-031 | 2024-01-12 | [10 empty] | 2024-02-29 | 8.4 | 271 | 413 | Virgil Frinculescu |  |  | old name WAI-7-201-003-40-SD | Completly new DN |  | 0 | SEP | SEP |  | 0
42033 | WAI-7-201-006-50-SD | 1 | true |  | 50 | 5K | UG | H3 | PEL-ZAU-T-031 | 2024-01-12 | [7 empty] | 2024-02-06 |  |  | 2024-03-14 | 6.38 | 271 | 413 | Virgil Frinculescu |  |  | New Isometric | No change |  | 0 | SEP | SEP |  | 0
42044 | WAI-7-201-024-50-SD | 2 | true |  | 50 | 5K | UG | H3 | PEL-ZAU-T-031 | 2024-01-12 | [7 empty] | 2024-02-06 |  |  | 2024-03-19 | 6.6 | 271 | 413 | Virgil Frinculescu |  |  | old name WAI-7-201-024-40-SD | New routing of ISO |  | 0 | SEP | SEP |  | 0
42045 | WAI-7-201-024-50-SD | 2 | true |  | 50 | 5K | UG | H3 | PEL-ZAU-T-031 | 2024-01-12 | [7 empty] | 2024-02-06 |  |  | 2024-03-19 | 9.9 | 271 | 413 | Virgil Frinculescu |  |  | old name WAI-7-201-024-40-SD | New routing of ISO |  | 0 | SEP | SEP |  | 0
42067 | WAI-7-201-071-32-SD | 1 | true |  | 32 | 5K | UG | H3 | PEL-ZAU-T-031 | 2024-01-12 | [7 empty] | 2024-02-06 |  |  | 2024-03-21 | 0.5 | 271 | 413 | Virgil Frinculescu |  |  | New Isometric | No change |  | 0 | SEP | SEP |  | 0
42068 | WAI-7-201-072-40-SD | 1 | false |  | 40 | 5K | UG | H3 | PEL-ZAU-T-031 | 2024-01-12 | [7 empty] | 2024-02-06 |  |  |  | 8.3 | 271 | 413 | Attila Henter |  |  | New Isometric | No change |  | 0 | SEP | SEP |  | 0
47424 | WAI-7-201-072-40-SD | 2 | true |  | 40 | 5K | UG | H3 | T-062 | 2024-03-21 | [7 empty] | 2024-02-06 |  |  | 2024-04-04 | 8.1 | 271 | 413 | Virgil Frinculescu |  |  | New Isometric | No change |  | 0 | SEP | SEP
42069 | WAI-7-201-073-40-SD | 1 | true |  | 40 | 5K | UG | H3 | PEL-ZAU-T-031 | 2024-01-12 | [7 empty] | 2024-02-06 |  |  | 2024-03-21 | 2.6 | 271 | 413 | Virgil Frinculescu |  |  | New Isometric | No change |  | 0 | SEP | SEP |  | 0
42070 | WAI-7-201-074-40-SD | 1 | true |  | 40 | 5K | UG | H3 | PEL-ZAU-T-031 | 2024-01-12 | [7 empty] | 2024-02-06 |  |  | 2024-03-21 | 2 | 271 | 413 | Virgil Frinculescu |  |  | New Isometric | No change |  | 0 | SEP | SEP |  | 0
42071 | WAI-7-201-083-150-SD | 3 | true |  | 150 | 5K | Riser | H3 | PEL-ZAU-T-031 | 2024-01-12 | 2024-02-05 | [6 empty] | 2024-05-24 |  |  | 2024-06-18 | 5.8 | 271 | 413 | Virgil Frinculescu |  |  | old name WAI-7-201-003-150-SD | No change |  | 0 | SEP | SEP |  | 1
42072 | WAI-7-201-084-150-SD | 1 | true |  | 150 | 5K | Riser | H3 | PEL-ZAU-T-031 | 2024-01-12 | 2024-01-25 | 2024-01-25 | 2024-01-31 |  | 2024-02-05 | 2024-02-16 |  | 2024-01-29 |  |  | 2024-04-17 | 1.6 | 271 | 413 | Virgil Frinculescu |  |  | New Isometric | No change |  | 0 | SEP | SEP |  | 1
42096 | WAA-7-931-006-65-SD | 2 | true |  | 65 | 5K | EG | H3 | PEL-ZAU-T-038 | 2024-01-15 |  | 2023-10-22 | 2023-10-31 | 2023-11-06 | 2023-11-06 | 2023-11-21 |  | 2023-11-26 |  | 2024-01-09 | 2024-02-20 | 5.8 | 271 | 411 | Virgil Frinculescu |  |  | Old ISO WAA-7-931-006-40-SD | Extra Stub In & Reducer |  | 0 | SEP | SEP |  | 1
42114 | WAA-7-931-075-40-SD | 1 | true |  | 40 | 5K | EG | H3 | PEL-ZAU-T-038 | 2024-01-15 | 2024-01-25 | 2024-01-25 | 2024-01-31 |  | 2024-02-05 | 2024-02-16 |  | 2024-02-21 |  |  | 2024-02-28 | 0.6 | 271 | 411 | Virgil Frinculescu |  |  |  | Line completly NEW for ZRO to prefab |  | 0 | SEP | SEP |  | 1
42484 | EtOHP-6-701-004-25-SP | 2 | true |  | 25 | 5K | EG | N/A | PEL-ZAU-T-041 | 2024-01-18 | 2024-01-22 | 2024-01-22 | 2024-01-31 | 2024-02-08 | 2024-02-08 | 2024-02-16 |  | 2024-05-28 |  |  | 2024-06-20 | 1.3 | 262 | 384 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP
42479 | EtOHP-6-701-002-25-SP | 2 | true |  | 25 | 5K | EG | N/A | PEL-ZAU-T-041 | 2024-01-18 | 2024-01-22 | 2024-01-22 | 2024-02-03 | 2024-02-08 | 2024-02-08 | 2024-02-16 |  | 2024-03-22 |  |  | 2024-04-03 | 4.4 | 262 | 384 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP
42480 | EtOHP-6-701-002-25-SP | 2 | true |  | 25 | 5K | EG | N/A | PEL-ZAU-T-041 | 2024-01-18 | 2024-01-22 | 2024-01-22 | 2024-02-03 | 2024-02-08 | 2024-02-08 | 2024-02-16 |  | 2024-03-22 |  |  | 2024-04-03 | 7 | 262 | 384 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP
42485 | EtOHP-6-701-005-20-SP | 2 | true |  | 20 | 5K | EG | N/A | PEL-ZAU-T-041 | 2024-01-18 | 2024-01-22 | 2024-01-22 | 2024-01-29 |  | 2024-02-12 | 2024-02-16 |  | 2024-05-28 |  |  | 2024-06-07 | 4.5 | 262 | 384 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP
42486 | EtOHP-6-701-005-20-SP | 2 | true |  | 20 | 5K | EG | N/A | PEL-ZAU-T-041 | 2024-01-18 | 2024-01-22 | 2024-01-22 | 2024-01-29 |  | 2024-02-12 | 2024-02-16 |  | 2024-05-28 |  |  | 2024-06-07 | 2.8 | 262 | 384 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP
42487 | EtOHP-6-701-006-20-SP | 2 | true |  | 20 | 5K | EG | N/A | PEL-ZAU-T-041 | 2024-01-18 | 2024-01-22 | 2024-01-22 | 2024-01-29 | 2024-02-08 | 2024-02-08 | 2024-02-16 |  | 2024-05-28 |  |  | 2024-06-06 | 2.6 | 262 | 384 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP
42488 | EtOHP-6-701-007-25-SP | 2 | true |  | 25 | 5K | OG1 | N/A | PEL-ZAU-T-041 | 2024-01-18 | 2024-01-22 | 2024-01-22 | 2024-01-31 |  | 2024-02-12 | 2024-02-16 |  | 2024-05-10 | 2024-05-25 |  | 2024-06-26 | 4 | 262 | 384 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP
42489 | EtOHP-6-701-007-25-SP | 2 | true |  | 25 | 5K | OG1 | N/A | PEL-ZAU-T-041 | 2024-01-18 | 2024-01-22 | 2024-01-22 | 2024-01-31 | 2024-02-08 | 2024-02-08 | 2024-02-16 |  | 2024-05-10 |  |  | 2024-05-25 | 21.1 | 262 | 384 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP
42472 | NaOHP-6-601-008-20-SP | 2 | true |  | 20 | 5K | EG | N/A | PEL-ZAU-T-041 | 2024-01-18 | 2024-01-22 | 2024-01-22 | 2024-01-29 | 2024-01-31 | 2024-01-31 | 2024-02-02 |  | 2024-04-18 |  |  | 2024-06-25 | 1.9 | 262 | 398 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP
42473 | NaOHP-6-601-008-20-SP | 2 | true |  | 20 | 5K | EG | N/A | PEL-ZAU-T-041 | 2024-01-18 | 2024-01-22 | 2024-01-22 | 2024-01-29 |  | 2024-02-12 | 2024-02-16 |  | 2024-04-18 |  |  | 2024-06-25 | 2.8 | 262 | 398 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP
42474 | NaOHP-6-601-009-20-SP | 2 | true |  | 20 | 5K | EG | N/A | PEL-ZAU-T-041 | 2024-01-18 | 2024-01-22 | 2024-01-22 | 2024-01-29 |  | 2024-02-02 | 2024-02-02 |  | 2024-04-18 |  |  | 2024-06-27 | 4.8 | 262 | 398 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP
42475 | NaOHP-6-601-010-20-SP | 2 | true |  | 20 | 5K | EG | N/A | PEL-ZAU-T-041 | 2024-01-18 | 2024-01-22 | 2024-01-22 | 2024-01-29 |  | 2024-02-12 | 2024-02-16 |  | 2024-04-18 |  |  | 2024-06-25 | 10.9 | 262 | 398 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP
42476 | NaOHP-6-601-011-25-SP | 2 | true |  | 25 | 5K | EG | N/A | PEL-ZAU-T-041 | 2024-01-18 | 2024-01-22 | 2024-01-22 | 2024-02-03 | 2024-02-08 | 2024-02-08 | 2024-02-16 |  | 2024-04-18 |  |  | 2024-06-25 | 6.8 | 262 | 398 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP
42477 | NaOHP-6-601-012-25-SP | 2 | true |  | 25 | 5K | EG | N/A | PEL-ZAU-T-041 | 2024-01-18 | 2024-01-22 | 2024-01-22 | 2024-02-03 | 2024-02-08 | 2024-02-08 | 2024-02-16 |  | 2024-04-18 |  |  | 2024-06-19 | 2.7 | 262 | 398 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP
42478 | WAI-7-201-059-25-SD1 | 2 | true |  | 25 | 5K | EG | N/A | PEL-ZAU-T-041 | 2024-01-18 | 2024-01-22 | 2024-01-22 | 2024-02-03 |  | 2024-02-12 | 2024-02-16 |  | 2024-06-18 |  |  | 2024-06-20 | 0.6 | 262 | 413 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP
42481 | EtOHP-6-701-003-25-SP | 2 | true |  | 25 | 5K | EG | N/A | PEL-ZAU-T-041 | 2024-01-18 | 2024-01-22 | 2024-01-22 | 2024-01-31 | 2024-02-08 | 2024-02-08 | 2024-02-16 |  | 2024-05-28 |  |  | 2024-06-10 | 3.2 | 262 | 384 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP
42482 | EtOHP-6-701-003-25-SP | 2 | true |  | 25 | 5K | EG | N/A | PEL-ZAU-T-041 | 2024-01-18 | 2024-01-22 | 2024-01-22 | 2024-01-31 |  | 2024-02-12 | 2024-02-16 |  | 2024-05-28 |  |  | 2024-06-06 | 5.1 | 262 | 384 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP
42483 | EtOHP-6-701-003-25-SP | 2 | true |  | 25 | 5K | EG | N/A | PEL-ZAU-T-041 | 2024-01-18 | 2024-01-22 | 2024-01-22 | 2024-01-31 | 2024-02-08 | 2024-02-08 | 2024-02-16 |  | 2024-05-28 |  |  | 2024-06-06 | 1.3 | 262 | 384 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP
42466 | NaOHP-6-601-002-25-SP | 2 | true |  | 25 | 5K | EG | N/A | PEL-ZAU-T-041 | 2024-01-18 | 2024-02-05 | 2024-02-05 | 2024-02-03 |  | 2024-02-12 | 2024-02-16 |  | 2024-04-18 |  |  | 2024-06-25 | 0.6 | 262 | 398 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP
42467 | NaOHP-6-601-004-25-SP | 2 | true |  | 25 | 5K | EG | N/A | PEL-ZAU-T-041 | 2024-01-18 | 2024-01-22 | 2024-01-22 | 2024-02-03 | 2024-02-08 | 2024-02-08 | 2024-02-16 |  | 2024-04-18 |  |  | 2024-06-28 | 4.1 | 262 | 398 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP
42468 | NaOHP-6-601-005-20-SP | 2 | true |  | 20 | 5K | EG | N/A | PEL-ZAU-T-041 | 2024-01-18 | 2024-01-22 | 2024-01-22 | 2024-01-29 | 2024-01-31 | 2024-01-31 | 2024-02-02 |  | 2024-04-18 |  |  | 2024-06-28 | 1.7 | 262 | 398 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP
42469 | NaOHP-6-601-006-20-SP | 2 | true |  | 20 | 5K | EG | N/A | PEL-ZAU-T-041 | 2024-01-18 | 2024-01-22 | 2024-01-22 | 2024-01-29 | 2024-01-31 | 2024-01-31 | 2024-02-02 |  | 2024-04-18 |  |  | 2024-06-28 | 4.4 | 262 | 398 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP
42470 | NaOHP-6-601-007-20-SP | 2 | true |  | 20 | 5K | EG | N/A | PEL-ZAU-T-041 | 2024-01-18 | 2024-01-22 | 2024-01-22 | 2024-01-29 |  | 2024-02-12 | 2024-02-16 |  | 2024-04-18 |  |  | 2024-06-28 | 4 | 262 | 398 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP
42471 | NaOHP-6-601-007-20-SP | 2 | true |  | 20 | 5K | EG | N/A | PEL-ZAU-T-041 | 2024-01-18 | 2024-01-22 | 2024-01-22 | 2024-01-29 | 2024-01-31 | 2024-01-31 | 2024-02-02 |  | 2024-04-18 |  |  | 2024-06-28 | 4.1 | 262 | 398 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP
42490 | TIE-IN-EtOHP-40-SP | 2 | true |  | 40 | 5K | OG1 | N/A | PEL-ZAU-T-041 | 2024-01-18 | 2024-02-05 | [9 empty] | 2024-06-26 | 0.1 | 262 | 384 | Virgil Frinculescu | 126 |  |  | It will be welded at the site. |  | 0 | SEP | SEP
42491 | WA-EtOH-7-500-003-15-SD | 2 | true |  | 15 | 5K | EG | N/A | PEL-ZAU-T-041 | 2024-01-18 | 2024-01-22 | 2024-01-22 | 2024-02-03 |  | 2024-02-12 | 2024-02-16 |  | 2024-06-06 |  |  | 2024-06-10 | 2.7 | 271 | 412 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP
42517 | WFIA-7-105-001-40-SP1 | 2 | true |  | 40 | 5K | UG | H3 | PEL-ZAU-T-042 | 2024-01-18 | 2024-01-25 | 2024-01-25 | 2024-02-01 | 2024-02-08 | 2024-02-08 | 2024-02-16 |  | 2024-02-29 |  |  | 2024-03-07 | 17.4 | 264 | 416 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP
42518 | WFIA-7-105-002-40-SP1 | 2 | true |  | 40 | 5K | OG1 | H3 | PEL-ZAU-T-042 | 2024-01-18 | 2024-01-25 | 2024-01-25 | 2024-02-01 |  | 2024-02-12 | 2024-02-16 |  | 2024-04-03 |  |  | 2024-04-10 | 6.6 | 264 | 416 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP
42519 | WFIA-7-105-002-40-SP1 | 2 | true |  | 40 | 5K | OG1 | H3 | PEL-ZAU-T-042 | 2024-01-18 | 2024-01-25 | 2024-01-25 | 2024-02-01 |  | 2024-02-12 | 2024-02-16 |  | 2024-04-03 |  |  | 2024-04-12 | 11.2 | 264 | 416 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP
42520 | WFIA-7-105-003-40-SP1 | 2 | true |  | 40 | 5K | OG1 | H3 | PEL-ZAU-T-042 | 2024-01-18 | 2024-01-25 | 2024-01-25 | 2024-02-01 |  | 2024-02-12 | 2024-02-16 |  | 2024-04-03 |  |  | 2024-04-10 | 4.9 | 264 | 416 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP
42521 | WFIA-7-105-003-40-SP1 | 2 | true |  | 40 | 5K | OG1 | H3 | PEL-ZAU-T-042 | 2024-01-18 | 2024-01-25 | 2024-01-25 | 2024-02-01 |  | 2024-02-12 | 2024-02-16 |  | 2024-04-03 |  |  | 2024-04-10 | 7.6 | 264 | 416 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP
42522 | WFIA-7-105-004-40-SP1 | 2 | true |  | 40 | 5K | OG1 | H3 | PEL-ZAU-T-042 | 2024-01-18 | 2024-01-25 | 2024-01-25 | 2024-02-01 | 2024-02-08 | 2024-02-08 | 2024-02-16 |  | 2024-04-03 |  |  | 2024-04-10 | 6.7 | 264 | 416 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP
42523 | WFIA-7-105-005-40-SP1 | 2 | true |  | 40 | 5K | EG | H3 | PEL-ZAU-T-042 | 2024-01-18 | 2024-01-25 | 2024-01-25 | 2024-02-01 |  | 2024-02-12 | 2024-02-16 |  | 2024-02-29 |  | 2024-03-20 | 2024-04-05 | 8.6 | 264 | 416 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP
42524 | WFIA-7-105-006-40-SP1 | 2 | true |  | 40 | 5K | EG | H3 | PEL-ZAU-T-042 | 2024-01-18 | 2024-01-25 | 2024-01-25 | 2024-02-01 |  | 2024-02-12 | 2024-02-16 |  | 2024-02-29 |  | 2024-03-20 | 2024-04-08 | 4.8 | 264 | 416 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP
42525 | WFIA-7-105-007-40-SP1 | 2 | true |  | 40 | 5K | EG | H3 | PEL-ZAU-T-042 | 2024-01-18 | 2024-01-25 | 2024-01-25 | 2024-02-02 |  | 2024-02-12 | 2024-02-16 |  | 2024-02-29 |  | 2024-03-20 | 2024-04-05 | 9.6 | 264 | 416 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP
42526 | WFIA-7-105-008-40-SP1 | 2 | true |  | 40 | 5K | EG | H3 | PEL-ZAU-T-042 | 2024-01-18 | 2024-01-25 | 2024-01-25 | 2024-02-02 |  | 2024-02-12 | 2024-02-16 |  | 2024-02-29 |  | 2024-03-20 | 2024-04-05 | 3.7 | 264 | 416 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP
42527 | WFIA-7-105-009-40-SP1 | 2 | true |  | 40 | 5K | EG | H3 | PEL-ZAU-T-042 | 2024-01-18 | 2024-01-25 | 2024-01-25 | 2024-02-02 |  | 2024-02-12 | 2024-02-16 |  | 2024-02-29 |  | 2024-03-20 | 2024-04-05 | 12.4 | 264 | 416 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP
42528 | WFIA-7-105-010-40-SP1 | 2 | true |  | 40 | 5K | EG | H3 | PEL-ZAU-T-042 | 2024-01-18 | 2024-01-25 | 2024-01-25 | 2024-02-02 |  | 2024-02-12 | 2024-02-16 |  | 2024-02-29 |  | 2024-03-20 | 2024-04-05 | 4.3 | 264 | 416 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP
42529 | WFIA-7-105-011-40-SP1 | 2 | true |  | 40 | 5K | EG | H3 | PEL-ZAU-T-042 | 2024-01-18 | 2024-01-25 | 2024-01-25 | 2024-02-02 |  | 2024-02-12 | 2024-02-16 |  | 2024-02-29 |  |  | 2024-03-07 | 12.2 | 264 | 416 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP
42530 | WFIA-7-811-730-32-SP1 | 2 | true |  | 32 | 5K | UG | H3 | PEL-ZAU-T-042 | 2024-01-18 | 2024-01-25 | 2024-01-25 | 2024-02-02 |  | 2024-02-12 | 2024-02-16 |  | 2024-02-29 |  |  | 2024-03-11 | 16.9 | 264 | 416 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP
42531 | CSL-7-201-026-15-SP | 2 | true |  | 15 | 5K | EG | H2 | PEL-ZAU-T-042 | 2024-01-18 | 2024-01-25 | 2024-01-25 | 2024-02-03 |  | 2024-02-12 | 2024-02-16 |  | 2024-04-08 |  |  | 2024-04-17 | 4.3 | 262 | 373 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP
42532 | CSL-7-201-027-15-SP | 2 | true |  | 15 | 5K | EG | H2 | PEL-ZAU-T-042 | 2024-01-18 | 2024-01-25 | 2024-01-25 | 2024-02-03 |  | 2024-02-12 | 2024-02-16 |  | 2024-04-08 |  |  | 2024-04-18 | 6.2 | 262 | 373 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP
42533 | CSL-7-201-028-15-SP | 2 | true |  | 15 | 5K | EG | H2 | PEL-ZAU-T-042 | 2024-01-18 | 2024-01-25 | 2024-01-25 | 2024-02-03 |  | 2024-02-12 | 2024-02-16 |  | 2024-04-08 |  |  | 2024-04-17 | 3.8 | 262 | 373 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP
42534 | CSL-7-201-029-15-SP | 2 | true |  | 15 | 5K | EG | H2 | PEL-ZAU-T-042 | 2024-01-18 | 2024-01-25 | 2024-01-25 | 2024-02-03 |  | 2024-02-12 | 2024-02-16 |  | 2024-04-08 |  |  | 2024-04-17 | 7.7 | 262 | 373 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP
42535 | CSL-7-201-030-15-SP | 2 | true |  | 15 | 5K | EG | H2 | PEL-ZAU-T-042 | 2024-01-18 | 2024-01-25 | 2024-01-25 | 2024-02-03 |  | 2024-02-12 | 2024-02-16 |  | 2024-04-08 |  |  | 2024-04-12 | 7.7 | 262 | 373 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP
42536 | CSL-7-201-031-15-SP | 2 | true |  | 15 | 5K | EG | H2 | PEL-ZAU-T-042 | 2024-01-18 | 2024-01-25 | 2024-01-25 | 2024-02-03 |  | 2024-02-12 | 2024-02-16 |  | 2024-04-08 |  |  | 2024-04-12 | 4.7 | 262 | 373 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP
42537 | CSL-7-201-033-40-SP1 | 2 | true |  | 40 | 5K | EG | H2 | PEL-ZAU-T-042 | 2024-01-18 | 2024-01-25 | 2024-01-25 | 2024-02-03 |  | 2024-02-12 | 2024-02-16 |  | 2024-04-08 |  |  | 2024-04-17 | 6.7 | 264 | 373 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP
42538 | CSL-7-201-040-40-SP1 | 2 | true |  | 40 | 5K | EG | H2 | PEL-ZAU-T-042 | 2024-01-18 | 2024-01-25 | 2024-01-25 | 2024-02-03 |  | 2024-02-12 | 2024-02-16 |  | 2024-04-08 |  |  | 2024-04-17 | 6.7 | 264 | 373 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP
42539 | CSL-7-201-005-40-SP1 | 2 | true |  | 40 | 5K | EG | H2 | PEL-ZAU-T-042 | 2024-01-18 | 2024-01-25 | 2024-01-25 | 2024-02-03 | 2024-02-08 | 2024-02-08 | 2024-02-16 |  | 2024-04-08 |  |  | 2024-04-25 | 1.5 | 264 | 373 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP
42540 | CSL-7-201-005-40-SP1 | 2 | true |  | 40 | 5K | EG | H2 | PEL-ZAU-T-042 | 2024-01-18 | 2024-01-25 | 2024-01-25 | 2024-02-03 | 2024-02-08 | 2024-02-08 | 2024-02-16 |  | 2024-04-08 |  |  | 2024-04-25 | 0.6 | 264 | 373 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP
42541 | CSL-7-201-005-40-SP1 | 2 | true |  | 40 | 5K | EG | H2 | PEL-ZAU-T-042 | 2024-01-18 | 2024-01-25 | 2024-01-25 | 2024-02-03 | 2024-02-08 | 2024-02-08 | 2024-02-16 |  | 2024-04-08 |  |  | 2024-04-25 | 0.1 | 264 | 373 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP
42542 | KR-0-216-051-25-SD | 2 | true |  | 25 | 5K | EG | N/A | PEL-ZAU-T-042 | 2024-01-18 | 2024-01-25 | 2024-01-25 | 2024-01-30 |  | 2024-02-05 | 2024-02-16 |  | 2024-04-17 |  |  | 2024-04-23 | 1.7 | 271 | 393 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP
42543 | KV-0-216-049-20-SD5 | 2 | true |  | 20 | 5K | EG | C2 | PEL-ZAU-T-042 | 2024-01-18 | 2024-01-25 | 2024-01-25 | 2024-01-30 |  | 2024-02-05 | 2024-02-16 |  | 2024-04-17 |  |  | 2024-07-17 | 0.6 | 260 | 394 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP
42544 | CSL-7-201-015-25-SP1 | 2 | true |  | 25 | 5K | EG | H2 | PEL-ZAU-T-042 | 2024-01-18 | 2024-01-25 | 2024-01-25 | 2024-02-03 | 2024-02-08 | 2024-02-08 | 2024-02-16 |  | 2024-04-08 |  |  | 2024-06-28 | 0.2 | 264 | 373 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP
42545 | CSL-7-201-016-15-SP1 | 2 | true |  | 15 | 5K | EG | H3 | PEL-ZAU-T-042 | 2024-01-18 | 2024-01-25 | 2024-01-25 | 2024-02-03 | 2024-02-08 | 2024-02-08 | 2024-02-16 |  | 2024-04-08 |  |  | 2024-07-19 | 0.2 | 264 | 373 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP
42546 | DKS-7-401-024-15-SD | 2 | true |  | 15 | 5K | EG | H3 | PEL-ZAU-T-042 | 2024-01-18 | 2024-01-25 | 2024-01-25 | 2024-01-29 |  | 2024-02-05 | 2024-02-16 |  | 2024-04-16 |  |  | 2024-04-23 | 1.1 | 271 | 378 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP
42547 | KR-0-216-050-20-SD5 | 2 | true |  | 20 | 5K | EG | N/A | PEL-ZAU-T-042 | 2024-01-18 | 2024-01-25 | 2024-01-25 | 2024-01-29 |  | 2024-02-05 | 2024-02-16 |  | 2024-04-17 |  |  | 2024-04-23 | 0.5 | 260 | 393 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP
42548 | WAI-7-201-067-25-SD | 2 | true |  | 25 | 5K | EG | N/A | PEL-ZAU-T-042 | 2024-01-18 | 2024-01-25 | 2024-01-25 | 2024-01-30 |  | 2024-02-05 | 2024-02-16 |  | 2024-04-05 |  |  | 2024-06-18 | 0.6 | 271 | 413 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP
42549 | WAI-7-201-068-25-SD | 2 | true |  | 25 | 5K | EG | N/A | PEL-ZAU-T-042 | 2024-01-18 | 2024-01-25 | 2024-01-25 | 2024-01-29 |  | 2024-02-05 | 2024-02-16 |  | 2024-04-05 |  |  | 2024-06-18 | 0.6 | 271 | 413 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP
42550 | CSL-7-201-011-15-SP1 | 2 | true |  | 15 | 5K | EG | H3 | PEL-ZAU-T-042 | 2024-01-18 | 2024-01-25 | 2024-01-25 | 2024-02-03 |  | 2024-02-12 | 2024-02-16 |  | 2024-04-08 |  |  | 2024-07-19 | 0.2 | 264 | 373 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP
42551 | CSL-7-201-012-40-SP1 | 2 | true |  | 40 | 5K | EG | H2 | PEL-ZAU-T-042 | 2024-01-18 | 2024-01-25 | 2024-01-25 | 2024-02-03 | 2024-02-08 | 2024-02-08 | 2024-02-16 |  | 2024-04-08 |  |  | 2024-04-24 | 1.5 | 264 | 373 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP
42552 | CSL-7-201-012-40-SP1 | 2 | true |  | 40 | 5K | EG | H2 | PEL-ZAU-T-042 | 2024-01-18 | 2024-01-25 | 2024-01-25 | 2024-02-03 | 2024-02-08 | 2024-02-08 | 2024-02-16 |  | 2024-04-08 |  |  | 2024-04-24 | 0.6 | 264 | 373 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP
42553 | CSL-7-201-012-40-SP1 | 2 | true |  | 40 | 5K | EG | H2 | PEL-ZAU-T-042 | 2024-01-18 | 2024-01-25 | 2024-01-25 | 2024-02-03 |  | 2024-02-12 | 2024-02-16 |  | 2024-04-08 |  | 2024-05-01 | 2024-07-15 | 0.1 | 264 | 373 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP
42554 | DKS-7-401-025-15-SD | 2 | true |  | 15 | 5K | EG | H3 | PEL-ZAU-T-042 | 2024-01-18 | 2024-01-25 | 2024-01-25 | 2024-01-29 |  | 2024-02-05 | 2024-02-16 |  | 2024-04-16 |  |  | 2024-04-23 | 1 | 271 | 378 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP
42555 | KR-0-216-053-20-SD5 | 2 | true |  | 20 | 5K | EG | N/A | PEL-ZAU-T-042 | 2024-01-18 | 2024-01-25 | 2024-01-25 | 2024-01-29 |  | 2024-02-05 | 2024-02-16 |  | 2024-04-17 |  |  | 2024-04-23 | 0.5 | 260 | 393 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP
42556 | KR-0-216-054-25-SD | 2 | true |  | 25 | 5K | EG | N/A | PEL-ZAU-T-042 | 2024-01-18 | 2024-01-25 | 2024-01-25 | 2024-01-30 |  | 2024-02-05 | 2024-02-16 |  | 2024-04-17 |  |  | 2024-04-23 | 1.7 | 271 | 393 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP
42557 | KV-0-216-052-SD5 | 2 | true |  | 52 | 5K | EG | C2 | PEL-ZAU-T-042 | 2024-01-18 | 2024-01-25 | 2024-01-25 | 2024-01-29 |  | 2024-02-05 | 2024-02-16 |  | 2024-04-17 |  |  | 2024-07-17 | 0.6 | 260 | 394 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP
42558 | WAI_SAMPLE_SP-2107 | 2 | true |  | 15 | 5K | OG1 | N/A | PEL-ZAU-T-042 | 2024-01-18 | 2024-01-25 | 2024-01-25 | 2024-02-02 |  | 2024-02-12 | 2024-02-16 |  | 2024-06-18 |  |  | 2024-06-19 | 0.4 | 271 | 413 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP
42559 | CSL-7-201-013-50-SP1 | 2 | true |  | 50 | 5K | OG1 | H2 | PEL-ZAU-T-042 | 2024-01-18 | 2024-01-25 | 2024-01-25 | 2024-02-03 |  | 2024-02-12 | 2024-02-16 |  | 2024-04-02 |  |  | 2024-04-11 | 3.1 | 264 | 373 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP
42560 | CSL-7-201-013-50-SP1 | 2 | true |  | 50 | 5K | OG1 | H2 | PEL-ZAU-T-042 | 2024-01-18 | 2024-01-25 | 2024-01-25 | 2024-02-03 |  | 2024-02-12 | 2024-02-16 |  | 2024-04-02 |  |  | 2024-04-11 | 0.5 | 264 | 373 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP
42561 | CSL-7-201-013-50-SP1 | 2 | true |  | 50 | 5K | OG1 | H2 | PEL-ZAU-T-042 | 2024-01-18 | 2024-01-25 | 2024-01-25 | 2024-02-03 | 2024-02-08 | 2024-02-08 | 2024-02-16 |  | 2024-04-02 |  |  | 2024-04-11 | 0.3 | 264 | 373 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP
42562 | CSL-7-201-017-25-SP1 | 2 | true |  | 25 | 5K | OG1 | H2 | PEL-ZAU-T-042 | 2024-01-18 | 2024-01-25 | 2024-01-25 | 2024-02-03 | 2024-02-08 | 2024-02-08 | 2024-02-16 |  | 2024-04-02 |  |  | 2024-06-28 | 0.2 | 264 | 373 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP
42563 | CSL-7-201-018-15-SP1 | 2 | true |  | 15 | 5K | OG1 | H3 | PEL-ZAU-T-042 | 2024-01-18 | 2024-01-25 | 2024-01-25 | 2024-02-03 | 2024-02-08 | 2024-02-08 | 2024-02-16 |  | 2024-06-28 |  |  | 2024-07-19 | 0.2 | 264 | 373 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP
42564 | DKS-7-401-023-15-SD | 2 | true |  | 15 | 5K | OG1 | H3 | PEL-ZAU-T-042 | 2024-01-18 | 2024-01-25 | 2024-01-25 | 2024-01-31 |  | 2024-02-05 | 2024-02-16 |  | 2024-04-16 |  |  | 2024-04-18 | 1.6 | 271 | 378 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP
42565 | DKS-7-401-023-15-SD | 2 | true |  | 15 | 5K | OG1 | H3 | PEL-ZAU-T-042 | 2024-01-18 | 2024-01-25 | 2024-01-25 | 2024-01-29 |  | 2024-02-05 | 2024-02-16 |  | 2024-04-16 |  |  | 2024-04-18 | 0.3 | 271 | 378 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP
42566 | KR-0-216-047-20-SD5 | 2 | true |  | 20 | 5K | OG1 | N/A | PEL-ZAU-T-042 | 2024-01-18 | 2024-01-25 | 2024-01-25 | 2024-01-30 |  | 2024-02-05 | 2024-02-16 |  | 2024-04-17 |  |  | 2024-04-18 | 0.5 | 260 | 393 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP
42567 | KR-0-216-048-25-SD | 2 | true |  | 25 | 5K | OG1 | N/A | PEL-ZAU-T-042 | 2024-01-18 | 2024-01-25 | 2024-01-25 | 2024-01-30 |  | 2024-02-05 | 2024-02-16 |  | 2024-04-17 |  |  | 2024-04-18 | 1.7 | 271 | 393 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP
42568 | KV-0-216-046-20-SD5 | 2 | true |  | 20 | 5K | OG1 | C2 | PEL-ZAU-T-042 | 2024-01-18 | 2024-01-25 | 2024-01-25 | 2024-01-30 |  | 2024-02-05 | 2024-02-16 |  | 2024-04-17 |  |  | 2024-07-17 | 0.7 | 260 | 394 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP
42569 | CSL-7-201-009-25-SP1 | 2 | true |  | 25 | 5K | EG | H2 | PEL-ZAU-T-042 | 2024-01-18 | 2024-01-25 | 2024-01-25 | 2024-02-03 | 2024-02-08 | 2024-02-08 | 2024-02-16 |  | 2024-04-08 |  |  | 2024-06-28 | 0.2 | 264 | 373 | Virgil Frinculescu | 126 |  |  |  |  | 0 | SEP | SEP
43466 | ABP-7-701-026-80-SD | 3 | true |  | 0 |  |  |  | T-055 | 2024-02-16 | [7 empty] | 2024-05-24 |  |  | 2024-06-18 | 5.8 | 271 |  | Virgil Frinculescu | [5 empty] | 0
43467 | ABP-7-701-027-80-SD | 3 | true |  | 0 |  |  |  | T-055 | 2024-02-16 | [7 empty] | 2024-05-24 |  |  | 2024-06-18 | 5.8 | 271 |  | Virgil Frinculescu | [5 empty] | 0
43983 | KR-0-216-004-80-SD5 | 3 | true |  | 0 |  |  | =0 | T-051 | 2024-02-01 | 2024-02-05 | 2024-02-05 | 2024-02-06 |  | 2024-02-12 | 2024-02-16 |  | 2024-02-26 |  | 2024-03-12 | 2024-05-21 | 21.7 | 260 |  | Virgil Frinculescu |  |  |  | Diameter changed from DN65 to DN80 |  | 0 | SEP | SEP
43984 | KR-0-216-004-80-SD5 | 3 | true |  | 0 |  |  | =0 | T-051 | 2024-02-01 | 2024-02-05 | 2024-02-05 | 2024-02-06 |  | 2024-02-12 | 2024-02-16 |  | 2024-02-26 | 2024-03-12 |  | 2024-05-21 | 1.2 | 260 |  | Virgil Frinculescu |  |  |  | Diameter changed from DN65 to DN80 |  | 0 | SEP | SEP
43997 | KV-0-216-005-80-SD5 | 3 | true |  | 0 |  |  | =0 | T-051 | 2024-02-01 | 2024-02-05 | 2024-02-05 | 2024-02-06 |  | 2024-02-12 | 2024-02-16 |  | 2024-02-26 | 2024-03-12 |  | 2024-05-21 | 1.2 | 260 |  | Virgil Frinculescu |  |  |  | Diameter changed from DN65 to DN80 |  | 0 | SEP | SEP
43998 | KV-0-216-005-80-SD5 | 3 | true |  | 0 |  |  | =0 | T-051 | 2024-02-01 | 2024-02-05 | 2024-02-05 | 2024-02-06 |  | 2024-02-12 | 2024-02-16 |  | 2024-02-26 |  | 2024-03-12 | 2024-05-21 | 21 | 260 |  | Virgil Frinculescu |  |  |  | Diameter changed from DN65 to DN80 |  | 0 | SEP | SEP
44372 | HR-NT-0-L600-010-40-CA | 2 | true | L600 | 0 | 5K | OG3 | H1 | T-052 | 2024-02-12 | [7 empty] | 2024-03-12 |  |  | 2024-04-10 | 1.1 | 249 | 389 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
44373 | HR-NT-0-L600-010-40-CA | 2 | true | L600 | 0 | 5K | OG3 | H1 | T-052 | 2024-02-12 | [7 empty] | 2024-03-12 |  |  | 2024-04-08 | 3.5 | 249 | 389 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
44374 | HR-NT-0-L601-011-40-CA | 2 | true | L601 | 0 | 5K | OG3 | H1 | T-052 | 2024-02-12 | [7 empty] | 2024-03-12 |  |  | 2024-04-10 | 0.8 | 249 | 389 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
44375 | HR-NT-0-L601-011-40-CA | 2 | true | L601 | 0 | 5K | OG3 | H1 | T-052 | 2024-02-12 | [7 empty] | 2024-03-12 |  |  | 2024-04-08 | 1.8 | 249 | 389 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
44376 | HR-NT-0-L602-008-40-CA | 2 | true | L602 | 0 | 5K | OG3 | H1 | T-052 | 2024-02-12 | [7 empty] | 2024-03-12 |  | 2024-04-30 | 2024-05-15 | 0.9 | 249 | 389 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
44377 | HR-NT-0-L602-008-40-CA | 2 | true | L602 | 0 | 5K | OG3 | H1 | T-052 | 2024-02-12 | [7 empty] | 2024-03-12 |  |  | 2024-04-12 | 3.2 | 249 | 389 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
44378 | HR-NT-0-L603-007-50-CA | 2 | true | L603 | 0 | 5K | OG3 | H1 | T-052 | 2024-02-12 | [7 empty] | 2024-03-12 |  | 2024-04-30 | 2024-07-18 | 1.2 | 249 | 389 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
44379 | HR-NT-0-L603-007-50-CA | 2 | true | L603 | 0 | 5K | OG3 | H1 | T-052 | 2024-02-12 | [7 empty] | 2024-03-12 |  | 2024-04-30 | 2024-06-29 | 3.2 | 249 | 389 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
44380 | HR-NT-0-L604-006-50-CA | 2 | true | L604 | 0 | 5K | OG3 | H1 | T-052 | 2024-02-12 | [7 empty] | 2024-03-12 |  |  | 2024-07-18 | 0.6 | 249 | 389 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
44381 | HR-NT-0-L604-006-50-CA | 2 | true | L604 | 0 | 5K | OG3 | H1 | T-052 | 2024-02-12 | [7 empty] | 2024-03-12 |  | 2024-04-30 | 2024-06-25 | 1.8 | 249 | 389 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
44382 | HR-NT-0-WRG-009-65-CA | 1 | true | WRG | 0 | 5K | OG3 | H1 | T-052 | 2024-02-12 | [7 empty] | 2024-03-12 |  | 2024-04-30 | 2024-06-24 | 2.9 | 249 | 389 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
44383 | HV-NT-0-L600-011-40-CA | 2 | true | L600 | 0 | 5K | OG3 | H1 | T-052 | 2024-02-12 | [7 empty] | 2024-03-12 |  |  | 2024-04-05 | 2 | 249 | 390 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
44384 | HV-NT-0-L600-011-40-CA | 2 | true | L600 | 0 | 5K | OG3 | H1 | T-052 | 2024-02-12 | [7 empty] | 2024-03-12 |  |  | 2024-04-05 | 2.7 | 249 | 390 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
44385 | HV-NT-0-L601-012-40-CA | 2 | true | L601 | 0 | 5K | OG3 | H1 | T-052 | 2024-02-12 | [7 empty] | 2024-03-12 |  |  | 2024-04-05 | 2.4 | 249 | 390 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
44386 | HV-NT-0-L601-012-40-CA | 2 | true | L601 | 0 | 5K | OG3 | H1 | T-052 | 2024-02-12 | [7 empty] | 2024-03-12 |  |  | 2024-04-05 | 1.2 | 249 | 390 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
44387 | HV-NT-0-L602-009-40-CA | 2 | true | L602 | 0 | 5K | OG3 | H1 | T-052 | 2024-02-12 | [7 empty] | 2024-03-12 |  | 2024-04-30 | 2024-07-16 | 2.5 | 249 | 390 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
44388 | HV-NT-0-L602-009-40-CA | 2 | true | L602 | 0 | 5K | OG3 | H1 | T-052 | 2024-02-12 | [7 empty] | 2024-03-12 |  |  | 2024-04-15 | 0.6 | 249 | 390 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
44389 | HV-NT-0-L603-008-50-CA | 2 | true | L603 | 0 | 5K | OG3 | H1 | T-052 | 2024-02-12 | [7 empty] | 2024-03-12 |  | 2024-04-30 | 2024-06-27 | 2.7 | 249 | 390 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
44390 | HV-NT-0-L603-008-50-CA | 2 | true | L603 | 0 | 5K | OG3 | H1 | T-052 | 2024-02-12 | [7 empty] | 2024-03-12 |  | 2024-04-30 | 2024-07-18 | 0.5 | 249 | 390 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
44391 | HV-NT-0-L604-007-50-CA | 2 | true | L604 | 0 | 5K | OG3 | H1 | T-052 | 2024-02-12 | [7 empty] | 2024-03-12 |  | 2024-04-30 | 2024-06-27 | 3 | 249 | 390 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
44392 | HV-NT-0-L604-007-50-CA | 2 | true | L604 | 0 | 5K | OG3 | H1 | T-052 | 2024-02-12 | [7 empty] | 2024-03-12 |  | 2024-04-30 | 2024-07-18 | 0.8 | 249 | 390 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
44393 | HV-NT-0-WRG-010-65-CA | 1 | true | WRG | 0 | 5K | OG3 | H1 | T-052 | 2024-02-12 | [7 empty] | 2024-03-12 |  | 2024-04-30 | 2024-06-24 | 2.3 | 249 | 390 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
44394 | KKR-0-L600-009-065-SD5 | 2 | true | L601 | 0 | 5K | OG3 | C2 | T-052 | 2024-02-12 | [7 empty] | 2024-04-11 |  | 2024-04-30 | 2024-07-22 | 1 | 260 | 391 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
44395 | KKR-0-L600-009-065-SD5 | 2 | true | L601 | 0 | 5K | OG3 | C2 | T-052 | 2024-02-12 | [7 empty] | 2024-04-11 |  | 2024-04-30 | 2024-06-25 | 3.3 | 260 | 391 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
44396 | KKR-0-L601-008-065-SD5 | 2 | true | L601 | 0 | 5K | OG3 | C2 | T-052 | 2024-02-12 | [7 empty] | 2024-04-11 |  | 2024-04-30 | 2024-07-22 | 2.9 | 260 | 391 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
44397 | KKV-0-L600-010-065-SD5 | 2 | true | L600 | 0 | 5K | OG3 | C2 | T-052 | 2024-02-12 | [7 empty] | 2024-04-11 |  | 2024-04-30 | 2024-07-22 | 4.7 | 260 | 392 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
44398 | KKV-0-L600-010-065-SD5 | 2 | true | L600 | 0 | 5K | OG3 | C2 | T-052 | 2024-02-12 | [7 empty] | 2024-04-11 |  |  | 2024-04-18 | 1.1 | 260 | 392 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
44399 | KKV-0-L601-009-065-SD5 | 2 | true | L601 | 0 | 5K | OG3 | C2 | T-052 | 2024-02-12 | [7 empty] | 2024-04-11 |  | 2024-04-30 | 2024-07-22 | 3.3 | 260 | 392 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
44400 | KKV-0-L601-009-065-SD5 | 2 | true | L601 | 0 | 5K | OG3 | C2 | T-052 | 2024-02-12 | [7 empty] | 2024-04-11 |  |  | 2024-04-17 | 0.9 | 260 | 392 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
44401 | KR-0-L600-026-40-SD5 | 2 | true | L600 | 0 | 5K | OG3 | C2 | T-052 | 2024-02-12 | [7 empty] | 2024-03-07 |  |  | 2024-04-23 | 0.9 | 260 | 393 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
44402 | KR-0-L600-026-40-SD5 | 2 | true | L600 | 0 | 5K | OG3 | C2 | T-052 | 2024-02-12 | [7 empty] | 2024-03-07 |  |  | 2024-04-18 | 2.6 | 260 | 393 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
44403 | KR-0-L601-025-40-SD5 | 2 | true | L601 | 0 | 5K | OG3 | C2 | T-052 | 2024-02-12 | [7 empty] | 2024-03-07 |  |  | 2024-04-23 | 1.8 | 260 | 393 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
44404 | KR-0-L602-029-40-SD5 | 2 | true | L602 | 0 | 5K | OG3 | C2 | T-052 | 2024-02-12 | [7 empty] | 2024-03-08 |  |  | 2024-05-01 | 0.9 | 260 | 393 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
44405 | KR-0-L602-029-40-SD5 | 2 | true | L602 | 0 | 5K | OG3 | C2 | T-052 | 2024-02-12 | [7 empty] | 2024-03-08 |  |  | 2024-05-08 | 2.4 | 260 | 393 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
44406 | KR-0-L603-028-65-SD5 | 2 | false | L603 | 0 | 5K | OG3 | C2 | T-052 | 2024-02-12 | [7 empty] | 2024-03-08 |  |  |  | 2.4 | 260 | 393 | Jozef Kotul | [5 empty] | 0 | SEP | SEP
44407 | KR-0-L603-028-65-SD5 | 2 | false | L603 | 0 | 5K | OG3 | C2 | T-052 | 2024-02-12 | [7 empty] | 2024-03-08 |  | 2024-03-23 |  | 4.8 | 260 | 393 | Jozef Kotul | [5 empty] | 0 | SEP | SEP
48440 | KR-0-L603-028-65-SD5 | 3 | true | L603 | 0 | 5K | OG3 | C2 | T-072 | 2024-04-09 | [7 empty] | 2024-04-15 |  |  | 2024-05-01 | 0.6 | 260 | 393 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48441 | KR-0-L603-028-65-SD5 | 3 | true | L603 | 0 | 5K | OG3 | C2 | T-072 | 2024-04-09 | [7 empty] | 2024-04-15 |  | 2024-03-23 | 2024-07-19 | 3.4 | 260 | 393 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
44408 | KR-0-L604-027-65-SD5 | 2 | false | L604 | 0 | 5K | OG3 | C2 | T-052 | 2024-02-12 | [7 empty] | 2024-03-05 |  |  | 2024-04-08 | 3.4 | 260 | 393 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
44409 | KR-0-L604-027-65-SD5 | 2 | false | L604 | 0 | 5K | OG3 | C2 | T-052 | 2024-02-12 | [7 empty] | 2024-03-05 | 2024-03-23 |  |  | 4.8 | 260 | 393 | Jozef Kotul | [5 empty] | 0 | SEP | SEP
48442 | KR-0-L604-027-65-SD5 | 3 | true | L604 | 0 | 5K | OG3 | C2 | T-072 | 2024-04-09 | [7 empty] | 2024-04-15 |  | 2024-04-12 | 2024-04-24 | 1 | 260 | 393 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48443 | KR-0-L604-027-65-SD5 | 3 | true | L604 | 0 | 5K | OG3 | C2 | T-072 | 2024-04-09 | [7 empty] | 2024-04-15 | 2024-03-23 | 2024-06-27 | 2024-07-18 | 1.8 | 260 | 393 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
44410 | KV-0-L600-027-40-SD5 | 2 | true | L600 | 0 | 5K | OG3 | C2 | T-052 | 2024-02-12 | [7 empty] | 2024-03-07 |  |  | 2024-03-21 | 2.1 | 260 | 394 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
44411 | KV-0-L600-027-40-SD5 | 2 | true | L600 | 0 | 5K | OG3 | C2 | T-052 | 2024-02-12 | [7 empty] | 2024-03-07 |  |  | 2024-04-24 | 2.4 | 260 | 394 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
44412 | KV-0-L601-026-40-SD5 | 2 | true | L601 | 0 | 5K | OG3 | C2 | T-052 | 2024-02-12 | [7 empty] | 2024-03-07 |  |  | 2024-03-21 | 2.4 | 260 | 394 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
44413 | KV-0-L601-026-40-SD5 | 2 | true | L601 | 0 | 5K | OG3 | C2 | T-052 | 2024-02-12 | [7 empty] | 2024-03-07 |  |  | 2024-04-18 | 0.9 | 260 | 394 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
44414 | KV-0-L602-030-40-SD5 | 2 | true | L602 | 0 | 5K | OG3 | C2 | T-052 | 2024-02-12 | [7 empty] | 2024-03-08 |  |  | 2024-04-03 | 1.6 | 260 | 394 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
44415 | KV-0-L602-030-40-SD5 | 2 | true | L602 | 0 | 5K | OG3 | C2 | T-052 | 2024-02-12 | [7 empty] | 2024-03-08 |  | 2024-05-01 | 2024-05-21 | 0.6 | 260 | 394 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
44416 | KV-0-L603-029-65-SD5 | 2 | false | L603 | 0 | 5K | OG3 | C2 | T-052 | 2024-02-12 | [7 empty] | 2024-03-08 |  |  |  | 5.6 | 260 | 394 | Jozef Kotul | [5 empty] | 0 | SEP | SEP
44417 | KV-0-L603-029-65-SD5 | 2 | false | L603 | 0 | 5K | OG3 | C2 | T-052 | 2024-02-12 | [7 empty] | 2024-03-08 |  |  |  | 2.6 | 260 | 394 | Jozef Kotul | [5 empty] | 0 | SEP | SEP
44418 | KV-0-L603-029-65-SD5 | 2 | false | L603 | 0 | 5K | OG3 | C2 | T-052 | 2024-02-12 | [7 empty] | 2024-03-08 |  |  | 2024-03-27 | 2.1 | 260 | 394 | Jozef Kotul | [5 empty] | 0 | SEP | SEP
48444 | KV-0-L603-029-65-SD5 | 3 | true | L603 | 0 | 5K | OG3 | C2 | T-072 | 2024-04-09 | [7 empty] | 2024-04-15 |  | 2024-05-01 | 2024-07-19 | 1.7 | 260 | 394 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48445 | KV-0-L603-029-65-SD5 | 3 | true | L603 | 0 | 5K | OG3 | C2 | T-072 | 2024-04-09 | [7 empty] | 2024-04-15 |  |  | 2024-05-29 | 1.1 | 260 | 394 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
44419 | KV-0-L604-028-65-SD5 | 2 | false | L604 | 0 | 5K | OG3 | C2 | T-052 | 2024-02-12 | [7 empty] | 2024-03-05 | 2024-03-23 |  |  | 5 | 260 | 394 | Jozef Kotul | [5 empty] | 0 | SEP | SEP
44420 | KV-0-L604-028-65-SD5 | 2 | false | L604 | 0 | 5K | OG3 | C2 | T-052 | 2024-02-12 | [7 empty] | 2024-03-05 |  |  | 2024-04-08 | 2.9 | 260 | 394 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48447 | KV-0-L604-028-65-SD5 | 3 | true | L604 | 0 | 5K | OG3 | C2 | T-072 | 2024-04-09 | [7 empty] | 2024-04-15 | 2024-03-23 | 2024-05-25 | 2024-07-18 | 3.3 | 260 | 394 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48448 | KV-0-L604-028-65-SD5 | 3 | true | L604 | 0 | 5K | OG3 | C2 | T-072 | 2024-04-09 | [7 empty] | 2024-04-15 |  | 2024-04-12 | 2024-04-24 | 0.9 | 260 | 394 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
44421 | WRGR-0-L600-002-40-SD5 | 1 | false | L600 | 0 | 5K | OG3 | H8 | T-052 | 2024-02-12 | [11 empty] | 2.5 | 260 | 1638 |  |  |  |  | HOLD |  | 0 | SEP | SEP
44422 | WRGR-0-L600-002-40-SD5 | 1 | false | L600 | 0 | 5K | OG3 | H8 | T-052 | 2024-02-12 | [11 empty] | 3.4 | 260 | 1638 |  |  |  |  | HOLD |  | 0 | SEP | SEP
45316 | WRGR-0-L600-002-40-SD5 | 2 | true | L600 | 0 | 5K | OG3 | H8 | T-060 | 2024-03-05 | [7 empty] | 2024-03-22 |  | 2024-05-01 | 2024-05-25 | 2.5 | 260 | 1638 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45317 | WRGR-0-L600-002-40-SD5 | 2 | true | L600 | 0 | 5K | OG3 | H8 | T-060 | 2024-03-05 | [7 empty] | 2024-03-22 |  | 2024-05-01 | 2024-05-25 | 3.4 | 260 | 1638 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
44423 | WRGR-0-L601-001-40-SD5 | 1 | false | L601 | 0 | 5K | OG3 | H8 | T-052 | 2024-02-12 | [11 empty] | 0.9 | 260 | 1638 |  |  |  |  | HOLD |  | 0 | SEP | SEP
44424 | WRGR-0-L601-001-40-SD5 | 1 | false | L601 | 0 | 5K | OG3 | H8 | T-052 | 2024-02-12 | [11 empty] | 2.3 | 260 | 1638 |  |  |  |  | HOLD |  | 0 | SEP | SEP
44425 | WRGR-0-L601-001-40-SD5 | 1 | false | L601 | 0 | 5K | OG3 | H8 | T-052 | 2024-02-12 | [11 empty] | 4.4 | 260 | 1638 |  |  |  |  | HOLD |  | 0 | SEP | SEP
45318 | WRGR-0-L601-001-40-SD5 | 2 | false | L601 | 0 | 5K | OG3 | H8 | T-060 | 2024-03-05 | [7 empty] | 2024-03-22 |  |  |  | 1.3 | 260 | 1638 | Jozef Kotul | [5 empty] | 0 | SEP | SEP
45319 | WRGR-0-L601-001-40-SD5 | 2 | false | L601 | 0 | 5K | OG3 | H8 | T-060 | 2024-03-05 | [7 empty] | 2024-03-22 |  |  | 2024-05-25 | 6.2 | 260 | 1638 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48416 | WRGR-0-L601-001-40-SD5 | 3 | true | L601 | 0 | 5K | OG3 | H8 | T-070 | 2024-04-08 | [7 empty] | 2024-04-17 |  | 2024-05-01 | 2024-05-25 | 1 | 260 | 1638 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48417 | WRGR-0-L601-001-40-SD5 | 3 | true | L601 | 0 | 5K | OG3 | H8 | T-070 | 2024-04-08 | [7 empty] | 2024-04-17 |  | 2024-05-01 | 2024-05-25 | 7 | 260 | 1638 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
44426 | WRGR-0-L606-003-65-SD5 | 1 | false | L606 | 0 | 5K | OG3 | H8 | T-052 | 2024-02-12 | [7 empty] | 2024-03-22 |  |  |  | 1.5 | 260 | 1638 | Jozef Kotul | [5 empty] | 0 | SEP | SEP
44427 | WRGR-0-L606-003-65-SD5 | 1 | false | L606 | 0 | 5K | OG3 | H8 | T-052 | 2024-02-12 | [7 empty] | 2024-03-22 |  |  |  | 4.5 | 260 | 1638 | Jozef Kotul | [5 empty] | 0 | SEP | SEP
44428 | WRGR-0-L606-003-65-SD5 | 1 | false | L606 | 0 | 5K | OG3 | H8 | T-052 | 2024-02-12 | [7 empty] | 2024-03-22 |  |  |  | 14.3 | 260 | 1638 | Jozef Kotul | [5 empty] | 0 | SEP | SEP
44429 | WRGR-0-L606-003-65-SD5 | 1 | false | L606 | 0 | 5K | OG3 | H8 | T-052 | 2024-02-12 | [7 empty] | 2024-03-22 |  |  |  | 20.5 | 260 | 1638 | Jozef Kotul | [5 empty] | 0 | SEP | SEP
48418 | WRGR-0-L606-003-65-SD5 | 2 | true | L606 | 0 | 5K | OG3 | H8 | T-070 | 2024-04-08 | [7 empty] | 2024-04-17 |  | 2024-05-01 | 2024-07-19 | 1 | 260 | 1638 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48419 | WRGR-0-L606-003-65-SD5 | 2 | true | L606 | 0 | 5K | OG3 | H8 | T-070 | 2024-04-08 | [7 empty] | 2024-04-17 |  | 2024-05-01 | 2024-05-24 | 3.9 | 260 | 1638 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48420 | WRGR-0-L606-003-65-SD5 | 2 | true | L606 | 0 | 5K | OG3 | H8 | T-070 | 2024-04-08 | [7 empty] | 2024-04-17 |  | 2024-05-25 | 2024-06-25 | 4.2 | 260 | 1638 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48421 | WRGR-0-L606-003-65-SD5 | 2 | true | L606 | 0 | 5K | OG3 | H8 | T-070 | 2024-04-08 | [7 empty] | 2024-04-17 |  |  | 2024-05-24 | 12 | 260 | 1638 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48422 | WRGR-0-L606-003-65-SD5 | 2 | true | L606 | 0 | 5K | OG3 | H8 | T-070 | 2024-04-08 | [7 empty] | 2024-04-17 |  |  | 2024-05-24 | 19.9 | 260 | 1638 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
44430 | WRGR-0-L607-004-50-SD5 | 1 | false | L607 | 0 | 5K | OG3 | H8 | T-052 | 2024-02-12 | [7 empty] | 2024-03-22 |  |  |  | 3.8 | 260 | 1638 | Jozef Kotul | [5 empty] | 0 | SEP | SEP
48423 | WRGR-0-L607-004-50-SD5 | 2 | true | L607 | 0 | 5K | OG3 | H8 | T-070 | 2024-04-08 | [7 empty] | 2024-04-17 |  | 2024-05-01 | 2024-07-19 | 1 | 260 | 1638 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48424 | WRGR-0-L607-004-50-SD5 | 2 | true | L607 | 0 | 5K | OG3 | H8 | T-070 | 2024-04-08 | [7 empty] | 2024-04-17 |  | 2024-05-01 | 2024-06-25 | 3.4 | 260 | 1638 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
44431 | WRGV-0-L600-003-50-SD5 | 1 | true | L600 | 0 | 5K | OG3 | H8 | T-052 | 2024-02-12 | [7 empty] | 2024-03-22 |  | 2024-05-01 | 2024-06-28 | 2.1 | 260 | 1637 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
44432 | WRGV-0-L600-003-50-SD5 | 1 | true | L600 | 0 | 5K | OG3 | H8 | T-052 | 2024-02-12 | [7 empty] | 2024-03-22 |  | 2024-05-01 | 2024-07-22 | 1.1 | 260 | 1637 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
44433 | WRGV-0-L600-004-40-SD5 | 1 | true | L600 | 0 | 5K | OG3 | H8 | T-052 | 2024-02-12 | [7 empty] | 2024-03-22 |  |  | 2024-04-17 | 2.7 | 260 | 1637 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
44434 | WRGV-0-L601-001-65-SD5 | 1 | false | L601 | 0 | 5K | OG3 | H8 | T-052 | 2024-02-12 | [7 empty] | 2024-03-22 |  |  |  | 8.9 | 260 | 1637 | Jozef Kotul | [5 empty] | 0 | SEP | SEP
44435 | WRGV-0-L601-001-65-SD5 | 1 | false | L601 | 0 | 5K | OG3 | H8 | T-052 | 2024-02-12 | [7 empty] | 2024-03-22 |  |  |  | 0.9 | 260 | 1637 | Jozef Kotul | [5 empty] | 0 | SEP | SEP
48425 | WRGV-0-L601-001-65-SD5 | 2 | true | L601 | 0 | 5K | OG3 | H8 | T-070 | 2024-04-08 | [7 empty] | 2024-04-17 |  | 2024-05-01 | 2024-06-28 | 8.8 | 260 | 1637 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48426 | WRGV-0-L601-001-65-SD5 | 2 | true | L601 | 0 | 5K | OG3 | H8 | T-070 | 2024-04-08 | [7 empty] | 2024-04-17 |  | 2024-05-01 | 2024-07-22 | 0.9 | 260 | 1637 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
44436 | WRGV-0-L601-002-40-SD5 | 1 | true | L601 | 0 | 5K | OG3 | H8 | T-052 | 2024-02-12 | [7 empty] | 2024-03-22 |  |  | 2024-04-17 | 2.7 | 260 | 1637 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
44437 | WRGV-0-L606-005-65-SD5 | 1 | false | L606 | 0 | 5K | OG3 | H8 | T-052 | 2024-02-12 | [7 empty] | 2024-03-22 |  |  |  | 18.5 | 260 | 1637 | Jozef Kotul | [5 empty] | 0 | SEP | SEP
44438 | WRGV-0-L606-005-65-SD5 | 1 | false | L606 | 0 | 5K | OG3 | H8 | T-052 | 2024-02-12 | [7 empty] | 2024-03-22 |  |  |  | 11.9 | 260 | 1637 | Jozef Kotul | [5 empty] | 0 | SEP | SEP
44439 | WRGV-0-L606-005-65-SD5 | 1 | false | L606 | 0 | 5K | OG3 | H8 | T-052 | 2024-02-12 | [7 empty] | 2024-03-22 |  |  |  | 4.2 | 260 | 1637 | Jozef Kotul | [5 empty] | 0 | SEP | SEP
44440 | WRGV-0-L606-005-65-SD5 | 1 | false | L606 | 0 | 5K | OG3 | H8 | T-052 | 2024-02-12 | [7 empty] | 2024-03-22 |  |  |  | 1.5 | 260 | 1637 | Jozef Kotul | [5 empty] | 0 | SEP | SEP
44441 | WRGV-0-L606-005-65-SD5 | 1 | false | L606 | 0 | 5K | OG3 | H8 | T-052 | 2024-02-12 | [7 empty] | 2024-03-22 |  |  |  | 2.2 | 260 | 1637 | Jozef Kotul | [5 empty] | 0 | SEP | SEP
48427 | WRGV-0-L606-005-65-SD5 | 2 | true | L606 | 0 | 5K | OG3 | H8 | T-070 | 2024-04-08 | [7 empty] | 2024-05-01 |  |  | 2024-05-24 | 16.5 | 260 | 1637 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48428 | WRGV-0-L606-005-65-SD5 | 2 | true | L606 | 0 | 5K | OG3 | H8 | T-070 | 2024-04-08 | [7 empty] | 2024-05-01 |  |  | 2024-05-24 | 13.5 | 260 | 1637 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48429 | WRGV-0-L606-005-65-SD5 | 2 | true | L606 | 0 | 5K | OG3 | H8 | T-070 | 2024-04-08 | [7 empty] | 2024-05-01 |  |  | 2024-05-24 | 3.6 | 260 | 1637 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48430 | WRGV-0-L606-005-65-SD5 | 2 | true | L606 | 0 | 5K | OG3 | H8 | T-070 | 2024-04-08 | [7 empty] | 2024-05-01 |  | 2024-05-25 | 2024-06-25 | 4.2 | 260 | 1637 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48431 | WRGV-0-L606-005-65-SD5 | 2 | true | L606 | 0 | 5K | OG3 | H8 | T-070 | 2024-04-08 | [7 empty] | 2024-05-01 |  | 2024-05-25 | 2024-07-19 | 0.8 | 260 | 1637 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
44442 | WRGV-0-L607-005-50-SD5 | 1 | false | L607 | 0 | 5K | OG3 | H8 | T-052 | 2024-02-12 | [7 empty] | 2024-03-22 |  |  |  | 1.6 | 260 | 1637 | Jozef Kotul | [5 empty] | 0 | SEP | SEP
44443 | WRGV-0-L607-005-50-SD5 | 1 | false | L607 | 0 | 5K | OG3 | H8 | T-052 | 2024-02-12 | [7 empty] | 2024-03-22 |  |  |  | 0.7 | 260 | 1637 | Jozef Kotul | [5 empty] | 0 | SEP | SEP
48432 | WRGV-0-L607-005-50-SD5 | 2 | true | L607 | 0 | 5K | OG3 | H8 | T-070 | 2024-04-08 | [7 empty] | 2024-05-01 |  | 2024-05-25 | 2024-06-26 | 0.6 | 260 | 1637 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48433 | WRGV-0-L607-005-50-SD5 | 2 | true | L607 | 0 | 5K | OG3 | H8 | T-070 | 2024-04-08 | [7 empty] | 2024-05-01 |  | 2024-05-25 | 2024-07-19 | 0.6 | 260 | 1637 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
44930 | WA_EtOH-7-500-004-50-SD | 1 | true | CH06822004-BD-PI-0642 | 0 |  | UG |  | T-047 | 2024-01-25 | [7 empty] | 2024-03-20 |  |  | 2024-06-27 | 2.2 | 271 | 1640 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45094 | WAI-7-201-070-40-SD | 1 | true | CH06822004-BD-PI-0635 | 0 | 5K | EG | H3 | T-058 | 2024-02-28 | [7 empty] | 2024-03-08 |  |  | 2024-03-14 | 9.4 | 271 | 413 | Virgil Frinculescu | [5 empty] | 0
45095 | WAI-7-201-070-40-SD | 1 | true | CH06822004-BD-PI-0635 | 0 | 5K | EG | H3 | T-058 | 2024-02-28 | [7 empty] | 2024-03-08 |  |  | 2024-03-14 | 4.6 | 271 | 413 | Virgil Frinculescu | [5 empty] | 0
45097 | CS-7-201-044-40-SP1 | 3 | true | CH06822004-BD-PI-1179 | 0 | 5K | OG3 | H2 | T-058 | 2024-02-28 | [7 empty] | 2024-03-14 |  | 2024-03-23 | 2024-06-28 | 0.6 | 264 | 371 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45098 | CS-7-201-045-40-SP1 | 3 | true | CH06822004-BD-PI-1179 | 0 | 5K | OG3 | H2 | T-058 | 2024-02-28 | [7 empty] | 2024-03-14 |  | 2024-03-23 | 2024-06-28 | 0.5 | 264 | 371 | Virgil Frinculescu | [5 empty] | 0
45099 | CS-7-201-070-40-SP1 | 3 | true | CH06822004-BD-PI-1179 | 0 | 5K | OG3 | H2 | T-058 | 2024-02-28 | [7 empty] | 2024-03-14 |  |  | 2024-03-21 | 7.8 | 264 | 371 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45100 | CS-7-201-070-40-SP1 | 3 | true | CH06822004-BD-PI-1179 | 0 | 5K | OG3 | H2 | T-058 | 2024-02-28 | [7 empty] | 2024-03-14 |  |  | 2024-03-21 | 1.2 | 264 | 371 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45128 | DKS-7-401-030-25-SD | 1 | true | CH06822004-BD-PI-0530 | 0 | 5K | OG3 | H3 | T-058 | 2024-02-28 | [7 empty] | 2024-03-20 |  |  | 2024-04-23 | 1.1 | 271 | 378 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45130 | DKS-7-401-031-15-SD | 1 | true | CH06822004-BD-PI-0530 | 0 | 5K | OG3 | H3 | T-058 | 2024-02-28 | [7 empty] | 2024-03-20 |  |  | 2024-04-23 | 0.7 | 271 | 378 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45131 | DKS-7-401-032-15-SD | 1 | true | CH06822004-BD-PI-0530 | 0 | 5K | OG3 | H3 | T-058 | 2024-02-28 | [7 empty] | 2024-03-20 |  |  | 2024-04-23 | 2.1 | 271 | 378 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45132 | DKS-7-401-033-15-SD | 1 | true | CH06822004-BD-PI-0530 | 0 | 5K | OG3 | H3 | T-058 | 2024-02-28 | [7 empty] | 2024-03-20 |  |  | 2024-04-23 | 1.3 | 271 | 378 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45134 | DKS-7-401-034-32-SD | 1 | true | CH06822004-BD-PI-0530 | 0 | 5K | OG3 | H3 | T-058 | 2024-02-28 | [7 empty] | 2024-03-20 |  |  | 2024-05-08 | 2.4 | 271 | 378 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45145 | DKS-7-401-034-32-SD | 1 | true | CH06822004-BD-PI-0530 | 0 | 5K | OG3 | H3 | T-058 | 2024-02-28 | [7 empty] | 2024-03-20 |  |  | 2024-04-04 | 0.2 | 271 | 378 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45152 | US4-0-244-010-15-SD6 | 3 | true | CH06822004-BD-PI-0586 | 0 | 5K | OG3 | H5 | T-058 | 2024-02-28 | [7 empty] | 2024-03-14 |  |  | 2024-05-08 | 16.5 | 261 | 410 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45153 | US4-0-244-010-15-SD6 | 3 | true | CH06822004-BD-PI-0586 | 0 | 5K | OG3 | H5 | T-058 | 2024-02-28 | [7 empty] | 2024-03-14 |  | 2024-05-01 | 2024-05-07 | 0.7 | 261 | 410 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45154 | US4-0-244-010-15-SD6 | 3 | true | CH06822004-BD-PI-0586 | 0 | 5K | OG3 | H5 | T-058 | 2024-02-28 | [7 empty] | 2024-03-14 |  | 2024-05-01 | 2024-05-07 | 1.6 | 261 | 410 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45155 | US4-0-244-010-15-SD6 | 3 | true | CH06822004-BD-PI-0586 | 0 | 5K | OG3 | H5 | T-058 | 2024-02-28 | [7 empty] | 2024-03-14 |  |  | 2024-06-18 | 7.3 | 261 | 410 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45160 | KR-0-216-020-32-SD5 | 2 | true | L604 | 0 | 5K | OG1 | C2 | T-058 | 2024-02-28 | [7 empty] | 2024-04-04 |  |  | 2024-04-11 | 5.9 | 260 | 393 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45161 | KR-0-216-020-32-SD5 | 2 | true | L604 | 0 | 5K | OG1 | C2 | T-058 | 2024-02-28 | [7 empty] | 2024-04-04 |  |  | 2024-04-11 | 10.2 | 260 | 393 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45162 | KR-0-WK002-020-20-SD5 | 2 | true | L604 | 0 | 5K | OG1 | C2 | T-058 | 2024-02-28 | [7 empty] | 2024-04-04 |  |  | 2024-08-13 | 2.4 | 260 | 393 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45163 | KR-0-WK003-020-20-SD5 | 2 | true | L604 | 0 | 5K | OG1 | C2 | T-058 | 2024-02-28 | [7 empty] | 2024-04-04 |  |  | 2024-08-12 | 2.7 | 260 | 393 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45164 | KR-0-WK005-020-20-SD5 | 2 | true | L604 | 0 | 5K | OG1 | C2 | T-058 | 2024-02-28 | [7 empty] | 2024-04-04 |  |  | 2024-08-12 | 2 | 260 | 393 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45165 | KV-0-216-021-32-SD5 | 2 | true | L604 | 0 | 5K | OG1 | C2 | T-058 | 2024-02-28 | [7 empty] | 2024-04-04 |  |  | 2024-04-11 | 7.4 | 260 | 394 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45166 | KV-0-216-021-32-SD5 | 2 | true | L604 | 0 | 5K | OG1 | C2 | T-058 | 2024-02-28 | [7 empty] | 2024-04-04 |  |  | 2024-04-11 | 8.3 | 260 | 394 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45167 | KV-0-WK002-021-20-SD5 | 2 | true | L604 | 0 | 5K | OG1 | C2 | T-058 | 2024-02-28 | [7 empty] | 2024-04-04 |  |  | 2024-08-13 | 2.6 | 260 | 394 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45168 | KV-0-WK003-021-20-SD5 | 2 | true | L604 | 0 | 5K | OG1 | C2 | T-058 | 2024-02-28 | [7 empty] | 2024-04-04 |  |  | 2024-08-12 | 3.1 | 260 | 394 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45169 | KV-0-WK005-021-20-SD5 | 2 | true | L604 | 0 | 5K | OG1 | C2 | T-058 | 2024-02-28 | [7 empty] | 2024-04-04 |  |  | 2024-08-12 | 2.1 | 260 | 394 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45170 | HR-NT-0-212-014-50-CA | 2 | true | CH06822004-BD-PI-0579 | 0 | 5K | OG2 | =0 | T-058 | 2024-02-28 | [7 empty] | 2024-03-12 |  |  | 2024-05-30 | 1.5 | 249 | 389 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45171 | HR-NT-0-212-014-50-CA | 2 | true | CH06822004-BD-PI-0579 | 0 | 5K | OG2 | =0 | T-058 | 2024-02-28 | [7 empty] | 2024-03-12 |  |  | 2024-05-11 | 11.4 | 249 | 389 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45172 | HR-NT-0-212-014-50-CA | 2 | true | CH06822004-BD-PI-0579 | 0 | 5K | OG2 | =0 | T-058 | 2024-02-28 | [7 empty] | 2024-03-12 |  |  | 2024-05-11 | 14.4 | 249 | 389 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45173 | HR-NT-0-L605-014-50-CA | 2 | false | L605 | 0 | 5K | OG2 | H1 | T-058 | 2024-02-28 | [7 empty] | 2024-03-12 |  |  |  | 4.2 | 249 | 389 | Attila Henter | [5 empty] | 0 | SEP | SEP
45174 | HR-NT-0-L605-014-50-CA | 2 | false | L605 | 0 | 5K | OG2 | H1 | T-058 | 2024-02-28 | [7 empty] | 2024-03-12 |  |  |  | 0.7 | 249 | 389 | Attila Henter | [5 empty] | 0 | SEP | SEP
45175 | HR-NT-0-L605-014-50-CA | 2 | false | L605 | 0 | 5K | OG2 | H1 | T-058 | 2024-02-28 | [7 empty] | 2024-03-12 |  |  |  | 3.7 | 249 | 389 | Attila Henter | [5 empty] | 0 | SEP | SEP
48435 | HR-NT-0-L605-014-50-CA | 3 | true | L605 | 0 | 5K | OG2 | H1 | T-072 | 2024-04-09 | [7 empty] | 2024-04-15 |  |  | 2024-06-27 | 1.3 | 249 | 389 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48436 | HR-NT-0-L605-014-50-CA | 3 | true | L605 | 0 | 5K | OG2 | H1 | T-072 | 2024-04-09 | [7 empty] | 2024-04-15 |  |  | 2024-07-18 | 1 | 249 | 389 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48437 | HR-NT-0-L605-014-50-CA | 3 | true | L605 | 0 | 5K | OG2 | H1 | T-072 | 2024-04-09 | [7 empty] | 2024-04-15 |  |  | 2024-06-27 | 2.6 | 249 | 389 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45176 | HV-NT-0-212-015-50-CA | 2 | true | CH06822004-BD-PI-0579 | 0 | 5K | OG2 | =0 | T-058 | 2024-02-28 | [7 empty] | 2024-03-12 |  |  | 2024-05-11 | 16.9 | 249 | 390 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45177 | HV-NT-0-212-015-50-CA | 2 | true | CH06822004-BD-PI-0579 | 0 | 5K | OG2 | =0 | T-058 | 2024-02-28 | [7 empty] | 2024-03-12 | 2024-05-11 |  | 2024-05-30 | 8.9 | 249 | 390 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45178 | HV-NT-0-L605-015-50-CA | 2 | false | L605 | 0 | 5K | OG2 | H1 | T-058 | 2024-02-28 | [7 empty] | 2024-03-12 |  |  |  | 2.4 | 249 | 390 | Attila Henter | [5 empty] | 0 | SEP | SEP
45179 | HV-NT-0-L605-015-50-CA | 2 | false | L605 | 0 | 5K | OG2 | H1 | T-058 | 2024-02-28 | [7 empty] | 2024-03-12 |  |  |  | 3.9 | 249 | 390 | Attila Henter | [5 empty] | 0 | SEP | SEP
48438 | HV-NT-0-L605-015-50-CA | 3 | true | L605 | 0 | 5K | OG2 | H1 | T-072 | 2024-04-09 | [7 empty] | 2024-04-15 |  |  | 2024-07-18 | 2.3 | 249 | 390 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48439 | HV-NT-0-L605-015-50-CA | 3 | true | L605 | 0 | 5K | OG2 | H1 | T-072 | 2024-04-09 | [7 empty] | 2024-04-15 |  |  | 2024-05-30 | 3.6 | 249 | 390 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45180 | KR-0-216-024-80-SD5 | 2 | true | CH06822004-BD-PI-0607 | 0 | 5K | OG2 | =0 | T-058 | 2024-02-28 | [7 empty] | 2024-03-19 |  |  | 2024-04-09 | 2.8 | 260 | 393 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45181 | KR-0-216-024-80-SD5 | 2 | true | CH06822004-BD-PI-0607 | 0 | 5K | OG2 | =0 | T-058 | 2024-02-28 | [7 empty] | 2024-03-19 |  |  | 2024-04-09 | 13.2 | 260 | 393 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45182 | KR-0-216-024-80-SD5 | 2 | true | CH06822004-BD-PI-0607 | 0 | 5K | OG2 | =0 | T-058 | 2024-02-28 | [7 empty] | 2024-03-19 |  |  | 2024-04-09 | 10.8 | 260 | 393 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45183 | KR-0-216-024-80-SD5 | 2 | true | CH06822004-BD-PI-0607 | 0 | 5K | OG2 | =0 | T-058 | 2024-02-28 | [7 empty] | 2024-03-19 |  |  | 2024-04-05 | 3.4 | 260 | 393 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45184 | KR-0-216-044-32-SD5 | 2 | true | L609 | 0 | 5K | OG2 | C2 | T-058 | 2024-02-28 | [7 empty] | 2024-04-04 |  |  | 2024-04-16 | 3 | 260 | 393 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45185 | KR-0-216-044-32-SD5-SITE | 2 | true | L609 | 0 | 5K | OG2 | C2 | T-058 | 2024-02-28 | [7 empty] | 2024-04-04 |  |  | 2024-08-12 | 0.9 | 260 | 393 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45186 | KR-0-216-045-32-SD5 | 2 | true | L609 | 0 | 5K | OG2 | C2 | T-058 | 2024-02-28 | [7 empty] | 2024-04-04 |  |  | 2024-04-10 | 6.9 | 260 | 393 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45187 | KR-0-216-045-32-SD5 | 2 | true | L609 | 0 | 5K | OG2 | C2 | T-058 | 2024-02-28 | [7 empty] | 2024-04-04 |  |  | 2024-04-12 | 5.7 | 260 | 393 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45188 | KR-0-216-045-32-SD5-SITE | 2 | true | L609 | 0 | 5K | OG2 | C2 | T-058 | 2024-02-28 | [7 empty] | 2024-04-04 |  |  | 2024-08-12 | 1.1 | 260 | 393 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45189 | KR-0-216-046-32-SD5-SITE | 2 | true | L609 | 0 | 5K | OG2 | C2 | T-058 | 2024-02-28 | [7 empty] | 2024-04-04 |  |  | 2024-05-21 | 0.9 | 260 | 393 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45190 | KR-0-216-046-32-SD5 | 2 | true | L609 | 0 | 5K | OG2 | C2 | T-058 | 2024-02-28 | [7 empty] | 2024-04-04 |  |  | 2024-04-29 | 0.9 | 260 | 393 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45191 | KR-0-216-046-32-SD5 | 2 | true | L609 | 0 | 5K | OG2 | C2 | T-058 | 2024-02-28 | [7 empty] | 2024-04-04 |  |  | 2024-04-29 | 5.4 | 260 | 393 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45192 | KR-0-216-047-80-SD5 | 2 | true | L605 | 0 | 5K | OG2 | C2 | T-058 | 2024-02-28 | [7 empty] | 2024-04-16 |  | 2024-05-01 | 2024-07-18 | 0.7 | 260 | 393 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45193 | KR-0-216-047-80-SD5 | 2 | true | L605 | 0 | 5K | OG2 | C2 | T-058 | 2024-02-28 | [7 empty] | 2024-04-16 |  | 2024-05-01 | 2024-06-27 | 2.3 | 260 | 393 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45194 | KV-0-216-025-80-SD5 | 2 | true | CH06822004-BD-PI-0607 | 0 | 5K | OG2 | C2 | T-058 | 2024-02-28 | [7 empty] | 2024-03-19 |  |  | 2024-03-27 | 3.6 | 260 | 394 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45195 | KV-0-216-025-80-SD5 | 2 | true | CH06822004-BD-PI-0607 | 0 | 5K | OG2 | C2 | T-058 | 2024-02-28 | [7 empty] | 2024-03-19 |  |  | 2024-04-08 | 14.1 | 260 | 394 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45196 | KV-0-216-025-80-SD5 | 2 | true | CH06822004-BD-PI-0607 | 0 | 5K | OG2 | C2 | T-058 | 2024-02-28 | [7 empty] | 2024-03-19 |  |  | 2024-04-09 | 13 | 260 | 394 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45200 | KV-0-216-044-32-SD5 | 2 | true | L609 | 0 | 5K | OG2 | C2 | T-058 | 2024-02-28 | [7 empty] | 2024-04-04 |  |  | 2024-04-16 | 1.8 | 260 | 394 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45201 | KV-0-216-044-32-SD5 | 2 | true | L609 | 0 | 5K | OG2 | C2 | T-058 | 2024-02-28 | [7 empty] | 2024-04-04 |  |  | 2024-04-16 | 1.5 | 260 | 394 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45202 | KV-0-216-044-32-SD5-SITE | 2 | true | L609 | 0 | 5K | OG2 | C2 | T-058 | 2024-02-28 | [7 empty] | 2024-04-04 |  |  | 2024-08-12 | 0.8 | 260 | 394 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45203 | KV-0-216-045-32-SD5 | 2 | true | L609 | 0 | 5K | OG2 | C2 | T-058 | 2024-02-28 | [7 empty] | 2024-04-04 |  |  | 2024-04-12 | 6.3 | 260 | 394 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45204 | KV-0-216-045-32-SD5 | 2 | true | L609 | 0 | 5K | OG2 | C2 | T-058 | 2024-02-28 | [7 empty] | 2024-04-04 |  |  | 2024-04-11 | 6.5 | 260 | 394 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45205 | KV-0-216-045-32-SD5-SITE | 2 | true | L609 | 0 | 5K | OG2 | C2 | T-058 | 2024-02-28 | [7 empty] | 2024-04-04 |  |  | 2024-08-12 | 1.1 | 260 | 394 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45206 | KV-0-216-046-32-SD5 | 2 | true | L609 | 0 | 5K | OG2 | C2 | T-058 | 2024-02-28 | [7 empty] | 2024-04-04 |  |  | 2024-05-01 | 5.9 | 260 | 394 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45207 | KV-0-216-046-32-SD5-SITE | 2 | true | L609 | 0 | 5K | OG2 | C2 | T-058 | 2024-02-28 | [7 empty] | 2024-04-04 |  |  | 2024-05-21 | 1 | 260 | 394 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45208 | KV-0-216-047-80-SD5 | 2 | true | L605 | 0 | 5K | OG2 | C2 | T-058 | 2024-02-28 | [7 empty] | 2024-04-16 |  | 2024-05-01 | 2024-07-18 | 2.8 | 260 | 394 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45209 | KV-0-216-047-80-SD5 | 2 | true | L605 | 0 | 5K | OG2 | C2 | T-058 | 2024-02-28 | [7 empty] | 2024-04-16 |  | 2024-05-01 | 2024-06-27 | 2.6 | 260 | 394 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45347 | CIP-2-000-010-40-SP | 1 | true | CH06822004-BD-PI-0523 | 0 | 5K | UG | H3 | T-060 | 2024-03-05 | [7 empty] | 2024-05-01 | 2024-05-11 |  | 2024-05-24 | 20.9 | 262 | 460 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45348 | CIP-2-000-010-40-SP | 1 | true | CH06822004-BD-PI-0523 | 0 | 5K | UG | H3 | T-060 | 2024-03-05 | [7 empty] | 2024-05-01 |  |  | 2024-05-24 | 14.8 | 262 | 460 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45349 | CIPR-2-300-500-40-SP | 1 | true | CH06822004-BD-PI-0523 | 0 | 5K | UG | H3 | T-060 | 2024-03-05 | [7 empty] | 2024-06-12 |  |  | 2024-06-26 | 0.3 | 262 | 365 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45350 | DK4-0-600-004-15-SD6 | 1 | true | CH06822004-BD-PI-0558 | 0 | 5K | OG1 | H6 | T-060 | 2024-03-05 | [7 empty] | 2024-04-16 |  |  | 2024-04-23 | 0.7 | 261 | 375 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45351 | DK4-0-600-005-25-SD6 | 1 | true | CH06822004-BD-PI-0558 | 0 | 5K | OG1 | H6 | T-060 | 2024-03-05 | [7 empty] | 2024-04-16 |  |  | 2024-04-23 | 4 | 261 | 375 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45352 | DK4-0-600-006-15-SD6 | 1 | true | CH06822004-BD-PI-0558 | 0 | 5K | OG1 | H6 | T-060 | 2024-03-05 | [7 empty] | 2024-04-16 |  |  | 2024-04-23 | 4.3 | 261 | 375 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45360 | GR-0-244-015-65-SD5 | 1 | true | CH06822004-BD-PI-0565 | 0 | 5K | OG1 | C3 | T-060 | 2024-03-05 | [7 empty] | 2024-06-06 |  |  | 2024-07-22 | 4.8 | 260 | 387 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45361 | GV-0-244-016-65-SD5 | 1 | true | CH06822004-BD-PI-0565 | 0 | 5K | OG1 | C3 | T-060 | 2024-03-05 | [7 empty] | 2024-06-06 |  |  | 2024-07-22 | 6.5 | 260 | 388 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45364 | US4-0-244-005-25-SD6 | 1 | true | CH06822004-BD-PI-0586 | 0 | 5K | OG1 | H5 | T-060 | 2024-03-05 | [7 empty] | 2024-04-09 |  |  | 2024-04-25 | 4.8 | 261 | 410 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45365 | US4-0-244-005-25-SD6 | 1 | true | CH06822004-BD-PI-0586 | 0 | 5K | OG1 | H5 | T-060 | 2024-03-05 | [7 empty] | 2024-04-09 |  |  | 2024-04-25 | 5 | 261 | 410 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45366 | US4-0-244-006-15-SD6 | 1 | true | CH06822004-BD-PI-0586 | 0 | 5K | OG1 | H5 | T-060 | 2024-03-05 | [7 empty] | 2024-04-09 |  |  | 2024-07-10 | 1.3 | 261 | 410 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45369 | US4-0-244-012-15-SD6 | 1 | true | CH06822004-BD-PI-0586 | 0 | 5K | OG1 | H5 | T-060 | 2024-03-05 | [7 empty] | 2024-04-09 |  |  | 2024-04-25 | 4.7 | 261 | 410 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45601 | DLF-7-831-046-15-SP1 | 2 | true | CH06822004-BD-PI-0537 | 0 | 5K | OG3 | N/A | T-061 | 2024-03-07 | [7 empty] | 2024-03-14 |  |  | 2024-03-19 | 0.7 | 264 | 380 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45602 | DLF-7-831-047-25-SP1 | 2 | true | CH06822004-BD-PI-0537 | 0 | 5K | OG1 | N/A | T-061 | 2024-03-07 | [7 empty] | 2024-03-14 |  |  | 2024-03-22 | 4.2 | 264 | 380 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45603 | DLF-7-831-048-25-SP1 | 2 | true | CH06822004-BD-PI-0537 | 0 | 5K | OG1 | N/A | T-061 | 2024-03-07 | [7 empty] | 2024-03-14 |  |  | 2024-03-21 | 2.7 | 264 | 380 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45604 | DLF-7-831-049-25-SP1 | 2 | true | CH06822004-BD-PI-0537 | 0 | 5K | EG | N/A | T-061 | 2024-03-07 | [7 empty] | 2024-03-19 |  |  | 2024-03-27 | 3.8 | 264 | 380 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45605 | DLF-7-831-049-25-SP1 | 2 | true | CH06822004-BD-PI-0537 | 0 | 5K | EG | N/A | T-061 | 2024-03-07 | [7 empty] | 2024-03-19 |  |  | 2024-03-27 | 0.6 | 264 | 380 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45606 | DLF-7-831-050-25-SP1 | 2 | true | CH06822004-BD-PI-0537 | 0 | 5K | EG | N/A | T-061 | 2024-03-08 | [7 empty] | 2024-03-19 |  |  | 2024-04-08 | 3.5 | 264 | 380 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45607 | DLF-7-831-050-25-SP1 | 2 | true | CH06822004-BD-PI-0537 | 0 | 5K | EG | N/A | T-061 | 2024-03-08 | [7 empty] | 2024-03-19 |  |  | 2024-04-08 | 1 | 264 | 380 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45629 | CIPR-6-085-850-25-SP | 2 | true | CH06822004-BD-PI-1435 | 0 | 5K | UG | H3 | T-061 | 2024-03-07 | [7 empty] | 2024-03-20 |  |  | 2024-03-26 | 12.2 | 262 | 365 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45630 | CIPR-6-085-850-25-SP | 2 | true | CH06822004-BD-PI-1435 | 0 | 5K | UG | H3 | T-061 | 2024-03-07 | [7 empty] | 2024-03-20 |  |  | 2024-03-25 | 6.1 | 262 | 365 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45631 | CIPR-6-700-101-32-SP | 2 | true | CH06822004-BD-PI-0893 | 0 | 5K | EG | H3 | T-061 | 2024-03-08 | [7 empty] | 2024-03-20 |  |  | 2024-04-04 | 10.2 | 262 | 365 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45632 | CIPR-6-700-101-32-SP | 2 | true | CH06822004-BD-PI-0893 | 0 | 5K | EG | H3 | T-061 | 2024-03-08 | [7 empty] | 2024-03-20 |  | 2024-05-01 | 2024-06-26 | 7.6 | 262 | 365 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45633 | CIPR-6-750-101-32-SP | 2 | true | CH06822004-BD-PI-0893 | 0 | 5K | EG | H3 | T-061 | 2024-03-08 | [7 empty] | 2024-03-20 |  |  | 2024-04-05 | 10.9 | 262 | 365 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45634 | CIPR-6-750-101-32-SP | 2 | true | CH06822004-BD-PI-0893 | 0 | 5K | EG | H3 | T-061 | 2024-03-08 | [7 empty] | 2024-03-20 |  | 2024-05-01 | 2024-06-25 | 6.3 | 262 | 365 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45635 | MDC-6-010-726-32-SP2 | 2 | true | CH06822004-BD-PI-0893 | 0 | 5K | OG1 | H3 | T-061 | 2024-03-08 | [7 empty] | 2024-04-08 |  |  | 2024-04-18 | 12.5 | 265 | 395 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45636 | MDC-6-010-726-32-SP2 | 2 | true | CH06822004-BD-PI-0893 | 0 | 5K | OG1 | H3 | T-061 | 2024-03-08 | [7 empty] | 2024-04-08 |  |  | 2024-04-18 | 5.4 | 265 | 395 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45637 | MDC-6-010-726-32-SP2 | 2 | true | CH06822004-BD-PI-0893 | 0 | 5K | OG1 | H3 | T-061 | 2024-03-08 | [7 empty] | 2024-04-08 |  |  | 2024-05-02 | 24.2 | 265 | 395 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45638 | MDC-6-010-726-32-SP2 | 2 | true | CH06822004-BD-PI-0893 | 0 | 5K | OG1 | H3 | T-061 | 2024-03-08 | [7 empty] | 2024-04-08 |  |  | 2024-05-07 | 16.5 | 265 | 395 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45639 | MDC-6-010-726-32-SP2 | 2 | true | CH06822004-BD-PI-0893 | 0 | 5K | OG1 | H3 | T-061 | 2024-03-08 | [7 empty] | 2024-04-24 |  |  | 2024-05-11 | 18.8 | 265 | 395 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45640 | MDC-6-010-726-32-SP2 | 2 | true | CH06822004-BD-PI-0893 | 0 | 5K | OG1 | H3 | T-061 | 2024-03-08 | [7 empty] | 2024-04-24 |  |  | 2024-05-15 | 14.8 | 265 | 395 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45641 | MDC-6-010-726-32-SP2 | 2 | true | CH06822004-BD-PI-0893 | 0 | 5K | OG1 | H3 | T-061 | 2024-03-08 | [7 empty] | 2024-04-24 | 2024-05-25 |  | 2024-06-12 | 18.2 | 265 | 395 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45642 | MDC-6-010-726-32-SP2 | 2 | true | CH06822004-BD-PI-0893 | 0 | 5K | OG1 | H3 | T-061 | 2024-03-08 | [7 empty] | 2024-04-24 |  | 2024-06-27 | 2024-08-22 | 6.6 | 265 | 395 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45643 | MDC-6-011-726-32-SP2 | 2 | true | CH06822004-BD-PI-0893 | 0 | 5K | OG1 | H3 | T-061 | 2024-03-08 | [7 empty] | 2024-04-08 |  |  | 2024-04-18 | 2 | 265 | 395 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45644 | MDC-6-011-726-32-SP2 | 2 | true | CH06822004-BD-PI-0893 | 0 | 5K | OG1 | H3 | T-061 | 2024-03-08 | [7 empty] | 2024-04-08 |  |  | 2024-04-18 | 11 | 265 | 395 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45645 | MDC-6-011-726-32-SP2 | 2 | true | CH06822004-BD-PI-0893 | 0 | 5K | OG1 | H3 | T-061 | 2024-03-08 | [7 empty] | 2024-04-08 |  |  | 2024-05-02 | 26.1 | 265 | 395 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45646 | MDC-6-011-726-32-SP2 | 2 | true | CH06822004-BD-PI-0893 | 0 | 5K | OG1 | H3 | T-061 | 2024-03-08 | [7 empty] | 2024-04-08 |  |  | 2024-05-07 | 16.7 | 265 | 395 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45647 | MDC-6-011-726-32-SP2 | 2 | true | CH06822004-BD-PI-0893 | 0 | 5K | OG1 | H3 | T-061 | 2024-03-08 | [7 empty] | 2024-04-24 |  |  | 2024-05-11 | 14.3 | 265 | 395 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45648 | MDC-6-011-726-32-SP2 | 2 | true | CH06822004-BD-PI-0893 | 0 | 5K | OG1 | H3 | T-061 | 2024-03-08 | [7 empty] | 2024-04-24 |  |  | 2024-05-15 | 19 | 265 | 395 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45649 | MDC-6-011-726-32-SP2 | 2 | true | CH06822004-BD-PI-0893 | 0 | 5K | OG1 | H3 | T-061 | 2024-03-08 | [7 empty] | 2024-04-24 |  |  | 2024-05-24 | 18.3 | 265 | 395 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45650 | MDC-6-011-726-32-SP2 | 2 | true | CH06822004-BD-PI-0893 | 0 | 5K | OG1 | H3 | T-061 | 2024-03-08 | [7 empty] | 2024-04-24 |  | 2024-06-27 | 2024-08-22 | 6.9 | 265 | 395 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45651 | MDC-6-012-714-20-SP2 | 2 | true | CH06822004-BD-PI-0893 | 0 | 5K | OG1 | H3 | T-061 | 2024-03-08 | [7 empty] | 2024-04-08 |  |  | 2024-04-18 | 2.9 | 265 | 395 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45652 | MDC-6-012-714-20-SP2 | 2 | true | CH06822004-BD-PI-0893 | 0 | 5K | OG1 | H3 | T-061 | 2024-03-08 | [7 empty] | 2024-04-08 |  |  | 2024-04-18 | 10.3 | 265 | 395 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45653 | MDC-6-012-714-20-SP2 | 2 | true | CH06822004-BD-PI-0893 | 0 | 5K | OG1 | H3 | T-061 | 2024-03-08 | [7 empty] | 2024-04-08 |  |  | 2024-05-02 | 26.6 | 265 | 395 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45654 | MDC-6-012-714-20-SP2 | 2 | true | CH06822004-BD-PI-0893 | 0 | 5K | OG1 | H3 | T-061 | 2024-03-08 | [7 empty] | 2024-04-08 |  |  | 2024-05-11 | 17.5 | 265 | 395 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45655 | MDC-6-012-714-20-SP2 | 2 | true | CH06822004-BD-PI-0893 | 0 | 5K | OG1 | H3 | T-061 | 2024-03-08 | [7 empty] | 2024-04-24 |  |  | 2024-05-11 | 18 | 265 | 395 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45656 | MDC-6-012-714-20-SP2 | 2 | true | CH06822004-BD-PI-0893 | 0 | 5K | OG1 | H3 | T-061 | 2024-03-08 | [7 empty] | 2024-04-24 |  |  | 2024-05-15 | 15.3 | 265 | 395 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45657 | MDC-6-012-714-20-SP2 | 2 | true | CH06822004-BD-PI-0893 | 0 | 5K | OG1 | H3 | T-061 | 2024-03-08 | [7 empty] | 2024-04-24 |  |  | 2024-05-24 | 17.7 | 265 | 395 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45658 | MDC-6-012-714-20-SP2 | 2 | true | CH06822004-BD-PI-0893 | 0 | 5K | OG1 | H3 | T-061 | 2024-03-08 | [7 empty] | 2024-04-24 |  | 2024-06-27 | 2024-08-22 | 6.7 | 265 | 395 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45659 | PFC-6-020-726-25-SP2 | 2 | true | CH06822004-BD-PI-1435 | 0 | 5K | EG | H3 | T-061 | 2024-03-08 | [7 empty] | 2024-05-13 |  |  | 2024-05-25 | 5 | 265 | 402 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45660 | PFC-6-020-726-25-SP2 | 2 | true | CH06822004-BD-PI-1435 | 0 | 5K | EG | H3 | T-061 | 2024-03-08 | [7 empty] | 2024-05-13 | 2024-05-25 |  | 2024-05-30 | 11.3 | 265 | 402 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45661 | PFC-6-020-726-25-SP2 | 2 | true | CH06822004-BD-PI-1435 | 0 | 5K | EG | H3 | T-061 | 2024-03-08 | [7 empty] | 2024-05-13 |  |  | 2024-06-04 | 10.2 | 265 | 402 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45662 | PFC-6-020-726-25-SP2 | 2 | true | CH06822004-BD-PI-1435 | 0 | 5K | EG | H3 | T-061 | 2024-03-08 | [7 empty] | 2024-05-13 |  | 2024-06-07 | 2024-06-19 | 12.2 | 265 | 402 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45663 | PFC-6-020-726-25-SP2 | 2 | true | CH06822004-BD-PI-1435 | 0 | 5K | EG | H3 | T-061 | 2024-03-08 | [7 empty] | 2024-05-13 | 2024-06-07 | 2024-06-27 | 2024-08-24 | 6.2 | 265 | 402 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45664 | PFC-6-021-726-25-SP2 | 2 | true | CH06822004-BD-PI-1435 | 0 | 5K | EG | H3 | T-061 | 2024-03-08 | [7 empty] | 2024-05-13 |  |  | 2024-05-25 | 3.7 | 265 | 402 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45665 | PFC-6-021-726-25-SP2 | 2 | true | CH06822004-BD-PI-1435 | 0 | 5K | EG | H3 | T-061 | 2024-03-08 | [7 empty] | 2024-05-13 | 2024-05-25 |  | 2024-05-29 | 11 | 265 | 402 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45666 | PFC-6-021-726-25-SP2 | 2 | true | CH06822004-BD-PI-1435 | 0 | 5K | EG | H3 | T-061 | 2024-03-08 | [7 empty] | 2024-05-13 |  |  | 2024-06-05 | 19.7 | 265 | 402 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45667 | PFC-6-021-726-25-SP2 | 2 | true | CH06822004-BD-PI-1435 | 0 | 5K | EG | H3 | T-061 | 2024-03-08 | [7 empty] | 2024-05-13 |  | 2024-06-27 | 2024-08-24 | 3.5 | 265 | 402 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45668 | PFC-6-021-726-25-SP2 | 2 | true | CH06822004-BD-PI-1435 | 0 | 5K | EG | H3 | T-061 | 2024-03-08 | [7 empty] | 2024-05-13 | 2024-06-07 | 2024-06-27 | 2024-08-24 | 5.5 | 265 | 402 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45669 | PFC-6-022-726-25-SP2 | 2 | true | CH06822004-BD-PI-1435 | 0 | 5K | EG | H3 | T-061 | 2024-03-08 | [7 empty] | 2024-05-13 |  |  | 2024-05-25 | 8.9 | 265 | 402 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45670 | PFC-6-022-726-25-SP2 | 2 | true | CH06822004-BD-PI-1435 | 0 | 5K | EG | H3 | T-061 | 2024-03-08 | [7 empty] | 2024-05-13 | 2024-05-25 |  | 2024-05-29 | 7.2 | 265 | 402 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45671 | PFC-6-022-726-25-SP2 | 2 | true | CH06822004-BD-PI-1435 | 0 | 5K | EG | H3 | T-061 | 2024-03-08 | [7 empty] | 2024-05-13 |  |  | 2024-06-05 | 18.2 | 265 | 402 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45672 | PFC-6-022-726-25-SP2 | 2 | true | CH06822004-BD-PI-1435 | 0 | 5K | EG | H3 | T-061 | 2024-03-08 | [7 empty] | 2024-05-13 |  | 2024-06-27 | 2024-08-24 | 5.7 | 265 | 402 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45673 | PFC-6-022-726-25-SP2 | 2 | true | CH06822004-BD-PI-1435 | 0 | 5K | EG | H3 | T-061 | 2024-03-08 | [7 empty] | 2024-05-13 | 2024-06-07 |  | 2024-06-07 | 2.4 | 265 | 402 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45674 | PFC-6-023-740-20-SP2 | 2 | true | CH06822004-BD-PI-1435 | 0 | 5K | EG | H3 | T-061 | 2024-03-08 | [7 empty] | 2024-05-13 |  |  | 2024-06-26 | 0.6 | 265 | 402 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45675 | PFC-6-023-740-20-SP2 | 2 | true | CH06822004-BD-PI-1435 | 0 | 5K | EG | H3 | T-061 | 2024-03-08 | [7 empty] | 2024-05-13 |  |  | 2024-06-26 | 4.8 | 265 | 402 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45676 | PFC-6-023-740-20-SP2 | 2 | true | CH06822004-BD-PI-1435 | 0 | 5K | EG | H3 | T-061 | 2024-03-08 | [7 empty] | 2024-05-13 |  |  | 2024-06-25 | 5.6 | 265 | 402 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45677 | PFC-6-023-740-20-SP2 | 2 | true | CH06822004-BD-PI-1435 | 0 | 5K | EG | H3 | T-061 | 2024-03-08 | [7 empty] | 2024-05-13 |  |  | 2024-06-21 | 8.1 | 265 | 402 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45678 | PFC-6-023-740-20-SP2 | 2 | true | CH06822004-BD-PI-1435 | 0 | 5K | EG | H3 | T-061 | 2024-03-08 | [7 empty] | 2024-05-13 |  |  | 2024-06-04 | 10.6 | 265 | 402 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45679 | PFC-6-023-740-20-SP2 | 2 | true | CH06822004-BD-PI-1435 | 0 | 5K | EG | H3 | T-061 | 2024-03-08 | [7 empty] | 2024-05-13 |  |  | 2024-05-25 | 8.5 | 265 | 402 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45680 | PFC-6-023-740-20-SP2 | 2 | true | CH06822004-BD-PI-1435 | 0 | 5K | EG | H3 | T-061 | 2024-03-08 | [7 empty] | 2024-05-13 |  | 2024-06-27 | 2024-08-24 | 6.4 | 265 | 402 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45681 | TIE-IN_6-070-521 | 2 | true | CH06822004-BD-PI-0893 | 0 | 5K | EG | H3 | T-061 | 2024-03-08 | [7 empty] | 2024-06-19 |  |  | 2024-06-26 | 0.5 | 262 | 365 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
45682 | TIE-IN_6-075-512 | 2 | true | CH06822004-BD-PI-0893 | 0 | 5K | EG | H3 | T-061 | 2024-03-08 | [7 empty] | 2024-06-19 |  |  | 2024-06-25 | 0.5 | 262 | 365 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48216 | ABP-7-701-007-32-SD1 | 1 | false | CH06822004-BD-PI-0495 | 0 | 5K | OG1 | N/A | T-069 | 2024-04-05 | [7 empty] | 2024-04-25 |  |  |  | 7.5 | 258 | 362 | Jozef Kotul | [5 empty] | 0
49687 | ABP-7-701-007-32-SD1 | 2 | true | CH06822004-BD-PI-0495 | 0 | 5K | OG1 | N/A | T-077 | 2024-04-25 | [7 empty] | 2024-05-02 |  |  | 2024-09-13 | 7.5 | 258 | 362 | Virgil Frinculescu | [5 empty] | 0
48217 | ABP-7-701-008-32-SD1 | 1 | false | CH06822004-BD-PI-0495 | 0 | 5K | OG1 | N/A | T-069 | 2024-04-05 | [7 empty] | 2024-04-25 |  |  |  | 3.2 | 258 | 362 | Jozef Kotul | [5 empty] | 0 | SEP | SEP
48218 | ABP-7-701-008-32-SD1 | 1 | false | CH06822004-BD-PI-0495 | 0 | 5K | OG1 | N/A | T-069 | 2024-04-05 | [7 empty] | 2024-04-25 |  |  |  | 4.7 | 258 | 362 | Jozef Kotul | [5 empty] | 0 | SEP | SEP
49688 | ABP-7-701-008-32-SD1 | 2 | true | CH06822004-BD-PI-0495 | 0 | 5K | OG1 | N/A | T-077 | 2024-04-25 | [7 empty] | 2024-05-02 | 2024-07-31 |  | 2024-09-07 | 3.2 | 258 | 362 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
49689 | ABP-7-701-008-32-SD1 | 2 | true | CH06822004-BD-PI-0495 | 0 | 5K | OG1 | N/A | T-077 | 2024-04-25 | [7 empty] | 2024-05-02 |  |  | 2024-05-07 | 4.7 | 258 | 362 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48219 | ABP-7-701-028-25-SD1 | 1 | false | CH06822004-BD-PI-0495 | 0 | 5K | OG1 | N/A | T-069 | 2024-04-05 | [7 empty] | 2024-04-25 |  |  | 2024-05-07 | 5.3 | 258 | 362 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48220 | ABP-7-701-028-25-SD1 | 1 | false | CH06822004-BD-PI-0495 | 0 | 5K | OG1 | N/A | T-069 | 2024-04-05 | [7 empty] | 2024-04-25 |  |  |  | 4 | 258 | 362 | Jozef Kotul | [5 empty] | 0 | SEP | SEP
50529 | ABP-7-701-028-25-SD1 | 2 | true | CH06822004-BD-PI-0495 | 0 | 5K | OG1 | N/A | T-081 | 2024-05-13 | [7 empty] | 2024-04-25 |  | 2024-05-13 | 2024-08-12 | 3.6 | 258 | 362 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
50530 | ABP-7-701-028-25-SD1 | 2 | true | CH06822004-BD-PI-0495 | 0 | 5K | OG1 | N/A | T-081 | 2024-05-13 | [7 empty] | 2024-04-25 |  |  | 2024-08-12 | 4.2 | 258 | 362 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
50531 | ABP-7-701-028-25-SD1 | 2 | true | CH06822004-BD-PI-0495 | 0 | 5K | OG1 | N/A | T-081 | 2024-05-13 | [10 empty] | 2024-08-12 | 6.1 | 258 | 362 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48221 | CIP-2-000-003-40-SP | 1 | true | CH06822004-BD-PI-0523 | 0 | 5K | EG | H3 | T-069 | 2024-04-05 | [7 empty] | 2024-05-27 |  |  | 2024-06-07 | 4.7 | 262 | 460 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48222 | CIP-2-000-004-40-SP | 1 | true | CH06822004-BD-PI-0523 | 0 | 5K | EG | H3 | T-069 | 2024-04-05 | [7 empty] | 2024-05-27 |  |  | 2024-06-18 | 0.6 | 262 | 460 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48223 | CIP-2-000-004-40-SP | 1 | true | CH06822004-BD-PI-0523 | 0 | 5K | EG | H3 | T-069 | 2024-04-05 | [7 empty] | 2024-06-12 |  |  | 2024-06-26 | 3.8 | 262 | 460 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48224 | CIP-2-000-006-32-SP | 1 | true | CH06822004-BD-PI-0523 | 0 | 5K | EG | H3 | T-069 | 2024-04-05 | [7 empty] | 2024-05-27 |  |  | 2024-06-07 | 1.5 | 262 | 460 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48225 | CIP-2-000-007-32-SP | 1 | true | CH06822004-BD-PI-0523 | 0 | 5K | EG | H3 | T-069 | 2024-04-05 | [7 empty] | 2024-05-27 |  |  | 2024-06-07 | 1.4 | 262 | 460 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48226 | CIP-2-000-008-32-SP | 1 | true | CH06822004-BD-PI-0523 | 0 | 5K | EG | H3 | T-069 | 2024-04-05 | [7 empty] | 2024-04-30 |  |  | 2024-06-07 | 8.54 | 262 | 460 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48227 | CIP-2-000-012-40-SP | 1 | true | CH06822004-BD-PI-0523 | 0 | 5K | OG1 | H3 | T-069 | 2024-04-05 | [7 empty] | 2024-05-27 |  |  | 2024-06-18 | 13.2 | 262 | 460 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48228 | CIP-2-000-014-32-SP | 1 | true | CH06822004-BD-PI-0523 | 0 | 5K | OG1 | B | T-069 | 2024-04-05 | [7 empty] | 2024-06-27 |  |  | 2024-07-18 | 5.2 | 262 | 460 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48229 | CIP-2-000-015-32-SP | 1 | true | CH06822004-BD-PI-0523 | 0 | 5K | OG1 | B | T-069 | 2024-04-05 | [7 empty] | 2024-06-27 |  |  | 2024-09-10 | 0.6 | 262 | 460 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48230 | CIP-2-000-016-32-SP | 1 | true | CH06822004-BD-PI-0523 | 0 | 5K | OG1 | B | T-069 | 2024-04-05 | [7 empty] | 2024-06-27 |  |  | 2024-09-10 | 0.7 | 262 | 460 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48231 | CIP-2-000-017-32-SP | 1 | true | CH06822004-BD-PI-0523 | 0 | 5K | EG | H3 | T-069 | 2024-04-05 | [7 empty] | 2024-05-27 |  |  | 2024-06-18 | 2.3 | 262 | 460 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48232 | CIP-2-000-018-32-SP | 1 | true | CH06822004-BD-PI-0523 | 0 | 5K | EG | H3 | T-069 | 2024-04-05 | [7 empty] | 2024-05-27 |  |  | 2024-06-18 | 2.8 | 262 | 460 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48233 | CIP-2-000-019-32-SP | 1 | true | CH06822004-BD-PI-0523 | 0 | 5K | EG | H3 | T-069 | 2024-04-05 | [7 empty] | 2024-05-01 |  |  | 2024-06-07 | 9.9 | 262 | 460 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48234 | CIP-2-000-020-32-SP | 1 | true | CH06822004-BD-PI-0523 | 0 | 5K | EG | H3 | T-069 | 2024-04-05 | [7 empty] | 2024-05-01 |  |  | 2024-06-07 | 9.3 | 262 | 460 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48235 | CIP-2-000-021-32-SP | 1 | true | CH06822004-BD-PI-0523 | 0 | 5K | EG | B | T-069 | 2024-04-05 | [7 empty] | 2024-06-27 |  |  | 2024-09-13 | 0.4 | 262 | 460 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48236 | CIP-2-000-022-32-SP | 1 | true | CH06822004-BD-PI-0523 | 0 | 5K | OG1 | B | T-069 | 2024-04-05 | [7 empty] | 2024-05-13 |  |  | 2024-09-09 | 1.4 | 262 | 460 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48237 | CIP-2-000-023-32-SP | 1 | true | CH06822004-BD-PI-0523 | 0 | 5K | OG1 | B | T-069 | 2024-04-05 | [7 empty] | 2024-06-27 |  |  | 2024-09-09 | 1.3 | 262 | 460 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48238 | CIP-2-000-024-32-SP | 1 | true | CH06822004-BD-PI-0523 | 0 | 5K | OG1 | B | T-069 | 2024-04-05 | [7 empty] | 2024-05-13 |  |  | 2024-09-18 | 5 | 262 | 460 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48239 | CIP-2-000-025-32-SP | 1 | true | CH06822004-BD-PI-0523 | 0 | 5K | OG1 | B | T-069 | 2024-04-05 | [7 empty] | 2024-05-13 |  |  | 2024-09-10 | 1.2 | 262 | 460 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48240 | CIPR-6-085-850_US21 | 1 | false | CH06822004-BD-PI-1435 | 0 | 5K | EG | B | T-069 | 2024-04-05 | [11 empty] | 0 | 262 | 365 | [6 empty] | 0 | SEP | SEP
49719 | CIPR-6-085-850_US21 | 2 | true | CH06822004-BD-PI-1435 | 0 | 5K | EG | B | T-077 | 2024-04-25 | [7 empty] | 2024-05-13 |  |  | 2024-07-17 | 4.8 | 262 | 365 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48241 | CIPR-6-700-101_US07 | 1 | true | CH06822004-BD-PI-0893 | 0 | 5K | OG1 | B | T-069 | 2024-04-05 | [7 empty] | 2024-05-13 |  |  | 2024-05-15 | 0 | 262 | 365 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48242 | CIPR-6-750-101_US07 | 1 | true | CH06822004-BD-PI-0893 | 0 | 5K | OG1 | B | T-069 | 2024-04-05 | [7 empty] | 2024-05-13 |  |  | 2024-05-15 | 0 | 262 | 365 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48243 | CIPV-2-000-005-32-SP | 1 | true | CH06822004-BD-PI-0523 | 0 | 5K | EG | H3 | T-069 | 2024-04-05 | [7 empty] | 2024-04-30 |  |  | 2024-06-07 | 7.4 | 262 | 367 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48244 | CO2F-7-600-008-15-SP | 1 | true | CH06822004-BD-PI-0449 | 0 | 5K | OG1 | N/A | T-069 | 2024-04-05 | [7 empty] | 2024-06-11 |  |  | 2024-06-13 | 0.4 | 262 | 369 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48245 | CO2F-7-600-009-15-SP | 1 | true | CH06822004-BD-PI-0449 | 0 | 5K | OG1 | N/A | T-069 | 2024-04-05 | [7 empty] | 2024-06-11 |  |  | 2024-06-13 | 0.5 | 262 | 369 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48246 | CO2F-7-600-010-15-SP | 1 | true | CH06822004-BD-PI-0449 | 0 | 5K | OG1 | N/A | T-069 | 2024-04-05 | [7 empty] | 2024-06-11 |  |  | 2024-06-13 | 0.5 | 262 | 369 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48247 | CSL-7-201-032-40-SP | 1 | false | CH06822004-BD-PI-1179 | 0 | 5K | OG1 | H2 | T-069 | 2024-04-05 | [11 empty] | 7.2 | 262 | 373 | [6 empty] | 0 | SEP | SEP
48248 | CSL-7-201-032-40-SP | 1 | false | CH06822004-BD-PI-1179 | 0 | 5K | OG1 | H2 | T-069 | 2024-04-05 | [11 empty] | 3 | 262 | 373 | [6 empty] | 0 | SEP | SEP
48453 | CSL-7-201-032-40-SP | 3 | true | CH06822004-BD-PI-1179 | 0 | 5K | OG1 | H2 | T-073 | 2024-04-11 | [7 empty] | 2024-06-28 |  |  | 2024-09-18 | 7.8 | 262 | 373 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48454 | CSL-7-201-032-40-SP | 3 | true | CH06822004-BD-PI-1179 | 0 | 5K | OG1 | H2 | T-073 | 2024-04-11 | [7 empty] | 2024-06-28 |  |  | 2024-09-18 | 3 | 262 | 373 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48249 | CSL-7-201-034-25-SP | 1 | true | CH06822004-BD-PI-1179 | 0 | 5K | OG1 | H2 | T-069 | 2024-04-05 | [7 empty] | 2024-06-28 |  |  | 2024-07-11 | 14.4 | 262 | 373 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48250 | CSL-7-201-034-25-SP | 1 | true | CH06822004-BD-PI-1179 | 0 | 5K | OG1 | H2 | T-069 | 2024-04-05 | [7 empty] | 2024-06-28 |  |  | 2024-07-11 | 5.5 | 262 | 373 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48251 | CSL-7-201-035-25-SP | 1 | true | CH06822004-BD-PI-1179 | 0 | 5K | OG1 | H2 | T-069 | 2024-04-05 | [7 empty] | 2024-06-28 |  |  | 2024-07-23 | 8.4 | 262 | 373 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48252 | CSL-7-201-035-25-SP | 1 | true | CH06822004-BD-PI-1179 | 0 | 5K | OG1 | H2 | T-069 | 2024-04-05 | [7 empty] | 2024-06-28 |  | 2024-07-23 | 2024-09-17 | 3.6 | 262 | 373 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48253 | CSL-7-201-037-15-SP | 1 | true | CH06822004-BD-PI-1179 | 0 | 5K | OG1 | H3 | T-069 | 2024-04-05 | [7 empty] | 2024-06-28 |  |  | 2024-07-17 | 4.1 | 262 | 373 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48254 | CSL-7-201-037-15-SP | 1 | true | CH06822004-BD-PI-1179 | 0 | 5K | OG1 | H3 | T-069 | 2024-04-05 | [7 empty] | 2024-06-28 |  |  | 2024-07-17 | 1.5 | 262 | 373 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48255 | CSL-7-201-038-15-SP | 1 | true | CH06822004-BD-PI-1179 | 0 | 5K | OG1 | H2 | T-069 | 2024-04-05 | [7 empty] | 2024-06-28 |  |  | 2024-07-30 | 0.4 | 262 | 373 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48256 | DKA-7-400-010-15-SD1 | 1 | true | CH06822004-BD-PI-0893 | 0 | 5K | OG1 | B | T-069 | 2024-04-05 | [7 empty] | 2024-04-24 |  |  | 2024-07-08 | 0.4 | 258 | 376 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48257 | DKA-7-400-021-20-SD1 | 1 | true | CH06822004-BD-PI-1179 | 0 | 5K | OG1 | B | T-069 | 2024-04-05 | [7 empty] | 2024-06-28 |  |  | 2024-07-03 | 1.4 | 258 | 376 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48258 | DKA-7-400-024-32-SD1 | 1 | true | CH06822004-BD-PI-1179 | 0 | 5K | OG1 | B | T-069 | 2024-04-05 | [7 empty] | 2024-04-24 |  |  | 2024-07-05 | 1.1 | 258 | 376 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48259 | DKA-7-400-026-20-SD1 | 1 | true | CH06822004-BD-PI-1179 | 0 | 5K | OG1 | B | T-069 | 2024-04-05 | [7 empty] | 2024-04-24 |  |  | 2024-07-05 | 2 | 258 | 376 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48260 | DKA-7-400-027-15-SD1 | 1 | true | CH06822004-BD-PI-1179 | 0 | 5K | OG1 | B | T-069 | 2024-04-05 | [7 empty] | 2024-08-28 |  |  | 2024-09-05 | 0.1 | 258 | 376 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48261 | DKA-7-400-028-15-SD1 | 1 | true | CH06822004-BD-PI-1179 | 0 | 5K | EG | B | T-069 | 2024-04-05 | [7 empty] | 2024-08-28 |  |  | 2024-09-13 | 0.1 | 258 | 376 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48262 | DKA-7-400-115-15-SD1 | 1 | true | CH06822004-BD-PI-1179 | 0 | 5K | OG1 | B | T-069 | 2024-04-05 | [7 empty] | 2024-04-24 |  |  | 2024-07-30 | 2.7 | 258 | 376 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48263 | DKA-7-400-116-15-SD1 | 1 | true | CH06822004-BD-PI-1179 | 0 | 5K | OG1 | B | T-069 | 2024-04-05 | [7 empty] | 2024-04-24 |  |  | 2024-07-30 | 6.1 | 258 | 376 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48264 | DKA-7-400-117-15-SD1 | 1 | true | CH06822004-BD-PI-1179 | 0 | 5K | OG1 | B | T-069 | 2024-04-05 | [7 empty] | 2024-08-28 |  |  | 2024-09-06 | 0.1 | 258 | 376 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48265 | DKA-7-400-118-15-SD1 | 1 | true | CH06822004-BD-PI-1179 | 0 | 5K | OG1 | B | T-069 | 2024-04-05 | [7 empty] | 2024-08-28 |  |  | 2024-09-13 | 0.1 | 258 | 376 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48266 | DKA-7-400-215-15-SD1 | 1 | false | CH06822004-BD-PI-1435 | 0 | 5K | EG | B | T-069 | 2024-04-05 | [7 empty] | 2024-04-24 |  |  |  | 0.4 | 258 | 376 | Jozef Kotul | [5 empty] | 0 | SEP | SEP
49720 | DKA-7-400-215-15-SD1 | 2 | true | CH06822004-BD-PI-1435 | 0 | 5K | EG | B | T-077 | 2024-04-25 | [7 empty] | 2024-06-26 |  |  | 2024-07-05 | 0.5 | 258 | 376 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
49721 | DKA-7-400-215-15-SD1 | 2 | true | CH06822004-BD-PI-1435 | 0 | 5K | EG | B | T-077 | 2024-04-25 | [7 empty] | 2024-06-26 |  |  | 2024-07-05 | 5 | 258 | 376 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48267 | DKS-7-401-009-15-SD1 | 1 | true | CH06822004-BD-PI-1179 | 0 | 5K | OG1 | B | T-069 | 2024-04-05 | [7 empty] | 2024-06-26 |  |  | 2024-07-04 | 3.2 | 258 | 378 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48268 | DKS-7-401-010-15-SD1 | 1 | true | CH06822004-BD-PI-1179 | 0 | 5K | OG1 | B | T-069 | 2024-04-05 | [7 empty] | 2024-05-13 |  |  | 2024-05-15 | 0 | 258 | 378 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48269 | DKS-7-401-039-15-SD1 | 1 | true | CH06822004-BD-PI-1179 | 0 | 5K | OG1 | B | T-069 | 2024-04-05 | [7 empty] | 2024-06-26 |  |  | 2024-07-04 | 0.5 | 258 | 378 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48270 | DKS-7-401-041-15-SD1 | 1 | true | CH06822004-BD-PI-1179 | 0 | 5K | OG1 | B | T-069 | 2024-04-05 | [7 empty] | 2024-06-25 |  |  | 2024-07-04 | 1.2 | 258 | 378 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48271 | DKS-7-401-042-15-SD1 | 1 | true | CH06822004-BD-PI-1179 | 0 | 5K | OG1 | B | T-069 | 2024-04-05 | [7 empty] | 2024-06-25 |  |  | 2024-07-04 | 5.8 | 258 | 378 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48273 | DLF-7-831-029-15-SP1 | 1 | false | CH06822004-BD-PI-0537 | 0 | 5K | OG1 |  | T-069 | 2024-04-05 | [11 empty] | 0.7 | 264 | 380 | [6 empty] | 0 | SEP | SEP
48456 | DLF-7-831-029-15-SP1 | 1 | false | CH06822004-BD-PI-0537 | 0 | 5K | OG1 |  | T-073 | 2024-04-11 | [11 empty] | 0.9 | 264 | 380 | [6 empty] | 0 | SEP | SEP
50180 | DLF-7-831-029-15-SP1 | 2 | true | CH06822004-BD-PI-0537 | 0 | 5K | OG1 |  | T-080 | 2024-05-01 | [7 empty] | 2024-05-21 |  |  | 2024-05-30 | 0 | 264 | 380 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48279 | DLF-7-831-051-15-SP1 | 1 | false |  | 0 | 5K | N/A | N/A | T-069 | 2024-04-05 | [11 empty] | 2 | 264 | 380 |  |  |  |  | HOLD |  | 0 | SEP | SEP
50181 | DLF-7-831-051-15-SP1 | 2 | true |  | 0 | 5K | N/A | N/A | T-080 | 2024-05-01 | [7 empty] | 2024-06-18 |  |  | 2024-05-30 | 5 | 264 | 380 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48280 | DLF-7-831-052-15-SP1 | 1 | false | CH06822004-BD-PI-0537 | 0 | 5K | OG1 | N/A | T-069 | 2024-04-05 | [11 empty] | 3.6 | 264 | 380 | [6 empty] | 0 | SEP | SEP
48281 | DLF-7-831-052-15-SP1 | 1 | false | CH06822004-BD-PI-0537 | 0 | 5K | OG1 | N/A | T-069 | 2024-04-05 | [11 empty] | 5.2 | 264 | 380 | [6 empty] | 0 | SEP | SEP
50534 | DLF-7-831-052-15-SP1 | 2 | true | CH06822004-BD-PI-0537 | 0 | 5K | OG1 | N/A | T-081 | 2024-05-13 | [7 empty] | 2024-05-21 |  |  | 2024-05-29 | 3.6 | 264 | 380 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
50535 | DLF-7-831-052-15-SP1 | 2 | true | CH06822004-BD-PI-0537 | 0 | 5K | OG1 | N/A | T-081 | 2024-05-13 | [7 empty] | 2024-05-21 | 2024-07-23 |  | 2024-08-22 | 5.2 | 264 | 380 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48282 | DLP-7-301-030-20-SP1 | 1 | true | CH06822004-BD-PI-0544 | 0 | 5K | OG1 | N/A | T-069 | 2024-04-05 | [7 empty] | 2024-05-23 |  |  | 2024-07-15 | 6.7 | 262 | 382 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48283 | DLP-7-301-031-20-SP1 | 1 | true | CH06822004-BD-PI-0544 | 0 | 5K | OG1 | N/A | T-069 | 2024-04-05 | [7 empty] | 2024-05-01 |  |  | 2024-06-18 | 0.1 | 262 | 382 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48284 | DLP-7-301-033-20-SP1 | 1 | false | CH06822004-BD-PI-0544 | 0 | 5K | OG1 | N/A | T-069 | 2024-04-05 | [11 empty] | 4.6 | 262 | 382 | [6 empty] | 0 | SEP | SEP
48285 | DLP-7-301-033-20-SP1 | 1 | false | CH06822004-BD-PI-0544 | 0 | 5K | OG1 | N/A | T-069 | 2024-04-05 | [11 empty] | 5.3 | 262 | 382 | [6 empty] | 0 | SEP | SEP
48462 | DLP-7-301-033-20-SP1 | 2 | true | CH06822004-BD-PI-0544 | 0 | 5K | OG1 | N/A | T-073 | 2024-04-11 | [7 empty] | 2024-05-01 |  | 2024-05-25 | 2024-06-18 | 4.3 | 262 | 382 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48463 | DLP-7-301-033-20-SP1 | 2 | true | CH06822004-BD-PI-0544 | 0 | 5K | OG1 | N/A | T-073 | 2024-04-11 | [7 empty] | 2024-05-01 |  | 2024-05-25 | 2024-09-05 | 5.5 | 262 | 382 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48286 | DLP-7-301-041-20-SP1 | 1 | true | CH06822004-BD-PI-0544 | 0 | 5K | OG1 | N/A | T-069 | 2024-04-05 | [7 empty] | 2024-05-01 | 2024-05-25 |  | 2024-09-04 | 7.7 | 262 | 382 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48287 | DLP-7-301-042-20-SP1 | 1 | true | CH06822004-BD-PI-0544 | 0 | 5K | OG1 | N/A | T-069 | 2024-04-05 | [7 empty] | 2024-05-01 |  |  | 2024-06-18 | 0.1 | 262 | 382 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48288 | DLP-7-301-043-20-SP1 | 1 | true | CH06822004-BD-PI-0544 | 0 | 5K | OG1 | N/A | T-069 | 2024-04-05 | [7 empty] | 2024-05-23 |  |  | 2024-06-26 | 0 | 262 | 382 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48289 | KR-0-216-048-25-SD1 | 1 | true | CH06822004-BD-PI-0607 | 0 | 5K | OG1 | C2 | T-069 | 2024-04-05 | [7 empty] | 2024-06-07 |  | 2024-06-27 | 2024-07-13 | 6.9 | 258 | 393 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48290 | KR-0-216-048-25-SD1 | 1 | true | CH06822004-BD-PI-0607 | 0 | 5K | OG1 | C2 | T-069 | 2024-04-05 | [7 empty] | 2024-06-07 |  |  | 2024-06-21 | 1.5 | 258 | 393 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48291 | KV-0-216-048-25-SD1 | 1 | true | CH06822004-BD-PI-0607 | 0 | 5K | OG1 | C2 | T-069 | 2024-04-05 | [7 empty] | 2024-06-07 |  | 2024-06-27 | 2024-07-13 | 7.8 | 258 | 394 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48292 | PROD-2-001-221-32-SP | 1 | true |  | 0 | 5K | OG1 | B | T-069 | 2024-04-05 | [7 empty] | 2024-07-23 |  |  | 2024-09-13 | 1.5 | 262 | 403 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48293 | PROD-2-001-260-32-SP | 1 | true |  | 0 | 5K | OG1 | B | T-069 | 2024-04-05 | [7 empty] | 2024-08-20 |  |  | 2024-09-06 | 4 | 262 | 403 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48294 | PROD-2-001-287-25-SP | 1 | true |  | 0 | 5K | OG1 | B | T-069 | 2024-04-05 | [7 empty] | 2024-08-20 |  |  | 2024-09-17 | 1.4 | 262 | 403 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48295 | PROD-2-001-297-25-SP | 1 | true |  | 0 | 5K | OG1 | B | T-069 | 2024-04-05 | [7 empty] | 2024-08-09 |  |  | 2024-09-10 | 5.1 | 262 | 403 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48296 | PROD-2-001-995-25-SP | 1 | true |  | 0 | 5K | OG1 | H3 | T-069 | 2024-04-05 | [7 empty] | 2024-08-20 |  |  | 2024-09-17 | 11.8 | 262 | 403 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48297 | PROD-2-001-996-25-SP | 1 | true |  | 0 | 5K | EG | H3 | T-069 | 2024-04-05 | [7 empty] | 2024-07-23 | 2024-08-24 |  | 2024-09-12 | 11 | 262 | 403 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48298 | PROD-2-001-997-32-SP | 1 | true |  | 0 | 5K | EG | H3 | T-069 | 2024-04-05 | [7 empty] | 2024-08-09 | 2024-08-24 |  | 2024-09-17 | 4.5 | 262 | 403 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48299 | PROD-2-001-998-32-SP | 1 | true |  | 0 | 5K | OG1 | B | T-069 | 2024-04-05 | [7 empty] | 2024-08-20 |  |  | 2024-09-09 | 0.4 | 262 | 403 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48300 | PROD-2-001-999-32-SP | 1 | true |  | 0 | 5K | OG1 | H3 | T-069 | 2024-04-05 | [7 empty] | 2024-07-17 |  |  | 2024-07-23 | 3.7 | 262 | 403 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48301 | PROD-2-001-999-32-SP | 1 | true |  | 0 | 5K | OG1 | H3 | T-069 | 2024-04-05 | [7 empty] | 2024-07-17 |  |  | 2024-07-23 | 7.2 | 262 | 403 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48302 | PROD-2-001-999-32-SP | 1 | true |  | 0 | 5K | OG1 | H3 | T-069 | 2024-04-05 | [7 empty] | 2024-07-17 |  | 2024-07-23 | 2024-09-17 | 5.8 | 262 | 403 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48303 | DKA-7-400-125-15-SD1 | 1 | true | CH06822004-BD-PI-0923 | 0 | 5K | EG | B | T-069 | 2024-04-05 | [7 empty] | 2024-04-24 |  |  | 2024-06-12 | 1.8 | 258 | 376 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48304 | DKS-7-401-126-15-SD1 | 1 | true | CH06822004-BD-PI-0923 | 0 | 5K | EG | B | T-069 | 2024-04-05 | [7 empty] | 2024-06-26 |  |  | 2024-07-03 | 2.1 | 258 | 378 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48305 | TMG-2-001-171-40-SD | 1 | true | 00053.15.QDW.00003 | 0 | 5K | OG1 | B | T-069 | 2024-04-05 | [7 empty] | 2024-08-20 | 2024-08-24 |  | 2024-09-05 | 6.8 | 271 | 500 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48306 | TMG-2-001-172-40-SD | 1 | true | 00053.15.QDW.00003 | 0 | 5K | OG1 | B | T-069 | 2024-04-05 | [7 empty] | 2024-08-20 | 2024-08-24 |  | 2024-09-05 | 3.1 | 271 | 500 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48307 | WA-ETOH-7-500-122-25-SD1 | 1 | true | CH06822004-BD-PI-0923 | 0 | 5K | EG | B | T-069 | 2024-04-05 | [7 empty] | 2024-05-27 |  |  | 2024-06-04 | 0.1 | 258 | 412 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48308 | WAI-7-201-062-25-SD1 | 1 | true | CH06822004-BD-PI-0923 | 0 | 5K | EG | B | T-069 | 2024-04-05 | [7 empty] | 2024-05-30 |  |  | 2024-06-18 | 1.5 | 258 | 413 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48309 | WAI-7-201-062-25-SD1 | 1 | true | CH06822004-BD-PI-0923 | 0 | 5K | EG | B | T-069 | 2024-04-05 | [7 empty] | 2024-05-30 |  |  | 2024-06-18 | 0.9 | 258 | 413 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48310 | WA-ETOH-7-500-142-25-SD1 | 1 | true | CH06822004-BD-PI-0935 | 0 | 5K | EG | B | T-069 | 2024-04-05 | [7 empty] | 2024-05-27 |  |  | 2024-06-04 | 0.1 | 258 | 412 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48311 | DKA-7-400-145-15-SD1 | 1 | true | CH06822004-BD-PI-0935 | 0 | 5K | EG | B | T-069 | 2024-04-05 | [7 empty] | 2024-06-19 |  |  | 2024-06-25 | 1.4 | 258 | 376 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48312 | DKS-7-401-146-15-SD1 | 1 | true | CH06822004-BD-PI-0935 | 0 | 5K | EG | B | T-069 | 2024-04-05 | [7 empty] | 2024-06-26 |  |  | 2024-07-03 | 2 | 258 | 378 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48313 | WAI-7-201-190-10-SD1 | 1 | true | CH06822004-BD-PI-0923 | 0 | 5K | EG | B | T-069 | 2024-04-05 | [7 empty] | 2024-06-11 |  |  | 2024-06-13 | 0.3 | 258 | 413 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48314 | WAI-7-201-078-25-SD1 | 1 | true | CH06822004-BD-PI-0923 | 0 | 5K | EG | B | T-069 | 2024-04-05 | [7 empty] | 2024-05-30 |  |  | 2024-06-07 | 0.1 | 258 | 413 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48315 | WAI-7-201-061-25-SD1 | 1 | true | CH06822004-BD-PI-0935 | 0 | 5K | EG | B | T-069 | 2024-04-05 | [7 empty] | 2024-05-30 |  |  | 2024-06-18 | 2.2 | 258 | 413 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48316 | WAI-7-201-061-25-SD1 | 1 | true | CH06822004-BD-PI-0935 | 0 | 5K | EG | B | T-069 | 2024-04-05 | [7 empty] | 2024-05-30 |  |  | 2024-06-18 | 0.9 | 258 | 413 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48317 | DKA-7-400-165-15-SD1 | 1 | true | CH06822004-BD-PI-0947 | 0 | 5K | EG | B | T-069 | 2024-04-05 | [7 empty] | 2024-04-24 |  |  | 2024-06-12 | 1.3 | 258 | 376 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48318 | DKS-7-401-166-15-SD1 | 1 | true | CH06822004-BD-PI-0947 | 0 | 5K | EG | B | T-069 | 2024-04-05 | [7 empty] | 2024-06-27 |  |  | 2024-07-04 | 1.8 | 258 | 378 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48319 | WA-ETOH-7-500-162-25-SD1 | 1 | true | CH06822004-BD-PI-0947 | 0 | 5K | EG | B | T-069 | 2024-04-05 | [7 empty] | 2024-05-27 |  |  | 2024-06-04 | 0.1 | 258 | 412 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48320 | WAI-7-201-077-25-SD1 | 1 | true | CH06822004-BD-PI-0935 | 0 | 5K | EG | B | T-069 | 2024-04-05 | [7 empty] | 2024-05-30 |  |  | 2024-06-07 | 0.1 | 258 | 413 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48321 | WAI-7-201-191-10-SD1 | 1 | true | CH06822004-BD-PI-0935 | 0 | 5K | EG | B | T-069 | 2024-04-05 | [7 empty] | 2024-06-11 |  |  | 2024-06-13 | 0.3 | 258 | 413 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48322 | WAI-7-201-080-25-SD1 | 1 | true | CH06822004-BD-PI-0947 | 0 | 5K | EG | B | T-069 | 2024-04-05 | [7 empty] | 2024-05-30 |  |  | 2024-06-13 | 0.1 | 258 | 413 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48323 | WAI-7-201-085-25-SD1 | 1 | true | CH06822004-BD-PI-0947 | 0 | 5K | EG | B | T-069 | 2024-04-05 | [7 empty] | 2024-05-30 |  |  | 2024-06-18 | 1.7 | 258 | 413 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48324 | WAI-7-201-085-25-SD1 | 1 | true | CH06822004-BD-PI-0947 | 0 | 5K | EG | B | T-069 | 2024-04-05 | [7 empty] | 2024-05-30 |  |  | 2024-06-18 | 0.9 | 258 | 413 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48325 | DKA-7-400-185-15-SD1 | 1 | true | CH06822004-BD-PI-0959 | 0 | 5K | EG | B | T-069 | 2024-04-05 | [7 empty] | 2024-04-24 |  |  | 2024-06-12 | 1.9 | 258 | 376 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48326 | DKS-7-401-186-15-SD1 | 1 | true | CH06822004-BD-PI-0959 | 0 | 5K | EG | B | T-069 | 2024-04-05 | [7 empty] | 2024-06-26 |  |  | 2024-07-04 | 2.9 | 258 | 378 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48327 | WA-ETOH-7-500-182-25-SD1 | 1 | true | CH06822004-BD-PI-0959 | 0 | 5K | EG | B | T-069 | 2024-04-05 | [7 empty] | 2024-05-27 |  |  | 2024-06-04 | 0.1 | 258 | 412 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48328 | WAI-7-201-056-25-SD1 | 1 | true | CH06822004-BD-PI-0959 | 0 | 5K | EG | B | T-069 | 2024-04-05 | [7 empty] | 2024-05-30 |  |  | 2024-06-12 | 3.1 | 258 | 413 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48329 | WAI-7-201-192-10-SD1 | 1 | true | CH06822004-BD-PI-0947 | 0 | 5K | EG | B | T-069 | 2024-04-05 | [7 empty] | 2024-06-11 |  |  | 2024-06-13 | 0.3 | 258 | 413 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48390 | DKS-7-401-196-15-SD1 | 1 | true | CH06822004-BD-PI-1429 | 0 | 5K | EG | B | T-069 | 2024-04-05 | [7 empty] | 2024-06-26 |  |  | 2024-07-03 | 3.1 | 258 | 378 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48391 | WA-ETOH-7-500-192-25-SD1 | 1 | true | CH06822004-BD-PI-1429 | 0 | 5K | EG | B | T-069 | 2024-04-05 | [7 empty] | 2024-05-27 |  |  | 2024-06-04 | 0.1 | 258 | 412 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48392 | WAI-7-201-057-40-SD1 | 1 | true | CH06822004-BD-PI-0959 | 0 | 5K | EG | B | T-069 | 2024-04-05 | [7 empty] | 2024-05-30 |  |  | 2024-06-07 | 0.1 | 258 | 413 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48393 | WAI-7-201-193-10-SD1 | 1 | true | CH06822004-BD-PI-0959 | 0 | 5K | EG | B | T-069 | 2024-04-05 | [7 empty] | 2024-06-11 |  |  | 2024-06-13 | 0.4 | 258 | 413 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48394 | WAI-7-201-195-10-SD1 | 1 | true | CH06822004-BD-PI-1460 | 0 | 5K | EG | B | T-069 | 2024-04-05 | [7 empty] | 2024-06-11 |  |  | 2024-06-13 | 0.3 | 258 | 413 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48335 | DKA-7-400-195-15-SD1 | 1 | true | CH06822004-BD-PI-1429 | 0 | 5K | EG | B | T-069 | 2024-04-05 | [7 empty] | 2024-04-24 |  |  | 2024-06-12 | 2.4 | 258 | 376 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48336 | WAI-7-201-054-25-SD1 | 1 | true | CH06822004-BD-PI-1429 | 0 | 5K | EG | B | T-069 | 2024-04-05 | [7 empty] | 2024-05-30 |  |  | 2024-06-12 | 2.9 | 258 | 413 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48337 | WAI-7-201-054-25-SD1 | 1 | true | CH06822004-BD-PI-1429 | 0 | 5K | EG | B | T-069 | 2024-04-05 | [7 empty] | 2024-05-30 |  |  | 2024-06-12 | 0.9 | 258 | 413 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48338 | DKA-7-400-245-15-SD1 | 1 | true | CH06822004-BD-PI-1460 | 0 | 5K | EG | B | T-069 | 2024-04-05 | [7 empty] | 2024-04-24 |  |  | 2024-06-12 | 2.1 | 258 | 376 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48339 | DKS-7-401-246-15-SD1 | 1 | true | CH06822004-BD-PI-1460 | 0 | 5K | EG | B | T-069 | 2024-04-05 | [7 empty] | 2024-06-26 |  |  | 2024-07-04 | 2 | 258 | 378 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48340 | WA-ETOH-7-500-242-25-SD1 | 1 | true | CH06822004-BD-PI-1460 | 0 | 5K | EG | B | T-069 | 2024-04-05 | [7 empty] | 2024-05-27 |  |  | 2024-06-04 | 0.1 | 258 | 412 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48341 | WAI-7-201-055-40-SD1 | 1 | true | CH06822004-BD-PI-1429 | 0 | 5K | EG | B | T-069 | 2024-04-05 | [7 empty] | 2024-05-30 |  |  | 2024-06-07 | 0.1 | 258 | 413 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48342 | WAI-7-201-194-10-SD1 | 1 | true | CH06822004-BD-PI-1429 | 0 | 5K | EG | B | T-069 | 2024-04-05 | [7 empty] | 2024-06-11 |  |  | 2024-06-13 | 0.2 | 258 | 413 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48343 | WAA-2-001-648-8-SD1 | 1 | true | 00053.14.QDW.00002 | 0 | 5K | OG1 | B | T-069 | 2024-04-05 | [7 empty] | 2024-06-18 |  |  | 2024-09-05 | 0.1 | 258 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48344 | WAA-7-931-035-40-SD1 | 1 | true | CH06822004-BD-PI-0473 | 0 | 5K | OG1 | B | T-069 | 2024-04-05 | [7 empty] | 2024-06-04 |  |  | 2024-06-18 | 0.1 | 258 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48345 | WAA-7-931-061-25-SD1 | 1 | true | CH06822004-BD-PI-0473 | 0 | 5K | OG1 |  | T-069 | 2024-04-05 | [10 empty] | 2024-05-23 | 0 | 258 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48346 | WAA-7-931-062-25-SD1 | 1 | true | CH06822004-BD-PI-1179 | 0 | 5K | OG1 | B | T-069 | 2024-04-05 | [7 empty] | 2024-06-26 |  |  | 2024-07-23 | 1.8 | 258 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48349 | WAA-7-931-062-25-SD1 | 1 | true | CH06822004-BD-PI-1179 | 0 | 5K | OG1 | B | T-069 | 2024-04-05 | [7 empty] | 2024-06-19 |  |  | 2024-07-19 | 5.2 | 258 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48347 | WAI-7-201-053-25-SD1 | 1 | true | CH06822004-BD-PI-1460 | 0 | 5K | EG | B | T-069 | 2024-04-05 | [7 empty] | 2024-05-30 |  |  | 2024-06-18 | 2.7 | 258 | 413 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48348 | WAI-7-201-079-25-SD1 | 1 | true | CH06822004-BD-PI-1460 | 0 | 5K | EG | B | T-069 | 2024-04-05 | [7 empty] | 2024-05-30 |  |  | 2024-06-13 | 0.1 | 258 | 413 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48350 | WAA-7-931-063-40-SD1 | 1 | true | CH06822004-BD-PI-1179 | 0 | 5K | OG1 | B | T-069 | 2024-04-05 | [7 empty] | 2024-06-19 |  |  | 2024-09-10 | 0.9 | 258 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48351 | WAA-7-931-064-15-SD1 | 1 | true | CH06822004-BD-PI-1179 | 0 | 5K | OG1 | B | T-069 | 2024-04-05 | [7 empty] | 2024-06-19 |  |  | 2024-09-04 | 0.3 | 258 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48352 | WAA-7-931-065-40-SD1 | 1 | true | CH06822004-BD-PI-0473 | 0 | 5K | OG1 | N/A | T-069 | 2024-04-05 | [7 empty] | 2024-06-04 |  |  | 2024-06-18 | 0.1 | 258 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48353 | WAA-7-931-066-50-SD1 | 1 | true | CH06822004-BD-PI-1179 | 0 | 5K | OG1 | B | T-069 | 2024-04-05 | [7 empty] | 2024-06-19 |  |  | 2024-07-30 | 1.1 | 258 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48354 | WAA-7-931-067-15-SD1 | 1 | true | CH06822004-BD-PI-1179 | 0 | 5K | OG1 | B | T-069 | 2024-04-05 | [7 empty] | 2024-06-19 |  |  | 2024-09-10 | 1.2 | 258 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48355 | WAA-7-931-068-40-SD1 | 1 | true | CH06822004-BD-PI-0473 | 0 | 5K | OG1 | N/A | T-069 | 2024-04-05 | [7 empty] | 2024-06-04 |  |  | 2024-06-18 | 0.1 | 258 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48356 | WAA-7-931-069-40-SD1 | 1 | true | CH06822004-BD-PI-0473 | 0 | 5K | OG1 | N/A | T-069 | 2024-04-05 | [7 empty] | 2024-06-04 |  |  | 2024-06-18 | 0.1 | 258 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48357 | WAA-7-931-070-40-SD1 | 1 | true | CH06822004-BD-PI-0893 | 0 | 5K | OG1 | N/A | T-069 | 2024-04-05 | [7 empty] | 2024-06-04 |  |  | 2024-06-18 | 0.1 | 258 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48358 | WAA-7-931-071-40-SD1 | 1 | true | CH06822004-BD-PI-0473 | 0 | 5K | OG1 | N/A | T-069 | 2024-04-05 | [7 empty] | 2024-06-04 |  |  | 2024-06-18 | 0.1 | 258 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48359 | WAA-7-931-072-40-SD1 | 1 | true | CH06822004-BD-PI-0473 | 0 | 5K | OG1 | N/A | T-069 | 2024-04-05 | [7 empty] | 2024-06-04 |  |  | 2024-06-18 | 0.1 | 258 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48360 | WAA-7-931-073-25-SD1 | 1 | true | CH06822004-BD-PI-1179 | 0 | 5K | OG1 | B | T-069 | 2024-04-05 | [7 empty] | 2024-06-18 |  |  | 2024-07-30 | 2.9 | 258 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48361 | WAA-7-931-073-25-SD1 | 1 | true | CH06822004-BD-PI-1179 | 0 | 5K | OG1 | B | T-069 | 2024-04-05 | [7 empty] | 2024-06-18 |  |  | 2024-07-30 | 0.8 | 258 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48362 | WAA-7-931-076-40-SD1 | 1 | true | CH06822004-BD-PI-1179 | 0 | 5K | OG1 | B | T-069 | 2024-04-05 | [7 empty] | 2024-06-19 |  |  | 2024-09-09 | 2.7 | 258 | 411 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48363 | WAI-7-201-058-40-SD1 | 1 | false | CH06822004-BD-PI-1179 | 0 | 5K | EG | B | T-069 | 2024-04-05 | [11 empty] | 0.1 | 258 | 413 | [6 empty] | 0 | SEP | SEP
49722 | WAI-7-201-058-40-SD1 | 2 | true | CH06822004-BD-PI-1179 | 0 | 5K | EG | B | T-077 | 2024-04-25 | [7 empty] | 2024-05-30 |  |  | 2024-07-03 | 4.7 | 258 | 413 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48364 | WAI-7-201-063-40-SD1 | 1 | true | CH06822004-BD-PI-0642 | 0 | 5K | EG | B | T-069 | 2024-04-05 | [7 empty] | 2024-05-30 |  |  | 2024-06-07 | 0.1 | 258 | 413 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48365 | WAI-7-201-064-32-SD1 | 1 | true | CH06822004-BD-PI-0642 | 0 | 5K | OG1 | B | T-069 | 2024-04-05 | [7 empty] | 2024-05-30 |  |  | 2024-09-10 | 1.8 | 258 | 413 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48366 | WAI-7-201-065-25-SD1 | 1 | true | CH06822004-BD-PI-0642 | 0 | 5K | OG1 | B | T-069 | 2024-04-05 | [7 empty] | 2024-06-18 |  |  | 2024-07-26 | 0.8 | 258 | 413 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48367 | WAI-7-201-075-40-SD1 | 1 | true | CH06822004-BD-PI-0642 | 0 | 5K | OG1 | B | T-069 | 2024-04-05 | [7 empty] | 2024-05-30 |  |  | 2024-09-07 | 1.5 | 258 | 413 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48368 | WAI-7-201-076-15-SD1 | 1 | true | CH06822004-BD-PI-0642 | 0 | 5K | EG | B | T-069 | 2024-04-05 | [7 empty] | 2024-06-18 |  |  | 2024-09-10 | 1.7 | 258 | 413 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48369 | WFIA-7-105-014-25-SP | 1 | true | CH06822004-BD-PI-0473 | 0 | 5K | OG1 | H3 | T-069 | 2024-04-05 | [7 empty] | 2024-06-28 |  |  | 2024-07-19 | 0.4 | 262 | 416 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48370 | WFIA-7-105-014-25-SP | 1 | true | CH06822004-BD-PI-0473 | 0 | 5K | OG1 | H3 | T-069 | 2024-04-05 | [7 empty] | 2024-06-28 |  |  | 2024-09-09 | 2.7 | 262 | 416 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48371 | WFIA-7-105-014-25-SP | 1 | true | CH06822004-BD-PI-0473 | 0 | 5K | OG1 | H3 | T-069 | 2024-04-05 | [7 empty] | 2024-06-28 |  |  | 2024-07-30 | 0.8 | 262 | 416 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48372 | WFIA-7-105-016-40-SP | 1 | true | CH06822004-BD-PI-0473 | 0 | 5K | OG1 | H3 | T-069 | 2024-04-05 | [7 empty] | 2024-06-21 |  |  | 2024-06-28 | 6.4 | 264 | 416 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48373 | WFIA-7-105-016-40-SP | 1 | true | CH06822004-BD-PI-0473 | 0 | 5K | OG1 | H3 | T-069 | 2024-04-05 | [7 empty] | 2024-06-21 |  |  | 2024-06-28 | 6.6 | 264 | 416 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48374 | WFIA-7-105-017-40-SP | 1 | true | CH06822004-BD-PI-0473 | 0 | 5K | OG1 | H3 | T-069 | 2024-04-05 | [7 empty] | 2024-06-25 |  |  | 2024-07-09 | 2.2 | 262 | 416 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48375 | WFIA-7-105-017-40-SP | 1 | true | CH06822004-BD-PI-0473 | 0 | 5K | OG1 | H3 | T-069 | 2024-04-05 | [7 empty] | 2024-06-25 |  |  | 2024-08-08 | 10.2 | 262 | 416 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48377 | WFIA-7-105-018-40-SP | 1 | true | CH06822004-BD-PI-0473 | 0 | 5K | OG1 | H3 | T-069 | 2024-04-05 | [7 empty] | 2024-06-28 |  |  | 2024-07-09 | 5 | 264 | 416 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48378 | WFIA-7-105-018-40-SP | 1 | true | CH06822004-BD-PI-0473 | 0 | 5K | OG1 | H3 | T-069 | 2024-04-05 | [7 empty] | 2024-06-28 |  |  | 2024-07-09 | 2.4 | 264 | 416 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48379 | WFIA-7-105-019-20-SP | 1 | true | CH06822004-BD-PI-0473 | 0 | 5K | OG1 | H3 | T-069 | 2024-04-05 | [7 empty] | 2024-06-28 |  |  | 2024-08-20 | 4.4 | 262 | 416 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48380 | WFIA-7-105-019-20-SP | 1 | true | CH06822004-BD-PI-0473 | 0 | 5K | OG1 | H3 | T-069 | 2024-04-05 | [7 empty] | 2024-06-28 |  |  | 2024-07-30 | 0.4 | 262 | 416 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48381 | WFI-7-811-770-40-SP1 | 1 | true | 00010.22.QDW.00008 | 0 | 5K | UG | H3 | T-069 | 2024-04-05 | [7 empty] | 2024-06-28 |  |  | 2024-08-15 | 1.7 | 264 | 414 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48384 | WFI-7-811-770-40-SP1 | 1 | true | 00010.22.QDW.00008 | 0 | 5K | UG | H3 | T-069 | 2024-04-05 | [7 empty] | 2024-06-28 |  |  | 2024-07-15 | 5.8 | 264 | 414 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48382 | WFIA-7-105-020-20-SP | 1 | true | CH06822004-BD-PI-0473 | 0 | 5K | OG1 | B | T-069 | 2024-04-05 | [7 empty] | 2024-06-28 |  |  | 2024-07-22 | 0.2 | 264 | 416 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48383 | WFI-7-810-715-40-SP1 | 1 | false | 00010.22.QDW.00008 | 0 | 5K | UG | H3 | T-069 | 2024-04-05 | [11 empty] | 1.1 | 264 | 414 | [6 empty] | 0 | SEP | SEP
49690 | WFI-7-810-715-40-SP1 | 2 | true | 00010.22.QDW.00008 | 0 | 5K | UG | H3 | T-077 | 2024-04-25 | [7 empty] | 2024-06-28 |  |  | 2024-07-15 | 1.1 | 264 | 414 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48385 | WFI-7-811-772-40-SP1 | 1 | true | 00010.22.QDW.00008 | 0 | 5K | UG | H3 | T-069 | 2024-04-05 | [7 empty] | 2024-06-28 |  |  | 2024-07-09 | 0.5 | 264 | 414 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48386 | WFIA-7-811-764-40-SP1 | 1 | true | 00010.22.QDW.00008 | 0 | 5K | UG | H3 | T-069 | 2024-04-10 | [7 empty] | 2024-06-28 |  |  | 2024-07-09 | 4.7 | 264 | 416 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48387 | WFIA-7-811-768-32-SP1 | 1 | true | 00010.22.QDW.00008 | 0 | 5K | UG | H3 | T-069 | 2024-04-10 | [7 empty] | 2024-06-28 |  |  | 2024-08-15 | 2.8 | 264 | 416 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48388 | WFIA-7-811-768-32-SP1 | 1 | true | 00010.22.QDW.00008 | 0 | 5K | UG | H3 | T-069 | 2024-04-10 | [7 empty] | 2024-06-28 |  |  | 2024-08-15 | 0.2 | 264 | 416 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48389 | WFIA-7-811-779-40-SP1 | 1 | true | 00010.22.QDW.00008 | 0 | 5K | UG | H3 | T-069 | 2024-04-05 | [7 empty] | 2024-06-28 |  |  | 2024-07-09 | 0.1 | 264 | 416 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48434 | CIPV-2-000-013-32-SP | 1 | true | CH06822004-BD-PI-0523 | 0 | 5K | OG1 | B | T-069 | 2024-04-05 | [7 empty] | 2024-06-27 |  |  | 2024-07-15 | 1.2 | 262 | 367 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48455 | DLF-7-831-019-15-SP1 | 1 | true |  | 0 |  |  |  | T-073 | 2024-04-11 | [7 empty] | 2024-05-21 | 2024-07-23 |  | 2024-09-04 | 9.4 | 262 |  | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48457 | DLF-7-831-037-15-SP1 | 1 | true |  | 0 |  |  |  | T-073 | 2024-04-11 | [7 empty] | 2024-05-21 |  | 2024-05-25 | 2024-05-29 | 6.4 | 264 |  | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48458 | DLF-7-831-037-15-SP1 | 1 | true |  | 0 |  |  |  | T-073 | 2024-04-11 | [7 empty] | 2024-05-21 |  |  | 2024-05-29 | 3.4 | 264 |  | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48459 | DLF-7-831-038-15-SP1 | 1 | true |  | 0 |  |  |  | T-073 | 2024-04-11 | [7 empty] | 2024-05-21 | 2024-05-25 |  | 2024-09-04 | 6 | 264 |  | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48460 | DLF-7-831-039-15-SP1 | 1 | true |  | 0 |  |  |  | T-073 | 2024-04-11 | [7 empty] | 2024-05-21 |  |  | 2024-06-10 | 2.9 | 262 |  | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
48461 | DLF-7-831-039-15-SP1 | 1 | true |  | 0 |  |  |  | T-073 | 2024-04-11 | [7 empty] | 2024-05-21 | 2024-07-23 |  | 2024-09-05 | 3.8 | 262 |  | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
49443 | 48272_DLF-7-831-009-15-SP1 | 3 | false |  | 0 |  |  |  | T-069 | 2024-04-04 | [11 empty] | 2 | 264 | [7 empty] | 0
49691 | ARO-7-811-773-65-SD | 1 | true |  | 0 |  |  | C2 | T-077 | 2024-04-25 | [7 empty] | 2024-06-28 |  |  | 2024-07-30 | 2.7 | 271 |  | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
49692 | AROW-7-811-774-65-SD | 1 | true |  | 0 |  |  | H2 | T-077 | 2024-04-25 | [7 empty] | 2024-06-28 | 2024-08-27 |  | 2024-09-13 | 2.3 | 271 |  | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
49693 | AROW-7-811-774-65-SD | 1 | true |  | 0 |  |  | H2 | T-077 | 2024-04-25 | [7 empty] | 2024-06-28 | 2024-08-27 |  | 2024-09-13 | 2.5 | 271 |  | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
49694 | DK4-7-811-224-25-SD | 1 | true |  | 0 |  |  | H2 | T-077 | 2024-04-25 | [10 empty] | 2024-09-23 | 0.9 | 271 |  | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
49695 | DK4-7-811-225-15-SD | 1 | true |  | 0 |  |  | H2 | T-077 | 2024-04-25 | [10 empty] | 2024-08-20 | 0 | 271 |  | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
49696 | DK4-7-811-226-25-SD | 1 | true |  | 0 |  |  | H2 | T-077 | 2024-04-25 | [10 empty] | 2024-08-20 | 5.7 | 271 |  | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
49697 | DK4-7-996-362-25-SD | 1 | true |  | 0 |  |  | H2 | T-077 | 2024-04-25 | [10 empty] | 2024-08-20 | 5.9 | 271 |  | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
49698 | DK4-7-996-363-15-SD | 1 | true |  | 0 |  |  | H2 | T-077 | 2024-04-25 | [10 empty] | 2024-08-20 | 0 | 271 |  | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
49699 | KR-7-812-233-80-SD5 | 1 | true |  | 0 |  |  | C2 | T-077 | 2024-04-25 | [7 empty] | 2024-06-27 |  | 2024-07-31 | 2024-08-20 | 2.8 | 260 |  | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
49700 | KR-7-812-233-80-SD5 | 1 | true |  | 0 |  |  | C2 | T-077 | 2024-04-25 | [7 empty] | 2024-06-27 | 2024-08-27 |  | 2024-09-18 | 0.6 | 260 |  | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
49701 | KR-7-812-233-80-SD5 | 1 | true |  | 0 |  |  | C2 | T-077 | 2024-04-25 | [7 empty] | 2024-06-27 |  | 2024-07-31 | 2024-08-20 | 0.9 | 260 |  | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
49702 | KR-7-812-233-80-SD5 | 1 | true |  | 0 |  |  | C2 | T-077 | 2024-04-25 | [7 empty] | 2024-06-27 |  |  | 2024-08-20 | 2.9 | 260 |  | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
49703 | KV-7-992-277-80-SD5 | 1 | true |  | 0 |  |  | C2 | T-077 | 2024-04-25 | [7 empty] | 2024-06-27 |  |  | 2024-07-30 | 2 | 260 |  | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
49704 | US4-7-996-212-25-SD6 | 1 | true |  | 0 |  |  | H2 | T-077 | 2024-04-25 | [7 empty] | 2024-06-19 |  |  | 2024-07-30 | 1.7 | 261 |  | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
49705 | US4-7-996-212-25-SD6 | 1 | true |  | 0 |  |  | H2 | T-077 | 2024-04-25 | [7 empty] | 2024-06-27 |  |  | 2024-09-17 | 2.6 | 261 |  | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
49706 | US4-7-996-212-25-SD6 | 1 | true |  | 0 |  |  | H2 | T-077 | 2024-04-25 | [7 empty] | 2024-06-27 |  |  | 2024-08-20 | 3.4 | 261 |  | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
49707 | WAI-7-811-717-25-SD | 1 | true |  | 0 |  |  |  | T-077 | 2024-04-25 | [7 empty] | 2024-06-28 |  |  | 2024-07-17 | 2 | 271 |  | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
49708 | WAI-7-811-761-15-SD | 1 | true |  | 0 |  |  |  | T-077 | 2024-04-25 | [7 empty] | 2024-06-28 |  |  | 2024-09-18 | 0.9 | 271 |  | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
49709 | WAI-7-811-765-25-SD | 1 | true |  | 0 |  |  |  | T-077 | 2024-04-25 | [7 empty] | 2024-06-28 |  |  | 2024-08-20 | 0.9 | 271 |  | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
49710 | WAI-7-811-769-25-SD | 1 | true |  | 0 |  |  |  | T-077 | 2024-04-25 | [7 empty] | 2024-06-28 |  |  | 2024-07-30 | 1.5 | 271 |  | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
49711 | WAI-7-811-771-25-SD | 1 | true |  | 0 |  |  |  | T-077 | 2024-04-25 | [7 empty] | 2024-06-28 |  |  | 2024-07-19 | 1.4 | 271 |  | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
49712 | WAS-7-811-766-25-SD | 1 | true |  | 0 |  |  |  | T-077 | 2024-04-25 | [7 empty] | 2024-06-28 |  |  | 2024-08-20 | 0.3 | 271 |  | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
49713 | KR-0-216-010-20-SD5 | 1 | true |  | 0 |  |  | C2 | T-077 | 2024-04-25 | [7 empty] | 2024-06-06 |  |  | 2024-07-05 | 0.7 | 260 |  | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
49714 | KR-0-216-011-20-SD5 | 1 | true |  | 0 |  |  | C2 | T-077 | 2024-04-25 | [7 empty] | 2024-06-06 |  |  | 2024-07-03 | 1.6 | 260 |  | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
49715 | KR-0-216-019-20-SD5 | 1 | true |  | 0 |  |  | C2 | T-077 | 2024-04-25 | [7 empty] | 2024-06-06 |  |  | 2024-07-08 | 1.8 | 260 |  | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
49716 | KV-0-216-011-20-SD5 | 1 | true |  | 0 |  |  | C2 | T-077 | 2024-04-25 | [7 empty] | 2024-06-06 |  |  | 2024-07-03 | 1.5 | 260 |  | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
49717 | KV-0-216-012-20-SD5 | 1 | true |  | 0 |  |  | C2 | T-077 | 2024-04-25 | [7 empty] | 2024-06-06 |  |  | 2024-07-03 | 2.1 | 260 |  | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
49718 | KV-0-216-020-20-SD5 | 1 | true |  | 0 |  |  | C2 | T-077 | 2024-04-25 | [7 empty] | 2024-06-06 |  |  | 2024-07-08 | 2.1 | 260 |  | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP
50188 | DLP-7-301-037-40-SP1 | 3 | true | CH06822004-BD-PI-0544 | 0 | 5K | OG1 |  | T-080 | 2024-05-01 | [7 empty] | 2024-05-14 |  |  | 2024-05-21 | 5.3 | 264 | 382 | Virgil Frinculescu | [5 empty] | 0 | SEP | SEP