## ag-grid
Id | Line No. | Rev. | Latest Rev. | Length | Name | PId | Pipe class | PRIOs | HOLD | Building | Floor | Insulation | Transmittal No. | Date Rec. | Spooling | Iss. to prefab | Prefab remarks | Prefab start | Welded | Latest location | Sent to site | Work package | Prefab compl. | Install start | Install 50 | Install 90 | Install compl. | Area | Company | Site remarks | As built | Site checked | Prefab Company | Ped Cat | Ped Cat | Rel. for Insulation | Insulation Start | Insulation 50% | Insulation 90% | Insulated | Insulated | Cladding | Cladding
44325 | 740-MHW-R-VH001-103-LH130-50-0 | 1 | false | 3.61 | 740-MHW-R-VH001-103-LH130-50-0 | LV1-105623.VH001 | 362 | 26.Apr.2024 |  | MC1 | LVL 6 | W60 | TR001 | 2024-02-07 | 2024-02-12 | 2024-03-01 | Connection to AHU correct acc. KO |  |  | Satu Mare | [7 empty] | 796 | 150 |  |  |  | 149 | SEP | SEP
45503 | 740-MHW-R-VH001-103-LH130-50-0 | 2 | true | 3.61 | 740-MHW-R-VH001-103-LH130-50-0 | LV1-105623.VH001 | 362 | 26.Apr.2024 |  | MC1 | LVL 6 | W60 | TR005 | 2024-03-03 | 2024-02-11 | 2024-02-29 | Connection to AHU correct acc. KO | 2024-04-04 | 2024-04-08 | Büro | 2024-04-12 |  | 2024-04-10 | 2024-05-22 |  |  | 2024-05-27 | 796 | 150 |  | 2024-07-10 | 2024-07-04 | 149 | SEP | SEP | 2024-07-10 |  | 2024-07-26 | 2024-07-26
44326 | 740-MHW-R-VH002-103-LH130-40-0 | 1 | false | 3.76 | 740-MHW-R-VH002-103-LH130-40-0 | LV1-105623.VH002 | 362 | 26.Apr.2024 |  | MC1 | LVL 6 | W60 | TR001 | 2024-02-07 | 2024-02-12 | 2024-03-01 |  |  |  | Satu Mare | [7 empty] | 796 | 150 |  |  |  | 149 | SEP | SEP
45504 | 740-MHW-R-VH002-103-LH130-40-0 | 2 | true | 3.76 | 740-MHW-R-VH002-103-LH130-40-0 | LV1-105623.VH002 | 362 | 26.Apr.2024 |  | MC1 | LVL 6 | W60 | TR005 | 2024-03-03 | 2024-02-11 | 2024-02-29 |  | 2024-04-18 | 2024-04-23 | Büro | 2024-04-26 |  | 2024-04-24 | 2024-05-22 |  |  | 2024-05-27 | 796 | 150 |  | 2024-07-10 | 2024-07-04 | 149 | SEP | SEP | 2024-07-10 |  | 2024-07-26 | 2024-07-26
44327 | 740-MHW-R-VH003-103-LH130-20-0 | 1 | false | 5.41 | 740-MHW-R-VH003-103-LH130-20-0 | LV1-105623.VH003 | 362 | 26.Apr.2024 |  | MC1 | LVL 6 | W60 | TR001 | 2024-02-07 | 2024-02-12 | 2024-03-01 |  |  |  | Satu Mare | [7 empty] | 796 | 150 |  |  |  | 149 | SEP | SEP
45505 | 740-MHW-R-VH003-103-LH130-20-0 | 2 | true | 5.41 | 740-MHW-R-VH003-103-LH130-20-0 | LV1-105623.VH003 | 362 | 26.Apr.2024 |  | MC1 | LVL 6 | W60 | TR005 | 2024-03-03 | 2024-02-11 | 2024-02-29 |  | 2024-04-12 | 2024-04-16 | Büro | 2024-04-26 |  | 2024-04-16 | 2024-05-20 |  |  | 2024-05-22 | 796 | 150 |  | 2024-07-10 | 2024-07-04 | 149 | SEP | SEP | 2024-07-10 |  | 2024-07-26 | 2024-07-26
44328 | 740-MHW-R-VH004-103-LH130-20-0 | 1 | false | 4.4 | 740-MHW-R-VH004-103-LH130-20-0 | LV1-105623.VH004 | 362 | 26.Apr.2024 |  | MC1 | LVL 6 | W60 | TR001 | 2024-02-07 | 2024-02-12 | 2024-03-01 |  |  |  | Satu Mare | [7 empty] | 796 | 150 |  |  |  | 149 | SEP | SEP
45506 | 740-MHW-R-VH004-103-LH130-20-0 | 2 | true | 4.4 | 740-MHW-R-VH004-103-LH130-20-0 | LV1-105623.VH004 | 362 | 26.Apr.2024 |  | MC1 | LVL 6 | W60 | TR005 | 2024-03-03 | 2024-02-11 | 2024-02-29 |  | 2024-04-12 | 2024-04-16 | Büro | 2024-04-26 |  | 2024-04-18 | 2024-05-22 |  |  | 2024-05-27 | 796 | 150 |  | 2024-07-10 | 2024-07-04 | 149 | SEP | SEP | 2024-07-10 |  | 2024-07-26 | 2024-07-26
44329 | 740-MHW-R-VH005-103-LH130-25-0 | 1 | false | 3.92 | 740-MHW-R-VH005-103-LH130-25-0 | LV1-105623.VH005 | 362 | 26.Apr.2024 |  | MC1 | LVL 6 | W60 | TR001 | 2024-02-07 | 2024-02-12 | 2024-03-01 | Connection to AHU correct acc. KO |  |  | Satu Mare | [7 empty] | 796 | 150 |  |  |  | 149 | SEP | SEP
45507 | 740-MHW-R-VH005-103-LH130-25-0 | 2 | true | 3.92 | 740-MHW-R-VH005-103-LH130-25-0 | LV1-105623.VH005 | 362 | 26.Apr.2024 |  | MC1 | LVL 6 | W60 | TR005 | 2024-03-03 | 2024-02-11 | 2024-02-29 | Connection to AHU correct acc. KO | 2024-04-12 | 2024-04-16 | Büro | 2024-04-26 |  | 2024-04-17 | 2024-05-08 |  |  | 2024-05-16 | 796 | 150 |  | 2024-07-10 | 2024-07-04 | 149 | SEP | SEP | 2024-07-10 |  | 2024-07-26 | 2024-07-26
44330 | 740-MHW-R-VH005-212-LH130-20-0 | 1 | false | 1.02 | 740-MHW-R-VH005-212-LH130-20-0 | LV0-105624.VH005 | 362 | 26.Apr.2024 |  | MC1 | LVL 6 | W60 | TR001 | 2024-02-07 | 2024-02-12 | 2024-03-01 | Connection to AHU correct acc. KO |  |  | Satu Mare | [7 empty] | 796 | 150 |  |  |  | 149 | SEP | SEP
45508 | 740-MHW-R-VH005-212-LH130-20-0 | 2 | false | 1.02 | 740-MHW-R-VH005-212-LH130-20-0 | LV0-105624.VH005 | 362 | 26.Apr.2024 |  | MC1 | LVL 6 | W60 | TR005 | 2024-03-04 | 2024-02-12 | 2024-03-01 | Connection to AHU correct acc. KO | [10 empty] | 796 | 150 |  |  |  | 149 | SEP | SEP
46734 | 740-MHW-R-VH005-212-LH130-20-0 | 3 | true | 1.02 | 740-MHW-R-VH005-212-LH130-20-0 | LV0-105624.VH005 | 362 | 26.Apr.2024 |  | MC1 | LVL 6 | W60 | TR008 | 2024-03-18 | 2024-03-26 | 2024-03-26 | Connection to AHU correct acc. KO | 2024-04-19 | 2024-04-25 | Büro | 2024-04-26 |  | 2024-04-25 | 2024-05-08 |  |  | 2024-05-14 | 796 | 150 |  | 2024-07-10 | 2024-07-04 | 149 | SEP | SEP | 2024-07-10 |  | 2024-07-26 | 2024-07-26
44331 | 740-MHW-R-VU221-105-LH001-50-0 | 1 | true | 30.73 | 740-MHW-R-VU221-105-LH001-50-0 | LV1-105638.VU221 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | W60 | TR001 | 2024-02-06 | 2024-02-11 | 2024-02-29 |  | 2024-04-05 | 2024-04-08 | Büro | 2024-04-12 |  | 2024-04-11 | 2024-04-26 |  |  | 2024-04-30 | 796 | 150 |  | 2024-07-10 | 2024-07-04 | 149 | SEP | SEP | 2024-07-10 |  | 2024-07-26 | 2024-07-26
44332 | 740-MHW-R-VU221-106-LH001-65-0 | 1 | true | 47.27 | 740-MHW-R-VU221-106-LH001-65-0 | LV1-105638.VU221 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | W60 | TR001 | 2024-02-08 | 2024-02-13 | 2024-03-02 |  | 2024-04-01 | 2024-04-05 | Büro | 2024-04-12 |  | 2024-04-08 | 2024-04-30 |  |  | 2024-05-08 | 796 | 150 |  | 2024-07-10 | 2024-07-04 | 149 | SEP | SEP | 2024-07-10 | 2024-07-26 | 2024-07-26 | 2024-07-26
44333 | 740-MHW-R-VU221-107-LH130-25-0 | 1 | true | 17.02 | 740-MHW-R-VU221-107-LH130-25-0 | LV1-105638.VU221 | 362 | 26.Apr.2024 |  | MC1 | LVL 6 | W60 | TR001 | 2024-02-06 | 2024-02-11 | 2024-02-29 |  | 2024-04-16 | 2024-04-18 | Büro | 2024-04-26 |  | 2024-04-18 | 2024-05-08 |  |  | 2024-05-14 | 796 | 150 |  | 2024-07-10 | 2024-07-04 | 149 | SEP | SEP | 2024-07-10 |  | 2024-07-26 | 2024-07-26
44334 | 740-MHW-S-VH001-101-LH130-50-0 | 1 | true | 0.94 | 740-MHW-S-VH001-101-LH130-50-0 | LV1-105623.VH001 | 362 | 26.Apr.2024 |  | MC1 | LVL 6 | W60 | TR001 | 2024-02-06 | 2024-02-11 | 2024-02-29 | Connection to AHU correct acc. KO | 2024-04-08 | 2024-04-10 | Büro | 2024-04-12 |  | 2024-04-11 | 2024-05-22 |  |  | 2024-05-27 | 796 | 150 |  | 2024-07-10 | 2024-07-10 | 149 | SEP | SEP | 2024-07-10 |  | 2024-07-26 | 2024-07-26
44335 | 740-MHW-S-VH001-102-LH130-50-0 | 1 | false | 2.88 | 740-MHW-S-VH001-102-LH130-50-0 | LV1-105623.VH001 | 362 | 26.Apr.2024 |  | MC1 | LVL 6 | W60 | TR001 | 2024-02-07 | 2024-02-12 | 2024-03-01 |  |  |  | Satu Mare | [7 empty] | 796 | 150 |  |  |  | 149 | SEP | SEP
45509 | 740-MHW-S-VH001-102-LH130-50-0 | 2 | true | 2.88 | 740-MHW-S-VH001-102-LH130-50-0 | LV1-105623.VH001 | 362 | 26.Apr.2024 |  | MC1 | LVL 6 | W60 | TR005 | 2024-03-03 | 2024-02-11 | 2024-02-29 |  | 2024-04-08 | 2024-04-11 | Büro | 2024-04-12 |  | 2024-04-12 | 2024-05-22 |  |  | 2024-05-27 | 796 | 150 |  | 2024-07-10 | 2024-07-04 | 149 | SEP | SEP | 2024-07-10 |  | 2024-07-26 | 2024-07-26 | 2024-09-26 | 2024-09-26
44336 | 740-MHW-S-VH002-101-LH130-40-0 | 1 | true | 1.13 | 740-MHW-S-VH002-101-LH130-40-0 | LV1-105623.VH002 | 362 | 26.Apr.2024 |  | MC1 | LVL 6 | W60 | TR001 | 2024-02-06 | 2024-02-11 | 2024-02-29 |  | 2024-04-18 | 2024-04-22 | Büro | 2024-04-26 |  | 2024-04-23 | 2024-05-22 |  |  | 2024-05-27 | 796 | 150 |  | 2024-07-10 | 2024-07-04 | 149 | SEP | SEP | 2024-07-10 |  | 2024-07-26 | 2024-07-26
44337 | 740-MHW-S-VH002-102-LH130-40-0 | 1 | false | 2.81 | 740-MHW-S-VH002-102-LH130-40-0 | LV1-105623.VH002 | 362 | 26.Apr.2024 |  | MC1 | LVL 6 | W60 | TR001 | 2024-02-07 | 2024-02-12 | 2024-03-01 |  |  |  | Satu Mare | [7 empty] | 796 | 150 |  |  |  | 149 | SEP | SEP
45510 | 740-MHW-S-VH002-102-LH130-40-0 | 2 | true | 2.81 | 740-MHW-S-VH002-102-LH130-40-0 | LV1-105623.VH002 | 362 | 26.Apr.2024 |  | MC1 | LVL 6 | W60 | TR005 | 2024-03-03 | 2024-02-11 | 2024-02-29 |  | 2024-04-12 | 2024-04-15 | Büro | 2024-04-26 |  | 2024-04-17 | 2024-05-22 |  |  | 2024-05-27 | 796 | 150 |  | 2024-07-10 | 2024-07-04 | 149 | SEP | SEP | 2024-07-10 |  | 2024-07-26 | 2024-07-26 | 2024-09-26 | 2024-09-26
44338 | 740-MHW-S-VH003-101-LH130-20-0 | 1 | true | 1.38 | 740-MHW-S-VH003-101-LH130-20-0 | LV1-105623.VH003 | 362 | 26.Apr.2024 |  | MC1 | LVL 6 | W60 | TR001 | 2024-02-06 | 2024-02-11 | 2024-02-29 | Connection to AHU correct acc. KO | 2024-04-19 | 2024-04-22 | Büro | 2024-04-26 |  | 2024-04-22 | 2024-05-20 |  |  | 2024-05-22 | 796 | 150 |  | 2024-07-10 | 2024-07-04 | 149 | SEP | SEP | 2024-07-10 |  | 2024-07-26 | 2024-07-26
44339 | 740-MHW-S-VH003-102-LH130-20-0 | 1 | false | 1.27 | 740-MHW-S-VH003-102-LH130-20-0 | LV1-105623.VH003 | 362 | 26.Apr.2024 |  | MC1 | LVL 6 | W60 | TR001 | 2024-02-07 | 2024-02-12 | 2024-03-01 | Connection to AHU correct acc. KO |  |  | Satu Mare | [7 empty] | 796 | 150 |  |  |  | 149 | SEP | SEP
45511 | 740-MHW-S-VH003-102-LH130-20-0 | 2 | true | 1.27 | 740-MHW-S-VH003-102-LH130-20-0 | LV1-105623.VH003 | 362 | 26.Apr.2024 |  | MC1 | LVL 6 | W60 | TR005 | 2024-03-03 | 2024-02-11 | 2024-02-29 | Connection to AHU correct acc. KO | 2024-04-19 | 2024-04-24 | Büro | 2024-04-26 |  | 2024-04-25 | 2024-05-20 |  |  | 2024-05-22 | 796 | 150 |  | 2024-07-10 | 2024-07-04 | 149 | SEP | SEP | 2024-07-10 |  | 2024-07-26 | 2024-07-26 | 2024-09-26 | 2024-09-26
44340 | 740-MHW-S-VH004-101-LH130-20-0 | 1 | true | 1.46 | 740-MHW-S-VH004-101-LH130-20-0 | LV1-105623.VH004 | 362 | 26.Apr.2024 |  | MC1 | LVL 6 | W60 | TR001 | 2024-02-06 | 2024-02-11 | 2024-02-29 |  | 2024-04-19 | 2024-04-22 | Büro | 2024-04-26 |  | 2024-04-23 | 2024-05-22 |  |  | 2024-05-27 | 796 | 150 |  | 2024-07-10 | 2024-07-04 | 149 | SEP | SEP | 2024-07-10 |  | 2024-07-26 | 2024-07-26
44341 | 740-MHW-S-VH004-102-LH130-20-0 | 1 | false | 3.64 | 740-MHW-S-VH004-102-LH130-20-0 | LV1-105623.VH004 | 362 | 26.Apr.2024 |  | MC1 | LVL 6 | W60 | TR001 | 2024-02-07 | 2024-02-12 | 2024-03-01 |  |  |  | Satu Mare | [7 empty] | 796 | 150 |  |  |  | 149 | SEP | SEP
45512 | 740-MHW-S-VH004-102-LH130-20-0 | 2 | true | 3.64 | 740-MHW-S-VH004-102-LH130-20-0 | LV1-105623.VH004 | 362 | 26.Apr.2024 |  | MC1 | LVL 6 | W60 | TR005 | 2024-03-03 | 2024-02-11 | 2024-02-29 |  | 2024-04-19 | 2024-04-26 | Büro | 2024-04-26 |  | 2024-04-26 | 2024-05-22 |  |  | 2024-05-27 | 796 | 150 |  | 2024-07-10 | 2024-07-04 | 149 | SEP | SEP | 2024-07-10 |  | 2024-07-26 | 2024-07-26
44342 | 740-MHW-S-VH005-101-LH130-20-0 | 1 | true | 0.84 | 740-MHW-S-VH005-101-LH130-20-0 | LV1-105623.VH005 | 362 | 26.Apr.2024 |  | MC1 | LVL 6 | W60 | TR001 | 2024-02-06 | 2024-02-11 | 2024-02-29 |  | 2024-04-19 | 2024-04-23 | Büro | 2024-04-26 |  | 2024-04-23 | 2024-05-15 |  |  | 2024-05-16 | 796 | 150 |  | 2024-07-10 | 2024-07-04 | 149 | SEP | SEP | 2024-07-10 |  | 2024-07-26 | 2024-07-26
44343 | 740-MHW-S-VH005-102-LH130-25-0 | 1 | false | 1.19 | 740-MHW-S-VH005-102-LH130-25-0 | LV1-105623.VH005 | 362 | 26.Apr.2024 |  | MC1 | LVL 6 | W60 | TR001 | 2024-02-07 | 2024-02-12 | 2024-03-01 |  |  |  | Satu Mare | [7 empty] | 796 | 150 |  |  |  | 149 | SEP | SEP
45513 | 740-MHW-S-VH005-102-LH130-25-0 | 2 | true | 1.19 | 740-MHW-S-VH005-102-LH130-25-0 | LV1-105623.VH005 | 362 | 26.Apr.2024 |  | MC1 | LVL 6 | W60 | TR005 | 2024-03-03 | 2024-02-11 | 2024-02-29 |  | 2024-04-19 | 2024-04-22 | Büro | 2024-04-26 |  | 2024-04-23 | 2024-05-08 |  |  | 2024-05-16 | 796 | 150 |  | 2024-07-10 | 2024-07-04 | 149 | SEP | SEP | 2024-07-10 |  | 2024-07-26 | 2024-07-26
44344 | 740-MHW-S-VH005-211-LH130-20-0 | 1 | false | 0.54 | 740-MHW-S-VH005-211-LH130-20-0 | LV0-105624.VH005 | 362 | 26.Apr.2024 |  | MC1 | LVL 6 | W60 | TR001 | 2024-02-07 | 2024-02-12 | 2024-03-01 |  |  |  | Satu Mare | [7 empty] | 796 | 150 |  |  |  | 149 | SEP | SEP
45514 | 740-MHW-S-VH005-211-LH130-20-0 | 2 | true | 0.54 | 740-MHW-S-VH005-211-LH130-20-0 | LV0-105624.VH005 | 362 | 26.Apr.2024 |  | MC1 | LVL 6 | W60 | TR005 | 2024-03-03 | 2024-02-11 | 2024-02-29 |  | 2024-04-12 | 2024-04-15 | Büro | 2024-04-26 |  | 2024-04-17 | 2024-05-08 |  | 2024-05-15 | 2024-11-12 | 796 | 150 |  | 2024-07-10 | 2024-07-04 | 149 | SEP | SEP | 2024-07-10 |  | 2024-07-26 | 2024-07-26
44345 | 740-MHW-S-VU221-101-LH001-65-0 | 1 | true | 47.94 | 740-MHW-S-VU221-101-LH001-65-0 | LV1-105638.VU221 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | W60 | TR001 | 2024-02-08 | 2024-02-13 | 2024-03-02 |  | 2024-04-01 | 2024-04-04 | Büro | 2024-04-12 |  | 2024-04-08 | 2024-04-30 |  |  | 2024-05-08 | 796 | 150 |  | 2024-07-10 | 2024-07-04 | 149 | SEP | SEP | 2024-07-10 | 2024-07-26 | 2024-07-26 | 2024-07-26 | 2024-09-26 | 2024-09-26
44346 | 740-MHW-S-VU221-102-LH001-50-0 | 1 | false | 30.85 | 740-MHW-S-VU221-102-LH001-50-0 | LV1-105638.VU221 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | W60 | TR001 | 2024-02-07 | 2024-02-12 |  |  |  |  | Paul Friedwagner | [7 empty] | 796 | 150 |  |  |  | 149 | SEP | SEP
44638 | 740-MHW-S-VU221-102-LH001-50-0 | 2 | true | 30.85 | 740-MHW-S-VU221-102-LH001-50-0 | LV1-105638.VU221 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | W60 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-04-08 | 2024-04-11 | Büro | 2024-04-12 |  | 2024-04-11 | 2024-04-24 |  |  | 2024-04-26 | 796 | 150 |  | 2024-07-10 | 2024-07-04 | 149 | SEP | SEP | 2024-07-10 |  | 2024-07-26 | 2024-07-26 | 2024-09-26 | 2024-09-26
44347 | 740-MHW-S-VU221-103-LH130-25-0 | 1 | true | 15.94 | 740-MHW-S-VU221-103-LH130-25-0 | LV1-105638.VU221 | 362 | 26.Apr.2024 |  | MC1 | LVL 6 | W60 | TR001 | 2024-02-06 | 2024-02-11 | 2024-02-29 |  | 2024-04-16 | 2024-04-19 | Büro | 2024-04-26 |  | 2024-04-19 | 2024-05-08 |  |  | 2024-05-14 | 796 | 150 |  | 2024-07-10 | 2024-07-04 | 149 | SEP | SEP | 2024-07-10 |  | 2024-07-26 | 2024-07-26 | 2024-09-26 | 2024-09-26
44636 | 727-MKWE-R-U241-507-LH001-150-0 | 1 | false | 24.3 | 727-MKWE-R-U241-507-LH001-150-0 | LV1-103542.U241 | 363 | 2.Apr.2024 |  | MC1 | Riser | K51 | TR002 | 2024-02-11 | 2024-02-24 |  |  |  |  | Friedwagner Paul | [7 empty] | 802 | 150 |  |  |  | 149 | SEP | SEP
44950 | 727-MKWE-R-U241-507-LH001-150-0 | 2 | false | 24.3 | 727-MKWE-R-U241-507-LH001-150-0 | LV1-103542.U241 | 363 | 2.Apr.2024 |  | MC1 | Riser | K51 | TR003 | 2024-02-20 | 2024-02-26 | 2024-02-29 |  | 2024-03-16 | 2024-03-22 | Büro | 2024-04-01 |  | 2024-03-25 | 2024-05-14 |  |  | 2024-05-22 | 802 | 150 |  | 2024-07-16 | 2024-07-11 | 149 | SEP | SEP | 2024-07-10
44637 | 727-MKWE-S-U241-506-LH001-150-0 | 1 | false | 24.35 | 727-MKWE-S-U241-506-LH001-150-0 | LV1-103542.U241 | 363 | 2.Apr.2024 |  | MC1 | Riser | K51 | TR002 | 2024-02-11 | 2024-02-24 |  |  |  |  | Friedwagner Paul | [7 empty] | 802 | 150 |  |  |  | 149 | SEP | SEP
44951 | 727-MKWE-S-U241-506-LH001-150-0 | 2 | false | 24.35 | 727-MKWE-S-U241-506-LH001-150-0 | LV1-103542.U241 | 363 | 2.Apr.2024 |  | MC1 | Riser | K51 | TR003 | 2024-02-20 | 2024-02-26 | 2024-02-29 |  | 2024-03-18 | 2024-03-22 | Büro | 2024-04-01 |  | 2024-03-25 | 2024-05-14 |  |  | 2024-05-22 | 802 | 150 |  |  | 2024-07-11 | 149 | SEP | SEP | 2024-07-10
44639 | 740-MKWE-R-VP001-301-LH001-50-0 | 1 | true | 2.02 | 740-MKWE-R-VP001-301-LH001-50-0 | LV1-105638.VU241 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | K51 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-04-02 | 2024-04-04 | Zauner Romania | 2024-04-12 |  | 2024-04-04 |  |  |  | 2024-10-18 | 803 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-11-30 | 2024-11-30
44640 | 740-MKWE-R-VP002-301-LH001-50-0 | 1 | true | 1.09 | 740-MKWE-R-VP002-301-LH001-50-0 | LV1-105638.VU241 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | K51 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-04-02 | 2024-04-03 | Büro | 2024-04-12 |  | 2024-04-04 | 2024-10-21 |  |  | 2024-10-23 | 803 | 150 |  | 2024-11-13 |  | 149 | SEP | SEP |  |  | 2024-11-30 | 2024-11-30
44641 | 740-MKWE-R-VP003-301-LH001-40-0 | 1 | true | 2.27 | 740-MKWE-R-VP003-301-LH001-40-0 | LV1-105638.VU241 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | K51 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-04-17 | 2024-04-18 | Zauner Romania | 2024-04-26 |  | 2024-04-18 |  |  |  | 2024-10-18 | 803 | 150 |  | 2024-11-13 |  | 149 | SEP | SEP |  |  | 2024-11-30 | 2024-11-30
44642 | 740-MKWE-R-VP004-301-LH001-40-0 | 1 | true | 2.29 | 740-MKWE-R-VP004-301-LH001-40-0 | LV1-105638.VU241 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | K51 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-04-17 | 2024-04-19 | Büro | 2024-04-26 |  | 2024-04-20 |  |  |  | 2024-10-22 | 803 | 150 |  |  | 2024-10-30 | 149 | SEP | SEP |  |  | 2024-11-30 | 2024-11-30
44643 | 740-MKWE-R-VP031-201-LH001-50-0 | 1 | true | 2.12 | 740-MKWE-R-VP031-201-LH001-50-0 | LV1-105638.VU241 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | K51 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-04-03 | 2024-04-08 | Büro | 2024-04-12 |  | 2024-04-09 |  |  |  | 2024-10-30 | 803 | 150 |  |  | 2024-11-04 | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
44644 | 740-MKWE-R-VP032-201-LH001-50-0 | 1 | true | 1.96 | 740-MKWE-R-VP032-201-LH001-50-0 | LV1-105638.VU241 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | K51 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-04-02 | 2024-04-03 | Büro | 2024-04-12 |  | 2024-04-04 | 2024-10-22 |  |  | 2024-10-24 | 803 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
44645 | 740-MKWE-R-VP033-201-LH001-50-0 | 1 | true | 2.11 | 740-MKWE-R-VP033-201-LH001-50-0 | LV1-105638.VU241 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | K51 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-04-02 | 2024-04-04 | Büro | 2024-04-12 |  | 2024-04-04 |  |  |  | 2024-11-04 | 803 | 150 |  | 2024-11-18 | 2024-11-05 | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
44646 | 740-MKWE-R-VP041-201-LH001-50-0 | 1 | true | 1.79 | 740-MKWE-R-VP041-201-LH001-50-0 | LV1-105638.VU241 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | K51 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-04-08 | 2024-04-09 | Büro | 2024-04-12 |  | 2024-04-09 |  |  |  | 2024-10-30 | 803 | 150 |  | 2024-11-18 | 2024-10-31 | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
44647 | 740-MKWE-R-VP042-201-LH001-50-0 | 1 | true | 1.53 | 740-MKWE-R-VP042-201-LH001-50-0 | LV1-105638.VU241 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | K51 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-04-05 | 2024-04-10 | Büro | 2024-04-12 |  | 2024-04-10 | 2024-10-22 |  |  | 2024-10-24 | 803 | 150 |  | 2024-11-18 | 2024-10-30 | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
44648 | 740-MKWE-R-VP043-201-LH001-50-0 | 1 | true | 1.96 | 740-MKWE-R-VP043-201-LH001-50-0 | LV1-105638.VU241 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | K51 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-04-08 | 2024-04-09 | Büro | 2024-04-12 |  | 2024-04-09 | 2024-10-24 |  |  | 2024-10-30 | 803 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
44649 | 740-MKWE-R-VP131-201-LH001-40-0 | 1 | true | 1.1 | 740-MKWE-R-VP131-201-LH001-40-0 | LV1-105638.VU241 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | K51 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-04-17 | 2024-04-19 | Büro | 2024-04-26 |  | 2024-04-19 |  |  |  | 2024-11-06 | 803 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-12-20 | 2024-12-20
44650 | 740-MKWE-R-VP132-201-LH001-40-0 | 1 | true | 1.08 | 740-MKWE-R-VP132-201-LH001-40-0 | LV1-105638.VU241 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | K51 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-04-17 | 2024-04-19 | Büro | 2024-04-26 |  | 2024-04-19 |  |  |  | 2024-11-06 | 803 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-12-20 | 2024-12-20
44651 | 740-MKWE-R-VP133-201-LH001-40-0 | 1 | true | 1.02 | 740-MKWE-R-VP133-201-LH001-40-0 | LV1-105638.VU241 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | K51 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-04-17 | 2024-04-19 | Büro | 2024-04-26 |  | 2024-04-20 |  |  |  | 2024-10-30 | 803 | 150 |  |  | 2024-10-31 | 149 | SEP | SEP |  |  | 2024-12-20 | 2024-12-20
44652 | 740-MKWE-R-VP141-201-LH001-40-0 | 1 | true | 0.08 | 740-MKWE-R-VP141-201-LH001-40-0 | LV1-105638.VU241 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | K51 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-04-17 | 2024-04-19 | Büro | 2024-04-26 |  | 2024-04-20 | 2024-10-22 |  |  | 2024-10-24 | 803 | 150 |  |  | 2024-10-30 | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
44653 | 740-MKWE-R-VP142-201-LH001-40-0 | 1 | true | 0.14 | 740-MKWE-R-VP142-201-LH001-40-0 | LV1-105638.VU241 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | K51 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-04-17 | 2024-04-19 | Büro | 2024-04-26 |  | 2024-04-20 |  |  |  | 2024-10-22 | 803 | 150 |  |  | 2024-10-30 | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
44654 | 740-MKWE-R-VP143-201-LH001-40-0 | 1 | true | 1.12 | 740-MKWE-R-VP143-201-LH001-40-0 | LV1-105638.VU241 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | K51 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-04-17 | 2024-04-19 | Büro | 2024-04-26 |  | 2024-04-19 | 2024-10-21 |  |  | 2024-10-23 | 803 | 150 |  |  | 2024-10-30 | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
44655 | 740-MKWE-R-VU241-121-LH001-100-0 | 1 | false | 72.04 | 740-MKWE-R-VU241-121-LH001-100-0 | LV1-105638.VU241 | 363 | 2.Apr.2024 |  | MC1 | LVL 6 | T60 | TR002 | 2024-02-11 | 2024-02-24 |  |  |  |  | Friedwagner Paul | [7 empty] | 803 | 150 |  |  |  | 149 | SEP | SEP
44968 | 740-MKWE-R-VU241-121-LH001-100-0 | 2 | false | 72.04 | 740-MKWE-R-VU241-121-LH001-100-0 | LV1-105638.VU241 | 363 | 2.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-21 | 2024-02-26 | 2024-02-29 |  | 2024-03-15 | 2024-03-22 | Büro | 2024-04-01 |  | 2024-03-25 | 2024-04-09 | 2024-04-26 | 2024-04-30 | 2024-05-14 | 803 | 150 |  | 2024-07-16 | 2024-07-11 | 149 | SEP | SEP | 2024-07-10
62771 | 740-MKWE-R-VU241-121-LH001-100-0 | 3 | true | 72.04 | 740-MKWE-R-VU241-121-LH001-100-0 | LV1-105638.VU241 | 363 |  |  | MC1 | LVL 6 | T60 | TR029_3 | 2024-08-07 | 2024-02-26 | 2024-02-29 |  | 2024-03-15 | 2024-03-22 |  | 2024-04-01 |  | 2024-03-25 | 2024-04-09 | 2024-04-26 | 2024-04-30 | 2024-05-14 | 803 | 150 |  | 2024-08-21 | 2024-07-11 | 149 | SEP | SEP | 2024-08-19 | 2024-08-12 | 2024-09-09 | 2024-09-30 | 2024-10-15 | 2024-10-15
44656 | 740-MKWE-R-VU241-122-LH001-50-0 | 1 | true | 6.45 | 740-MKWE-R-VU241-122-LH001-50-0 | LV1-105638.VU241 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | K51 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-04-05 | 2024-04-09 | Büro | 2024-04-12 |  | 2024-04-10 | 2024-05-20 |  |  | 2024-05-23 | 803 | 150 |  | 2024-07-16 | 2024-07-11 | 149 | SEP | SEP | 2024-07-10 | 2024-09-13 | 2024-09-13 | 2024-10-15 | 2024-10-15 | 2024-10-15
44657 | 740-MKWE-R-VU241-123-LH001-40-0 | 1 | true | 1.23 | 740-MKWE-R-VU241-123-LH001-40-0 | LV1-105638.VU241 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | K51 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-04-08 | 2024-04-10 | Büro | 2024-04-12 |  | 2024-04-10 | 2024-05-21 |  |  | 2024-05-23 | 803 | 150 |  | 2024-07-16 | 2024-07-11 | 149 | SEP | SEP | 2024-07-10 | 2024-09-20 | 2024-09-20 | 2024-09-20 | 2024-10-15 | 2024-10-15
44658 | 740-MKWE-R-VU241-124-LH001-40-0 | 1 | true | 1.64 | 740-MKWE-R-VU241-124-LH001-40-0 | LV1-105638.VU241 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | K51 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-04-08 | 2024-04-09 | Büro | 2024-04-12 |  | 2024-04-09 | 2024-05-21 |  |  | 2024-05-23 | 803 | 150 |  | 2024-07-16 | 2024-07-11 | 149 | SEP | SEP | 2024-07-10 | 2024-09-13 | 2024-09-13 | 2024-10-15 | 2024-10-15 | 2024-10-15
44659 | 740-MKWE-R-VU241-125-LH001-40-0 | 1 | true | 4.44 | 740-MKWE-R-VU241-125-LH001-40-0 | LV1-105638.VU241 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | K51 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-04-16 | 2024-04-17 | Büro | 2024-04-26 |  | 2024-04-18 | 2024-05-20 |  |  | 2024-05-23 | 803 | 150 |  | 2024-07-16 | 2024-07-11 | 149 | SEP | SEP | 2024-07-10 | 2024-09-13 | 2024-09-13 | 2024-10-15 | 2024-10-15 | 2024-10-15
44660 | 740-MKWE-R-VU241-126-LH001-65-0 | 1 | false | 12.92 | 740-MKWE-R-VU241-126-LH001-65-0 | LV1-105638.VU241 | 363 | 2.Apr.2024 |  | MC1 | LVL 6 | K51 | TR002 | 2024-02-09 | 2024-02-22 | 2024-02-28 |  | 2024-03-24 | 2024-03-26 | Maxim Tiebe | 2024-04-11 |  | 2024-04-08 |  |  |  |  | 803 | 150 |  |  |  | 150 | SEP | SEP
48792 | 740-MKWE-R-VU241-126-LH001-65-0 | 2 | true | 12.92 | 740-MKWE-R-VU241-126-LH001-65-0 | LV1-105638.VU241 | 363 |  |  | MC1 | LVL 6 | K51 | TR013_1 | 2024-04-15 | 2024-02-22 | 2024-02-28 |  | 2024-03-24 | 2024-03-26 | Büro | 2024-04-11 |  | 2024-04-08 | 2024-04-23 |  |  | 2024-04-26 | 803 | 150 | Modifikation to be made | 2024-07-16 | 2024-07-12 | 150 | SEP | SEP | 2024-08-19 | 2024-09-13 | 2024-09-13 | 2024-10-15 | 2024-10-15 | 2024-10-15
44661 | 740-MKWE-R-VU241-127-LH001-50-0 | 1 | true | 0.16 | 740-MKWE-R-VU241-127-LH001-50-0 | LV1-105638.VU241 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | K51 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-04-09 | 2024-04-10 | Zauner Romania | 2024-04-12 |  | 2024-04-10 | 2024-07-24 |  |  | 2024-07-25 | 803 | 150 |  | 2024-08-21 | 2024-08-05 | 149 | SEP | SEP | 2024-08-19 | 2024-09-20 | 2024-09-20 | 2024-09-20 | 2024-10-15 | 2024-10-15
44662 | 740-MKWE-R-VU241-128-LH001-50-0 | 1 | true | 0.21 | 740-MKWE-R-VU241-128-LH001-50-0 | LV1-105638.VU241 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | K51 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-04-09 | 2024-04-10 | Zauner Romania | 2024-04-12 |  | 2024-04-10 | 2024-07-24 |  |  | 2024-07-25 | 803 | 150 |  | 2024-08-21 | 2024-08-05 | 149 | SEP | SEP | 2024-08-19 | 2024-09-20 | 2024-09-20 | 2024-09-20 | 2024-10-15 | 2024-10-15
44663 | 740-MKWE-R-VU241-129-LH001-50-0 | 1 | true | 0.21 | 740-MKWE-R-VU241-129-LH001-50-0 | LV1-105638.VU241 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | K51 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-04-09 | 2024-04-09 | Zauner Romania | 2024-04-12 |  | 2024-04-09 | 2024-07-24 |  |  | 2024-07-25 | 803 | 150 |  | 2024-08-21 | 2024-08-05 | 149 | SEP | SEP | 2024-08-19 | 2024-09-20 | 2024-09-20 | 2024-09-20 | 2024-10-15 | 2024-10-15
44664 | 740-MKWE-R-VU241-130-LH001-50-0 | 1 | true | 0.05 | 740-MKWE-R-VU241-130-LH001-50-0 | LV1-105638.VU241 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | K51 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-04-09 | 2024-04-10 | Zauner Romania | 2024-04-12 |  | 2024-04-10 | 2024-07-24 |  |  | 2024-07-25 | 803 | 150 |  | 2024-08-21 | 2024-08-05 | 149 | SEP | SEP | 2024-08-19 | 2024-09-20 | 2024-09-20 | 2024-09-20 | 2024-10-15 | 2024-10-15
44665 | 740-MKWE-R-VU241-131-LH001-50-0 | 1 | true | 0.15 | 740-MKWE-R-VU241-131-LH001-50-0 | LV1-105638.VU241 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | K51 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-04-09 | 2024-04-09 | Zauner Romania | 2024-04-12 |  | 2024-04-09 | 2024-07-24 |  |  | 2024-07-25 | 803 | 150 |  | 2024-08-21 | 2024-08-05 | 149 | SEP | SEP | 2024-08-19 | 2024-09-20 | 2024-09-20 | 2024-09-20 | 2024-10-15 | 2024-10-15
44666 | 740-MKWE-R-VU241-132-LH001-50-0 | 1 | true | 0 | 740-MKWE-R-VU241-132-LH001-50-0 | LV1-105638.VU241 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | K51 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-04-09 | 2024-04-09 | Zauner Romania | 2024-04-12 |  | 2024-04-09 | 2024-07-24 |  |  | 2024-07-25 | 803 | 150 |  | 2024-08-21 | 2024-08-05 | 149 | SEP | SEP | 2024-08-19 | 2024-10-15 | 2024-10-15 | 2024-10-15 | 2024-10-15 | 2024-10-15
44667 | 740-MKWE-R-VU241-133-LH001-65-0 | 1 | true | 15.02 | 740-MKWE-R-VU241-133-LH001-65-0 | LV1-105638.VU241 | 363 | 2.Apr.2024 |  | MC1 | LVL 6 | K51 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-03-22 | 2024-04-04 | Büro | 2024-04-12 |  | 2024-04-10 | 2024-04-18 |  |  | 2024-04-19 | 803 | 150 |  | 2024-07-16 | 2024-07-03 | 149 | SEP | SEP | 2024-08-19 | 2024-09-13 | 2024-09-13
44668 | 740-MKWE-R-VU241-134-LH001-40-0 | 1 | true | 0.33 | 740-MKWE-R-VU241-134-LH001-40-0 | LV1-105638.VU241 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | K51 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-04-04 | 2024-04-08 | Zauner Romania | 2024-04-12 |  | 2024-04-08 | 2024-07-18 |  |  | 2024-07-19 | 803 | 150 |  | 2024-08-21 | 2024-07-04 | 149 | SEP | SEP | 2024-08-19 | 2024-09-20 | 2024-09-20 | 2024-09-20 | 2024-10-15 | 2024-10-15
44669 | 740-MKWE-R-VU241-135-LH001-40-0 | 1 | true | 0.3 | 740-MKWE-R-VU241-135-LH001-40-0 | LV1-105638.VU241 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | K51 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-04-04 | 2024-04-08 | Zauner Romania | 2024-04-12 |  | 2024-04-08 | 2024-07-18 |  |  | 2024-07-19 | 803 | 150 |  | 2024-08-21 | 2024-07-04 | 149 | SEP | SEP | 2024-08-19 | 2024-09-20 | 2024-09-20 | 2024-09-20 | 2024-10-15 | 2024-10-15
44670 | 740-MKWE-R-VU241-136-LH001-40-0 | 1 | true | 0.2 | 740-MKWE-R-VU241-136-LH001-40-0 | LV1-105638.VU241 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | K51 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-04-04 | 2024-04-09 | Zauner Romania | 2024-04-12 |  | 2024-04-09 | 2024-07-18 |  |  | 2024-07-19 | 803 | 150 |  | 2024-08-21 | 2024-07-04 | 149 | SEP | SEP | 2024-08-19 | 2024-09-20 | 2024-09-20 | 2024-09-20 | 2024-10-15 | 2024-10-15
44671 | 740-MKWE-R-VU241-137-LH001-40-0 | 1 | true | 0.2 | 740-MKWE-R-VU241-137-LH001-40-0 | LV1-105638.VU241 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | K51 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-04-04 | 2024-04-09 | Zauner Romania | 2024-04-12 |  | 2024-04-09 | 2024-07-18 |  |  | 2024-07-19 | 803 | 150 |  | 2024-08-21 | 2024-07-04 | 149 | SEP | SEP | 2024-08-19 | 2024-09-20 | 2024-09-20 | 2024-09-20 | 2024-10-15 | 2024-10-15
44672 | 740-MKWE-R-VU241-138-LH001-50-0 | 1 | true | 0.26 | 740-MKWE-R-VU241-138-LH001-50-0 | LV1-105638.VU241 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | K51 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-04-03 | 2024-04-05 | Zauner Romania | 2024-04-12 |  | 2024-04-05 | 2024-07-18 |  |  | 2024-07-19 | 803 | 150 |  | 2024-08-21 | 2024-07-04 | 149 | SEP | SEP | 2024-08-19 | 2024-09-20 | 2024-09-20 | 2024-09-20 | 2024-10-15 | 2024-10-15
44673 | 740-MKWE-R-VU241-139-LH001-40-0 | 1 | true | 0.21 | 740-MKWE-R-VU241-139-LH001-40-0 | LV1-105638.VU241 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | K51 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-04-04 | 2024-04-09 | Zauner Romania | 2024-04-12 |  | 2024-04-09 | 2024-07-18 |  |  | 2024-07-19 | 803 | 150 |  | 2024-08-21 | 2024-07-04 | 149 | SEP | SEP | 2024-08-19 | 2024-09-20 | 2024-09-20 | 2024-09-20 | 2024-10-15 | 2024-10-15
44674 | 740-MKWE-R-VU241-140-LH001-50-0 | 1 | true | 0.28 | 740-MKWE-R-VU241-140-LH001-50-0 | LV1-105638.VU241 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | K51 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-04-03 | 2024-04-08 | Zauner Romania | 2024-04-12 |  | 2024-04-08 | 2024-07-18 |  |  | 2024-07-19 | 803 | 150 |  | 2024-08-21 | 2024-07-05 | 149 | SEP | SEP | 2024-08-19 | 2024-09-20 | 2024-09-20 | 2024-09-20 | 2024-10-15 | 2024-10-15
44675 | 740-MKWE-S-VP001-301-LH001-50-0 | 1 | true | 2.09 | 740-MKWE-S-VP001-301-LH001-50-0 | LV1-105638.VU241 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | K51 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-04-03 | 2024-04-10 | Zauner Romania | 2024-04-12 |  | 2024-04-10 |  |  |  | 2024-10-18 | 803 | 150 |  | 2024-11-13 |  | 149 | SEP | SEP |  |  | 2024-11-30 | 2024-11-30
44676 | 740-MKWE-S-VP002-301-LH001-50-0 | 1 | true | 0.43 | 740-MKWE-S-VP002-301-LH001-50-0 | LV1-105638.VU241 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | K51 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-04-03 | 2024-04-09 | Büro | 2024-04-12 |  | 2024-04-09 | 2024-10-21 |  |  | 2024-10-23 | 803 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-11-30 | 2024-11-30
44677 | 740-MKWE-S-VP003-301-LH001-40-0 | 1 | true | 2.26 | 740-MKWE-S-VP003-301-LH001-40-0 | LV1-105638.VU241 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | K51 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-04-18 | 2024-04-20 | Büro | 2024-04-26 |  | 2024-04-20 |  |  |  | 2024-10-22 | 803 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-11-30 | 2024-11-30
44678 | 740-MKWE-S-VP004-301-LH001-40-0 | 1 | true | 2.11 | 740-MKWE-S-VP004-301-LH001-40-0 | LV1-105638.VU241 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | K51 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-04-18 | 2024-04-19 | Zauner Romania | 2024-04-26 |  | 2024-04-20 |  |  |  | 2024-10-18 | 803 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-11-30 | 2024-11-30
44679 | 740-MKWE-S-VP031-201-LH001-50-0 | 1 | true | 0.48 | 740-MKWE-S-VP031-201-LH001-50-0 | LV1-105638.VU241 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | K51 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-04-02 | 2024-04-09 | Büro | 2024-04-12 |  | 2024-04-09 |  |  |  | 2024-10-30 | 803 | 150 |  | 2024-11-18 | 2024-11-04 | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
44680 | 740-MKWE-S-VP032-201-LH001-50-0 | 1 | true | 0.69 | 740-MKWE-S-VP032-201-LH001-50-0 | LV1-105638.VU241 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | K51 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-04-02 | 2024-04-10 | Büro | 2024-04-12 |  | 2024-04-10 | 2024-10-22 |  |  | 2024-10-24 | 803 | 150 |  | 2024-11-18 | 2024-10-30 | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
44681 | 740-MKWE-S-VP033-201-LH001-50-0 | 1 | true | 0.6 | 740-MKWE-S-VP033-201-LH001-50-0 | LV1-105638.VU241 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | K51 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-04-02 | 2024-04-09 | Büro | 2024-04-12 |  | 2024-04-09 |  |  |  | 2024-11-04 | 803 | 150 |  | 2024-11-18 | 2024-11-05 | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
44682 | 740-MKWE-S-VP041-201-LH001-50-0 | 1 | true | 0.74 | 740-MKWE-S-VP041-201-LH001-50-0 | LV1-105638.VU241 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | K51 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-04-04 | 2024-04-10 | Büro | 2024-04-12 |  | 2024-04-10 |  |  |  | 2024-10-30 | 803 | 150 |  | 2024-11-18 | 2024-10-31 | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
44683 | 740-MKWE-S-VP042-201-LH001-50-0 | 1 | true | 0.74 | 740-MKWE-S-VP042-201-LH001-50-0 | LV1-105638.VU241 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | K51 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-04-10 | 2024-04-10 | Büro | 2024-04-12 |  | 2024-04-10 | 2024-10-22 |  |  | 2024-10-24 | 803 | 150 |  | 2024-11-18 | 2024-10-30 | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
44684 | 740-MKWE-S-VP043-201-LH001-50-0 | 1 | true | 0.68 | 740-MKWE-S-VP043-201-LH001-50-0 | LV1-105638.VU241 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | K51 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-04-08 | 2024-04-10 | Büro | 2024-04-12 |  | 2024-04-10 | 2024-10-24 |  |  | 2024-10-30 | 803 | 150 |  | 2024-11-18 |  | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
44685 | 740-MKWE-S-VP131-201-LH001-40-0 | 1 | true | 1.02 | 740-MKWE-S-VP131-201-LH001-40-0 | LV1-105638.VU241 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | K51 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-04-18 | 2024-04-19 | Büro | 2024-04-26 |  | 2024-04-19 |  |  |  | 2024-11-06 | 803 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-12-20 | 2024-12-20
44686 | 740-MKWE-S-VP132-201-LH001-40-0 | 1 | true | 1.02 | 740-MKWE-S-VP132-201-LH001-40-0 | LV1-105638.VU241 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | K51 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-04-18 | 2024-04-19 | Büro | 2024-04-26 |  | 2024-04-19 |  |  |  | 2024-11-04 | 803 | 150 |  |  | 2024-11-05 | 149 | SEP | SEP |  |  | 2024-12-20 | 2024-12-20
44687 | 740-MKWE-S-VP133-201-LH001-40-0 | 1 | true | 1.03 | 740-MKWE-S-VP133-201-LH001-40-0 | LV1-105638.VU241 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | K51 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-04-18 | 2024-04-19 | Büro | 2024-04-26 |  | 2024-04-19 |  |  |  | 2024-10-30 | 803 | 150 |  |  | 2024-10-31 | 149 | SEP | SEP |  |  | 2024-12-20 | 2024-12-20
44688 | 740-MKWE-S-VP141-201-LH001-40-0 | 1 | true | 0.08 | 740-MKWE-S-VP141-201-LH001-40-0 | LV1-105638.VU241 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | K51 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-04-16 | 2024-04-16 | Büro | 2024-04-26 |  | 2024-04-17 | 2024-10-22 |  |  | 2024-10-24 | 803 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
44689 | 740-MKWE-S-VP142-201-LH001-40-0 | 1 | true | 0.06 | 740-MKWE-S-VP142-201-LH001-40-0 | LV1-105638.VU241 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | K51 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-04-16 | 2024-04-18 | Büro | 2024-04-26 |  | 2024-04-18 |  |  |  | 2024-10-22 | 803 | 150 |  |  | 2024-10-30 | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
44690 | 740-MKWE-S-VP143-201-LH001-40-0 | 1 | true | 0.78 | 740-MKWE-S-VP143-201-LH001-40-0 | LV1-105638.VU241 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | K51 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-04-16 | 2024-04-17 | Büro | 2024-04-26 |  | 2024-04-18 | 2024-10-21 |  |  | 2024-10-23 | 803 | 150 |  |  | 2024-10-30 | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
44691 | 740-MKWE-S-VU241-101-LH001-100-0 | 1 | false | 71.9 | 740-MKWE-S-VU241-101-LH001-100-0 | LV1-105638.VU241 | 363 | 2.Apr.2024 |  | MC1 | LVL 6 | T60 | TR002 | 2024-02-11 | 2024-02-24 |  |  |  |  | Friedwagner Paul | [7 empty] | 803 | 150 |  |  |  | 149 | SEP | SEP
44969 | 740-MKWE-S-VU241-101-LH001-100-0 | 2 | false | 71.9 | 740-MKWE-S-VU241-101-LH001-100-0 | LV1-105638.VU241 | 363 | 2.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-21 | 2024-02-26 | 2024-02-29 |  | 2024-03-15 | 2024-03-23 | Büro | 2024-04-01 |  | 2024-03-24 | 2024-04-09 | 2024-04-26 |  | 2024-05-14 | 803 | 150 |  | 2024-07-16 | 2024-07-11 | 149 | SEP | SEP | 2024-07-10
62772 | 740-MKWE-S-VU241-101-LH001-100-0 | 3 | true | 71.9 | 740-MKWE-S-VU241-101-LH001-100-0 | LV1-105638.VU241 | 363 |  |  | MC1 | LVL 6 | T60 | TR029_3 | 2024-08-07 | 2024-02-26 | 2024-02-29 |  | 2024-03-15 | 2024-03-23 |  | 2024-04-01 |  | 2024-03-24 | 2024-04-09 | 2024-04-26 |  | 2024-05-14 | 803 | 150 |  | 2024-08-28 | 2024-07-11 | 149 | SEP | SEP | 2024-08-19 | 2024-08-12 | 2024-09-09 | 2024-09-30 | 2024-10-15 | 2024-10-15
44692 | 740-MKWE-S-VU241-102-LH001-50-0 | 1 | true | 7.09 | 740-MKWE-S-VU241-102-LH001-50-0 | LV1-105638.VU241 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | K51 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-04-08 | 2024-04-10 | Büro | 2024-04-12 |  | 2024-04-11 | 2024-05-20 |  |  | 2024-05-22 | 803 | 150 |  | 2024-07-16 | 2024-07-09 | 149 | SEP | SEP | 2024-07-10 | 2024-09-13 | 2024-09-13 | 2024-10-15 | 2024-10-15 | 2024-10-15
44693 | 740-MKWE-S-VU241-103-LH001-40-0 | 1 | true | 1 | 740-MKWE-S-VU241-103-LH001-40-0 | LV1-105638.VU241 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | K51 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-04-16 | 2024-04-17 | Büro | 2024-04-26 |  | 2024-04-18 | 2024-05-21 |  |  | 2024-05-22 | 803 | 150 |  | 2024-07-16 | 2024-07-09 | 149 | SEP | SEP | 2024-07-10 | 2024-09-20 | 2024-09-20 | 2024-09-20
44694 | 740-MKWE-S-VU241-104-LH001-40-0 | 1 | true | 1 | 740-MKWE-S-VU241-104-LH001-40-0 | LV1-105638.VU241 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | K51 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-04-16 | 2024-04-18 | Büro | 2024-04-26 |  | 2024-04-18 | 2024-05-21 |  |  | 2024-05-22 | 803 | 150 |  | 2024-07-16 | 2024-07-09 | 149 | SEP | SEP | 2024-07-10 | 2024-09-20 | 2024-09-20 | 2024-09-20 | 2024-10-15 | 2024-10-15
44695 | 740-MKWE-S-VU241-105-LH001-40-0 | 1 | true | 3.05 | 740-MKWE-S-VU241-105-LH001-40-0 | LV1-105638.VU241 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | K51 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-04-16 | 2024-04-22 | Büro | 2024-04-26 |  | 2024-04-22 | 2024-05-20 |  |  | 2024-05-22 | 803 | 150 |  | 2024-07-16 | 2024-07-09 | 149 | SEP | SEP | 2024-07-10 | 2024-09-13 | 2024-09-13 | 2024-10-15 | 2024-10-15 | 2024-10-15
44696 | 740-MKWE-S-VU241-106-LH001-65-0 | 1 | false | 12.68 | 740-MKWE-S-VU241-106-LH001-65-0 | LV1-105638.VU241 | 363 | 2.Apr.2024 |  | MC1 | LVL 6 | K51 | TR002 | 2024-02-09 | 2024-02-22 | 2024-02-28 |  | 2024-03-22 | 2024-04-07 | Maxim Tiebe | 2024-04-11 |  | 2024-04-09 |  |  |  |  | 803 | 150 |  |  |  | 150 | SEP | SEP
48793 | 740-MKWE-S-VU241-106-LH001-65-0 | 2 | true | 12.68 | 740-MKWE-S-VU241-106-LH001-65-0 | LV1-105638.VU241 | 363 |  |  | MC1 | LVL 6 | K51 | TR013_1 | 2024-04-15 | 2024-02-22 | 2024-02-28 |  | 2024-03-22 | 2024-04-07 | Büro | 2024-04-11 |  | 2024-04-09 | 2024-04-24 |  |  | 2024-04-26 | 803 | 150 | Modification to be made on site | 2024-07-16 | 2024-07-11 | 150 | SEP | SEP | 2024-08-19 | 2024-09-13 | 2024-09-13 | 2024-10-15 | 2024-10-15 | 2024-10-15
44697 | 740-MKWE-S-VU241-107-LH001-50-0 | 1 | true | 0.09 | 740-MKWE-S-VU241-107-LH001-50-0 | LV1-105638.VU241 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | K51 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-04-03 | 2024-04-10 | Zauner Romania | 2024-04-12 |  | 2024-04-10 | 2024-07-25 |  |  | 2024-07-26 | 803 | 150 |  | 2024-08-21 | 2024-08-05 | 149 | SEP | SEP | 2024-08-19 | 2024-09-20 | 2024-09-20 | 2024-09-20 | 2024-10-15 | 2024-10-15
44698 | 740-MKWE-S-VU241-108-LH001-50-0 | 1 | true | 0.15 | 740-MKWE-S-VU241-108-LH001-50-0 | LV1-105638.VU241 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | K51 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-04-03 | 2024-04-05 | Zauner Romania | 2024-04-12 |  | 2024-04-05 | 2024-07-25 |  |  | 2024-07-26 | 803 | 150 |  | 2024-08-21 | 2024-08-05 | 149 | SEP | SEP | 2024-08-19 | 2024-09-20 | 2024-09-20 | 2024-09-20 | 2024-10-15 | 2024-10-15
44699 | 740-MKWE-S-VU241-109-LH001-50-0 | 1 | true | 0.15 | 740-MKWE-S-VU241-109-LH001-50-0 | LV1-105638.VU241 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | K51 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-04-03 | 2024-04-05 | Zauner Romania | 2024-04-12 |  | 2024-04-05 | 2024-07-25 |  |  | 2024-07-26 | 803 | 150 |  | 2024-08-21 | 2024-08-05 | 149 | SEP | SEP | 2024-08-19 | 2024-09-20 | 2024-09-20 | 2024-09-20
44700 | 740-MKWE-S-VU241-110-LH001-50-0 | 1 | true | 0.15 | 740-MKWE-S-VU241-110-LH001-50-0 | LV1-105638.VU241 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | K51 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-04-03 | 2024-04-10 | Zauner Romania | 2024-04-12 |  | 2024-04-10 | 2024-07-25 |  |  | 2024-07-26 | 803 | 150 |  | 2024-08-21 | 2024-08-05 | 149 | SEP | SEP | 2024-08-19 | 2024-09-20 | 2024-09-20 | 2024-09-20 | 2024-10-15 | 2024-10-15
44701 | 740-MKWE-S-VU241-111-LH001-50-0 | 1 | true | 0.14 | 740-MKWE-S-VU241-111-LH001-50-0 | LV1-105638.VU241 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | K51 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-04-03 | 2024-04-08 | Zauner Romania | 2024-04-12 |  | 2024-04-08 | 2024-07-25 |  |  | 2024-07-26 | 803 | 150 |  | 2024-08-21 | 2024-08-05 | 149 | SEP | SEP | 2024-08-19 | 2024-09-20 | 2024-09-20 | 2024-09-20 | 2024-10-15 | 2024-10-15
44702 | 740-MKWE-S-VU241-112-LH001-50-0 | 1 | true | 0.38 | 740-MKWE-S-VU241-112-LH001-50-0 | LV1-105638.VU241 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | K51 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-04-03 | 2024-04-08 | Zauner Romania | 2024-04-12 |  | 2024-04-08 | 2024-07-25 |  |  | 2024-07-26 | 803 | 150 |  | 2024-08-21 | 2024-08-05 | 149 | SEP | SEP | 2024-08-19 | 2024-09-20 | 2024-09-20 | 2024-09-20 | 2024-10-15 | 2024-10-15
44703 | 740-MKWE-S-VU241-113-LH001-65-0 | 1 | true | 13.74 | 740-MKWE-S-VU241-113-LH001-65-0 | LV1-105638.VU241 | 363 | 2.Apr.2024 |  | MC1 | LVL 6 | K51 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-03-22 | 2024-04-08 | Büro | 2024-04-12 |  | 2024-04-11 | 2024-04-22 |  |  | 2024-04-24 | 803 | 150 |  | 2024-08-21 | 2024-07-09 | 149 | SEP | SEP | 2024-08-19 | 2024-09-13 | 2024-09-13 | 2024-10-15 | 2024-10-15 | 2024-10-15
44704 | 740-MKWE-S-VU241-114-LH001-40-0 | 1 | true | 0.58 | 740-MKWE-S-VU241-114-LH001-40-0 | LV1-105638.VU241 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | K51 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-04-05 | 2024-04-10 | Zauner Romania | 2024-04-12 |  | 2024-04-11 | 2024-07-18 |  |  | 2024-07-24 | 803 | 150 |  | 2024-08-21 | 2024-07-04 | 149 | SEP | SEP | 2024-08-19 | 2024-09-20 | 2024-09-20 | 2024-09-20 | 2024-10-15 | 2024-10-15
44705 | 740-MKWE-S-VU241-115-LH001-40-0 | 1 | true | 0.26 | 740-MKWE-S-VU241-115-LH001-40-0 | LV1-105638.VU241 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | K51 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-04-05 | 2024-04-10 | Zauner Romania | 2024-04-12 |  | 2024-04-11 | 2024-07-18 |  |  | 2024-07-24 | 803 | 150 |  | 2024-08-21 | 2024-07-04 | 149 | SEP | SEP | 2024-08-19 | 2024-09-20 | 2024-09-20 | 2024-09-20 | 2024-10-15 | 2024-10-15
44706 | 740-MKWE-S-VU241-116-LH001-40-0 | 1 | true | 0.51 | 740-MKWE-S-VU241-116-LH001-40-0 | LV1-105638.VU241 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | K51 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-04-05 | 2024-04-11 | Zauner Romania | 2024-04-12 |  | 2024-04-11 | 2024-07-18 |  |  | 2024-07-24 | 803 | 150 |  | 2024-08-21 | 2024-07-04 | 149 | SEP | SEP | 2024-08-19 | 2024-09-20 | 2024-09-20 | 2024-09-20 | 2024-10-15 | 2024-10-15
44707 | 740-MKWE-S-VU241-117-LH001-40-0 | 1 | true | 0.24 | 740-MKWE-S-VU241-117-LH001-40-0 | LV1-105638.VU241 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | K51 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-04-05 |  | Zauner Romania | 2024-04-12 |  | 2024-04-11 | 2024-07-18 |  |  | 2024-07-24 | 803 | 150 |  | 2024-08-21 | 2024-07-04 | 149 | SEP | SEP | 2024-08-19 | 2024-09-20 | 2024-09-20 | 2024-09-20 | 2024-10-15 | 2024-10-15
44708 | 740-MKWE-S-VU241-118-LH001-50-0 | 1 | true | 1.16 | 740-MKWE-S-VU241-118-LH001-50-0 | LV1-105638.VU241 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | K51 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-04-03 | 2024-04-10 | Zauner Romania | 2024-04-12 |  | 2024-04-10 | 2024-07-18 |  |  | 2024-07-24 | 803 | 150 |  | 2024-08-21 | 2024-07-04 | 149 | SEP | SEP | 2024-08-19 | 2024-09-20 | 2024-09-20 | 2024-09-20 | 2024-10-15 | 2024-10-15
44709 | 740-MKWE-S-VU241-119-LH001-40-0 | 1 | true | 0.21 | 740-MKWE-S-VU241-119-LH001-40-0 | LV1-105638.VU241 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | K51 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-04-05 | 2024-04-10 | Zauner Romania | 2024-04-12 |  | 2024-04-11 |  |  |  | 2024-07-24 | 803 | 150 |  | 2024-08-21 | 2024-07-04 | 149 | SEP | SEP | 2024-08-19 | 2024-09-20 | 2024-09-20 | 2024-09-20 | 2024-10-15 | 2024-10-15
44710 | 740-MKWE-S-VU241-120-LH001-50-0 | 1 | true | 0.52 | 740-MKWE-S-VU241-120-LH001-50-0 | LV1-105638.VU241 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | K51 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-04-03 | 2024-04-05 | Zauner Romania | 2024-04-12 |  | 2024-04-05 | 2024-07-18 |  |  | 2024-07-24 | 803 | 150 |  | 2024-08-21 | 2024-07-04 | 149 | SEP | SEP | 2024-08-19 | 2024-09-20 | 2024-09-20 | 2024-09-20 | 2024-10-15 | 2024-10-15
44711 | 740-MKWH-R-VH001-102-LH130-65-0 | 1 | false | 1.9 | 740-MKWH-R-VH001-102-LH130-65-0 | LV0-105623.VH001 | 362 | 2.Apr.2024 |  | MC1 | LVL 6 | T60 | TR002 | 2024-02-11 | 2024-02-24 | 2024-03-01 |  |  |  | Zauner Romania | [7 empty] | 804 | 150 |  |  |  | 149 | SEP | SEP
45515 | 740-MKWH-R-VH001-102-LH130-65-0 | 2 | true | 1.9 | 740-MKWH-R-VH001-102-LH130-65-0 | LV0-105623.VH001 | 362 | 2.Apr.2024 |  | MC1 | LVL 6 | T60 | TR005 | 2024-03-03 | 2024-02-23 | 2024-02-29 |  | 2024-04-02 | 2024-04-03 | Büro | 2024-04-12 |  | 2024-04-05 | 2024-05-02 |  |  | 2024-05-13 | 804 | 150 |  |  | 2024-07-05 | 149 | SEP | SEP | 2024-07-23
44712 | 740-MKWH-R-VH002-102-LH130-65-0 | 1 | false | 1.92 | 740-MKWH-R-VH002-102-LH130-65-0 | LV1-105623.VH002 | 362 | 2.Apr.2024 |  | MC1 | LVL 6 | T60 | TR002 | 2024-02-11 | 2024-02-24 | 2024-03-01 |  |  |  | Zauner Romania | [7 empty] | 804 | 150 |  |  |  | 149 | SEP | SEP
45516 | 740-MKWH-R-VH002-102-LH130-65-0 | 2 | true | 1.92 | 740-MKWH-R-VH002-102-LH130-65-0 | LV1-105623.VH002 | 362 | 2.Apr.2024 |  | MC1 | LVL 6 | T60 | TR005 | 2024-03-03 | 2024-02-23 | 2024-02-29 |  | 2024-04-02 | 2024-04-04 | Büro | 2024-04-12 |  | 2024-04-08 | 2024-05-08 |  |  | 2024-05-15 | 804 | 150 |  |  | 2024-07-05 | 149 | SEP | SEP | 2024-09-02 | 2024-09-02
44713 | 740-MKWH-R-VH003-102-LH130-50-0 | 1 | false | 3.92 | 740-MKWH-R-VH003-102-LH130-50-0 | LV1-105623.VH003 | 362 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR002 | 2024-02-11 | 2024-02-24 | 2024-03-01 |  |  |  | Zauner Romania | [7 empty] | 804 | 150 |  |  |  | 149 | SEP | SEP
45517 | 740-MKWH-R-VH003-102-LH130-50-0 | 2 | true | 3.92 | 740-MKWH-R-VH003-102-LH130-50-0 | LV1-105623.VH003 | 362 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR005 | 2024-03-03 | 2024-02-23 | 2024-02-29 |  | 2024-04-04 | 2024-04-05 | Büro | 2024-04-12 |  | 2024-04-08 | 2024-04-19 |  |  | 2024-04-30 | 804 | 150 |  |  | 2024-07-15 | 149 | SEP | SEP | 2024-07-23
44714 | 740-MKWH-R-VH004-102-LH130-50-0 | 1 | false | 1.45 | 740-MKWH-R-VH004-102-LH130-50-0 | LV0-105623.VH004 | 362 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR002 | 2024-02-11 | 2024-02-24 | 2024-03-01 |  |  |  | Zauner Romania | [7 empty] | 804 | 150 |  |  |  | 149 | SEP | SEP
45518 | 740-MKWH-R-VH004-102-LH130-50-0 | 2 | true | 1.45 | 740-MKWH-R-VH004-102-LH130-50-0 | LV0-105623.VH004 | 362 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR005 | 2024-03-03 | 2024-02-23 | 2024-02-29 |  | 2024-04-08 | 2024-04-10 | Büro | 2024-04-12 |  | 2024-04-11 | 2024-05-07 |  |  | 2024-05-13 | 804 | 150 |  |  | 2024-07-05 | 149 | SEP | SEP | 2024-09-02 | 2024-09-02 | 2024-09-02 | 2024-09-02
44715 | 740-MKWH-R-VH005-102-LH130-65-0 | 1 | false | 2.7 | 740-MKWH-R-VH005-102-LH130-65-0 | LV0-105623.VH005 | 362 | 2.Apr.2024 |  | MC1 | LVL 6 | T60 | TR002 | 2024-02-11 | 2024-02-24 | 2024-03-01 |  |  |  | Zauner Romania | [7 empty] | 804 | 150 |  |  |  | 149 | SEP | SEP
45519 | 740-MKWH-R-VH005-102-LH130-65-0 | 2 | true | 2.7 | 740-MKWH-R-VH005-102-LH130-65-0 | LV0-105623.VH005 | 362 | 2.Apr.2024 |  | MC1 | LVL 6 | T60 | TR005 | 2024-03-03 | 2024-02-23 | 2024-02-29 |  | 2024-04-02 | 2024-04-03 | Büro | 2024-04-12 |  | 2024-04-05 | 2024-05-02 |  |  | 2024-05-08 | 804 | 150 |  |  | 2024-07-05 | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
44716 | 740-MKWH-R-VH005-201-LH130-25-0 | 1 | true | 1.4 | 740-MKWH-R-VH005-201-LH130-25-0 | LV0-105624.VH005 | 362 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-04-19 | 2024-04-25 | Büro | 2024-04-26 |  | 2024-04-25 | 2024-09-10 |  |  | 2024-09-16 | 804 | 150 |  |  | 2024-09-17 | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
44717 | 740-MKWH-R-VH005-202-LH130-25-0 | 1 | false | 0.83 | 740-MKWH-R-VH005-202-LH130-25-0 | LV0-105624.VH005 | 362 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR002 | 2024-02-11 | 2024-02-24 | 2024-03-01 |  |  |  | Zauner Romania | [7 empty] | 804 | 150 |  |  |  | 149 | SEP | SEP
45520 | 740-MKWH-R-VH005-202-LH130-25-0 | 2 | true | 0.83 | 740-MKWH-R-VH005-202-LH130-25-0 | LV0-105624.VH005 | 362 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR005 | 2024-03-03 | 2024-02-23 | 2024-02-29 |  | 2024-04-12 | 2024-04-16 | Büro | 2024-04-26 |  | 2024-04-17 | 2024-09-10 |  |  | 2024-09-16 | 804 | 150 |  |  | 2024-09-17 | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
44718 | 740-MKWH-R-VH005-203-LH130-25-0 | 1 | true | 1.61 | 740-MKWH-R-VH005-203-LH130-25-0 | LV0-105624.VH005 | 362 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-04-18 | 2024-04-19 | Büro | 2024-04-26 |  | 2024-04-19 | 2024-09-10 |  |  | 2024-09-18 | 804 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
44719 | 740-MKWH-R-VH005-204-LH130-25-0 | 1 | true | 2.16 | 740-MKWH-R-VH005-204-LH130-25-0 | LV0-105624.VH005 | 362 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-04-19 | 2024-04-22 | Büro | 2024-04-26 |  | 2024-04-22 | 2024-09-05 |  |  | 2024-09-11 | 804 | 150 |  |  | 2024-09-11 | 149 | SEP | SEP
44720 | 740-MKWH-R-VH005-205-LH130-25-0 | 1 | true | 0.24 | 740-MKWH-R-VH005-205-LH130-25-0 | LV0-105624.VH005 | 362 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-04-16 | 2024-04-18 | Büro | 2024-04-26 |  | 2024-04-18 | 2024-09-05 |  |  | 2024-09-10 | 804 | 150 |  |  | 2024-09-11 | 149 | SEP | SEP
44721 | 740-MKWH-R-VH005-206-LH130-25-0 | 1 | true | 7.91 | 740-MKWH-R-VH005-206-LH130-25-0 | LV0-105624.VH005 | 362 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-04-16 | 2024-04-19 | Büro | 2024-04-26 |  | 2024-04-19 | 2024-05-17 |  | 2024-05-20 | 2024-10-30 | 804 | 150 |  |  | 2024-10-31 | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
44722 | 740-MKWH-R-VU211-112-LH001-150-0 | 1 | false | 49.77 | 740-MKWH-R-VU211-112-LH001-150-0 | LV1-105638.VU211 | 363 | 2.Apr.2024 |  | MC1 | LVL 6 | T60 | TR002 | 2024-02-11 | 2024-02-24 |  |  |  |  | Friedwagner Paul | [7 empty] | 804 | 150 |  |  |  | 149 | SEP | SEP
44970 | 740-MKWH-R-VU211-112-LH001-150-0 | 2 | false | 49.77 | 740-MKWH-R-VU211-112-LH001-150-0 | LV1-105638.VU211 | 363 | 2.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-21 | 2024-02-26 | 2024-02-29 |  | 2024-03-24 | 2024-03-28 | Büro | 2024-04-01 |  | 2024-04-01 | 2024-04-16 | 2024-04-16 |  | 2024-04-24 | 804 | 150 |  |  |  | 149 | SEP | SEP
52892 | 740-MKWH-R-VU211-112-LH001-150-0 | 3 | false | 49.77 | 740-MKWH-R-VU211-112-LH001-150-0 | LV1-105638.VU211 | 363 |  |  | MC1 | LVL 6 | T60 | TR027_1 | 2024-06-27 | 2024-02-26 | 2024-02-29 |  | 2024-03-24 | 2024-03-28 |  | 2024-04-01 |  | 2024-04-01 | 2024-04-16 | 2024-04-16 |  | 2024-04-24 | 804 | 150 |  |  | 2024-07-17 | 149 | SEP | SEP | 2024-07-23 | 2024-08-06 | 2024-08-06
62775 | 740-MKWH-R-VU211-112-LH001-150-0 | 4 | true | 49.77 | 740-MKWH-R-VU211-112-LH001-150-0 | LV1-105638.VU211 | 363 |  |  | MC1 | LVL 6 | T60 | TR029_3 | 2024-08-07 | 2024-02-26 | 2024-02-29 |  | 2024-03-24 | 2024-03-28 |  | 2024-04-01 |  | 2024-04-01 | 2024-04-16 | 2024-04-16 |  | 2024-04-24 | 804 | 150 |  | 2024-08-28 | 2024-07-17 | 149 | SEP | SEP | 2024-08-19 | 2024-08-12 | 2024-08-19 | 2024-09-02 | 2024-10-07 | 2024-10-07
44723 | 740-MKWH-R-VU211-114-LH130-65-0 | 1 | true | 18.67 | 740-MKWH-R-VU211-114-LH130-65-0 | LV1-105638.VU211 | 362 | 2.Apr.2024 |  | MC1 | LVL 6 | T60 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-03-22 | 2024-04-05 | Büro | 2024-04-12 |  | 2024-04-08 | 2024-04-26 |  |  | 2024-05-02 | 804 | 150 |  | 2024-08-20 | 2024-07-05 | 149 | SEP | SEP | 2024-07-23 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-10-07 | 2024-10-07
44724 | 740-MKWH-R-VU211-115-LH130-32-0 | 1 | true | 7.91 | 740-MKWH-R-VU211-115-LH130-32-0 | LV1-105638.VU211 | 362 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-04-16 | 2024-04-18 | Büro | 2024-04-26 |  | 2024-04-18 | 2024-05-15 |  |  | 2024-05-17 | 804 | 150 |  | 2024-08-20 | 2024-07-05 | 149 | SEP | SEP | 2024-07-23 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-10-07 | 2024-10-07
44725 | 740-MKWH-R-VU211-117-LH130-50-0 | 1 | true | 16.24 | 740-MKWH-R-VU211-117-LH130-50-0 | LV1-105638.VU211 | 362 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-04-05 | 2024-04-09 | Büro | 2024-04-12 |  | 2024-04-11 | 2024-04-30 |  |  | 2024-05-06 | 804 | 150 |  | 2024-08-20 | 2024-07-05 | 149 | SEP | SEP | 2024-07-23 | 2024-08-12 | 2024-08-12 | 2024-09-02 | 2024-10-07 | 2024-10-07
44726 | 740-MKWH-R-VU211-204-LH001-125-0 | 1 | true | 17.87 | 740-MKWH-R-VU211-204-LH001-125-0 | LV1-105639.VU211 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR002 | 2024-02-12 | 2024-02-25 | 2024-03-02 |  | 2024-04-01 | 2024-04-05 | Büro | 2024-04-12 |  | 2024-04-08 | 2024-04-18 |  |  | 2024-04-30 | 804 | 150 |  | 2024-08-20 | 2024-07-05 | 149 | SEP | SEP | 2024-07-23 | 2024-08-19 | 2024-08-26 | 2024-08-26 | 2024-10-07 | 2024-10-07
44727 | 740-MKWH-S-VH001-101-LH130-65-0 | 1 | false | 3.52 | 740-MKWH-S-VH001-101-LH130-65-0 | LV0-105623.VH001 | 362 | 2.Apr.2024 |  | MC1 | LVL 6 | T60 | TR002 | 2024-02-11 | 2024-02-24 | 2024-03-01 |  |  |  | Zauner Romania | [7 empty] | 804 | 150 |  |  |  | 149 | SEP | SEP
45521 | 740-MKWH-S-VH001-101-LH130-65-0 | 2 | true | 3.52 | 740-MKWH-S-VH001-101-LH130-65-0 | LV0-105623.VH001 | 362 | 2.Apr.2024 |  | MC1 | LVL 6 | T60 | TR005 | 2024-03-03 | 2024-02-23 | 2024-02-29 |  | 2024-04-02 | 2024-04-08 | Büro | 2024-04-12 |  | 2024-04-09 | 2024-05-02 |  |  | 2024-05-13 | 804 | 150 |  |  | 2024-07-05 | 149 | SEP | SEP | 2024-07-23 | 2024-08-26 | 2024-08-26 | 2024-09-02
44728 | 740-MKWH-S-VH002-101-LH130-65-0 | 1 | false | 3.04 | 740-MKWH-S-VH002-101-LH130-65-0 | LV1-105623.VH002 | 362 | 2.Apr.2024 |  | MC1 | LVL 6 | T60 | TR002 | 2024-02-11 | 2024-02-24 | 2024-03-01 |  |  |  | Zauner Romania | [7 empty] | 804 | 150 |  |  |  | 149 | SEP | SEP
45522 | 740-MKWH-S-VH002-101-LH130-65-0 | 2 | true | 3.04 | 740-MKWH-S-VH002-101-LH130-65-0 | LV1-105623.VH002 | 362 | 2.Apr.2024 |  | MC1 | LVL 6 | T60 | TR005 | 2024-03-05 | 2024-02-25 | 2024-03-02 |  | 2024-04-01 | 2024-04-03 | Büro | 2024-04-12 |  | 2024-04-05 | 2024-05-09 |  |  | 2024-05-15 | 804 | 150 |  |  | 2024-07-05 | 149 | SEP | SEP | 2024-07-23 | 2024-09-02 | 2024-09-02
44729 | 740-MKWH-S-VH003-101-LH130-50-0 | 1 | false | 2.9 | 740-MKWH-S-VH003-101-LH130-50-0 | LV1-105623.VH003 | 362 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR002 | 2024-02-11 | 2024-02-24 | 2024-03-01 |  |  |  | Zauner Romania | [7 empty] | 804 | 150 |  |  |  | 149 | SEP | SEP
45523 | 740-MKWH-S-VH003-101-LH130-50-0 | 2 | true | 2.9 | 740-MKWH-S-VH003-101-LH130-50-0 | LV1-105623.VH003 | 362 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR005 | 2024-03-03 | 2024-02-23 | 2024-02-29 |  | 2024-04-05 | 2024-04-08 | Büro | 2024-04-12 |  | 2024-04-09 | 2024-04-19 |  |  | 2024-05-01 | 804 | 150 |  |  | 2024-07-05 | 149 | SEP | SEP | 2024-07-23 | 2024-08-12 | 2024-08-12 | 2024-08-12
44730 | 740-MKWH-S-VH004-101-LH130-50-0 | 1 | false | 2.57 | 740-MKWH-S-VH004-101-LH130-50-0 | LV0-105623.VH004 | 362 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR002 | 2024-02-11 | 2024-02-24 | 2024-03-01 |  |  |  | Zauner Romania | [7 empty] | 804 | 150 |  |  |  | 149 | SEP | SEP
45524 | 740-MKWH-S-VH004-101-LH130-50-0 | 2 | true | 2.57 | 740-MKWH-S-VH004-101-LH130-50-0 | LV0-105623.VH004 | 362 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR005 | 2024-03-03 | 2024-02-23 | 2024-02-29 |  | 2024-04-02 | 2024-04-08 | Büro | 2024-04-12 |  | 2024-04-08 | 2024-05-07 |  |  | 2024-05-13 | 804 | 150 |  |  | 2024-07-05 | 149 | SEP | SEP | 2024-07-23 | 2024-08-12 | 2024-08-12 | 2024-08-12
44731 | 740-MKWH-S-VH005-101-LH130-65-0 | 1 | false | 1.54 | 740-MKWH-S-VH005-101-LH130-65-0 | LV0-105623.VH005 | 362 | 2.Apr.2024 |  | MC1 | LVL 6 | T60 | TR002 | 2024-02-11 | 2024-02-24 | 2024-03-01 |  |  |  | Zauner Romania | [7 empty] | 804 | 150 |  |  |  | 149 | SEP | SEP
45525 | 740-MKWH-S-VH005-101-LH130-65-0 | 2 | false | 1.54 | 740-MKWH-S-VH005-101-LH130-65-0 | LV0-105623.VH005 | 362 | 2.Apr.2024 |  | MC1 | LVL 6 | T60 | TR005 | 2024-03-03 | 2024-02-23 | 2024-02-29 |  | 2024-04-02 | 2024-04-05 | Büro | 2024-04-12 |  | 2024-04-08 | 2024-05-02 |  |  | 2024-06-11 | 804 | 150 |  |  |  | 149 | SEP | SEP
52776 | 740-MKWH-S-VH005-101-LH130-65-0 | 3 | true | 1.54 | 740-MKWH-S-VH005-101-LH130-65-0 | LV0-105623.VH005 | 362 |  |  | MC1 | LVL 6 | T60 | TR025_1 | 2024-06-18 | 2024-02-23 | 2024-02-29 |  | 2024-04-02 | 2024-04-05 | Büro | 2024-04-12 |  | 2024-04-08 | 2024-06-18 |  |  | 2024-06-11 | 804 | 150 |  | 2024-07-24 | 2024-08-06 | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
44732 | 740-MKWH-S-VH005-201-LH130-25-0 | 1 | true | 1.18 | 740-MKWH-S-VH005-201-LH130-25-0 | LV0-105624.VH005 | 362 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-04-16 | 2024-04-17 | Büro | 2024-04-26 |  | 2024-04-18 | 2024-09-10 |  |  | 2024-09-16 | 804 | 150 |  |  | 2024-09-17 | 149 | SEP | SEP
44733 | 740-MKWH-S-VH005-202-LH130-25-0 | 1 | true | 0.35 | 740-MKWH-S-VH005-202-LH130-25-0 | LV0-105624.VH005 | 362 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-04-16 | 2024-04-18 | Büro | 2024-04-26 |  | 2024-04-18 | 2024-09-10 |  |  | 2024-09-16 | 804 | 150 |  |  | 2024-09-17 | 149 | SEP | SEP
44734 | 740-MKWH-S-VH005-203-LH130-25-0 | 1 | true | 1.69 | 740-MKWH-S-VH005-203-LH130-25-0 | LV0-105624.VH005 | 362 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-04-16 | 2024-04-18 | Büro | 2024-04-26 |  | 2024-04-18 | 2024-09-10 |  |  | 2024-09-18 | 804 | 150 |  |  |  | 149 | SEP | SEP
44735 | 740-MKWH-S-VH005-204-LH130-25-0 | 1 | true | 1.71 | 740-MKWH-S-VH005-204-LH130-25-0 | LV0-105624.VH005 | 362 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-04-16 | 2024-04-17 | Büro | 2024-04-26 |  | 2024-04-18 | 2024-09-05 |  |  | 2024-09-11 | 804 | 150 |  |  | 2024-09-11 | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
44736 | 740-MKWH-S-VH005-205-LH130-25-0 | 1 | true | 0.15 | 740-MKWH-S-VH005-205-LH130-25-0 | LV0-105624.VH005 | 362 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-04-12 | 2024-04-16 | Büro | 2024-04-26 |  | 2024-04-17 | 2024-09-05 |  |  | 2024-09-10 | 804 | 150 |  |  | 2024-09-11 | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
44737 | 740-MKWH-S-VH005-206-LH130-25-0 | 1 | true | 7.75 | 740-MKWH-S-VH005-206-LH130-25-0 | LV0-105624.VH005 | 362 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-04-12 | 2024-04-16 | Büro | 2024-04-26 |  | 2024-04-17 | 2024-05-17 |  | 2024-05-20 | 2024-10-30 | 804 | 150 |  |  | 2024-11-04 | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
44738 | 740-MKWH-S-VU211-101-LH001-150-0 | 1 | false | 66.3 | 740-MKWH-S-VU211-101-LH001-150-0 | LV1-105638.VU211 | 363 | 2.Apr.2024 |  | MC1 | LVL 6 | T60 | TR002 | 2024-02-11 | 2024-02-24 |  |  |  |  | Friedwagner Paul | [7 empty] | 804 | 150 |  |  |  | 149 | SEP | SEP
44971 | 740-MKWH-S-VU211-101-LH001-150-0 | 2 | false | 66.3 | 740-MKWH-S-VU211-101-LH001-150-0 | LV1-105638.VU211 | 363 | 2.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-21 | 2024-02-26 | 2024-02-29 |  | 2024-03-24 | 2024-04-03 | Büro | 2024-04-12 |  | 2024-04-05 | 2024-04-18 |  |  | 2024-05-01 | 804 | 150 |  |  |  | 149 | SEP | SEP
52893 | 740-MKWH-S-VU211-101-LH001-150-0 | 3 | false | 66.3 | 740-MKWH-S-VU211-101-LH001-150-0 | LV1-105638.VU211 | 363 |  |  | MC1 | LVL 6 | T60 | TR027_1 | 2024-06-27 | 2024-02-26 | 2024-02-29 |  | 2024-03-24 | 2024-04-03 |  | 2024-04-12 |  | 2024-04-05 | 2024-04-18 |  |  | 2024-05-01 | 804 | 150 |  |  | 2024-07-17 | 149 | SEP | SEP | 2024-07-23 | 2024-08-06 | 2024-08-06
62777 | 740-MKWH-S-VU211-101-LH001-150-0 | 4 | true | 66.3 | 740-MKWH-S-VU211-101-LH001-150-0 | LV1-105638.VU211 | 363 |  |  | MC1 | LVL 6 | T60 | TR029_3 | 2024-08-07 | 2024-02-26 | 2024-02-29 |  | 2024-03-24 | 2024-04-03 |  | 2024-04-12 |  | 2024-04-05 | 2024-04-18 |  |  | 2024-05-01 | 804 | 150 |  | 2024-08-20 | 2024-07-17 | 149 | SEP | SEP | 2024-08-19 | 2024-08-12 | 2024-08-19 | 2024-08-26 | 2024-10-07 | 2024-10-07
44739 | 740-MKWH-S-VU211-102-LH130-50-0 | 1 | true | 17.02 | 740-MKWH-S-VU211-102-LH130-50-0 | LV1-105638.VU211 | 362 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-04-05 | 2024-04-12 | Büro | 2024-04-12 |  | 2024-04-12 | 2024-04-30 |  |  | 2024-05-06 | 804 | 150 |  | 2024-08-20 | 2024-07-05 | 149 | SEP | SEP | 2024-07-23 | 2024-08-12 | 2024-08-12 | 2024-08-26 | 2024-10-07 | 2024-10-07
44740 | 740-MKWH-S-VU211-107-LH130-32-0 | 1 | true | 7.94 | 740-MKWH-S-VU211-107-LH130-32-0 | LV1-105638.VU211 | 362 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR002 | 2024-02-10 | 2024-02-23 | 2024-02-29 |  | 2024-04-12 | 2024-04-15 | Büro | 2024-04-26 |  | 2024-04-17 | 2024-05-15 |  |  | 2024-05-17 | 804 | 150 |  | 2024-08-20 | 2024-07-05 | 149 | SEP | SEP | 2024-07-23 | 2024-08-06 | 2024-08-06 | 2024-08-26 | 2024-10-07 | 2024-10-07
44741 | 740-MKWH-S-VU211-108-LH130-65-0 | 1 | false | 20.86 | 740-MKWH-S-VU211-108-LH130-65-0 | LV1-105638.VU211 | 362 | 2.Apr.2024 |  | MC1 | LVL 6 | T60 | TR002 | 2024-02-11 | 2024-02-24 |  |  |  |  | Friedwagner Paul | [7 empty] | 804 | 150 |  |  |  | 149 | SEP | SEP
44972 | 740-MKWH-S-VU211-108-LH130-65-0 | 2 | true | 20.86 | 740-MKWH-S-VU211-108-LH130-65-0 | LV1-105638.VU211 | 362 | 2.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-21 | 2024-02-26 | 2024-02-29 |  | 2024-03-19 | 2024-03-27 | Büro | 2024-04-12 |  | 2024-04-02 | 2024-06-03 |  |  | 2024-06-07 | 804 | 150 |  | 2024-08-20 | 2024-07-05 | 149 | SEP | SEP | 2024-07-23 | 2024-08-26 | 2024-08-26 | 2024-09-02 | 2024-10-07 | 2024-10-07
44952 | 740-DH3-VH001-101-LH011-25-0 | 1 | true | 0.86 | 740-DH3-VH001-101-LH011-25-0 | LV1-105623.VH001 | 369 | 26.Apr.2024 |  | MC1 | LVL 6 | W23 | TR003 | 2024-02-20 | 2024-02-26 | 2024-02-29 |  | 2024-04-12 | 2024-04-16 | Büro | 2024-04-26 |  | 2024-04-17 | 2024-05-15 |  |  | 2024-07-16 | 827 | 150 |  | 2024-08-28 | 2024-07-22 | 149 | SEP | SEP |  |  | 2024-11-15 | 2024-11-15
44953 | 740-DH3-VH002-101-LH011-25-0 | 1 | true | 0.73 | 740-DH3-VH002-101-LH011-25-0 | LV1-105623.VH002 | 369 | 26.Apr.2024 |  | MC1 | LVL 6 | W23 | TR003 | 2024-02-20 | 2024-02-26 | 2024-02-29 |  | 2024-04-12 | 2024-04-15 | Büro | 2024-04-26 |  | 2024-04-15 | 2024-07-16 |  |  | 2024-10-24 | 827 | 150 |  | 2024-08-28 | 2024-07-22 | 149 | SEP | SEP |  |  | 2024-11-15 | 2024-11-15
44954 | 740-DH3-VH003-101-LH011-20-0 | 1 | true | 0.88 | 740-DH3-VH003-101-LH011-20-0 | LV1-105623.VH003 | 369 | 26.Apr.2024 |  | MC1 | LVL 6 | W23 | TR003 | 2024-02-20 | 2024-02-26 | 2024-02-29 |  | 2024-04-18 | 2024-04-19 | Attila Henter | 2024-04-26 |  | 2024-04-19 | 2024-07-16 |  |  | 2024-07-19 | 827 | 150 |  | 2024-07-24 | 2024-07-24 | 149 | SEP | SEP |  |  | 2024-11-15 | 2024-11-15
44955 | 740-DH3-VH004-101-LH011-20-0 | 1 | true | 0.77 | 740-DH3-VH004-101-LH011-20-0 | LV1-105623.VH004 | 369 | 26.Apr.2024 |  | MC1 | LVL 6 | W23 | TR003 | 2024-02-20 | 2024-02-26 | 2024-02-29 |  | 2024-04-18 | 2024-04-19 | Satu Mare | 2024-04-26 |  | 2024-04-19 |  |  |  | 2024-07-19 | 827 | 150 |  |  | 2024-07-24 | 149 | SEP | SEP |  |  | 2024-11-15 | 2024-11-15
44956 | 740-DH3-VH005-101-LH011-20-0 | 1 | true | 0.88 | 740-DH3-VH005-101-LH011-20-0 | LV1-105623.VH005 | 369 | 26.Apr.2024 |  | MC1 | LVL 6 | W23 | TR003 | 2024-02-20 | 2024-02-26 | 2024-02-29 |  | 2024-04-18 | 2024-04-19 | Büro | 2024-04-26 |  | 2024-04-19 | 2024-05-15 |  |  | 2024-07-10 | 827 | 150 |  | 2024-08-28 | 2024-07-22 | 149 | SEP | SEP |  |  | 2024-11-15 | 2024-11-15
44957 | 740-DH3-VH091-106-LH011-32-0 | 1 | true | 3.69 | 740-DH3-VH091-106-LH011-32-0 | LV1-105638.VU091 | 369 | 26.Apr.2024 |  | MC1 | LVL 6 | W23 | TR003 | 2024-02-20 | 2024-02-26 | 2024-02-29 |  | 2024-04-16 | 2024-04-19 | Büro | 2024-04-26 |  | 2024-04-19 | 2024-05-15 |  | 2024-05-16 | 2024-10-24 | 827 | 150 |  | 2024-08-22 | 2024-07-18 | 149 | SEP | SEP
44958 | 740-DH3-VU091-101-LH011-50-0 | 1 | false | 37.49 | 740-DH3-VU091-101-LH011-50-0 | LV1-105638.VU091 | 369 | 2.Apr.2024 |  | MC1 | LVL 6 | W23 | TR003 | 2024-02-22 | 2024-02-27 |  |  |  |  | Friedwagner Paul | [7 empty] | 827 | 150 |  |  |  | 149 | SEP | SEP
45238 | 740-DH3-VU091-101-LH011-50-0 | 2 | true | 37.49 | 740-DH3-VU091-101-LH011-50-0 | LV1-105638.VU091 | 369 | 2.Apr.2024 |  | MC1 | LVL 6 | W23 | TR004 | 2024-02-23 | 2024-03-02 | 2024-03-03 |  | 2024-03-22 | 2024-03-22 | Büro | 2024-04-01 |  | 2024-03-24 | 2024-04-15 |  |  | 2024-04-19 | 827 | 150 |  | 2024-08-22 | 2024-07-09 | 149 | SEP | SEP | 2024-08-20 | 2024-09-09 | 2024-09-09 | 2024-09-09 | 2024-09-23 | 2024-09-23
44959 | 740-DH3-VU091-102-LH011-50-0 | 1 | true | 34.74 | 740-DH3-VU091-102-LH011-50-0 | LV1-105638.VU091 | 369 | 2.Apr.2024 |  | MC1 | LVL 6 | W23 | TR003 | 2024-02-21 | 2024-02-26 | 2024-02-29 |  | 2024-03-22 | 2024-03-25 | Büro | 2024-04-01 |  | 2024-03-30 | 2024-04-10 |  |  | 2024-04-16 | 827 | 150 |  | 2024-08-22 | 2024-07-09 | 149 | SEP | SEP | 2024-08-20 | 2024-09-09 | 2024-09-09 | 2024-09-09 | 2024-09-23 | 2024-09-23
44960 | 740-DH3-VU091-103-LH011-20-0 | 1 | true | 9.71 | 740-DH3-VU091-103-LH011-20-0 | LV1-105638.VU091 | 369 | 26.Apr.2024 |  | MC1 | LVL 6 | W23 | TR003 | 2024-02-20 | 2024-02-26 | 2024-02-29 |  | 2024-04-16 | 2024-04-19 | Büro | 2024-04-26 |  | 2024-04-24 | 2024-05-15 |  |  | 2024-05-17 | 827 | 150 |  | 2024-08-22 | 2024-07-09 | 149 | SEP | SEP | 2024-08-20 | 2024-09-09 | 2024-09-09 | 2024-09-09 | 2024-09-23 | 2024-09-23
44961 | 740-DH3-VU091-104-LH011-20-0 | 1 | false | 9.81 | 740-DH3-VU091-104-LH011-20-0 | LV1-105638.VU091 | 369 | 26.Apr.2024 |  | MC1 | LVL 6 | W23 | TR003 | 2024-02-21 | 2024-02-27 |  |  |  |  | Friedwagner Paul | [7 empty] | 827 | 150 |  |  |  | 149 | SEP | SEP
45239 | 740-DH3-VU091-104-LH011-20-0 | 2 | true | 9.81 | 740-DH3-VU091-104-LH011-20-0 | LV1-105638.VU091 | 369 | 26.Apr.2024 |  | MC1 | LVL 6 | W23 | TR004 | 2024-02-23 | 2024-03-02 | 2024-03-03 |  | 2024-04-18 | 2024-04-26 | Büro | 2024-04-26 |  | 2024-04-26 | 2024-05-15 |  | 2024-05-20 | 2024-10-24 | 827 | 150 |  |  | 2024-07-09 | 149 | SEP | SEP | 2024-08-20 | 2024-09-09 | 2024-09-09 | 2024-09-09 | 2024-09-23 | 2024-09-23
44962 | 740-DH3-VU091-105-LH011-50-0 | 1 | true | 2.21 | 740-DH3-VU091-105-LH011-50-0 | LV1-105638.VU091 | 369 | 26.Apr.2024 |  | MC1 | LVL 6 | W23 | TR003 | 2024-02-20 | 2024-02-26 | 2024-02-29 |  | 2024-04-05 | 2024-04-10 | Büro | 2024-04-12 |  | 2024-04-10 | 2024-05-08 |  |  | 2024-05-13 | 827 | 150 |  | 2024-08-22 | 2024-07-09 | 149 | SEP | SEP | 2024-08-20 | 2024-09-09 | 2024-09-09 | 2024-09-09
44963 | 740-DH3-VU091-107-LH011-20-0 | 1 | true | 3.33 | 740-DH3-VU091-107-LH011-20-0 | LV1-105638.VU091 | 369 | 26.Apr.2024 |  | MC1 | LVL 6 | W23 | TR003 | 2024-02-20 | 2024-02-26 | 2024-02-29 |  | 2024-04-18 | 2024-04-24 | Büro | 2024-04-26 |  | 2024-04-24 | 2024-05-14 |  | 2024-05-15 | 2024-10-24 | 827 | 150 |  | 2024-08-22 | 2024-07-05 | 149 | SEP | SEP | 2024-08-20 | 2024-09-13 | 2024-09-13 | 2024-09-13 | 2024-09-23 | 2024-09-23
44964 | 740-DH3-VU091-108-LH011-40-0 | 1 | false | 4.15 | 740-DH3-VU091-108-LH011-40-0 | LV1-105638.VU091 | 369 | 26.Apr.2024 |  | MC1 | LVL 6 | W23 | TR003 | 2024-02-21 | 2024-02-27 | 2024-03-01 |  |  |  | Zauner Romania | [7 empty] | 827 | 150 |  |  |  | 149 | SEP | SEP
47230 | 740-DH3-VU091-108-LH011-40-0 | 2 | true | 4.15 | 740-DH3-VU091-108-LH011-40-0 | LV1-105638.VU091 | 369 | 26.Apr.2024 |  | MC1 | LVL 6 | W23 | TR011 | 2024-03-24 | 2024-04-04 | 2024-04-07 |  | 2024-04-12 | 2024-04-16 | Büro | 2024-04-26 |  | 2024-04-16 | 2024-05-14 |  |  | 2024-05-15 | 827 | 150 |  | 2024-08-22 | 2024-07-05 | 149 | SEP | SEP | 2024-08-20 | 2024-09-09 | 2024-09-09 | 2024-09-09 | 2024-09-23 | 2024-09-23
44965 | 740-DH3-VU091-109-LH011-32-0 | 1 | true | 5.57 | 740-DH3-VU091-109-LH011-32-0 | LV1-105638.VU091 | 369 | 26.Apr.2024 |  | MC1 | LVL 6 | W23 | TR003 | 2024-02-20 | 2024-02-26 | 2024-02-29 |  | 2024-04-18 | 2024-04-22 | Büro | 2024-04-26 |  | 2024-04-22 | 2024-05-14 |  | 2024-05-15 | 2024-10-24 | 827 | 150 |  | 2024-08-22 | 2024-07-05 | 149 | SEP | SEP | 2024-08-20 | 2024-09-13 | 2024-09-13 | 2024-09-20 | 2024-09-23 | 2024-09-23
44966 | 740-DH3-VU091-110-LH011-20-0 | 1 | true | 4.51 | 740-DH3-VU091-110-LH011-20-0 | LV1-105638.VU091 | 369 | 26.Apr.2024 |  | MC1 | LVL 6 | W23 | TR003 | 2024-02-20 | 2024-02-26 | 2024-02-29 |  | 2024-04-18 | 2024-04-25 | Büro | 2024-04-26 |  | 2024-04-25 | 2024-05-14 |  | 2024-05-15 | 2024-10-24 | 827 | 150 |  | 2024-08-22 | 2024-07-05 | 149 | SEP | SEP | 2024-08-20 | 2024-09-09 | 2024-09-09 | 2024-09-09 | 2024-09-23 | 2024-09-23
44967 | 740-DH3-VU091-111-LH011-32-0 | 1 | true | 6.12 | 740-DH3-VU091-111-LH011-32-0 | LV1-105638.VU091 | 369 | 26.Apr.2024 |  | MC1 | LVL 6 | W23 | TR003 | 2024-02-20 | 2024-02-26 | 2024-02-29 |  | 2024-04-18 | 2024-04-19 | Büro | 2024-04-26 |  | 2024-04-20 | 2024-05-14 |  |  | 2024-05-15 | 827 | 150 |  | 2024-08-22 | 2024-07-05 | 149 | SEP | SEP | 2024-08-20 | 2024-09-09 | 2024-09-09 | 2024-09-09 | 2024-09-23 | 2024-09-23
44973 | 740-MKWP-R-VP001-301-LH001-50-0 | 1 | false | 2 | 740-MKWP-R-VP001-301-LH001-50-0 | LV1-105630.VP001 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-21 | 2024-02-27 |  |  |  |  | Friedwagner Paul | [7 empty] | 828 | 150 |  |  |  | 149 | SEP | SEP
45218 | 740-MKWP-R-VP001-301-LH001-50-0 | 2 | true | 2 | 740-MKWP-R-VP001-301-LH001-50-0 | LV1-105630.VP001 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR004 | 2024-02-23 | 2024-03-02 | 2024-03-03 |  | 2024-04-02 | 2024-04-10 | Zauner Romania | 2024-04-12 |  | 2024-04-10 |  |  |  | 2024-10-18 | 828 | 150 |  | 2024-11-13 |  | 149 | SEP | SEP |  |  | 2024-11-15 | 2024-11-15
44974 | 740-MKWP-R-VP002-301-LH001-50-0 | 1 | false | 0.43 | 740-MKWP-R-VP002-301-LH001-50-0 | LV1-105630.VP002 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-21 | 2024-02-27 |  |  |  |  | Friedwagner Paul | [7 empty] | 828 | 150 |  |  |  | 149 | SEP | SEP
45219 | 740-MKWP-R-VP002-301-LH001-50-0 | 2 | true | 0.43 | 740-MKWP-R-VP002-301-LH001-50-0 | LV1-105630.VP002 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR004 | 2024-02-23 | 2024-03-02 | 2024-03-03 |  | 2024-04-02 | 2024-04-05 | Büro | 2024-04-12 |  | 2024-04-05 | 2024-10-21 |  |  | 2024-10-23 | 828 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-11-15 | 2024-11-15
44975 | 740-MKWP-R-VP003-301-LH001-40-0 | 1 | false | 4.17 | 740-MKWP-R-VP003-301-LH001-40-0 | LV1-105630.VP003 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-21 | 2024-02-27 |  |  |  |  | Friedwagner Paul | [7 empty] | 828 | 150 |  |  |  | 149 | SEP | SEP
45220 | 740-MKWP-R-VP003-301-LH001-40-0 | 2 | true | 4.17 | 740-MKWP-R-VP003-301-LH001-40-0 | LV1-105630.VP003 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR004 | 2024-02-23 | 2024-03-02 | 2024-03-03 |  | 2024-04-10 | 2024-04-16 | Büro | 2024-04-26 |  | 2024-04-16 |  |  |  | 2024-10-24 | 828 | 150 |  | 2024-11-13 | 2024-10-30 | 149 | SEP | SEP |  |  | 2024-11-30 | 2024-11-30
44976 | 740-MKWP-R-VP004-301-LH001-40-0 | 1 | false | 1.84 | 740-MKWP-R-VP004-301-LH001-40-0 | LV1-105630.VP004 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-21 | 2024-02-27 |  |  |  |  | Friedwagner Paul | [7 empty] | 828 | 150 |  |  |  | 149 | SEP | SEP
45221 | 740-MKWP-R-VP004-301-LH001-40-0 | 2 | true | 1.84 | 740-MKWP-R-VP004-301-LH001-40-0 | LV1-105630.VP004 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR004 | 2024-02-23 | 2024-03-02 | 2024-03-03 |  | 2024-04-10 | 2024-04-16 | Zauner Romania | 2024-04-26 |  | 2024-04-16 |  |  |  | 2024-10-18 | 828 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-11-30 | 2024-11-30
44977 | 740-MKWP-R-VP031-201-LH001-50-0 | 1 | false | 1.78 | 740-MKWP-R-VP031-201-LH001-50-0 | LV1-105629.VP031 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-21 | 2024-02-27 |  |  |  |  | Friedwagner Paul | [7 empty] | 828 | 150 |  |  |  | 149 | SEP | SEP
45222 | 740-MKWP-R-VP031-201-LH001-50-0 | 2 | true | 1.78 | 740-MKWP-R-VP031-201-LH001-50-0 | LV1-105629.VP031 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR004 | 2024-02-23 | 2024-03-02 | 2024-03-03 |  | 2024-04-08 | 2024-04-10 | Büro | 2024-04-12 |  | 2024-04-10 |  |  |  | 2024-10-30 | 828 | 150 |  | 2024-11-18 | 2024-11-04 | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
44978 | 740-MKWP-R-VP032-201-LH001-50-0 | 1 | false | 1.7 | 740-MKWP-R-VP032-201-LH001-50-0 | LV1-105629.VP032 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-21 | 2024-02-27 |  |  |  |  | Friedwagner Paul | [7 empty] | 828 | 150 |  |  |  | 149 | SEP | SEP
45223 | 740-MKWP-R-VP032-201-LH001-50-0 | 2 | true | 1.7 | 740-MKWP-R-VP032-201-LH001-50-0 | LV1-105629.VP032 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR004 | 2024-02-23 | 2024-03-02 | 2024-03-03 |  | 2024-04-08 | 2024-04-10 | Büro | 2024-04-12 |  | 2024-04-10 | 2024-10-22 |  |  | 2024-10-24 | 828 | 150 |  | 2024-11-18 | 2024-10-30 | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
44979 | 740-MKWP-R-VP033-201-LH001-50-0 | 1 | false | 1.48 | 740-MKWP-R-VP033-201-LH001-50-0 | LV1-105629.VP033 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-21 | 2024-02-27 |  |  |  |  | Friedwagner Paul | [7 empty] | 828 | 150 |  |  |  | 149 | SEP | SEP
45224 | 740-MKWP-R-VP033-201-LH001-50-0 | 2 | true | 1.48 | 740-MKWP-R-VP033-201-LH001-50-0 | LV1-105629.VP033 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR004 | 2024-02-23 | 2024-03-02 | 2024-03-03 |  | 2024-04-03 | 2024-04-10 | Büro | 2024-04-12 |  | 2024-04-10 |  |  |  | 2024-11-04 | 828 | 150 |  | 2024-11-18 | 2024-11-05 | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
44980 | 740-MKWP-R-VP041-201-LH001-50-0 | 1 | false | 1.54 | 740-MKWP-R-VP041-201-LH001-50-0 | LV1-105629.VP041 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-21 | 2024-02-27 |  |  |  |  | Friedwagner Paul | [7 empty] | 828 | 150 |  |  |  | 149 | SEP | SEP
45225 | 740-MKWP-R-VP041-201-LH001-50-0 | 2 | true | 1.54 | 740-MKWP-R-VP041-201-LH001-50-0 | LV1-105629.VP041 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR004 | 2024-02-23 | 2024-03-02 | 2024-03-03 |  | 2024-04-08 | 2024-04-11 | Büro | 2024-04-12 |  | 2024-04-11 |  |  |  | 2024-10-30 | 828 | 150 |  | 2024-11-18 | 2024-11-05 | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
44981 | 740-MKWP-R-VP042-201-LH001-50-0 | 1 | false | 2.8 | 740-MKWP-R-VP042-201-LH001-50-0 | LV1-105629.VP042 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-21 | 2024-02-27 |  |  |  |  | Friedwagner Paul | [7 empty] | 828 | 150 |  |  |  | 149 | SEP | SEP
45226 | 740-MKWP-R-VP042-201-LH001-50-0 | 2 | true | 2.8 | 740-MKWP-R-VP042-201-LH001-50-0 | LV1-105629.VP042 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR004 | 2024-02-23 | 2024-03-02 | 2024-03-03 |  | 2024-04-08 | 2024-04-10 | Büro | 2024-04-12 |  | 2024-04-10 | 2024-10-22 |  |  | 2024-10-24 | 828 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
44982 | 740-MKWP-R-VP043-201-LH001-50-0 | 1 | false | 1.74 | 740-MKWP-R-VP043-201-LH001-50-0 | LV1-105629.VP043 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-21 | 2024-02-27 |  |  |  |  | Friedwagner Paul | [7 empty] | 828 | 150 |  |  |  | 149 | SEP | SEP
45227 | 740-MKWP-R-VP043-201-LH001-50-0 | 2 | true | 1.74 | 740-MKWP-R-VP043-201-LH001-50-0 | LV1-105629.VP043 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR004 | 2024-02-23 | 2024-03-02 | 2024-03-03 |  | 2024-04-08 | 2024-04-10 | Büro | 2024-04-12 |  | 2024-04-10 | 2024-10-24 |  |  | 2024-10-30 | 828 | 150 |  | 2024-11-18 | 2024-10-31 | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
44983 | 740-MKWP-R-VP131-201-LH001-40-0 | 1 | false | 1.02 | 740-MKWP-R-VP131-201-LH001-40-0 | LV1-105638.VU231 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-21 | 2024-02-27 |  |  |  |  | Friedwagner Paul | [7 empty] | 828 | 150 |  |  |  | 149 | SEP | SEP
45228 | 740-MKWP-R-VP131-201-LH001-40-0 | 2 | true | 1.02 | 740-MKWP-R-VP131-201-LH001-40-0 | LV1-105638.VU231 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR004 | 2024-02-23 | 2024-03-02 | 2024-03-03 |  | 2024-04-10 | 2024-04-16 | Büro | 2024-04-26 |  | 2024-04-16 |  |  |  | 2024-11-06 | 828 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
44984 | 740-MKWP-R-VP132-201-LH001-40-0 | 1 | false | 1.26 | 740-MKWP-R-VP132-201-LH001-40-0 | LV1-105638.VU231 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-21 | 2024-02-27 |  |  |  |  | Friedwagner Paul | [7 empty] | 828 | 150 |  |  |  | 149 | SEP | SEP
45229 | 740-MKWP-R-VP132-201-LH001-40-0 | 2 | true | 1.26 | 740-MKWP-R-VP132-201-LH001-40-0 | LV1-105638.VU231 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR004 | 2024-02-23 | 2024-03-02 | 2024-03-03 |  | 2024-04-10 | 2024-04-16 | Büro | 2024-04-26 |  | 2024-04-16 |  |  |  | 2024-11-06 | 828 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
44985 | 740-MKWP-R-VP133-201-LH001-40-0 | 1 | false | 1.04 | 740-MKWP-R-VP133-201-LH001-40-0 | LV1-105638.VU231 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-21 | 2024-02-27 |  |  |  |  | Friedwagner Paul | [7 empty] | 828 | 150 |  |  |  | 149 | SEP | SEP
45230 | 740-MKWP-R-VP133-201-LH001-40-0 | 2 | true | 1.04 | 740-MKWP-R-VP133-201-LH001-40-0 | LV1-105638.VU231 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR004 | 2024-02-23 | 2024-03-02 | 2024-03-03 |  | 2024-04-10 | 2024-04-16 | Büro | 2024-04-26 |  | 2024-04-16 |  |  |  | 2024-10-30 | 828 | 150 |  |  | 2024-10-31 | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
44986 | 740-MKWP-R-VP141-201-LH001-40-0 | 1 | false | 0.38 | 740-MKWP-R-VP141-201-LH001-40-0 | LV1-105629.VP141 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-21 | 2024-02-27 |  |  |  |  | Friedwagner Paul | [7 empty] | 828 | 150 |  |  |  | 149 | SEP | SEP
45231 | 740-MKWP-R-VP141-201-LH001-40-0 | 2 | true | 0.38 | 740-MKWP-R-VP141-201-LH001-40-0 | LV1-105629.VP141 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR004 | 2024-02-23 | 2024-03-02 | 2024-03-03 |  | 2024-04-10 | 2024-04-16 | Büro | 2024-04-26 |  | 2024-04-16 | 2024-10-22 |  |  | 2024-10-24 | 828 | 150 |  |  | 2024-10-28 | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
44987 | 740-MKWP-R-VP142-201-LH001-40-0 | 1 | false | 0.38 | 740-MKWP-R-VP142-201-LH001-40-0 | LV1-105629.VP142 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-21 | 2024-02-27 |  |  |  |  | Friedwagner Paul | [7 empty] | 828 | 150 |  |  |  | 149 | SEP | SEP
45232 | 740-MKWP-R-VP142-201-LH001-40-0 | 2 | true | 0.38 | 740-MKWP-R-VP142-201-LH001-40-0 | LV1-105629.VP142 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR004 | 2024-02-23 | 2024-03-02 | 2024-03-03 |  | 2024-04-10 | 2024-04-12 | Büro | 2024-04-26 |  | 2024-04-17 |  |  |  | 2024-10-22 | 828 | 150 |  |  | 2024-10-30 | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
44988 | 740-MKWP-R-VP143-201-LH001-40-0 | 1 | false | 1.25 | 740-MKWP-R-VP143-201-LH001-40-0 | LV1-105629.VP143 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-21 | 2024-02-27 |  |  |  |  | Friedwagner Paul | [7 empty] | 828 | 150 |  |  |  | 149 | SEP | SEP
45233 | 740-MKWP-R-VP143-201-LH001-40-0 | 2 | true | 1.25 | 740-MKWP-R-VP143-201-LH001-40-0 | LV1-105629.VP143 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR004 | 2024-02-23 | 2024-03-02 | 2024-03-03 |  | 2024-04-10 | 2024-04-11 | Büro | 2024-04-26 |  | 2024-04-11 | 2024-10-21 |  |  | 2024-10-23 | 828 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
44989 | 740-MKWP-R-VU081-193-LH001-15-0 | 1 | false | 2.17 | 740-MKWP-R-VU081-193-LH001-15-0 | LV1-105638.VU231 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-21 | 2024-02-27 |  |  |  |  | Friedwagner Paul | [7 empty] | 828 | 150 |  |  |  | 149 | SEP | SEP
45234 | 740-MKWP-R-VU081-193-LH001-15-0 | 2 | false | 2.17 | 740-MKWP-R-VU081-193-LH001-15-0 | LV1-105638.VU231 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR004 | 2024-02-24 | 2024-03-03 | 2024-03-04 |  |  |  | Zauner Romania | [7 empty] | 828 | 150 |  |  |  | 149 | SEP | SEP
46660 | 740-MKWP-R-VU081-193-LH001-15-0 | 3 | false | 2.17 | 740-MKWP-R-VU081-193-LH001-15-0 | LV1-105638.VU231 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR007 | 2024-03-15 | 2024-03-23 | 2024-03-23 | Line got DELETED |  |  | Prefab ZRO | [7 empty] | 828 | 150 | Line got DELETED |  |  | 149 | SEP | SEP
44990 | 740-MKWP-R-VU161-102-LH001-125-0 | 1 | true | 0.2 | 740-MKWP-R-VU161-102-LH001-125-0 | LV1-105638.VU161 | 363 | 2.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-20 | 2024-02-26 | 2024-02-29 |  | 2024-03-22 | 2024-03-22 | Büro | 2024-04-01 |  | 2024-03-25 | 2024-07-08 |  |  | 2024-07-12 | 828 | 150 |  | 2024-07-24 | 2024-07-17 | 149 | SEP | SEP | 2024-07-23 | 2024-09-02 | 2024-09-02 | 2024-09-02
44991 | 740-MKWP-R-VU162-101-LH001-125-0 | 1 | true | 0.2 | 740-MKWP-R-VU162-101-LH001-125-0 | LV1-105638.VU162 | 363 | 2.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-20 | 2024-02-26 | 2024-02-29 |  | 2024-03-22 | 2024-03-22 | Büro | 2024-04-01 |  | 2024-03-25 | 2024-07-08 |  |  | 2024-07-12 | 828 | 150 |  | 2024-07-24 | 2024-07-17 | 149 | SEP | SEP | 2024-07-23 | 2024-09-02 | 2024-09-02 | 2024-09-02
44992 | 740-MKWP-R-VU231-121-LH001-150-0 | 1 | true | 11.8 | 740-MKWP-R-VU231-121-LH001-150-0 | LV1-105638.VU231 | 363 | 2.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-21 | 2024-02-26 | 2024-02-29 |  | 2024-03-15 | 2024-03-22 | Büro | 2024-04-01 |  | 2024-03-25 | 2024-04-30 |  |  | 2024-05-03 | 828 | 150 |  | 2024-07-24 | 2024-07-12 | 149 | SEP | SEP | 2024-09-02 | 2024-08-19 | 2024-09-02
44993 | 740-MKWP-R-VU231-122-LH001-125-0 | 1 | true | 1.47 | 740-MKWP-R-VU231-122-LH001-125-0 | LV1-105638.VU231 | 363 | 2.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-21 | 2024-02-27 | 2024-03-01 |  | 2024-03-18 | 2024-04-03 | Büro | 2024-04-12 |  | 2024-04-04 | 2024-07-08 |  |  | 2024-07-12 | 828 | 150 |  | 2024-07-24 | 2024-07-15 | 149 | SEP | SEP | 2024-07-23 | 2024-09-02 | 2024-09-02 | 2024-09-02
44994 | 740-MKWP-R-VU231-123-LH001-125-0 | 1 | true | 1.47 | 740-MKWP-R-VU231-123-LH001-125-0 | LV1-105638.VU231 | 363 | 2.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-21 | 2024-02-27 | 2024-03-01 |  | 2024-03-23 | 2024-04-03 | Büro | 2024-04-12 |  | 2024-04-04 | 2024-07-08 |  |  | 2024-07-12 | 828 | 150 |  | 2024-07-24 | 2024-07-15 | 149 | SEP | SEP | 2024-09-02 | 2024-09-02 | 2024-09-02 | 2024-09-02
44995 | 740-MKWP-R-VU231-127-LH001-50-0 | 1 | true | 9.52 | 740-MKWP-R-VU231-127-LH001-50-0 | LV1-105638.VU231 | 363 | 2.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-20 | 2024-02-26 | 2024-02-29 |  | 2024-03-17 | 2024-03-25 | Büro | 2024-04-01 |  | 2024-03-30 | 2024-04-16 |  |  | 2024-04-19 | 828 | 150 |  | 2024-07-24 | 2024-07-05 | 149 | SEP | SEP | 2024-07-23 | 2024-09-02 | 2024-09-02 | 2024-09-02
44996 | 740-MKWP-R-VU231-128-LH001-40-0 | 1 | true | 0.65 | 740-MKWP-R-VU231-128-LH001-40-0 | LV1-105638.VU231 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-20 | 2024-02-26 | 2024-02-29 |  | 2024-04-09 | 2024-04-10 | Büro | 2024-04-12 |  | 2024-04-11 | 2024-06-13 |  |  | 2024-06-14 | 828 | 150 |  | 2024-07-24 | 2024-07-12 | 149 | SEP | SEP | 2024-09-02 | 2024-09-02 | 2024-09-02 | 2024-09-02
44997 | 740-MKWP-R-VU231-129-LH001-40-0 | 1 | true | 0.65 | 740-MKWP-R-VU231-129-LH001-40-0 | LV1-105638.VU231 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-20 | 2024-02-26 | 2024-02-29 |  | 2024-04-09 | 2024-04-11 | Büro | 2024-04-26 |  | 2024-04-11 | 2024-06-13 |  |  | 2024-06-14 | 828 | 150 |  | 2024-07-24 | 2024-07-12 | 149 | SEP | SEP | 2024-07-23 | 2024-09-02 | 2024-09-02 | 2024-09-02
44998 | 740-MKWP-R-VU231-130-LH001-40-0 | 1 | true | 0.65 | 740-MKWP-R-VU231-130-LH001-40-0 | LV1-105638.VU231 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-20 | 2024-02-26 | 2024-02-29 |  | 2024-04-09 | 2024-04-11 | Büro | 2024-04-26 |  | 2024-04-11 | 2024-06-13 |  |  | 2024-06-14 | 828 | 150 |  | 2024-07-24 | 2024-07-12 | 149 | SEP | SEP | 2024-09-02 | 2024-09-02 | 2024-09-02 | 2024-09-02
44999 | 740-MKWP-R-VU231-131-LH001-15-0 | 1 | false | 1.38 | 740-MKWP-R-VU231-131-LH001-15-0 | LV1-105638.VU231 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-21 | 2024-02-27 | 2024-03-01 |  |  |  | Zauner Romania | [7 empty] | 828 | 150 |  |  |  | 149 | SEP | SEP
46661 | 740-MKWP-R-VU231-131-LH001-15-0 | 2 | true | 1.38 | 740-MKWP-R-VU231-131-LH001-15-0 | LV1-105638.VU231 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR007 | 2024-03-14 | 2024-03-22 | 2024-03-22 |  | 2024-04-23 | 2024-04-23 | Büro | 2024-04-26 |  | 2024-04-23 | 2024-06-13 |  |  | 2024-06-14 | 828 | 150 |  | 2024-07-24 | 2024-07-12 | 149 | SEP | SEP | 2024-09-02 | 2024-09-02 | 2024-09-02 | 2024-09-02
45000 | 740-MKWP-R-VU231-221-LH001-150-0 | 1 | false | 67.81 | 740-MKWP-R-VU231-221-LH001-150-0 | LV1-105638.VU231 | 363 | 2.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-22 | 2024-02-27 | 2024-03-01 |  | 2024-03-16 | 2024-03-20 | Miljenko Lazar | 2024-04-02 |  | 2024-03-25 | 2024-04-09 |  |  |  | 828 | 150 |  |  |  | 149 | SEP | SEP
46670 | 740-MKWP-R-VU231-221-LH001-150-0 | 2 | true | 67.81 | 740-MKWP-R-VU231-221-LH001-150-0 | LV1-105638.VU231 | 363 | 2.Apr.2024 |  | MC1 | LVL 6 | T60 | TR007 | 2024-03-14 | 2024-03-22 | 2024-03-22 |  | 2024-03-15 | 2024-03-21 | Büro | 2024-04-02 |  | 2024-03-26 | 2024-04-09 | 2024-04-26 |  | 2024-05-01 | 828 | 150 |  | 2024-07-24 | 2024-07-05 | 149 | SEP | SEP | 2024-07-23 | 2024-08-06 | 2024-08-06
45001 | 740-MKWP-R-VU231-222-LH001-50-0 | 1 | true | 0.75 | 740-MKWP-R-VU231-222-LH001-50-0 | LV1-105639.VU231 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-20 | 2024-02-26 | 2024-02-29 |  | 2024-04-09 | 2024-04-10 | Büro | 2024-04-12 |  | 2024-04-10 | 2024-06-05 |  |  | 2024-06-06 | 828 | 150 |  | 2024-07-24 | 2024-07-05 | 149 | SEP | SEP | 2024-07-23 | 2024-09-02 | 2024-09-02 | 2024-09-02
45002 | 740-MKWP-R-VU231-223-LH001-65-0 | 1 | true | 9.84 | 740-MKWP-R-VU231-223-LH001-65-0 | LV1-105639.VU231 | 363 | 2.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-20 | 2024-02-26 | 2024-02-29 |  | 2024-03-18 | 2024-03-22 | Büro | 2024-04-01 |  | 2024-03-25 | 2024-04-16 |  |  | 2024-04-17 | 828 | 150 |  | 2024-07-24 | 2024-07-12 | 149 | SEP | SEP | 2024-09-02 | 2024-09-02 | 2024-09-02 | 2024-09-02
45003 | 740-MKWP-R-VU231-224-LH001-50-0 | 1 | true | 0.15 | 740-MKWP-R-VU231-224-LH001-50-0 | LV1-105639.VU231 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-20 | 2024-02-26 | 2024-02-29 |  | 2024-04-09 | 2024-04-09 | Büro | 2024-04-12 |  | 2024-04-09 | 2024-05-29 |  |  | 2024-06-05 | 828 | 150 |  | 2024-07-24 | 2024-07-05 | 149 | SEP | SEP | 2024-07-23 | 2024-09-02 | 2024-09-02 | 2024-09-02
45004 | 740-MKWP-R-VU231-225-LH001-50-0 | 1 | true | 0.15 | 740-MKWP-R-VU231-225-LH001-50-0 | LV1-105639.VU231 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-20 | 2024-02-26 | 2024-02-29 |  | 2024-04-09 | 2024-04-10 | Büro | 2024-04-12 |  | 2024-04-10 | 2024-05-29 |  |  | 2024-06-05 | 828 | 150 |  | 2024-07-24 | 2024-07-05 | 149 | SEP | SEP | 2024-09-02 | 2024-09-02 | 2024-09-02 | 2024-09-02
45005 | 740-MKWP-R-VU231-226-LH001-50-0 | 1 | true | 0.15 | 740-MKWP-R-VU231-226-LH001-50-0 | LV1-105639.VU231 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-20 | 2024-02-26 | 2024-02-29 |  | 2024-04-09 | 2024-04-09 | Büro | 2024-04-12 |  | 2024-04-09 | 2024-05-29 |  |  | 2024-06-05 | 828 | 150 |  | 2024-07-24 | 2024-07-05 | 149 | SEP | SEP | 2024-07-23 | 2024-09-02 | 2024-09-02 | 2024-09-02
45006 | 740-MKWP-R-VU231-227-LH001-50-0 | 1 | true | 0.15 | 740-MKWP-R-VU231-227-LH001-50-0 | LV1-105639.VU231 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-20 | 2024-02-26 | 2024-02-29 |  | 2024-04-09 | 2024-04-10 | Büro | 2024-04-12 |  | 2024-04-10 | 2024-05-29 |  |  | 2024-06-05 | 828 | 150 |  | 2024-07-24 | 2024-07-12 | 149 | SEP | SEP | 2024-09-02 | 2024-09-02 | 2024-09-02 | 2024-09-02
45007 | 740-MKWP-R-VU231-228-LH001-50-0 | 1 | true | 0.14 | 740-MKWP-R-VU231-228-LH001-50-0 | LV1-105639.VU231 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-20 | 2024-02-26 | 2024-02-29 |  | 2024-04-09 | 2024-04-09 | Büro | 2024-04-12 |  | 2024-04-09 | 2024-05-29 |  |  | 2024-06-06 | 828 | 150 |  | 2024-07-24 | 2024-07-05 | 149 | SEP | SEP | 2024-07-23 | 2024-09-02 | 2024-09-02 | 2024-09-02
45008 | 740-MKWP-R-VU231-231-LH001-65-0 | 1 | false | 9.84 | 740-MKWP-R-VU231-231-LH001-65-0 | LV1-105639.VU231 | 363 | 2.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-21 | 2024-02-27 |  |  |  |  | Friedwagner Paul | [7 empty] | 828 | 150 |  |  |  | 149 | SEP | SEP
45235 | 740-MKWP-R-VU231-231-LH001-65-0 | 2 | true | 9.84 | 740-MKWP-R-VU231-231-LH001-65-0 | LV1-105639.VU231 | 363 | 2.Apr.2024 |  | MC1 | LVL 6 | T60 | TR004 | 2024-02-23 | 2024-03-02 | 2024-03-03 |  | 2024-03-18 | 2024-03-28 | Büro | 2024-04-01 |  | 2024-04-01 | 2024-04-16 |  |  | 2024-04-17 | 828 | 150 |  | 2024-07-24 | 2024-07-15 | 149 | SEP | SEP | 2024-10-14 | 2024-10-14 | 2024-10-14 | 2024-10-14
45009 | 740-MKWP-R-VU231-232-LH001-40-0 | 1 | true | 0.15 | 740-MKWP-R-VU231-232-LH001-40-0 | LV1-105639.VU231 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-20 | 2024-02-26 | 2024-02-29 |  | 2024-04-09 | 2024-04-11 | Büro | 2024-04-26 |  | 2024-04-11 | 2024-05-27 |  |  | 2024-05-28 | 828 | 150 |  | 2024-07-24 | 2024-07-05 | 149 | SEP | SEP | 2024-07-23 | 2024-09-02 | 2024-09-02 | 2024-09-02
45010 | 740-MKWP-R-VU231-233-LH001-50-0 | 1 | false | 0.07 | 740-MKWP-R-VU231-233-LH001-50-0 | LV1-105639.VU231 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-21 | 2024-02-27 |  |  |  |  | Friedwagner Paul | [7 empty] | 828 | 150 |  |  |  | 149 | SEP | SEP
45236 | 740-MKWP-R-VU231-233-LH001-50-0 | 2 | true | 0.07 | 740-MKWP-R-VU231-233-LH001-50-0 | LV1-105639.VU231 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR004 | 2024-02-23 | 2024-03-02 | 2024-03-03 |  | 2024-04-03 | 2024-04-09 | Büro | 2024-04-12 |  | 2024-04-09 | 2024-05-27 |  |  | 2024-05-28 | 828 | 150 |  | 2024-07-24 | 2024-07-15 | 149 | SEP | SEP | 2024-09-02 | 2024-09-02 | 2024-09-02 | 2024-09-02
45011 | 740-MKWP-R-VU231-234-LH001-40-0 | 1 | false | 0.15 | 740-MKWP-R-VU231-234-LH001-40-0 | LV1-105639.VU231 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-21 | 2024-02-27 |  |  |  |  | Friedwagner Paul | [7 empty] | 828 | 150 |  |  |  | 149 | SEP | SEP
45237 | 740-MKWP-R-VU231-234-LH001-40-0 | 2 | true | 0.15 | 740-MKWP-R-VU231-234-LH001-40-0 | LV1-105639.VU231 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR004 | 2024-02-23 | 2024-03-02 | 2024-03-03 |  | 2024-04-12 | 2024-04-16 | Büro | 2024-04-26 |  | 2024-04-16 | 2024-05-27 |  |  | 2024-05-28 | 828 | 150 |  | 2024-07-24 | 2024-07-15 | 149 | SEP | SEP | 2024-09-02 | 2024-09-02 | 2024-09-02 | 2024-09-02
45012 | 740-MKWP-R-VU231-235-LH001-50-0 | 1 | true | 0.74 | 740-MKWP-R-VU231-235-LH001-50-0 | LV1-105639.VU231 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-20 | 2024-02-26 | 2024-02-29 |  | 2024-04-03 | 2024-04-05 | Büro | 2024-04-12 |  | 2024-04-05 | 2024-05-27 |  |  | 2024-05-28 | 828 | 150 |  | 2024-07-24 | 2024-07-15 | 149 | SEP | SEP | 2024-07-23 | 2024-09-02 | 2024-09-02 | 2024-09-02
45013 | 740-MKWP-R-VU231-236-LH001-40-0 | 1 | true | 0.2 | 740-MKWP-R-VU231-236-LH001-40-0 | LV1-105639.VU231 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-20 | 2024-02-26 | 2024-02-29 |  | 2024-04-09 | 2024-04-11 | Büro | 2024-04-26 |  | 2024-04-11 | 2024-05-27 |  |  | 2024-05-28 | 828 | 150 |  | 2024-07-24 | 2024-07-15 | 149 | SEP | SEP | 2024-09-02 | 2024-09-02 | 2024-09-02 | 2024-09-02
45014 | 740-MKWP-R-VU231-238-LH001-40-0 | 1 | true | 0.76 | 740-MKWP-R-VU231-238-LH001-40-0 | LV1-105639.VU231 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-20 | 2024-02-26 | 2024-02-29 |  | 2024-04-09 | 2024-04-10 | Büro | 2024-04-12 |  | 2024-04-11 | 2024-05-28 |  |  | 2024-05-29 | 828 | 150 |  | 2024-07-24 | 2024-07-15 | 149 | SEP | SEP | 2024-07-23 | 2024-09-02 | 2024-09-02 | 2024-09-02
45015 | 740-MKWP-R-VU231-239-LH001-40-0 | 1 | true | 0.39 | 740-MKWP-R-VU231-239-LH001-40-0 | LV1-105639.VU231 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-20 | 2024-02-26 | 2024-02-29 |  | 2024-04-09 | 2024-04-11 | Büro | 2024-04-26 |  | 2024-04-11 | 2024-05-27 |  |  | 2024-05-28 | 828 | 150 |  | 2024-07-24 | 2024-07-15 | 149 | SEP | SEP | 2024-09-02 | 2024-09-02 | 2024-09-02 | 2024-09-02
45016 | 740-MKWP-S-VP001-301-LH001-50-0 | 1 | true | 1.72 | 740-MKWP-S-VP001-301-LH001-50-0 | LV1-105630.VP001 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-20 | 2024-02-26 | 2024-02-29 |  | 2024-04-02 | 2024-04-04 | Zauner Romania | 2024-04-12 |  | 2024-04-04 |  |  |  | 2024-10-18 | 828 | 150 |  | 2024-11-13 |  | 149 | SEP | SEP |  |  | 2024-11-15 | 2024-11-15
45017 | 740-MKWP-S-VP002-301-LH001-50-0 | 1 | true | 0.43 | 740-MKWP-S-VP002-301-LH001-50-0 | LV1-105630.VP002 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-20 | 2024-02-26 | 2024-02-29 |  | 2024-04-02 | 2024-04-03 | Büro | 2024-04-12 |  | 2024-04-05 | 2024-10-21 |  |  | 2024-10-23 | 828 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-11-15 | 2024-11-15
45018 | 740-MKWP-S-VP003-301-LH001-40-0 | 1 | true | 2.93 | 740-MKWP-S-VP003-301-LH001-40-0 | LV1-105630.VP003 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-20 | 2024-02-26 | 2024-02-29 |  | 2024-04-09 | 2024-04-10 | Zauner Romania | 2024-04-12 |  | 2024-04-11 |  |  |  | 2024-10-21 | 828 | 150 |  | 2024-11-13 | 2024-10-29 | 149 | SEP | SEP |  |  | 2024-11-30 | 2024-11-30
45019 | 740-MKWP-S-VP004-301-LH001-40-0 | 1 | true | 1.4 | 740-MKWP-S-VP004-301-LH001-40-0 | LV1-105630.VP004 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-20 | 2024-02-26 | 2024-02-29 |  | 2024-04-09 | 2024-04-10 | Zauner Romania | 2024-04-12 |  | 2024-04-11 |  |  |  | 2024-10-21 | 828 | 150 |  | 2024-11-13 | 2024-10-29 | 149 | SEP | SEP |  |  | 2024-11-30 | 2024-11-30
45020 | 740-MKWP-S-VP031-201-LH001-50-0 | 1 | true | 0.39 | 740-MKWP-S-VP031-201-LH001-50-0 | LV1-105629.VP031 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-20 | 2024-02-26 | 2024-02-29 |  | 2024-04-08 | 2024-04-09 | Büro | 2024-04-12 |  | 2024-04-09 |  |  |  | 2024-10-30 | 828 | 150 |  |  | 2024-11-04 | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
45021 | 740-MKWP-S-VP032-201-LH001-50-0 | 1 | true | 0.39 | 740-MKWP-S-VP032-201-LH001-50-0 | LV1-105629.VP032 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-20 | 2024-02-26 | 2024-02-29 |  | 2024-04-08 | 2024-04-10 | Büro | 2024-04-12 |  | 2024-04-10 | 2024-10-22 |  |  | 2024-10-24 | 828 | 150 |  | 2024-11-18 |  | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
45022 | 740-MKWP-S-VP033-201-LH001-50-0 | 1 | true | 0.48 | 740-MKWP-S-VP033-201-LH001-50-0 | LV1-105629.VP033 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-20 | 2024-02-26 | 2024-02-29 |  | 2024-04-08 | 2024-04-10 | Büro | 2024-04-12 |  | 2024-04-10 |  |  |  | 2024-11-04 | 828 | 150 |  | 2024-11-18 | 2024-11-05 | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
45023 | 740-MKWP-S-VP041-201-LH001-50-0 | 1 | true | 0.39 | 740-MKWP-S-VP041-201-LH001-50-0 | LV1-105629.VP041 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-20 | 2024-02-26 | 2024-02-29 |  | 2024-04-08 | 2024-04-10 | Büro | 2024-04-12 |  | 2024-04-10 |  |  |  | 2024-10-30 | 828 | 150 |  |  | 2024-11-14 | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
45024 | 740-MKWP-S-VP042-201-LH001-50-0 | 1 | true | 1.74 | 740-MKWP-S-VP042-201-LH001-50-0 | LV1-105629.VP042 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-20 | 2024-02-26 | 2024-02-29 |  | 2024-04-08 | 2024-04-10 | Büro | 2024-04-12 |  | 2024-04-10 | 2024-10-22 |  |  | 2024-10-24 | 828 | 150 |  |  | 2024-10-30 | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
45025 | 740-MKWP-S-VP043-201-LH001-50-0 | 1 | true | 0.39 | 740-MKWP-S-VP043-201-LH001-50-0 | LV1-105629.VP043 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-20 | 2024-02-26 | 2024-02-29 |  | 2024-04-08 | 2024-04-10 | Büro | 2024-04-12 |  | 2024-04-10 | 2024-10-24 |  |  | 2024-10-30 | 828 | 150 |  | 2024-11-18 | 2024-10-31 | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
45026 | 740-MKWP-S-VP131-201-LH001-40-0 | 1 | true | 1.02 | 740-MKWP-S-VP131-201-LH001-40-0 | LV1-105638.VU231 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-20 | 2024-02-26 | 2024-02-29 |  | 2024-04-12 | 2024-04-17 | Büro | 2024-04-26 |  | 2024-04-18 |  |  |  | 2024-11-06 | 828 | 150 |  | 2024-12-02 |  | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
45027 | 740-MKWP-S-VP132-201-LH001-40-0 | 1 | true | 1.02 | 740-MKWP-S-VP132-201-LH001-40-0 | LV1-105638.VU231 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-20 | 2024-02-26 | 2024-02-29 |  | 2024-04-10 | 2024-04-10 | Büro | 2024-04-12 |  | 2024-04-11 |  |  |  | 2024-11-04 | 828 | 150 |  |  | 2024-11-05 | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
45028 | 740-MKWP-S-VP133-201-LH001-40-0 | 1 | true | 1.01 | 740-MKWP-S-VP133-201-LH001-40-0 | LV1-105638.VU231 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-20 | 2024-02-26 | 2024-02-29 |  | 2024-04-10 | 2024-04-10 | Büro | 2024-04-12 |  | 2024-04-11 |  |  |  | 2024-10-30 | 828 | 150 |  |  | 2024-11-05 | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
45029 | 740-MKWP-S-VP141-201-LH001-40-0 | 1 | true | 0.38 | 740-MKWP-S-VP141-201-LH001-40-0 | LV1-105629.VP141 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-20 | 2024-02-26 | 2024-02-29 |  | 2024-04-10 | 2024-04-10 | Büro | 2024-04-12 |  | 2024-04-11 | 2024-10-22 |  |  | 2024-10-24 | 828 | 150 |  |  | 2024-10-30 | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
45030 | 740-MKWP-S-VP142-201-LH001-40-0 | 1 | true | 0.51 | 740-MKWP-S-VP142-201-LH001-40-0 | LV1-105629.VP142 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-20 | 2024-02-26 | 2024-02-29 |  | 2024-04-10 | 2024-04-10 | Büro | 2024-04-12 |  | 2024-04-11 |  |  |  | 2024-10-22 | 828 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
45031 | 740-MKWP-S-VP143-201-LH001-40-0 | 1 | true | 1.5 | 740-MKWP-S-VP143-201-LH001-40-0 | LV1-105629.VP143 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-20 | 2024-02-26 | 2024-02-29 |  | 2024-04-10 | 2024-04-10 | Büro | 2024-04-12 |  | 2024-04-11 | 2024-10-21 |  |  | 2024-10-23 | 828 | 150 |  |  | 2024-10-30 | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
45032 | 740-MKWP-S-VU081-194-LH001-15-0 | 1 | false | 0.06 | 740-MKWP-S-VU081-194-LH001-15-0 | LV1-105638.VU231 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-21 | 2024-02-27 | 2024-03-01 |  |  |  | Zauner Romania | [7 empty] | 828 | 150 |  |  |  | 149 | SEP | SEP
46671 | 740-MKWP-S-VU081-194-LH001-15-0 | 2 | false | 0.06 | 740-MKWP-S-VU081-194-LH001-15-0 | LV1-105638.VU231 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR007 | 2024-03-15 | 2024-03-23 | 2024-03-23 | Line got DELETED |  |  | Prefab ZRO | [7 empty] | 828 | 150 | Line got DELETED |  |  | 149 | SEP | SEP
45033 | 740-MKWP-S-VU161-101-LH001-125-0 | 1 | true | 0.5 | 740-MKWP-S-VU161-101-LH001-125-0 | LV1-105638.VU161 | 363 | 2.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-20 | 2024-02-26 | 2024-02-29 |  | 2024-03-22 | 2024-04-02 | Büro | 2024-04-12 |  | 2024-04-02 | 2024-07-08 |  |  | 2024-07-12 | 828 | 150 |  | 2024-07-24 | 2024-07-17 | 149 | SEP | SEP | 2024-09-02 | 2024-09-02 | 2024-09-02 | 2024-09-02
45034 | 740-MKWP-S-VU162-101-LH001-125-0 | 1 | true | 0.5 | 740-MKWP-S-VU162-101-LH001-125-0 | LV1-105638.VU162 | 363 | 2.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-20 | 2024-02-26 | 2024-02-29 |  | 2024-03-22 | 2024-04-02 | Büro | 2024-04-12 |  | 2024-04-02 | 2024-07-08 |  |  | 2024-07-12 | 828 | 150 |  | 2024-07-24 | 2024-07-17 | 149 | SEP | SEP | 2024-07-23 | 2024-09-02 | 2024-09-02 | 2024-09-02
45035 | 740-MKWP-S-VU231-101-LH001-150-0 | 1 | false | 69.45 | 740-MKWP-S-VU231-101-LH001-150-0 | LV1-105638.VU231 | 363 | 2.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-22 | 2024-02-27 | 2024-03-01 |  | 2024-03-16 | 2024-03-26 | Miljenko Lazar | 2024-04-02 |  | 2024-03-31 | 2024-04-09 |  |  |  | 828 | 150 |  |  |  | 149 | SEP | SEP
46672 | 740-MKWP-S-VU231-101-LH001-150-0 | 2 | true | 69.45 | 740-MKWP-S-VU231-101-LH001-150-0 | LV1-105638.VU231 | 363 | 2.Apr.2024 |  | MC1 | LVL 6 | T60 | TR007 | 2024-03-14 | 2024-03-22 | 2024-03-22 |  | 2024-03-17 | 2024-03-27 | Büro | 2024-04-02 |  | 2024-04-01 | 2024-04-09 | 2024-04-26 |  | 2024-10-24 | 828 | 150 |  | 2024-07-24 | 2024-07-15 | 149 | SEP | SEP | 2024-08-06 | 2024-08-26 | 2024-08-06 | 2024-09-02
45036 | 740-MKWP-S-VU231-102-LH001-150-0 | 1 | true | 11.29 | 740-MKWP-S-VU231-102-LH001-150-0 | LV1-105638.VU231 | 363 | 2.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-20 | 2024-02-26 | 2024-02-29 |  | 2024-03-15 | 2024-03-16 | Büro | 2024-04-01 |  | 2024-03-24 | 2024-04-30 |  |  | 2024-05-03 | 828 | 150 |  | 2024-07-24 | 2024-07-15 | 149 | SEP | SEP | 2024-07-23 | 2024-08-19 | 2024-08-26 | 2024-08-26
45037 | 740-MKWP-S-VU231-103-LH001-125-0 | 1 | true | 1.17 | 740-MKWP-S-VU231-103-LH001-125-0 | LV1-105638.VU231 | 363 | 2.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-20 | 2024-02-26 | 2024-02-29 |  | 2024-03-22 | 2024-03-23 | Büro | 2024-04-01 |  | 2024-03-23 | 2024-07-08 |  |  | 2024-07-12 | 828 | 150 |  | 2024-07-24 | 2024-07-15 | 149 | SEP | SEP | 2024-07-23
45038 | 740-MKWP-S-VU231-104-LH001-125-0 | 1 | true | 1.17 | 740-MKWP-S-VU231-104-LH001-125-0 | LV1-105638.VU231 | 363 | 2.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-20 | 2024-02-26 | 2024-02-29 |  | 2024-03-22 | 2024-03-22 | Büro | 2024-04-01 |  | 2024-03-25 | 2024-07-08 |  |  | 2024-07-12 | 828 | 150 |  | 2024-07-24 | 2024-07-15 | 149 | SEP | SEP | 2024-07-23 | 2024-09-02 | 2024-09-02 | 2024-09-02
45039 | 740-MKWP-S-VU231-108-LH001-50-0 | 1 | true | 9.09 | 740-MKWP-S-VU231-108-LH001-50-0 | LV1-105638.VU231 | 363 | 2.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-20 | 2024-02-26 | 2024-02-29 |  | 2024-03-17 | 2024-03-28 | Büro | 2024-04-01 |  | 2024-04-01 | 2024-04-16 |  |  | 2024-04-19 | 828 | 150 |  | 2024-07-24 | 2024-07-05 | 149 | SEP | SEP | 2024-07-23
45040 | 740-MKWP-S-VU231-109-LH001-40-0 | 1 | true | 0.8 | 740-MKWP-S-VU231-109-LH001-40-0 | LV1-105638.VU231 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-20 | 2024-02-26 | 2024-02-29 |  | 2024-04-12 | 2024-04-16 | Büro | 2024-04-26 |  | 2024-04-16 | 2024-06-13 |  |  | 2024-06-14 | 828 | 150 |  | 2024-07-24 | 2024-07-15 | 149 | SEP | SEP | 2024-07-23 | 2024-09-02 | 2024-09-02 | 2024-09-02
45041 | 740-MKWP-S-VU231-110-LH001-40-0 | 1 | true | 0.8 | 740-MKWP-S-VU231-110-LH001-40-0 | LV1-105638.VU231 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-20 | 2024-02-26 | 2024-02-29 |  | 2024-04-12 | 2024-04-16 | Büro | 2024-04-26 |  | 2024-04-16 | 2024-06-13 |  |  | 2024-06-14 | 828 | 150 |  | 2024-07-24 | 2024-07-15 | 149 | SEP | SEP | 2024-09-02 | 2024-09-02 | 2024-09-02 | 2024-09-02
45042 | 740-MKWP-S-VU231-111-LH001-40-0 | 1 | true | 0.8 | 740-MKWP-S-VU231-111-LH001-40-0 | LV1-105638.VU231 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-20 | 2024-02-26 | 2024-02-29 |  | 2024-04-12 | 2024-04-16 | Büro | 2024-04-26 |  | 2024-04-16 | 2024-06-13 |  |  | 2024-06-14 | 828 | 150 |  | 2024-07-24 | 2024-07-15 | 149 | SEP | SEP | 2024-07-23 | 2024-09-02 | 2024-09-02 | 2024-09-02
45043 | 740-MKWP-S-VU231-112-LH001-15-0 | 1 | false | 2.52 | 740-MKWP-S-VU231-112-LH001-15-0 | LV1-105638.VU231 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-21 | 2024-02-27 | 2024-03-01 |  |  |  | Zauner Romania | [7 empty] | 828 | 150 |  |  |  | 149 | SEP | SEP
46673 | 740-MKWP-S-VU231-112-LH001-15-0 | 2 | true | 2.52 | 740-MKWP-S-VU231-112-LH001-15-0 | LV1-105638.VU231 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR007 | 2024-03-14 | 2024-03-22 | 2024-03-22 |  | 2024-04-23 | 2024-04-23 | Büro | 2024-04-26 |  | 2024-04-23 | 2024-06-13 |  |  | 2024-06-14 | 828 | 150 |  | 2024-07-24 | 2024-07-15 | 149 | SEP | SEP | 2024-09-02 | 2024-09-02 | 2024-09-02 | 2024-09-02
45044 | 740-MKWP-S-VU231-201-LH001-50-0 | 1 | true | 0.71 | 740-MKWP-S-VU231-201-LH001-50-0 | LV1-105639.VU231 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-20 | 2024-02-26 | 2024-02-29 |  | 2024-04-03 | 2024-04-03 | Büro | 2024-04-12 |  | 2024-04-05 | 2024-06-05 |  |  | 2024-06-06 | 828 | 150 |  | 2024-07-24 | 2024-07-05 | 149 | SEP | SEP | 2024-07-23 | 2024-09-02 | 2024-09-02 | 2024-09-02
45045 | 740-MKWP-S-VU231-202-LH001-65-0 | 1 | true | 10.5 | 740-MKWP-S-VU231-202-LH001-65-0 | LV1-105639.VU231 | 363 | 2.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-20 | 2024-02-26 | 2024-02-29 |  | 2024-03-18 | 2024-03-28 | Büro | 2024-04-01 |  | 2024-04-01 | 2024-04-11 |  |  | 2024-04-17 | 828 | 150 |  | 2024-07-24 | 2024-07-05 | 149 | SEP | SEP | 2024-09-02 | 2024-09-02 | 2024-10-14 | 2024-10-14
45046 | 740-MKWP-S-VU231-203-LH001-50-0 | 1 | true | 0.15 | 740-MKWP-S-VU231-203-LH001-50-0 | LV1-105639.VU231 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-20 | 2024-02-26 | 2024-02-29 |  | 2024-04-08 | 2024-04-08 | Büro | 2024-04-12 |  | 2024-04-08 | 2024-05-29 |  |  | 2024-06-05 | 828 | 150 |  | 2024-07-24 | 2024-07-05 | 149 | SEP | SEP | 2024-07-23 | 2024-09-02 | 2024-09-02 | 2024-09-02
45047 | 740-MKWP-S-VU231-204-LH001-50-0 | 1 | true | 0.15 | 740-MKWP-S-VU231-204-LH001-50-0 | LV1-105639.VU231 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-20 | 2024-02-26 | 2024-02-29 |  | 2024-04-08 | 2024-04-09 | Büro | 2024-04-12 |  | 2024-04-09 | 2024-05-29 |  |  | 2024-06-05 | 828 | 150 |  | 2024-07-24 | 2024-07-15 | 149 | SEP | SEP | 2024-09-02 | 2024-09-02 | 2024-09-02 | 2024-09-02
45048 | 740-MKWP-S-VU231-205-LH001-50-0 | 1 | true | 0.15 | 740-MKWP-S-VU231-205-LH001-50-0 | LV1-105639.VU231 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-20 | 2024-02-26 | 2024-02-29 |  | 2024-04-08 | 2024-04-09 | Büro | 2024-04-12 |  | 2024-04-09 | 2024-05-29 |  |  | 2024-06-06 | 828 | 150 |  |  | 2024-07-05 | 149 | SEP | SEP | 2024-10-01 |  | 2024-11-01 | 2024-11-01
45049 | 740-MKWP-S-VU231-206-LH001-50-0 | 1 | true | 0.15 | 740-MKWP-S-VU231-206-LH001-50-0 | LV1-105639.VU231 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-20 | 2024-02-26 | 2024-02-29 |  | 2024-04-08 | 2024-04-09 | Büro | 2024-04-12 |  | 2024-04-09 | 2024-05-29 |  |  | 2024-06-06 | 828 | 150 |  | 2024-07-24 | 2024-07-05 | 149 | SEP | SEP | 2024-09-02 | 2024-09-02 | 2024-09-02 | 2024-09-02
45050 | 740-MKWP-S-VU231-207-LH001-50-0 | 1 | true | 0.2 | 740-MKWP-S-VU231-207-LH001-50-0 | LV1-105639.VU231 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-20 | 2024-02-26 | 2024-02-29 |  | 2024-04-08 | 2024-04-09 | Büro | 2024-04-12 |  | 2024-04-09 | 2024-05-29 |  |  | 2024-06-06 | 828 | 150 |  | 2024-07-24 | 2024-07-05 | 149 | SEP | SEP | 2024-07-23 | 2024-09-02 | 2024-09-02 | 2024-09-02
45051 | 740-MKWP-S-VU231-212-LH001-65-0 | 1 | true | 8.91 | 740-MKWP-S-VU231-212-LH001-65-0 | LV1-105639.VU231 | 363 | 2.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-20 | 2024-02-26 | 2024-02-29 |  | 2024-03-18 | 2024-03-23 | Büro | 2024-04-01 |  | 2024-03-24 | 2024-04-16 |  |  | 2024-04-16 | 828 | 150 |  | 2024-07-24 | 2024-07-05 | 149 | SEP | SEP | 2024-09-02 | 2024-09-02 | 2024-09-02 | 2024-09-02
45052 | 740-MKWP-S-VU231-213-LH001-40-0 | 1 | true | 0.32 | 740-MKWP-S-VU231-213-LH001-40-0 | LV1-105639.VU231 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-20 | 2024-02-26 | 2024-02-29 |  | 2024-04-12 | 2024-04-16 | Büro | 2024-04-26 |  | 2024-04-16 | 2024-05-28 |  |  | 2024-05-29 | 828 | 150 |  | 2024-07-24 | 2024-07-15 | 149 | SEP | SEP | 2024-07-23 | 2024-09-02 | 2024-09-02 | 2024-09-02
45053 | 740-MKWP-S-VU231-214-LH001-50-0 | 1 | true | 0.28 | 740-MKWP-S-VU231-214-LH001-50-0 | LV1-105639.VU231 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-20 | 2024-02-26 | 2024-02-29 |  | 2024-04-08 | 2024-04-10 | Büro | 2024-04-12 |  | 2024-04-10 | 2024-05-28 |  |  | 2024-05-29 | 828 | 150 |  | 2024-07-24 | 2024-07-15 | 149 | SEP | SEP | 2024-09-02 | 2024-09-02 | 2024-09-02 | 2024-09-02
45054 | 740-MKWP-S-VU231-215-LH001-40-0 | 1 | true | 0.2 | 740-MKWP-S-VU231-215-LH001-40-0 | LV1-105639.VU231 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-20 | 2024-02-26 | 2024-02-29 |  | 2024-04-12 | 2024-04-16 | Büro | 2024-04-26 |  | 2024-04-16 | 2024-05-28 |  |  | 2024-05-29 | 828 | 150 |  | 2024-07-24 | 2024-07-15 | 149 | SEP | SEP | 2024-07-23 | 2024-09-02 | 2024-09-02 | 2024-09-02
45055 | 740-MKWP-S-VU231-217-LH001-40-0 | 1 | true | 0.16 | 740-MKWP-S-VU231-217-LH001-40-0 | LV1-105639.VU231 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-20 | 2024-02-26 | 2024-02-29 |  | 2024-04-12 | 2024-04-16 | Büro | 2024-04-26 |  | 2024-04-16 | 2024-05-28 |  |  | 2024-05-29 | 828 | 150 |  | 2024-07-24 | 2024-07-17 | 149 | SEP | SEP | 2024-09-02 | 2024-09-02 | 2024-09-02 | 2024-09-02
45056 | 740-MKWP-S-VU231-219-LH001-40-0 | 1 | true | 1.03 | 740-MKWP-S-VU231-219-LH001-40-0 | LV1-105639.VU231 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-20 | 2024-02-26 | 2024-02-29 |  | 2024-04-12 | 2024-04-16 | Büro | 2024-04-26 |  | 2024-04-18 | 2024-05-28 |  |  | 2024-05-29 | 828 | 150 |  | 2024-07-24 | 2024-07-15 | 149 | SEP | SEP | 2024-07-23 | 2024-09-02 | 2024-09-02 | 2024-09-02
45057 | 740-MKWP-S-VU231-220-LH001-40-0 | 1 | true | 0.77 | 740-MKWP-S-VU231-220-LH001-40-0 | LV1-105639.VU231 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-20 | 2024-02-26 | 2024-02-29 |  | 2024-04-10 | 2024-04-16 | Büro | 2024-04-26 |  | 2024-04-16 | 2024-05-28 |  |  | 2024-05-29 | 828 | 150 |  | 2024-07-24 | 2024-07-15 | 149 | SEP | SEP | 2024-09-02 | 2024-09-02 | 2024-09-02 | 2024-09-02
45058 | 740-MKWP-S-VU231-242-LH001-50-0 | 1 | true | 0.52 | 740-MKWP-S-VU231-242-LH001-50-0 | LV1-105639.VU231 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR003 | 2024-02-20 | 2024-02-26 | 2024-02-29 |  | 2024-04-03 | 2024-04-09 | Büro | 2024-04-12 |  | 2024-04-09 | 2024-05-28 |  |  | 2024-05-29 | 828 | 150 |  | 2024-07-24 | 2024-07-15 | 149 | SEP | SEP | 2024-07-23 | 2024-09-02 | 2024-09-02 | 2024-09-02
45210 | 736-DKH-OU118-101-LH011-25_ED-0 | 1 | false | 9.69 | 736-DKH-OU118-101-LH011-25_ED-0 | LV2-104465 - Blatt 118 | 369 |  |  | MC1 | LVL 5 | W23 | TR004 | 2024-02-24 | 2024-03-03 |  |  |  |  | Büro | [6 empty] | 2024-04-26 | 836 | 150 |  |  |  | 150 | SEP | SEP
46687 | 736-DKH-OU118-101-LH011-25_ED-0 | 2 | true | 9.69 | 736-DKH-OU118-101-LH011-25_ED-0 | LV2-104465 - Blatt 118 | 369 |  |  | MC1 | LVL 5 | W23 | TR008 | 2024-03-19 | 2024-03-27 | 2024-03-27 |  |  |  | Andrija Klanjic |  |  | 2024-04-22 | 2024-04-24 |  |  | 2024-04-26 | 836 | 150 |  | 2024-06-26 | 2024-06-25 | 150 | SEP | SEP
45211 | 736-DKH-OU118-107-LH011-20-0 | 1 | false | 2.23 | 736-DKH-OU118-107-LH011-20-0 | LV2-104465 - Blatt 118 | 369 |  |  | MC1 | LVL 5 | W23 | TR004 | 2024-02-24 | 2024-03-03 |  |  |  |  | Büro |  |  | 2024-04-16 |  |  |  | 2024-04-26 | 836 | 150 |  |  |  | 150 | SEP | SEP
46688 | 736-DKH-OU118-107-LH011-20-0 | 2 | true | 2.23 | 736-DKH-OU118-107-LH011-20-0 | LV2-104465 - Blatt 118 | 369 |  |  | MC1 | LVL 5 | W23 | TR008 | 2024-03-19 | 2024-03-27 | 2024-03-27 |  |  |  | Andrija Klanjic |  |  | 2024-04-22 | 2024-04-24 |  |  | 2024-04-26 | 836 | 150 |  | 2024-06-26 | 2024-06-25 | 150 | SEP | SEP
45212 | 736-DKR-OU117-101-LH011-25-0 | 1 | false | 20.61 | 736-DKR-OU117-101-LH011-25-0 | LV1-104465 - Blatt 117 | 369 |  |  | MC1 | LVL 5 | W23 | TR004 | 2024-02-24 | 2024-03-03 | [7 empty] | 2024-04-16 |  |  |  |  | 836 | 150 |  | 2024-07-03 |  | 150 | SEP | SEP
46689 | 736-DKR-OU117-101-LH011-25-0 | 2 | true | 20.61 | 736-DKR-OU117-101-LH011-25-0 | LV1-104465 - Blatt 117 | 369 |  |  | MC1 | LVL 5 | W23 | TR008 | 2024-03-19 | 2024-03-27 | 2024-03-27 |  |  |  | Andrija Klanjic |  |  | 2024-04-22 | 2024-04-24 |  |  | 2024-04-30 | 836 | 150 |  | 2024-06-26 | 2024-09-09 | 150 | SEP | SEP
45213 | 736-DKR-OU117-108-LH011-15_ED-0 | 1 | true | 2.3 | 736-DKR-OU117-108-LH011-15_ED-0 | LV1-104465 - Blatt 117 | 369 |  |  | MC1 | LVL 5 | W23 | TR004 | 2024-02-24 | 2024-03-03 | [7 empty] | 2024-04-16 | 2024-04-24 |  |  | 2024-04-30 | 836 | 150 |  | 2024-06-26 | 2024-06-25 | 150 | SEP | SEP
45214 | 736-DKR-OU117-109-LH011-15_ED-0 | 1 | true | 2.14 | 736-DKR-OU117-109-LH011-15_ED-0 | LV2-104465 - Blatt 118 | 369 |  |  | MC1 | LVL 5 | W23 | TR004 | 2024-02-24 | 2024-03-03 | [7 empty] | 2024-04-16 | 2024-04-24 |  |  | 2024-04-30 | 836 | 150 |  | 2024-06-26 | 2024-06-25 | 150 | SEP | SEP
45215 | 736-DKR-OU117-115-LH011-15_ED-0 | 1 | true | 2.08 | 736-DKR-OU117-115-LH011-15_ED-0 | LV1-104465 - Blatt 117 | 369 |  |  | MC1 | LVL 5 | W23 | TR004 | 2024-02-24 | 2024-03-03 | [7 empty] | 2024-04-16 | 2024-04-24 |  |  | 2024-04-30 | 836 | 150 |  | 2024-06-26 | 2024-06-25 | 150 | SEP | SEP
45216 | 736-DKR-OU117-181-LH011-20-0 | 1 | true | 1.67 | 736-DKR-OU117-181-LH011-20-0 | LV1-104465 - Blatt 080 | 369 |  |  | MC1 | LVL 5 | W23 | TR004 | 2024-02-24 | 2024-03-03 | [7 empty] | 2024-04-16 | 2024-04-24 |  |  | 2024-04-30 | 836 | 150 |  | 2024-06-26 | 2024-06-25 | 150 | SEP | SEP
45217 | 736-DKR-OU117-183-LH011-20-0 | 1 | true | 2.33 | 736-DKR-OU117-183-LH011-20-0 | LV1-104465 - Blatt 080 | 369 |  |  | MC1 | LVL 5 | W23 | TR004 | 2024-02-24 | 2024-03-03 | [7 empty] | 2024-04-16 | 2024-04-24 |  |  | 2024-04-30 | 836 | 150 |  | 2024-06-26 | 2024-06-25 | 150 | SEP | SEP
45690 | 740-HLK-VH001-101-LH130-50-0 | 1 | true | 17.22 | 740-HLK-VH001-101-LH130-50-0 | LV1-105623.VH001 | 362 | 24.Mai.2024 |  | MC1 | LVL 6 | W60 | TR006 | 2024-03-07 | 2024-04-02 | 2024-04-03 |  | 2024-05-08 | 2024-05-13 |  | 2024-05-17 |  | 2024-05-13 | 2024-07-24 | 2024-07-26 |  | 2024-08-27 | 849 | 150 |  |  | 2024-09-03 | 149 | SEP | SEP | 2024-09-28 | 2024-10-18 | 2024-10-18 | 2024-10-18
45691 | 740-HLK-VH001-102-LH130-50-0 | 1 | true | 3.11 | 740-HLK-VH001-102-LH130-50-0 | LV1-105623.VH001 | 362 | 24.Mai.2024 |  | MC1 | LVL 6 | W60 | TR006 | 2024-03-07 | 2024-04-02 | 2024-04-03 |  | 2024-05-07 | 2024-05-10 | Büro | 2024-05-17 |  | 2024-05-10 | 2024-09-05 |  |  | 2024-09-10 | 849 | 150 |  |  | 2024-09-12 | 149 | SEP | SEP | 2024-09-28 | 2024-10-18 | 2024-10-18 | 2024-10-18
45692 | 740-HLK-VH001-104-LH130-50-0 | 1 | true | 18.72 | 740-HLK-VH001-104-LH130-50-0 | LV1-105623.VH001 | 362 | 24.Mai.2024 |  | MC1 | LVL 6 | W60 | TR006 | 2024-03-07 | 2024-04-02 | 2024-04-03 |  | 2024-05-08 | 2024-05-09 |  | 2024-05-17 |  | 2024-05-14 | 2024-07-24 | 2024-07-26 |  | 2024-08-27 | 849 | 150 |  |  | 2024-09-03 | 149 | SEP | SEP | 2024-09-28 | 2024-10-18 | 2024-10-18 | 2024-10-18
45693 | 740-HLK-VH001-105-LH130-50-0 | 1 | true | 4.35 | 740-HLK-VH001-105-LH130-50-0 | LV1-105623.VH001 | 362 | 24.Mai.2024 |  | MC1 | LVL 6 | W60 | TR006 | 2024-03-07 | 2024-04-02 | 2024-04-03 |  | 2024-05-07 | 2024-05-13 | Büro | 2024-05-17 |  | 2024-05-14 | 2024-09-05 |  |  | 2024-09-10 | 849 | 150 |  |  | 2024-09-12 | 149 | SEP | SEP | 2024-09-28 | 2024-10-18 | 2024-10-18 | 2024-10-18
45694 | 740-HLK-VH002-101-LH130-50-0 | 1 | true | 13.75 | 740-HLK-VH002-101-LH130-50-0 | LV1-105623.VH002 | 362 | 24.Mai.2024 |  | MC1 | LVL 6 | W60 | TR006 | 2024-03-07 | 2024-04-02 | 2024-04-03 |  | 2024-05-07 | 2024-05-13 | Büro | 2024-05-17 |  | 2024-05-14 | 2024-08-08 |  | 2024-08-12 | 2024-09-07 | 849 | 150 |  |  | 2024-09-12 | 149 | SEP | SEP | 2024-09-28 | 2024-10-18 | 2024-10-18 | 2024-10-18
45695 | 740-HLK-VH002-102-LH130-50-0 | 1 | true | 12.72 | 740-HLK-VH002-102-LH130-50-0 | LV1-105623.VH002 | 362 | 24.Mai.2024 |  | MC1 | LVL 6 | W60 | TR006 | 2024-03-07 | 2024-04-02 | 2024-04-03 |  | 2024-05-08 | 2024-05-13 | Büro | 2024-05-17 |  | 2024-05-14 | 2024-05-28 |  | 2024-06-04 | 2024-09-07 | 849 | 150 |  |  | 2024-09-12 | 149 | SEP | SEP | 2024-09-28 | 2024-10-18 | 2024-10-18 | 2024-10-18
45696 | 740-HLK-VH002-104-LH130-50-0 | 1 | true | 15.7 | 740-HLK-VH002-104-LH130-50-0 | LV1-105623.VH002 | 362 | 24.Mai.2024 |  | MC1 | LVL 6 | W60 | TR006 | 2024-03-07 | 2024-04-02 | 2024-04-03 |  | 2024-05-09 | 2024-05-13 | Büro | 2024-05-17 |  | 2024-05-15 | 2024-08-08 |  | 2024-08-12 | 2024-09-07 | 849 | 150 |  |  | 2024-09-12 | 149 | SEP | SEP | 2024-09-28 | 2024-10-18 | 2024-10-18 | 2024-10-18
45697 | 740-HLK-VH002-105-LH130-50-0 | 1 | true | 14.18 | 740-HLK-VH002-105-LH130-50-0 | LV1-105623.VH002 | 362 | 24.Mai.2024 |  | MC1 | LVL 6 | W60 | TR006 | 2024-03-07 | 2024-04-02 | 2024-04-03 |  | 2024-04-30 | 2024-05-10 | Büro | 2024-05-17 |  | 2024-05-10 | 2024-05-28 |  | 2024-06-04 | 2024-09-07 | 849 | 150 |  |  | 2024-09-12 | 149 | SEP | SEP | 2024-09-28 | 2024-10-18 | 2024-10-18 | 2024-10-18
45698 | 740-HLK-VH003-101-LH130-32-0 | 1 | false | 7.01 | 740-HLK-VH003-101-LH130-32-0 | LV1-105623.VH003 | 362 |  |  | MC1 | LVL 6 | W60 | TR006 | 2024-03-08 | [13 empty] | 849 | 150 |  |  |  | 149 | SEP | SEP
46659 | 740-HLK-VH003-101-LH130-32-0 | 2 | true | 7.01 | 740-HLK-VH003-101-LH130-32-0 | LV1-105623.VH003 | 362 | 24.Mai.2024 |  | MC1 | LVL 6 | W60 | TR007 | 2024-03-14 | 2024-03-22 | 2024-03-22 |  | 2024-04-18 | 2024-04-22 | Büro | 2024-04-26 |  | 2024-04-23 | 2024-08-27 |  |  | 2024-08-29 | 849 | 150 |  | 2024-09-09 | 2024-09-03 | 149 | SEP | SEP | 2024-09-20 | 2024-09-20 | 2024-09-20 | 2024-09-20
45699 | 740-HLK-VH003-102-LH130-32-0 | 1 | true | 10.24 | 740-HLK-VH003-102-LH130-32-0 | LV1-105623.VH003 | 362 | 24.Mai.2024 |  | MC1 | LVL 6 | W60 | TR006 | 2024-03-07 | 2024-04-02 | 2024-04-03 |  | 2024-05-13 | 2024-05-15 | Büro | 2024-05-31 |  | 2024-05-17 | 2024-08-12 |  |  | 2024-08-29 | 849 | 150 |  | 2024-09-09 | 2024-09-03 | 149 | SEP | SEP | 2024-09-04 | 2024-09-20 | 2024-09-20 | 2024-09-20
45700 | 740-HLK-VH003-104-LH130-32-0 | 1 | true | 7.14 | 740-HLK-VH003-104-LH130-32-0 | LV1-105623.VH003 | 362 | 24.Mai.2024 |  | MC1 | LVL 6 | W60 | TR006 | 2024-03-07 | 2024-04-02 | 2024-04-03 |  | 2024-05-13 | 2024-05-17 | Büro | 2024-05-31 |  | 2024-05-21 | 2024-08-27 |  |  | 2024-08-29 | 849 | 150 |  | 2024-09-09 | 2024-09-03 | 149 | SEP | SEP | 2024-09-20 | 2024-09-20 | 2024-09-20 | 2024-09-20
45701 | 740-HLK-VH003-105-LH130-32-0 | 1 | true | 11.04 | 740-HLK-VH003-105-LH130-32-0 | LV1-105623.VH003 | 362 | 24.Mai.2024 |  | MC1 | LVL 6 | W60 | TR006 | 2024-03-07 | 2024-04-02 | 2024-04-03 |  | 2024-05-10 | 2024-05-13 | Büro | 2024-05-17 |  | 2024-05-16 | 2024-08-12 |  |  | 2024-08-29 | 849 | 150 |  | 2024-09-09 | 2024-09-03 | 149 | SEP | SEP | 2024-09-04 | 2024-09-20 | 2024-09-20 | 2024-09-20
45702 | 740-HLK-VH004-101-LH130-32-0 | 1 | true | 6.56 | 740-HLK-VH004-101-LH130-32-0 | LV1-105623.VH004 | 362 | 24.Mai.2024 |  | MC1 | LVL 6 | W60 | TR006 | 2024-03-07 | 2024-04-02 | 2024-04-03 |  | 2024-05-14 | 2024-05-15 | Büro | 2024-05-17 |  | 2024-05-16 |  |  |  | 2024-09-11 | 849 | 150 |  |  | 2024-09-12 | 149 | SEP | SEP | 2024-09-28 | 2024-10-18 | 2024-10-18 | 2024-10-18
45703 | 740-HLK-VH004-102-LH130-32-0 | 1 | true | 23.43 | 740-HLK-VH004-102-LH130-32-0 | LV1-105623.VH004 | 362 | 24.Mai.2024 |  | MC1 | LVL 6 | W60 | TR006 | 2024-03-07 | 2024-04-02 | 2024-04-03 |  | 2024-05-09 | 2024-05-16 | Büro | 2024-05-31 |  | 2024-05-17 | 2024-08-14 |  |  | 2024-08-24 | 849 | 150 |  |  | 2024-09-09 | 149 | SEP | SEP | 2024-09-28 | 2024-10-18 | 2024-10-18 | 2024-10-18
45704 | 740-HLK-VH004-104-LH130-32-0 | 1 | true | 7.49 | 740-HLK-VH004-104-LH130-32-0 | LV1-105623.VH004 | 362 | 24.Mai.2024 |  | MC1 | LVL 6 | W60 | TR006 | 2024-03-07 | 2024-04-02 | 2024-04-03 |  | 2024-05-10 | 2024-05-14 | Büro | 2024-05-17 |  | 2024-05-16 |  |  |  | 2024-09-12 | 849 | 150 |  |  | 2024-09-12 | 149 | SEP | SEP | 2024-09-28 | 2024-10-18 | 2024-10-18 | 2024-10-18
45705 | 740-HLK-VH004-105-LH130-32-0 | 1 | true | 23.33 | 740-HLK-VH004-105-LH130-32-0 | LV1-105623.VH004 | 362 | 24.Mai.2024 |  | MC1 | LVL 6 | W60 | TR006 | 2024-03-07 | 2024-04-02 | 2024-04-03 |  | 2024-05-10 | 2024-05-15 | Büro | 2024-05-31 |  | 2024-05-17 | 2024-08-14 |  |  | 2024-08-24 | 849 | 150 |  |  | 2024-09-09 | 149 | SEP | SEP | 2024-09-28 | 2024-10-18 | 2024-10-18 | 2024-10-18
45706 | 740-HLK-VH005-101-LH130-32-0 | 1 | true | 16.03 | 740-HLK-VH005-101-LH130-32-0 | LV1-105623.VH005 | 362 | 24.Mai.2024 |  | MC1 | LVL 6 | W60 | TR006 | 2024-03-07 | 2024-04-02 | 2024-04-03 |  | 2024-05-09 | 2024-05-15 | Büro | 2024-05-17 |  | 2024-05-16 |  |  | 2024-06-07 | 2024-08-29 | 849 | 150 |  | 2024-09-09 | 2024-09-02 | 149 | SEP | SEP | 2024-09-20 | 2024-09-20 | 2024-09-20 | 2024-09-20
45707 | 740-HLK-VH005-102-LH130-32-0 | 1 | true | 18.29 | 740-HLK-VH005-102-LH130-32-0 | LV1-105623.VH005 | 362 | 24.Mai.2024 |  | MC1 | LVL 6 | W60 | TR006 | 2024-03-07 | 2024-04-02 | 2024-04-03 |  | 2024-05-09 | 2024-05-13 | Büro | 2024-05-17 |  | 2024-05-14 |  |  | 2024-06-11 | 2024-08-29 | 849 | 150 |  | 2024-09-09 | 2024-09-02 | 149 | SEP | SEP | 2024-09-04 | 2024-09-20 | 2024-09-20 | 2024-09-20
45708 | 740-HLK-VH005-104-LH130-32-0 | 1 | true | 15.91 | 740-HLK-VH005-104-LH130-32-0 | LV1-105623.VH005 | 362 | 24.Mai.2024 |  | MC1 | LVL 6 | W60 | TR006 | 2024-03-07 | 2024-04-02 | 2024-04-03 |  | 2024-05-13 | 2024-05-14 | Büro | 2024-05-17 |  | 2024-05-16 |  |  | 2024-06-10 | 2024-08-29 | 849 | 150 |  | 2024-09-09 | 2024-09-02 | 149 | SEP | SEP | 2024-09-20 | 2024-09-20 | 2024-09-20 | 2024-09-20
45709 | 740-HLK-VH005-105-LH130-32-0 | 1 | true | 20.13 | 740-HLK-VH005-105-LH130-32-0 | LV1-105623.VH005 | 362 | 24.Mai.2024 |  | MC1 | LVL 6 | W60 | TR006 | 2024-03-07 | 2024-04-02 | 2024-04-03 |  | 2024-05-13 | 2024-05-13 | Büro | 2024-05-31 |  | 2024-05-20 |  |  | 2024-06-12 | 2024-08-29 | 849 | 150 |  | 2024-09-09 | 2024-09-02 | 149 | SEP | SEP | 2024-09-04 | 2024-09-20 | 2024-09-20 | 2024-09-20
45710 | 740-LS-VU020-101-LH023-32-0 | 1 | false | 15.73 | 740-LS-VU020-101-LH023-32-0 | LV1-105638.VU020 | 368 | 16.May.2024 |  | MC1 | LVL 6 | N/A | TR006 | 2024-03-05 | 2024-04-22 | 2024-04-23 | [11 empty] | 850 | 150 |  |  |  | 149 | SEP | SEP
50143 | 740-LS-VU020-101-LH023-32-0 | 2 | true | 15.73 | 740-LS-VU020-101-LH023-32-0 | LV1-105638.VU020 | 368 | 16.May.2024 |  | MC1 | LVL 6 | N/A | TR015_1 | 2024-04-30 | 2024-04-21 | 2024-04-22 |  | 2024-05-09 | 2024-05-13 | Büro | 2024-05-17 |  | 2024-05-14 | 2024-06-17 |  |  | 2024-06-20 | 850 | 150 |  |  | 2024-10-24 | 149 | SEP | SEP
45711 | 740-LS-VU020-102-LH023-32-0 | 1 | true | 43.9 | 740-LS-VU020-102-LH023-32-0 | LV1-105638.VU020 | 368 | 16.May.2024 |  | MC1 | LVL 6 | N/A | TR006 | 2024-03-05 | 2024-04-22 | 2024-04-23 |  | 2024-06-03 | 2024-06-08 | Büro | 2024-06-28 |  | 2024-06-14 | 2024-07-04 | 2024-07-05 |  | 2024-07-09 | 850 | 150 |  |  | 2024-07-17 | 149 | SEP | SEP
45712 | 740-LS-VU020-103-LH023-15-0 | 1 | true | 16.95 | 740-LS-VU020-103-LH023-15-0 | LV1-105638.VU020 | 368 | 23.May.2024 |  | MC1 | LVL 6 | N/A | TR006 | 2024-03-05 | 2024-04-22 | 2024-04-23 |  | 2024-06-06 | 2024-06-12 | Büro | 2024-06-28 |  | 2024-06-14 | 2024-07-09 |  |  | 2024-07-12 | 850 | 150 |  | 2024-07-26 | 2024-07-17 | 149 | SEP | SEP
45713 | 740-LS-VU020-104-LH023-15-0 | 1 | true | 4.47 | 740-LS-VU020-104-LH023-15-0 | LV1-105638.VU020 | 368 |  |  | MC1 | LVL 6 | N/A | TR006 | 2024-03-05 | 2024-04-22 | 2024-04-23 |  | 2024-06-06 | 2024-06-11 |  | 2024-06-28 |  | 2024-06-11 | 2024-07-10 |  |  | 2024-07-19 | 850 | 150 |  |  | 2024-07-17 | 149 | SEP | SEP
45714 | 740-LS-VU020-105-LH023-15-0 | 1 | true | 4.61 | 740-LS-VU020-105-LH023-15-0 | LV1-105638.VU020 | 368 |  |  | MC1 | LVL 6 | N/A | TR006 | 2024-03-05 | 2024-04-22 | 2024-04-23 |  | 2024-06-06 | 2024-06-11 |  | 2024-06-28 |  | 2024-06-11 | 2024-07-10 |  |  | 2024-07-19 | 850 | 150 |  |  | 2024-07-17 | 149 | SEP | SEP
45715 | 740-LS-VU020-106-LH023-15-0 | 1 | true | 18.22 | 740-LS-VU020-106-LH023-15-0 | LV1-105638.VU020 | 368 | 23.May.2024 |  | MC1 | LVL 6 | N/A | TR006 | 2024-03-05 | 2024-04-22 | 2024-04-23 |  | 2024-06-06 | 2024-06-11 | Attila Henter | 2024-06-28 |  | 2024-06-11 | 2024-07-09 |  |  | 2024-07-19 | 850 | 150 |  |  | 2024-07-17 | 149 | SEP | SEP
45716 | 740-LS-VU020-107-LH023-15-0 | 1 | true | 8.8 | 740-LS-VU020-107-LH023-15-0 | LV1-105638.VU020 | 368 |  |  | MC1 | LVL 6 | N/A | TR006 | 2024-03-05 | 2024-04-22 | 2024-04-23 |  | 2024-06-06 | 2024-06-13 | Büro | 2024-06-28 |  | 2024-06-17 | 2024-07-12 |  |  | 2024-07-16 | 850 | 150 |  |  | 2024-07-17 | 149 | SEP | SEP
45717 | 740-LS-VU020-109-LH023-15-0 | 1 | true | 5.96 | 740-LS-VU020-109-LH023-15-0 | LV1-105638.VU020 | 368 | 23.May.2024 |  | MC1 | LVL 6 | N/A | TR006 | 2024-03-05 | 2024-04-22 | 2024-04-23 |  | 2024-06-06 | 2024-06-08 | Büro | 2024-06-14 |  | 2024-06-08 | 2024-06-25 |  |  | 2024-06-28 | 850 | 150 |  |  | 2024-07-03 | 149 | SEP | SEP
45718 | 740-LS-VU020-110-LH023-15-0 | 1 | true | 9.5 | 740-LS-VU020-110-LH023-15-0 | LV1-105638.VU020 | 368 | 23.May.2024 |  | MC1 | LVL 6 | N/A | TR006 | 2024-03-05 | 2024-04-22 | 2024-04-23 |  | 2024-06-06 | 2024-06-12 | Büro | 2024-06-28 |  | 2024-06-14 | 2024-07-08 |  |  | 2024-07-10 | 850 | 150 |  |  | 2024-07-17 | 149 | SEP | SEP
45719 | 740-LS-VU020-111-LH023-15-0 | 1 | true | 8.46 | 740-LS-VU020-111-LH023-15-0 | LV1-105638.VU020 | 368 | 23.May.2024 |  | MC1 | LVL 6 | N/A | TR006 | 2024-03-05 | 2024-04-22 | 2024-04-23 |  | 2024-06-06 | 2024-06-08 | Büro | 2024-06-14 |  | 2024-06-08 | 2024-06-25 |  |  | 2024-06-27 | 850 | 150 |  |  | 2024-07-03 | 149 | SEP | SEP
45720 | 740-LS-VU020-112-LH023-15-0 | 1 | true | 1.82 | 740-LS-VU020-112-LH023-15-0 | LV1-105638.VU020 | 368 |  |  | MC1 | LVL 6 | N/A | TR006 | 2024-03-05 | 2024-04-22 | 2024-04-23 |  | 2024-06-06 | 2024-06-07 | Büro | 2024-06-14 |  | 2024-06-07 | 2024-07-08 |  |  | 2024-07-08 | 850 | 150 |  |  | 2024-07-17 | 149 | SEP | SEP
45721 | 740-LS-VU020-113-LH023-25-0 | 1 | true | 15.97 | 740-LS-VU020-113-LH023-25-0 | LV1-105638.VU020 | 368 | 23.May.2024 |  | MC1 | LVL 6 | N/A | TR006 | 2024-03-05 | 2024-04-22 | 2024-04-23 |  | 2024-06-06 | 2024-06-10 | Büro | 2024-06-14 |  | 2024-06-10 | 2024-06-24 |  |  | 2024-06-25 | 850 | 150 |  |  | 2024-07-17 | 149 | SEP | SEP
45722 | 740-LS-VU020-115-LH023-15-0 | 1 | true | 13.59 | 740-LS-VU020-115-LH023-15-0 | LV1-105638.VU020 | 368 | 23.May.2024 |  | MC1 | LVL 6 | N/A | TR006 | 2024-03-05 | 2024-04-22 | 2024-04-23 |  | 2024-06-06 | 2024-06-11 | Büro | 2024-06-28 |  | 2024-06-14 | 2024-07-08 |  |  | 2024-07-09 | 850 | 150 |  |  | 2024-07-17 | 149 | SEP | SEP
45723 | 740-LS-VU020-118-LH023-15-0 | 1 | true | 5.95 | 740-LS-VU020-118-LH023-15-0 | LV1-105638.VU020 | 368 |  |  | MC1 | LVL 6 | N/A | TR006 | 2024-03-05 | 2024-04-22 | 2024-04-23 |  | 2024-06-06 | 2024-06-10 | Büro | 2024-06-14 |  | 2024-06-10 | 2024-07-02 |  |  | 2024-07-08 | 850 | 150 |  |  | 2024-07-17 | 149 | SEP | SEP
45724 | 740-LS-VU020-119-LH023-25-0 | 1 | true | 3.43 | 740-LS-VU020-119-LH023-25-0 | LV1-105638.VU020 | 368 |  |  | MC1 | LVL 6 | N/A | TR006 | 2024-03-05 | 2024-04-22 | 2024-04-23 |  | 2024-06-05 | 2024-06-07 | Büro | 2024-06-14 |  | 2024-06-07 | 2024-07-08 |  |  | 2024-07-09 | 850 | 150 |  |  | 2024-07-17 | 149 | SEP | SEP
45725 | 740-LS-VU020-126-LH023-25-0 | 1 | true | 5.6 | 740-LS-VU020-126-LH023-25-0 | LV1-105638.VU020 | 368 | 23.May.2024 |  | MC1 | LVL 6 | N/A | TR006 | 2024-03-05 | 2024-04-22 | 2024-04-23 |  | 2024-06-05 | 2024-06-08 | Büro | 2024-06-14 |  | 2024-06-08 | 2024-07-09 |  |  | 2024-07-10 | 850 | 150 |  |  | 2024-07-17 | 149 | SEP | SEP
45726 | 740-LS-VU020-137-LH023-15-0 | 1 | true | 3.38 | 740-LS-VU020-137-LH023-15-0 | LV1-105638.VU020 | 368 |  |  | MC1 | LVL 6 | N/A | TR006 | 2024-03-05 | 2024-04-22 | 2024-04-23 |  | 2024-06-06 | 2024-06-11 | Büro | 2024-06-28 |  | 2024-06-13 | 2024-07-09 |  |  | 2024-07-10 | 850 | 150 |  |  | 2024-07-17 | 149 | SEP | SEP
45727 | 740-LS-VU020-138-LH023-15-0 | 1 | true | 7.02 | 740-LS-VU020-138-LH023-15-0 | LV1-105638.VU020 | 368 | 23.May.2024 |  | MC1 | LVL 6 | N/A | TR006 | 2024-03-05 | 2024-04-22 | 2024-04-23 |  | 2024-06-06 | 2024-06-12 | Büro | 2024-06-28 |  | 2024-06-12 | 2024-07-10 |  |  | 2024-07-11 | 850 | 150 |  |  | 2024-07-16 | 149 | SEP | SEP
45728 | 740-LS-VU020-139-LH023-25-0 | 1 | true | 3.12 | 740-LS-VU020-139-LH023-25-0 | LV1-105638.VU020 | 368 |  |  | MC1 | LVL 6 | N/A | TR006 | 2024-03-05 | 2024-04-22 | 2024-04-23 |  | 2024-06-05 | 2024-06-08 | Büro | 2024-06-14 |  | 2024-06-08 | 2024-07-10 |  |  | 2024-07-10 | 850 | 150 |  |  | 2024-07-16 | 149 | SEP | SEP
45729 | 740-LS-VU020-141-LH023-25-0 | 1 | true | 1.47 | 740-LS-VU020-141-LH023-25-0 | LV1-105638.VU020 | 368 |  |  | MC1 | LVL 6 | N/A | TR006 | 2024-03-05 | 2024-04-22 | 2024-04-23 |  | 2024-06-05 | 2024-06-08 | Büro | 2024-06-14 |  | 2024-06-08 | 2024-07-10 |  |  | 2024-07-10 | 850 | 150 |  |  | 2024-07-16 | 149 | SEP | SEP
45730 | 740-LS-VU020-149-LH023-15-0 | 1 | true | 1.67 | 740-LS-VU020-149-LH023-15-0 | LV1-105638.VU020 | 368 |  |  | MC1 | LVL 6 | N/A | TR006 | 2024-03-05 | 2024-04-22 | 2024-04-23 |  | 2024-06-06 | 2024-06-10 | Büro | 2024-06-28 |  | 2024-06-10 |  |  |  | 2024-07-15 | 850 | 150 |  |  | 2024-07-16 | 149 | SEP | SEP
45731 | 740-LS-VU020-150-LH023-15-0 | 1 | true | 0.1 | 740-LS-VU020-150-LH023-15-0 | LV1-105638.VU020 | 368 |  |  | MC1 | LVL 6 | N/A | TR006 | 2024-03-05 | 2024-04-22 | 2024-04-23 |  | 2024-06-06 | 2024-06-08 | Büro | 2024-06-14 |  | 2024-06-08 | 2024-07-10 |  |  | 2024-07-11 | 850 | 150 |  |  | 2024-07-16 | 149 | SEP | SEP
45732 | 740-LS-VU020-151-LH023-15-0 | 1 | true | 10.33 | 740-LS-VU020-151-LH023-15-0 | LV1-105638.VU020 | 368 | 23.May.2024 |  | MC1 | LVL 6 | N/A | TR006 | 2024-03-05 | 2024-04-22 | 2024-04-23 |  | 2024-06-06 | 2024-06-10 | Büro | 2024-06-14 |  | 2024-06-10 |  |  |  | 2024-07-09 | 850 | 150 |  |  | 2024-07-16 | 149 | SEP | SEP
45733 | 740-LS-VU020-152-LH023-15-0 | 1 | true | 19.86 | 740-LS-VU020-152-LH023-15-0 | LV1-105638.VU020 | 368 | 23.May.2024 |  | MC1 | LVL 6 | N/A | TR006 | 2024-03-05 | 2024-04-22 | 2024-04-23 |  | 2024-06-06 | 2024-06-11 | Büro | 2024-06-28 |  | 2024-06-11 | 2024-07-10 |  |  | 2024-07-11 | 850 | 150 |  |  | 2024-07-16 | 149 | SEP | SEP
45734 | 740-LS-VU020-153-LH023-25-0 | 1 | false | 3.81 | 740-LS-VU020-153-LH023-25-0 | LV1-105638.VU020 | 368 |  |  | MC1 | LVL 6 | N/A | TR006 | 2024-03-05 | [13 empty] | 850 | 150 |  |  |  | 149 | SEP | SEP
49506 | 740-LS-VU020-153-LH023-25-0 | 2 | true | 3.81 | 740-LS-VU020-153-LH023-25-0 | LV1-105638.VU020 | 368 |  |  | MC1 | LVL 6 | N/A | TR013_2 | 2024-04-21 | 2024-04-23 | 2024-04-23 |  | 2024-06-12 | 2024-06-17 | Büro | 2024-06-28 |  | 2024-06-20 | 2024-07-10 |  |  | 2024-07-11 | 850 | 150 |  |  | 2024-07-16 | 149 | SEP | SEP
46657 | 727-AGO-U335-110-LH032-25-0 | 1 | true | 13.24 | 727-AGO-U335-110-LH032-25-0 | LV1-103542 Blatt 335 | 385 |  |  | MC1 | LVL 6 | N/A | TR007 | 2024-03-15 | 2024-03-23 | 2024-03-23 |  |  |  | Büro |  |  | 2024-05-29 | 2024-05-29 |  |  | 2024-06-04 | 858 | 150 |  | 2024-07-05 | 2024-07-05 | 149 | SEP | SEP
46658 | 727-AGO-U335-111-LH032-25-0 | 1 | true | 13.24 | 727-AGO-U335-111-LH032-25-0 | LV1-103542 Blatt 335 | 385 |  |  | MC1 | LVL 6 | N/A | TR007 | 2024-03-15 | 2024-03-23 | 2024-03-23 |  |  |  | Büro |  |  | 2024-05-29 | 2024-05-29 |  |  | 2024-06-04 | 858 | 150 |  | 2024-07-05 | 2024-07-05 | 149 | SEP | SEP
46662 | 740-MKWP-R-VU231-132-LH001-50-0 | 1 | true | 39.49 | 740-MKWP-R-VU231-132-LH001-50-0 | LV1-105638.VU231 | 363 | 26.Apr.2024 |  | MC1 | LVL 5 | T60 | TR007 | 2024-03-14 | 2024-03-22 | 2024-03-22 |  | 2024-04-20 | 2024-04-25 | Büro | 2024-04-26 |  | 2024-04-25 | 2024-05-14 | 2024-05-24 |  | 2024-05-28 | 860 | 150 |  | 2024-10-02 | 2024-07-12 | 149 | SEP | SEP | 2024-09-27 | 2024-08-19 | 2024-10-04 | 2024-10-04
46663 | 740-MKWP-R-VU231-133-LH099-15-0 | 1 | true | 1.31 | 740-MKWP-R-VU231-133-LH099-15-0 | LV1-105638.VU231 | 386 |  |  | MC1 | LVL 5 | Tt6 | TR007 | 2024-03-14 | 2024-03-22 | 2024-03-22 |  | 2024-06-07 | 2024-06-10 | Büro | 2024-06-28 |  | 2024-06-10 | 2024-09-11 |  |  | 2024-09-21 | 860 | 150 |  | 2024-10-02 | 2024-09-24 | 149 | SEP | SEP | 2024-09-27 |  | 2024-11-01 | 2024-11-01
46664 | 740-MKWP-R-VU231-134-LH099-15-0 | 1 | true | 1.23 | 740-MKWP-R-VU231-134-LH099-15-0 | LV1-105638.VU231 | 386 |  |  | MC1 | LVL 5 | Tt6 | TR007 | 2024-03-14 | 2024-03-22 | 2024-03-22 |  | 2024-06-07 | 2024-06-10 | Büro | 2024-06-28 |  | 2024-06-10 | 2024-09-11 |  |  | 2024-09-21 | 860 | 150 |  | 2024-10-02 | 2024-09-24 | 149 | SEP | SEP | 2024-09-27 |  | 2024-11-01 | 2024-11-01
46665 | 740-MKWP-R-VU231-135-LH099-15-0 | 1 | true | 1.29 | 740-MKWP-R-VU231-135-LH099-15-0 | LV1-105638.VU231 | 386 |  |  | MC1 | LVL 5 | Tt6 | TR007 | 2024-03-14 | 2024-03-22 | 2024-03-22 |  | 2024-06-07 | 2024-06-10 | Büro | 2024-06-28 |  | 2024-06-10 | 2024-09-11 |  |  | 2024-09-21 | 860 | 150 |  | 2024-10-02 | 2024-09-24 | 149 | SEP | SEP | 2024-09-27 |  | 2024-11-01 | 2024-11-01
46666 | 740-MKWP-R-VU231-136-LH099-15-0 | 1 | true | 1.29 | 740-MKWP-R-VU231-136-LH099-15-0 | LV1-105638.VU231 | 386 |  |  | MC1 | LVL 5 | Tt6 | TR007 | 2024-03-14 | 2024-03-22 | 2024-03-22 |  | 2024-06-07 | 2024-06-10 | Büro | 2024-06-28 |  | 2024-06-10 | 2024-09-11 |  |  | 2024-09-21 | 860 | 150 |  | 2024-10-02 | 2024-09-24 | 149 | SEP | SEP | 2024-09-27 |  | 2024-11-01 | 2024-11-01
46667 | 740-MKWP-R-VU231-137-LH099-15-0 | 1 | true | 1.29 | 740-MKWP-R-VU231-137-LH099-15-0 | LV1-105638.VU231 | 386 |  |  | MC1 | LVL 5 | Tt6 | TR007 | 2024-03-14 | 2024-03-22 | 2024-03-22 |  | 2024-06-07 | 2024-06-10 | Büro | 2024-06-28 |  | 2024-06-10 | 2024-09-11 |  |  | 2024-09-21 | 860 | 150 |  | 2024-10-02 | 2024-09-24 | 149 | SEP | SEP | 2024-09-27 |  | 2024-11-01 | 2024-11-01
46668 | 740-MKWP-R-VU231-138-LH099-15-0 | 1 | true | 1.29 | 740-MKWP-R-VU231-138-LH099-15-0 | LV1-105638.VU231 | 386 |  |  | MC1 | LVL 5 | Tt6 | TR007 | 2024-03-14 | 2024-03-22 | 2024-03-22 |  | 2024-06-07 | 2024-06-10 | Büro | 2024-06-28 |  | 2024-06-10 | 2024-09-11 |  |  | 2024-09-21 | 860 | 150 |  | 2024-10-02 | 2024-07-12 | 149 | SEP | SEP | 2024-09-27 |  | 2024-11-01 | 2024-11-01
46669 | 740-MKWP-R-VU231-139-LH099-15-0 | 1 | true | 1.45 | 740-MKWP-R-VU231-139-LH099-15-0 | LV1-105638.VU231 | 386 |  |  | MC1 | LVL 5 | Tt6 | TR007 | 2024-03-14 | 2024-03-22 | 2024-03-22 |  | 2024-06-07 | 2024-06-10 | Büro | 2024-06-28 |  | 2024-06-10 | 2024-09-11 |  |  | 2024-09-21 | 860 | 150 |  | 2024-10-02 | 2024-07-12 | 149 | SEP | SEP | 2024-09-27 |  | 2024-11-01 | 2024-11-01
46674 | 740-MKWP-S-VU231-113-LH001-50-0 | 1 | true | 39.62 | 740-MKWP-S-VU231-113-LH001-50-0 | LV1-105638.VU231 | 363 | 26.Apr.2024 |  | MC1 | LVL 5 | T60 | TR007 | 2024-03-14 | 2024-03-22 | 2024-03-22 |  | 2024-04-19 | 2024-04-25 | Büro | 2024-04-26 |  | 2024-04-25 | 2024-05-14 | 2024-05-24 |  | 2024-05-28 | 860 | 150 |  | 2024-10-02 | 2024-07-15 | 149 | SEP | SEP | 2024-09-27 | 2024-10-04 | 2024-10-04 | 2024-10-04
46675 | 740-MKWP-S-VU231-114-LH099-15-0 | 1 | true | 1.31 | 740-MKWP-S-VU231-114-LH099-15-0 | LV1-105638.VU231 | 386 |  |  | MC1 | LVL 5 | Tt6 | TR007 | 2024-03-14 | 2024-03-22 | 2024-03-22 |  | 2024-06-06 | 2024-06-07 | Büro | 2024-06-14 |  | 2024-06-07 | 2024-09-11 |  |  | 2024-09-21 | 860 | 150 |  | 2024-10-02 | 2024-09-24 | 149 | SEP | SEP | 2024-09-27 |  | 2024-11-01 | 2024-11-01
46676 | 740-MKWP-S-VU231-115-LH099-15-0 | 1 | true | 1.23 | 740-MKWP-S-VU231-115-LH099-15-0 | LV1-105638.VU231 | 386 |  |  | MC1 | LVL 5 | Tt6 | TR007 | 2024-03-14 | 2024-03-22 | 2024-03-22 |  | 2024-06-06 | 2024-06-07 | Büro | 2024-06-14 |  | 2024-06-07 | 2024-09-11 |  |  | 2024-09-21 | 860 | 150 |  | 2024-10-02 | 2024-09-24 | 149 | SEP | SEP | 2024-09-27 |  | 2024-11-01 | 2024-11-01
46677 | 740-MKWP-S-VU231-116-LH099-15-0 | 1 | true | 1.29 | 740-MKWP-S-VU231-116-LH099-15-0 | LV1-105638.VU231 | 386 |  |  | MC1 | LVL 5 | Tt6 | TR007 | 2024-03-14 | 2024-03-22 | 2024-03-22 |  | 2024-06-06 | 2024-06-07 | Büro | 2024-06-14 |  | 2024-06-07 | 2024-09-11 |  |  | 2024-09-21 | 860 | 150 |  | 2024-10-02 | 2024-09-24 | 149 | SEP | SEP | 2024-09-27 |  | 2024-11-01 | 2024-11-01
46678 | 740-MKWP-S-VU231-117-LH099-15-0 | 1 | true | 1.29 | 740-MKWP-S-VU231-117-LH099-15-0 | LV1-105638.VU231 | 386 |  |  | MC1 | LVL 5 | Tt6 | TR007 | 2024-03-14 | 2024-03-22 | 2024-03-22 |  | 2024-06-06 | 2024-06-07 | Büro | 2024-06-14 |  | 2024-06-07 | 2024-09-11 |  |  | 2024-09-21 | 860 | 150 |  | 2024-10-02 | 2024-09-24 | 149 | SEP | SEP | 2024-09-27 |  | 2024-11-01 | 2024-11-01
46679 | 740-MKWP-S-VU231-118-LH099-15-0 | 1 | true | 1.29 | 740-MKWP-S-VU231-118-LH099-15-0 | LV1-105638.VU231 | 386 |  |  | MC1 | LVL 5 | Tt6 | TR007 | 2024-03-14 | 2024-03-22 | 2024-03-22 |  | 2024-06-06 | 2024-06-07 | Büro | 2024-06-14 |  | 2024-06-07 | 2024-09-11 |  |  | 2024-09-21 | 860 | 150 |  | 2024-10-02 | 2024-09-24 | 149 | SEP | SEP | 2024-09-27 |  | 2024-11-01 | 2024-11-01
46680 | 740-MKWP-S-VU231-119-LH099-15-0 | 1 | true | 1.29 | 740-MKWP-S-VU231-119-LH099-15-0 | LV1-105638.VU231 | 386 |  |  | MC1 | LVL 5 | Tt6 | TR007 | 2024-03-14 | 2024-03-22 | 2024-03-22 |  | 2024-06-06 | 2024-06-07 | Büro | 2024-06-14 |  | 2024-06-07 | 2024-09-11 |  |  | 2024-09-21 | 860 | 150 |  | 2024-10-02 | 2024-09-24 | 149 | SEP | SEP | 2024-09-27 |  | 2024-11-01 | 2024-11-01
46681 | 740-MKWP-S-VU231-120-LH099-15-0 | 1 | true | 1.45 | 740-MKWP-S-VU231-120-LH099-15-0 | LV1-105638.VU231 | 386 |  |  | MC1 | LVL 5 | Tt6 | TR007 | 2024-03-14 | 2024-03-22 | 2024-03-22 |  | 2024-06-06 | 2024-06-07 | Büro | 2024-06-14 |  | 2024-06-07 | 2024-09-11 |  |  | 2024-09-21 | 860 | 150 |  | 2024-10-02 | 2024-09-24 | 149 | SEP | SEP | 2024-09-27 |  | 2024-11-01 | 2024-11-01
46682 | 740-WASH-VH001-111-LH032-20-0 | 1 | true | 0.47 | 740-WASH-VH001-111-LH032-20-0 | LV1-105623.VH001 | 385 | 24.Mai.2024 |  | MC1 | LVL 6 | N/A | TR007 | 2024-03-14 | 2024-03-22 | 2024-03-22 |  | 2024-05-13 | 2024-05-15 |  | 2024-05-17 |  | 2024-05-16 | 2024-10-22 |  |  | 2024-10-23 | 861 | 150 |  |  |  | 149 | SEP | SEP
46683 | 740-WASH-VH002-111-LH032-20-0 | 1 | true | 0.38 | 740-WASH-VH002-111-LH032-20-0 | LV1-105623.VH002 | 385 | 24.Mai.2024 |  | MC1 | LVL 6 | N/A | TR007 | 2024-03-14 | 2024-03-22 | 2024-03-22 |  | 2024-05-13 | 2024-05-17 |  | 2024-05-31 |  | 2024-05-17 | 2024-10-22 |  |  | 2024-10-23 | 861 | 150 |  |  |  | 149 | SEP | SEP
46684 | 740-WASH-VH003-112-LH032-20-0 | 1 | true | 0.99 | 740-WASH-VH003-112-LH032-20-0 | LV1-105623.VH003 | 385 | 24.Mai.2024 |  | MC1 | LVL 6 | N/A | TR007 | 2024-03-14 | 2024-03-22 | 2024-03-22 |  | 2024-05-11 | 2024-05-13 | Büro | 2024-05-17 |  | 2024-05-14 | 2024-10-11 |  |  | 2024-10-15 | 861 | 150 |  |  |  | 149 | SEP | SEP
46685 | 740-WASH-VH004-111-LH032-20-0 | 1 | true | 1.01 | 740-WASH-VH004-111-LH032-20-0 | LV1-105623.VH004 | 385 | 24.Mai.2024 |  | MC1 | LVL 6 | N/A | TR007 | 2024-03-14 | 2024-03-22 | 2024-03-22 |  | 2024-05-14 | 2024-05-14 |  | 2024-05-17 |  | 2024-05-16 | 2024-10-22 |  |  | 2024-10-22 | 861 | 150 |  |  | 2024-11-04 | 149 | SEP | SEP
46686 | 740-WASH-VH005-112-LH032-20-0 | 1 | true | 0.91 | 740-WASH-VH005-112-LH032-20-0 | LV1-105623.VH005 | 385 | 24.Mai.2024 |  | MC1 | LVL 6 | N/A | TR007 | 2024-03-14 | 2024-03-22 | 2024-03-22 |  | 2024-05-14 | 2024-05-15 | Büro | 2024-05-17 |  | 2024-05-16 | 2024-10-11 |  |  | 2024-10-15 | 861 | 150 |  |  |  | 149 | SEP | SEP
46690 | 740-D3-VP001-303-LC008-50-0 | 1 | true | 4.35 | 740-D3-VP001-303-LC008-50-0 | LV1-105638.VU111 | 388 | 3.May.2024 |  | MC1 | LVL 6 | W23 | TR008 | 2024-03-18 | 2024-03-26 | 2024-03-26 |  | 2024-04-09 | 2024-04-17 | Büro | 2024-04-29 |  | 2024-04-18 | 2024-09-25 |  |  | 2024-09-30 | 901 | 150 |  | 2024-11-13 | 2024-10-01 | 149 | SEP | SEP | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22
46691 | 740-D3-VP002-303-LC008-50-0 | 1 | true | 4.44 | 740-D3-VP002-303-LC008-50-0 | LV1-105638.VU111 | 388 | 3.May.2024 |  | MC1 | LVL 6 | W23 | TR008 | 2024-03-18 | 2024-03-26 | 2024-03-26 |  | 2024-04-10 | 2024-04-12 | Büro | 2024-04-29 |  | 2024-04-18 | 2024-09-25 |  |  | 2024-09-28 | 901 | 150 |  |  | 2024-09-30 | 149 | SEP | SEP | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22
46692 | 740-D3-VP003-303-LC008-25-0 | 1 | true | 3.97 | 740-D3-VP003-303-LC008-25-0 | LV1-105638.VU111 | 388 | 3.May.2024 |  | MC1 | LVL 6 | W23 | TR008 | 2024-03-18 | 2024-03-26 | 2024-03-26 |  | 2024-04-26 | 2024-04-27 | Büro | 2024-04-29 |  | 2024-04-27 | 2024-09-25 |  |  | 2024-09-27 | 901 | 150 |  |  |  | 149 | SEP | SEP | 2024-10-25 | 2024-10-25 | 2024-10-25 | 2024-10-25 | 2024-10-25 | 2024-10-25
46693 | 740-D3-VP004-303-LC008-25-0 | 1 | true | 3.55 | 740-D3-VP004-303-LC008-25-0 | LV1-105638.VU111 | 388 | 3.May.2024 |  | MC1 | LVL 6 | W23 | TR008 | 2024-03-18 | 2024-03-26 | 2024-03-26 |  | 2024-04-23 | 2024-04-26 | Büro | 2024-04-29 |  | 2024-04-26 | 2024-09-25 |  |  | 2024-09-27 | 901 | 150 |  |  |  | 149 | SEP | SEP | 2024-10-25 | 2024-10-25 | 2024-10-25 | 2024-10-25 | 2024-10-25 | 2024-10-25
46694 | 740-D3-VP031-203-LC008-50-0 | 1 | true | 1.64 | 740-D3-VP031-203-LC008-50-0 | LV1-105638.VU111 | 388 | 3.May.2024 |  | MC1 | LVL 6 | W23 | TR008 | 2024-03-18 | 2024-03-26 | 2024-03-26 |  | 2024-04-10 | 2024-04-15 | Büro | 2024-04-29 |  | 2024-04-18 |  |  |  | 2024-10-04 | 901 | 150 |  |  |  | 149 | SEP | SEP
46695 | 740-D3-VP032-203-LC008-50-0 | 1 | true | 2.28 | 740-D3-VP032-203-LC008-50-0 | LV1-105638.VU111 | 388 | 3.May.2024 |  | MC1 | LVL 6 | W23 | TR008 | 2024-03-18 | 2024-03-26 | 2024-03-26 |  | 2024-04-10 | 2024-04-12 | Büro | 2024-04-29 |  | 2024-04-18 |  |  |  | 2024-10-04 | 901 | 150 |  |  |  | 149 | SEP | SEP | 2024-10-25 | 2024-10-25 | 2024-10-25 | 2024-10-25 | 2024-10-25 | 2024-10-25
46696 | 740-D3-VP033-203-LC008-50-0 | 1 | true | 1.76 | 740-D3-VP033-203-LC008-50-0 | LV1-105638.VU111 | 388 | 3.May.2024 |  | MC1 | LVL 6 | W23 | TR008 | 2024-03-18 | 2024-03-26 | 2024-03-26 |  | 2024-04-09 | 2024-04-18 | Büro | 2024-04-29 |  | 2024-04-18 |  |  |  | 2024-10-03 | 901 | 150 |  |  | 2024-10-04 | 149 | SEP | SEP | 2024-10-25 | 2024-10-25 | 2024-10-25 | 2024-10-25 | 2024-10-25 | 2024-10-25
46697 | 740-D3-VP041-203-LC008-50-0 | 1 | true | 1.58 | 740-D3-VP041-203-LC008-50-0 | LV1-105638.VU111 | 388 | 3.May.2024 |  | MC1 | LVL 6 | W23 | TR008 | 2024-03-18 | 2024-03-26 | 2024-03-26 |  | 2024-04-09 | 2024-04-27 | Büro | 2024-04-29 |  | 2024-04-27 |  |  |  | 2024-10-03 | 901 | 150 |  |  | 2024-10-04 | 149 | SEP | SEP | 2024-10-25 | 2024-10-25 | 2024-10-25 | 2024-10-25 | 2024-10-25 | 2024-10-25
46698 | 740-D3-VP042-203-LC008-50-0 | 1 | true | 1 | 740-D3-VP042-203-LC008-50-0 | LV1-105638.VU111 | 388 | 3.May.2024 |  | MC1 | LVL 6 | W23 | TR008 | 2024-03-18 | 2024-03-26 | 2024-03-26 |  | 2024-04-10 | 2024-04-16 | Büro | 2024-04-29 |  | 2024-04-18 |  |  |  | 2024-10-01 | 901 | 150 |  |  | 2024-10-03 | 149 | SEP | SEP | 2024-10-25 | 2024-10-25 | 2024-10-25 | 2024-10-25 | 2024-10-25 | 2024-10-25
46699 | 740-D3-VP043-203-LC008-50-0 | 1 | true | 2.5 | 740-D3-VP043-203-LC008-50-0 | LV1-105638.VU111 | 388 | 3.May.2024 |  | MC1 | LVL 6 | W23 | TR008 | 2024-03-18 | 2024-03-26 | 2024-03-26 |  | 2024-04-10 | 2024-04-16 | Büro | 2024-04-29 |  | 2024-04-18 |  |  |  | 2024-10-01 | 901 | 150 |  |  | 2024-10-01 | 149 | SEP | SEP
46700 | 740-D3-VP131-203-LC008-25-0 | 1 | true | 2.26 | 740-D3-VP131-203-LC008-25-0 | LV1-105638.VU111 | 388 | 3.May.2024 |  | MC1 | LVL 6 | W23 | TR008 | 2024-03-18 | 2024-03-26 | 2024-03-26 |  | 2024-04-23 | 2024-04-26 | Büro | 2024-04-29 |  | 2024-04-26 |  |  |  | 2024-10-07 | 901 | 150 |  | 2024-12-02 |  | 149 | SEP | SEP | 2024-10-25 | 2024-10-25 | 2024-10-25 | 2024-10-25 | 2024-10-25 | 2024-10-25
46701 | 740-D3-VP132-203-LC008-25-0 | 1 | true | 3.17 | 740-D3-VP132-203-LC008-25-0 | LV1-105638.VU111 | 388 | 3.May.2024 |  | MC1 | LVL 6 | W23 | TR008 | 2024-03-18 | 2024-03-26 | 2024-03-26 |  | 2024-04-23 | 2024-04-26 | Büro | 2024-04-29 |  | 2024-04-26 |  |  |  | 2024-10-08 | 901 | 150 |  |  |  | 149 | SEP | SEP
46702 | 740-D3-VP133-203-LC008-25-0 | 1 | true | 3.18 | 740-D3-VP133-203-LC008-25-0 | LV1-105638.VU111 | 388 | 3.May.2024 |  | MC1 | LVL 6 | W23 | TR008 | 2024-03-18 | 2024-03-26 | 2024-03-26 |  | 2024-04-23 | 2024-04-26 | Büro | 2024-04-29 |  | 2024-04-26 |  |  |  | 2024-10-09 | 901 | 150 |  |  | 2024-10-09 | 149 | SEP | SEP
46703 | 740-D3-VP141-203-LC008-25-0 | 1 | true | 1.27 | 740-D3-VP141-203-LC008-25-0 | LV1-105638.VU111 | 388 | 3.May.2024 |  | MC1 | LVL 6 | W23 | TR008 | 2024-03-18 | 2024-03-26 | 2024-03-26 |  | 2024-04-23 | 2024-04-26 | Büro | 2024-04-29 |  | 2024-04-26 | 2024-09-25 |  |  | 2024-09-26 | 901 | 150 |  |  |  | 149 | SEP | SEP
46704 | 740-D3-VP142-203-LC008-25-0 | 1 | true | 2.25 | 740-D3-VP142-203-LC008-25-0 | LV1-105638.VU111 | 388 | 3.May.2024 |  | MC1 | LVL 6 | W23 | TR008 | 2024-03-18 | 2024-03-26 | 2024-03-26 |  | 2024-04-11 | 2024-04-16 | Büro | 2024-04-29 |  | 2024-04-18 | 2024-09-25 |  |  | 2024-09-26 | 901 | 150 |  |  |  | 149 | SEP | SEP | 2024-10-25 | 2024-10-25 | 2024-10-25 | 2024-10-25 | 2024-10-25 | 2024-10-25
46705 | 740-D3-VP143-203-LC008-25-0 | 1 | true | 1.9 | 740-D3-VP143-203-LC008-25-0 | LV1-105638.VU111 | 388 | 3.May.2024 |  | MC1 | LVL 6 | W23 | TR008 | 2024-03-18 | 2024-03-26 | 2024-03-26 |  | 2024-04-23 | 2024-04-26 | Büro | 2024-04-29 |  | 2024-04-26 | 2024-09-25 |  |  | 2024-09-26 | 901 | 150 |  |  |  | 149 | SEP | SEP
46706 | 740-D3-VS001-101-LC008-25-0 | 1 | true | 5.28 | 740-D3-VS001-101-LC008-25-0 | LV1-105638.VU111 | 388 | 3.May.2024 |  | MC1 | LVL 5 | W23 | TR008 | 2024-03-18 | 2024-03-26 | 2024-03-26 |  | 2024-04-11 | 2024-04-15 | Büro | 2024-04-29 |  | 2024-04-18 | 2024-10-08 |  |  | 2024-10-09 | 902 | 150 |  |  | 2024-10-09 | 149 | SEP | SEP | 2024-10-25 | 2024-10-25 | 2024-10-25 | 2024-10-25 | 2024-10-25 | 2024-10-25
46707 | 740-D3-VS020-101-LC008-20-0 | 1 | true | 4.25 | 740-D3-VS020-101-LC008-20-0 | LV1-105638.VU111 | 388 | 3.May.2024 |  | MC1 | LVL 5 | W23 | TR008 | 2024-03-18 | 2024-03-26 | 2024-03-26 |  | 2024-04-25 | 2024-04-27 | Büro | 2024-04-29 |  | 2024-04-27 | 2024-10-08 |  |  | 2024-10-10 | 902 | 150 |  |  |  | 149 | SEP | SEP
46708 | 740-D3-VS671-101-LC008-65-0 | 1 | false | 1.59 | 740-D3-VS671-101-LC008-65-0 |  | 388 | 3.May.2024 |  | MC1 | LVL 6 | W23 | TR008 | 2024-03-18 | 2024-03-26 | 2024-03-26 |  | 2024-04-24 | 2024-04-26 |  | 2024-04-29 |  | 2024-04-26 | 2024-10-08 |  |  |  | 901 | 150 |  |  |  | 149 | SEP | SEP | 2024-09-25
46709 | 740-D3-VS671-103-LC008-65-0 | 1 | true | 1.59 | 740-D3-VS671-103-LC008-65-0 | LV1-105638.VU111 | 388 | 3.May.2024 |  | MC1 | LVL 6 | W23 | TR008 | 2024-03-18 | 2024-03-26 | 2024-03-26 |  | 2024-04-18 | 2024-04-23 | ZRO Prefab | 2024-04-29 |  | 2024-04-23 | 2024-07-18 |  |  | 2024-07-31 | 901 | 150 |  | 2024-08-28 | 2024-08-28 | 149 | SEP | SEP | 2024-09-25 |  | 2024-11-01 | 2024-11-01
46710 | 740-D3-VS672-101-LC008-65-0 | 1 | false | 1.6 | 740-D3-VS672-101-LC008-65-0 |  | 388 | 3.May.2024 |  | MC1 | LVL 6 | W23 | TR008 | 2024-03-18 | 2024-03-26 | 2024-03-26 |  | 2024-04-18 | 2024-04-20 |  | 2024-04-29 |  | 2024-04-23 | 2024-10-08 |  |  |  | 901 | 150 |  |  |  | 149 | SEP | SEP | 2024-09-25
46711 | 740-D3-VS672-103-LC008-65-0 | 1 | true | 1.6 | 740-D3-VS672-103-LC008-65-0 | LV1-105638.VU111 | 388 | 3.May.2024 |  | MC1 | LVL 6 | W23 | TR008 | 2024-03-18 | 2024-03-26 | 2024-03-26 |  | 2024-04-18 | 2024-04-20 | ZRO Prefab | 2024-04-29 |  | 2024-04-23 | 2024-07-18 |  |  | 2024-07-31 | 901 | 150 |  | 2024-08-28 | 2024-08-28 | 149 | SEP | SEP | 2024-09-25 |  | 2024-11-01 | 2024-11-01
46712 | 740-D3-VS673-101-LC008-65-0 | 1 | false | 1.58 | 740-D3-VS673-101-LC008-65-0 |  | 388 | 3.May.2024 |  | MC1 | LVL 6 | W23 | TR008 | 2024-03-18 | 2024-03-26 | 2024-03-26 |  | 2024-04-24 | 2024-04-26 |  | 2024-04-29 |  | 2024-04-26 | 2024-10-08 |  |  |  | 901 | 150 |  |  |  | 149 | SEP | SEP | 2024-09-25
46713 | 740-D3-VS673-103-LC008-65-0 | 1 | true | 1.58 | 740-D3-VS673-103-LC008-65-0 | LV1-105638.VU111 | 388 | 3.May.2024 |  | MC1 | LVL 6 | W23 | TR008 | 2024-03-18 | 2024-03-26 | 2024-03-26 |  | 2024-04-18 | 2024-04-22 | ZRO Prefab | 2024-04-29 |  | 2024-04-23 | 2024-07-18 |  |  | 2024-07-29 | 901 | 150 |  | 2024-08-28 | 2024-08-28 | 149 | SEP | SEP | 2024-09-25 |  | 2024-11-01 | 2024-11-01
46714 | 740-D3-VU111-101-LC008-100-0 | 1 | false | 68.2 | 740-D3-VU111-101-LC008-100-0 | LV1-105638.VU111 | 388 | 3.May.2024 |  | MC1 | LVL 6 | W23 | TR008 | 2024-03-19 | 2024-03-27 | 2024-03-27 |  |  |  | ZRO Prefab | [7 empty] | 901 | 150 |  |  |  | 149 | SEP | SEP
47228 | 740-D3-VU111-101-LC008-100-0 | 2 | true | 68.2 | 740-D3-VU111-101-LC008-100-0 | LV1-105638.VU111 | 388 | 3.May.2024 |  | MC1 | LVL 6 | W23 | TR011 | 2024-03-24 | 2024-04-04 | 2024-04-07 |  | 2024-04-15 | 2024-04-26 | Büro | 2024-04-29 |  | 2024-04-26 | 2024-05-15 |  | 2024-05-24 | 2024-05-29 | 901 | 150 |  | 2024-08-21 | 2024-07-24 | 149 | SEP | SEP | 2024-08-20 | 2024-09-09 | 2024-09-09 | 2024-09-09
46715 | 740-D3-VU111-103-LC008-80-0 | 1 | true | 9.86 | 740-D3-VU111-103-LC008-80-0 | LV1-105638.VU111 | 388 | 3.May.2024 |  | MC1 | LVL 6 | W23 | TR008 | 2024-03-18 | 2024-03-26 | 2024-03-26 |  | 2024-04-08 | 2024-04-09 | Büro | 2024-04-29 |  | 2024-04-10 | 2024-05-24 |  |  | 2024-05-29 | 901 | 150 |  | 2024-08-21 | 2024-07-24 | 149 | SEP | SEP | 2024-08-20 | 2024-09-18 | 2024-09-18 | 2024-09-18
46716 | 740-D3-VU111-105-LC008-65-0 | 1 | true | 2.6 | 740-D3-VU111-105-LC008-65-0 | LV1-105638.VU111 | 388 | 3.May.2024 |  | MC1 | LVL 6 | W23 | TR008 | 2024-03-18 | 2024-03-26 | 2024-03-26 |  | 2024-04-08 | 2024-04-10 | Büro | 2024-04-29 |  | 2024-04-11 | 2024-07-18 |  |  | 2024-07-31 | 901 | 150 |  | 2024-08-21 | 2024-07-24 | 149 | SEP | SEP | 2024-08-20 | 2024-09-09 | 2024-09-09 | 2024-09-09
46717 | 740-D3-VU111-106-LC008-80-0 | 1 | true | 14.7 | 740-D3-VU111-106-LC008-80-0 | LV1-105638.VU111 | 388 | 3.May.2024 |  | MC1 | LVL 6 | W23 | TR008 | 2024-03-18 | 2024-03-26 | 2024-03-26 |  | 2024-04-22 | 2024-04-29 | Büro | 2024-04-29 |  | 2024-04-29 | 2024-05-23 |  |  | 2024-05-24 | 901 | 150 |  | 2024-08-21 | 2024-07-24 | 149 | SEP | SEP | 2024-08-20 | 2024-09-09 | 2024-09-09 | 2024-09-09
46718 | 740-D3-VU111-107-LC008-65-0 | 1 | true | 2.95 | 740-D3-VU111-107-LC008-65-0 | LV1-105638.VU111 | 388 | 3.May.2024 |  | MC1 | LVL 6 | W23 | TR008 | 2024-03-18 | 2024-03-26 | 2024-03-26 |  | 2024-04-08 | 2024-04-10 | Büro | 2024-04-29 |  | 2024-04-11 | 2024-07-18 |  |  | 2024-07-31 | 901 | 150 |  | 2024-08-21 | 2024-07-24 | 149 | SEP | SEP | 2024-08-20 | 2024-09-09 | 2024-09-09 | 2024-09-09
46719 | 740-D3-VU111-109-LC008-65-0 | 1 | true | 2.5 | 740-D3-VU111-109-LC008-65-0 | LV1-105638.VU111 | 388 | 3.May.2024 |  | MC1 | LVL 6 | W23 | TR008 | 2024-03-18 | 2024-03-26 | 2024-03-26 |  | 2024-04-08 | 2024-04-10 | Büro | 2024-04-29 |  | 2024-04-11 | 2024-05-29 |  |  | 2024-06-10 | 901 | 150 |  | 2024-08-21 | 2024-07-24 | 149 | SEP | SEP | 2024-08-20 | 2024-09-09 | 2024-09-09 | 2024-09-09
46720 | 740-D3-VU111-110-LC008-65-0 | 1 | true | 12.71 | 740-D3-VU111-110-LC008-65-0 | LV1-105638.VU111 | 388 | 3.May.2024 |  | MC1 | LVL 6 | W23 | TR008 | 2024-03-18 | 2024-03-26 | 2024-03-26 |  | 2024-04-09 | 2024-04-18 | Büro | 2024-04-29 |  | 2024-04-18 | 2024-05-29 |  |  | 2024-06-13 | 901 | 150 |  | 2024-08-21 | 2024-07-24 | 149 | SEP | SEP | 2024-08-20 | 2024-09-09 | 2024-09-09 | 2024-09-09
46721 | 740-D3-VU111-111-LC008-20-0 | 1 | true | 0.36 | 740-D3-VU111-111-LC008-20-0 | LV1-105638.VU111 | 388 | 3.May.2024 |  | MC1 | LVL 5 | W23 | TR008 | 2024-03-18 | 2024-03-26 | 2024-03-26 |  | 2024-04-25 | 2024-04-27 | Büro | 2024-04-29 |  | 2024-04-27 | 2024-07-12 |  |  | 2024-07-15 | 902 | 150 |  | 2024-08-21 | 2024-07-24 | 149 | SEP | SEP | 2024-08-20 | 2024-09-13 | 2024-09-13 | 2024-09-13
46722 | 740-D3-VU111-112-LC008-25-0 | 1 | true | 0.35 | 740-D3-VU111-112-LC008-25-0 | LV1-105638.VU111 | 388 | 3.May.2024 |  | MC1 | LVL 5 | W23 | TR008 | 2024-03-18 | 2024-03-26 | 2024-03-26 |  | 2024-04-10 | 2024-04-18 | Büro | 2024-04-29 |  | 2024-04-23 | 2024-07-12 |  |  | 2024-07-15 | 902 | 150 |  | 2024-08-21 | 2024-07-24 | 149 | SEP | SEP | 2024-08-20 | 2024-09-13 | 2024-09-13 | 2024-09-13
46723 | 740-D3-VU111-112-LC008-40-0 | 1 | true | 30.08 | 740-D3-VU111-112-LC008-40-0 | LV1-105638.VU111 | 388 | 3.May.2024 |  | MC1 | LVL 6 | W23 | TR008 | 2024-03-18 | 2024-03-26 | 2024-03-26 |  | 2024-04-17 | 2024-04-19 | Büro | 2024-04-29 |  | 2024-04-23 | 2024-05-27 |  | 2024-06-13 | 2024-06-19 | 901 | 150 |  | 2024-08-21 | 2024-07-24 | 149 | SEP | SEP | 2024-08-20 | 2024-09-09 | 2024-09-09 | 2024-10-04
46724 | 740-D3-VU111-113-LC008-20-0 | 1 | true | 1.48 | 740-D3-VU111-113-LC008-20-0 | LV1-105638.VU111 | 388 | 3.May.2024 |  | MC1 | LVL 6 | W23 | TR008 | 2024-03-18 | 2024-03-26 | 2024-03-26 |  | 2024-04-10 | 2024-04-12 | Büro | 2024-04-29 |  | 2024-04-18 | 2024-05-29 |  |  | 2024-06-10 | 901 | 150 |  | 2024-08-21 | 2024-07-24 | 149 | SEP | SEP | 2024-08-20 | 2024-09-09 | 2024-09-09 | 2024-09-09
46725 | 740-D3-VU111-115-LC008-20-0 | 1 | true | 0.13 | 740-D3-VU111-115-LC008-20-0 | LV1-105638.VU111 | 388 | 3.May.2024 |  | MC1 | LVL 5 | W23 | TR008 | 2024-03-18 | 2024-03-26 | 2024-03-26 |  | 2024-04-10 | 2024-04-16 | Büro | 2024-04-29 |  | 2024-04-18 | 2024-07-12 |  |  | 2024-07-15 | 902 | 150 |  | 2024-08-21 | 2024-07-24 | 149 | SEP | SEP | 2024-08-20 | 2024-09-13 | 2024-09-13 | 2024-09-13
46726 | 740-D3-VU111-116-LC008-80-0 | 1 | true | 13.4 | 740-D3-VU111-116-LC008-80-0 | LV1-105638.VU111 | 388 | 3.May.2024 |  | MC1 | LVL 6 | W23 | TR008 | 2024-03-18 | 2024-03-26 | 2024-03-26 |  | 2024-04-17 | 2024-04-27 | Büro | 2024-04-29 |  | 2024-04-27 | 2024-05-27 |  |  | 2024-06-07 | 901 | 150 |  | 2024-08-21 | 2024-07-24 | 149 | SEP | SEP | 2024-08-20 | 2024-09-09 | 2024-09-09 | 2024-09-09
46727 | 740-D3-VU111-127-LC008-20-0 | 1 | true | 2.71 | 740-D3-VU111-127-LC008-20-0 | LV1-105638.VU111 | 388 | 3.May.2024 |  | MC1 | LVL 6 | W23 | TR008 | 2024-03-18 | 2024-03-26 | 2024-03-26 |  | 2024-04-25 | 2024-04-27 | Büro | 2024-04-29 |  | 2024-04-27 | 2024-05-29 |  |  | 2024-06-12 | 901 | 150 |  | 2024-08-21 | 2024-07-24 | 149 | SEP | SEP | 2024-08-20 | 2024-09-13 | 2024-09-13 | 2024-09-13
46728 | 740-D3-VU111-128-LC008-50-0 | 1 | true | 11.82 | 740-D3-VU111-128-LC008-50-0 | LV1-105638.VU111 | 388 | 3.May.2024 |  | MC1 | LVL 6 | W23 | TR008 | 2024-03-18 | 2024-03-26 | 2024-03-26 |  | 2024-04-09 | 2024-04-18 | Büro | 2024-04-29 |  | 2024-04-18 | 2024-05-27 |  | 2024-06-10 | 2024-07-03 | 901 | 150 |  | 2024-08-21 | 2024-07-24 | 149 | SEP | SEP | 2024-08-20 | 2024-09-09 | 2024-09-09 | 2024-09-09
46729 | 740-D3-VU111-135-LC008-20-0 | 1 | true | 2.39 | 740-D3-VU111-135-LC008-20-0 | LV1-105638.VU111 | 388 | 3.May.2024 |  | MC1 | LVL 6 | W23 | TR008 | 2024-03-18 | 2024-03-26 | 2024-03-26 |  | 2024-04-25 | 2024-04-29 | Büro | 2024-04-29 |  | 2024-04-29 | 2024-05-29 |  |  | 2024-07-03 | 901 | 150 |  | 2024-08-21 | 2024-07-24 | 149 | SEP | SEP | 2024-08-20 | 2024-09-09 | 2024-09-09 | 2024-09-09
46730 | 740-D3-VU111-136-LC008-20-0 | 1 | true | 3.13 | 740-D3-VU111-136-LC008-20-0 | LV1-105638.VU111 | 388 | 3.May.2024 |  | MC1 | LVL 6 | W23 | TR008 | 2024-03-18 | 2024-03-26 | 2024-03-26 |  | 2024-04-10 | 2024-04-18 | Büro | 2024-04-29 |  | 2024-04-18 | 2024-05-29 |  |  | 2024-06-12 | 901 | 150 |  | 2024-08-21 | 2024-07-22 | 149 | SEP | SEP | 2024-08-20 | 2024-09-09 | 2024-09-09 | 2024-09-09
46731 | 740-D3-VU111-137-LC008-20-0 | 1 | false | 4.6 | 740-D3-VU111-137-LC008-20-0 | LV1-105638.VU111 | 388 | 3.May.2024 |  | MC1 | LVL 6 | W23 | TR008 | 2024-03-19 | 2024-03-27 | 2024-03-27 |  |  |  | ZRO Prefab | [7 empty] | 901 | 150 |  |  |  | 149 | SEP | SEP
47229 | 740-D3-VU111-137-LC008-20-0 | 2 | true | 4.6 | 740-D3-VU111-137-LC008-20-0 | LV1-105638.VU111 | 388 | 3.May.2024 |  | MC1 | LVL 6 | W23 | TR011 | 2024-03-24 | 2024-04-04 | 2024-04-07 |  | 2024-04-09 | 2024-04-18 | Büro | 2024-04-29 |  | 2024-04-23 | 2024-05-29 |  |  | 2024-06-11 | 901 | 150 |  | 2024-08-21 | 2024-07-24 | 149 | SEP | SEP | 2024-08-20 | 2024-09-09 | 2024-09-09 | 2024-09-09
46732 | 740-D3-VU111-138-LC008-20-0 | 1 | true | 2.54 | 740-D3-VU111-138-LC008-20-0 | LV1-105638.VU111 | 388 | 3.May.2024 |  | MC1 | LVL 6 | W23 | TR008 | 2024-03-18 | 2024-03-26 | 2024-03-26 |  | 2024-04-10 | 2024-04-18 | Büro | 2024-04-29 |  | 2024-04-18 | 2024-05-29 |  |  | 2024-06-12 | 901 | 150 |  | 2024-08-21 | 2024-07-22 | 149 | SEP | SEP | 2024-08-20 | 2024-09-09 | 2024-09-09 | 2024-09-09
46733 | 740-D3-VU163-103-LC008-65-0 | 1 | true | 5.13 | 740-D3-VU163-103-LC008-65-0 | LV1-105638.VU111 | 388 | 3.May.2024 |  | MC1 | LVL 6 | W23 | TR008 | 2024-03-18 | 2024-03-26 | 2024-03-26 |  | 2024-04-09 | 2024-04-10 | ZRO Prefab | 2024-04-29 |  | 2024-04-17 | 2024-07-18 |  |  | 2024-07-26 | 901 | 150 |  | 2024-07-26 | 2024-08-22 | 149 | SEP | SEP | 2024-10-01 | 2024-10-14 | 2024-10-14 | 2024-10-14
46735 | 740-MKWH-R-VP010-104-LH001-25-0 | 1 | true | 16.2 | 740-MKWH-R-VP010-104-LH001-25-0 | LV1-105628.VP010 | 363 | 26.Apr.2024 |  | MC1 | LVL 6 | T60 | TR008 | 2024-03-18 | 2024-03-26 | 2024-03-26 |  | 2024-06-04 | 2024-06-07 | Büro | 2024-06-14 |  | 2024-06-07 | 2024-07-03 |  |  | 2024-07-15 | 804 | 150 |  | 2024-08-28 | 2024-07-22 | 149 | SEP | SEP | 2024-11-08 | 2024-11-08 | 2024-11-08 | 2024-11-08
46736 | 740-MKWH-R-VU081-197-LH001-15-0 | 1 | false | 1.55 | 740-MKWH-R-VU081-197-LH001-15-0 | LV1-105628.VP010 | 363 | 17.May.2024 | true | MC1 | LVL 6 | T60 | TR008 | 2024-03-18 | 2024-03-26 | 2024-03-26 |  |  |  | ZRO Prefab | [7 empty] | 804 | 150 |  |  |  | 149 | SEP | SEP
49651 | 740-MKWH-R-VU081-197-LH001-15-0 | 2 | false | 1.55 | 740-MKWH-R-VU081-197-LH001-15-0 | LV1-105628.VP010 | 363 |  |  | MC1 | LVL 6 | T60 | TR014_1 | 2024-04-22 | 2024-04-29 | 2024-04-29 |  | 2024-06-25 | 2024-06-26 |  | 2024-07-12 |  | 2024-07-01 |  |  |  | 2024-11-15 | 804 | 150 |  |  |  | 149 | SEP | SEP
62774 | 740-MKWH-R-VU081-197-LH001-15-0 | 3 | true | 1.55 | 740-MKWH-R-VU081-197-LH001-15-0 | LV1-105628.VP010 | 363 |  |  | MC1 | LVL 6 | T60 | TR029_3 | 2024-08-07 | 2024-04-29 | 2024-04-29 |  | 2024-06-25 | 2024-06-26 |  | 2024-07-12 |  | 2024-07-01 |  |  |  | 2024-11-15 | 804 | 150 |  |  |  | 149 | SEP | SEP
46737 | 740-MKWH-R-VU211-205-LH130-32-0 | 1 | true | 8.08 | 740-MKWH-R-VU211-205-LH130-32-0 | LV1-105639.VU211 | 362 |  |  | MC1 | LVL 6 | T60 | TR008 | 2024-03-18 | 2024-03-26 | 2024-03-26 |  | 2024-06-04 | 2024-06-07 | Büro | 2024-06-14 |  | 2024-06-07 | 2024-07-02 |  |  | 2024-07-03 | 804 | 150 |  | 2024-08-20 | 2024-07-16 | 149 | SEP | SEP | 2024-07-23 | 2024-08-26 | 2024-08-26 | 2024-09-02 | 2024-10-07 | 2024-10-07
46738 | 740-MKWH-R-VU211-207-LH130-15-0 | 1 | true | 4.16 | 740-MKWH-R-VU211-207-LH130-15-0 | LV1-105639.VU211 | 362 |  |  | MC1 | LVL 6 | T60 | TR008 | 2024-03-18 | 2024-03-26 | 2024-03-26 |  | 2024-06-05 | 2024-06-07 | Büro | 2024-06-14 |  | 2024-06-07 | 2024-07-03 |  |  | 2024-07-08 | 804 | 150 |  | 2024-08-20 | 2024-07-16 | 149 | SEP | SEP | 2024-09-02 | 2024-09-02 | 2024-09-02 | 2024-09-02 | 2024-10-07 | 2024-10-07
46739 | 740-MKWH-S-VP010-101-LH001-25-0 | 1 | true | 17.09 | 740-MKWH-S-VP010-101-LH001-25-0 | LV1-105628.VP010 | 363 |  |  | MC1 | LVL 6 | T60 | TR008 | 2024-03-18 | 2024-03-26 | 2024-03-26 |  | 2024-06-04 | 2024-06-08 | Büro | 2024-06-14 |  | 2024-06-08 | 2024-07-03 |  |  | 2024-07-15 | 804 | 150 |  |  | 2024-07-23 | 149 | SEP | SEP | 2024-11-08 | 2024-11-08 | 2024-11-08 | 2024-11-08
46740 | 740-MKWH-S-VU081-198-LH001-15-0 | 1 | true | 0.33 | 740-MKWH-S-VU081-198-LH001-15-0 | LV0-105638.VU081 | 363 | 17.May.2024 |  | MC1 | LVL 6 | T60 | TR008 | 2024-03-18 | 2024-03-26 | 2024-03-26 |  | 2024-05-08 | 2024-05-13 | Büro | 2024-05-17 |  | 2024-05-13 |  |  |  | 2024-10-30 | 804 | 150 |  |  | 2024-10-31 | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
46741 | 740-MKWH-S-VU211-109-LH130-50-0 | 1 | true | 18.85 | 740-MKWH-S-VU211-109-LH130-50-0 | LV1-105638.VU211 | 362 |  |  | MC1 | LVL 6 | T60 | TR008 | 2024-03-18 | 2024-03-26 | 2024-03-26 |  | 2024-06-03 | 2024-06-07 | Büro | 2024-06-28 |  | 2024-06-14 | 2024-07-11 |  |  | 2024-07-15 | 804 | 150 |  | 2024-08-20 | 2024-07-16 | 149 | SEP | SEP | 2024-07-23 | 2024-08-26 | 2024-08-26 | 2024-09-16 | 2024-10-07 | 2024-10-07
46742 | 740-MKWH-S-VU211-202-LH130-32-0 | 1 | true | 8.07 | 740-MKWH-S-VU211-202-LH130-32-0 | LV1-105639.VU211 | 362 |  |  | MC1 | LVL 6 | T60 | TR008 | 2024-03-18 | 2024-03-26 | 2024-03-26 |  | 2024-06-04 | 2024-06-07 | Büro | 2024-06-14 |  | 2024-06-07 | 2024-07-02 |  |  | 2024-07-03 | 804 | 150 |  | 2024-08-20 | 2024-07-15 | 149 | SEP | SEP | 2024-07-23 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-10-07 | 2024-10-07
46743 | 740-MKWH-S-VU211-203-LH130-15-0 | 1 | true | 5.35 | 740-MKWH-S-VU211-203-LH130-15-0 | LV1-105639.VU211 | 362 |  |  | MC1 | LVL 6 | T60 | TR008 | 2024-03-18 | 2024-03-26 | 2024-03-26 |  | 2024-06-05 | 2024-06-07 | Büro | 2024-06-14 |  | 2024-06-07 | 2024-07-03 |  |  | 2024-07-08 | 804 | 150 |  | 2024-08-20 | 2024-07-15 | 149 | SEP | SEP | 2024-07-23 | 2024-09-02 | 2024-09-02 | 2024-09-02 | 2024-10-07 | 2024-10-07
46884 | 740-DMA-VU340-105-LH032-15-0 | 1 | false | 4.65 | 740-DMA-VU340-105-LH032-15-0 | LV1-105638.VU340 | 385 |  |  | MC1 | LVL 6 | N/A | TR009 | 2024-03-20 | 2024-03-23 | 2024-03-23 |  | 2024-06-04 | 2024-06-07 |  | 2024-06-14 |  | 2024-06-07 |  |  |  |  | 903 | 150 |  |  |  | 149 | SEP | SEP
62194 | 740-DMA-VU340-105-LH032-15-0 | 2 | true | 4.65 | 740-DMA-VU340-105-LH032-15-0 | LV1-105638.VU340 | 385 |  |  | MC1 | LVL 6 | N/A | TR029_1 | 2024-07-24 | 2024-03-23 | 2024-03-23 |  | 2024-06-04 | 2024-06-07 | Büro | 2024-06-14 |  | 2024-06-07 | 2024-08-28 |  |  | 2024-08-29 | 903 | 150 |  |  | 2024-09-09 | 149 | SEP | SEP
46885 | 740-DMA-VU340-106-LH032-15-0 | 1 | false | 5.22 | 740-DMA-VU340-106-LH032-15-0 | LV1-105638.VU340 | 385 |  |  | MC1 | LVL 6 | N/A | TR009 | 2024-03-21 | 2024-03-24 | 2024-03-24 | [11 empty] | 903 | 150 |  |  |  | 149 | SEP | SEP
47231 | 740-DMA-VU340-106-LH032-15-0 | 2 | false | 5.22 | 740-DMA-VU340-106-LH032-15-0 | LV1-105638.VU340 | 385 |  |  | MC1 | LVL 6 | N/A | TR011 | 2024-03-24 | 2024-04-04 | 2024-04-07 |  | 2024-05-31 | 2024-06-07 | Büro | 2024-06-14 |  | 2024-06-07 |  |  |  | 2024-09-03 | 903 | 150 |  |  |  | 149 | SEP | SEP
62195 | 740-DMA-VU340-106-LH032-15-0 | 3 | true | 5.22 | 740-DMA-VU340-106-LH032-15-0 | LV1-105638.VU340 | 385 |  |  | MC1 | LVL 6 | N/A | TR029_1 | 2024-07-24 | 2024-04-04 | 2024-04-07 |  | 2024-05-31 | 2024-06-07 | Büro | 2024-06-14 |  | 2024-06-07 | 2024-08-28 |  |  | 2024-09-03 | 903 | 150 |  |  | 2024-09-11 | 149 | SEP | SEP
46886 | 740-DMA-VU340-107-LH032-15-0 | 1 | false | 4.47 | 740-DMA-VU340-107-LH032-15-0 | LV1-105638.VU340 | 385 |  |  | MC1 | LVL 6 | N/A | TR009 | 2024-03-20 | 2024-03-23 | 2024-03-23 |  | 2024-06-04 | 2024-06-08 |  | 2024-06-14 |  | 2024-06-08 |  |  |  |  | 903 | 150 |  |  |  | 149 | SEP | SEP
62196 | 740-DMA-VU340-107-LH032-15-0 | 2 | true | 4.47 | 740-DMA-VU340-107-LH032-15-0 | LV1-105638.VU340 | 385 |  |  | MC1 | LVL 6 | N/A | TR029_1 | 2024-07-24 | 2024-03-23 | 2024-03-23 |  | 2024-06-04 | 2024-06-08 | Büro | 2024-06-14 |  | 2024-06-08 | 2024-08-28 |  |  | 2024-09-03 | 903 | 150 |  |  | 2024-09-11 | 149 | SEP | SEP
46887 | 740-DMA-VU340-110-LH032-25-0 | 1 | true | 57.31 | 740-DMA-VU340-110-LH032-25-0 | LV1-105638.VU340 | 385 |  |  | MC1 | LVL 6 | N/A | TR009 | 2024-03-20 | 2024-03-23 | 2024-03-23 |  | 2024-06-05 | 2024-06-07 |  | 2024-06-14 |  | 2024-06-07 | 2024-07-25 |  |  | 2024-07-31 | 903 | 150 |  | 2024-09-13 | 2024-08-22 | 149 | SEP | SEP
46888 | 740-LP-VS671-101-LH099-25-0 | 1 | true | 0.51 | 740-LP-VS671-101-LH099-25-0 | LV1-105638.VU001 | 386 | 22.Aug.2024 |  | MC1 | LVL 6 | N/A | TR009 | 2024-03-20 | 2024-03-23 | 2024-03-23 |  | 2024-06-11 | 2024-06-17 | Büro | 2024-06-28 |  | 2024-06-20 | 2024-08-20 |  |  | 2024-08-23 | 904 | 150 |  |  | 2024-09-09 | 149 | SEP | SEP
46889 | 740-LP-VS672-101-LH099-25-0 | 1 | true | 0.47 | 740-LP-VS672-101-LH099-25-0 | LV1-105638.VU001 | 386 | 22.Aug.2024 |  | MC1 | LVL 6 | N/A | TR009 | 2024-03-20 | 2024-03-23 | 2024-03-23 |  | 2024-06-11 |  | Büro | 2024-06-28 |  | 2024-06-19 | 2024-08-20 |  |  | 2024-08-22 | 904 | 150 |  |  | 2024-09-09 | 149 | SEP | SEP
46890 | 740-LP-VS673-101-LH099-25-0 | 1 | true | 0.47 | 740-LP-VS673-101-LH099-25-0 | LV1-105638.VU001 | 386 | 22.Aug.2024 |  | MC1 | LVL 6 | N/A | TR009 | 2024-03-20 | 2024-03-23 | 2024-03-23 |  | 2024-06-11 |  | Büro | 2024-06-28 |  | 2024-06-19 | 2024-08-20 |  |  | 2024-08-22 | 904 | 150 |  |  | 2024-09-09 | 149 | SEP | SEP
46891 | 740-LP-VU001-101-LH023-50-0 | 1 | true | 8.76 | 740-LP-VU001-101-LH023-50-0 | LV1-105638.VU001 | 368 | 6 |  | MC1 | LVL 6 | N/A | TR009 | 2024-03-20 | 2024-03-23 | 2024-03-23 |  | 2024-05-15 | 2024-05-21 | Büro | 2024-05-31 |  | 2024-05-23 | 2024-06-26 |  |  | 2024-09-05 | 904 | 150 |  |  | 2024-09-06 | 149 | SEP | SEP
46892 | 740-LP-VU001-102-LH023-50-0 | 1 | true | 0.26 | 740-LP-VU001-102-LH023-50-0 | LV1-105638.VU001 | 368 | 6 |  | MC1 | LVL 6 | N/A | TR009 | 2024-03-20 | 2024-03-23 | 2024-03-23 |  | 2024-05-13 | 2024-05-15 | Büro | 2024-05-17 |  | 2024-05-16 | 2024-06-26 |  |  | 2024-07-15 | 904 | 150 |  | 2024-09-20 | 2024-08-26 | 149 | SEP | SEP
46893 | 740-LP-VU001-103-LH099-25-0 | 1 | true | 0.15 | 740-LP-VU001-103-LH099-25-0 | LV1-105638.VU001 | 386 |  |  | MC1 | LVL 6 | N/A | TR009 | 2024-03-20 | 2024-03-23 | 2024-03-23 |  | 2024-06-05 | 2024-06-07 | Büro | 2024-06-14 |  | 2024-06-07 | 2024-06-26 |  |  | 2024-07-15 | 904 | 150 |  | 2024-09-20 | 2024-08-26 | 149 | SEP | SEP
46894 | 740-LP-VU001-104-LH099-15-0 | 1 | true | 0 | 740-LP-VU001-104-LH099-15-0 | LV1-105638.VU001 | 386 |  |  | MC1 | LVL 6 | N/A | TR009 | 2024-03-20 | 2024-03-23 | 2024-03-23 |  | 2024-06-12 | 2024-06-13 | Dawid Mierzwa | 2024-06-28 |  | 2024-06-17 |  |  |  | 2024-08-30 | 904 | 150 |  |  | 2024-09-02 | 149 | SEP | SEP
46895 | 740-LP-VU001-105-LH099-50-0 | 1 | true | 0.22 | 740-LP-VU001-105-LH099-50-0 | LV1-105638.VU001 | 386 | 6 |  | MC1 | LVL 6 | N/A | TR009 | 2024-03-20 | 2024-03-23 | 2024-03-23 |  | 2024-05-16 | 2024-05-17 | Büro | 2024-05-31 |  | 2024-05-18 | 2024-06-26 |  |  | 2024-07-15 | 904 | 150 |  |  | 2024-08-26 | 149 | SEP | SEP
46896 | 740-LP-VU001-106-LH099-25-0 | 1 | true | 0.15 | 740-LP-VU001-106-LH099-25-0 | LV1-105638.VU001 | 386 |  |  | MC1 | LVL 6 | N/A | TR009 | 2024-03-20 | 2024-03-23 | 2024-03-23 |  | 2024-06-05 | 2024-06-07 | Büro | 2024-06-14 |  | 2024-06-07 | 2024-06-26 |  |  | 2024-07-15 | 904 | 150 |  |  | 2024-08-26 | 149 | SEP | SEP
46897 | 740-LP-VU001-107-LH099-15-0 | 1 | true | 0 | 740-LP-VU001-107-LH099-15-0 | LV1-105638.VU001 | 386 |  |  | MC1 | LVL 6 | N/A | TR009 | 2024-03-20 | 2024-03-23 | 2024-03-23 |  | 2024-06-12 | 2024-06-13 | Dawid Mierzwa | 2024-06-28 |  | 2024-06-17 |  |  |  | 2024-08-30 | 904 | 150 |  |  | 2024-09-02 | 149 | SEP | SEP
46898 | 740-LP-VU001-108-LH099-50-0 | 1 | false | 19.51 | 740-LP-VU001-108-LH099-50-0 | LV1-105638.VU001 | 386 | 6 |  | MC1 | LVL 6 | N/A | TR009 | 2024-03-20 | 2024-03-23 | 2024-03-23 | [11 empty] | 904 | 150 |  |  |  | 149 | SEP | SEP
49504 | 740-LP-VU001-108-LH099-50-0 | 2 | true | 19.51 | 740-LP-VU001-108-LH099-50-0 | LV1-105638.VU001 | 386 | 6 |  | MC1 | LVL 6 | N/A | TR013_2 | 2024-04-21 | 2024-04-23 | 2024-04-23 |  | 2024-05-13 | 2024-05-15 | Büro | 2024-05-31 |  | 2024-05-17 | 2024-06-13 |  | 2024-06-20 | 2024-08-22 | 904 | 150 |  |  | 2024-08-26 | 149 | SEP | SEP
46899 | 740-LP-VU001-109-LH099-25-0 | 1 | false | 13.11 | 740-LP-VU001-109-LH099-25-0 | LV1-105638.VU001 | 386 |  |  | MC1 | LVL 6 | N/A | TR009 | 2024-03-21 | 2024-03-24 | 2024-03-24 | [11 empty] | 904 | 150 |  |  |  | 149 | SEP | SEP
47237 | 740-LP-VU001-109-LH099-25-0 | 2 | true | 13.11 | 740-LP-VU001-109-LH099-25-0 | LV1-105638.VU001 | 386 |  |  | MC1 | LVL 6 | N/A | TR011 | 2024-04-09 | 2024-04-04 | 2024-04-07 |  | 2024-05-31 | 2024-06-07 | Büro | 2024-06-14 |  | 2024-06-07 |  |  |  | 2024-08-21 | 904 | 150 |  |  | 2024-08-26 | 149 | SEP | SEP
46900 | 740-LP-VU001-110-LH099-25-0 | 1 | true | 3.12 | 740-LP-VU001-110-LH099-25-0 | LV1-105638.VU001 | 386 |  |  | MC1 | LVL 6 | N/A | TR009 | 2024-03-20 | 2024-03-23 | 2024-03-23 |  | 2024-06-05 | 2024-06-07 | Büro | 2024-06-14 |  | 2024-06-07 | 2024-08-20 |  |  | 2024-08-23 | 904 | 150 |  |  | 2024-08-26 | 149 | SEP | SEP
46901 | 740-LP-VU001-111-LH099-25-0 | 1 | false | 4.03 | 740-LP-VU001-111-LH099-25-0 | LV1-105638.VU001 | 386 |  |  | MC1 | LVL 6 | N/A | TR009 | 2024-03-21 | 2024-03-24 | 2024-03-24 | [11 empty] | 904 | 150 |  |  |  | 149 | SEP | SEP
47238 | 740-LP-VU001-111-LH099-25-0 | 2 | true | 4.03 | 740-LP-VU001-111-LH099-25-0 | LV1-105638.VU001 | 386 |  |  | MC1 | LVL 6 | N/A | TR011 | 2024-04-09 | 2024-04-04 | 2024-04-07 |  | 2024-05-31 | 2024-06-03 | Büro | 2024-06-14 |  | 2024-06-06 | 2024-08-20 |  |  | 2024-08-22 | 904 | 150 |  |  | 2024-08-26 | 149 | SEP | SEP
46902 | 740-LP-VU001-112-LH099-25-0 | 1 | true | 3.13 | 740-LP-VU001-112-LH099-25-0 | LV1-105638.VU001 | 386 |  |  | MC1 | LVL 6 | N/A | TR009 | 2024-03-20 | 2024-03-23 | 2024-03-23 |  | 2024-06-05 | 2024-06-07 | Büro | 2024-06-14 |  | 2024-06-07 | 2024-08-20 |  |  | 2024-08-22 | 904 | 150 |  |  | 2024-08-26 | 149 | SEP | SEP
46903 | 740-LP-VU001-113-LH099-50-0 | 1 | false | 51.14 | 740-LP-VU001-113-LH099-50-0 | LV1-105638.VU001 | 386 | 6 |  | MC1 | LVL 6 | N/A | TR009 | 2024-03-20 | 2024-03-23 | 2024-03-23 | [11 empty] | 904 | 150 |  |  |  | 149 | SEP | SEP
49505 | 740-LP-VU001-113-LH099-50-0 | 2 | true | 51.14 | 740-LP-VU001-113-LH099-50-0 | LV1-105638.VU001 | 386 | 6 |  | MC1 | LVL 6 | N/A | TR013_2 | 2024-04-21 | 2024-04-23 | 2024-04-23 |  | 2024-05-15 | 2024-05-21 | Büro | 2024-05-31 |  | 2024-05-23 | 2024-06-13 |  |  | 2024-06-20 | 904 | 150 |  |  | 2024-08-26 | 149 | SEP | SEP
46904 | 740-LP-VU001-114-LH099-25-0 | 1 | true | 6.91 | 740-LP-VU001-114-LH099-25-0 | LV1-105638.VU001 | 386 |  |  | MC1 | LVL 6 | N/A | TR009 | 2024-03-20 | 2024-03-23 | 2024-03-23 |  | 2024-06-05 | 2024-06-07 | Büro | 2024-06-14 |  | 2024-06-07 |  |  |  | 2024-08-21 | 904 | 150 |  |  | 2024-08-26 | 149 | SEP | SEP
46905 | 740-LP-VU001-115-LH099-25-0 | 1 | true | 12.92 | 740-LP-VU001-115-LH099-25-0 | LV1-105638.VU001 | 386 |  |  | MC1 | LVL 6 | N/A | TR009 | 2024-03-20 | 2024-03-23 | 2024-03-23 |  | 2024-06-05 | 2024-06-07 | Büro | 2024-06-14 |  | 2024-06-07 | 2024-08-23 |  |  | 2024-08-27 | 904 | 150 |  |  | 2024-08-28 | 149 | SEP | SEP
46906 | 740-LP-VU001-120-LH099-50-0 | 1 | true | 5.22 | 740-LP-VU001-120-LH099-50-0 | LV1-105638.VU001 | 386 | 6 |  | MC1 | LVL 6 | N/A | TR009 | 2024-03-20 | 2024-03-23 | 2024-03-23 |  | 2024-05-16 | 2024-05-16 | Büro | 2024-05-31 |  | 2024-05-17 | 2024-08-26 |  |  | 2024-08-29 | 904 | 150 |  |  | 2024-08-30 | 149 | SEP | SEP
46907 | 740-LP-VU001-124-LH099-20-0 | 1 | true | 3.72 | 740-LP-VU001-124-LH099-20-0 | LV1-105638.VU001 | 386 |  |  | MC1 | LVL 6 | N/A | TR009 | 2024-03-20 | 2024-03-23 | 2024-03-23 |  | 2024-06-04 | 2024-06-07 | Büro | 2024-06-14 |  | 2024-06-07 | 2024-08-26 |  |  | 2024-09-10 | 904 | 150 |  |  | 2024-09-11 | 149 | SEP | SEP
46908 | 740-LP-VU001-126-LH099-25-0 | 1 | true | 5.73 | 740-LP-VU001-126-LH099-25-0 | LV1-105638.VU001 | 386 |  |  | MC1 | LVL 6 | N/A | TR009 | 2024-03-20 | 2024-03-23 | 2024-03-23 |  | 2024-06-05 | 2024-06-07 | Büro | 2024-06-14 |  | 2024-06-07 |  |  |  | 2024-08-27 | 904 | 150 |  |  | 2024-08-28 | 149 | SEP | SEP
46909 | 740-N2-VU060-101-LH023-50-0 | 1 | true | 7.23 | 740-N2-VU060-101-LH023-50-0 | LV1-105638.VU060 | 368 | 6 |  | MC1 | LVL 6 | N/A | TR009 | 2024-03-20 | 2024-03-23 | 2024-03-23 |  | 2024-05-13 | 2024-05-16 | Büro | 2024-05-31 |  | 2024-05-18 | 2024-06-26 |  |  | 2024-09-05 | 905 | 150 |  |  | 2024-09-09 | 149 | SEP | SEP
46910 | 740-N2-VU060-102-LH023-15-0 | 1 | true | 0.1 | 740-N2-VU060-102-LH023-15-0 | LV1-105638.VU060 | 368 |  |  | MC1 | LVL 6 | N/A | TR009 | 2024-03-20 | 2024-03-23 | 2024-03-23 |  | 2024-05-17 | 2024-05-17 | Büro | 2024-05-31 |  | 2024-05-18 | 2024-06-26 |  |  | 2024-07-15 | 905 | 150 |  |  | 2024-08-27 | 149 | SEP | SEP
46911 | 740-N2-VU060-103-LH023-50-0 | 1 | true | 0.55 | 740-N2-VU060-103-LH023-50-0 | LV1-105638.VU060 | 368 | 6 |  | MC1 | LVL 6 | N/A | TR009 | 2024-03-20 | 2024-03-23 | 2024-03-23 |  | 2024-05-13 | 2024-05-14 | Büro | 2024-05-17 |  | 2024-05-16 | 2024-06-26 |  |  | 2024-07-15 | 905 | 150 |  |  | 2024-08-27 | 149 | SEP | SEP
46912 | 740-N2-VU060-104-LH099-15-0 | 1 | true | 0.15 | 740-N2-VU060-104-LH099-15-0 | LV1-105638.VU001 | 386 |  |  | MC1 | LVL 6 | N/A | TR009 | 2024-03-20 | 2024-03-23 | 2024-03-23 |  | 2024-06-05 | 2024-06-07 | Büro | 2024-06-14 |  | 2024-06-07 | 2024-06-26 |  |  | 2024-07-15 | 905 | 150 |  |  | 2024-08-27 | 149 | SEP | SEP
46913 | 740-N2-VU060-105-LH099-15-0 | 1 | true | 0 | 740-N2-VU060-105-LH099-15-0 | LV1-105638.VU060 | 386 |  |  | MC1 | LVL 6 | N/A | TR009 | 2024-03-20 | 2024-03-23 | 2024-03-23 |  | 2024-06-12 | 2024-06-13 | Büro | 2024-06-28 |  | 2024-06-17 |  |  |  | 2024-09-05 | 905 | 150 |  |  | 2024-09-09 | 149 | SEP | SEP
46914 | 740-N2-VU060-106-LH099-50-0 | 1 | true | 0.22 | 740-N2-VU060-106-LH099-50-0 | LV1-105638.VU060 | 386 | 6 |  | MC1 | LVL 6 | N/A | TR009 | 2024-03-20 | 2024-03-23 | 2024-03-23 |  | 2024-05-15 | 2024-05-21 | Büro | 2024-05-31 |  | 2024-05-23 | 2024-06-26 |  |  | 2024-07-15 | 905 | 150 |  |  | 2024-08-27 | 149 | SEP | SEP
46915 | 740-N2-VU060-107-LH099-15-0 | 1 | true | 0.15 | 740-N2-VU060-107-LH099-15-0 | LV1-105638.VU001 | 386 |  |  | MC1 | LVL 6 | N/A | TR009 | 2024-03-20 | 2024-03-23 | 2024-03-23 |  | 2024-06-05 | 2024-06-07 | Büro | 2024-06-14 |  | 2024-06-07 | 2024-06-26 |  |  | 2024-07-15 | 905 | 150 |  |  | 2024-08-27 | 149 | SEP | SEP
46916 | 740-N2-VU060-108-LH099-15-0 | 1 | true | 0 | 740-N2-VU060-108-LH099-15-0 | LV1-105638.VU060 | 386 |  |  | MC1 | LVL 6 | N/A | TR009 | 2024-03-20 | 2024-03-23 | 2024-03-23 |  | 2024-06-12 | 2024-06-13 | Büro | 2024-06-28 |  | 2024-06-17 |  |  |  | 2024-09-05 | 905 | 150 |  |  | 2024-09-09 | 149 | SEP | SEP
46917 | 740-N2-VU060-109-LH099-50-0 | 1 | true | 62.69 | 740-N2-VU060-109-LH099-50-0 | LV1-105638.VU060 | 386 | 6 |  | MC1 | LVL 6 | N/A | TR009 | 2024-03-20 | 2024-03-23 | 2024-03-23 |  | 2024-05-14 | 2024-05-15 | Büro | 2024-05-31 |  | 2024-05-20 | 2024-06-10 |  |  | 2024-06-14 | 905 | 150 |  |  | 2024-08-27 | 149 | SEP | SEP
46918 | 740-N2-VU060-110-LH099-25-0 | 1 | true | 4.53 | 740-N2-VU060-110-LH099-25-0 | LV1-105638.VU060 | 386 |  |  | MC1 | LVL 6 | N/A | TR009 | 2024-03-20 | 2024-03-23 | 2024-03-23 |  | 2024-06-05 | 2024-06-07 | Büro | 2024-06-14 |  | 2024-06-07 | 2024-09-02 |  |  | 2024-09-05 | 905 | 150 |  |  | 2024-09-09 | 149 | SEP | SEP
46919 | 740-N2-VU060-111-LH099-40-0 | 1 | true | 3.62 | 740-N2-VU060-111-LH099-40-0 | LV1-105638.VU060 | 386 |  |  | MC1 | LVL 6 | N/A | TR009 | 2024-03-20 | 2024-03-23 | 2024-03-23 |  | 2024-06-04 | 2024-06-07 | Büro | 2024-06-14 |  | 2024-06-07 | 2024-09-02 |  |  | 2024-09-26 | 905 | 150 |  |  | 2024-10-07 | 149 | SEP | SEP
46920 | 740-N2-VU060-116-LH099-50-0 | 1 | true | 5.34 | 740-N2-VU060-116-LH099-50-0 | LV1-105638.VU060 | 386 | 6 |  | MC1 | LVL 6 | N/A | TR009 | 2024-03-20 | 2024-03-23 | 2024-03-23 |  | 2024-05-16 | 2024-05-16 | Büro | 2024-05-31 |  | 2024-05-18 | 2024-09-03 |  |  | 2024-09-11 | 905 | 150 |  |  | 2024-09-12 | 149 | SEP | SEP
46921 | 740-N2-VU060-124-LH099-40-0 | 1 | true | 5.63 | 740-N2-VU060-124-LH099-40-0 | LV1-105638.VU060 | 386 |  |  | MC1 | LVL 6 | N/A | TR009 | 2024-03-20 | 2024-03-23 | 2024-03-23 |  | 2024-06-04 | 2024-06-07 | Büro | 2024-06-14 |  | 2024-06-07 | 2024-09-02 |  |  | 2024-09-05 | 905 | 150 |  |  | 2024-09-09 | 149 | SEP | SEP
46922 | 740-N2-VU060-146-LH099-25-0 | 1 | true | 1.49 | 740-N2-VU060-146-LH099-25-0 | LV1-105638.VU060 | 386 |  |  | MC1 | LVL 6 | N/A | TR009 | 2024-03-20 | 2024-03-23 | 2024-03-23 |  | 2024-05-31 | 2024-06-07 | Büro | 2024-06-14 |  | 2024-06-07 | 2024-09-02 |  |  | 2024-09-05 | 905 | 150 |  |  | 2024-09-09 | 149 | SEP | SEP
46923 | 740-SP-VU331-105-LH032-15-0 | 1 | false | 4.11 | 740-SP-VU331-105-LH032-15-0 | LV1-105638.VU331 | 385 |  |  | MC1 | LVL 6 | N/A | TR009 | 2024-03-20 | 2024-03-23 | 2024-03-23 |  | 2024-05-31 | 2024-06-07 |  | 2024-06-14 |  | 2024-06-07 |  |  |  |  | 906 | 150 |  |  |  | 149 | SEP | SEP
62203 | 740-SP-VU331-105-LH032-15-0 | 2 | true | 4.11 | 740-SP-VU331-105-LH032-15-0 | LV1-105638.VU331 | 385 |  |  | MC1 | LVL 6 | N/A | TR029_1 | 2024-07-24 | 2024-03-23 | 2024-03-23 |  | 2024-05-31 | 2024-06-07 | Büro | 2024-06-14 |  | 2024-06-07 | 2024-08-07 |  |  | 2024-09-10 | 906 | 150 |  | 2024-09-24 | 2024-09-11 | 149 | SEP | SEP
46924 | 740-SP-VU331-106-LH032-15-0 | 1 | false | 5.55 | 740-SP-VU331-106-LH032-15-0 | LV1-105638.VU331 | 385 |  |  | MC1 | LVL 6 | N/A | TR009 | 2024-03-20 | 2024-03-23 | 2024-03-23 |  | 2024-05-31 | 2024-06-07 |  | 2024-06-14 |  | 2024-06-07 |  |  |  |  | 906 | 150 |  |  |  | 149 | SEP | SEP
62204 | 740-SP-VU331-106-LH032-15-0 | 2 | true | 5.55 | 740-SP-VU331-106-LH032-15-0 | LV1-105638.VU331 | 385 |  |  | MC1 | LVL 6 | N/A | TR029_1 | 2024-07-24 | 2024-03-23 | 2024-03-23 |  | 2024-05-31 | 2024-06-07 | Büro | 2024-06-14 |  | 2024-06-07 | 2024-08-07 |  |  | 2024-08-12 | 906 | 150 |  | 2024-09-24 | 2024-09-11 | 149 | SEP | SEP
46925 | 740-SP-VU331-107-LH032-15-0 | 1 | false | 4.37 | 740-SP-VU331-107-LH032-15-0 | LV1-105638.VU331 | 385 |  |  | MC1 | LVL 6 | N/A | TR009 | 2024-03-20 | 2024-03-23 | 2024-03-23 |  | 2024-05-31 | 2024-06-07 |  | 2024-06-14 |  | 2024-06-07 |  |  |  |  | 906 | 150 |  |  |  | 149 | SEP | SEP
62205 | 740-SP-VU331-107-LH032-15-0 | 2 | true | 4.37 | 740-SP-VU331-107-LH032-15-0 | LV1-105638.VU331 | 385 |  |  | MC1 | LVL 6 | N/A | TR029_1 | 2024-07-24 | 2024-03-23 | 2024-03-23 |  | 2024-05-31 | 2024-06-07 | Büro | 2024-06-14 |  | 2024-06-07 | 2024-08-07 |  |  | 2024-09-05 | 906 | 150 |  | 2024-09-24 | 2024-09-11 | 149 | SEP | SEP
46926 | 740-SP-VU331-108-LH032-15-0 | 1 | true | 11.27 | 740-SP-VU331-108-LH032-15-0 | LV1-105638.VU331 | 385 |  |  | MC1 | LVL 6 | N/A | TR009 | 2024-03-20 | 2024-03-23 | 2024-03-23 |  | 2024-06-03 | 2024-06-08 | Büro | 2024-06-14 |  | 2024-06-08 | 2024-08-07 |  |  | 2024-08-14 | 906 | 150 |  | 2024-09-24 | 2024-08-22 | 149 | SEP | SEP
46927 | 740-SP-VU331-110-LH032-25-0 | 1 | true | 48.4 | 740-SP-VU331-110-LH032-25-0 | LV1-105638.VU331 | 385 |  |  | MC1 | LVL 6 | N/A | TR009 | 2024-03-20 | 2024-03-23 | 2024-03-23 |  | 2024-05-31 | 2024-06-08 | Büro | 2024-06-14 |  | 2024-06-08 | 2024-07-31 |  |  | 2024-08-08 | 906 | 150 |  | 2024-09-24 | 2024-08-22 | 149 | SEP | SEP
47018 | 740-DR2-VS671-101-LH088-25-0 | 1 | false | 1.52 | 740-DR2-VS671-101-LH088-25-0 | LV0-105633.VS671 | 391 | 22.Aug.2024 |  | MC1 | LVL 6 | W23 | TR010 | 2024-03-21 | 2024-03-26 | 2024-03-26 | HOLD_SISTO fehlt | 2024-05-25 | 2024-05-27 | ZRO Prefab | 2024-06-14 |  | 2024-06-03 | 2024-07-26 |  |  |  | 907 | 150 |  |  |  | 149 | SEP | SEP
62197 | 740-DR2-VS671-101-LH088-25-0 | 2 | true | 1.52 | 740-DR2-VS671-101-LH088-25-0 | LV0-105633.VS671 | 391 |  |  | MC1 | LVL 6 | W23 | TR029_1 | 2024-07-24 | 2024-03-26 | 2024-03-26 | HOLD_SISTO fehlt | 2024-05-25 | 2024-05-27 | Büro | 2024-06-14 |  | 2024-06-03 |  |  |  | 2024-10-24 | 907 | 150 |  |  |  | 149 | SEP | SEP | 2024-09-25 |  | 2024-11-01 | 2024-11-01
47019 | 740-DR2-VS671-102-LH088-15-0 | 1 | true | 0.23 | 740-DR2-VS671-102-LH088-15-0 | LV0-105633.VS671 | 391 | 22.Aug.2024 |  | MC1 | LVL 6 | W23 | TR010 | 2024-03-21 | 2024-03-26 | 2024-03-26 |  | 2024-05-21 | 2024-05-23 | Dawid Mierzwa | 2024-05-31 |  | 2024-05-23 | 2024-07-26 | 2024-08-30 | 2024-08-30 | 2024-08-30 | 907 | 150 |  | 2024-10-03 | 2024-09-09 | 149 | SEP | SEP | 2024-09-25 |  | 2024-11-01 | 2024-11-01
47020 | 740-DR2-VS671-103-LH088-15-0 | 1 | true | 0.11 | 740-DR2-VS671-103-LH088-15-0 | LV0-105633.VS671 | 391 | 22.Aug.2024 |  | MC1 | LVL 6 | W23 | TR010 | 2024-03-21 | 2024-03-26 | 2024-03-26 |  | 2024-05-23 | 2024-05-23 | Dawid Mierzwa | 2024-05-31 |  | 2024-05-27 | 2024-07-26 | 2024-08-30 | 2024-08-30 | 2024-08-30 | 907 | 150 |  | 2024-10-03 | 2024-09-09 | 149 | SEP | SEP | 2024-09-25 |  | 2024-11-01 | 2024-11-01
47021 | 740-DR2-VS671-104-LH088-15-0 | 1 | true | 1.25 | 740-DR2-VS671-104-LH088-15-0 | LV0-105633.VS671 | 391 | 22.Aug.2024 |  | MC1 | LVL 6 | W23 | TR010 | 2024-03-21 | 2024-03-26 | 2024-03-26 |  | 2024-05-20 | 2024-05-21 | Dawid Mierzwa | 2024-05-31 |  | 2024-05-21 | 2024-07-26 | 2024-08-30 | 2024-08-30 | 2024-08-30 | 907 | 150 |  | 2024-10-03 | 2024-09-09 | 149 | SEP | SEP | 2024-09-25 |  | 2024-11-01 | 2024-11-01
47022 | 740-DR2-VS672-101-LH088-25-0 | 1 | false | 1.52 | 740-DR2-VS672-101-LH088-25-0 | LV0-105633.VS672 | 391 | 22.Aug.2024 |  | MC1 | LVL 6 | W23 | TR010 | 2024-03-21 | 2024-03-26 | 2024-03-26 | HOLD_SISTO fehlt | 2024-05-23 | 2024-05-24 | Büro | 2024-05-31 |  | 2024-05-27 | 2024-07-26 |  |  | 2024-10-24 | 907 | 150 |  |  |  | 149 | SEP | SEP
62198 | 740-DR2-VS672-101-LH088-25-0 | 2 | true | 1.52 | 740-DR2-VS672-101-LH088-25-0 | LV0-105633.VS672 | 391 |  |  | MC1 | LVL 6 | W23 | TR029_1 | 2024-07-24 | 2024-03-26 | 2024-03-26 | HOLD_SISTO fehlt | 2024-05-23 | 2024-05-24 | Büro | 2024-05-31 |  | 2024-05-27 |  |  |  | 2024-10-24 | 907 | 150 |  |  |  | 149 | SEP | SEP | 2024-09-25 |  | 2024-11-01 | 2024-11-01
47023 | 740-DR2-VS672-102-LH088-15-0 | 1 | true | 0.23 | 740-DR2-VS672-102-LH088-15-0 | LV0-105633.VS672 | 391 | 22.Aug.2024 |  | MC1 | LVL 6 | W23 | TR010 | 2024-03-21 | 2024-03-26 | 2024-03-26 |  | 2024-05-23 | 2024-05-24 | Büro | 2024-05-31 |  | 2024-05-27 | 2024-07-26 |  |  | 2024-08-23 | 907 | 150 |  |  | 2024-09-03 | 149 | SEP | SEP | 2024-09-25 |  | 2024-11-01 | 2024-11-01
47024 | 740-DR2-VS672-103-LH088-15-0 | 1 | true | 0.11 | 740-DR2-VS672-103-LH088-15-0 | LV0-105633.VS672 | 391 | 22.Aug.2024 |  | MC1 | LVL 6 | W23 | TR010 | 2024-03-21 | 2024-03-26 | 2024-03-26 |  | 2024-05-23 | 2024-05-23 | Büro | 2024-05-31 |  | 2024-05-27 |  |  |  | 2024-08-23 | 907 | 150 |  |  | 2024-09-03 | 149 | SEP | SEP | 2024-09-25 |  | 2024-11-01 | 2024-11-01
47025 | 740-DR2-VS672-104-LH088-15-0 | 1 | true | 1.26 | 740-DR2-VS672-104-LH088-15-0 | LV0-105633.VS672 | 391 | 22.Aug.2024 |  | MC1 | LVL 6 | W23 | TR010 | 2024-03-21 | 2024-03-26 | 2024-03-26 |  | 2024-05-20 | 2024-05-21 | Büro | 2024-05-31 |  | 2024-05-21 | 2024-07-26 |  |  | 2024-08-23 | 907 | 150 |  |  | 2024-09-03 | 149 | SEP | SEP | 2024-09-25 |  | 2024-11-01 | 2024-11-01
47026 | 740-DR2-VS673-101-LH088-25-0 | 1 | false | 1.52 | 740-DR2-VS673-101-LH088-25-0 | LV0-105633.VS673 | 391 | 22.Aug.2024 |  | MC1 | LVL 6 | W23 | TR010 | 2024-03-21 | 2024-03-26 | 2024-03-26 | HOLD_SISTO fehlt | 2024-05-24 | 2024-05-27 | Büro | 2024-06-14 |  | 2024-06-03 | 2024-07-26 |  |  | 2024-10-24 | 907 | 150 |  |  |  | 149 | SEP | SEP
62199 | 740-DR2-VS673-101-LH088-25-0 | 2 | true | 1.52 | 740-DR2-VS673-101-LH088-25-0 | LV0-105633.VS673 | 391 |  |  | MC1 | LVL 6 | W23 | TR029_1 | 2024-07-24 | 2024-03-26 | 2024-03-26 | HOLD_SISTO fehlt | 2024-05-24 | 2024-05-27 | Büro | 2024-06-14 |  | 2024-06-03 | 2024-08-26 | 2024-08-30 |  | 2024-10-24 | 907 | 150 |  |  |  | 149 | SEP | SEP | 2024-09-25 |  | 2024-11-01 | 2024-11-01
47027 | 740-DR2-VS673-102-LH088-15-0 | 1 | true | 0.3 | 740-DR2-VS673-102-LH088-15-0 | LV0-105633.VS673 | 391 | 22.Aug.2024 |  | MC1 | LVL 6 | W23 | TR010 | 2024-03-21 | 2024-03-26 | 2024-03-26 |  | 2024-05-22 | 2024-05-23 | Dawid Mierzwa | 2024-05-31 |  | 2024-05-23 | 2024-07-26 | 2024-08-30 | 2024-08-30 | 2024-08-30 | 907 | 150 |  |  | 2024-09-09 | 149 | SEP | SEP | 2024-09-25 |  | 2024-11-01 | 2024-11-01
47028 | 740-DR2-VS673-103-LH088-15-0 | 1 | true | 2.47 | 740-DR2-VS673-103-LH088-15-0 | LV0-105633.VS673 | 391 | 22.Aug.2024 |  | MC1 | LVL 6 | W23 | TR010 | 2024-03-21 | 2024-03-26 | 2024-03-26 |  | 2024-05-20 | 2024-05-21 | Dawid Mierzwa | 2024-05-31 |  | 2024-05-21 | 2024-07-26 | 2024-08-30 | 2024-08-30 | 2024-08-30 | 907 | 150 |  |  | 2024-09-09 | 149 | SEP | SEP | 2024-09-25 |  | 2024-11-01 | 2024-11-01
47029 | 740-DR2-VS673-104-LH088-15-0 | 1 | true | 0.1 | 740-DR2-VS673-104-LH088-15-0 | LV0-105633.VS673 | 391 | 22.Aug.2024 |  | MC1 | LVL 6 | W23 | TR010 | 2024-03-21 | 2024-03-26 | 2024-03-26 |  | 2024-05-23 | 2024-05-23 | Dawid Mierzwa | 2024-05-31 |  | 2024-05-23 | 2024-07-26 | 2024-08-30 | 2024-08-30 | 2024-08-30 | 907 | 150 |  |  | 2024-09-09 | 149 | SEP | SEP | 2024-09-25 |  | 2024-11-01 | 2024-11-01
47030 | 740-DR2-VU081-101-LH088-80-0 | 1 | false | 30.98 | 740-DR2-VU081-101-LH088-80-0 | LV0-105638.VU081 | 391 | 17.May.2024 |  | MC1 | LVL 6 | W23 | TR010 | 2024-03-21 | 2024-03-26 | 2024-03-26 |  |  |  | ZRO Prefab | [7 empty] | 907 | 150 |  |  |  | 149 | SEP | SEP
52569 | 740-DR2-VU081-101-LH088-80-0 | 2 | true | 30.98 | 740-DR2-VU081-101-LH088-80-0 | LV0-105638.VU081 | 391 |  |  | MC1 | LVL 6 | W23 | TR024_1 | 2024-06-10 | 2024-03-26 | 2024-03-26 |  | 2024-06-18 | 2024-06-21 |  | 2024-06-28 |  | 2024-06-26 | 2024-07-03 |  |  | 2024-07-19 | 907 | 150 |  |  | 2024-08-20 | 149 | SEP | SEP | 2024-09-26 | 2024-11-22 | 2024-11-22 | 2024-11-22
47031 | 740-DR2-VU081-102-LH088-25-0 | 1 | true | 5.92 | 740-DR2-VU081-102-LH088-25-0 | LV0-105638.VU081 | 391 | 17.May.2024 |  | MC1 | LVL 6 | W23 | TR010 | 2024-03-21 | 2024-03-26 | 2024-03-26 |  | 2024-05-13 | 2024-05-15 |  | 2024-05-17 |  | 2024-05-15 | 2024-07-04 |  |  | 2024-07-31 | 907 | 150 |  |  | 2024-08-19 | 149 | SEP | SEP | 2024-09-26 | 2024-11-22 | 2024-11-22 | 2024-11-22
47032 | 740-DR2-VU081-103-LH088-15-0 | 1 | true | 6.3 | 740-DR2-VU081-103-LH088-15-0 | LV0-105638.VU081 | 391 | 17.May.2024 |  | MC1 | LVL 6 | W23 | TR010 | 2024-03-21 | 2024-03-26 | 2024-03-26 |  | 2024-05-21 | 2024-05-22 |  | 2024-05-31 |  | 2024-05-23 | 2024-07-04 |  |  | 2024-07-31 | 907 | 150 |  |  | 2024-08-19 | 149 | SEP | SEP | 2024-09-26 | 2024-11-22 | 2024-11-22 | 2024-11-22
47033 | 740-DR2-VU081-104-LH088-25-0 | 1 | true | 3.02 | 740-DR2-VU081-104-LH088-25-0 | LV0-105638.VU081 | 391 | 17.May.2024 |  | MC1 | LVL 6 | W23 | TR010 | 2024-03-21 | 2024-03-26 | 2024-03-26 |  | 2024-05-13 | 2024-05-15 |  | 2024-05-17 |  | 2024-05-15 | 2024-07-04 |  |  | 2024-07-31 | 907 | 150 |  |  | 2024-08-19 | 149 | SEP | SEP | 2024-09-26 | 2024-11-22 | 2024-11-22 | 2024-11-22
47034 | 740-DR2-VU081-105-LH088-15-0 | 1 | true | 6.48 | 740-DR2-VU081-105-LH088-15-0 | LV0-105638.VU081 | 391 | 17.May.2024 |  | MC1 | LVL 6 | W23 | TR010 | 2024-03-21 | 2024-03-26 | 2024-03-26 |  | 2024-05-20 | 2024-05-22 |  | 2024-05-31 |  | 2024-05-23 | 2024-07-04 |  |  | 2024-07-31 | 907 | 150 |  |  | 2024-08-19 | 149 | SEP | SEP | 2024-09-26 | 2024-11-22 | 2024-11-22 | 2024-11-22
47035 | 740-DR2-VU081-106-LH088-25-0 | 1 | true | 2.97 | 740-DR2-VU081-106-LH088-25-0 | LV0-105638.VU081 | 391 | 17.May.2024 |  | MC1 | LVL 6 | W23 | TR010 | 2024-03-21 | 2024-03-26 | 2024-03-26 |  | 2024-05-20 | 2024-05-21 |  | 2024-05-31 |  | 2024-05-22 | 2024-07-04 |  |  | 2024-07-31 | 907 | 150 |  |  | 2024-08-19 | 149 | SEP | SEP | 2024-09-26 | 2024-11-22 | 2024-11-22 | 2024-11-22
47036 | 740-DR2-VU081-107-LH088-15-0 | 1 | true | 8.91 | 740-DR2-VU081-107-LH088-15-0 | LV0-105638.VU081 | 391 | 17.May.2024 |  | MC1 | LVL 6 | W23 | TR010 | 2024-03-21 | 2024-03-26 | 2024-03-26 |  | 2024-05-20 | 2024-05-23 |  | 2024-05-31 |  | 2024-05-23 | 2024-07-04 |  |  | 2024-07-26 | 907 | 150 |  |  | 2024-08-19 | 149 | SEP | SEP | 2024-09-26 | 2024-11-22 | 2024-11-22 | 2024-11-22
47037 | 740-DR2-VU081-108-LH088-15-0 | 1 | true | 6.58 | 740-DR2-VU081-108-LH088-15-0 | LV0-105638.VU081 | 391 | 17.May.2024 |  | MC1 | LVL 6 | W23 | TR010 | 2024-03-21 | 2024-03-26 | 2024-03-26 |  | 2024-05-22 | 2024-05-22 |  | 2024-05-31 |  | 2024-05-23 | 2024-07-04 |  |  | 2024-07-26 | 907 | 150 |  |  | 2024-08-14 | 149 | SEP | SEP | 2024-09-26 | 2024-11-22 | 2024-11-22 | 2024-11-22
47038 | 740-DR2-VU081-109-LH088-15-0 | 1 | true | 8.88 | 740-DR2-VU081-109-LH088-15-0 | LV0-105638.VU081 | 391 | 17.May.2024 |  | MC1 | LVL 6 | W23 | TR010 | 2024-03-21 | 2024-03-26 | 2024-03-26 |  | 2024-05-20 | 2024-05-21 |  | 2024-05-31 |  | 2024-05-22 | 2024-07-04 |  |  | 2024-07-26 | 907 | 150 |  |  | 2024-08-19 | 149 | SEP | SEP | 2024-09-26 | 2024-11-22 | 2024-11-22 | 2024-11-22
47039 | 740-DR2-VU081-110-LH088-50-0 | 1 | true | 9.05 | 740-DR2-VU081-110-LH088-50-0 | LV0-105638.VU081 | 391 | 17.May.2024 |  | MC1 | LVL 6 | W23 | TR010 | 2024-03-21 | 2024-03-26 | 2024-03-26 |  | 2024-05-20 | 2024-05-17 | Büro | 2024-05-31 |  | 2024-05-22 | 2024-06-14 |  |  | 2024-06-21 | 907 | 150 |  |  | 2024-08-14 | 149 | SEP | SEP | 2024-09-26 | 2024-11-22 | 2024-11-22 | 2024-11-22
47040 | 740-DR2-VU081-111-LH088-80-0 | 1 | false | 9.9 | 740-DR2-VU081-111-LH088-80-0 | LV0-105638.VU081 | 391 | 17.May.2024 |  | MC1 | LVL 6 | W23 | TR010 | 2024-03-21 | 2024-03-26 | 2024-03-26 |  | 2024-05-20 | 2024-05-20 | Büro | 2024-05-31 |  | 2024-05-22 |  |  |  | 2024-06-21 | 907 | 150 |  |  |  | 149 | SEP | SEP
52570 | 740-DR2-VU081-111-LH088-80-0 | 2 | true | 9.9 | 740-DR2-VU081-111-LH088-80-0 | LV0-105638.VU081 | 391 |  |  | MC1 | LVL 6 | W23 | TR024_1 | 2024-06-10 | 2024-03-26 | 2024-03-26 |  | 2024-05-20 | 2024-05-20 |  | 2024-05-31 |  | 2024-05-22 | 2024-06-10 | 2024-06-12 |  | 2024-06-21 | 907 | 150 |  |  | 2024-08-20 | 149 | SEP | SEP | 2024-09-26 | 2024-10-04 | 2024-10-04 | 2024-10-04
47041 | 740-DR2-VU081-114-LH088-15-0 | 1 | true | 7.03 | 740-DR2-VU081-114-LH088-15-0 | LV0-105638.VU081 | 391 | 17.May.2024 |  | MC1 | LVL 6 | W23 | TR010 | 2024-03-21 | 2024-03-26 | 2024-03-26 |  | 2024-05-22 | 2024-05-22 |  | 2024-05-31 |  | 2024-05-23 | 2024-07-04 |  |  | 2024-07-26 | 907 | 150 |  |  | 2024-08-14 | 149 | SEP | SEP | 2024-09-26 | 2024-11-22 | 2024-11-22 | 2024-11-22
47042 | 740-DR2-VU081-146-LH088-15-0 | 1 | true | 4.67 | 740-DR2-VU081-146-LH088-15-0 | LV0-105638.VU081 | 391 | 17.May.2024 |  | MC1 | LVL 6 | W23 | TR010 | 2024-03-21 | 2024-03-26 | 2024-03-26 |  | 2024-05-20 | 2024-05-23 |  | 2024-05-31 |  | 2024-05-23 | 2024-07-04 |  |  | 2024-07-26 | 907 | 150 |  |  | 2024-08-14 | 149 | SEP | SEP | 2024-09-26 | 2024-11-22 | 2024-11-22 | 2024-11-22
47043 | 740-DR2-VU081-147-LH088-80-0 | 1 | false | 47.75 | 740-DR2-VU081-147-LH088-80-0 | LV0-105638.VU081 | 391 | 17.May.2024 |  | MC1 | LVL 6 | W23 | TR010 | 2024-03-21 | 2024-03-26 | 2024-03-26 |  | 2024-05-23 | 2024-05-24 | ZRO Prefab | 2024-05-31 |  | 2024-05-27 |  | 2024-06-07 |  |  | 907 | 150 |  |  |  | 149 | SEP | SEP
52572 | 740-DR2-VU081-147-LH088-80-0 | 2 | true | 47.75 | 740-DR2-VU081-147-LH088-80-0 | LV0-105638.VU081 | 391 |  |  | MC1 | LVL 6 | W23 | TR024_1 | 2024-06-10 | 2024-03-26 | 2024-03-26 |  | 2024-05-23 | 2024-05-24 |  | 2024-05-31 |  | 2024-05-27 |  | 2024-06-07 | 2024-06-12 | 2024-09-05 | 907 | 150 |  |  | 2024-08-20 | 149 | SEP | SEP | 2024-09-30 | 2024-09-30 | 2024-09-30 | 2024-09-30
47044 | 740-DR2-VU081-148-LH088-15-0 | 1 | true | 2.56 | 740-DR2-VU081-148-LH088-15-0 | LV0-105638.VU081 | 391 | 17.May.2024 |  | MC1 | LVL 6 | W23 | TR010 | 2024-03-21 | 2024-03-26 | 2024-03-26 |  | 2024-05-21 | 2024-05-22 |  | 2024-05-31 |  | 2024-05-23 | 2024-07-04 |  |  | 2024-07-19 | 907 | 150 |  |  | 2024-08-14 | 149 | SEP | SEP | 2024-09-26 | 2024-11-22 | 2024-11-22 | 2024-11-22
47045 | 740-UN-VU330-105-LH032-15-0 | 1 | false | 4.4 | 740-UN-VU330-105-LH032-15-0 | LV1-105638.VU330 | 385 |  |  | MC1 | LVL 6 | N/A | TR010 | 2024-03-21 | 2024-03-26 | 2024-03-26 |  | 2024-06-03 | 2024-06-07 | ZRO Prefab | 2024-06-14 |  | 2024-06-07 |  |  |  |  | 908 | 150 |  |  |  | 149 | SEP | SEP
62209 | 740-UN-VU330-105-LH032-15-0 | 2 | true | 4.4 | 740-UN-VU330-105-LH032-15-0 | LV1-105638.VU330 | 385 |  |  | MC1 | LVL 6 | N/A | TR029_1 | 2024-07-24 | 2024-03-26 | 2024-03-26 |  | 2024-06-03 | 2024-06-07 | Büro | 2024-06-14 |  | 2024-06-07 | 2024-09-02 |  |  | 2024-09-03 | 908 | 150 |  | 2024-09-24 | 2024-09-11 | 149 | SEP | SEP
47046 | 740-UN-VU330-106-LH032-15-0 | 1 | false | 5.58 | 740-UN-VU330-106-LH032-15-0 | LV1-105638.VU330 | 385 |  |  | MC1 | LVL 6 | N/A | TR010 | 2024-03-21 | 2024-03-26 | 2024-03-26 |  | 2024-06-03 | 2024-06-07 | ZRO Prefab | 2024-06-14 |  | 2024-06-07 |  |  |  |  | 908 | 150 |  |  |  | 149 | SEP | SEP
62210 | 740-UN-VU330-106-LH032-15-0 | 2 | true | 5.58 | 740-UN-VU330-106-LH032-15-0 | LV1-105638.VU330 | 385 |  |  | MC1 | LVL 6 | N/A | TR029_1 | 2024-07-24 | 2024-03-26 | 2024-03-26 |  | 2024-06-03 | 2024-06-07 | Büro | 2024-06-14 |  | 2024-06-07 | 2024-09-02 |  |  | 2024-09-03 | 908 | 150 |  | 2024-09-24 | 2024-09-09 | 149 | SEP | SEP
47047 | 740-UN-VU330-107-LH032-15-0 | 1 | false | 4.4 | 740-UN-VU330-107-LH032-15-0 | LV1-105638.VU330 | 385 |  |  | MC1 | LVL 6 | N/A | TR010 | 2024-03-21 | 2024-03-26 | 2024-03-26 |  | 2024-06-03 | 2024-06-07 | ZRO Prefab | 2024-06-14 |  | 2024-06-07 |  |  |  |  | 908 | 150 |  |  |  | 149 | SEP | SEP
62211 | 740-UN-VU330-107-LH032-15-0 | 2 | true | 4.4 | 740-UN-VU330-107-LH032-15-0 | LV1-105638.VU330 | 385 |  |  | MC1 | LVL 6 | N/A | TR029_1 | 2024-07-24 | 2024-03-26 | 2024-03-26 |  | 2024-06-03 | 2024-06-07 | Büro | 2024-06-14 |  | 2024-06-07 | 2024-09-02 |  |  | 2024-09-03 | 908 | 150 |  | 2024-09-24 | 2024-09-09 | 149 | SEP | SEP
47048 | 740-UN-VU330-108-LH032-15-0 | 1 | true | 11.63 | 740-UN-VU330-108-LH032-15-0 | LV1-105638.VU330 | 385 |  |  | MC1 | LVL 6 | N/A | TR010 | 2024-03-21 | 2024-03-26 | 2024-03-26 |  | 2024-06-03 | 2024-06-07 | Büro | 2024-06-14 |  | 2024-06-07 | 2024-08-27 |  |  | 2024-08-29 | 908 | 150 |  | 2024-09-24 | 2024-08-30 | 149 | SEP | SEP
47049 | 740-UN-VU330-110-LH032-25-0 | 1 | true | 54.86 | 740-UN-VU330-110-LH032-25-0 | LV1-105638.VU330 | 385 |  |  | MC1 | LVL 6 | N/A | TR010 | 2024-03-21 | 2024-03-26 | 2024-03-26 |  | 2024-05-31 | 2024-06-07 | Büro | 2024-06-14 |  | 2024-06-07 | 2024-07-23 |  |  | 2024-08-21 | 908 | 150 |  | 2024-09-24 | 2024-08-22 | 149 | SEP | SEP
47050 | 740-WBU-VU285-101-LH001-25-0 | 1 | false | 55.29 | 740-WBU-VU285-101-LH001-25-0 | LV1-105638.VU285 | 363 |  |  | MC1 | LVL 6 | T60 | TR010 | 2024-03-21 | 2024-03-26 | 2024-03-26 |  | 2024-06-03 |  | ZRO Prefab | [7 empty] | 909 | 150 |  |  | 2024-08-30 | 149 | SEP | SEP
52292 | 740-WBU-VU285-101-LH001-25-0 | 2 | true | 55.29 | 740-WBU-VU285-101-LH001-25-0 | LV1-105638.VU285 | 363 |  |  | MC1 | LVL 6 | T60 | TR021_2 | 2024-06-05 | 2024-03-26 | 2024-03-26 |  | 2024-06-03 | 2024-06-07 | Büro | 2024-06-14 |  | 2024-06-07 | 2024-07-25 |  |  | 2024-08-22 | 909 | 150 |  | 2024-09-05 | 2024-08-30 | 149 | SEP | SEP | 2024-09-04 | 2024-09-30 | 2024-09-30 | 2024-09-30
47051 | 740-WBU-VU285-102-LH001-25-0 | 1 | true | 3.15 | 740-WBU-VU285-102-LH001-25-0 | LV1-105638.VU285 | 363 |  |  | MC1 | LVL 6 | T60 | TR010 | 2024-03-21 | 2024-03-26 | 2024-03-26 |  | 2024-06-03 | 2024-06-07 | Büro | 2024-06-14 |  | 2024-06-07 | 2024-08-27 |  |  | 2024-08-28 | 909 | 150 |  | 2024-09-05 | 2024-08-30 | 149 | SEP | SEP | 2024-09-04 | 2024-09-30 | 2024-09-30 | 2024-09-30
47052 | 740-WBU-VU285-103-LH001-25-0 | 1 | true | 11.18 | 740-WBU-VU285-103-LH001-25-0 | LV1-105638.VU285 | 363 |  |  | MC1 | LVL 6 | T60 | TR010 | 2024-03-21 | 2024-03-26 | 2024-03-26 |  | 2024-06-03 | 2024-06-07 | Büro | 2024-06-14 |  | 2024-06-07 | 2024-08-27 |  |  | 2024-08-28 | 909 | 150 |  | 2024-09-05 | 2024-08-30 | 149 | SEP | SEP | 2024-09-30 | 2024-09-30 | 2024-09-30 | 2024-09-30
47232 | 740-DR3-VS020-101-LH088-40-0 | 1 | true | 2.64 | 740-DR3-VS020-101-LH088-40-0 | LV0-105638.VU081 | 391 |  |  | MC1 | LVL 5 | W23 | TR011 | 2024-04-09 | 2024-04-04 | 2024-04-10 |  | 2024-07-08 | 2024-07-09 | Büro | 2024-07-12 |  | 2024-07-09 |  |  |  | 2024-10-04 | 911 | 150 |  |  |  | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
47233 | 740-DR3-VU081-101-LH088-65-0 | 1 | true | 1.15 | 740-DR3-VU081-101-LH088-65-0 | LV0-105638.VU081 | 391 | 26.Apr.2024 |  | MC1 | LVL 6 | W23 | TR011 | 2024-04-09 | 2024-04-04 | 2024-04-10 |  | 2024-04-23 | 2024-04-25 | Dawid Mierzwa | 2024-04-26 |  | 2024-04-25 | 2024-07-04 | 2024-08-19 | 2024-07-19 | 2024-08-30 | 912 | 150 |  |  | 2024-09-10 | 149 | SEP | SEP | 2024-09-26 | 2024-11-22 | 2024-11-22 | 2024-11-22
47234 | 740-DR3-VU081-114-LH088-40-0 | 1 | false | 57.14 | 740-DR3-VU081-114-LH088-40-0 | LV0-105638.VU081 | 391 | 26.Apr.2024 |  | MC1 | LVL 6 | W23 | TR011 | 2024-04-09 | 2024-04-04 | 2024-04-10 | [11 empty] | 912 | 150 |  |  |  | 149 | SEP | SEP
52573 | 740-DR3-VU081-114-LH088-40-0 | 2 | true | 57.14 | 740-DR3-VU081-114-LH088-40-0 | LV0-105638.VU081 | 391 |  |  | MC1 | LVL 6 | W23 | TR024_1 | 2024-06-10 | 2024-04-04 | 2024-04-10 |  | 2024-07-18 | 2024-07-30 | Dawid Mierzwa | 2024-08-02 |  | 2024-07-30 | 2024-08-07 | 2024-08-09 | 2024-08-09 | 2024-08-30 | 912 | 150 |  |  | 2024-09-12 | 149 | SEP | SEP | 2024-09-26 | 2024-10-04 | 2024-10-04 | 2024-10-04
47235 | 740-DR3-VU081-115-LH088-15-0 | 1 | false | 6.99 | 740-DR3-VU081-115-LH088-15-0 | LV0-105638.VU081 | 391 | 26.Apr.2024 |  | MC1 | LVL 6 | W23 | TR011 | 2024-04-09 | 2024-04-04 | 2024-04-10 |  | 2024-04-15 | 2024-04-15 | Dawid Mierzwa | 2024-04-26 |  | 2024-04-23 |  |  |  | 2024-08-30 | 912 | 150 |  |  |  | 149 | SEP | SEP
52574 | 740-DR3-VU081-115-LH088-15-0 | 2 | true | 6.99 | 740-DR3-VU081-115-LH088-15-0 | LV0-105638.VU081 | 391 |  |  | MC1 | LVL 6 | W23 | TR024_1 | 2024-06-10 | 2024-04-04 | 2024-04-10 |  | 2024-04-15 | 2024-04-15 | Dawid Mierzwa | 2024-04-26 |  | 2024-04-23 | 2024-08-28 | 2024-08-30 | 2024-08-30 | 2024-08-30 | 912 | 150 |  |  | 2024-09-12 | 149 | SEP | SEP | 2024-09-26 | 2024-11-22 | 2024-11-22 | 2024-11-22
47236 | 740-DR3-VU081-116-LH088-40-0 | 1 | true | 0.51 | 740-DR3-VU081-116-LH088-40-0 | LV0-105638.VU081 | 391 | 26.Apr.2024 |  | MC1 | LVL 5 | W23 | TR011 | 2024-04-09 | 2024-04-04 | 2024-04-10 |  | 2024-07-22 | 2024-07-31 | Büro | 2024-08-02 |  | 2024-07-31 |  |  |  | 2024-10-04 | 911 | 150 |  |  | 2024-11-14 | 149 | SEP | SEP
47239 | 740-SP-VS001-101-LH032-15-0 | 1 | true | 2.52 | 740-SP-VS001-101-LH032-15-0 | LV1-105638.VU331 | 385 |  |  | MC1 | LVL 5 | N/A | TR011 | 2024-03-24 | 2024-04-04 | 2024-04-07 |  | 2024-05-31 | 2024-06-07 | Büro | 2024-06-28 |  | 2024-06-14 |  |  |  | 2024-10-08 | 913 | 150 |  |  |  | 149 | SEP | SEP
47240 | 740-SP-VU331-101-LH032-25-0 | 1 | true | 12.64 | 740-SP-VU331-101-LH032-25-0 | LV1-105638.VU331 | 385 |  |  | MC1 | LVL 6 | N/A | TR011 | 2024-03-24 | 2024-04-04 | 2024-04-07 |  | 2024-05-31 | 2024-06-03 | Büro | 2024-06-14 |  | 2024-06-04 | 2024-08-07 |  |  | 2024-08-09 | 906 | 150 |  | 2024-09-24 | 2024-08-22 | 149 | SEP | SEP
47241 | 740-SP-VU331-109-LH032-15-0 | 1 | true | 21.94 | 740-SP-VU331-109-LH032-15-0 | LV1-105638.VU331 | 385 | 26.Apr.2024 |  | MC1 | LVL 5 | N/A | TR011 | 2024-03-24 | 2024-04-04 | 2024-04-07 |  | 2024-04-10 | 2024-04-22 |  | 2024-04-26 |  | 2024-04-22 | 2024-07-04 |  |  | 2024-07-19 | 913 | 150 |  | 2024-09-24 | 2024-07-25 | 149 | SEP | SEP
47242 | 740-WAn-VU200-102-LH032-100-0 | 1 | false | 30.41 | 740-WAn-VU200-102-LH032-100-0 | LV0-105638.VU200 | 385 | 26.Apr.2024 |  | MC1 | LVL 4 | N/A | TR011 | 2024-03-24 | 2024-04-04 | 2024-04-07 |  | 2024-04-19 | 2024-04-24 | Büro | 2024-04-26 |  | 2024-04-24 | 2024-05-07 | 2024-05-13 | 2024-05-15 | 2024-08-21 | 914 | 150 |  |  | 2024-09-03 | 149 | SEP | SEP
63722 | 740-WAn-VU200-102-LH032-100-0 | 2 | true | 30.41 | 740-WAn-VU200-102-LH032-100-0 | LV0-105638.VU200 | 385 |  |  | MC1 | LVL 4 | N/A | TR036_1 | 2024-09-06 | 2024-04-04 | 2024-04-07 |  | 2024-04-19 | 2024-04-24 |  | 2024-04-26 |  | 2024-04-24 | 2024-05-07 | 2024-05-13 | 2024-05-15 | 2024-08-14 | 914 | 150 |  |  | 2024-09-11 | 149 | SEP | SEP
47243 | 740-WAn-VU200-103-LH032-100-0 | 1 | true | 22.39 | 740-WAn-VU200-103-LH032-100-0 | LV0-105638.VU200 | 385 | 26.Apr.2024 |  | MC1 | LVL 4 | N/A | TR011 | 2024-03-24 | 2024-04-04 | 2024-04-07 |  | 2024-04-10 | 2024-04-19 | Büro | 2024-04-26 |  | 2024-04-19 | 2024-05-20 |  |  | 2024-05-24 | 914 | 150 |  |  | 2024-09-02 | 149 | SEP | SEP
47244 | 740-WAn-VU200-112-LH032-65-0 | 1 | true | 6.82 | 740-WAn-VU200-112-LH032-65-0 | LV0-105638.VU200 | 385 |  |  | MC1 | LVL 4 | N/A | TR011 | 2024-03-24 | 2024-04-04 | 2024-04-07 |  | 2024-05-31 | 2024-06-07 | Büro | 2024-06-14 |  | 2024-06-07 | 2024-07-11 |  |  | 2024-07-16 | 914 | 150 |  |  | 2024-09-03 | 149 | SEP | SEP
47245 | 740-WAn-VU200-126-LH032-100-0 | 1 | true | 19.71 | 740-WAn-VU200-126-LH032-100-0 | LV0-105638.VU200 | 385 | 26.Apr.2024 |  | MC1 | LVL 4 | N/A | TR011 | 2024-03-24 | 2024-04-04 | 2024-04-07 |  | 2024-04-10 | 2024-04-18 | Büro | 2024-04-26 |  | 2024-04-18 | 2024-05-13 |  |  | 2024-05-17 | 914 | 150 |  |  | 2024-09-02 | 149 | SEP | SEP
47246 | 740-WAn-VU200-127-LH032-65-0 | 1 | true | 3.88 | 740-WAn-VU200-127-LH032-65-0 | LV0-105638.VU200 | 385 |  |  | MC1 | LVL 4 | N/A | TR011 | 2024-03-24 | 2024-04-04 | 2024-04-07 |  | 2024-06-07 | 2024-06-11 | Büro | 2024-06-28 |  | 2024-06-11 | 2024-07-15 |  |  | 2024-07-16 | 914 | 150 |  |  | 2024-09-03 | 149 | SEP | SEP
47247 | 740-WAn-VU200-139-LH032-65-0 | 1 | false | 5.17 | 740-WAn-VU200-139-LH032-65-0 | LV0-105638.VU200 | 385 |  |  | MC1 | LVL 4 | N/A | TR011 | 2024-03-24 | 2024-04-04 | 2024-04-07 | [11 empty] | 914 | 150 |  |  |  | 149 | SEP | SEP
50255 | 740-WAn-VU200-139-LH032-65-0 | 2 | true | 5.17 | 740-WAn-VU200-139-LH032-65-0 | LV0-105638.VU200 | 385 |  |  | MC1 | LVL 4 | N/A | TR015_2 | 2024-05-05 | 2024-04-03 | 2024-04-06 |  | 2024-06-17 | 2024-06-19 |  | 2024-06-28 |  | 2024-06-20 | 2024-07-15 |  |  | 2024-07-19 | 914 | 150 |  |  | 2024-09-23 | 149 | SEP | SEP
47248 | 740-WAn-VU200-144-LH032-80-0 | 1 | true | 8.5 | 740-WAn-VU200-144-LH032-80-0 | LV0-105638.VU200 | 385 | 26.Apr.2024 |  | MC1 | LVL 4 | N/A | TR011 | 2024-03-24 | 2024-04-04 | 2024-04-07 |  | 2024-04-15 | 2024-04-16 | Büro | 2024-04-26 |  | 2024-04-18 | 2024-05-20 |  |  | 2024-05-24 | 914 | 150 |  |  | 2024-09-02 | 149 | SEP | SEP
47249 | 740-WAn-VU200-152-LH032-80-0 | 1 | true | 8.5 | 740-WAn-VU200-152-LH032-80-0 | LV0-105638.VU200 | 385 | 26.Apr.2024 |  | MC1 | LVL 4 | N/A | TR011 | 2024-03-24 | 2024-04-04 | 2024-04-07 |  | 2024-04-10 | 2024-04-16 | Büro | 2024-04-26 |  | 2024-04-16 | 2024-05-20 |  |  | 2024-05-21 | 914 | 150 |  |  | 2024-09-02 | 149 | SEP | SEP
47250 | 740-WAn-VU200-159-LH032-80-0 | 1 | true | 25.71 | 740-WAn-VU200-159-LH032-80-0 | LV0-105638.VU200 | 385 | 26.Apr.2024 |  | MC1 | LVL 4 | N/A | TR011 | 2024-03-24 | 2024-04-04 | 2024-04-07 |  | 2024-04-10 | 2024-04-19 | Büro | 2024-04-26 |  | 2024-04-19 | 2024-05-13 |  | 2024-05-17 | 2024-05-21 | 914 | 150 |  |  | 2024-09-02 | 149 | SEP | SEP
47251 | 740-WAn-VU200-164-LH032-25-0 | 1 | false | 9.36 | 740-WAn-VU200-164-LH032-25-0 | LV0-105638.VU200 | 385 |  |  | MC1 | LVL 4 | N/A | TR011 | 2024-03-24 | 2024-04-04 | 2024-04-07 | [11 empty] | 914 | 150 |  |  |  | 149 | SEP | SEP
50256 | 740-WAn-VU200-164-LH032-25-0 | 2 | true | 9.36 | 740-WAn-VU200-164-LH032-25-0 | LV0-105638.VU200 | 385 |  |  | MC1 | LVL 4 | N/A | TR015_2 | 2024-05-05 | 2024-04-03 | 2024-04-06 |  | 2024-06-17 | 2024-06-19 | Büro | 2024-06-28 |  | 2024-06-20 | 2024-07-15 |  |  | 2024-10-14 | 914 | 150 |  |  |  | 149 | SEP | SEP
47252 | 740-WAn-VU200-200-LH032-50-0 | 1 | true | 26.15 | 740-WAn-VU200-200-LH032-50-0 | LV0-105638.VU200 | 385 |  |  | MC1 | LVL 4 | N/A | TR011 | 2024-03-24 | 2024-04-04 | 2024-04-07 |  | 2024-06-10 | 2024-06-11 | Büro | 2024-06-28 |  | 2024-06-14 | 2024-07-09 |  |  | 2024-07-11 | 914 | 150 |  |  | 2024-09-03 | 149 | SEP | SEP
47253 | 740-WAn-VU200-222-LH032-80-0 | 1 | false | 25.68 | 740-WAn-VU200-222-LH032-80-0 | LV1-105639.VU200 | 385 | 26.Apr.2024 |  | MC1 | LVL 4 | N/A | TR011 | 2024-03-24 | 2024-04-04 | 2024-04-07 |  | 2024-04-10 | 2024-04-17 | Attila Henter | 2024-04-26 |  | 2024-04-18 | 2024-05-13 |  |  |  | 915 | 150 |  |  |  | 149 | SEP | SEP
50319 | 740-WAn-VU200-222-LH032-80-0 | 2 | true | 25.68 | 740-WAn-VU200-222-LH032-80-0 | LV1-105639.VU200 | 385 |  |  | MC1 | LVL 4 | N/A | TR016_1 | 2024-05-08 | 2024-04-04 | 2024-04-07 |  | 2024-04-10 | 2024-04-17 | Büro | 2024-04-26 |  | 2024-04-18 | 2024-05-13 | 2024-05-17 |  | 2024-05-21 | 915 | 150 |  |  | 2024-09-02 | 149 | SEP | SEP
47254 | 740-WAn-VU200-234-LH032-80-0 | 1 | false | 22.35 | 740-WAn-VU200-234-LH032-80-0 | LV1-105639.VU200 | 385 | 26.Apr.2024 |  | MC1 | LVL 4 | N/A | TR011 | 2024-03-24 | 2024-04-04 | 2024-04-07 |  | 2024-04-10 | 2024-04-19 | Büro | 2024-04-26 |  | 2024-04-19 | 2024-05-13 |  |  | 2024-05-21 | 915 | 150 |  |  |  | 149 | SEP | SEP
51726 | 740-WAn-VU200-234-LH032-80-0 | 3 | true | 22.35 | 740-WAn-VU200-234-LH032-80-0 | LV1-105639.VU200 | 385 |  |  | MC1 | LVL 4 | N/A | TR018_3 | 2024-05-20 | 2024-04-04 | 2024-04-07 |  | 2024-04-10 | 2024-04-19 | Büro | 2024-04-26 |  | 2024-04-19 | 2024-05-13 |  |  | 2024-06-21 | 915 | 150 |  |  | 2024-09-09 | 149 | SEP | SEP
47255 | 740-WAn-VU200-248-LH032-80-0 | 1 | true | 22.9 | 740-WAn-VU200-248-LH032-80-0 | LV1-105639.VU200 | 385 | 26.Apr.2024 |  | MC1 | LVL 4 | N/A | TR011 | 2024-03-24 | 2024-04-04 | 2024-04-07 |  | 2024-04-19 | 2024-04-20 | Büro | 2024-04-26 |  | 2024-04-20 | 2024-05-20 |  |  | 2024-05-24 | 915 | 150 |  |  | 2024-09-02 | 149 | SEP | SEP
47256 | 740-WAn-VU200-251-LH032-100-0 | 1 | false | 31.67 | 740-WAn-VU200-251-LH032-100-0 | LV1-105639.VU200 | 385 | 26.Apr.2024 |  | MC1 | LVL 4 | N/A | TR011 | 2024-03-24 | 2024-04-04 | 2024-04-07 |  | 2024-04-15 | 2024-04-15 | Attila Henter | 2024-04-26 |  | 2024-04-18 | 2024-05-07 |  | 2024-05-21 |  | 915 | 150 |  |  |  | 149 | SEP | SEP
50257 | 740-WAn-VU200-251-LH032-100-0 | 2 | true | 31.67 | 740-WAn-VU200-251-LH032-100-0 | LV1-105639.VU200 | 385 | 26.Apr.2024 |  | MC1 | LVL 4 | N/A | TR015_2 | 2024-05-05 | 2024-04-03 | 2024-04-06 |  | 2024-04-14 | 2024-04-14 | Büro | 2024-04-25 |  | 2024-04-17 | 2024-05-07 |  | 2024-05-17 | 2024-08-15 | 915 | 150 |  | 2024-10-09 | 2024-10-08 | 149 | SEP | SEP
47257 | 740-WAn-VU200-252-LH032-80-0 | 1 | true | 8.75 | 740-WAn-VU200-252-LH032-80-0 | LV0-105638.VU161 | 385 |  |  | MC1 | LVL 4 | N/A | TR011 | 2024-03-24 | 2024-04-04 | 2024-04-07 |  | 2024-06-10 | 2024-06-12 | Büro | 2024-06-28 |  | 2024-06-14 | 2024-07-11 |  |  | 2024-07-16 | 915 | 150 |  |  | 2024-09-03 | 149 | SEP | SEP
47258 | 740-WAn-VU200-256-LH032-65-0 | 1 | true | 14.12 | 740-WAn-VU200-256-LH032-65-0 | LV1-105639.VU200 | 385 |  |  | MC1 | LVL 4 | N/A | TR011 | 2024-03-24 | 2024-04-04 | 2024-04-07 |  | 2024-06-07 | 2024-06-12 | Büro | 2024-06-28 |  | 2024-06-12 | 2024-07-09 |  |  | 2024-07-11 | 915 | 150 |  |  | 2024-09-03 | 149 | SEP | SEP
47259 | 740-WFI-VU161-108-LH089-65-0 | 1 | true | 19.02 | 740-WFI-VU161-108-LH089-65-0 | LV0-105638.VU161 | 394 | 10.May.2024 |  | MC1 | LVL 6 | W23 | TR011 | 2024-04-06 | 2024-04-04 | 2024-04-09 |  | 2024-04-15 | 2024-04-17 | Büro | 2024-04-26 |  | 2024-04-18 | 2024-05-20 | 2024-05-24 |  | 2024-07-10 | 916 | 150 |  | 2024-10-15 | 2024-07-18 | 149 | SEP | SEP |  | 2024-10-18 | 2024-10-18 | 2024-10-25
47260 | 740-WFI-VU161-201-LH089-50-0 | 1 | true | 8.35 | 740-WFI-VU161-201-LH089-50-0 | LV1-105639.VU161 | 394 | 10.May.2024 |  | MC1 | LVL 6 | W23 | TR011 | 2024-04-06 | 2024-04-04 | 2024-04-09 |  | 2024-04-18 | 2024-04-18 | Büro | 2024-04-26 |  | 2024-04-18 | 2024-05-13 |  | 2024-05-17 | 2024-07-05 | 916 | 150 |  |  | 2024-07-18 | 149 | SEP | SEP | 2024-10-25 | 2024-10-25 | 2024-10-25 | 2024-10-25 | 2024-10-25 | 2024-10-25
47261 | 740-WFI-VU161-202-LH089-50-0 | 1 | true | 22.38 | 740-WFI-VU161-202-LH089-50-0 | LV1-105639.VU161 | 394 | 26.Apr.2024 |  | MC1 | LVL 6 | W23 | TR011 | 2024-04-06 | 2024-04-04 | 2024-04-09 |  | 2024-04-10 | 2024-04-11 | Dawid Mierzwa | 2024-04-26 |  | 2024-04-11 | 2024-05-13 | 2024-05-17 |  | 2024-05-24 | 916 | 150 |  | 2024-10-15 | 2024-09-02 | 149 | SEP | SEP |  | 2024-10-18 | 2024-10-18 | 2024-10-18
47262 | 740-WFI-VU161-206-LH089-40-0 | 1 | true | 25.9 | 740-WFI-VU161-206-LH089-40-0 | LV1-105639.VU161 | 394 | 26.Apr.2024 |  | MC1 | LVL 6 | W23 | TR011 | 2024-04-06 | 2024-04-04 | 2024-04-09 |  | 2024-04-23 | 2024-04-24 | Dawid Mierzwa | 2024-04-26 |  | 2024-04-24 | 2024-05-13 | 2024-05-17 | 2024-05-24 | 2024-07-26 | 916 | 150 |  |  | 2024-09-10 | 149 | SEP | SEP | 2024-10-25 | 2024-10-25 | 2024-10-25 | 2024-10-25
47263 | 740-WFI-VU162-108-LH089-65-0 | 1 | true | 17.09 | 740-WFI-VU162-108-LH089-65-0 | LV0-105638.VU162 | 394 | 10.May.2024 |  | MC1 | LVL 6 | W23 | TR011 | 2024-04-06 | 2024-04-04 | 2024-04-09 |  | 2024-07-24 | 2024-07-24 | Büro | 2024-08-02 |  | 2024-07-31 | 2024-08-07 |  |  | 2024-08-23 | 917 | 150 |  | 2024-10-15 | 2024-09-04 | 149 | SEP | SEP |  | 2024-10-18 | 2024-10-18 | 2024-10-25
47264 | 740-WFI-VU162-201-LH089-50-0 | 1 | true | 7.9 | 740-WFI-VU162-201-LH089-50-0 | LV1-105639.VU162 | 394 | 10.May.2024 |  | MC1 | LVL 6 | W23 | TR011 | 2024-04-06 | 2024-04-04 | 2024-04-09 |  | 2024-04-18 | 2024-04-18 | Büro | 2024-04-26 |  | 2024-04-18 | 2024-05-13 |  | 2024-05-17 | 2024-10-10 | 917 | 150 |  |  |  | 149 | SEP | SEP | 2024-10-25 | 2024-10-25 | 2024-10-25 | 2024-10-25
47265 | 740-WFI-VU162-202-LH089-50-0 | 1 | true | 22.24 | 740-WFI-VU162-202-LH089-50-0 | LV1-105639.VU162 | 394 | 26.Apr.2024 |  | MC1 | LVL 6 | W23 | TR011 | 2024-04-06 | 2024-04-04 | 2024-04-09 |  | 2024-04-10 | 2024-04-11 | Dawid Mierzwa | 2024-04-26 |  | 2024-04-11 | 2024-05-13 | 2024-05-17 |  | 2024-05-24 | 917 | 150 |  |  | 2024-09-04 | 149 | SEP | SEP |  | 2024-10-18 | 2024-10-18 | 2024-10-18
47266 | 740-WFI-VU162-207-LH089-40-0 | 1 | true | 26.81 | 740-WFI-VU162-207-LH089-40-0 | LV1-105639.VU162 | 394 | 26.Apr.2024 |  | MC1 | LVL 6 | W23 | TR011 | 2024-04-06 | 2024-04-04 | 2024-04-09 |  | 2024-04-23 | 2024-04-24 | Dawid Mierzwa | 2024-04-26 |  | 2024-04-24 | 2024-05-13 | 2024-05-17 | 2024-05-24 | 2024-07-26 | 917 | 150 |  |  | 2024-09-10 | 149 | SEP | SEP |  | 2024-10-18 | 2024-10-18 | 2024-10-18
47267 | 740-WFI-VU163-107-LH089-80-0 | 1 | true | 8.6 | 740-WFI-VU163-107-LH089-80-0 | LV0-105638.VU163 | 394 | 10.May.2024 |  | MC1 | LVL 6 | W23 | TR011 | 2024-04-06 | 2024-04-04 | 2024-04-09 |  | 2024-04-18 | 2024-04-19 | Dawid Mierzva | 2024-04-26 |  | 2024-04-19 | 2024-05-20 | 2024-05-24 |  | 2024-07-19 | 918 | 150 |  |  | 2024-09-10 | 149 | SEP | SEP | 2024-10-01 | 2024-10-14 | 2024-10-14 | 2024-10-14 | 2024-10-14 | 2024-10-14
47268 | 740-WFI-VU163-108-LH089-80-0 | 1 | true | 8.92 | 740-WFI-VU163-108-LH089-80-0 | LV1-105639.VU163 | 394 | 10.May.2024 |  | MC1 | LVL 6 | W23 | TR011 | 2024-04-06 | 2024-04-04 | 2024-04-09 |  | 2024-04-18 | 2024-04-19 | Büro | 2024-04-26 |  | 2024-04-19 | 2024-05-20 | 2024-05-24 |  | 2024-07-05 | 918 | 150 |  |  | 2024-09-10 | 149 | SEP | SEP | 2024-10-01 | 2024-10-14 | 2024-10-14 | 2024-10-14
47269 | 740-WFI-VU163-201-LH089-80-0 | 1 | true | 31.01 | 740-WFI-VU163-201-LH089-80-0 | LV1-105639.VU163 | 394 | 26.Apr.2024 |  | MC1 | LVL 6 | W23 | TR011 | 2024-04-06 | 2024-04-04 | 2024-04-09 |  | 2024-04-12 | 2024-04-15 | Dawid Mierzwa | 2024-04-26 |  | 2024-04-15 | 2024-05-13 | 2024-05-17 |  | 2024-05-24 | 918 | 150 |  |  | 2024-09-10 | 149 | SEP | SEP | 2024-10-01 | 2024-10-14 | 2024-10-14
47270 | 740-WFI-VU163-205-LH089-65-0 | 1 | true | 24.38 | 740-WFI-VU163-205-LH089-65-0 | LV1-105639.VU163 | 394 | 26.Apr.2024 |  | MC1 | LVL 6 | W23 | TR011 | 2024-04-06 | 2024-04-04 | 2024-04-09 |  | 2024-04-15 | 2024-04-16 | Büro | 2024-04-26 |  | 2024-04-23 | 2024-05-13 |  | 2024-05-24 | 2024-07-10 | 918 | 150 |  |  | 2024-09-10 | 149 | SEP | SEP | 2024-10-01 | 2024-10-14 | 2024-10-14 | 2024-10-14
47633 | 740-AB-VU020-182-LH099-15-0 | 1 | true | 0.89 | 740-AB-VU020-182-LH099-15-0 | LV1-105638.VU020 | 386 |  |  | MC1 | LVL 5 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-06-12 | 2024-06-12 | Büro | 2024-06-28 |  | 2024-06-14 |  |  |  | 2024-10-23 | 926 | 150 |  |  | 2024-10-30 | 149 | SEP | SEP
47634 | 740-CIP-S-VS681-101-LH089-40-0 | 1 | true | 14.18 | 740-CIP-S-VS681-101-LH089-40-0 | LV0-105633.VS681 | 394 |  |  | MC1 | LVL 6 | W23 | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-05-24 | 2024-05-27 | Büro | 2024-05-31 |  | 2024-05-27 | 2024-06-25 |  | 2024-06-28 | 2024-08-09 | 927 | 150 |  | 2024-11-12 | 2024-09-10 | 149 | SEP | SEP |  |  | 2024-11-15 | 2024-11-15
47635 | 740-CIP-S-VS681-102-LH089-40-0 | 1 | true | 14.49 | 740-CIP-S-VS681-102-LH089-40-0 | LV0-105633.VS681 | 394 |  |  | MC1 | LVL 6 | W23 | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-05-29 | 2024-05-30 | Büro | 2024-06-14 |  | 2024-06-03 | 2024-06-25 |  | 2024-06-28 | 2024-08-09 | 927 | 150 |  | 2024-11-12 | 2024-09-12 | 149 | SEP | SEP |  |  | 2024-11-15 | 2024-11-15
47636 | 740-CIP-S-VS681-103-LH089-40-0 | 1 | true | 17.83 | 740-CIP-S-VS681-103-LH089-40-0 | LV0-105633.VS681 | 394 |  |  | MC1 | LVL 6 | W23 | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-05-28 | 2024-05-29 | Büro | 2024-06-14 |  | 2024-06-03 | 2024-06-25 |  | 2024-06-28 | 2024-09-20 | 927 | 150 |  | 2024-11-12 |  | 149 | SEP | SEP |  |  | 2024-11-15 | 2024-11-15
47637 | 740-CIP-S-VS681-115-LH089-40-0 | 1 | true | 1.14 | 740-CIP-S-VS681-115-LH089-40-0 | LV0-105633.VS681 | 394 |  |  | MC1 | LVL 6 | W23 | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-07-05 | 2024-07-08 | Büro | 2024-07-12 |  | 2024-07-10 | 2024-07-31 |  |  | 2024-08-09 | 927 | 150 |  | 2024-11-12 | 2024-09-11 | 149 | SEP | SEP |  |  | 2024-11-15 | 2024-11-15
47638 | 740-CIP-S-VS681-119-LH089-40-0 | 1 | true | 1.39 | 740-CIP-S-VS681-119-LH089-40-0 | LV0-105633.VS681 | 394 |  |  | MC1 | LVL 6 | W23 | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-07-05 | 2024-07-08 | Büro | 2024-07-12 |  | 2024-07-10 |  |  |  | 2024-09-20 | 927 | 150 |  | 2024-11-12 |  | 149 | SEP | SEP |  |  | 2024-11-15 | 2024-11-15
47639 | 740-CIP-S-VS681-121-LH089-40-0 | 1 | true | 26.84 | 740-CIP-S-VS681-121-LH089-40-0 | LV0-105633.VS681 | 394 |  | false | MC1 | LVL 5 | W23 | TR012 | 2024-04-13 | 2024-08-20 |  | ISO NOT Submitted to AZI Date received WRONG | 2024-09-04 | [8 empty] | 2024-10-18 | 928 | 150 |  | 2024-11-12 | 2024-10-29 | 149 | SEP | SEP |  |  | 2024-11-15 | 2024-11-15
47640 | 740-CIP-S-VS681-124-LH089-40-0 | 1 | true | 2.06 | 740-CIP-S-VS681-124-LH089-40-0 | LV0-105633.VS681 | 394 |  |  | MC1 | LVL 6 | W23 | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-07-05 | 2024-07-08 | Büro | 2024-07-12 |  | 2024-07-10 | 2024-07-31 |  |  | 2024-08-09 | 927 | 150 |  | 2024-11-12 | 2024-09-11 | 149 | SEP | SEP |  |  | 2024-11-15 | 2024-11-15
47641 | 740-CIP-S-VS681-126-LH089-40-0 | 1 | true | 26.34 | 740-CIP-S-VS681-126-LH089-40-0 | LV0-105633.VS681 | 394 |  | false | MC1 | LVL 5 | W23 | TR012 | 2024-04-13 | 2024-08-20 |  | ISO NOT Submitted to AZI Date received WRONG | 2024-09-04 |  |  |  |  | 2024-09-06 |  |  |  | 2024-10-18 | 928 | 150 |  |  | 2024-10-29 | 149 | SEP | SEP | 2024-11-08 | 2024-11-08 | 2024-11-08
47642 | 740-CIP-S-VS681-132-LH089-40-0 | 1 | true | 1.17 | 740-CIP-S-VS681-132-LH089-40-0 | LV0-105633.VS681 | 394 |  | false | MC1 | LVL 6 | W23 | TR012 | 2024-04-13 | 2024-08-20 |  | ISO NOT Submitted to AZI Date received WRONG | 2024-09-27 |  | Büro |  |  |  | 2024-09-27 |  |  | 2024-10-10 | 927 | 150 |  | 2024-11-12 |  | 149 | SEP | SEP |  |  | 2024-11-15 | 2024-11-15
47643 | 740-CIP-S-VS681-133-LH089-40-0 | 1 | true | 1.17 | 740-CIP-S-VS681-133-LH089-40-0 | LV0-105633.VS681 | 394 |  | false | MC1 | LVL 6 | W23 | TR012 | 2024-04-13 | 2024-08-20 |  | ISO NOT Submitted to AZI Date received WRONG | 2024-09-27 |  | Büro |  |  |  | 2024-09-27 |  |  | 2024-10-10 | 927 | 150 |  | 2024-11-12 |  | 149 | SEP | SEP |  |  | 2024-11-15 | 2024-11-15
47644 | 740-CIP-S-VS681-134-LH089-40-0 | 1 | true | 1.17 | 740-CIP-S-VS681-134-LH089-40-0 | LV0-105633.VS681 | 394 |  | false | MC1 | LVL 6 | W23 | TR012 | 2024-04-13 | 2024-08-20 |  | ISO NOT Submitted to AZI Date received WRONG | 2024-09-27 |  | Büro |  |  |  | 2024-09-27 |  |  | 2024-10-10 | 927 | 150 |  | 2024-11-12 |  | 149 | SEP | SEP |  |  | 2024-11-15 | 2024-11-15
47645 | 740-CIP-S-VS681-205-LH089-40-0 | 1 | false | 45.87 | 740-CIP-S-VS681-205-LH089-40-0 | LV0-105633.VS681 | 394 |  | false | MC1 | LVL 5 | W23 | TR012 | 2024-04-13 |  |  | ISO NOT Submitted to AZI Date received WRONG | [10 empty] | 928 | 150 |  |  |  | 149 | SEP | SEP
49444 | 740-CIP-S-VS681-205-LH089-40-0 | 2 | false | 45.87 | 740-CIP-S-VS681-205-LH089-40-0 | LV0-105633.VS681 | 394 |  |  | MC1 | LVL 5 | W23 | TR013_2 | 2024-04-21 | 2024-04-23 |  | ISO NOT Submitted to AZI Date received WRONG | [10 empty] | 928 | 150 |  |  |  | 149 | SEP | SEP
49627 | 740-CIP-S-VS681-205-LH089-40-0 | 3 | true | 45.87 | 740-CIP-S-VS681-205-LH089-40-0 | LV0-105633.VS681 | 394 |  |  | MC1 | LVL 5 | W23 | TR014_1 | 2024-04-22 | 2024-04-29 | 2024-04-29 | ISO NOT Submitted to AZI Date received WRONG | 2024-07-22 | 2024-07-25 |  | 2024-08-02 |  | 2024-07-31 |  |  |  | 2024-10-18 | 928 | 150 |  |  | 2024-10-29 | 149 | SEP | SEP | 2024-11-08 | 2024-11-08 | 2024-11-08
47646 | 740-CIP-S-VS681-210-LH089-40-0 | 1 | false | 45.36 | 740-CIP-S-VS681-210-LH089-40-0 | LV0-105633.VS681 | 394 |  | false | MC1 | LVL 5 | W23 | TR012 | 2024-04-13 |  |  | ISO NOT Submitted to AZI Date received WRONG | [10 empty] | 928 | 150 |  |  |  | 149 | SEP | SEP
49628 | 740-CIP-S-VS681-210-LH089-40-0 | 2 | true | 45.36 | 740-CIP-S-VS681-210-LH089-40-0 | LV0-105633.VS681 | 394 |  |  | MC1 | LVL 5 | W23 | TR014_1 | 2024-04-22 | 2024-04-29 | 2024-04-29 | ISO NOT Submitted to AZI Date received WRONG | 2024-05-27 | 2024-05-29 | Büro | 2024-06-14 |  | 2024-06-03 | 2024-06-25 |  | 2024-07-10 | 2024-10-04 | 928 | 150 |  |  |  | 149 | SEP | SEP | 2024-11-08 | 2024-11-08 | 2024-11-08
47647 | 740-CIP-S-VS681-305-LH089-40-0 | 1 | true | 40.25 | 740-CIP-S-VS681-305-LH089-40-0 | LV1-105635.VS681 | 394 |  | false | MC1 | LVL 5 | Tt-6 | TR012 | 2024-04-13 | 2024-08-20 |  | ISO NOT Submitted to AZI Date received WRONG |  |  | Büro |  |  | 2024-09-06 |  |  |  | 2024-10-04 | 928 | 150 |  |  |  | 149 | SEP | SEP | 2024-11-08 | 2024-11-08 | 2024-11-08 | 2024-11-15
47648 | 740-CIP-S-VS681-314-LH089-40-0 | 1 | true | 27.62 | 740-CIP-S-VS681-314-LH089-40-0 | LV1-105635.VS681 | 394 |  | false | MC1 | LVL 5 | Tt-6 | TR012 | 2024-04-13 | 2024-08-20 |  | ISO NOT Submitted to AZI Date received WRONG |  |  | Büro |  |  | 2024-09-06 | 2024-09-09 |  | 2024-09-16 | 2024-10-04 | 928 | 150 |  |  |  | 149 | SEP | SEP | 2024-11-08 | 2024-11-08 | 2024-11-08
47649 | 740-CIP-S-VS681-320-LH089-25-0 | 1 | true | 3.08 | 740-CIP-S-VS681-320-LH089-25-0 | LV1-105635.VS681 | 394 |  | false | MC1 | LVL 6 | W23 | TR012 | 2024-04-13 | 2024-08-20 |  | ISO NOT Submitted to AZI Date received WRONG | 2024-09-27 |  | Büro |  |  |  | 2024-09-27 |  |  | 2024-10-10 | 927 | 150 |  | 2024-11-12 |  | 149 | SEP | SEP |  |  | 2024-11-15 | 2024-11-15
47650 | 740-CIP-S-VS681-325-LH089-25-0 | 1 | true | 3.07 | 740-CIP-S-VS681-325-LH089-25-0 | LV1-105635.VS681 | 394 |  | false | MC1 | LVL 6 | W23 | TR012 | 2024-04-13 |  |  | ISO NOT Submitted to AZI Date received WRONG | 2024-09-27 |  | Büro |  |  |  | 2024-09-27 |  |  | 2024-10-10 | 927 | 150 |  | 2024-11-12 |  | 149 | SEP | SEP |  |  | 2024-11-15 | 2024-11-15
47651 | 740-CIP-S-VS685-107-LH089-32-0 | 1 | false | 24.91 | 740-CIP-S-VS685-107-LH089-32-0 | LV0-105633.VS681 | 394 |  | false | MC1 | LVL 5 | W23 | TR012 | 2024-04-13 | 2024-08-20 |  | ISO NOT Submitted to AZI Date received WRONG | [10 empty] | 928 | 150 |  |  |  | 149 | SEP | SEP
52275 | 740-CIP-S-VS685-107-LH089-32-0 | 2 | true | 24.91 | 740-CIP-S-VS685-107-LH089-32-0 | LV0-105633.VS681 | 394 |  |  | MC1 | LVL 5 | W23 | TR021_2 | 2024-06-05 | 2024-06-05 | 2024-06-05 | ISO NOT Submitted to AZI Date received WRONG | 2024-06-27 | 2024-06-28 | Büro | 2024-07-12 |  | 2024-07-05 | 2024-07-23 |  | 2024-07-31 | 2024-10-04 | 928 | 150 |  |  |  | 149 | SEP | SEP | 2024-11-08 | 2024-11-08 | 2024-11-08 | 2024-11-15 | 2024-12-06 | 2024-12-06
47652 | 740-LP-VP001-101-LH099-20-0 | 1 | true | 8.27 | 740-LP-VP001-101-LH099-20-0 | LV1-105638.VU001 | 386 | 10.May.2024 |  | MC1 | LVL 5 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-04-25 | 2024-04-27 | Büro | 2024-05-17 |  | 2024-04-29 | 2024-06-04 |  | 2024-06-06 | 2024-09-18 | 929 | 150 |  | 2024-11-13 | 2024-09-25 | 149 | SEP | SEP
47653 | 740-LP-VP002-101-LH099-20-0 | 1 | true | 6.91 | 740-LP-VP002-101-LH099-20-0 | LV1-105638.VU001 | 386 | 10.May.2024 |  | MC1 | LVL 5 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-04-25 | 2024-04-25 | Büro | 2024-05-17 |  | 2024-04-29 | 2024-06-04 |  | 2024-06-07 | 2024-09-18 | 929 | 150 |  |  | 2024-09-25 | 149 | SEP | SEP
47654 | 740-LP-VP003-101-LH099-15-0 | 1 | true | 8.99 | 740-LP-VP003-101-LH099-15-0 | LV1-105638.VU001 | 386 | 10.May.2024 |  | MC1 | LVL 5 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-04-25 | 2024-04-25 | Büro | 2024-05-17 |  | 2024-04-29 | 2024-06-04 |  | 2024-06-07 | 2024-09-06 | 929 | 150 |  |  | 2024-09-09 | 149 | SEP | SEP
47655 | 740-LP-VP004-101-LH099-15-0 | 1 | true | 10.01 | 740-LP-VP004-101-LH099-15-0 | LV1-105638.VU001 | 386 | 10.May.2024 |  | MC1 | LVL 5 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-04-25 | 2024-04-26 | Büro | 2024-05-17 |  | 2024-04-29 | 2024-06-04 |  | 2024-06-10 | 2024-09-06 | 929 | 150 |  |  | 2024-09-09 | 149 | SEP | SEP
47656 | 740-LP-VP031-101-LH099-25-0 | 1 | true | 12.65 | 740-LP-VP031-101-LH099-25-0 | LV1-105638.VU001 | 386 | 10.May.2024 |  | MC1 | LVL 5 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-04-24 | 2024-04-30 | Büro | 2024-05-17 |  | 2024-04-30 | 2024-09-18 |  |  | 2024-09-20 | 929 | 150 |  |  | 2024-09-25 | 149 | SEP | SEP
47657 | 740-LP-VP032-101-LH099-25-0 | 1 | true | 4.45 | 740-LP-VP032-101-LH099-25-0 | LV1-105638.VU001 | 386 |  |  | MC1 | LVL 5 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-06-10 | 2024-06-11 | Büro | 2024-06-28 |  | 2024-06-11 | 2024-10-23 |  |  | 2024-10-25 | 929 | 150 |  | 2024-11-18 |  | 149 | SEP | SEP
47658 | 740-LP-VP033-101-LH099-25-0 | 1 | true | 6.84 | 740-LP-VP033-101-LH099-25-0 | LV1-105638.VU001 | 386 |  |  | MC1 | LVL 5 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-06-10 | 2024-06-12 | Büro | 2024-06-28 |  | 2024-06-12 | 2024-09-21 |  |  | 2024-09-25 | 929 | 150 |  | 2024-11-18 | 2024-11-12 | 149 | SEP | SEP
47659 | 740-LP-VP041-101-LH099-25-0 | 1 | true | 8.39 | 740-LP-VP041-101-LH099-25-0 | LV1-105638.VU001 | 386 | 10.May.2024 |  | MC1 | LVL 5 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-04-24 | 2024-04-25 | Büro | 2024-05-17 |  | 2024-04-25 | 2024-08-20 |  |  | 2024-09-17 | 929 | 150 |  |  | 2024-09-25 | 149 | SEP | SEP
47660 | 740-LP-VP042-101-LH099-25-0 | 1 | true | 2.78 | 740-LP-VP042-101-LH099-25-0 | LV1-105638.VU001 | 386 |  |  | MC1 | LVL 5 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-06-10 | 2024-06-11 |  | 2024-06-28 |  | 2024-06-14 | 2024-09-18 |  |  | 2024-09-21 | 929 | 150 |  |  | 2024-09-25 | 149 | SEP | SEP
47661 | 740-LP-VP043-101-LH099-25-0 | 1 | true | 2.15 | 740-LP-VP043-101-LH099-25-0 | LV1-105638.VU001 | 386 |  |  | MC1 | LVL 5 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-06-10 | 2024-06-11 | Büro | 2024-06-28 |  | 2024-06-14 | 2024-10-23 |  |  | 2024-10-25 | 929 | 150 |  | 2024-11-18 |  | 149 | SEP | SEP
47662 | 740-LP-VS001-101-LH099-25-0 | 1 | false | 3.36 | 740-LP-VS001-101-LH099-25-0 | LV1-105638.VU001 | 386 |  |  | MC1 | LVL 5 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 | [11 empty] | 929 | 150 |  |  |  | 149 | SEP | SEP
50963 | 740-LP-VS001-101-LH099-25-0 | 2 | true | 3.36 | 740-LP-VS001-101-LH099-25-0 | LV1-105638.VU001 | 386 |  |  | MC1 | LVL 5 | N/A | TR018_1 | 2024-05-15 | 2024-04-17 | 2024-04-17 |  | 2024-06-10 | 2024-06-10 | Büro | 2024-06-28 |  | 2024-06-10 |  |  |  | 2024-10-16 | 929 | 150 |  |  |  | 149 | SEP | SEP
47663 | 740-LP-VS020-101-LH099-15-0 | 1 | true | 4.09 | 740-LP-VS020-101-LH099-15-0 | LV1-105638.VU001 | 386 |  |  | MC1 | LVL 5 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-06-10 | 2024-06-12 | Büro | 2024-06-28 |  | 2024-06-12 | 2024-10-23 |  |  | 2024-10-25 | 929 | 150 |  |  | 2024-11-07 | 149 | SEP | SEP
47664 | 740-LP-VS681-101-LH099-25-0 | 1 | true | 4.1 | 740-LP-VS681-101-LH099-25-0 | LV0-105633.VS681 | 386 |  |  | MC1 | LVL 5 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-06-11 | 2024-06-18 | Büro | 2024-06-28 |  | 2024-06-21 |  |  |  | 2024-11-12 | 929 | 150 |  |  |  | 149 | SEP | SEP
47665 | 740-LP-VS681-201-LH099-25-0 | 1 | false | 15.94 | 740-LP-VS681-201-LH099-25-0 | LV0-105634.VS681 | 386 | 10.May.2024 |  | MC1 | LVL 5 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-04-24 | 2024-04-25 |  |  |  | 2024-04-29 |  |  |  |  | 929 | 150 |  |  |  | 149 | SEP | SEP
49503 | 740-LP-VS681-201-LH099-25-0 | 2 | false | 15.94 | 740-LP-VS681-201-LH099-25-0 | LV0-105634.VS681 | 386 | 10.May.2024 |  | MC1 | LVL 5 | N/A | TR013_2 | 2024-04-21 | 2024-04-23 | [12 empty] | 929 | 150 |  |  |  | 149 | SEP | SEP
49641 | 740-LP-VS681-201-LH099-25-0 | 3 | true | 15.94 | 740-LP-VS681-201-LH099-25-0 | LV0-105634.VS681 | 386 | 10.May.2024 |  | MC1 | LVL 5 | N/A | TR014_1 | 2024-04-22 | 2024-04-29 | 2024-04-29 |  | 2024-04-23 | 2024-04-23 | Büro | 2024-05-17 |  | 2024-05-16 |  |  | 2024-10-10 | 2024-12-17 | 929 | 150 |  |  |  | 149 | SEP | SEP
47666 | 740-LP-VU001-116-LH099-25-0 | 1 | true | 4.72 | 740-LP-VU001-116-LH099-25-0 | LV1-105638.VU001 | 386 |  |  | MC1 | LVL 5 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-06-12 | 2024-06-13 |  | 2024-06-28 |  | 2024-06-21 | 2024-07-26 |  |  | 2024-07-31 | 929 | 150 |  | 2024-09-20 | 2024-08-26 | 149 | SEP | SEP
47667 | 740-LP-VU001-121-LH099-50-0 | 1 | true | 11.97 | 740-LP-VU001-121-LH099-50-0 | LV1-105638.VU001 | 386 | 10.May.2024 |  | MC1 | LVL 5 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-04-23 | 2024-05-08 | Büro | 2024-05-17 |  | 2024-05-08 | 2024-05-28 |  |  | 2024-06-13 | 929 | 150 |  |  | 2024-08-26 | 149 | SEP | SEP
47668 | 740-LP-VU001-123-LH099-50-0 | 1 | true | 7.61 | 740-LP-VU001-123-LH099-50-0 | LV1-105638.VU001 | 386 | 10.May.2024 |  | MC1 | LVL 5 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-04-23 | 2024-05-08 | Büro | 2024-05-17 |  | 2024-05-08 | 2024-05-28 |  |  | 2024-06-13 | 929 | 150 |  |  | 2024-08-26 | 149 | SEP | SEP
47669 | 740-LP-VU001-125-LH099-20-0 | 1 | false | 18.39 | 740-LP-VU001-125-LH099-20-0 | LV1-105638.VU001 | 386 | 10.May.2024 |  | MC1 | LVL 5 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-04-23 | 2024-04-25 | Miljenko Lazar | 2024-05-17 |  | 2024-04-25 | 2024-06-04 |  |  |  | 929 | 150 |  |  |  | 149 | SEP | SEP
52269 | 740-LP-VU001-125-LH099-20-0 | 2 | true | 18.39 | 740-LP-VU001-125-LH099-20-0 | LV1-105638.VU001 | 386 |  |  | MC1 | LVL 5 | N/A | TR021_1 | 2024-06-04 | 2024-04-17 | 2024-04-17 |  | 2024-04-23 | 2024-04-25 | Büro | 2024-05-17 |  | 2024-04-25 | 2024-09-19 |  | 2024-06-11 | 2024-09-20 | 929 | 150 |  |  | 2024-09-19 | 149 | SEP | SEP
47670 | 740-LP-VU001-127-LH099-25-0 | 1 | false | 9.88 | 740-LP-VU001-127-LH099-25-0 | LV1-105638.VU001 | 386 | 10.May.2024 |  | MC1 | LVL 5 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-04-24 | 2024-05-09 |  | 2024-05-17 |  | 2024-05-09 |  |  |  |  | 929 | 150 |  |  |  | 149 | SEP | SEP
50965 | 740-LP-VU001-127-LH099-25-0 | 2 | true | 9.88 | 740-LP-VU001-127-LH099-25-0 | LV1-105638.VU001 | 386 |  |  | MC1 | LVL 5 | N/A | TR018_1 | 2024-05-15 | 2024-04-17 | 2024-04-17 |  | 2024-04-24 | 2024-05-09 | Satu Mare |  |  | 2024-05-09 | 2024-05-23 |  |  | 2024-05-29 | 929 | 150 |  |  | 2024-08-26 | 149 | SEP | SEP
47671 | 740-LS-VS001-101-LH023-15-0 | 1 | true | 3.32 | 740-LS-VS001-101-LH023-15-0 | LV1-105638.VU020 | 368 |  |  | MC1 | LVL 5 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-06-10 | 2024-06-12 | Büro | 2024-06-28 |  | 2024-06-14 | 2024-10-04 |  |  | 2024-10-10 | 926 | 150 |  |  | 2024-10-24 | 149 | SEP | SEP
47672 | 740-LS-VS020-101-LH023-15-0 | 1 | true | 4.37 | 740-LS-VS020-101-LH023-15-0 | LV1-105638.VU020 | 368 |  |  | MC1 | LVL 5 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-06-10 | 2024-06-17 | Büro | 2024-06-28 |  | 2024-06-19 | 2024-10-04 |  |  | 2024-10-09 | 926 | 150 |  |  | 2024-10-09 | 149 | SEP | SEP
47673 | 740-LS-VU020-114-LH023-25-0 | 1 | true | 4.39 | 740-LS-VU020-114-LH023-25-0 | LV1-105638.VU020 | 368 |  |  | MC1 | LVL 5 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-06-10 | 2024-06-11 | Büro | 2024-06-28 |  | 2024-06-14 | 2024-10-04 |  |  | 2024-10-08 | 926 | 150 |  |  | 2024-10-24 | 149 | SEP | SEP
47674 | 740-LS-VU020-120-LH023-25-0 | 1 | true | 2.04 | 740-LS-VU020-120-LH023-25-0 | LV1-105638.VU020 | 368 |  |  | MC1 | LVL 5 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-06-10 | 2024-06-10 | Büro | 2024-06-28 |  | 2024-06-10 | 2024-10-07 |  |  | 2024-10-09 | 926 | 150 |  |  | 2024-10-24 | 149 | SEP | SEP
47675 | 740-LS-VU020-121-LH023-15-0 | 1 | true | 2.66 | 740-LS-VU020-121-LH023-15-0 | LV1-105638.VU020 | 368 |  |  | MC1 | LVL 5 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-06-10 | 2024-06-12 | Büro | 2024-06-28 |  | 2024-06-14 |  |  |  | 2024-10-16 | 926 | 150 |  |  | 2024-10-24 | 149 | SEP | SEP
47676 | 740-LS-VU020-122-LH099-15-0 | 1 | true | 0.83 | 740-LS-VU020-122-LH099-15-0 | LV1-105638.VU020 | 386 |  |  | MC1 | LVL 5 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-06-12 | 2024-06-12 | Büro | 2024-06-28 |  | 2024-06-14 |  |  |  | 2024-10-16 | 926 | 150 |  |  | 2024-10-24 | 149 | SEP | SEP
47677 | 740-LS-VU020-123-LH099-15-0 | 1 | true | 3.97 | 740-LS-VU020-123-LH099-15-0 | LV1-105638.VU020 | 386 |  |  | MC1 | LVL 5 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-06-12 | 2024-06-13 | Büro | 2024-06-28 |  | 2024-06-19 |  |  |  | 2024-10-15 | 926 | 150 |  |  | 2024-10-24 | 149 | SEP | SEP
47678 | 740-LS-VU020-124-LH099-15-0 | 1 | true | 0.06 | 740-LS-VU020-124-LH099-15-0 | LV1-105638.VU020 | 386 |  |  | MC1 | LVL 5 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-06-11 | 2024-06-12 | Büro | 2024-06-28 |  | 2024-06-14 |  |  |  | 2024-10-15 | 926 | 150 |  |  | 2024-10-24 | 149 | SEP | SEP
47679 | 740-LS-VU020-125-LH099-15-0 | 1 | true | 0.06 | 740-LS-VU020-125-LH099-15-0 | LV1-105638.VU020 | 386 |  |  | MC1 | LVL 5 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-06-11 | 2024-06-12 | Büro | 2024-06-28 |  | 2024-06-14 |  |  |  | 2024-10-15 | 926 | 150 |  |  | 2024-10-24 | 149 | SEP | SEP
47680 | 740-LS-VU020-127-LH023-25-0 | 1 | true | 6.08 | 740-LS-VU020-127-LH023-25-0 | LV1-105638.VU020 | 368 |  |  | MC1 | LVL 5 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-06-10 | 2024-06-11 |  | 2024-06-28 |  | 2024-06-14 | 2024-07-23 |  |  | 2024-07-30 | 926 | 150 |  |  | 2024-08-28 | 149 | SEP | SEP
47681 | 740-LS-VU020-128-LH099-15-0 | 1 | true | 0.11 | 740-LS-VU020-128-LH099-15-0 | LV1-105638.VU020 | 386 |  |  | MC1 | LVL 5 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-06-11 | 2024-06-12 | Büro | 2024-06-28 |  | 2024-06-14 | 2024-10-01 |  |  | 2024-10-07 | 926 | 150 |  |  | 2024-10-07 | 149 | SEP | SEP
47682 | 740-LS-VU020-129-LH099-15-0 | 1 | true | 4.59 | 740-LS-VU020-129-LH099-15-0 | LV1-105638.VU020 | 386 |  |  | MC1 | LVL 5 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-06-12 | 2024-06-12 | Büro | 2024-06-28 |  | 2024-06-14 |  |  |  | 2024-10-04 | 926 | 150 |  |  | 2024-10-24 | 149 | SEP | SEP
47683 | 740-LS-VU020-130-LH023-25-0 | 1 | true | 20.66 | 740-LS-VU020-130-LH023-25-0 | LV1-105638.VU020 | 368 |  |  | MC1 | LVL 5 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-06-10 | 2024-06-11 | Büro | 2024-06-28 |  | 2024-06-14 | 2024-07-23 |  |  | 2024-09-20 | 926 | 150 |  |  | 2024-09-25 | 149 | SEP | SEP
47684 | 740-LS-VU020-131-LH099-15-0 | 1 | true | 4.37 | 740-LS-VU020-131-LH099-15-0 | LV1-105638.VU020 | 386 |  |  | MC1 | LVL 5 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-06-12 | 2024-06-13 | Büro | 2024-06-28 |  | 2024-06-14 |  |  |  | 2024-10-12 | 926 | 150 |  |  | 2024-10-24 | 149 | SEP | SEP
47685 | 740-LS-VU020-132-LH099-15-0 | 1 | true | 0.51 | 740-LS-VU020-132-LH099-15-0 | LV1-105638.VU020 | 386 |  |  | MC1 | LVL 5 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-06-12 | 2024-06-12 | Büro | 2024-06-28 |  | 2024-06-14 | 2024-10-01 |  |  | 2024-10-07 | 926 | 150 |  |  | 2024-10-07 | 149 | SEP | SEP
47686 | 740-LS-VU020-133-LH099-15-0 | 1 | true | 0.3 | 740-LS-VU020-133-LH099-15-0 | LV1-105638.VU020 | 386 |  |  | MC1 | LVL 5 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-06-12 | 2024-06-13 | Büro | 2024-06-28 |  | 2024-06-17 | 2024-10-01 |  |  | 2024-10-07 | 926 | 150 |  |  | 2024-10-07 | 149 | SEP | SEP
47687 | 740-LS-VU020-134-LH099-15-0 | 1 | true | 0.9 | 740-LS-VU020-134-LH099-15-0 | LV1-105638.VU020 | 386 |  |  | MC1 | LVL 5 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-06-12 | 2024-06-13 | Büro | 2024-06-28 |  | 2024-06-17 | 2024-09-30 |  |  | 2024-10-07 | 926 | 150 |  |  |  | 149 | SEP | SEP
47688 | 740-LS-VU020-135-LH099-15-0 | 1 | true | 1.82 | 740-LS-VU020-135-LH099-15-0 | LV1-105638.VU020 | 386 |  |  | MC1 | LVL 5 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-06-12 | 2024-06-12 | Büro | 2024-06-28 |  | 2024-06-14 | 2024-09-27 |  |  | 2024-09-30 | 926 | 150 |  |  | 2024-10-01 | 149 | SEP | SEP
47689 | 740-LS-VU020-136-LH099-15-0 | 1 | true | 2.22 | 740-LS-VU020-136-LH099-15-0 | LV1-105638.VU020 | 386 |  |  | MC1 | LVL 5 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-06-12 | 2024-06-12 | Büro | 2024-06-28 |  | 2024-06-14 | 2024-09-27 |  |  | 2024-09-30 | 926 | 150 |  |  | 2024-10-01 | 149 | SEP | SEP
47690 | 740-MKWE-R-VU241-142-LH001-20-0 | 1 | true | 3.16 | 740-MKWE-R-VU241-142-LH001-20-0 | LV1-105638.VU241 | 363 | 31.May.2024 |  | MC1 | LVL 6 | K51 | TR012 | 2024-04-04 | 2024-04-09 | 2024-04-12 |  | 2024-05-16 | 2024-05-16 | Attila Henter | 2024-05-31 |  | 2024-05-17 | 2024-07-15 |  |  | 2024-07-19 | 803 | 150 |  | 2024-08-21 | 2024-08-05 | 149 | SEP | SEP | 2024-08-19 | 2024-09-20 | 2024-09-20 | 2024-09-20 | 2024-10-15 | 2024-10-15
47691 | 740-MKWE-R-VU311-144-LH001-20-0 | 1 | true | 6.52 | 740-MKWE-R-VU311-144-LH001-20-0 | LV1-105638.VU311 | 363 | 31.May.2024 |  | MC1 | LVL 6 | K51 | TR012 | 2024-04-04 | 2024-04-09 | 2024-04-12 |  | 2024-05-16 | 2024-05-20 | Attila Henter | 2024-05-31 |  | 2024-05-23 | 2024-07-15 |  |  | 2024-07-19 | 803 | 150 |  | 2024-08-28 | 2024-08-05 | 149 | SEP | SEP
47692 | 740-MKWE-S-VU241-141-LH001-20-0 | 1 | true | 3.25 | 740-MKWE-S-VU241-141-LH001-20-0 | LV1-105638.VU241 | 363 | 31.May.2024 |  | MC1 | LVL 6 | K51 | TR012 | 2024-04-04 | 2024-04-09 | 2024-04-12 |  | 2024-05-16 | 2024-05-16 | Attila Henter | 2024-05-31 |  | 2024-05-17 | 2024-07-15 |  |  | 2024-07-19 | 803 | 150 |  | 2024-08-21 | 2024-08-05 | 149 | SEP | SEP | 2024-08-19 | 2024-09-20 | 2024-09-20 | 2024-09-20 | 2024-10-15 | 2024-10-15
47693 | 740-MKWE-S-VU311-143-LH001-20-0 | 1 | true | 7.71 | 740-MKWE-S-VU311-143-LH001-20-0 | LV1-105638.VU311 | 363 | 31.May.2024 |  | MC1 | LVL 6 | K51 | TR012 | 2024-04-04 | 2024-04-09 | 2024-04-12 |  | 2024-05-16 | 2024-05-17 | Attila Henter | 2024-05-31 |  | 2024-05-23 | 2024-07-15 |  |  | 2024-07-19 | 803 | 150 |  | 2024-08-28 | 2024-08-05 | 149 | SEP | SEP
47694 | 740-MKWP-R-VS020-101-LH001-20-0 | 1 | true | 2.49 | 740-MKWP-R-VS020-101-LH001-20-0 | LV1-105633.VS020 | 363 | 31.May.2024 |  | MC1 | LVL 5 | T60 | TR012 | 2024-04-04 | 2024-04-09 | 2024-04-12 |  | 2024-05-16 | 2024-05-20 | Büro | 2024-05-31 |  | 2024-05-21 |  |  |  | 2024-10-17 | 860 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
47695 | 740-MKWP-R-VU231-124-LH001-40-0 | 1 | false | 25.56 | 740-MKWP-R-VU231-124-LH001-40-0 | LV1-105638.VU231 | 363 | 10.May.2024 |  | MC1 | LVL 5 | T60 | TR012 | 2024-04-04 | 2024-04-09 | 2024-04-12 |  | 2024-04-20 | 2024-04-25 | Büro | 2024-05-17 |  | 2024-04-25 | 2024-05-24 |  |  | 2024-05-28 | 828 | 150 |  |  |  | 149 | SEP | SEP
52270 | 740-MKWP-R-VU231-124-LH001-40-0 | 2 | true | 25.56 | 740-MKWP-R-VU231-124-LH001-40-0 | LV1-105638.VU231 | 363 |  |  | MC1 | LVL 5 | T60 | TR021_1 | 2024-06-04 | 2024-04-09 | 2024-04-12 |  | 2024-04-20 | 2024-04-25 |  | 2024-05-17 |  | 2024-04-25 | 2024-05-24 |  |  | 2024-05-28 | 828 | 150 |  | 2024-10-02 | 2024-09-09 | 149 | SEP | SEP | 2024-07-23 | 2024-09-02 | 2024-09-02 | 2024-09-02
47696 | 740-MKWP-R-VU231-125-LH099-15-0 | 1 | true | 1.78 | 740-MKWP-R-VU231-125-LH099-15-0 | LV1-105638.VU231 | 386 | 31.May.2024 |  | MC1 | LVL 5 | Tt-6 | TR012 | 2024-04-04 | 2024-04-09 | 2024-04-12 |  | 2024-05-16 | 2024-05-16 | Büro | 2024-05-31 |  | 2024-05-17 | 2024-09-11 |  |  | 2024-09-26 | 860 | 150 |  | 2024-10-02 | 2024-09-27 | 149 | SEP | SEP | 2024-10-01 |  | 2024-11-01 | 2024-11-01
47697 | 740-MKWP-R-VU231-126-LH001-20-0 | 1 | true | 0.18 | 740-MKWP-R-VU231-126-LH001-20-0 | LV1-105638.VU231 | 363 | 31.May.2024 |  | MC1 | LVL 5 | T60 | TR012 | 2024-04-04 | 2024-04-09 | 2024-04-12 |  | 2024-05-16 | 2024-05-20 | Büro | 2024-05-31 |  | 2024-05-23 | 2024-07-01 |  |  | 2024-07-02 | 860 | 150 |  | 2024-10-02 | 2024-07-03 | 149 | SEP | SEP | 2024-10-01 |  | 2024-11-01 | 2024-11-01
47698 | 740-MKWP-R-VU231-230-LH001-40-0 | 1 | true | 14.12 | 740-MKWP-R-VU231-230-LH001-40-0 | LV1-105639.VU231 | 363 | 17.May.2024 |  | MC1 | LVL 5 | T60 | TR012 | 2024-04-04 | 2024-04-09 | 2024-04-12 |  | 2024-04-30 | 2024-05-13 | Büro | 2024-05-17 |  | 2024-05-13 | 2024-05-28 |  |  | 2024-06-10 | 860 | 150 | Lvl 6 Decke | 2024-07-24 | 2024-07-15 | 149 | SEP | SEP | 2024-07-23 | 2024-10-14 | 2024-10-14 | 2024-10-14
47699 | 740-MKWP-R-VU231-240-LH099-25-0 | 1 | false | 1.69 | 740-MKWP-R-VU231-240-LH099-25-0 | LV1-105639.VU231 | 386 |  | true | MC1 | LVL 5 | Tt-6 | TR012 | 2024-04-04 | 2024-04-09 | [12 empty] | 860 | 150 |  |  |  | 149 | SEP | SEP
49660 | 740-MKWP-R-VU231-240-LH099-25-0 | 2 | true | 1.69 | 740-MKWP-R-VU231-240-LH099-25-0 | LV1-105639.VU231 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR014_1 | 2024-04-22 | 2024-04-29 | 2024-04-29 |  | 2024-06-25 |  | Büro | 2024-07-12 |  | 2024-07-09 | 2024-09-11 |  |  | 2024-09-26 | 860 | 150 |  |  |  | 149 | SEP | SEP | 2024-10-01 |  | 2024-11-01 | 2024-11-01
47700 | 740-MKWP-R-VU231-241-LH099-25-0 | 1 | false | 1.69 | 740-MKWP-R-VU231-241-LH099-25-0 | LV1-105639.VU231 | 386 |  | true | MC1 | LVL 5 | Tt-6 | TR012 | 2024-04-04 | 2024-04-09 | [12 empty] | 860 | 150 |  |  |  | 149 | SEP | SEP
49661 | 740-MKWP-R-VU231-241-LH099-25-0 | 2 | true | 1.69 | 740-MKWP-R-VU231-241-LH099-25-0 | LV1-105639.VU231 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR014_1 | 2024-04-22 | 2024-04-29 | 2024-04-29 |  | 2024-06-25 |  | Büro | 2024-07-12 |  | 2024-07-09 | 2024-09-11 |  |  | 2024-09-26 | 860 | 150 |  | 2024-10-02 | 2024-09-27 | 149 | SEP | SEP | 2024-10-01 |  | 2024-11-01 | 2024-11-01
47701 | 740-MKWP-S-VS020-101-LH001-20-0 | 1 | true | 3.01 | 740-MKWP-S-VS020-101-LH001-20-0 | LV1-105633.VS020 | 363 | 31.May.2024 |  | MC1 | LVL 5 | T60 | TR012 | 2024-04-04 | 2024-04-09 | 2024-04-12 |  | 2024-05-16 | 2024-05-20 | Büro | 2024-05-31 |  | 2024-05-21 |  |  |  | 2024-10-17 | 860 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
47702 | 740-MKWP-S-VU231-105-LH001-40-0 | 1 | true | 25.03 | 740-MKWP-S-VU231-105-LH001-40-0 | LV1-105638.VU231 | 363 | 10.May.2024 |  | MC1 | LVL 5 | T60 | TR012 | 2024-04-04 | 2024-04-09 | 2024-04-12 |  | 2024-04-20 | 2024-04-24 | Büro | 2024-05-17 |  | 2024-04-24 | 2024-05-24 |  |  | 2024-06-11 | 828 | 150 |  | 2024-10-02 | 2024-07-15 | 149 | SEP | SEP | 2024-09-02 | 2024-09-02 | 2024-09-02 | 2024-10-14
47703 | 740-MKWP-S-VU231-106-LH099-15-0 | 1 | true | 1.78 | 740-MKWP-S-VU231-106-LH099-15-0 | LV1-105638.VU231 | 386 | 31.May.2024 |  | MC1 | LVL 5 | Tt-6 | TR012 | 2024-04-04 | 2024-04-09 | 2024-04-12 |  | 2024-05-15 | 2024-05-16 | Büro | 2024-05-31 |  | 2024-05-17 | 2024-09-11 |  |  | 2024-09-26 | 860 | 150 |  | 2024-10-02 | 2024-09-27 | 149 | SEP | SEP | 2024-10-01 |  | 2024-11-01 | 2024-11-01
47704 | 740-MKWP-S-VU231-107-LH001-20-0 | 1 | true | 0.32 | 740-MKWP-S-VU231-107-LH001-20-0 | LV1-105638.VU231 | 363 | 31.May.2024 |  | MC1 | LVL 5 | T60 | TR012 | 2024-04-04 | 2024-04-09 | 2024-04-12 |  | 2024-05-16 | 2024-05-20 | Büro | 2024-05-31 |  | 2024-05-21 | 2024-07-01 |  |  | 2024-07-02 | 860 | 150 |  | 2024-10-02 | 2024-07-03 | 149 | SEP | SEP | 2024-10-01 |  | 2024-11-01 | 2024-11-01
47705 | 740-MKWP-S-VU231-209-LH001-40-0 | 1 | true | 13.92 | 740-MKWP-S-VU231-209-LH001-40-0 | LV1-105639.VU231 | 363 | 17.May.2024 |  | MC1 | LVL 5 | T60 | TR012 | 2024-04-04 | 2024-04-09 | 2024-04-12 |  | 2024-04-30 | 2024-05-09 | Büro | 2024-05-17 |  | 2024-05-09 | 2024-05-28 |  |  | 2024-06-10 | 860 | 150 |  | 2024-10-02 | 2024-07-12 | 149 | SEP | SEP | 2024-07-23 | 2024-10-14 | 2024-10-14 | 2024-10-14
47706 | 740-MKWP-S-VU231-210-LH099-25-0 | 1 | false | 1.69 | 740-MKWP-S-VU231-210-LH099-25-0 | LV1-105639.VU231 | 386 |  | true | MC1 | LVL 5 | Tt-6 | TR012 | 2024-04-04 | 2024-04-09 | [12 empty] | 860 | 150 |  |  |  | 149 | SEP | SEP
49662 | 740-MKWP-S-VU231-210-LH099-25-0 | 2 | true | 1.69 | 740-MKWP-S-VU231-210-LH099-25-0 | LV1-105639.VU231 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR014_1 | 2024-04-22 | 2024-04-29 | 2024-04-29 |  | 2024-06-25 |  | Büro | 2024-07-12 |  | 2024-07-09 | 2024-09-11 |  |  | 2024-09-26 | 860 | 150 |  | 2024-10-02 |  | 149 | SEP | SEP | 2024-10-01 |  | 2024-11-01 | 2024-11-01
47707 | 740-MKWP-S-VU231-211-LH099-25-0 | 1 | false | 1.69 | 740-MKWP-S-VU231-211-LH099-25-0 | LV1-105639.VU231 | 386 |  | true | MC1 | LVL 5 | Tt-6 | TR012 | 2024-04-04 | 2024-04-09 | [12 empty] | 860 | 150 |  |  |  | 149 | SEP | SEP
49663 | 740-MKWP-S-VU231-211-LH099-25-0 | 2 | true | 1.69 | 740-MKWP-S-VU231-211-LH099-25-0 | LV1-105639.VU231 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR014_1 | 2024-04-22 | 2024-04-29 | 2024-04-29 |  | 2024-06-25 |  | Büro | 2024-07-12 |  | 2024-07-09 | 2024-09-11 |  |  | 2024-09-26 | 860 | 150 |  | 2024-10-02 | 2024-09-27 | 149 | SEP | SEP | 2024-10-01 |  | 2024-11-01 | 2024-11-01
47708 | 740-N2-VP001-101-LH099-20-0 | 1 | true | 8.85 | 740-N2-VP001-101-LH099-20-0 | LV1-105638.VU060 | 386 | 14.May.2024 |  | MC1 | LVL 5 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-04-26 | 2024-04-30 | Büro | 2024-05-17 |  | 2024-04-30 | 2024-09-04 |  |  | 2024-09-06 | 930 | 150 |  | 2024-11-13 |  | 149 | SEP | SEP
47709 | 740-N2-VP002-101-LH099-20-0 | 1 | true | 7.42 | 740-N2-VP002-101-LH099-20-0 | LV1-105638.VU060 | 386 | 14.May.2024 |  | MC1 | LVL 5 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-04-26 | 2024-04-30 | Büro | 2024-05-17 |  | 2024-04-30 | 2024-09-04 |  |  | 2024-09-10 | 930 | 150 |  |  | 2024-09-12 | 149 | SEP | SEP
47710 | 740-N2-VP003-101-LH099-15-0 | 1 | true | 8.21 | 740-N2-VP003-101-LH099-15-0 | LV1-105638.VU060 | 386 |  |  | MC1 | LVL 5 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-06-10 | 2024-06-12 | Büro | 2024-06-28 |  | 2024-06-14 | 2024-09-03 |  |  | 2024-09-05 | 930 | 150 |  |  | 2024-09-09 | 149 | SEP | SEP
47711 | 740-N2-VP004-101-LH099-15-0 | 1 | true | 9.58 | 740-N2-VP004-101-LH099-15-0 | LV1-105638.VU060 | 386 |  |  | MC1 | LVL 5 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-06-10 | 2024-06-13 | Büro | 2024-06-28 |  | 2024-06-14 | 2024-09-03 |  |  | 2024-09-05 | 930 | 150 |  | 2024-11-13 | 2024-09-09 | 149 | SEP | SEP
47712 | 740-N2-VP031-101-LH099-20-0 | 1 | false | 15.78 | 740-N2-VP031-101-LH099-20-0 | LV1-105638.VU060 | 386 | 14.May.2024 |  | MC1 | LVL 5 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-04-26 | 2024-04-30 |  |  |  | 2024-04-30 |  |  |  |  | 930 | 150 |  |  |  | 149 | SEP | SEP
49664 | 740-N2-VP031-101-LH099-20-0 | 2 | true | 15.78 | 740-N2-VP031-101-LH099-20-0 | LV1-105638.VU060 | 386 |  |  | MC1 | LVL 5 | N/A | TR014_1 | 2024-04-22 | 2024-04-29 | 2024-04-29 |  | 2024-04-26 | 2024-04-30 | Büro | 2024-05-17 |  | 2024-04-30 | 2024-07-02 |  | 2024-07-05 | 2024-10-30 | 930 | 150 |  |  | 2024-11-04 | 149 | SEP | SEP
47713 | 740-N2-VP032-101-LH099-32-0 | 1 | false | 3.1 | 740-N2-VP032-101-LH099-32-0 | LV1-105638.VU060 | 386 |  |  | MC1 | LVL 5 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 | [11 empty] | 930 | 150 |  |  |  | 149 | SEP | SEP
49665 | 740-N2-VP032-101-LH099-32-0 | 2 | true | 3.1 | 740-N2-VP032-101-LH099-32-0 | LV1-105638.VU060 | 386 |  |  | MC1 | LVL 5 | N/A | TR014_1 | 2024-04-22 | 2024-04-29 | 2024-04-29 |  | 2024-06-12 | 2024-06-14 | Büro | 2024-06-28 |  | 2024-06-17 | 2024-10-09 |  |  | 2024-10-10 | 930 | 150 |  | 2024-11-18 | 2024-11-12 | 149 | SEP | SEP
47714 | 740-N2-VP033-101-LH099-32-0 | 1 | false | 6.25 | 740-N2-VP033-101-LH099-32-0 | LV1-105638.VU060 | 386 |  |  | MC1 | LVL 5 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 | [11 empty] | 930 | 150 |  |  |  | 149 | SEP | SEP
49666 | 740-N2-VP033-101-LH099-32-0 | 2 | true | 6.25 | 740-N2-VP033-101-LH099-32-0 | LV1-105638.VU060 | 386 |  |  | MC1 | LVL 5 | N/A | TR014_1 | 2024-04-22 | 2024-04-29 | 2024-04-29 |  | 2024-06-12 | 2024-06-14 | Büro | 2024-06-28 |  | 2024-06-18 | 2024-07-23 |  | 2024-07-26 | 2024-09-25 | 930 | 150 |  | 2024-11-18 | 2024-11-13 | 149 | SEP | SEP
47715 | 740-N2-VP041-101-LH099-20-0 | 1 | false | 12.01 | 740-N2-VP041-101-LH099-20-0 | LV1-105638.VU060 | 386 | 14.May.2024 |  | MC1 | LVL 5 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-04-26 | 2024-04-30 |  |  |  | 2024-04-30 |  |  |  |  | 930 | 150 |  |  |  | 149 | SEP | SEP
49667 | 740-N2-VP041-101-LH099-20-0 | 2 | true | 12.01 | 740-N2-VP041-101-LH099-20-0 | LV1-105638.VU060 | 386 |  |  | MC1 | LVL 5 | N/A | TR014_1 | 2024-04-22 | 2024-04-29 | 2024-04-29 |  | 2024-04-26 | 2024-04-30 | Büro | 2024-05-17 |  | 2024-04-30 | 2024-07-02 |  | 2024-07-05 | 2024-10-30 | 930 | 150 |  |  | 2024-10-31 | 149 | SEP | SEP
47716 | 740-N2-VP042-101-LH099-32-0 | 1 | false | 1.99 | 740-N2-VP042-101-LH099-32-0 | LV1-105638.VU060 | 386 |  |  | MC1 | LVL 5 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-04-20 | 2024-04-24 |  |  |  | 2024-04-25 |  |  |  |  | 930 | 150 |  |  |  | 149 | SEP | SEP
49668 | 740-N2-VP042-101-LH099-32-0 | 2 | true | 1.99 | 740-N2-VP042-101-LH099-32-0 | LV1-105638.VU060 | 386 |  |  | MC1 | LVL 5 | N/A | TR014_1 | 2024-04-22 | 2024-04-29 | 2024-04-29 |  | 2024-06-12 | 2024-06-13 | Büro | 2024-06-28 |  | 2024-06-14 |  |  |  | 2024-10-10 | 930 | 150 |  |  |  | 149 | SEP | SEP
47717 | 740-N2-VP043-101-LH099-32-0 | 1 | true | 8.69 | 740-N2-VP043-101-LH099-32-0 | LV1-105638.VU060 | 386 | 14.May.2024 |  | MC1 | LVL 5 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-04-26 | 2024-04-30 | Büro | 2024-05-17 |  | 2024-04-30 | 2024-07-01 |  | 2024-07-11 | 2024-10-30 | 930 | 150 |  | 2024-11-18 |  | 149 | SEP | SEP
47718 | 740-N2-VP130-101-LH099-20-0 | 1 | false | 9.51 | 740-N2-VP130-101-LH099-20-0 | LV1-105638.VU060 | 386 |  |  | MC1 | LVL 5 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 | [11 empty] | 930 | 150 |  |  |  | 149 | SEP | SEP
49669 | 740-N2-VP130-101-LH099-20-0 | 2 | true | 9.51 | 740-N2-VP130-101-LH099-20-0 | LV1-105638.VU060 | 386 |  |  | MC1 | LVL 5 | N/A | TR014_1 | 2024-04-22 | 2024-04-29 | 2024-04-29 |  | 2024-06-12 | 2024-06-13 | Büro | 2024-06-28 |  | 2024-06-20 | 2024-09-23 |  | 2024-08-07 | 2024-09-25 | 930 | 150 |  |  |  | 149 | SEP | SEP
47719 | 740-N2-VP131-101-LH099-15-0 | 1 | true | 15.45 | 740-N2-VP131-101-LH099-15-0 | LV1-105638.VU060 | 386 |  |  | MC1 | LVL 5 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-06-10 | 2024-06-12 | Büro | 2024-06-28 |  | 2024-06-12 | 2024-08-05 |  | 2024-08-07 | 2024-10-28 | 930 | 150 |  |  |  | 149 | SEP | SEP
47720 | 740-N2-VP132-101-LH099-15-0 | 1 | true | 5.72 | 740-N2-VP132-101-LH099-15-0 | LV1-105638.VU060 | 386 |  |  | MC1 | LVL 5 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-06-10 | 2024-06-12 | Büro | 2024-06-28 |  | 2024-06-12 | 2024-08-05 |  | 2024-08-07 | 2024-10-30 | 930 | 150 |  |  |  | 149 | SEP | SEP
47721 | 740-N2-VP133-101-LH099-15-0 | 1 | true | 13.09 | 740-N2-VP133-101-LH099-15-0 | LV1-105638.VU060 | 386 |  |  | MC1 | LVL 5 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-06-10 | 2024-06-12 | Büro | 2024-06-28 |  | 2024-06-14 | 2024-08-05 |  | 2024-08-07 | 2024-10-28 | 930 | 150 |  |  | 2024-10-30 | 149 | SEP | SEP
47722 | 740-N2-VP134-131-LH099-15-0 | 1 | true | 5.9 | 740-N2-VP134-131-LH099-15-0 | LV1-105638.VU060 | 386 |  |  | MC1 | LVL 5 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-06-10 | 2024-06-12 | Büro | 2024-06-28 |  | 2024-06-14 | 2024-08-05 |  | 2024-08-07 | 2024-10-30 | 930 | 150 |  |  |  | 149 | SEP | SEP
47723 | 740-N2-VP137-101-LH099-15-0 | 1 | true | 8.48 | 740-N2-VP137-101-LH099-15-0 | LV1-105638.VU060 | 386 |  |  | MC1 | LVL 5 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-06-10 | 2024-06-12 | Büro | 2024-06-28 |  | 2024-06-18 | 2024-09-23 |  | 2024-08-07 | 2024-09-25 | 930 | 150 |  |  |  | 149 | SEP | SEP
47724 | 740-N2-VP140-101-LH099-20-0 | 1 | false | 8.91 | 740-N2-VP140-101-LH099-20-0 | LV1-105638.VU060 | 386 |  |  | MC1 | LVL 5 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 | [11 empty] | 930 | 150 |  |  |  | 149 | SEP | SEP
49670 | 740-N2-VP140-101-LH099-20-0 | 2 | true | 8.91 | 740-N2-VP140-101-LH099-20-0 | LV1-105638.VU060 | 386 |  |  | MC1 | LVL 5 | N/A | TR014_1 | 2024-04-22 | 2024-04-29 | 2024-04-29 |  | 2024-06-12 | 2024-06-13 | Büro | 2024-06-28 |  | 2024-06-18 |  |  |  | 2024-09-21 | 930 | 150 |  |  | 2024-09-27 | 149 | SEP | SEP
47725 | 740-N2-VP141-101-LH099-15-0 | 1 | true | 2.1 | 740-N2-VP141-101-LH099-15-0 | LV1-105638.VU060 | 386 |  |  | MC1 | LVL 5 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-06-10 | 2024-06-12 | Büro | 2024-06-28 |  | 2024-06-14 | 2024-09-18 |  |  | 2024-09-19 | 930 | 150 |  |  |  | 149 | SEP | SEP
47726 | 740-N2-VP142-101-LH099-15-0 | 1 | true | 0.28 | 740-N2-VP142-101-LH099-15-0 | LV1-105638.VU060 | 386 |  |  | MC1 | LVL 5 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-06-10 | 2024-06-12 | Büro | 2024-06-28 |  | 2024-06-14 | 2024-09-12 |  |  | 2024-09-16 | 930 | 150 |  |  | 2024-09-17 | 149 | SEP | SEP
47727 | 740-N2-VP143-101-LH099-15-0 | 1 | true | 4.73 | 740-N2-VP143-101-LH099-15-0 | LV1-105638.VU060 | 386 |  |  | MC1 | LVL 5 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-06-10 | 2024-06-12 | Büro | 2024-06-28 |  | 2024-06-14 | 2024-09-07 |  |  | 2024-09-16 | 930 | 150 |  |  |  | 149 | SEP | SEP
47728 | 740-N2-VP144-131-LH099-15-0 | 1 | true | 0.11 | 740-N2-VP144-131-LH099-15-0 | LV1-105638.VU060 | 386 |  |  | MC1 | LVL 5 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-06-10 | 2024-06-12 | Büro | 2024-06-28 |  | 2024-06-14 |  |  |  | 2024-09-16 | 930 | 150 |  |  | 2024-09-17 | 149 | SEP | SEP
47729 | 740-N2-VP147-101-LH099-15-0 | 1 | true | 7.31 | 740-N2-VP147-101-LH099-15-0 | LV1-105638.VU060 | 386 |  |  | MC1 | LVL 5 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-06-10 | 2024-06-12 | Büro | 2024-06-28 |  | 2024-06-14 |  |  |  | 2024-09-21 | 930 | 150 |  |  | 2024-09-27 | 149 | SEP | SEP
47730 | 740-N2-VU060-112-LH099-40-0 | 1 | true | 4.59 | 740-N2-VU060-112-LH099-40-0 | LV1-105638.VU060 | 386 | 14.May.2024 |  | MC1 | LVL 5 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-04-27 | 2024-04-30 | Büro | 2024-05-17 |  | 2024-04-30 | 2024-06-12 |  |  | 2024-06-14 | 930 | 150 |  |  | 2024-08-27 | 149 | SEP | SEP
47731 | 740-N2-VU060-119-LH099-50-0 | 1 | true | 8.69 | 740-N2-VU060-119-LH099-50-0 | LV1-105638.VU060 | 386 | 14.May.2024 |  | MC1 | LVL 5 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-04-25 | 2024-04-27 | Büro | 2024-05-17 |  | 2024-04-29 | 2024-06-20 |  |  | 2024-06-25 | 930 | 150 |  |  | 2024-08-27 | 149 | SEP | SEP
47732 | 740-N2-VU060-120-LH099-50-0 | 1 | true | 6.48 | 740-N2-VU060-120-LH099-50-0 | LV1-105638.VU060 | 386 | 14.May.2024 |  | MC1 | LVL 5 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-04-25 | 2024-04-30 | Büro | 2024-05-17 |  | 2024-04-30 | 2024-06-20 |  |  | 2024-06-25 | 930 | 150 |  |  | 2024-08-27 | 149 | SEP | SEP
47733 | 740-N2-VU060-125-LH099-40-0 | 1 | true | 5.96 | 740-N2-VU060-125-LH099-40-0 | LV1-105638.VU060 | 386 | 14.May.2024 |  | MC1 | LVL 5 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-04-25 | 2024-04-30 | Büro | 2024-05-17 |  | 2024-04-30 | 2024-06-12 | 2024-06-18 |  | 2024-08-22 | 930 | 150 |  |  | 2024-08-27 | 149 | SEP | SEP
47734 | 740-N2-VU060-126-LH099-25-0 | 1 | true | 8.5 | 740-N2-VU060-126-LH099-25-0 | LV1-105638.VU060 | 386 | 14.May.2024 |  | MC1 | LVL 5 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-04-27 | 2024-05-09 | Büro | 2024-05-17 |  | 2024-05-14 |  |  |  | 2024-09-16 | 930 | 150 |  |  | 2024-09-09 | 149 | SEP | SEP
47735 | 740-N2-VU060-127-LH099-25-0 | 1 | true | 0.07 | 740-N2-VU060-127-LH099-25-0 | LV1-105638.VU060 | 386 |  |  | MC1 | LVL 5 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-06-12 | 2024-06-12 | Büro | 2024-06-28 |  | 2024-06-14 |  |  |  | 2024-09-16 | 930 | 150 |  |  | 2024-09-17 | 149 | SEP | SEP
47736 | 740-N2-VU060-135-LH099-40-0 | 1 | false | 9.91 | 740-N2-VU060-135-LH099-40-0 | LV1-105638.VU060 | 386 | 14.May.2024 |  | MC1 | LVL 5 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 | [11 empty] | 930 | 150 |  |  |  | 149 | SEP | SEP
49508 | 740-N2-VU060-135-LH099-40-0 | 2 | true | 9.91 | 740-N2-VU060-135-LH099-40-0 | LV1-105638.VU060 | 386 | 14.May.2024 |  | MC1 | LVL 5 | N/A | TR013_2 | 2024-04-21 | 2024-04-23 | 2024-04-23 |  | 2024-04-29 | 2024-05-09 | Büro | 2024-05-17 |  | 2024-05-09 | 2024-06-12 | 2024-06-18 |  | 2024-08-21 | 930 | 150 |  |  | 2024-08-27 | 149 | SEP | SEP
47737 | 740-WAKont-VU190-101-LH032-100-0 | 1 | true | 46.48 | 740-WAKont-VU190-101-LH032-100-0 | LV1-105638.VU190 | 385 | 10.May.2024 |  | MC1 | LVL 4 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-05-09 | 2024-05-13 | Büro | 2024-05-17 |  | 2024-05-14 | 2024-05-24 |  | 2024-05-28 | 2024-08-24 | 931 | 150 |  |  | 2024-09-09 | 149 | SEP | SEP
47738 | 740-WAKont-VU190-104-LH032-65-0 | 1 | true | 6.31 | 740-WAKont-VU190-104-LH032-65-0 | LV1-105638.VU190 | 385 |  |  | MC1 | LVL 4 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-06-07 | 2024-06-11 | Büro | 2024-06-28 |  | 2024-06-14 | 2024-07-19 |  |  | 2024-10-22 | 931 | 150 |  |  | 2024-11-05 | 149 | SEP | SEP
47739 | 740-WAKont-VU190-105-LH032-65-0 | 1 | true | 11.67 | 740-WAKont-VU190-105-LH032-65-0 | LV1-105638.VU190 | 385 | 10.May.2024 |  | MC1 | LVL 4 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-04-29 | 2024-05-09 | Büro | 2024-05-17 |  | 2024-05-14 | 2024-06-10 |  | 2024-06-12 | 2024-10-22 | 931 | 150 |  |  | 2024-11-05 | 149 | SEP | SEP
47740 | 740-WAKont-VU190-109-LH032-80-0 | 1 | true | 16.66 | 740-WAKont-VU190-109-LH032-80-0 | LV1-105638.VU190 | 385 | 10.May.2024 |  | MC1 | LVL 4 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-05-07 | 2024-05-11 | Büro | 2024-05-17 |  | 2024-05-14 | 2024-05-29 |  |  | 2024-06-12 | 931 | 150 |  |  | 2024-09-11 | 149 | SEP | SEP
47741 | 740-WAKont-VU190-113-LH032-65-0 | 1 | true | 2.04 | 740-WAKont-VU190-113-LH032-65-0 | LV1-105638.VU190 | 385 |  |  | MC1 | LVL 4 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-06-07 | 2024-06-12 | Attila Henter | 2024-06-28 |  | 2024-06-12 | 2024-07-17 |  |  | 2024-07-30 | 931 | 150 |  |  | 2024-09-23 | 149 | SEP | SEP
47742 | 740-WAKont-VU190-116-LH032-65-0 | 1 | true | 12.04 | 740-WAKont-VU190-116-LH032-65-0 | LV1-105638.VU190 | 385 |  |  | MC1 | LVL 4 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-06-07 | 2024-06-12 | Büro | 2024-06-28 |  | 2024-06-12 |  |  | 2024-07-19 | 2024-10-22 | 931 | 150 |  |  | 2024-11-05 | 149 | SEP | SEP
47743 | 740-WAKont-VU190-117-LH032-65-0 | 1 | true | 2.95 | 740-WAKont-VU190-117-LH032-65-0 | LV1-105638.VU190 | 385 | 10.May.2024 |  | MC1 | LVL 4 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-04-23 | 2024-04-24 | Büro | 2024-05-17 |  | 2024-04-24 | 2024-06-10 |  | 2024-06-12 | 2024-10-22 | 931 | 150 |  |  | 2024-11-05 | 149 | SEP | SEP
47744 | 740-WAKont-VU190-118-LH032-32-0 | 1 | true | 7.82 | 740-WAKont-VU190-118-LH032-32-0 | LV1-105638.VU190 | 385 | 10.May.2024 |  | MC1 | LVL 4 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-04-23 | 2024-04-25 | Büro | 2024-05-17 |  | 2024-04-25 | 2024-06-12 |  |  | 2024-06-13 | 931 | 150 |  |  | 2024-09-19 | 149 | SEP | SEP
47745 | 740-WAKont-VU190-119-LH099-32-0 | 1 | false | 0.62 | 740-WAKont-VU190-119-LH099-32-0 | LV1-105638.VU190 | 386 |  |  | MC1 | LVL 4 | Tt-6 | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 | [11 empty] | 932 | 150 |  |  |  | 149 | SEP | SEP
51941 | 740-WAKont-VU190-119-LH099-32-0 | 2 | true | 0.62 | 740-WAKont-VU190-119-LH099-32-0 | LV1-105638.VU190 | 386 |  |  | MC1 | LVL 4 | Tt-6 | TR019_1 | 2024-05-22 | 2024-04-17 | 2024-05-23 |  | 2024-06-10 | 2024-06-12 |  | 2024-06-28 |  | 2024-06-12 | 2024-10-16 |  |  | 2024-10-21 | 932 | 150 |  |  | 2024-10-30 | 149 | SEP | SEP
47746 | 740-WAKont-VU190-120-LH099-32-0 | 1 | false | 0.62 | 740-WAKont-VU190-120-LH099-32-0 | LV1-105638.VU190 | 386 |  |  | MC1 | LVL 4 | Tt-6 | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 | [11 empty] | 932 | 150 |  |  |  | 149 | SEP | SEP
51942 | 740-WAKont-VU190-120-LH099-32-0 | 2 | true | 0.62 | 740-WAKont-VU190-120-LH099-32-0 | LV1-105638.VU190 | 386 |  |  | MC1 | LVL 4 | Tt-6 | TR019_1 | 2024-05-22 | 2024-04-17 | 2024-05-23 |  | 2024-06-10 | 2024-06-12 | Büro | 2024-06-28 |  | 2024-06-12 | 2024-10-14 |  |  | 2024-10-16 | 932 | 150 |  |  |  | 149 | SEP | SEP
47747 | 740-WAKont-VU190-121-LH032-32-0 | 1 | true | 7.01 | 740-WAKont-VU190-121-LH032-32-0 | LV1-105638.VU190 | 385 | 10.May.2024 |  | MC1 | LVL 4 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-04-23 | 2024-04-25 | Büro | 2024-05-17 |  | 2024-04-25 | 2024-06-12 |  |  | 2024-06-13 | 931 | 150 |  |  | 2024-09-19 | 149 | SEP | SEP
47748 | 740-WAKont-VU190-202-LH032-100-0 | 1 | false | 35.15 | 740-WAKont-VU190-202-LH032-100-0 | LV1-105639.VU190 | 385 | 10.May.2024 |  | MC1 | LVL 4 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-05-08 | 2024-05-13 | Attila Henter | 2024-05-17 |  | 2024-05-14 | 2024-05-24 |  | 2024-05-29 |  | 933 | 150 |  |  |  | 149 | SEP | SEP
52278 | 740-WAKont-VU190-202-LH032-100-0 | 2 | true | 35.15 | 740-WAKont-VU190-202-LH032-100-0 | LV1-105639.VU190 | 385 |  |  | MC1 | LVL 4 | N/A | TR021_2 | 2024-06-05 | 2024-04-17 | 2024-04-17 |  | 2024-05-08 | 2024-05-13 | Büro | 2024-05-17 |  | 2024-05-14 | 2024-05-24 |  | 2024-05-29 | 2024-08-24 | 933 | 150 |  |  | 2024-09-09 | 149 | SEP | SEP
47749 | 740-WAKont-VU190-203-LH032-80-0 | 1 | false | 10.25 | 740-WAKont-VU190-203-LH032-80-0 | LV1-105639.VU190 | 385 | 10.May.2024 |  | MC1 | LVL 4 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-05-08 | 2024-05-13 | Büro | 2024-05-17 |  | 2024-05-13 | 2024-06-10 |  |  | 2024-06-12 | 933 | 150 |  |  |  | 149 | SEP | SEP
56822 | 740-WAKont-VU190-203-LH032-80-0 | 2 | true | 10.25 | 740-WAKont-VU190-203-LH032-80-0 | LV1-105639.VU190 | 385 |  |  | MC1 | LVL 4 | N/A | TR027_2 | 2024-07-02 | 2024-04-17 | 2024-04-17 |  | 2024-05-08 | 2024-05-13 |  | 2024-05-17 |  | 2024-05-13 | 2024-06-10 |  |  | 2024-06-12 | 933 | 150 |  |  |  | 149 | SEP | SEP
47750 | 740-WAKont-VU190-207-LH099-40-0 | 1 | true | 0.66 | 740-WAKont-VU190-207-LH099-40-0 | LV1-105639.VU190 | 386 |  |  | MC1 | LVL 4 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-06-10 | 2024-06-12 | Büro | 2024-06-28 |  | 2024-06-14 |  |  |  | 2024-10-16 | 934 | 150 |  |  |  | 149 | SEP | SEP
47751 | 740-WAKont-VU190-212-LH032-80-0 | 1 | true | 5.56 | 740-WAKont-VU190-212-LH032-80-0 | LV1-105639.VU190 | 385 | 10.May.2024 |  | MC1 | LVL 4 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-05-07 | 2024-05-13 | Büro | 2024-05-17 |  | 2024-05-13 | 2024-05-29 |  |  | 2024-06-12 | 933 | 150 |  |  | 2024-09-19 | 149 | SEP | SEP
47752 | 740-WAKont-VU190-214-LH032-32-0 | 1 | true | 1.81 | 740-WAKont-VU190-214-LH032-32-0 | LV1-105639.VU190 | 385 |  |  | MC1 | LVL 4 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-06-10 | 2024-06-11 | Attila Henter | 2024-06-28 |  | 2024-06-14 | 2024-07-17 |  |  | 2024-07-19 | 933 | 150 |  |  | 2024-09-19 | 149 | SEP | SEP
47753 | 740-WAKont-VU190-215-LH032-50-0 | 1 | true | 1.58 | 740-WAKont-VU190-215-LH032-50-0 | LV1-105639.VU190 | 385 |  |  | MC1 | LVL 4 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-06-07 | 2024-06-12 | Attila Henter | 2024-06-28 |  | 2024-06-12 | 2024-07-17 |  |  | 2024-07-19 | 933 | 150 |  |  | 2024-09-19 | 149 | SEP | SEP
47754 | 740-WAKont-VU190-221-LH032-32-0 | 1 | true | 3.37 | 740-WAKont-VU190-221-LH032-32-0 | LV1-105639.VU190 | 385 |  |  | MC1 | LVL 4 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-06-07 | 2024-06-12 | Attila Henter | 2024-06-28 |  | 2024-06-14 | 2024-07-17 |  |  | 2024-07-19 | 933 | 150 |  |  | 2024-09-19 | 149 | SEP | SEP
47755 | 740-WAKont-VU190-223-LH032-32-0 | 1 | true | 2.02 | 740-WAKont-VU190-223-LH032-32-0 | LV1-105639.VU190 | 385 |  |  | MC1 | LVL 4 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-06-07 | 2024-06-12 | Attila Henter | 2024-06-28 |  | 2024-06-14 | 2024-07-17 |  |  | 2024-07-19 | 933 | 150 |  |  | 2024-09-20 | 149 | SEP | SEP
47756 | 740-WAKont-VU190-224-LH032-32-0 | 1 | true | 2.39 | 740-WAKont-VU190-224-LH032-32-0 | LV1-105639.VU190 | 385 |  |  | MC1 | LVL 4 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-06-07 | 2024-06-12 | Attila Henter | 2024-06-28 |  | 2024-06-14 | 2024-07-17 |  |  | 2024-07-19 | 933 | 150 |  |  | 2024-09-20 | 149 | SEP | SEP
47757 | 740-WAKont-VU190-226-LH032-32-0 | 1 | true | 0.37 | 740-WAKont-VU190-226-LH032-32-0 | LV1-105639.VU190 | 385 |  |  | MC1 | LVL 4 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-06-07 | 2024-06-12 | Büro | 2024-06-28 |  | 2024-06-14 | 2024-09-04 |  |  | 2024-09-05 | 933 | 150 |  |  | 2024-09-09 | 149 | SEP | SEP
47758 | 740-WAKont-VU190-227-LH032-32-0 | 1 | true | 4.15 | 740-WAKont-VU190-227-LH032-32-0 | LV1-105639.VU190 | 385 |  |  | MC1 | LVL 4 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-06-07 | 2024-06-11 |  | 2024-06-28 |  | 2024-06-14 |  |  |  | 2024-07-19 | 933 | 150 |  |  | 2024-09-20 | 149 | SEP | SEP
47759 | 740-WAKont-VU190-228-LH032-50-0 | 1 | true | 3.11 | 740-WAKont-VU190-228-LH032-50-0 | LV1-105639.VU190 | 385 |  |  | MC1 | LVL 4 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-06-07 | 2024-06-11 |  | 2024-06-28 |  | 2024-06-14 |  |  |  | 2024-07-30 | 933 | 150 |  |  | 2024-09-20 | 149 | SEP | SEP
47760 | 740-WAKont-VU190-229-LH032-32-0 | 1 | true | 1.42 | 740-WAKont-VU190-229-LH032-32-0 | LV1-105639.VU190 | 385 |  |  | MC1 | LVL 4 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-06-07 | 2024-06-11 |  | 2024-06-28 |  | 2024-06-14 |  |  |  | 2024-07-19 | 933 | 150 |  |  | 2024-09-20 | 149 | SEP | SEP
47761 | 740-WAKont-VU190-230-LH032-32-0 | 1 | true | 3.59 | 740-WAKont-VU190-230-LH032-32-0 | LV1-105639.VU190 | 385 |  |  | MC1 | LVL 4 | N/A | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-06-07 | 2024-06-13 |  | 2024-06-28 |  | 2024-06-18 |  |  |  | 2024-07-19 | 933 | 150 |  |  | 2024-09-20 | 149 | SEP | SEP
47762 | 740-WBU-VS020-101-LH001-20-0 | 1 | true | 6.43 | 740-WBU-VS020-101-LH001-20-0 | LV1-105638.VU285 | 363 | 15.May.2024 |  | MC1 | LVL 5 | T60 | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-05-14 | 2024-05-16 | Büro | 2024-05-17 |  | 2024-05-16 |  |  |  | 2024-10-16 | 935 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
47763 | 740-WBU-VU285-104-LH001-25-0 | 1 | true | 21.95 | 740-WBU-VU285-104-LH001-25-0 | LV1-105638.VU285 | 363 | 15.May.2024 |  | MC1 | LVL 5 | T60 | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-05-14 | 2024-05-15 |  | 2024-05-17 |  | 2024-05-16 | 2024-07-04 |  |  | 2024-07-19 | 935 | 150 |  | 2024-09-05 | 2024-08-30 | 149 | SEP | SEP | 2024-09-30 | 2024-09-30 | 2024-09-30 | 2024-09-30
47764 | 740-WBU-VU285-106-LH001-20-0 | 1 | true | 0.12 | 740-WBU-VU285-106-LH001-20-0 | LV1-105638.VU285 | 363 | 15.May.2024 |  | MC1 | LVL 5 | T60 | TR012 | 2024-04-15 | 2024-04-17 | 2024-04-17 |  | 2024-05-14 | 2024-05-15 | Büro | 2024-05-17 |  | 2024-05-16 |  |  |  | 2024-09-03 | 935 | 150 |  | 2024-09-05 | 2024-08-30 | 149 | SEP | SEP | 2024-09-04 | 2024-09-30 | 2024-09-30 | 2024-09-30
47765 | 740-WFI-VU161-203-LH089-50-0 | 1 | true | 22.92 | 740-WFI-VU161-203-LH089-50-0 | LV1-105639.VU161 | 394 | 17.May.2024 |  | MC1 | LVL 5 | W23 | TR012 | 2024-04-10 | 2024-04-16 | 2024-04-17 |  | 2024-04-25 | 2024-04-26 | Dawid Mierzwa | 2024-05-17 |  | 2024-04-30 | 2024-05-23 | 2024-05-29 |  | 2024-08-30 | 936 | 150 |  |  | 2024-09-12 | 149 | SEP | SEP | 2024-10-25 | 2024-10-25 | 2024-10-25 | 2024-10-25
47766 | 740-WFI-VU161-204-LH089-50-0 | 1 | true | 29.35 | 740-WFI-VU161-204-LH089-50-0 | LV1-105639.VU161 | 394 | 17.May.2024 |  | MC1 | LVL 5 | W23 | TR012 | 2024-04-10 | 2024-04-16 | 2024-04-17 |  | 2024-04-25 | 2024-04-29 | Büro | 2024-05-17 |  | 2024-04-30 | 2024-06-03 | 2024-06-07 | 2024-06-12 | 2024-09-06 | 936 | 150 |  | 2024-10-15 | 2024-09-13 | 149 | SEP | SEP |  | 2024-10-18 | 2024-10-18 | 2024-10-28
47767 | 740-WFI-VU161-205-LH089-50-0 | 1 | true | 65.35 | 740-WFI-VU161-205-LH089-50-0 | LV1-105639.VU161 | 394 | 17.May.2024 |  | MC1 | LVL 5 | W23 | TR012 | 2024-04-10 | 2024-04-16 | 2024-04-17 |  | 2024-05-27 | 2024-05-30 | Büro | 2024-05-31 |  | 2024-05-30 |  | 2024-06-07 | 2024-06-21 | 2024-10-10 | 936 | 150 |  |  |  | 149 | SEP | SEP |  | 2024-10-18 | 2024-10-18 | 2024-10-18
47768 | 740-WFI-VU161-213-LH089-40-0 | 1 | true | 32.03 | 740-WFI-VU161-213-LH089-40-0 | LV1-105639.VU161 | 394 | 17.May.2024 |  | MC1 | LVL 5 | W23 | TR012 | 2024-04-10 | 2024-04-16 | 2024-04-17 |  | 2024-05-07 | 2024-05-10 | Büro | 2024-05-17 |  | 2024-05-10 | 2024-06-03 | 2024-06-07 | 2024-06-21 | 2024-09-20 | 936 | 150 |  | 2024-10-15 |  | 149 | SEP | SEP |  | 2024-10-18 | 2024-10-18 | 2024-10-18
47769 | 740-WFI-VU162-203-LH089-50-0 | 1 | true | 46.23 | 740-WFI-VU162-203-LH089-50-0 | LV1-105639.VU162 | 394 | 17.May.2024 |  | MC1 | LVL 5 | W23 | TR012 | 2024-04-10 | 2024-04-16 | 2024-04-17 |  | 2024-04-22 | 2024-04-23 | Büro | 2024-04-26 |  | 2024-04-23 | 2024-05-20 | 2024-05-24 |  | 2024-09-16 | 937 | 150 |  | 2024-10-08 | 2024-09-18 | 149 | SEP | SEP |  | 2024-10-18 | 2024-10-18
47770 | 740-WFI-VU162-204-LH089-50-0 | 1 | true | 53.19 | 740-WFI-VU162-204-LH089-50-0 | LV1-105639.VU162 | 394 | 17.May.2024 |  | MC1 | LVL 5 | W23 | TR012 | 2024-04-10 | 2024-04-16 | 2024-04-17 |  | 2024-04-30 | 2024-05-10 | Büro | 2024-05-17 |  | 2024-05-10 | 2024-05-23 | 2024-05-29 | 2024-06-12 | 2024-09-16 | 937 | 150 |  |  | 2024-09-18 | 149 | SEP | SEP |  | 2024-10-18 | 2024-10-18 | 2024-10-18
47771 | 740-WFI-VU162-205-LH089-50-0 | 1 | true | 33.44 | 740-WFI-VU162-205-LH089-50-0 | LV1-105639.VU162 | 394 | 17.May.2024 |  | MC1 | LVL 5 | W23 | TR012 | 2024-04-10 | 2024-04-16 | 2024-04-17 |  | 2024-04-30 | 2024-05-10 | Büro | 2024-05-17 |  | 2024-05-10 | 2024-06-03 | 2024-06-07 |  | 2024-10-10 | 937 | 150 |  |  |  | 149 | SEP | SEP |  | 2024-10-18 | 2024-10-18 | 2024-10-25
47772 | 740-WFI-VU163-202-LH089-80-0 | 1 | true | 25.12 | 740-WFI-VU163-202-LH089-80-0 | LV1-105639.VU163 | 394 | 17.May.2024 |  | MC1 | LVL 5 | W23 | TR012 | 2024-04-10 | 2024-04-16 | 2024-04-17 |  | 2024-04-30 | 2024-05-10 | Büro | 2024-05-17 |  | 2024-05-10 | 2024-05-23 | 2024-05-29 |  | 2024-09-16 | 938 | 150 |  |  | 2024-09-18 | 149 | SEP | SEP | 2024-10-01 | 2024-10-04 | 2024-10-04
47773 | 740-WFI-VU163-203-LH089-80-0 | 1 | true | 55.49 | 740-WFI-VU163-203-LH089-80-0 | LV1-105639.VU163 | 394 | 17.May.2024 |  | MC1 | LVL 5 | W23 | TR012 | 2024-04-10 | 2024-04-16 | 2024-04-17 |  | 2024-05-13 | 2024-05-15 | Büro | 2024-05-17 |  | 2024-05-15 | 2024-05-23 | 2024-05-29 | 2024-06-12 | 2024-10-10 | 938 | 150 |  |  |  | 149 | SEP | SEP | 2024-10-14 | 2024-10-14 | 2024-10-14
47774 | 740-WFI-VU163-204-LH089-80-0 | 1 | true | 15.46 | 740-WFI-VU163-204-LH089-80-0 | LV1-105639.VU163 | 394 | 17.May.2024 |  | MC1 | LVL 5 | W23 | TR012 | 2024-04-10 | 2024-04-16 | 2024-04-17 |  | 2024-06-24 | 2024-06-25 | Büro | 2024-06-28 |  | 2024-06-26 | 2024-07-03 |  | 2024-07-10 | 2024-09-27 | 938 | 150 |  |  |  | 149 | SEP | SEP | 2024-10-01 | 2024-10-14 | 2024-10-14 | 2024-10-14 | 2024-10-14 | 2024-10-14
48734 | 740-DK-VH001-102-LH011-20-0 | 1 | true | 0.69 | 740-DK-VH001-102-LH011-20-0 | LV1-105623.VH001 | 369 |  |  | MC1 | LVL 5 | W23 | TR013_1 | 2024-04-14 | 2024-04-18 | 2024-04-18 |  | 2024-06-10 | 2024-06-14 | Büro | 2024-06-28 |  | 2024-06-20 | 2024-09-30 |  |  | 2024-10-02 | 986 | 150 |  |  | 2024-10-02 | 149 | SEP | SEP |  |  | 2024-11-15 | 2024-11-15
48735 | 740-DK-VH002-102-LH011-20-0 | 1 | true | 0.77 | 740-DK-VH002-102-LH011-20-0 | LV1-105623.VH002 | 369 |  |  | MC1 | LVL 5 | W23 | TR013_1 | 2024-04-14 | 2024-04-18 | 2024-04-18 |  | 2024-06-10 | 2024-06-17 | Büro | 2024-06-28 |  | 2024-06-20 | 2024-09-28 |  |  | 2024-10-02 | 986 | 150 |  |  | 2024-10-02 | 149 | SEP | SEP |  |  | 2024-11-15 | 2024-11-15
48736 | 740-DK-VH003-102-LH011-20-0 | 1 | true | 0.8 | 740-DK-VH003-102-LH011-20-0 | LV1-105623.VH003 | 369 |  |  | MC1 | LVL 5 | W23 | TR013_1 | 2024-04-14 | 2024-04-18 | 2024-04-18 |  | 2024-06-10 | 2024-06-18 | Büro | 2024-06-28 |  | 2024-06-19 | 2024-09-25 |  |  | 2024-09-27 | 986 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-11-15 | 2024-11-15
48737 | 740-DK-VH004-102-LH011-20-0 | 1 | true | 0.85 | 740-DK-VH004-102-LH011-20-0 | LV1-105623.VH004 | 369 |  |  | MC1 | LVL 5 | W23 | TR013_1 | 2024-04-14 | 2024-04-18 | 2024-04-18 |  | 2024-06-14 | 2024-06-14 | Büro | 2024-06-28 |  | 2024-06-20 |  |  |  | 2024-10-02 | 986 | 150 |  |  | 2024-10-02 | 149 | SEP | SEP |  |  | 2024-11-15 | 2024-11-15
48738 | 740-DK-VH005-102-LH011-20-0 | 1 | true | 0.79 | 740-DK-VH005-102-LH011-20-0 | LV1-105623.VH005 | 369 |  |  | MC1 | LVL 5 | W23 | TR013_1 | 2024-04-14 | 2024-04-18 | 2024-04-18 |  | 2024-06-10 | 2024-06-17 | Büro | 2024-06-28 |  | 2024-06-20 | 2024-09-30 |  |  | 2024-10-03 | 986 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-11-15 | 2024-11-15
48739 | 740-DK-VP116-125-LH011-20-0 | 1 | true | 2.45 | 740-DK-VP116-125-LH011-20-0 | LV1-105638.VU116 | 369 |  | true | MC1 | LVL 5 | W23 | TR013_1 | 2024-04-14 | 2024-04-18 | 2024-04-18 | [10 empty] | 2024-09-28 | 986 | 150 |  |  |  | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
48740 | 740-DK-VP116-126-LH011-20-0 | 1 | true | 2.36 | 740-DK-VP116-126-LH011-20-0 | LV1-105638.VU116 | 369 |  | true | MC1 | LVL 5 | W23 | TR013_1 | 2024-04-14 | 2024-04-18 | 2024-04-18 | [10 empty] | 2024-09-28 | 986 | 150 |  |  |  | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
48741 | 740-DK-VS671-104-LH011-20-0 | 1 | false | 0.1 | 740-DK-VS671-104-LH011-20-0 | LV0-105633.VS671 | 369 |  |  | MC1 | LVL 6 | W23 | TR013_1 | 2024-04-14 | 2024-04-18 | 2024-04-18 |  | 2024-06-10 | 2024-06-13 |  |  |  | 2024-06-14 |  |  |  |  | 987 | 150 |  |  |  | 149 | SEP | SEP
57059 | 740-DK-VS671-104-LH011-20-0 | 2 | true | 0.1 | 740-DK-VS671-104-LH011-20-0 | LV0-105633.VS671 | 369 |  |  | MC1 | LVL 6 | W23 | TR028_2 | 2024-07-05 | 2024-04-18 | 2024-04-18 |  | 2024-06-10 | 2024-06-13 | Büro | 2024-08-02 |  | 2024-06-14 | 2024-09-17 |  |  | 2024-09-23 | 987 | 150 |  |  | 2024-09-26 | 149 | SEP | SEP | 2024-09-25 |  | 2024-11-01 | 2024-11-01
48742 | 740-DK-VS671-105-LH011-40-0 | 1 | false | 1.2 | 740-DK-VS671-105-LH011-40-0 | LV0-105633.VS671 | 369 |  | true | MC1 | LVL 6 | W23 | TR013_1 | 2024-04-14 | 2024-04-18 | [12 empty] | 987 | 150 |  |  |  | 149 | SEP | SEP
49629 | 740-DK-VS671-105-LH011-40-0 | 2 | false | 1.2 | 740-DK-VS671-105-LH011-40-0 | LV0-105633.VS671 | 369 |  |  | MC1 | LVL 6 | W23 | TR014_1 | 2024-04-22 | 2024-04-29 | 2024-04-29 |  | 2024-06-25 | 2024-06-26 |  | 2024-07-12 |  | 2024-07-01 |  |  |  |  | 987 | 150 |  |  |  | 149 | SEP | SEP
48743 | 740-DK-VS672-104-LH011-20-0 | 1 | false | 0.1 | 740-DK-VS672-104-LH011-20-0 | LV0-105633.VS672 | 369 |  |  | MC1 | LVL 6 | W23 | TR013_1 | 2024-04-14 | 2024-04-18 | 2024-04-18 |  | 2024-06-10 | 2024-06-13 | Büro | 2024-06-28 |  | 2024-06-14 |  |  |  | 2024-09-23 | 987 | 150 |  |  |  | 149 | SEP | SEP
57060 | 740-DK-VS672-104-LH011-20-0 | 2 | true | 0.1 | 740-DK-VS672-104-LH011-20-0 | LV0-105633.VS672 | 369 |  |  | MC1 | LVL 6 | W23 | TR028_2 | 2024-07-05 | 2024-04-18 | 2024-04-18 |  | 2024-06-10 | 2024-06-13 | Büro | 2024-06-28 |  | 2024-06-14 | 2024-09-17 |  |  | 2024-09-23 | 987 | 150 |  |  | 2024-09-25 | 149 | SEP | SEP | 2024-09-25 |  | 2024-11-01 | 2024-11-01
48744 | 740-DK-VS672-105-LH011-40-0 | 1 | false | 1.2 | 740-DK-VS672-105-LH011-40-0 | LV0-105633.VS672 | 369 |  | true | MC1 | LVL 6 | W23 | TR013_1 | 2024-04-14 | 2024-04-18 | [12 empty] | 987 | 150 |  |  |  | 149 | SEP | SEP
49630 | 740-DK-VS672-105-LH011-40-0 | 2 | false | 1.2 | 740-DK-VS672-105-LH011-40-0 | LV0-105633.VS672 | 369 |  |  | MC1 | LVL 6 | W23 | TR014_1 | 2024-04-22 | 2024-04-29 | 2024-04-29 |  | 2024-06-25 | 2024-07-01 |  | 2024-07-12 |  | 2024-07-03 |  |  |  |  | 987 | 150 |  |  |  | 149 | SEP | SEP
48745 | 740-DK-VS673-104-LH011-20-0 | 1 | false | 0.1 | 740-DK-VS673-104-LH011-20-0 | LV0-105633.VS673 | 369 |  |  | MC1 | LVL 6 | W23 | TR013_1 | 2024-04-14 | 2024-04-18 | 2024-04-18 |  | 2024-06-10 | 2024-06-13 |  | 2024-06-28 |  | 2024-06-14 | 2024-09-17 |  |  |  | 987 | 150 |  |  |  | 149 | SEP | SEP
57061 | 740-DK-VS673-104-LH011-20-0 | 2 | true | 0.1 | 740-DK-VS673-104-LH011-20-0 | LV0-105633.VS673 | 369 |  |  | MC1 | LVL 6 | W23 | TR028_2 | 2024-07-05 | 2024-04-18 | 2024-04-18 |  | 2024-06-10 | 2024-06-13 | Büro | 2024-06-28 |  | 2024-06-14 | 2024-09-17 |  |  | 2024-09-23 | 987 | 150 |  |  | 2024-09-25 | 149 | SEP | SEP | 2024-09-25 |  | 2024-11-01 | 2024-11-01
48746 | 740-DK-VS673-105-LH011-40-0 | 1 | false | 0.92 | 740-DK-VS673-105-LH011-40-0 | LV0-105633.VS673 | 369 |  | true | MC1 | LVL 6 | W23 | TR013_1 | 2024-04-14 | 2024-04-18 | [12 empty] | 987 | 150 |  |  |  | 149 | SEP | SEP
49631 | 740-DK-VS673-105-LH011-40-0 | 2 | false | 0.92 | 740-DK-VS673-105-LH011-40-0 | LV0-105633.VS673 | 369 |  |  | MC1 | LVL 6 | W23 | TR014_1 | 2024-04-22 | 2024-04-29 | 2024-04-29 |  | 2024-06-25 | 2024-06-28 | Büro | 2024-07-12 |  | 2024-07-03 | 2024-09-17 |  |  | 2024-09-23 | 987 | 150 |  |  |  | 149 | SEP | SEP
48747 | 740-DK-VU116-102-LH011-50-0 | 1 | true | 26.88 | 740-DK-VU116-102-LH011-50-0 | LV1-105638.VU116 | 369 | 15.May.2024 |  | MC1 | LVL 5 | W23 | TR013_1 | 2024-04-14 | 2024-04-18 | 2024-04-18 |  | 2024-04-29 | 2024-05-08 | Büro | 2024-05-17 |  | 2024-05-08 | 2024-06-20 | 2024-06-21 |  | 2024-06-27 | 986 | 150 |  |  | 2024-08-29 | 149 | SEP | SEP |  |  | 2024-11-01 | 2024-11-01
48784 | 740-DK-VU116-144-LH011-20-0 | 1 | true | 8.8 | 740-DK-VU116-144-LH011-20-0 | LV1-105638.VU116 | 369 |  |  | MC1 | LVL 6 | W23 | TR013_1 | 2024-04-14 | 2024-04-18 | 2024-04-18 |  | 2024-06-06 | 2024-06-10 | Büro | 2024-06-14 |  | 2024-06-10 | 2024-10-01 |  |  | 2024-10-02 | 987 | 150 |  |  | 2024-10-02 | 149 | SEP | SEP |  |  | 2024-11-01 | 2024-11-01
48785 | 740-DK-VU116-145-LH011-20-0 | 1 | true | 8.09 | 740-DK-VU116-145-LH011-20-0 | LV1-105638.VU116 | 369 |  |  | MC1 | LVL 6 | W23 | TR013_1 | 2024-04-14 | 2024-04-18 | 2024-04-18 |  | 2024-06-07 | 2024-06-11 | Büro | 2024-06-28 |  | 2024-06-14 | 2024-09-25 |  |  | 2024-09-27 | 987 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-11-01 | 2024-11-01
48786 | 740-DK-VU116-147-LH011-20-0 | 1 | true | 6.6 | 740-DK-VU116-147-LH011-20-0 | LV1-105638.VU116 | 369 |  |  | MC1 | LVL 5 | W23 | TR013_1 | 2024-04-14 | 2024-04-18 | 2024-04-18 |  | 2024-06-07 | 2024-06-14 | Büro | 2024-06-28 |  | 2024-06-18 | 2024-08-07 |  |  | 2024-08-09 | 986 | 150 |  |  | 2024-08-28 | 149 | SEP | SEP |  |  | 2024-11-01 | 2024-11-01
48748 | 740-DK-VU116-104-LH011-40-0 | 1 | false | 2.68 | 740-DK-VU116-104-LH011-40-0 | LV1-105638.VU116 | 369 |  |  | MC1 | LVL 5 | W23 | TR013_1 | 2024-04-14 | 2024-04-18 | 2024-04-18 |  | 2024-06-03 | 2024-06-07 | Büro | 2024-06-14 |  | 2024-06-07 |  |  |  | 2024-08-28 | 986 | 150 |  |  |  | 149 | SEP | SEP
57064 | 740-DK-VU116-104-LH011-40-0 | 2 | true | 2.68 | 740-DK-VU116-104-LH011-40-0 | LV1-105638.VU116 | 369 |  |  | MC1 | LVL 5 | W23 | TR028_2 | 2024-07-05 | 2024-04-18 | 2024-04-18 |  | 2024-06-03 | 2024-06-07 | Büro | 2024-06-14 |  | 2024-06-07 | 2024-07-18 |  |  | 2024-08-28 | 986 | 150 |  |  | 2024-09-03 | 149 | SEP | SEP |  |  | 2024-11-01 | 2024-11-01
48749 | 740-DK-VU116-105-LH011-40-0 | 1 | false | 3.8 | 740-DK-VU116-105-LH011-40-0 | LV1-105638.VU116 | 369 |  |  | MC1 | LVL 5 | W23 | TR013_1 | 2024-04-14 | 2024-04-18 | 2024-04-18 |  | 2024-06-03 | 2024-06-07 |  | 2024-06-14 |  | 2024-06-07 |  |  |  |  | 986 | 150 |  |  |  | 149 | SEP | SEP
57065 | 740-DK-VU116-105-LH011-40-0 | 1 | true | 0.92 | 740-DK-VU116-105-LH011-40-0 | LV1-105638.VU116 | 369 |  | true | MC1 | LVL 5 | W23 | TR028_2 | 2024-07-05 | 2024-04-29 | 2024-04-29 |  | 2024-06-25 | 2024-06-28 | Büro | 2024-07-12 |  | 2024-07-03 | 2024-09-17 |  |  | 2024-09-23 | 986 | 150 |  |  | 2024-09-26 | 149 | SEP | SEP |  |  | 2024-11-01 | 2024-11-01
48750 | 740-DK-VU116-106-LH011-50-0 | 1 | false | 8.13 | 740-DK-VU116-106-LH011-50-0 | LV1-105638.VU116 | 369 |  |  | MC1 | LVL 5 | W23 | TR013_1 | 2024-04-14 | 2024-04-18 | 2024-04-18 |  | 2024-06-03 | 2024-06-07 |  | 2024-06-14 |  | 2024-06-07 |  |  |  | 2024-07-19 | 986 | 150 |  |  |  | 149 | SEP | SEP
57066 | 740-DK-VU116-106-LH011-50-0 | 2 | true | 8.13 | 740-DK-VU116-106-LH011-50-0 | LV1-105638.VU116 | 369 |  |  | MC1 | LVL 5 | W23 | TR028_2 | 2024-07-05 | 2024-04-18 | 2024-04-18 |  | 2024-06-03 | 2024-06-07 | Büro | 2024-06-14 |  | 2024-06-07 | 2024-07-15 |  |  | 2024-10-01 | 986 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-11-01 | 2024-11-01
48751 | 740-DK-VU116-107-LH011-40-0 | 1 | false | 3.56 | 740-DK-VU116-107-LH011-40-0 | LV1-105638.VU116 | 369 |  |  | MC1 | LVL 5 | W23 | TR013_1 | 2024-04-14 | 2024-04-18 | 2024-04-18 |  | 2024-06-03 | 2024-06-07 |  | 2024-06-14 |  | 2024-06-07 |  |  |  | 2024-07-19 | 986 | 150 |  |  |  | 149 | SEP | SEP
57067 | 740-DK-VU116-107-LH011-40-0 | 2 | true | 3.56 | 740-DK-VU116-107-LH011-40-0 | LV1-105638.VU116 | 369 |  |  | MC1 | LVL 5 | W23 | TR028_2 | 2024-07-05 | 2024-04-18 | 2024-04-18 |  | 2024-06-03 | 2024-06-07 | Büro | 2024-06-14 |  | 2024-06-07 | 2024-07-15 |  |  | 2024-10-01 | 986 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-11-01 | 2024-11-01
48752 | 740-DK-VU116-108-LH011-40-0 | 1 | true | 3.72 | 740-DK-VU116-108-LH011-40-0 | LV1-105638.VU116 | 369 |  |  | MC1 | LVL 5 | W23 | TR013_1 | 2024-04-14 | 2024-04-18 | 2024-04-18 |  | 2024-06-03 | 2024-06-07 |  | 2024-06-14 |  | 2024-06-07 | 2024-07-15 |  |  | 2024-07-19 | 986 | 150 |  |  | 2024-07-29 | 149 | SEP | SEP |  |  | 2024-11-01 | 2024-11-01
48753 | 740-DK-VU116-109-LH011-20-0 | 1 | true | 12.65 | 740-DK-VU116-109-LH011-20-0 | LV1-105638.VU111 | 369 |  |  | MC1 | LVL 6 | W23 | TR013_1 | 2024-04-14 | 2024-04-18 | 2024-04-18 |  | 2024-06-06 | 2024-06-11 |  | 2024-06-28 |  | 2024-06-11 | 2024-08-22 |  |  | 2024-08-27 | 987 | 150 |  | 2024-10-25 | 2024-08-28 | 149 | SEP | SEP |  |  | 2024-11-01 | 2024-11-01
48754 | 740-DK-VU116-110-LH011-20-0 | 1 | true | 1.6 | 740-DK-VU116-110-LH011-20-0 | LV1-105638.VU116 | 369 |  |  | MC1 | LVL 6 | W23 | TR013_1 | 2024-04-14 | 2024-04-18 | 2024-04-18 |  | 2024-06-06 | 2024-06-08 | Büro | 2024-06-14 |  | 2024-06-08 | 2024-09-30 |  |  | 2024-10-03 | 987 | 150 |  | 2024-10-25 |  | 149 | SEP | SEP |  |  | 2024-11-01 | 2024-11-01
48755 | 740-DK-VU116-111-LH011-50-0 | 1 | true | 30.08 | 740-DK-VU116-111-LH011-50-0 | LV1-105638.VU116 | 369 | 15.May.2024 |  | MC1 | LVL 5 | W23 | TR013_1 | 2024-04-14 | 2024-04-18 | 2024-04-18 |  | 2024-04-29 | 2024-05-09 | Büro | 2024-05-17 |  | 2024-05-09 | 2024-06-20 | 2024-06-21 |  | 2024-06-27 | 986 | 150 |  | 2024-10-25 | 2024-07-03 | 149 | SEP | SEP |  |  | 2024-11-01 | 2024-11-01
48756 | 740-DK-VU116-112-LH011-20-0 | 1 | true | 1.21 | 740-DK-VU116-112-LH011-20-0 | LV1-105638.VU116 | 369 |  |  | MC1 | LVL 5 | W23 | TR013_1 | 2024-04-14 | 2024-04-18 | 2024-04-18 |  | 2024-06-07 | 2024-06-11 | Büro | 2024-06-28 |  | 2024-06-11 | 2024-09-30 |  |  | 2024-10-03 | 986 | 150 |  | 2024-10-25 |  | 149 | SEP | SEP |  |  | 2024-11-01 | 2024-11-01
48757 | 740-DK-VU116-113-LH011-20-0 | 1 | true | 1.32 | 740-DK-VU116-113-LH011-20-0 | LV1-105638.VU116 | 369 |  |  | MC1 | LVL 5 | W23 | TR013_1 | 2024-04-14 | 2024-04-18 | 2024-04-18 |  | 2024-06-07 | 2024-06-08 | Büro | 2024-06-14 |  | 2024-06-08 | 2024-09-30 |  |  | 2024-10-03 | 986 | 150 |  | 2024-10-25 |  | 149 | SEP | SEP |  |  | 2024-11-01 | 2024-11-01
48758 | 740-DK-VU116-114-LH011-20-0 | 1 | true | 1.84 | 740-DK-VU116-114-LH011-20-0 | LV1-105638.VU116 | 369 |  |  | MC1 | LVL 5 | W23 | TR013_1 | 2024-04-14 | 2024-04-18 | 2024-04-18 |  | 2024-06-07 | 2024-06-11 | Büro | 2024-06-28 |  | 2024-06-11 | 2024-07-09 |  | 2024-07-15 | 2024-10-03 | 986 | 150 |  | 2024-10-25 |  | 149 | SEP | SEP |  |  | 2024-11-01 | 2024-11-01
48759 | 740-DK-VU116-116-LH011-50-0 | 1 | true | 19.92 | 740-DK-VU116-116-LH011-50-0 | LV1-105638.VU116 | 369 | 15.May.2024 |  | MC1 | LVL 5 | W23 | TR013_1 | 2024-04-14 | 2024-04-18 | 2024-04-18 |  | 2024-04-27 | 2024-05-09 | Büro | 2024-05-17 |  | 2024-05-09 | 2024-07-03 |  |  | 2024-07-09 | 986 | 150 |  | 2024-10-25 | 2024-07-26 | 149 | SEP | SEP |  |  | 2024-11-01 | 2024-11-01
48760 | 740-DK-VU116-117-LH011-25-0 | 1 | true | 2.62 | 740-DK-VU116-117-LH011-25-0 | LV1-105638.VU116 | 369 | 15.May.2024 |  | MC1 | LVL 5 | W23 | TR013_1 | 2024-04-14 | 2024-04-18 | 2024-04-18 |  | 2024-04-29 | 2024-04-30 | Büro | 2024-05-17 |  | 2024-04-30 |  |  |  | 2024-09-27 | 986 | 150 |  | 2024-10-25 |  | 149 | SEP | SEP |  |  | 2024-11-01 | 2024-11-01
48761 | 740-DK-VU116-118-LH011-25-0 | 1 | true | 2.79 | 740-DK-VU116-118-LH011-25-0 | LV1-105638.VU116 | 369 | 15.May.2024 |  | MC1 | LVL 5 | W23 | TR013_1 | 2024-04-14 | 2024-04-18 | 2024-04-18 |  | 2024-04-29 | 2024-04-30 | Büro | 2024-05-17 |  | 2024-04-30 |  |  |  | 2024-09-27 | 986 | 150 |  | 2024-10-25 |  | 149 | SEP | SEP |  |  | 2024-11-01 | 2024-11-01
48762 | 740-DK-VU116-119-LH011-25-0 | 1 | true | 2.81 | 740-DK-VU116-119-LH011-25-0 | LV1-105638.VU116 | 369 | 15.May.2024 |  | MC1 | LVL 5 | W23 | TR013_1 | 2024-04-14 | 2024-04-18 | 2024-04-18 |  | 2024-04-29 | 2024-04-30 | Büro | 2024-05-17 |  | 2024-04-30 |  |  |  | 2024-09-27 | 986 | 150 |  | 2024-10-25 |  | 149 | SEP | SEP |  |  | 2024-11-01 | 2024-11-01
48763 | 740-DK-VU116-120-LH011-25-0 | 1 | true | 1.38 | 740-DK-VU116-120-LH011-25-0 | LV1-105638.VU116 | 369 | 15.May.2024 |  | MC1 | LVL 5 | W23 | TR013_1 | 2024-04-14 | 2024-04-18 | 2024-04-18 |  | 2024-04-29 | 2024-04-30 | Büro | 2024-05-17 |  | 2024-04-30 |  |  |  | 2024-09-27 | 986 | 150 |  | 2024-10-25 |  | 149 | SEP | SEP |  |  | 2024-11-01 | 2024-11-01
48764 | 740-DK-VU116-121-LH011-20-0 | 1 | true | 1.51 | 740-DK-VU116-121-LH011-20-0 | LV1-105638.VU116 | 369 |  |  | MC1 | LVL 5 | W23 | TR013_1 | 2024-04-14 | 2024-04-18 | 2024-04-18 |  | 2024-06-07 | 2024-06-08 | Büro | 2024-06-14 |  | 2024-06-08 |  |  |  | 2024-09-27 | 986 | 150 |  | 2024-10-25 |  | 149 | SEP | SEP |  |  | 2024-11-01 | 2024-11-01
48765 | 740-DK-VU116-122-LH011-20-0 | 1 | true | 1.49 | 740-DK-VU116-122-LH011-20-0 | LV1-105638.VU116 | 369 |  |  | MC1 | LVL 5 | W23 | TR013_1 | 2024-04-14 | 2024-04-18 | 2024-04-18 |  | 2024-06-07 | 2024-06-10 | Büro | 2024-06-28 |  | 2024-06-10 |  |  |  | 2024-09-27 | 986 | 150 |  | 2024-10-25 |  | 149 | SEP | SEP |  |  | 2024-11-01 | 2024-11-01
48766 | 740-DK-VU116-123-LH011-20-0 | 1 | true | 7.24 | 740-DK-VU116-123-LH011-20-0 | LV1-105638.VU116 | 369 |  |  | MC1 | LVL 6 | W23 | TR013_1 | 2024-04-14 | 2024-04-18 | 2024-04-18 |  | 2024-06-06 | 2024-06-11 | Büro | 2024-06-28 |  | 2024-06-14 |  |  |  | 2024-09-28 | 987 | 150 |  | 2024-10-25 | 2024-09-30 | 149 | SEP | SEP |  |  | 2024-11-01 | 2024-11-01
48767 | 740-DK-VU116-124-LH011-20-0 | 1 | true | 5.2 | 740-DK-VU116-124-LH011-20-0 | LV1-105638.VU116 | 369 |  |  | MC1 | LVL 5 | W23 | TR013_1 | 2024-04-14 | 2024-04-18 | 2024-04-18 |  | 2024-06-07 | 2024-06-11 | Büro | 2024-06-28 |  | 2024-06-11 |  |  |  | 2024-09-27 | 986 | 150 |  | 2024-10-25 |  | 149 | SEP | SEP |  |  | 2024-11-01 | 2024-11-01
48768 | 740-DK-VU116-127-LH011-20-0 | 1 | true | 1.39 | 740-DK-VU116-127-LH011-20-0 | LV1-105638.VU116 | 369 |  |  | MC1 | LVL 5 | W23 | TR013_1 | 2024-04-14 | 2024-04-18 | 2024-04-18 |  | 2024-06-07 | 2024-06-11 | Büro | 2024-06-28 |  | 2024-06-11 |  |  |  | 2024-09-26 | 986 | 150 |  | 2024-10-25 |  | 149 | SEP | SEP |  |  | 2024-11-01 | 2024-11-01
48769 | 740-DK-VU116-128-LH011-20-0 | 1 | true | 3.15 | 740-DK-VU116-128-LH011-20-0 | LV1-105638.VU116 | 369 |  |  | MC1 | LVL 6 | W23 | TR013_1 | 2024-04-14 | 2024-04-18 | 2024-04-18 |  | 2024-06-06 | 2024-06-12 | Büro | 2024-06-28 |  | 2024-06-14 | 2024-07-09 |  |  | 2024-07-15 | 987 | 150 |  | 2024-10-25 | 2024-07-26 | 149 | SEP | SEP |  |  | 2024-11-01 | 2024-11-01
48770 | 740-DK-VU116-130-LH011-20-0 | 1 | true | 2.29 | 740-DK-VU116-130-LH011-20-0 | LV1-105638.VU116 | 369 |  |  | MC1 | LVL 5 | W23 | TR013_1 | 2024-04-14 | 2024-04-18 | 2024-04-18 |  | 2024-04-29 | 2024-05-09 | Büro | 2024-05-17 |  | 2024-05-09 |  |  |  | 2024-09-24 | 986 | 150 |  | 2024-10-25 | 2024-09-27 | 149 | SEP | SEP |  |  | 2024-11-01 | 2024-11-01
48771 | 740-DK-VU116-131-LH011-32-0 | 1 | true | 9.45 | 740-DK-VU116-131-LH011-32-0 | LV1-105638.VU116 | 369 | 15.May.2024 |  | MC1 | LVL 5 | W23 | TR013_1 | 2024-04-14 | 2024-04-18 | 2024-04-18 |  | 2024-04-29 | 2024-05-09 | Büro | 2024-05-17 |  | 2024-05-09 | 2024-08-14 |  |  | 2024-08-22 | 986 | 150 |  | 2024-10-25 | 2024-08-28 | 149 | SEP | SEP |  |  | 2024-11-01 | 2024-11-01
48772 | 740-DK-VU116-132-LH011-20-0 | 1 | true | 2.96 | 740-DK-VU116-132-LH011-20-0 | LV1-105638.VU116 | 369 |  |  | MC1 | LVL 5 | W23 | TR013_1 | 2024-04-14 | 2024-04-18 | 2024-04-18 |  | 2024-06-07 | 2024-06-11 | Büro | 2024-06-28 |  | 2024-06-11 |  |  |  | 2024-09-26 | 986 | 150 |  | 2024-10-25 |  | 149 | SEP | SEP |  |  | 2024-11-01 | 2024-11-01
48773 | 740-DK-VU116-133-LH011-20-0 | 1 | true | 2.33 | 740-DK-VU116-133-LH011-20-0 | LV1-105638.VU116 | 369 |  |  | MC1 | LVL 5 | W23 | TR013_1 | 2024-04-14 | 2024-04-18 | 2024-04-18 |  | 2024-06-07 | 2024-06-12 | Büro | 2024-06-28 |  | 2024-06-12 |  |  |  | 2024-09-25 | 986 | 150 |  | 2024-10-25 |  | 149 | SEP | SEP |  |  | 2024-11-01 | 2024-11-01
48774 | 740-DK-VU116-134-LH011-20-0 | 1 | true | 8.87 | 740-DK-VU116-134-LH011-20-0 | LV1-105638.VU116 | 369 |  |  | MC1 | LVL 6 | W23 | TR013_1 | 2024-04-14 | 2024-04-18 | 2024-04-18 |  | 2024-06-06 | 2024-06-12 | Büro | 2024-06-28 |  | 2024-06-14 | 2024-09-28 |  |  | 2024-10-02 | 987 | 150 |  | 2024-10-25 | 2024-10-02 | 149 | SEP | SEP |  |  | 2024-11-01 | 2024-11-01
48775 | 740-DK-VU116-135-LH011-32-0 | 1 | false | 25.64 | 740-DK-VU116-135-LH011-32-0 | LV1-105638.VU116 | 369 | 15.May.2024 |  | MC1 | LVL 5 | W23 | TR013_1 | 2024-04-14 | 2024-04-18 | 2024-04-18 |  | 2024-04-29 | [9 empty] | 986 | 150 |  |  |  | 149 | SEP | SEP
49634 | 740-DK-VU116-135-LH011-32-0 | 2 | true | 25.64 | 740-DK-VU116-135-LH011-32-0 | LV1-105638.VU116 | 369 |  |  | MC1 | LVL 5 | W23 | TR014_1 | 2024-04-22 | 2024-04-29 | 2024-04-29 |  | 2024-05-08 | 2024-05-11 | Büro | 2024-05-17 |  | 2024-05-14 | 2024-06-26 |  |  | 2024-10-23 | 986 | 150 |  |  | 2024-07-26 | 149 | SEP | SEP |  |  | 2024-11-01 | 2024-11-01
48776 | 740-DK-VU116-136-LH011-20-0 | 1 | true | 7.64 | 740-DK-VU116-136-LH011-20-0 | LV1-105638.VU116 | 369 |  |  | MC1 | LVL 5 | W23 | TR013_1 | 2024-04-14 | 2024-04-18 | 2024-04-18 |  | 2024-06-06 | 2024-06-08 | Büro | 2024-06-14 |  | 2024-06-08 | 2024-07-29 |  | 2024-07-31 | 2024-10-02 | 986 | 150 |  | 2024-10-25 | 2024-10-02 | 149 | SEP | SEP |  |  | 2024-11-01 | 2024-11-01
48777 | 740-DK-VU116-137-LH011-20-0 | 1 | true | 3.86 | 740-DK-VU116-137-LH011-20-0 | LV1-105638.VU116 | 369 |  |  | MC1 | LVL 5 | W23 | TR013_1 | 2024-04-14 | 2024-04-18 | 2024-04-18 |  | 2024-06-06 | 2024-06-08 | Büro | 2024-06-14 |  | 2024-06-08 | 2024-09-28 |  |  | 2024-10-02 | 986 | 150 |  | 2024-10-25 | 2024-10-02 | 149 | SEP | SEP |  |  | 2024-11-01 | 2024-11-01
48778 | 740-DK-VU116-138-LH011-20-0 | 1 | true | 4.41 | 740-DK-VU116-138-LH011-20-0 | LV1-105638.VU116 | 369 |  |  | MC1 | LVL 6 | W23 | TR013_1 | 2024-04-14 | 2024-04-18 | 2024-04-18 |  | 2024-06-06 | 2024-06-12 | Büro | 2024-06-28 |  | 2024-06-14 | 2024-10-01 |  |  | 2024-10-02 | 987 | 150 |  | 2024-10-25 | 2024-10-02 | 149 | SEP | SEP |  |  | 2024-11-01 | 2024-11-01
48779 | 740-DK-VU116-139-LH011-20-0 | 1 | true | 2.82 | 740-DK-VU116-139-LH011-20-0 | LV1-105638.VU116 | 369 |  |  | MC1 | LVL 6 | W23 | TR013_1 | 2024-04-14 | 2024-04-18 | 2024-04-18 |  | 2024-06-06 | 2024-06-12 | Büro | 2024-06-28 |  | 2024-06-17 |  |  |  | 2024-09-27 | 987 | 150 |  | 2024-10-25 |  | 149 | SEP | SEP |  |  | 2024-11-01 | 2024-11-01
48780 | 740-DK-VU116-140-LH011-20-0 | 1 | true | 0.52 | 740-DK-VU116-140-LH011-20-0 | LV1-105638.VU116 | 369 |  |  | MC1 | LVL 5 | W23 | TR013_1 | 2024-04-14 | 2024-04-18 | 2024-04-18 |  | 2024-06-06 | 2024-06-07 | Büro | 2024-06-14 |  | 2024-06-07 | 2024-09-25 |  |  | 2024-09-27 | 986 | 150 |  | 2024-10-25 |  | 149 | SEP | SEP |  |  | 2024-11-01 | 2024-11-01
48781 | 740-DK-VU116-141-LH011-20-0 | 1 | true | 10.7 | 740-DK-VU116-141-LH011-20-0 | LV1-105638.VU116 | 369 |  |  | MC1 | LVL 5 | W23 | TR013_1 | 2024-04-14 | 2024-04-18 | 2024-04-18 |  | 2024-06-06 | 2024-06-10 | Büro | 2024-06-14 |  | 2024-06-10 | 2024-07-29 |  | 2024-07-31 | 2024-10-02 | 986 | 150 |  | 2024-10-25 | 2024-10-02 | 149 | SEP | SEP |  |  | 2024-11-01 | 2024-11-01
48782 | 740-DK-VU116-142-LH011-20-0 | 1 | true | 11.46 | 740-DK-VU116-142-LH011-20-0 | LV1-105638.VU116 | 369 |  |  | MC1 | LVL 5 | W23 | TR013_1 | 2024-04-14 | 2024-04-18 | 2024-04-18 |  | 2024-06-06 | 2024-06-10 |  | 2024-06-28 |  | 2024-06-14 | 2024-07-18 |  |  | 2024-07-19 | 986 | 150 |  | 2024-10-25 | 2024-07-29 | 149 | SEP | SEP |  |  | 2024-11-01 | 2024-11-01
48783 | 740-DK-VU116-143-LH011-20-0 | 1 | true | 2.7 | 740-DK-VU116-143-LH011-20-0 | LV1-105638.VU116 | 369 |  |  | MC1 | LVL 5 | W23 | TR013_1 | 2024-04-14 | 2024-04-18 | 2024-04-18 |  | 2024-06-06 | 2024-06-10 |  | 2024-06-28 |  | 2024-06-10 | 2024-07-18 |  |  | 2024-07-19 | 986 | 150 |  | 2024-10-25 | 2024-07-26 | 149 | SEP | SEP |  |  | 2024-11-01 | 2024-11-01
48787 | 740-DK-VU117-101-LH011-50-0 | 1 | true | 20.66 | 740-DK-VU117-101-LH011-50-0 | LV1-105638.VU117 | 369 |  |  | MC1 | LVL 4 | W23 | TR013_1 | 2024-04-14 | 2024-04-18 | 2024-04-18 |  | 2024-06-11 | 2024-06-11 | Büro | 2024-06-28 |  | 2024-06-14 | 2024-07-08 |  |  | 2024-08-24 | 988 | 150 |  |  | 2024-08-28 | 149 | SEP | SEP | 2024-11-08 | 2024-11-08 | 2024-11-08 | 2024-11-08
48788 | 740-DK-VU117-102-LH011-20-0 | 1 | false | 12.49 | 740-DK-VU117-102-LH011-20-0 | LV1-105638.VU117 | 369 |  |  | MC1 | LVL 4 | W23 | TR013_1 | 2024-04-14 | 2024-04-18 | 2024-04-18 | [11 empty] | 988 | 150 |  |  |  | 149 | SEP | SEP
49635 | 740-DK-VU117-102-LH011-20-0 | 2 | true | 12.49 | 740-DK-VU117-102-LH011-20-0 | LV1-105638.VU117 | 369 |  |  | MC1 | LVL 4 | W23 | TR014_1 | 2024-04-22 | 2024-04-29 | 2024-04-29 |  | 2024-06-25 | 2024-06-27 | Büro | 2024-07-12 |  | 2024-07-01 | 2024-09-05 |  |  | 2024-09-12 | 988 | 150 |  |  | 2024-09-12 | 149 | SEP | SEP | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22
48789 | 740-DK-VU117-103-LH011-20-0 | 1 | true | 2.33 | 740-DK-VU117-103-LH011-20-0 | LV1-105638.VU117 | 369 |  |  | MC1 | LVL 4 | W23 | TR013_1 | 2024-04-14 | 2024-04-18 | 2024-04-18 |  | 2024-06-07 | 2024-06-11 |  | 2024-06-28 |  | 2024-06-14 | 2024-07-08 |  |  | 2024-07-19 | 988 | 150 |  | 2024-08-26 | 2024-07-23 | 149 | SEP | SEP |  |  | 2024-11-01 | 2024-11-01
48790 | 740-DK-VU117-108-LH011-40-0 | 1 | false | 18.5 | 740-DK-VU117-108-LH011-40-0 | LV1-105638.VU117 | 369 | 15.May.2024 |  | MC1 | LVL 4 | W23 | TR013_1 | 2024-04-14 | 2024-04-18 | 2024-04-18 |  | 2024-04-29 | 2024-05-09 | Büro | 2024-05-17 |  | 2024-05-09 | 2024-07-08 |  |  |  | 988 | 150 |  |  |  | 149 | SEP | SEP
52183 | 740-DK-VU117-108-LH011-40-0 | 2 | true | 18.5 | 740-DK-VU117-108-LH011-40-0 | LV1-105638.VU117 | 369 |  |  | MC1 | LVL 4 | W23 | TR020_1 | 2024-05-29 | 2024-04-18 | 2024-04-18 |  | 2024-04-29 | 2024-05-09 | Büro | 2024-05-17 |  | 2024-05-09 | 2024-07-08 |  |  | 2024-07-16 | 988 | 150 |  | 2024-08-26 | 2024-07-29 | 149 | SEP | SEP | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22
48791 | 740-DK-VU117-162-LH011-50-0 | 1 | false | 22.77 | 740-DK-VU117-162-LH011-50-0 | LV1-105638.VU117 | 369 | 15.May.2024 |  | MC1 | LVL 4 | W23 | TR013_1 | 2024-04-14 | 2024-04-18 | 2024-04-18 | [11 empty] | 988 | 150 |  |  |  | 149 | SEP | SEP
49636 | 740-DK-VU117-162-LH011-50-0 | 2 | true | 22.77 | 740-DK-VU117-162-LH011-50-0 | LV1-105638.VU117 | 369 |  |  | MC1 | LVL 4 | W23 | TR014_1 | 2024-04-22 | 2024-04-29 | 2024-04-29 |  | 2024-04-27 | 2024-05-08 | Büro | 2024-05-17 |  | 2024-05-08 | 2024-07-08 |  |  | 2024-07-11 | 988 | 150 |  | 2024-08-26 | 2024-07-29 | 149 | SEP | SEP | 2024-11-08 | 2024-11-08 | 2024-11-08 | 2024-11-08 | 2024-11-08 | 2024-11-08
48794 | 740-MKWH-R-H015-501-LH130-32-0 | 1 | true | 0.61 | 740-MKWH-R-H015-501-LH130-32-0 | LV1-103549.H015 | 362 |  |  | MC1 | LVL 6 | T60 | TR013_1 | 2024-04-14 | 2024-04-18 | 2024-04-18 |  | 2024-06-11 | 2024-06-12 | Büro | 2024-06-28 |  | 2024-06-14 | 2024-08-09 |  |  | 2024-08-13 | 804 | 150 |  | 2024-09-10 | 2024-09-09 | 149 | SEP | SEP | 2024-09-11 | 2024-10-14 | 2024-10-14 | 2024-10-14
48795 | 740-MKWH-R-H015-502-LH130-32-0 | 1 | true | 0.91 | 740-MKWH-R-H015-502-LH130-32-0 | LV1-103549.H015 | 362 |  |  | MC1 | LVL 6 | T60 | TR013_1 | 2024-04-14 | 2024-04-18 | 2024-04-18 |  | 2024-06-11 | 2024-06-13 | Büro | 2024-06-28 |  | 2024-06-17 | 2024-08-27 |  |  | 2024-08-29 | 804 | 150 |  | 2024-09-10 | 2024-09-09 | 149 | SEP | SEP | 2024-09-11 | 2024-10-14 | 2024-10-14 | 2024-10-14
48796 | 740-MKWH-R-H015-503-LH130-32-0 | 1 | true | 1.11 | 740-MKWH-R-H015-503-LH130-32-0 | LV1-103549.H015 | 362 |  |  | MC1 | LVL 6 | T60 | TR013_1 | 2024-04-14 | 2024-04-18 | 2024-04-18 |  | 2024-06-11 | 2024-06-12 | Büro | 2024-06-28 |  | 2024-06-14 | 2024-08-27 |  |  | 2024-08-29 | 804 | 150 |  |  | 2024-09-09 | 149 | SEP | SEP | 2024-09-11 | 2024-10-14 | 2024-10-14 | 2024-10-14
48797 | 740-MKWH-R-H015-504-LH130-32-0 | 1 | true | 0.83 | 740-MKWH-R-H015-504-LH130-32-0 | LV1-103549.H015 | 362 |  |  | MC1 | LVL 6 | T60 | TR013_1 | 2024-04-14 | 2024-04-18 | 2024-04-18 |  | 2024-06-11 | 2024-06-12 | Büro | 2024-06-28 |  | 2024-06-14 | 2024-09-03 |  |  | 2024-09-05 | 804 | 150 |  | 2024-09-10 | 2024-09-09 | 149 | SEP | SEP | 2024-09-11 | 2024-10-14 | 2024-10-14 | 2024-10-14
48798 | 740-MKWH-S-H015-501-LH130-32-0 | 1 | true | 1.61 | 740-MKWH-S-H015-501-LH130-32-0 | LV1-103549.H015 | 362 |  |  | MC1 | LVL 6 | T60 | TR013_1 | 2024-04-14 | 2024-04-18 | 2024-04-18 |  | 2024-06-11 | 2024-06-13 | Büro | 2024-06-28 |  | 2024-06-18 | 2024-08-09 |  |  | 2024-08-13 | 804 | 150 |  | 2024-09-10 | 2024-09-09 | 149 | SEP | SEP | 2024-09-11 | 2024-10-14 | 2024-10-14 | 2024-10-14
48799 | 740-MKWH-S-H015-502-LH130-32-0 | 1 | true | 0.26 | 740-MKWH-S-H015-502-LH130-32-0 | LV1-103549.H015 | 362 |  |  | MC1 | LVL 6 | T60 | TR013_1 | 2024-04-14 | 2024-04-18 | 2024-04-18 |  | 2024-06-11 | 2024-06-13 | Büro | 2024-06-28 |  | 2024-06-17 | 2024-08-27 |  |  | 2024-08-29 | 804 | 150 |  | 2024-09-10 | 2024-09-09 | 149 | SEP | SEP | 2024-09-11 | 2024-10-14 | 2024-10-14 | 2024-10-14
48800 | 740-MKWH-S-H015-503-LH130-32-0 | 1 | true | 0.48 | 740-MKWH-S-H015-503-LH130-32-0 | LV1-103549.H015 | 362 |  |  | MC1 | LVL 6 | T60 | TR013_1 | 2024-04-14 | 2024-04-18 | 2024-04-18 |  | 2024-06-11 | 2024-06-13 | Büro | 2024-06-28 |  | 2024-06-18 | 2024-08-27 |  |  | 2024-08-29 | 804 | 150 |  | 2024-09-10 | 2024-09-09 | 149 | SEP | SEP | 2024-09-11 | 2024-10-14 | 2024-10-14 | 2024-10-14
48801 | 740-MKWH-S-H015-504-LH130-32-0 | 1 | true | 0.33 | 740-MKWH-S-H015-504-LH130-32-0 | LV1-103549.H015 | 362 |  |  | MC1 | LVL 6 | T60 | TR013_1 | 2024-04-14 | 2024-04-18 | 2024-04-18 |  | 2024-06-11 | 2024-06-13 | Büro | 2024-06-28 |  | 2024-06-17 | 2024-09-03 |  |  | 2024-09-05 | 804 | 150 |  | 2024-09-10 | 2024-09-09 | 149 | SEP | SEP | 2024-09-11 | 2024-10-14 | 2024-10-14 | 2024-10-14
49445 | 740-DR2-VU081-115-LH088-15-0 | 1 | true | 23.89 | 740-DR2-VU081-115-LH088-15-0 | LV0-105638.VU081 | 391 | 25.May.2024 |  | MC1 | LVL 5 | Tt-12 | TR013_2 | 2024-04-21 | 2024-04-23 | 2024-04-23 |  | 2024-05-14 | 2024-05-15 | Büro | 2024-05-31 |  | 2024-05-18 | 2024-06-19 |  | 2024-06-28 | 2024-10-04 | 1005 | 150 |  |  | 2024-11-14 | 149 | SEP | SEP | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22
49446 | 740-DR2-VU081-116-LH088-15-0 | 1 | false | 37.04 | 740-DR2-VU081-116-LH088-15-0 | LV0-105638.VU081 | 391 | 25.May.2024 |  | MC1 | LVL 5 | Tt-12 | TR013_2 | 2024-04-21 | 2024-04-23 | 2024-04-23 |  | 2024-05-13 | 2024-05-15 | Büro | 2024-05-17 |  | 2024-05-15 | 2024-06-19 |  | 2024-06-28 | 2024-10-04 | 1005 | 150 |  |  |  | 149 | SEP | SEP
52200 | 740-DR2-VU081-116-LH088-15-0 | 2 | false | 37.04 | 740-DR2-VU081-116-LH088-15-0 | LV0-105638.VU081 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR020_1 | 2024-05-29 | 2024-04-23 | 2024-04-23 |  | 2024-05-13 | 2024-05-15 |  | 2024-05-17 |  | 2024-05-15 |  |  |  |  | 1005 | 150 |  |  |  | 149 | SEP | SEP
52773 | 740-DR2-VU081-116-LH088-15-0 | 3 | true | 37.04 | 740-DR2-VU081-116-LH088-15-0 | LV0-105638.VU081 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR025_1 | 2024-06-18 | 2024-04-23 | 2024-04-23 |  | 2024-05-13 | 2024-05-15 | Büro | 2024-05-17 |  | 2024-05-15 | 2024-06-19 |  | 2024-06-28 | 2024-10-04 | 1005 | 150 |  |  | 2024-11-14 | 149 | SEP | SEP | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22
49447 | 740-DR2-VU081-117-LH088-15-0 | 1 | true | 12.55 | 740-DR2-VU081-117-LH088-15-0 | LV0-105638.VU081 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR013_2 | 2024-04-21 | 2024-04-23 | 2024-04-23 |  | 2024-06-12 | 2024-06-14 | Büro | 2024-06-28 |  | 2024-06-20 | 2024-07-10 |  | 2024-07-19 | 2024-09-27 | 1005 | 150 |  |  | 2024-11-14 | 149 | SEP | SEP | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22
49448 | 740-DR2-VU081-118-LH088-15-0 | 1 | false | 18.14 | 740-DR2-VU081-118-LH088-15-0 | LV0-105638.VU081 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR013_2 | 2024-04-21 | 2024-04-23 | 2024-04-23 | [11 empty] | 1005 | 150 |  |  |  | 149 | SEP | SEP
52201 | 740-DR2-VU081-118-LH088-15-0 | 2 | true | 18.14 | 740-DR2-VU081-118-LH088-15-0 | LV0-105638.VU081 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR020_1 | 2024-05-29 | 2024-04-23 | 2024-04-23 |  | 2024-06-17 | 2024-06-18 | Büro | 2024-06-28 |  | 2024-06-20 | 2024-07-10 |  | 2024-07-19 | 2024-09-20 | 1005 | 150 |  |  | 2024-09-24 | 149 | SEP | SEP | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22
49449 | 740-DR2-VU081-119-LH088-25-0 | 1 | true | 8.29 | 740-DR2-VU081-119-LH088-25-0 | LV0-105638.VU081 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR013_2 | 2024-04-21 | 2024-04-23 | 2024-04-23 |  | 2024-07-01 | 2024-07-02 | Büro | 2024-07-12 |  | 2024-07-05 | 2024-07-18 |  | 2024-07-26 | 2024-10-04 | 1005 | 150 |  |  | 2024-11-14 | 149 | SEP | SEP | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22
49450 | 740-DR2-VU081-120-LH088-25-0 | 1 | true | 8.05 | 740-DR2-VU081-120-LH088-25-0 | LV0-105638.VU081 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR013_2 | 2024-04-21 | 2024-04-23 | 2024-04-23 |  | 2024-06-28 | 2024-07-01 | Büro | 2024-07-12 |  | 2024-07-05 | 2024-10-22 |  | 2024-07-26 | 2024-10-30 | 1005 | 150 |  |  | 2024-10-31 | 149 | SEP | SEP | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22
49451 | 740-DR2-VU081-121-LH088-20-0 | 1 | true | 9.25 | 740-DR2-VU081-121-LH088-20-0 | LV0-105638.VU081 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR013_2 | 2024-04-21 | 2024-04-23 | 2024-04-23 |  | 2024-06-26 | 2024-06-27 | Büro | 2024-07-12 |  | 2024-07-05 | 2024-07-18 |  | 2024-07-26 | 2024-10-04 | 1005 | 150 |  |  | 2024-11-14 | 149 | SEP | SEP | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22
49452 | 740-DR2-VU081-123-LH088-15-0 | 1 | true | 12.98 | 740-DR2-VU081-123-LH088-15-0 | LV0-105638.VU081 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR013_2 | 2024-04-21 | 2024-04-23 | 2024-04-23 |  | 2024-06-07 | 2024-06-10 |  | 2024-06-14 |  | 2024-06-13 |  |  | 2024-06-28 | 2024-10-18 | 1005 | 150 |  |  | 2024-10-29 | 149 | SEP | SEP | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22
49453 | 740-DR2-VU081-124-LH088-25-0 | 1 | true | 9.17 | 740-DR2-VU081-124-LH088-25-0 | LV0-105638.VU081 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR013_2 | 2024-04-21 | 2024-04-23 | 2024-04-23 |  | 2024-06-28 | 2024-07-01 | Büro | 2024-07-12 |  | 2024-07-05 | 2024-07-18 |  | 2024-07-19 | 2024-09-27 | 1005 | 150 |  |  | 2024-11-14 | 149 | SEP | SEP | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22
49454 | 740-DR2-VU081-125-LH088-32-0 | 1 | true | 19.04 | 740-DR2-VU081-125-LH088-32-0 | LV0-105638.VU081 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR013_2 | 2024-04-21 | 2024-04-23 | 2024-04-23 |  | 2024-06-03 | 2024-06-06 | Büro | 2024-06-14 |  | 2024-06-06 |  |  | 2024-06-28 | 2024-09-27 | 1005 | 150 |  |  |  | 149 | SEP | SEP | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22
49455 | 740-DR2-VU081-126-LH088-32-0 | 1 | true | 16.72 | 740-DR2-VU081-126-LH088-32-0 | LV0-105638.VU081 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR013_2 | 2024-04-21 | 2024-04-23 | 2024-04-23 |  | 2024-05-23 | 2024-05-24 | Büro | 2024-05-31 |  | 2024-05-27 | 2024-06-11 |  | 2024-06-21 | 2024-10-04 | 1005 | 150 |  |  |  | 149 | SEP | SEP | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22
49456 | 740-DR2-VU081-128-LH088-25-0 | 1 | true | 7.16 | 740-DR2-VU081-128-LH088-25-0 | LV0-105638.VU081 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR013_2 | 2024-04-21 | 2024-04-23 | 2024-04-23 |  | 2024-06-25 | 2024-06-26 | Büro | 2024-06-28 |  | 2024-06-27 | 2024-07-09 |  | 2024-07-19 | 2024-09-27 | 1005 | 150 |  |  | 2024-11-14 | 149 | SEP | SEP | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22
49457 | 740-DR2-VU081-129-LH088-32-0 | 1 | true | 12.59 | 740-DR2-VU081-129-LH088-32-0 | LV0-105638.VU081 | 391 | 31.May.2024 |  | MC1 | LVL 5 | Tt-12 | TR013_2 | 2024-04-21 | 2024-04-23 | 2024-04-23 |  | 2024-05-14 | 2024-05-15 | Büro | 2024-05-31 |  | 2024-05-18 | 2024-06-11 |  | 2024-06-21 | 2024-09-27 | 1005 | 150 |  |  | 2024-11-14 | 149 | SEP | SEP | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22
49458 | 740-DR2-VU081-130-LH088-32-0 | 1 | true | 8.78 | 740-DR2-VU081-130-LH088-32-0 | LV0-105638.VU081 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR013_2 | 2024-04-21 | 2024-04-23 | 2024-04-23 |  | 2024-05-23 | 2024-05-24 | Büro | 2024-05-31 |  | 2024-05-27 | 2024-06-11 |  | 2024-06-21 | 2024-09-27 | 1005 | 150 |  |  |  | 149 | SEP | SEP | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22
49459 | 740-DR2-VU081-132-LH088-25-0 | 1 | true | 11.78 | 740-DR2-VU081-132-LH088-25-0 | LV0-105638.VU081 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR013_2 | 2024-04-21 | 2024-04-23 | 2024-04-23 |  | 2024-06-26 | 2024-06-27 | Büro | 2024-06-28 |  | 2024-06-28 | 2024-07-04 | 2024-08-23 |  | 2024-09-20 | 1005 | 150 |  |  | 2024-09-24 | 149 | SEP | SEP | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22
49460 | 740-DR2-VU081-133-LH088-25-0 | 1 | true | 15.33 | 740-DR2-VU081-133-LH088-25-0 | LV0-105638.VU081 | 391 | 31.May.2024 |  | MC1 | LVL 5 | Tt-12 | TR013_2 | 2024-04-21 | 2024-04-23 | 2024-04-23 |  | 2024-05-17 | 2024-05-21 | Büro | 2024-05-31 |  | 2024-05-22 |  |  | 2024-06-21 | 2024-09-20 | 1005 | 150 |  |  | 2024-09-24 | 149 | SEP | SEP | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22
49461 | 740-DR2-VU081-134-LH088-20-0 | 1 | true | 9.01 | 740-DR2-VU081-134-LH088-20-0 | LV0-105638.VU081 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR013_2 | 2024-04-21 | 2024-04-23 | 2024-04-23 |  | 2024-06-20 | 2024-06-21 | Büro | 2024-06-28 |  | 2024-06-26 | 2024-07-04 | 2024-08-23 |  | 2024-09-20 | 1005 | 150 |  |  | 2024-09-24 | 149 | SEP | SEP | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22
49462 | 740-DR2-VU081-135-LH088-15-0 | 1 | false | 17.65 | 740-DR2-VU081-135-LH088-15-0 | LV0-105638.VU081 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR013_2 | 2024-04-21 | 2024-04-23 | [12 empty] | 1005 | 150 |  |  |  | 149 | SEP | SEP
49639 | 740-DR2-VU081-135-LH088-15-0 | 2 | true | 17.65 | 740-DR2-VU081-135-LH088-15-0 | LV0-105638.VU081 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR014_1 | 2024-04-22 | 2024-04-29 | 2024-04-29 |  | 2024-06-25 | 2024-06-27 | Büro | 2024-06-28 |  | 2024-06-28 | 2024-07-04 |  | 2024-08-23 | 2024-11-08 | 1005 | 150 |  |  |  | 149 | SEP | SEP | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22
49463 | 740-DR2-VU081-136-LH088-25-0 | 1 | true | 9.65 | 740-DR2-VU081-136-LH088-25-0 | LV0-105638.VU081 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR013_2 | 2024-04-21 | 2024-04-23 | 2024-04-23 |  | 2024-06-25 | 2024-06-26 | Dawid Mierzwa | 2024-06-28 |  | 2024-06-27 | 2024-07-04 | 2024-08-30 | 2024-08-23 | 2024-08-30 | 1005 | 150 |  |  | 2024-09-13 | 149 | SEP | SEP | 2024-09-26 | 2024-11-22 | 2024-11-22 | 2024-11-22
49464 | 740-DR2-VU081-137-LH088-15-0 | 1 | true | 11.36 | 740-DR2-VU081-137-LH088-15-0 | LV0-105638.VU081 | 391 |  |  | MC1 | LVL 5 | W23 | TR013_2 | 2024-04-21 | 2024-04-23 | 2024-04-23 |  | 2024-06-10 | 2024-06-11 | Büro | 2024-06-28 |  | 2024-06-20 | 2024-07-04 | 2024-08-23 |  | 2024-09-20 | 1005 | 150 |  |  | 2024-09-24 | 149 | SEP | SEP | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22
49465 | 740-DR2-VU081-138-LH088-25-0 | 1 | true | 6.94 | 740-DR2-VU081-138-LH088-25-0 | LV0-105638.VU081 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR013_2 | 2024-04-21 | 2024-04-23 | 2024-04-23 |  | 2024-06-25 | 2024-06-26 | Dawid Mierzwa | 2024-06-28 |  | 2024-06-27 | 2024-07-04 | 2024-08-23 | 2024-08-23 | 2024-08-30 | 1005 | 150 |  |  | 2024-09-18 | 149 | SEP | SEP | 2024-09-26 | 2024-11-22 | 2024-11-22 | 2024-11-22
49466 | 740-DR2-VU081-139-LH088-15-0 | 1 | false | 22.89 | 740-DR2-VU081-139-LH088-15-0 | LV0-105638.VU081 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR013_2 | 2024-04-21 | 2024-04-23 | 2024-04-23 | [11 empty] | 1005 | 150 |  |  |  | 149 | SEP | SEP
52204 | 740-DR2-VU081-139-LH088-15-0 | 2 | true | 22.89 | 740-DR2-VU081-139-LH088-15-0 | LV0-105638.VU081 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR020_1 | 2024-05-29 | 2024-04-23 | 2024-04-23 |  | 2024-06-14 | 2024-06-17 | Büro | 2024-06-28 |  | 2024-06-21 | 2024-07-23 | 2024-08-23 | 2024-08-09 | 2024-09-06 | 1005 | 150 |  |  | 2024-09-18 | 149 | SEP | SEP | 2024-09-26 | 2024-11-22 | 2024-11-22 | 2024-11-22
49467 | 740-DR2-VU081-141-LH088-20-0 | 1 | true | 5.64 | 740-DR2-VU081-141-LH088-20-0 | LV0-105638.VU081 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR013_2 | 2024-04-21 | 2024-04-23 | 2024-04-23 |  | 2024-06-24 | 2024-06-25 | Büro | 2024-06-28 |  | 2024-06-26 | 2024-07-03 |  |  | 2024-09-06 | 1005 | 150 |  |  | 2024-09-18 | 149 | SEP | SEP | 2024-09-26 | 2024-11-22 | 2024-11-22 | 2024-11-22
49468 | 740-DR2-VU081-142-LH088-20-0 | 1 | true | 7.94 | 740-DR2-VU081-142-LH088-20-0 | LV0-105638.VU081 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR013_2 | 2024-04-21 | 2024-04-23 | 2024-04-23 |  | 2024-06-24 | 2024-06-26 | Büro | 2024-06-28 |  | 2024-06-27 | 2024-07-03 |  |  | 2024-09-06 | 1005 | 150 |  |  | 2024-09-18 | 149 | SEP | SEP | 2024-09-26 | 2024-11-22 | 2024-11-22 | 2024-11-22
49469 | 740-DR2-VU081-144-LH088-20-0 | 1 | false | 28.03 | 740-DR2-VU081-144-LH088-20-0 | LV0-105638.VU081 | 391 | 25.May.2024 |  | MC1 | LVL 5 | Tt-12 | TR013_2 | 2024-04-21 | 2024-04-23 | 2024-04-23 |  | 2024-05-13 | 2024-05-15 | Büro | 2024-05-17 |  | 2024-05-15 | 2024-06-03 | 2024-06-07 | 2024-06-21 | 2024-10-10 | 1005 | 150 |  |  |  | 149 | SEP | SEP
52268 | 740-DR2-VU081-144-LH088-20-0 | 2 | true | 28.03 | 740-DR2-VU081-144-LH088-20-0 | LV0-105638.VU081 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR021_1 | 2024-06-04 | 2024-04-23 | 2024-04-23 |  | 2024-05-13 | 2024-05-15 | Büro | 2024-05-17 |  | 2024-05-15 | 2024-06-03 |  | 2024-06-21 | 2024-10-10 | 1005 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-11-15 | 2024-11-15
49470 | 740-DR3-VU081-118-LH088-8-0 | 1 | true | 0 | 740-DR3-VU081-118-LH088-8-0 | LV0-105638.VU081 | 391 |  |  | MC1 | LVL 5 | W23 | TR013_2 | 2024-04-21 | 2024-04-23 | 2024-04-23 |  | 2024-06-13 | 2024-06-14 | Büro | 2024-06-28 |  | 2024-06-20 |  |  |  | 2024-10-04 | 911 | 150 |  |  |  | 149 | SEP | SEP
49471 | 740-HKK-R-VP001-102-LH099-50-0 | 1 | true | 6.08 | 740-HKK-R-VP001-102-LH099-50-0 | LV1-105630.VP001 | 386 |  |  | MC1 | LVL 5 | WK60 | TR013_2 | 2024-04-21 | 2024-04-24 | 2024-04-26 |  | 2024-06-06 | 2024-06-08 | Büro | 2024-06-14 |  | 2024-06-08 | 2024-08-27 |  |  | 2024-08-29 | 1006 | 150 |  | 2024-11-13 | 2024-09-02 | 149 | SEP | SEP |  |  | 2024-11-15 | 2024-11-15
49472 | 740-HKK-R-VP002-102-LH099-50-0 | 1 | true | 6.78 | 740-HKK-R-VP002-102-LH099-50-0 | LV1-105630.VP002 | 386 |  |  | MC1 | LVL 5 | WK60 | TR013_2 | 2024-04-21 | 2024-04-24 | 2024-04-26 |  | 2024-06-06 | 2024-06-08 | Büro | 2024-06-14 |  | 2024-06-08 | 2024-09-02 |  |  | 2024-09-04 | 1006 | 150 |  | 2024-11-13 | 2024-09-09 | 149 | SEP | SEP |  |  | 2024-11-30 | 2024-11-30
49473 | 740-HKK-R-VP003-102-LH099-40-0 | 1 | true | 18.23 | 740-HKK-R-VP003-102-LH099-40-0 | LV1-105630.VP003 | 386 | 25.May.2024 |  | MC1 | LVL 5 | WK60 | TR013_2 | 2024-04-21 | 2024-04-24 | 2024-04-26 |  | 2024-05-14 | 2024-05-16 | Büro | 2024-05-31 |  | 2024-05-18 | 2024-09-03 | 2024-06-21 | 2024-06-21 | 2024-09-06 | 1006 | 150 |  |  | 2024-09-09 | 149 | SEP | SEP |  |  | 2024-11-30 | 2024-11-30
49474 | 740-HKK-R-VP004-102-LH099-40-0 | 1 | true | 21.26 | 740-HKK-R-VP004-102-LH099-40-0 | LV1-105630.VP004 | 386 | 25.May.2024 |  | MC1 | LVL 5 | WK60 | TR013_2 | 2024-04-21 | 2024-04-24 | 2024-04-26 |  | 2024-05-14 | 2024-05-16 | Büro | 2024-05-31 |  | 2024-05-18 | 2024-08-22 |  |  | 2024-09-03 | 1006 | 150 |  |  | 2024-09-09 | 149 | SEP | SEP |  |  | 2024-11-30 | 2024-11-30
49475 | 740-HKK-R-VP031-103-LH099-50-0 | 1 | true | 7.48 | 740-HKK-R-VP031-103-LH099-50-0 | LV1-105629.VP031 | 386 |  |  | MC1 | LVL 5 | WK60 | TR013_2 | 2024-04-21 | 2024-04-24 | 2024-04-26 |  | 2024-06-06 | 2024-06-07 | Büro | 2024-06-14 |  | 2024-06-07 |  | 2024-07-16 |  | 2024-10-25 | 1006 | 150 |  | 2024-11-18 | 2024-11-12 | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
49476 | 740-HKK-R-VP032-103-LH099-50-0 | 1 | true | 13.72 | 740-HKK-R-VP032-103-LH099-50-0 | LV1-105629.VP032 | 386 |  |  | MC1 | LVL 5 | WK60 | TR013_2 | 2024-04-21 | 2024-04-24 | 2024-04-26 |  | 2024-06-06 | 2024-06-08 | Büro | 2024-06-14 |  | 2024-06-08 | 2024-07-10 | 2024-07-15 |  | 2024-10-30 | 1006 | 150 |  | 2024-11-18 | 2024-11-12 | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
49477 | 740-HKK-R-VP033-103-LH099-50-0 | 1 | true | 12.88 | 740-HKK-R-VP033-103-LH099-50-0 | LV1-105629.VP033 | 386 |  |  | MC1 | LVL 5 | WK60 | TR013_2 | 2024-04-21 | 2024-04-24 | 2024-04-26 |  | 2024-06-06 | 2024-06-11 | Büro | 2024-06-28 |  | 2024-06-11 | 2024-07-12 | 2024-07-16 |  | 2024-10-30 | 1006 | 150 |  | 2024-11-18 | 2024-11-13 | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
49478 | 740-HKK-R-VP041-103-LH099-50-0 | 1 | true | 6.45 | 740-HKK-R-VP041-103-LH099-50-0 | LV1-105629.VP041 | 386 |  |  | MC1 | LVL 5 | WK60 | TR013_2 | 2024-04-21 | 2024-04-24 | 2024-04-26 |  | 2024-06-06 | 2024-06-08 | Büro | 2024-06-14 |  | 2024-06-08 | 2024-07-16 | 2024-07-19 |  | 2024-10-24 | 1006 | 150 |  | 2024-11-18 |  | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
49479 | 740-HKK-R-VP042-103-LH099-50-0 | 1 | true | 12.61 | 740-HKK-R-VP042-103-LH099-50-0 | LV1-105629.VP042 | 386 |  |  | MC1 | LVL 5 | WK60 | TR013_2 | 2024-04-21 | 2024-04-24 | 2024-04-26 |  | 2024-06-06 | 2024-06-11 | Büro | 2024-06-28 |  | 2024-06-13 |  |  |  | 2024-10-15 | 1006 | 150 |  | 2024-11-18 |  | 149 | SEP | SEP |  |  | 2024-11-30 | 2024-11-30
49480 | 740-HKK-R-VP043-103-LH099-50-0 | 1 | true | 11.91 | 740-HKK-R-VP043-103-LH099-50-0 | LV1-105629.VP043 | 386 |  |  | MC1 | LVL 5 | WK60 | TR013_2 | 2024-04-21 | 2024-04-24 | 2024-04-26 |  | 2024-06-06 | 2024-06-12 | Büro | 2024-06-28 |  | 2024-06-13 | 2024-07-18 | 2024-07-23 |  | 2024-10-30 | 1006 | 150 |  |  | 2024-11-14 | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
49481 | 740-HKK-R-VP131-102-LH099-40-0 | 1 | true | 17.6 | 740-HKK-R-VP131-102-LH099-40-0 | LV1-105629.VP131 | 386 | 25.May.2024 |  | MC1 | LVL 5 | WK60 | TR013_2 | 2024-04-21 | 2024-04-24 | 2024-04-26 |  | 2024-05-14 | 2024-05-17 | Büro | 2024-05-31 |  | 2024-05-20 | 2024-06-27 |  | 2024-07-03 | 2024-10-30 | 1006 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-12-20 | 2024-12-20
49482 | 740-HKK-R-VP132-102-LH099-40-0 | 1 | true | 9.2 | 740-HKK-R-VP132-102-LH099-40-0 | LV1-105629.VP132 | 386 |  |  | MC1 | LVL 5 | WK60 | TR013_2 | 2024-04-21 | 2024-04-24 | 2024-04-26 |  | 2024-06-06 | 2024-06-10 | Büro | 2024-06-14 |  | 2024-06-10 | 2024-07-02 | 2024-07-16 | 2024-07-05 | 2024-10-23 | 1006 | 150 |  |  | 2024-10-30 | 149 | SEP | SEP |  |  | 2024-12-20 | 2024-12-20
49483 | 740-HKK-R-VP133-102-LH099-40-0 | 1 | true | 14.09 | 740-HKK-R-VP133-102-LH099-40-0 | LV1-105629.VP133 | 386 | 25.May.2024 |  | MC1 | LVL 5 | WK60 | TR013_2 | 2024-04-21 | 2024-04-24 | 2024-04-26 |  | 2024-05-14 | 2024-05-15 | Büro | 2024-05-31 |  | 2024-05-17 | 2024-06-27 |  | 2024-07-09 | 2024-10-24 | 1006 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-12-20 | 2024-12-20
49484 | 740-HKK-R-VP141-102-LH099-40-0 | 1 | true | 10.11 | 740-HKK-R-VP141-102-LH099-40-0 | LV1-105629.VP141 | 386 | 25.May.2024 |  | MC1 | LVL 5 | WK60 | TR013_2 | 2024-04-21 | 2024-04-24 | 2024-04-26 |  | 2024-05-14 | 2024-05-15 | Büro | 2024-05-17 |  | 2024-05-16 | 2024-09-19 |  |  | 2024-09-19 | 1006 | 150 |  |  | 2024-09-25 | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
49485 | 740-HKK-R-VP142-102-LH099-40-0 | 1 | true | 10.16 | 740-HKK-R-VP142-102-LH099-40-0 | LV1-105629.VP142 | 386 |  |  | MC1 | LVL 5 | WK60 | TR013_2 | 2024-04-21 | 2024-04-24 | 2024-04-26 |  | 2024-06-12 | 2024-06-18 | Büro | 2024-06-28 |  | 2024-06-20 | 2024-09-20 |  |  | 2024-09-25 | 1006 | 150 |  |  |  | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
49486 | 740-HKK-R-VP143-102-LH099-40-0 | 1 | true | 7.99 | 740-HKK-R-VP143-102-LH099-40-0 | LV1-105629.VP143 | 386 |  |  | MC1 | LVL 5 | WK60 | TR013_2 | 2024-04-21 | 2024-04-24 | 2024-04-26 |  | 2024-06-12 | 2024-06-14 | Büro | 2024-06-28 |  | 2024-06-20 | 2024-09-03 |  |  | 2024-09-12 | 1006 | 150 |  |  | 2024-09-12 | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
49487 | 740-HKK-S-VP001-104-LH099-50-0 | 1 | true | 7.41 | 740-HKK-S-VP001-104-LH099-50-0 | LV1-105630.VP001 | 386 |  |  | MC1 | LVL 5 | WK60 | TR013_2 | 2024-04-21 | 2024-04-24 | 2024-04-26 |  | 2024-06-12 | 2024-06-14 | Büro | 2024-06-28 |  | 2024-06-19 | 2024-08-27 |  |  | 2024-08-29 | 1006 | 150 |  | 2024-11-13 | 2024-09-02 | 149 | SEP | SEP |  |  | 2024-11-15 | 2024-11-15
49488 | 740-HKK-S-VP002-104-LH099-50-0 | 1 | true | 7.3 | 740-HKK-S-VP002-104-LH099-50-0 | LV1-105630.VP002 | 386 |  |  | MC1 | LVL 5 | Tt-12 | TR013_2 | 2024-04-21 | 2024-04-24 | 2024-04-26 |  | 2024-06-12 | 2024-06-15 | Büro | 2024-06-28 |  | 2024-06-19 | 2024-09-02 |  |  | 2024-09-04 | 1006 | 150 |  |  | 2024-09-09 | 149 | SEP | SEP |  |  | 2024-11-30 | 2024-11-30
49489 | 740-HKK-S-VP003-104-LH099-40-0 | 1 | true | 19.73 | 740-HKK-S-VP003-104-LH099-40-0 | LV1-105630.VP003 | 386 | 25.May.2024 |  | MC1 | LVL 5 | WK60 | TR013_2 | 2024-04-21 | 2024-04-24 | 2024-04-26 |  | 2024-05-14 | 2024-05-17 | Büro | 2024-05-31 |  | 2024-05-18 | 2024-09-03 |  | 2024-06-21 | 2024-09-05 | 1006 | 150 |  |  | 2024-09-09 | 149 | SEP | SEP |  |  | 2024-11-30 | 2024-11-30
49490 | 740-HKK-S-VP004-104-LH099-40-0 | 1 | true | 20.72 | 740-HKK-S-VP004-104-LH099-40-0 | LV1-105630.VP004 | 386 | 25.May.2024 |  | MC1 | LVL 5 | WK60 | TR013_2 | 2024-04-21 | 2024-04-24 | 2024-04-26 |  | 2024-05-14 | 2024-05-14 | Büro | 2024-05-17 |  | 2024-05-16 | 2024-08-22 |  |  | 2024-09-03 | 1006 | 150 |  |  | 2024-09-09 | 149 | SEP | SEP |  |  | 2024-11-30 | 2024-11-30 | 2024-12-06 | 2024-12-06
49491 | 740-HKK-S-VP031-104-LH099-50-0 | 1 | true | 7.33 | 740-HKK-S-VP031-104-LH099-50-0 | LV1-105629.VP031 | 386 |  |  | MC1 | LVL 5 | WK60 | TR013_2 | 2024-04-21 | 2024-04-24 | 2024-04-26 |  | 2024-06-12 | 2024-06-14 | Büro | 2024-06-28 |  | 2024-06-19 |  | 2024-07-16 |  | 2024-10-25 | 1006 | 150 |  |  | 2024-11-12 | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
49492 | 740-HKK-S-VP032-104-LH099-50-0 | 1 | true | 15.29 | 740-HKK-S-VP032-104-LH099-50-0 | LV1-105629.VP032 | 386 |  |  | MC1 | LVL 5 | WK60 | TR013_2 | 2024-04-21 | 2024-04-24 | 2024-04-26 |  | 2024-06-12 | 2024-06-14 | Büro | 2024-06-28 |  | 2024-06-20 | 2024-07-10 |  | 2024-07-15 | 2024-10-30 | 1006 | 150 |  |  | 2024-11-12 | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
49493 | 740-HKK-S-VP033-104-LH099-50-0 | 1 | true | 14.4 | 740-HKK-S-VP033-104-LH099-50-0 | LV1-105629.VP033 | 386 |  |  | MC1 | LVL 5 | WK60 | TR013_2 | 2024-04-21 | 2024-04-24 | 2024-04-26 |  | 2024-06-12 | 2024-06-12 | Büro | 2024-06-28 |  | 2024-06-14 | 2024-07-12 | 2024-07-19 |  | 2024-10-30 | 1006 | 150 |  |  | 2024-11-13 | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
49494 | 740-HKK-S-VP041-104-LH099-50-0 | 1 | true | 7.14 | 740-HKK-S-VP041-104-LH099-50-0 | LV1-105629.VP041 | 386 |  |  | MC1 | LVL 5 | WK60 | TR013_2 | 2024-04-21 | 2024-04-24 | 2024-04-26 |  | 2024-06-12 | 2024-06-14 | Büro | 2024-06-28 |  | 2024-06-17 | 2024-07-16 | 2024-07-19 |  | 2024-10-24 | 1006 | 150 |  |  | 2024-11-14 | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
49495 | 740-HKK-S-VP042-204-LH099-50-0 | 1 | true | 13.2 | 740-HKK-S-VP042-204-LH099-50-0 | LV1-105629.VP042 | 386 |  |  | MC1 | LVL 5 | WK60 | TR013_2 | 2024-04-21 | 2024-04-24 | 2024-04-26 |  | 2024-06-12 | 2024-06-17 | Büro | 2024-06-28 |  | 2024-06-20 |  |  |  | 2024-10-15 | 1006 | 150 |  |  | 2024-11-14 | 149 | SEP | SEP |  |  | 2024-11-30 | 2024-11-30
49496 | 740-HKK-S-VP043-204-LH099-50-0 | 1 | true | 12.72 | 740-HKK-S-VP043-204-LH099-50-0 | LV1-105629.VP043 | 386 |  |  | MC1 | LVL 5 | WK60 | TR013_2 | 2024-04-21 | 2024-04-24 | 2024-04-26 |  | 2024-06-12 | 2024-06-14 | Büro | 2024-06-28 |  | 2024-06-18 | 2024-07-19 | 2024-07-23 |  | 2024-10-28 | 1006 | 150 |  |  | 2024-10-30 | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
49497 | 740-HKK-S-VP131-101-LH099-40-0 | 1 | true | 18.14 | 740-HKK-S-VP131-101-LH099-40-0 | LV1-105629.VP131 | 386 | 25.May.2024 |  | MC1 | LVL 5 | WK60 | TR013_2 | 2024-04-21 | 2024-04-24 | 2024-04-26 |  | 2024-05-14 | 2024-05-17 | Büro | 2024-05-31 |  | 2024-05-21 | 2024-06-27 |  | 2024-07-03 | 2024-10-30 | 1006 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-12-20 | 2024-12-20
49498 | 740-HKK-S-VP132-101-LH099-40-0 | 1 | true | 7.79 | 740-HKK-S-VP132-101-LH099-40-0 | LV1-105629.VP132 | 386 |  |  | MC1 | LVL 5 | WK60 | TR013_2 | 2024-04-21 | 2024-04-24 | 2024-04-26 |  | 2024-06-12 | 2024-06-15 | Büro | 2024-06-28 |  | 2024-06-20 | 2024-07-18 | 2024-07-23 |  | 2024-10-23 | 1006 | 150 |  |  | 2024-10-30 | 149 | SEP | SEP |  |  | 2024-12-20 | 2024-12-20
49499 | 740-HKK-S-VP133-101-LH099-40-0 | 1 | true | 14.95 | 740-HKK-S-VP133-101-LH099-40-0 | LV1-105629.VP133 | 386 | 25.May.2024 |  | MC1 | LVL 5 | WK60 | TR013_2 | 2024-04-21 | 2024-04-24 | 2024-04-26 |  | 2024-05-14 | 2024-05-20 | Büro | 2024-05-31 |  | 2024-05-21 | 2024-06-27 |  | 2024-07-05 | 2024-10-24 | 1006 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-12-20 | 2024-12-20
49500 | 740-HKK-S-VP141-101-LH099-40-0 | 1 | true | 11.27 | 740-HKK-S-VP141-101-LH099-40-0 | LV1-105629.VP141 | 386 | 25.May.2024 |  | MC1 | LVL 5 | WK60 | TR013_2 | 2024-04-21 | 2024-04-24 | 2024-04-26 |  | 2024-05-14 | 2024-05-15 | Büro | 2024-05-17 |  | 2024-05-16 | 2024-09-19 |  |  | 2024-09-19 | 1006 | 150 |  |  | 2024-09-25 | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
49501 | 740-HKK-S-VP142-204-LH099-40-0 | 1 | false | 9.76 | 740-HKK-S-VP142-204-LH099-40-0 | LV1-105629.VP142 | 386 |  |  | MC1 | LVL 5 | WK60 | TR013_2 | 2024-04-21 | 2024-04-24 | 2024-04-26 |  | 2024-06-12 | 2024-06-17 |  | 2024-06-28 |  | 2024-06-19 |  |  |  |  | 1006 | 150 |  |  |  | 149 | SEP | SEP
49502 | 740-HKK-S-VP143-204-LH099-40-0 | 1 | false | 10.33 | 740-HKK-S-VP143-204-LH099-40-0 | LV1-105629.VP143 | 386 |  |  | MC1 | LVL 5 | WK60 | TR013_2 | 2024-04-21 | 2024-04-24 | 2024-04-26 |  | 2024-06-12 | 2024-06-14 |  | 2024-06-28 |  | 2024-06-19 | 2024-07-19 |  |  |  | 1006 | 150 |  |  |  | 149 | SEP | SEP
49507 | 740-LS-VU020-154-LH023-25-0 | 2 | false | 6.64 | 740-LS-VU020-154-LH023-25-0 | LV1-105638.VU020 | 368 | 25.May.2024 |  | MC1 | LVL 5 | N/A | TR013_2 | 2024-04-21 | 2024-04-23 | [12 empty] | 926 | 150 |  |  |  | 149 | SEP | SEP
49644 | 740-LS-VU020-154-LH023-25-0 | 3 | true | 6.64 | 740-LS-VU020-154-LH023-25-0 | LV1-105638.VU020 | 368 |  |  | MC1 | LVL 5 | N/A | TR014_1 | 2024-04-22 | 2024-04-29 | 2024-04-29 |  | 2024-06-11 | 2024-06-12 | Büro | 2024-06-28 |  | 2024-06-14 | 2024-08-06 |  |  | 2024-08-08 | 926 | 150 |  |  | 2024-09-02 | 149 | SEP | SEP
49509 | 740-WFI-VS681-101-LH089-40-0 | 1 | true | 1.74 | 740-WFI-VS681-101-LH089-40-0 | LV0-105633.VS681 | 394 |  |  | MC1 | LVL 5 | Tt-12 | TR013_2 | 2024-04-21 | 2024-04-23 | 2024-04-23 |  | 2024-05-30 | 2024-06-06 | Büro | 2024-06-14 |  | 2024-06-06 |  |  |  | 2024-10-24 | 938 | 150 |  | 2024-11-12 | 2024-10-28 | 149 | SEP | SEP |  |  | 2024-11-15 | 2024-11-15
49510 | 740-WFI-VS681-104-LH089-40-0 | 1 | true | 1.81 | 740-WFI-VS681-104-LH089-40-0 | LV0-105633.VS681 | 394 |  |  | MC1 | LVL 5 | Tt-12 | TR013_2 | 2024-04-21 | 2024-04-23 | 2024-04-23 |  | 2024-05-30 | 2024-06-04 | Büro | 2024-06-14 |  | 2024-06-04 |  |  |  | 2024-10-24 | 938 | 150 |  | 2024-11-12 | 2024-10-28 | 149 | SEP | SEP |  |  | 2024-11-15 | 2024-11-15
49511 | 740-WFI-VS681-201-LH089-32-0 | 1 | true | 2.82 | 740-WFI-VS681-201-LH089-32-0 | LV0-105634.VS681 | 394 |  |  | MC1 | LVL 5 | Tt-12 | TR013_2 | 2024-04-21 | 2024-04-23 | 2024-04-23 |  | 2024-06-10 | 2024-06-11 |  | 2024-06-14 |  | 2024-06-13 | 2024-09-25 |  |  | 2024-10-18 | 938 | 150 |  | 2024-11-12 | 2024-10-29 | 149 | SEP | SEP
49512 | 740-WFI-VS681-204-LH089-32-0 | 1 | true | 2.83 | 740-WFI-VS681-204-LH089-32-0 | LV0-105634.VS681 | 394 |  |  | MC1 | LVL 5 | Tt-12 | TR013_2 | 2024-04-21 | 2024-04-23 | 2024-04-23 |  | 2024-06-10 | 2024-06-11 |  | 2024-06-14 |  | 2024-06-13 | 2024-09-25 |  |  | 2024-10-18 | 938 | 150 |  | 2024-11-12 | 2024-10-29 | 149 | SEP | SEP
49632 | 740-DK-VU116-125-LH011-20-0 | 2 | true | 2.45 | 740-DK-VU116-125-LH011-20-0 | LV1-105638.VU116 | 369 |  |  | MC1 | LVL 5 | W23 | TR014_1 | 2024-04-22 | 2024-04-29 | 2024-04-29 |  | 2024-06-07 | 2024-06-11 | Büro | 2024-06-28 |  | 2024-06-11 |  |  |  | 2024-09-24 | 986 | 150 |  | 2024-10-25 | 2024-09-27 | 149 | SEP | SEP |  |  | 2024-11-01 | 2024-11-01
49633 | 740-DK-VU116-126-LH011-20-0 | 2 | true | 2.36 | 740-DK-VU116-126-LH011-20-0 | LV1-105638.VU116 | 369 |  |  | MC1 | LVL 5 | W23 | TR014_1 | 2024-04-22 | 2024-04-29 | 2024-04-29 |  | 2024-06-07 | 2024-06-10 | Büro | 2024-06-28 |  | 2024-06-10 |  |  |  | 2024-09-25 | 986 | 150 |  | 2024-10-25 |  | 149 | SEP | SEP |  |  | 2024-11-01 | 2024-11-01
49637 | 740-DR2-VU081-127-LH088-15-0 | 2 | false | 15.28 | 740-DR2-VU081-127-LH088-15-0 | LV0-105638.VU081 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR014_1 | 2024-04-22 | 2024-04-29 | 2024-04-29 | [11 empty] | 1005 | 150 |  |  |  | 149 | SEP | SEP
52202 | 740-DR2-VU081-127-LH088-15-0 | 3 | true | 15.28 | 740-DR2-VU081-127-LH088-15-0 | LV0-105638.VU081 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR020_1 | 2024-05-29 | 2024-04-29 | 2024-04-29 |  | 2024-06-14 | 2024-06-17 | Büro | 2024-06-28 |  | 2024-06-20 | 2024-07-09 |  | 2024-07-19 | 2024-09-16 | 1005 | 150 |  |  | 2024-09-19 | 149 | SEP | SEP |  |  | 2024-11-15 | 2024-11-22
49638 | 740-DR2-VU081-131-LH088-15-0 | 2 | false | 24.11 | 740-DR2-VU081-131-LH088-15-0 | LV0-105638.VU081 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR014_1 | 2024-04-22 | 2024-04-29 | 2024-04-29 | [11 empty] | 1005 | 150 |  |  |  | 149 | SEP | SEP
52203 | 740-DR2-VU081-131-LH088-15-0 | 3 | true | 24.11 | 740-DR2-VU081-131-LH088-15-0 | LV0-105638.VU081 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR020_1 | 2024-05-29 | 2024-04-29 | 2024-04-29 |  | 2024-06-10 | 2024-06-14 | Büro | 2024-06-28 |  | 2024-06-20 | 2024-07-04 |  | 2024-08-23 | 2024-09-16 | 1005 | 150 |  |  | 2024-09-19 | 149 | SEP | SEP |  |  | 2024-11-15 | 2024-11-22
49640 | 740-DR2-VU081-143-LH088-15-0 | 2 | false | 17.79 | 740-DR2-VU081-143-LH088-15-0 | LV0-105638.VU081 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR014_1 | 2024-04-22 | 2024-04-29 | 2024-04-29 | [11 empty] | 1005 | 150 |  |  |  | 149 | SEP | SEP
50139 | 740-DR2-VU081-143-LH088-15-0 | 3 | false | 17.79 | 740-DR2-VU081-143-LH088-15-0 | LV0-105638.VU081 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR015_1 | 2024-04-30 | 2024-04-28 | 2024-04-28 | [11 empty] | 1005 | 150 |  |  |  | 149 | SEP | SEP
52205 | 740-DR2-VU081-143-LH088-15-0 | 4 | true | 17.79 | 740-DR2-VU081-143-LH088-15-0 | LV0-105638.VU081 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR020_1 | 2024-05-29 | 2024-04-28 | 2024-04-28 |  | 2024-06-24 | 2024-06-26 | Dawid Mierzwa | 2024-06-28 |  | 2024-06-27 | 2024-07-03 | 2024-08-23 | 2024-08-09 | 2024-08-30 | 1005 | 150 |  |  |  | 149 | SEP | SEP | 2024-09-26 | 2024-11-22 | 2024-11-22 | 2024-11-22
49643 | 740-LP-VS681-203-LH099-25-0 | 1 | true | 0.24 | 740-LP-VS681-203-LH099-25-0 | LV0-105634.VS681 | 386 |  |  | MC1 | LVL 5 | N/A | TR014_1 | 2024-04-22 | 2024-04-29 | 2024-04-29 |  | 2024-06-11 | 2024-06-17 | Büro | 2024-06-28 |  | 2024-06-19 | 2024-10-09 |  |  | 2024-10-10 | 929 | 150 |  | 2024-11-12 |  | 149 | SEP | SEP
49645 | 740-MKWH-R-VH005-207-LH130-20-0 | 1 | false | 49.9 | 740-MKWH-R-VH005-207-LH130-20-0 | LV0-105624.VH005 | 362 | 2.Juny.2024 |  | MC1 | LVL 5 | T60 | TR014_1 | 2024-04-22 | 2024-04-29 | 2024-04-29 |  | 2024-05-20 | 2024-05-25 | Büro | 2024-05-31 |  | 2024-05-25 | 2024-06-27 |  |  | 2024-07-05 | 1017 | 150 |  |  | 2024-07-22 | 149 | SEP | SEP
62773 | 740-MKWH-R-VH005-207-LH130-20-0 | 2 | false | 49.9 | 740-MKWH-R-VH005-207-LH130-20-0 | LV0-105624.VH005 | 362 |  |  | MC1 | LVL 5 | T60 | TR029_3 | 2024-08-07 | 2024-04-29 | 2024-04-29 |  | 2024-05-20 | 2024-05-25 |  | 2024-05-31 |  | 2024-05-25 | 2024-06-27 |  |  | 2024-07-05 | 1017 | 150 |  |  | 2024-07-22 | 149 | SEP | SEP
62838 | 740-MKWH-R-VH005-207-LH130-20-0 | 3 | true | 49.93 | 740-MKWH-R-VH005-207-LH130-20-0 | LV0-105624.VH005 | 362 |  |  | MC1 | LVL 5 | T60 | TR030_3 | 2024-08-12 | 2024-08-12 | 2024-08-12 |  | 2024-08-12 | 2024-08-12 | Büro | 2024-08-12 |  | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-08-22 | 1017 | 150 |  | 2024-08-28 | 2024-09-09 | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
49646 | 740-MKWH-R-VH005-209-LH130-20-0 | 1 | true | 32.21 | 740-MKWH-R-VH005-209-LH130-20-0 | LV0-105624.VH005 | 362 | 2.Juny.2024 |  | MC1 | LVL 5 | T60 | TR014_1 | 2024-04-22 | 2024-04-29 | 2024-04-29 |  | 2024-05-28 | 2024-05-30 | Büro | 2024-06-14 |  | 2024-06-03 | 2024-06-26 |  |  | 2024-10-30 | 1017 | 150 |  |  | 2024-07-22 | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
49647 | 740-MKWH-R-VH005-210-LH130-25-0 | 1 | true | 33.65 | 740-MKWH-R-VH005-210-LH130-25-0 | LV0-105624.VH005 | 362 | 2.Juny.2024 |  | MC1 | LVL 5 | T60 | TR014_1 | 2024-04-22 | 2024-04-29 | 2024-04-29 |  | 2024-05-29 | 2024-06-07 | Büro | 2024-06-14 |  | 2024-06-07 | 2024-06-26 |  | 2024-07-02 | 2024-11-07 | 1017 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
49648 | 740-MKWH-R-VH005-211-LH130-25-0 | 1 | true | 24.61 | 740-MKWH-R-VH005-211-LH130-25-0 | LV0-105624.VH005 | 362 |  |  | MC1 | LVL 5 | T60 | TR014_1 | 2024-04-22 | 2024-04-29 | 2024-04-29 |  | 2024-06-12 | 2024-06-17 | Büro | 2024-06-28 |  | 2024-06-19 | 2024-07-15 |  | 2024-07-29 | 2024-11-06 | 1017 | 150 |  | 2024-08-28 | 2024-08-06 | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
49649 | 740-MKWH-R-VH005-301-LH130-20-0 | 1 | true | 6.43 | 740-MKWH-R-VH005-301-LH130-20-0 | LV1-105625.VH005 | 362 |  |  | MC1 | LVL 5 | T60 | TR014_1 | 2024-04-22 | 2024-04-29 | 2024-04-29 |  | 2024-06-11 | 2024-06-12 | Büro | 2024-06-28 |  | 2024-06-17 | 2024-08-09 |  |  | 2024-08-14 | 1017 | 150 |  |  | 2024-08-21 | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
49650 | 740-MKWH-R-VH005-302-LH130-20-0 | 1 | true | 8.52 | 740-MKWH-R-VH005-302-LH130-20-0 | LV1-105625.VH005 | 362 |  |  | MC1 | LVL 5 | T60 | TR014_1 | 2024-04-22 | 2024-04-29 | 2024-04-29 |  | 2024-06-25 | 2024-06-28 | Büro | 2024-07-12 |  | 2024-07-03 | 2024-08-09 |  |  | 2024-08-13 | 1017 | 150 |  |  | 2024-08-21 | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
49652 | 740-MKWH-R-VU211-113-LH130-50-0 | 1 | true | 21.44 | 740-MKWH-R-VU211-113-LH130-50-0 | LV1-105638.VU211 | 362 | 2.Juny.2024 |  | MC1 | LVL 6 | T60 | TR014_1 | 2024-04-22 | 2024-04-29 | 2024-04-29 |  | 2024-05-22 | 2024-05-24 | Büro | 2024-05-31 |  | 2024-05-28 | 2024-06-12 |  |  | 2024-06-18 | 804 | 150 |  | 2024-08-20 | 2024-07-16 | 149 | SEP | SEP | 2024-08-19 | 2024-09-02 | 2024-09-02 | 2024-09-02 | 2024-10-07 | 2024-10-07
49653 | 740-MKWH-S-VH005-207-LH130-20-0 | 1 | true | 50.05 | 740-MKWH-S-VH005-207-LH130-20-0 | LV0-105624.VH005 | 362 | 2.Juny.2024 |  | MC1 | LVL 5 | T60 | TR014_1 | 2024-04-22 | 2024-04-29 | 2024-04-29 |  | 2024-05-20 | 2024-05-24 | Büro | 2024-05-31 |  | 2024-05-24 | 2024-06-27 |  |  | 2024-08-22 | 1017 | 150 |  |  | 2024-07-22 | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
49654 | 740-MKWH-S-VH005-208-LH130-20-0 | 1 | true | 32.51 | 740-MKWH-S-VH005-208-LH130-20-0 | LV0-105624.VH005 | 362 |  |  | MC1 | LVL 5 | T60 | TR014_1 | 2024-04-22 | 2024-04-29 | 2024-04-29 |  | 2024-06-25 | 2024-06-28 | Büro | 2024-07-12 |  | 2024-07-04 | 2024-08-07 | 2024-08-12 |  | 2024-10-30 | 1017 | 150 |  |  | 2024-10-31 | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
49655 | 740-MKWH-S-VH005-209-LH130-25-0 | 1 | true | 33.5 | 740-MKWH-S-VH005-209-LH130-25-0 | LV0-105624.VH005 | 362 | 2.Juny.2024 |  | MC1 | LVL 5 | T60 | TR014_1 | 2024-04-22 | 2024-04-29 | 2024-04-29 |  | 2024-05-30 | 2024-06-07 | Büro | 2024-06-14 |  | 2024-06-07 | 2024-06-25 |  | 2024-07-05 | 2024-11-07 | 1017 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
49656 | 740-MKWH-S-VH005-210-LH130-25-0 | 1 | false | 24.32 | 740-MKWH-S-VH005-210-LH130-25-0 | LV0-105624.VH005 | 362 |  |  | MC1 | LVL 5 | T60 | TR014_1 | 2024-04-22 | 2024-04-29 | 2024-04-29 |  | 2024-06-12 | 2024-06-21 | Attila Henter | 2024-06-28 |  | 2024-06-26 | 2024-07-15 |  | 2024-07-29 |  | 1017 | 150 |  |  | 2024-08-06 | 149 | SEP | SEP
62776 | 740-MKWH-S-VH005-210-LH130-25-0 | 2 | true | 24.32 | 740-MKWH-S-VH005-210-LH130-25-0 | LV0-105624.VH005 | 362 |  |  | MC1 | LVL 5 | T60 | TR029_3 | 2024-08-07 | 2024-04-29 | 2024-04-29 |  | 2024-06-12 | 2024-06-21 | Büro | 2024-06-28 |  | 2024-06-26 | 2024-07-15 |  | 2024-07-29 | 2024-11-06 | 1017 | 150 |  | 2024-08-28 | 2024-08-06 | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
49657 | 740-MKWH-S-VH005-301-LH130-20-0 | 1 | true | 5.99 | 740-MKWH-S-VH005-301-LH130-20-0 | LV1-105625.VH005 | 362 |  |  | MC1 | LVL 5 | T60 | TR014_1 | 2024-04-22 | 2024-04-29 | 2024-04-29 |  | 2024-06-25 | 2024-06-28 | Büro | 2024-07-12 |  | 2024-07-03 | 2024-08-09 |  |  | 2024-08-13 | 1017 | 150 |  |  | 2024-08-21 | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
49658 | 740-MKWH-S-VH005-302-LH130-20-0 | 1 | true | 10.01 | 740-MKWH-S-VH005-302-LH130-20-0 | LV1-105625.VH005 | 362 |  |  | MC1 | LVL 5 | T60 | TR014_1 | 2024-04-22 | 2024-04-29 | 2024-04-29 |  | 2024-06-25 | 2024-06-26 | Büro | 2024-07-12 |  | 2024-07-02 | 2024-08-09 |  |  | 2024-08-13 | 1017 | 150 |  |  | 2024-08-21 | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
49659 | 740-MKWH-S-VU211-110-LH130-32-0 | 1 | false | 1.6 | 740-MKWH-S-VU211-110-LH130-32-0 | LV1-105638.VU211 | 362 | 2.Juny.2024 |  | MC1 | LVL 6 | T60 | TR014_1 | 2024-04-22 | 2024-04-29 | 2024-04-29 |  | 2024-05-20 | 2024-05-21 | Büro | 2024-05-31 |  | 2024-05-23 | 2024-06-12 |  |  | 2024-06-18 | 804 | 150 |  | 2024-08-28 | 2024-07-15 | 149 | SEP | SEP | 2024-07-23
49684 | 740-AB-VU200-180-LH032-50-0 | 1 | true | 3.27 | 740-AB-VU200-180-LH032-50-0 |  | 385 |  |  | MC1 | LVL 5 | N/A | TR013_3 | 2024-04-24 | 2024-04-29 | 2024-04-29 |  | 2024-06-12 | 2024-06-13 |  | 2024-06-28 |  | 2024-06-17 | 2024-07-23 |  |  | 2024-07-26 | 1018 | 150 |  |  | 2024-09-02 | 149 | SEP | SEP
49685 | 740-AB-VU200-201-LH032-25-0 | 1 | false | 16.49 | 740-AB-VU200-201-LH032-25-0 | LV1-105639.VU200 | 385 |  |  | MC1 | LVL 6 | N/A | TR013_3 | 2024-04-24 | 2024-04-29 | 2024-04-29 | [11 empty] | 1019 | 150 |  |  |  | 149 | SEP | SEP
50252 | 740-AB-VU200-201-LH032-25-0 | 2 | true | 16.49 | 740-AB-VU200-201-LH032-25-0 | LV1-105639.VU200 | 385 |  |  | MC1 | LVL 6 | N/A | TR014_4 | 2024-05-05 | 2024-04-28 | 2024-05-07 |  | 2024-06-17 | 2024-06-25 | Attila Henter | 2024-06-28 |  | 2024-06-26 | 2024-07-09 |  |  | 2024-07-19 | 1019 | 150 |  |  | 2024-09-02 | 149 | SEP | SEP
49686 | 740-AB-VU200-203-LH032-25-0 | 1 | true | 7.11 | 740-AB-VU200-203-LH032-25-0 |  | 385 |  |  | MC1 | LVL 5 | N/A | TR013_3 | 2024-04-24 | 2024-04-29 | 2024-04-29 |  | 2024-06-25 | 2024-06-26 | Büro | 2024-07-12 |  | 2024-07-01 | 2024-08-22 |  |  | 2024-08-27 | 1018 | 150 |  |  | 2024-09-02 | 149 | SEP | SEP
49884 | 740-WAn-VP001-302-LH032-40-0 | 1 | true | 0.15 | 740-WAn-VP001-302-LH032-40-0 | LV1-105630.VP001 | 385 |  |  | MC1 | LVL 5 | N/A | TR013_4 | 2024-04-27 | 2024-05-01 | 2024-05-01 |  | 2024-06-12 | 2024-06-18 | Büro | 2024-06-28 |  | 2024-06-19 | 2024-09-25 |  |  | 2024-10-01 | 1034 | 150 |  | 2024-11-13 | 2024-11-07 | 149 | SEP | SEP
49885 | 740-WAn-VP002-302-LH032-40-0 | 1 | true | 0.37 | 740-WAn-VP002-302-LH032-40-0 | LV1-105630.VP002 | 385 |  |  | MC1 | LVL 5 | N/A | TR013_4 | 2024-04-27 | 2024-05-01 | 2024-05-01 |  | 2024-06-12 | 2024-06-17 | Büro | 2024-06-28 |  | 2024-06-19 | 2024-09-25 |  |  | 2024-10-01 | 1034 | 150 |  | 2024-11-13 | 2024-11-07 | 149 | SEP | SEP
49886 | 740-WAn-VP003-302-LH032-40-0 | 1 | true | 0.15 | 740-WAn-VP003-302-LH032-40-0 | LV1-105630.VP003 | 385 |  |  | MC1 | LVL 5 | N/A | TR013_4 | 2024-04-27 | 2024-05-01 | 2024-05-01 |  | 2024-06-12 | 2024-06-13 | Büro | 2024-06-28 |  | 2024-06-14 | 2024-09-25 |  |  | 2024-09-28 | 1034 | 150 |  |  | 2024-09-30 | 149 | SEP | SEP
49887 | 740-WAn-VP004-302-LH032-40-0 | 1 | true | 0.2 | 740-WAn-VP004-302-LH032-40-0 | LV1-105630.VP004 | 385 |  |  | MC1 | LVL 5 | N/A | TR013_4 | 2024-04-27 | 2024-05-01 | 2024-05-01 |  | 2024-06-12 | 2024-06-13 | Büro | 2024-06-28 |  | 2024-06-14 |  |  |  | 2024-09-30 | 1034 | 150 |  |  | 2024-10-01 | 149 | SEP | SEP
49888 | 740-WAn-VP031-202-LH032-40-0 | 1 | true | 0.2 | 740-WAn-VP031-202-LH032-40-0 | LV1-105629.VP031 | 385 |  |  | MC1 | LVL 5 | N/A | TR013_4 | 2024-04-27 | 2024-05-01 | 2024-05-01 |  | 2024-06-12 | 2024-06-13 | Büro | 2024-06-28 |  | 2024-06-14 | 2024-10-01 |  |  | 2024-10-07 | 1034 | 150 |  |  | 2024-11-12 | 149 | SEP | SEP
49889 | 740-WAn-VP032-202-LH032-40-0 | 1 | true | 0.21 | 740-WAn-VP032-202-LH032-40-0 | LV1-105629.VP032 | 385 |  |  | MC1 | LVL 5 | N/A | TR013_4 | 2024-04-27 | 2024-05-01 | 2024-05-01 |  | 2024-06-12 | 2024-06-13 | Büro | 2024-06-28 |  | 2024-06-17 | 2024-10-01 |  |  | 2024-10-11 | 1034 | 150 |  |  | 2024-11-12 | 149 | SEP | SEP
49890 | 740-WAn-VP033-202-LH032-40-0 | 1 | true | 0.2 | 740-WAn-VP033-202-LH032-40-0 | LV1-105629.VP033 | 385 |  |  | MC1 | LVL 5 | N/A | TR013_4 | 2024-04-27 | 2024-05-01 | 2024-05-01 |  | 2024-06-12 | 2024-06-12 | Büro | 2024-06-28 |  | 2024-06-14 | 2024-10-01 |  |  | 2024-10-11 | 1034 | 150 |  |  | 2024-11-13 | 149 | SEP | SEP
49891 | 740-WAn-VP041-202-LH032-40-0 | 1 | true | 0.2 | 740-WAn-VP041-202-LH032-40-0 | LV1-105629.VP041 | 385 |  |  | MC1 | LVL 5 | N/A | TR013_4 | 2024-04-27 | 2024-05-01 | 2024-05-01 |  | 2024-06-12 | 2024-06-12 | Büro | 2024-06-28 |  | 2024-06-14 | 2024-10-01 |  |  | 2024-10-11 | 1034 | 150 |  |  | 2024-11-14 | 149 | SEP | SEP
49892 | 740-WAn-VP042-202-LH032-40-0 | 1 | false | 0.24 | 740-WAn-VP042-202-LH032-40-0 | LV1-105629.VP042 | 385 |  |  | MC1 | LVL 5 | N/A | TR013_4 | 2024-04-27 | 2024-05-01 | 2024-05-01 | [11 empty] | 1034 | 150 |  |  |  | 149 | SEP | SEP
50253 | 740-WAn-VP042-202-LH032-40-0 | 2 | true | 0.24 | 740-WAn-VP042-202-LH032-40-0 | LV1-105629.VP042 | 385 |  |  | MC1 | LVL 5 | N/A | TR014_4 | 2024-05-05 | 2024-05-01 | 2024-05-07 |  | 2024-06-17 | 2024-06-18 | Büro | 2024-06-28 |  | 2024-06-19 | 2024-10-01 |  |  | 2024-10-04 | 1034 | 150 |  |  | 2024-11-14 | 149 | SEP | SEP
49893 | 740-WAn-VP043-202-LH032-40-0 | 1 | true | 0.2 | 740-WAn-VP043-202-LH032-40-0 | LV1-105629.VP043 | 385 |  |  | MC1 | LVL 5 | N/A | TR013_4 | 2024-04-27 | 2024-05-01 | 2024-05-01 |  | 2024-06-12 | 2024-06-13 | Büro | 2024-06-28 |  | 2024-06-17 | 2024-10-01 |  |  | 2024-10-11 | 1034 | 150 |  |  | 2024-11-14 | 149 | SEP | SEP
49894 | 740-WAn-VP131-202-LH032-40-0 | 1 | true | 0.22 | 740-WAn-VP131-202-LH032-40-0 | LV1-105629.VP131 | 385 |  |  | MC1 | LVL 5 | N/A | TR013_4 | 2024-04-27 | 2024-05-01 | 2024-05-01 |  | 2024-06-12 | 2024-06-13 | Büro | 2024-06-28 |  | 2024-06-17 | 2024-10-07 |  |  | 2024-10-09 | 1034 | 150 |  |  |  | 149 | SEP | SEP
49895 | 740-WAn-VP132-202-LH032-40-0 | 1 | true | 0.2 | 740-WAn-VP132-202-LH032-40-0 | LV1-105629.VP132 | 385 |  |  | MC1 | LVL 5 | N/A | TR013_4 | 2024-04-27 | 2024-05-01 | 2024-05-01 |  | 2024-06-12 | 2024-06-13 | Büro | 2024-06-28 |  | 2024-06-17 | 2024-10-07 |  |  | 2024-10-09 | 1034 | 150 |  |  |  | 149 | SEP | SEP
49896 | 740-WAn-VP133-202-LH032-40-0 | 1 | true | 0.2 | 740-WAn-VP133-202-LH032-40-0 | LV1-105629.VP133 | 385 |  |  | MC1 | LVL 5 | N/A | TR013_4 | 2024-04-27 | 2024-05-01 | 2024-05-01 |  | 2024-06-12 | 2024-06-17 | Büro | 2024-06-28 |  | 2024-06-19 | 2024-10-07 |  |  | 2024-10-09 | 1034 | 150 |  |  |  | 149 | SEP | SEP
49897 | 740-WAn-VP141-202-LH032-40-0 | 1 | true | 0.2 | 740-WAn-VP141-202-LH032-40-0 | LV1-105629.VP141 | 385 |  |  | MC1 | LVL 5 | N/A | TR013_4 | 2024-04-27 | 2024-05-01 | 2024-05-01 |  | 2024-06-12 | 2024-06-17 | Büro | 2024-06-28 |  | 2024-06-19 |  |  |  | 2024-09-25 | 1034 | 150 |  |  |  | 149 | SEP | SEP
49898 | 740-WAn-VP142-202-LH032-40-0 | 1 | true | 0.15 | 740-WAn-VP142-202-LH032-40-0 | LV1-105629.VP142 | 385 |  |  | MC1 | LVL 5 | N/A | TR013_4 | 2024-04-27 | 2024-05-01 | 2024-05-01 |  | 2024-06-12 | 2024-06-17 | Büro | 2024-06-28 |  | 2024-06-19 |  |  |  | 2024-09-25 | 1034 | 150 |  |  |  | 149 | SEP | SEP
49899 | 740-WAn-VP143-202-LH032-40-0 | 1 | true | 0.28 | 740-WAn-VP143-202-LH032-40-0 | LV1-105629.VP143 | 385 |  |  | MC1 | LVL 5 | N/A | TR013_4 | 2024-04-27 | 2024-05-01 | 2024-05-01 |  | 2024-06-12 | 2024-06-17 | Büro | 2024-06-28 |  | 2024-06-19 |  |  |  | 2024-09-26 | 1034 | 150 |  |  |  | 149 | SEP | SEP
49900 | 740-WAn-VS671-102-LH099-15-0 | 1 | true | 0 | 740-WAn-VS671-102-LH099-15-0 | LV0-105633.VS671 | 386 |  |  | MC1 | LVL 6 | W23 | TR013_4 | 2024-04-27 | 2024-05-01 | 2024-05-01 |  | 2024-06-17 | 2024-06-18 | Büro | 2024-06-28 |  | 2024-06-20 |  |  |  | 2024-09-20 | 1035 | 150 |  |  | 2024-09-25 | 149 | SEP | SEP | 2024-09-25
49901 | 740-WAn-VS671-103-LH032-15-0 | 1 | false | 0.21 | 740-WAn-VS671-103-LH032-15-0 | LV0-105633.VS671 | 385 |  |  | MC1 | LVL 6 | W23 | TR013_4 | 2024-04-27 | 2024-05-01 | 2024-05-01 |  | 2024-06-21 | 2024-06-26 |  | 2024-07-12 |  | 2024-07-01 |  |  |  |  | 1035 | 150 |  |  |  | 149 | SEP | SEP
62212 | 740-WAn-VS671-103-LH032-15-0 | 2 | true | 0.21 | 740-WAn-VS671-103-LH032-15-0 | LV0-105633.VS671 | 385 |  |  | MC1 | LVL 6 | W23 | TR029_1 | 2024-07-24 | 2024-05-01 | 2024-05-01 |  | 2024-06-21 | 2024-06-26 | Büro | 2024-07-12 |  | 2024-07-01 | 2024-09-12 |  |  | 2024-09-17 | 1035 | 150 |  |  | 2024-09-24 | 149 | SEP | SEP | 2024-09-25
49902 | 740-WAn-VS671-104-LH099-15-0 | 1 | true | 0 | 740-WAn-VS671-104-LH099-15-0 | LV0-105633.VS671 | 386 |  |  | MC1 | LVL 6 | W23 | TR013_4 | 2024-04-27 | 2024-05-01 | 2024-05-01 |  | 2024-06-17 | 2024-06-18 | Büro | 2024-06-28 |  | 2024-06-20 |  |  |  | 2024-09-20 | 1035 | 150 |  |  | 2024-09-25 | 149 | SEP | SEP | 2024-09-25
49903 | 740-WAn-VS671-105-LH032-15-0 | 1 | false | 0.22 | 740-WAn-VS671-105-LH032-15-0 | LV0-105633.VS671 | 385 |  |  | MC1 | LVL 6 | W23 | TR013_4 | 2024-04-27 | 2024-05-01 | 2024-05-01 |  | 2024-06-21 | 2024-06-27 | Büro | 2024-07-12 |  | 2024-07-01 |  |  |  | 2024-09-17 | 1035 | 150 |  |  |  | 149 | SEP | SEP
62213 | 740-WAn-VS671-105-LH032-15-0 | 2 | true | 0.22 | 740-WAn-VS671-105-LH032-15-0 | LV0-105633.VS671 | 385 |  |  | MC1 | LVL 6 | W23 | TR029_1 | 2024-07-24 | 2024-05-01 | 2024-05-01 |  | 2024-06-21 | 2024-06-27 | Büro | 2024-07-12 |  | 2024-07-01 | 2024-09-12 |  |  | 2024-09-17 | 1035 | 150 |  |  | 2024-09-24 | 149 | SEP | SEP | 2024-09-25
49904 | 740-WAn-VS671-106-LH099-15-0 | 1 | true | 0 | 740-WAn-VS671-106-LH099-15-0 | LV0-105633.VS671 | 386 |  |  | MC1 | LVL 6 | W23 | TR013_4 | 2024-04-27 | 2024-05-01 | 2024-05-01 |  | 2024-06-17 | 2024-06-18 | Büro | 2024-06-28 |  | 2024-06-20 |  |  |  | 2024-09-20 | 1035 | 150 |  |  | 2024-09-25 | 149 | SEP | SEP | 2024-09-25
49905 | 740-WAn-VS671-107-LH032-15-0 | 1 | false | 0.22 | 740-WAn-VS671-107-LH032-15-0 | LV0-105633.VS671 | 385 |  |  | MC1 | LVL 6 | W23 | TR013_4 | 2024-04-27 | 2024-05-01 | 2024-05-01 |  | 2024-06-21 | 2024-06-26 |  | 2024-07-12 |  | 2024-07-01 |  |  |  |  | 1035 | 150 |  |  |  | 149 | SEP | SEP
62214 | 740-WAn-VS671-107-LH032-15-0 | 2 | true | 0.22 | 740-WAn-VS671-107-LH032-15-0 | LV0-105633.VS671 | 385 |  |  | MC1 | LVL 6 | W23 | TR029_1 | 2024-07-24 | 2024-05-01 | 2024-05-01 |  | 2024-06-21 | 2024-06-26 | Büro | 2024-07-12 |  | 2024-07-01 | 2024-09-12 |  |  | 2024-09-17 | 1035 | 150 |  |  | 2024-09-24 | 149 | SEP | SEP | 2024-09-25
49906 | 740-WAn-VS672-102-LH099-15-0 | 1 | true | 0 | 740-WAn-VS672-102-LH099-15-0 | LV0-105633.VS672 | 386 |  |  | MC1 | LVL 6 | W23 | TR013_4 | 2024-04-27 | 2024-05-01 | 2024-05-01 |  | 2024-06-17 | 2024-06-18 | Büro | 2024-06-28 |  | 2024-06-20 |  |  |  | 2024-09-20 | 1035 | 150 |  |  | 2024-09-25 | 149 | SEP | SEP | 2024-09-25
49907 | 740-WAn-VS672-103-LH032-15-0 | 1 | false | 0.21 | 740-WAn-VS672-103-LH032-15-0 | LV0-105633.VS672 | 385 |  |  | MC1 | LVL 6 | W23 | TR013_4 | 2024-04-27 | 2024-05-01 | 2024-05-01 |  | 2024-06-26 | 2024-06-26 |  | 2024-07-12 |  | 2024-07-01 |  |  |  |  | 1035 | 150 |  |  |  | 149 | SEP | SEP
62216 | 740-WAn-VS672-103-LH032-15-0 | 2 | true | 0.21 | 740-WAn-VS672-103-LH032-15-0 | LV0-105633.VS672 | 385 |  |  | MC1 | LVL 6 | W23 | TR029_1 | 2024-07-24 | 2024-05-01 | 2024-05-01 |  | 2024-06-26 | 2024-06-26 | Büro | 2024-07-12 |  | 2024-07-01 |  |  |  | 2024-09-17 | 1035 | 150 |  |  | 2024-09-24 | 149 | SEP | SEP | 2024-09-25
49908 | 740-WAn-VS672-104-LH099-15-0 | 1 | true | 0 | 740-WAn-VS672-104-LH099-15-0 | LV0-105633.VS672 | 386 |  |  | MC1 | LVL 6 | W23 | TR013_4 | 2024-04-27 | 2024-05-01 | 2024-05-01 |  | 2024-06-17 | 2024-06-18 | Büro | 2024-06-28 |  | 2024-06-20 |  |  |  | 2024-09-20 | 1035 | 150 |  |  | 2024-09-25 | 149 | SEP | SEP | 2024-09-25
49909 | 740-WAn-VS672-105-LH032-15-0 | 1 | false | 0.22 | 740-WAn-VS672-105-LH032-15-0 | LV0-105633.VS672 | 385 |  |  | MC1 | LVL 6 | W23 | TR013_4 | 2024-04-27 | 2024-05-01 | 2024-05-01 |  | 2024-06-21 | 2024-06-26 |  | 2024-07-12 |  | 2024-07-01 |  |  |  |  | 1035 | 150 |  |  |  | 149 | SEP | SEP
62217 | 740-WAn-VS672-105-LH032-15-0 | 2 | true | 0.22 | 740-WAn-VS672-105-LH032-15-0 | LV0-105633.VS672 | 385 |  |  | MC1 | LVL 6 | W23 | TR029_1 | 2024-07-24 | 2024-05-01 | 2024-05-01 |  | 2024-06-21 | 2024-06-26 | Büro | 2024-07-12 |  | 2024-07-01 |  |  |  | 2024-09-17 | 1035 | 150 |  |  | 2024-09-24 | 149 | SEP | SEP | 2024-09-25
49910 | 740-WAn-VS672-106-LH099-15-0 | 1 | true | 0 | 740-WAn-VS672-106-LH099-15-0 | LV0-105633.VS672 | 386 |  |  | MC1 | LVL 6 | W23 | TR013_4 | 2024-04-27 | 2024-05-01 | 2024-05-01 |  | 2024-06-17 | 2024-06-18 | Büro | 2024-06-28 |  | 2024-06-20 |  |  |  | 2024-09-20 | 1035 | 150 |  |  | 2024-09-25 | 149 | SEP | SEP | 2024-09-25
49911 | 740-WAn-VS672-107-LH032-15-0 | 1 | false | 0.22 | 740-WAn-VS672-107-LH032-15-0 | LV0-105633.VS672 | 385 |  |  | MC1 | LVL 6 | W23 | TR013_4 | 2024-04-27 | 2024-05-01 | 2024-05-01 |  | 2024-06-21 | 2024-06-26 |  | 2024-07-12 |  | 2024-07-01 |  |  |  |  | 1035 | 150 |  |  |  | 149 | SEP | SEP
62218 | 740-WAn-VS672-107-LH032-15-0 | 2 | true | 0.22 | 740-WAn-VS672-107-LH032-15-0 | LV0-105633.VS672 | 385 |  |  | MC1 | LVL 6 | W23 | TR029_1 | 2024-07-24 | 2024-05-01 | 2024-05-01 |  | 2024-06-21 | 2024-06-26 | Büro | 2024-07-12 |  | 2024-07-01 |  |  |  | 2024-09-17 | 1035 | 150 |  |  | 2024-09-24 | 149 | SEP | SEP | 2024-09-25
49912 | 740-WAn-VS673-102-LH099-15-0 | 1 | true | 0 | 740-WAn-VS673-102-LH099-15-0 | LV0-105633.VS673 | 386 |  |  | MC1 | LVL 6 | W23 | TR013_4 | 2024-04-27 | 2024-05-01 | 2024-05-01 |  | 2024-06-17 | 2024-06-18 | Büro | 2024-06-28 |  | 2024-06-20 |  |  |  | 2024-09-20 | 1035 | 150 |  |  | 2024-09-25 | 149 | SEP | SEP | 2024-09-25
49913 | 740-WAn-VS673-103-LH032-15-0 | 1 | false | 0.21 | 740-WAn-VS673-103-LH032-15-0 | LV0-105633.VS673 | 385 |  |  | MC1 | LVL 6 | W23 | TR013_4 | 2024-04-27 | 2024-05-01 | 2024-05-01 |  | 2024-06-21 | 2024-06-26 |  | 2024-07-12 |  | 2024-07-01 |  |  |  |  | 1035 | 150 |  |  |  | 149 | SEP | SEP
62220 | 740-WAn-VS673-103-LH032-15-0 | 2 | true | 0.21 | 740-WAn-VS673-103-LH032-15-0 | LV0-105633.VS673 | 385 |  |  | MC1 | LVL 6 | W23 | TR029_1 | 2024-07-24 | 2024-05-01 | 2024-05-01 |  | 2024-06-21 | 2024-06-26 | Büro | 2024-07-12 |  | 2024-07-01 |  |  |  | 2024-09-17 | 1035 | 150 |  |  | 2024-09-25 | 149 | SEP | SEP | 2024-09-25
49914 | 740-WAn-VS673-104-LH099-15-0 | 1 | true | 0 | 740-WAn-VS673-104-LH099-15-0 | LV0-105633.VS673 | 386 |  |  | MC1 | LVL 6 | W23 | TR013_4 | 2024-04-27 | 2024-05-01 | 2024-05-01 |  | 2024-06-17 | 2024-06-18 | Büro | 2024-06-28 |  | 2024-06-20 |  |  |  | 2024-09-20 | 1035 | 150 |  |  | 2024-09-25 | 149 | SEP | SEP | 2024-09-25
49915 | 740-WAn-VS673-105-LH032-15-0 | 1 | false | 0.22 | 740-WAn-VS673-105-LH032-15-0 | LV0-105633.VS673 | 385 |  |  | MC1 | LVL 6 | W23 | TR013_4 | 2024-04-27 | 2024-05-01 | 2024-05-01 |  | 2024-06-21 | 2024-06-26 |  | 2024-07-12 |  | 2024-07-01 |  |  |  |  | 1035 | 150 |  |  |  | 149 | SEP | SEP
62221 | 740-WAn-VS673-105-LH032-15-0 | 2 | true | 0.22 | 740-WAn-VS673-105-LH032-15-0 | LV0-105633.VS673 | 385 |  |  | MC1 | LVL 6 | W23 | TR029_1 | 2024-07-24 | 2024-05-01 | 2024-05-01 |  | 2024-06-21 | 2024-06-26 | Büro | 2024-07-12 |  | 2024-07-01 |  |  |  | 2024-09-17 | 1035 | 150 |  |  | 2024-09-25 | 149 | SEP | SEP | 2024-09-25
49916 | 740-WAn-VS673-106-LH099-15-0 | 1 | true | 0 | 740-WAn-VS673-106-LH099-15-0 | LV0-105633.VS673 | 386 |  |  | MC1 | LVL 6 | W23 | TR013_4 | 2024-04-27 | 2024-05-01 | 2024-05-01 |  | 2024-06-17 | 2024-06-18 | Büro | 2024-06-28 |  | 2024-06-20 |  |  |  | 2024-09-20 | 1035 | 150 |  |  | 2024-09-25 | 149 | SEP | SEP | 2024-09-25
49917 | 740-WAn-VS673-107-LH032-15-0 | 1 | false | 0.22 | 740-WAn-VS673-107-LH032-15-0 | LV0-105633.VS673 | 385 |  |  | MC1 | LVL 6 | W23 | TR013_4 | 2024-04-27 | 2024-05-01 | 2024-05-01 |  | 2024-06-21 | 2024-06-26 |  | 2024-07-12 |  | 2024-07-01 |  |  |  |  | 1035 | 150 |  |  |  | 149 | SEP | SEP
62222 | 740-WAn-VS673-107-LH032-15-0 | 2 | true | 0.22 | 740-WAn-VS673-107-LH032-15-0 | LV0-105633.VS673 | 385 |  |  | MC1 | LVL 6 | W23 | TR029_1 | 2024-07-24 | 2024-05-01 | 2024-05-01 |  | 2024-06-21 | 2024-06-26 | Büro | 2024-07-12 |  | 2024-07-01 |  |  |  | 2024-09-17 | 1035 | 150 |  |  | 2024-09-25 | 149 | SEP | SEP | 2024-09-25
49918 | 740-WAn-VU200-101-LH032-80-0 | 1 | false | 19.88 | 740-WAn-VU200-101-LH032-80-0 | LV0-105638.VU200 | 385 | 27.May.2024 |  | MC1 | LVL 5 | W23 | TR013_4 | 2024-04-27 | 2024-05-01 | 2024-05-01 |  | 2024-05-16 | 2024-05-24 | Büro | 2024-05-31 |  | 2024-05-24 | 2024-06-10 |  |  | 2024-06-18 | 1036 | 150 |  |  |  | 149 | SEP | SEP
49919 | 740-WAn-VU200-119-LH032-65-0 | 1 | false | 1.33 | 740-WAn-VU200-119-LH032-65-0 | LV0-105638.VU200 | 385 | 27.May.2024 |  | MC1 | LVL 5 | W60 | TR013_4 | 2024-04-27 | 2024-05-01 | 2024-05-01 |  | 2024-05-16 | 2024-05-20 |  | 2024-05-31 |  | 2024-05-22 |  |  |  |  | 1036 | 150 |  |  |  | 149 | SEP | SEP
56824 | 740-WAn-VU200-119-LH032-65-0 | 2 | true | 1.33 | 740-WAn-VU200-119-LH032-65-0 | LV0-105638.VU200 | 385 |  |  | MC1 | LVL 5 | W60 | TR027_2 | 2024-07-02 | 2024-05-01 | 2024-05-01 |  | 2024-05-16 | 2024-05-20 | Büro | 2024-05-31 |  | 2024-05-22 |  |  |  | 2024-08-07 | 1036 | 150 |  |  | 2024-10-08 | 149 | SEP | SEP | 2024-09-27
49920 | 740-WAn-VU200-122-LH032-50-0 | 1 | false | 13.61 | 740-WAn-VU200-122-LH032-50-0 | LV0-105638.VU200 | 385 | 27.May.2024 |  | MC1 | LVL 5 | N/A | TR013_4 | 2024-04-27 | 2024-05-01 | 2024-05-01 |  | 2024-05-15 | 2024-05-16 |  | 2024-05-31 |  | 2024-05-21 |  |  |  |  | 1036 | 150 |  |  |  | 149 | SEP | SEP
56825 | 740-WAn-VU200-122-LH032-50-0 | 2 | true | 13.61 | 740-WAn-VU200-122-LH032-50-0 | LV0-105638.VU200 | 385 |  |  | MC1 | LVL 5 | N/A | TR027_2 | 2024-07-02 | 2024-05-01 | 2024-05-01 |  | 2024-05-15 | 2024-05-16 |  | 2024-05-31 |  | 2024-05-21 |  |  |  | 2024-07-30 | 1036 | 150 |  |  | 2024-10-08 | 149 | SEP | SEP | 2024-09-27 | 2024-10-04 | 2024-10-04 | 2024-10-04
49921 | 740-WAn-VU200-174-LH032-50-0 | 1 | false | 2.92 | 740-WAn-VU200-174-LH032-50-0 | LV0-105638.VU200 | 385 | 27.May.2024 |  | MC1 | LVL 5 | W23 | TR013_4 | 2024-04-27 | 2024-05-01 | 2024-05-01 |  | 2024-05-15 | 2024-05-15 | Büro | 2024-05-31 |  | 2024-05-17 |  |  |  | 2024-09-21 | 1036 | 150 |  |  |  | 149 | SEP | SEP
56826 | 740-WAn-VU200-174-LH032-50-0 | 2 | false | 2.92 | 740-WAn-VU200-174-LH032-50-0 | LV0-105638.VU200 | 385 |  |  | MC1 | LVL 5 | W23 | TR027_2 | 2024-07-02 | 2024-05-01 | 2024-05-01 |  | 2024-05-15 | 2024-05-15 |  | 2024-05-31 |  | 2024-05-17 |  |  |  |  | 1036 | 150 |  |  |  | 149 | SEP | SEP
62226 | 740-WAn-VU200-174-LH032-50-0 | 3 | true | 3.5 | 740-WAn-VU200-174-LH032-50-0 | LV0-105638.VU200 | 385 |  |  | MC1 | LVL 5 | W23 | TR029_1 | 2024-07-24 | 2024-05-01 | 2024-05-01 |  | 2024-05-15 | 2024-05-15 | Büro | 2024-05-31 |  | 2024-05-17 | 2024-08-07 |  |  | 2024-09-21 | 1036 | 150 |  |  | 2024-09-25 | 149 | SEP | SEP | 2024-09-27 | 2024-10-04 | 2024-10-04 | 2024-10-04
49922 | 740-WAn-VU200-176-LH032-50-0 | 1 | false | 2.55 | 740-WAn-VU200-176-LH032-50-0 | LV0-105638.VU200 | 385 | 27.May.2024 |  | MC1 | LVL 5 | W23 | TR013_4 | 2024-04-27 | 2024-05-01 | 2024-05-01 |  | 2024-05-15 | 2024-05-16 | Büro | 2024-05-31 |  | 2024-05-17 |  |  |  | 2024-08-21 | 1036 | 150 |  |  |  | 149 | SEP | SEP
56827 | 740-WAn-VU200-176-LH032-50-0 | 2 | false | 2.55 | 740-WAn-VU200-176-LH032-50-0 | LV0-105638.VU200 | 385 |  |  | MC1 | LVL 5 | W23 | TR027_2 | 2024-07-02 | 2024-05-01 | 2024-05-01 |  | 2024-05-15 | 2024-05-16 |  | 2024-05-31 |  | 2024-05-17 |  |  |  |  | 1036 | 150 |  |  |  | 149 | SEP | SEP
62227 | 740-WAn-VU200-176-LH032-50-0 | 3 | true | 2.55 | 740-WAn-VU200-176-LH032-50-0 | LV0-105638.VU200 | 385 |  |  | MC1 | LVL 5 | W23 | TR029_1 | 2024-07-24 | 2024-05-01 | 2024-05-01 |  | 2024-05-15 | 2024-05-16 | Büro | 2024-05-31 |  | 2024-05-17 | 2024-08-07 |  |  | 2024-08-21 | 1036 | 150 |  |  | 2024-10-08 | 149 | SEP | SEP | 2024-09-27 | 2024-10-04 | 2024-10-04 | 2024-10-04
49923 | 740-WAn-VU200-178-LH032-50-0 | 1 | false | 2.52 | 740-WAn-VU200-178-LH032-50-0 | LV0-105638.VU200 | 385 | 27.May.2024 |  | MC1 | LVL 5 | W23 | TR013_4 | 2024-04-27 | 2024-05-01 | 2024-05-01 |  | 2024-05-15 | 2024-05-16 |  | 2024-05-31 |  | 2024-05-17 |  |  |  |  | 1036 | 150 |  |  |  | 149 | SEP | SEP
56828 | 740-WAn-VU200-178-LH032-50-0 | 2 | false | 2.52 | 740-WAn-VU200-178-LH032-50-0 | LV0-105638.VU200 | 385 |  |  | MC1 | LVL 5 | W23 | TR027_2 | 2024-07-02 | 2024-05-01 | 2024-05-01 |  | 2024-05-15 | 2024-05-16 |  | 2024-05-31 |  | 2024-05-17 |  |  |  | 2024-07-25 | 1036 | 150 |  |  |  | 149 | SEP | SEP
62228 | 740-WAn-VU200-178-LH032-50-0 | 3 | true | 2.52 | 740-WAn-VU200-178-LH032-50-0 | LV0-105638.VU200 | 385 |  |  | MC1 | LVL 5 | W23 | TR029_1 | 2024-07-24 | 2024-05-01 | 2024-05-01 |  | 2024-05-15 | 2024-05-16 |  | 2024-05-31 |  | 2024-05-17 |  |  |  | 2024-07-25 | 1036 | 150 |  |  | 2024-10-08 | 149 | SEP | SEP | 2024-09-27 | 2024-10-04 | 2024-10-04 | 2024-10-04
49924 | 740-WAn-VU200-181-LH032-25-0 | 1 | true | 0.99 | 740-WAn-VU200-181-LH032-25-0 | LV0-105638.VU200 | 385 | 27.May.2024 |  | MC1 | LVL 5 | N/A | TR013_4 | 2024-04-27 | 2024-05-01 | 2024-05-01 |  | 2024-05-15 | 2024-05-16 | Büro | 2024-05-31 |  | 2024-05-17 | 2024-09-23 |  |  | 2024-09-26 | 1036 | 150 |  | 2024-10-09 | 2024-10-08 | 149 | SEP | SEP
49925 | 740-WAn-VU200-182-LH032-25-0 | 1 | true | 1.25 | 740-WAn-VU200-182-LH032-25-0 | LV0-105638.VU200 | 385 | 27.May.2024 |  | MC1 | LVL 5 | N/A | TR013_4 | 2024-04-27 | 2024-05-01 | 2024-05-01 |  | 2024-05-15 | 2024-05-15 | Büro | 2024-05-31 |  | 2024-05-21 | 2024-09-23 |  |  | 2024-09-26 | 1036 | 150 |  | 2024-10-09 | 2024-10-08 | 149 | SEP | SEP
49926 | 740-WAn-VU200-185-LH032-25-0 | 1 | false | 2.94 | 740-WAn-VU200-185-LH032-25-0 | LV0-105638.VU200 | 385 | 27.May.2024 |  | MC1 | LVL 5 | W23 | TR013_4 | 2024-04-27 | 2024-05-01 | 2024-05-01 |  | 2024-05-15 | 2024-05-17 |  | 2024-05-31 |  | 2024-05-21 |  |  |  |  | 1036 | 150 |  |  |  | 149 | SEP | SEP
56829 | 740-WAn-VU200-185-LH032-25-0 | 2 | true | 2.94 | 740-WAn-VU200-185-LH032-25-0 | LV0-105638.VU200 | 385 |  |  | MC1 | LVL 5 | W23 | TR027_2 | 2024-07-02 | 2024-05-01 | 2024-05-01 |  | 2024-05-15 | 2024-05-17 |  | 2024-05-31 |  | 2024-05-21 |  |  |  | 2024-07-25 | 1036 | 150 |  |  | 2024-10-08 | 149 | SEP | SEP | 2024-09-27 | 2024-10-04 | 2024-10-04 | 2024-10-04
49927 | 740-WAn-VU200-186-LH032-40-0 | 1 | false | 2.86 | 740-WAn-VU200-186-LH032-40-0 | LV0-105638.VU200 | 385 | 27.May.2024 |  | MC1 | LVL 5 | W23 | TR013_4 | 2024-04-27 | 2024-05-01 | 2024-05-01 |  | 2024-05-15 | [9 empty] | 1036 | 150 |  |  |  | 149 | SEP | SEP
50317 | 740-WAn-VU200-186-LH032-40-0 | 2 | true | 2.86 | 740-WAn-VU200-186-LH032-40-0 | LV0-105638.VU200 | 385 |  |  | MC1 | LVL 5 | W23 | TR016_1 | 2024-05-08 | 2024-05-01 | 2024-05-01 |  | 2024-05-15 | 2024-05-16 | Büro | 2024-05-31 |  | 2024-05-18 | 2024-09-21 |  |  | 2024-09-26 | 1036 | 150 |  | 2024-10-09 | 2024-10-08 | 149 | SEP | SEP | 2024-09-27 | 2024-10-04 | 2024-10-04 | 2024-10-04
49928 | 740-WAn-VU200-187-LH032-25-0 | 1 | true | 2.31 | 740-WAn-VU200-187-LH032-25-0 | LV1-105639.VU200 | 385 | 27.May.2024 |  | MC1 | LVL 5 | N/A | TR013_4 | 2024-04-27 | 2024-05-01 | 2024-05-01 |  | 2024-05-15 | 2024-05-16 |  | 2024-05-31 |  | 2024-05-17 |  |  |  | 2024-10-16 | 1034 | 150 |  |  |  | 149 | SEP | SEP
49929 | 740-WAn-VU200-191-LH032-65-0 | 1 | false | 1.16 | 740-WAn-VU200-191-LH032-65-0 | LV0-105638.VU200 | 385 |  |  | MC1 | LVL 5 | W60 | TR013_4 | 2024-04-27 | 2024-05-01 | 2024-05-01 |  | 2024-06-21 | 2024-06-27 |  |  |  | 2024-07-01 |  |  |  |  | 1036 | 150 |  |  |  | 149 | SEP | SEP
56830 | 740-WAn-VU200-191-LH032-65-0 | 2 | true | 1.16 | 740-WAn-VU200-191-LH032-65-0 | LV0-105638.VU200 | 385 |  |  | MC1 | LVL 5 | W60 | TR027_2 | 2024-07-02 | 2024-05-01 | 2024-05-01 |  | 2024-06-21 | 2024-06-27 | Büro | 2024-07-12 |  | 2024-07-01 | 2024-07-18 |  |  | 2024-08-21 | 1036 | 150 |  |  | 2024-10-08 | 149 | SEP | SEP | 2024-09-27
49930 | 740-WAn-VU200-192-LH032-65-0 | 1 | false | 1.4 | 740-WAn-VU200-192-LH032-65-0 | LV0-105638.VU200 | 385 |  |  | MC1 | LVL 5 | W60 | TR013_4 | 2024-04-27 | 2024-05-01 | 2024-05-01 |  | 2024-06-21 | 2024-06-26 |  | 2024-06-28 |  | 2024-06-27 |  |  |  |  | 1036 | 150 |  |  |  | 149 | SEP | SEP
56831 | 740-WAn-VU200-192-LH032-65-0 | 2 | true | 1.4 | 740-WAn-VU200-192-LH032-65-0 | LV0-105638.VU200 | 385 |  |  | MC1 | LVL 5 | W60 | TR027_2 | 2024-07-02 | 2024-05-01 | 2024-05-01 |  | 2024-06-21 | 2024-06-26 | Büro | 2024-06-28 |  | 2024-06-27 |  |  |  | 2024-08-07 | 1036 | 150 |  |  | 2024-10-08 | 149 | SEP | SEP | 2024-09-27 | 2024-10-04 | 2024-10-04 | 2024-10-04
49931 | 740-WAn-VU200-204-LH032-25-0 | 1 | false | 3.47 | 740-WAn-VU200-204-LH032-25-0 | LV1-105639.VU200 | 385 | 27.May.2024 |  | MC1 | LVL 5 | N/A | TR013_4 | 2024-04-27 | 2024-05-01 | 2024-05-01 |  | 2024-05-15 | [9 empty] | 1034 | 150 |  |  |  | 149 | SEP | SEP
50318 | 740-WAn-VU200-204-LH032-25-0 | 2 | true | 3.47 | 740-WAn-VU200-204-LH032-25-0 | LV1-105639.VU200 | 385 |  |  | MC1 | LVL 5 | N/A | TR016_1 | 2024-05-08 | 2024-05-01 | 2024-05-01 |  | 2024-05-15 | 2024-05-16 | Büro | 2024-05-31 |  | 2024-05-18 | 2024-07-09 |  |  | 2024-07-16 | 1034 | 150 |  |  |  | 149 | SEP | SEP
49932 | 740-WAn-VU200-219-LH032-25-0 | 1 | false | 11.5 | 740-WAn-VU200-219-LH032-25-0 | LV1-105639.VU200 | 385 |  |  | MC1 | LVL 5 | N/A | TR013_4 | 2024-04-27 | 2024-05-01 | 2024-05-01 | [11 empty] | 1034 | 150 |  |  |  | 149 | SEP | SEP
52291 | 740-WAn-VU200-219-LH032-25-0 | 3 | true | 11.5 | 740-WAn-VU200-219-LH032-25-0 | LV1-105639.VU200 | 385 |  |  | MC1 | LVL 5 | N/A | TR021_2 | 2024-06-05 | 2024-05-01 | 2024-05-01 |  | 2024-07-24 | 2024-07-25 | Büro | 2024-08-02 |  | 2024-07-26 | 2024-08-10 |  |  | 2024-08-14 | 1034 | 150 |  |  |  | 149 | SEP | SEP
49933 | 740-WAn-VU200-221-LH032-25-0 | 1 | false | 2.44 | 740-WAn-VU200-221-LH032-25-0 | LV1-105639.VU200 | 385 |  |  | MC1 | LVL 5 | N/A | TR013_4 | 2024-04-27 | 2024-05-01 | 2024-05-01 | [11 empty] | 1034 | 150 |  |  |  | 149 | SEP | SEP
52247 | 740-WAn-VU200-221-LH032-25-0 | 2 | true | 2.44 | 740-WAn-VU200-221-LH032-25-0 | LV1-105639.VU200 | 385 |  |  | MC1 | LVL 5 | N/A | TR020_2 | 2024-06-03 | 2024-05-01 | 2024-05-01 |  | 2024-07-05 | 2024-07-08 | Büro | 2024-07-12 |  | 2024-07-10 | 2024-08-10 |  |  | 2024-08-14 | 1034 | 150 |  |  |  | 149 | SEP | SEP
49934 | 740-WAn-VU200-224-LH032-25-0 | 1 | false | 1.45 | 740-WAn-VU200-224-LH032-25-0 | LV1-105639.VU200 | 385 | 27.May.2024 |  | MC1 | LVL 5 | N/A | TR013_4 | 2024-04-27 | 2024-05-01 | 2024-05-01 |  | 2024-05-15 | [9 empty] | 1034 | 150 |  |  |  | 149 | SEP | SEP
50320 | 740-WAn-VU200-224-LH032-25-0 | 2 | true | 1.45 | 740-WAn-VU200-224-LH032-25-0 | LV1-105639.VU200 | 385 |  |  | MC1 | LVL 5 | N/A | TR016_1 | 2024-05-08 | 2024-05-01 | 2024-05-01 |  | 2024-05-15 | 2024-05-18 | Büro | 2024-05-31 |  | 2024-05-21 | 2024-10-01 |  |  | 2024-10-04 | 1034 | 150 |  |  |  | 149 | SEP | SEP
49935 | 740-WAn-VU200-236-LH032-40-0 | 1 | true | 0.91 | 740-WAn-VU200-236-LH032-40-0 | LV1-105639.VU200 | 385 | 27.May.2024 |  | MC1 | LVL 5 | N/A | TR013_4 | 2024-04-27 | 2024-05-01 | 2024-05-01 |  | 2024-05-17 | 2024-05-21 | Büro | 2024-05-31 |  | 2024-05-22 | 2024-10-07 |  |  | 2024-10-09 | 1034 | 150 |  |  | 2024-11-11 | 149 | SEP | SEP
49936 | 740-WAn-VU200-240-LH032-50-0 | 1 | true | 29.64 | 740-WAn-VU200-240-LH032-50-0 | LV1-105639.VU200 | 385 | 27.May.2024 |  | MC1 | LVL 5 | N/A | TR013_4 | 2024-04-27 | 2024-05-01 | 2024-05-01 |  | 2024-05-15 | 2024-05-20 | Büro | 2024-05-31 |  | 2024-05-22 | 2024-07-04 |  |  | 2024-07-10 | 1034 | 150 |  |  | 2024-11-11 | 149 | SEP | SEP
49937 | 740-WAn-VU200-242-LH032-40-0 | 1 | true | 0.76 | 740-WAn-VU200-242-LH032-40-0 | LV1-105639.VU200 | 385 | 27.May.2024 |  | MC1 | LVL 5 | N/A | TR013_4 | 2024-04-27 | 2024-05-01 | 2024-05-01 |  | 2024-05-15 | 2024-05-17 | Büro | 2024-05-31 |  | 2024-05-18 | 2024-10-07 |  |  | 2024-10-09 | 1034 | 150 |  |  | 2024-10-10 | 149 | SEP | SEP
49938 | 740-WAn-VU200-243-LH032-50-0 | 1 | true | 15.21 | 740-WAn-VU200-243-LH032-50-0 | LV1-105639.VU200 | 385 | 27.May.2024 |  | MC1 | LVL 5 | N/A | TR013_4 | 2024-04-27 | 2024-05-01 | 2024-05-01 |  | 2024-05-15 | 2024-05-24 | Büro | 2024-05-31 |  | 2024-05-24 | 2024-08-14 |  |  | 2024-08-21 | 1034 | 150 |  |  |  | 149 | SEP | SEP
49939 | 740-WAn-VU200-250-LH032-65-0 | 1 | false | 16.65 | 740-WAn-VU200-250-LH032-65-0 | LV1-105639.VU200 | 385 | 27.May.2024 |  | MC1 | LVL 5 | N/A | TR013_4 | 2024-04-27 | 2024-05-01 | 2024-05-01 |  | 2024-05-16 | [9 empty] | 1034 | 150 |  |  |  | 149 | SEP | SEP
51951 | 740-WAn-VU200-250-LH032-65-0 | 2 | true | 16.65 | 740-WAn-VU200-250-LH032-65-0 | LV1-105639.VU200 | 385 |  |  | MC1 | LVL 5 | N/A | TR019_1 | 2024-05-22 | 2024-05-01 | 2024-05-23 |  | 2024-05-16 | 2024-05-24 | Büro | 2024-05-31 |  | 2024-05-27 | 2024-07-02 |  |  | 2024-07-05 | 1034 | 150 |  | 2024-10-09 |  | 149 | SEP | SEP
49940 | 740-WAn-VU200-252-LH032-100-0 | 1 | true | 39.2 | 740-WAn-VU200-252-LH032-100-0 | LV1-105639.VU200 | 385 | 27.May.2024 |  | MC1 | LVL 5 | W23 | TR013_4 | 2024-04-27 | 2024-05-01 | 2024-05-01 |  | 2024-05-16 | 2024-05-23 | Büro | 2024-05-31 |  | 2024-05-28 | 2024-06-20 |  |  | 2024-06-26 | 1034 | 150 |  | 2024-10-09 | 2024-10-08 | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
49941 | 740-WAn-VU200-257-LH032-50-0 | 1 | true | 11.11 | 740-WAn-VU200-257-LH032-50-0 | LV1-105639.VU200 | 385 | 27.May.2024 |  | MC1 | LVL 5 | W60 | TR013_4 | 2024-04-27 | 2024-05-01 | 2024-05-01 |  | 2024-05-15 | 2024-05-23 | Büro | 2024-05-31 |  | 2024-05-23 | 2024-08-08 |  |  | 2024-08-12 | 1034 | 150 |  |  | 2024-11-11 | 149 | SEP | SEP
49942 | 740-WAn-VU200-258-LH032-50-0 | 1 | true | 19.59 | 740-WAn-VU200-258-LH032-50-0 | LV1-105639.VU200 | 385 | 27.May.2024 |  | MC1 | LVL 5 | N/A | TR013_4 | 2024-04-27 | 2024-05-01 | 2024-05-01 |  | 2024-05-15 | 2024-05-24 | Büro | 2024-05-31 |  | 2024-05-28 |  |  |  | 2024-09-27 | 1034 | 150 |  |  |  | 149 | SEP | SEP
49943 | 740-WAn-VU200-268-LH032-40-0 | 1 | true | 0.67 | 740-WAn-VU200-268-LH032-40-0 | LV1-105639.VU200 | 385 | 27.May.2024 |  | MC1 | LVL 5 | N/A | TR013_4 | 2024-04-27 | 2024-05-01 | 2024-05-01 |  | 2024-05-17 | 2024-05-22 | Büro | 2024-05-31 |  | 2024-05-23 | 2024-07-09 |  |  | 2024-07-15 | 1034 | 150 |  |  | 2024-11-11 | 149 | SEP | SEP
49944 | 740-WAn-VU200-269-LH032-40-0 | 1 | false | 1.06 | 740-WAn-VU200-269-LH032-40-0 | LV1-105639.VU200 | 385 | 27.May.2024 |  | MC1 | LVL 5 | N/A | TR013_4 | 2024-04-27 | 2024-05-01 | 2024-05-01 | [11 empty] | 1034 | 150 |  |  |  | 149 | SEP | SEP
50254 | 740-WAn-VU200-269-LH032-40-0 | 2 | true | 1.06 | 740-WAn-VU200-269-LH032-40-0 | LV1-105639.VU200 | 385 | 27. May 2024 |  | MC1 | LVL 5 | N/A | TR014_4 | 2024-05-05 | 2024-05-01 | 2024-05-07 |  | 2024-05-17 | 2024-05-20 | Büro | 2024-05-31 |  | 2024-05-22 | 2024-10-01 |  |  | 2024-10-04 | 1034 | 150 |  |  |  | 149 | SEP | SEP
49945 | 740-WAn-VU200-270-LH032-40-0 | 1 | true | 0.98 | 740-WAn-VU200-270-LH032-40-0 | LV1-105639.VU200 | 385 | 27.May.2024 |  | MC1 | LVL 5 | N/A | TR013_4 | 2024-04-27 | 2024-05-01 | 2024-05-01 |  | 2024-05-17 | 2024-05-20 | Büro | 2024-05-31 |  | 2024-05-22 | 2024-10-01 |  |  | 2024-10-09 | 1034 | 150 |  |  | 2024-10-09 | 149 | SEP | SEP
49946 | 740-WAn-VU200-272-LH032-40-0 | 1 | true | 0.97 | 740-WAn-VU200-272-LH032-40-0 | LV1-105639.VU200 | 385 | 27.May.2024 |  | MC1 | LVL 5 | N/A | TR013_4 | 2024-04-27 | 2024-05-01 | 2024-05-01 |  | 2024-05-17 | 2024-05-18 | Büro | 2024-05-31 |  | 2024-05-21 | 2024-10-01 |  |  | 2024-10-09 | 1034 | 150 |  |  | 2024-10-09 | 149 | SEP | SEP
49947 | 740-WAn-VU200-273-LH032-40-0 | 1 | true | 0.93 | 740-WAn-VU200-273-LH032-40-0 | LV1-105639.VU200 | 385 | 27.May.2024 |  | MC1 | LVL 5 | N/A | TR013_4 | 2024-04-27 | 2024-05-01 | 2024-05-01 |  | 2024-05-17 | 2024-05-18 | Büro | 2024-05-31 |  | 2024-05-21 | 2024-10-01 |  |  | 2024-10-09 | 1034 | 150 |  |  | 2024-10-09 | 149 | SEP | SEP
49948 | 740-WAn-VU200-274-LH032-40-0 | 1 | true | 0.71 | 740-WAn-VU200-274-LH032-40-0 | LV1-105639.VU200 | 385 | 27.May.2024 |  | MC1 | LVL 5 | N/A | TR013_4 | 2024-04-27 | 2024-05-01 | 2024-05-01 |  | 2024-05-15 | 2024-05-16 | Büro | 2024-05-31 |  | 2024-05-17 |  |  |  | 2024-09-25 | 1034 | 150 |  |  |  | 149 | SEP | SEP
49949 | 740-WAn-VU200-275-LH032-40-0 | 1 | true | 0.73 | 740-WAn-VU200-275-LH032-40-0 | LV1-105639.VU200 | 385 | 27.May.2024 |  | MC1 | LVL 5 | N/A | TR013_4 | 2024-04-27 | 2024-05-01 | 2024-05-01 |  | 2024-05-17 | 2024-05-20 | Büro | 2024-05-31 |  | 2024-05-21 |  |  |  | 2024-09-25 | 1034 | 150 |  |  |  | 149 | SEP | SEP
49950 | 740-WAn-VU200-276-LH032-40-0 | 1 | true | 0.61 | 740-WAn-VU200-276-LH032-40-0 | LV1-105639.VU200 | 385 | 27.May.2024 |  | MC1 | LVL 5 | N/A | TR013_4 | 2024-04-27 | 2024-05-01 | 2024-05-01 |  | 2024-05-16 | 2024-05-17 | Büro | 2024-05-31 |  | 2024-05-18 |  |  |  | 2024-09-26 | 1034 | 150 |  |  |  | 149 | SEP | SEP
49951 | 740-WAn-VU200-277-LH032-40-0 | 1 | true | 0.67 | 740-WAn-VU200-277-LH032-40-0 | LV1-105639.VU200 | 385 | 27.May.2024 |  | MC1 | LVL 5 | N/A | TR013_4 | 2024-04-27 | 2024-05-01 | 2024-05-01 |  | 2024-05-17 | 2024-05-18 | Büro | 2024-05-31 |  | 2024-05-21 | 2024-09-25 |  |  | 2024-09-30 | 1034 | 150 |  |  | 2024-10-01 | 149 | SEP | SEP
49952 | 740-WAn-VU200-278-LH032-40-0 | 1 | true | 0.71 | 740-WAn-VU200-278-LH032-40-0 | LV1-105639.VU200 | 385 | 27.May.2024 |  | MC1 | LVL 5 | N/A | TR013_4 | 2024-04-27 | 2024-05-01 | 2024-05-01 |  | 2024-05-17 | 2024-05-17 | Büro | 2024-05-31 |  | 2024-05-18 | 2024-09-25 |  |  | 2024-09-28 | 1034 | 150 |  |  | 2024-09-30 | 149 | SEP | SEP
49953 | 740-WAn-VU200-279-LH032-40-0 | 1 | true | 0.66 | 740-WAn-VU200-279-LH032-40-0 | LV1-105639.VU200 | 385 | 27.May.2024 |  | MC1 | LVL 5 | N/A | TR013_4 | 2024-04-27 | 2024-05-01 | 2024-05-01 |  | 2024-05-16 | 2024-05-17 | Büro | 2024-05-31 |  | 2024-05-18 | 2024-09-25 |  |  | 2024-10-01 | 1034 | 150 |  |  |  | 149 | SEP | SEP
49954 | 740-WAn-VU200-280-LH032-40-0 | 1 | true | 0.61 | 740-WAn-VU200-280-LH032-40-0 | LV1-105639.VU200 | 385 | 27.May.2024 |  | MC1 | LVL 5 | N/A | TR013_4 | 2024-04-27 | 2024-05-01 | 2024-05-01 |  | 2024-05-15 | 2024-05-15 | Büro | 2024-05-17 |  | 2024-05-16 | 2024-09-25 |  |  | 2024-10-01 | 1034 | 150 |  |  |  | 149 | SEP | SEP
49955 | 740-WAn-VU200-282-LH032-40-0 | 1 | true | 0.89 | 740-WAn-VU200-282-LH032-40-0 | LV1-105639.VU200 | 385 | 27.May.2024 |  | MC1 | LVL 5 | N/A | TR013_4 | 2024-04-27 | 2024-05-01 | 2024-05-01 |  | 2024-05-17 | 2024-05-18 | Büro | 2024-05-31 |  | 2024-05-18 | 2024-10-01 |  |  | 2024-10-07 | 1034 | 150 |  |  |  | 149 | SEP | SEP
49956 | 740-WAn-VU200-290-LH032-40-0 | 1 | true | 1.03 | 740-WAn-VU200-290-LH032-40-0 | LV1-105639.VU200 | 385 | 27.May.2024 |  | MC1 | LVL 5 | N/A | TR013_4 | 2024-04-27 | 2024-05-01 | 2024-05-01 |  | 2024-05-16 | 2024-05-18 | Büro | 2024-05-31 |  | 2024-05-18 | 2024-10-01 |  |  | 2024-10-12 | 1034 | 150 |  |  |  | 149 | SEP | SEP
49975 | 740-DKR-VU117-101-LH011-50-0 | 1 | true | 10.92 | 740-DKR-VU117-101-LH011-50-0 | LV1-105638.VU117 | 369 | 26.May.2024 |  | MC1 | LVL 4 | W23 | TR014_2 | 2024-04-28 | 2024-05-02 | 2024-05-02 |  | 2024-05-15 | 2024-05-24 | Attila Henter | 2024-05-31 |  | 2024-05-24 | 2024-06-13 |  |  | 2024-07-24 | 1037 | 150 |  |  | 2024-11-06 | 149 | SEP | SEP | 2024-11-08 | 2024-11-08 | 2024-11-08 | 2024-11-08
49976 | 740-DKR-VU117-103-LH011-20-0 | 1 | true | 4.95 | 740-DKR-VU117-103-LH011-20-0 | LV1-105638.VU117 | 369 |  |  | MC1 | LVL 4 | W23 | TR014_2 | 2024-04-28 | 2024-05-02 | 2024-05-02 |  | 2024-06-25 | 2024-07-03 |  | 2024-07-12 |  | 2024-07-03 | 2024-07-29 |  |  | 2024-07-31 | 1037 | 150 |  |  | 2024-08-29 | 149 | SEP | SEP | 2024-11-08 | 2024-11-08 | 2024-11-08 | 2024-11-08
49977 | 740-DKR-VU117-104-LH011-20-0 | 1 | true | 10.48 | 740-DKR-VU117-104-LH011-20-0 | LV1-105638.VU117 | 369 |  |  | MC1 | LVL 4 | W23 | TR014_2 | 2024-04-28 | 2024-05-02 | 2024-05-02 |  | 2024-06-25 | 2024-06-28 |  | 2024-07-12 |  | 2024-07-03 | 2024-07-29 |  |  | 2024-07-31 | 1037 | 150 |  | 2024-08-26 | 2024-08-23 | 149 | SEP | SEP | 2024-11-08 | 2024-11-08 | 2024-11-08 | 2024-11-08
49978 | 740-DKR-VU117-105-LH011-20-0 | 1 | true | 10.35 | 740-DKR-VU117-105-LH011-20-0 | LV1-105638.VU117 | 369 |  |  | MC1 | LVL 4 | W23 | TR014_2 | 2024-04-28 | 2024-05-02 | 2024-05-02 |  | 2024-07-02 | 2024-07-02 |  | 2024-07-12 |  | 2024-07-10 | 2024-07-29 |  |  | 2024-07-31 | 1037 | 150 |  | 2024-08-26 | 2024-08-22 | 149 | SEP | SEP | 2024-11-08 | 2024-11-08 | 2024-11-08 | 2024-11-08 | 2024-11-08 | 2024-11-08
49979 | 740-DKR-VU117-106-LH011-20-0 | 1 | true | 8.51 | 740-DKR-VU117-106-LH011-20-0 | LV1-105638.VU117 | 369 |  |  | MC1 | LVL 4 | W23 | TR014_2 | 2024-04-28 | 2024-05-02 | 2024-05-02 |  | 2024-06-25 | 2024-07-01 | Büro | 2024-07-12 |  | 2024-07-03 | 2024-09-03 |  |  | 2024-09-03 | 1037 | 150 |  |  | 2024-09-03 | 149 | SEP | SEP | 2024-11-08 | 2024-11-08 | 2024-11-08 | 2024-11-08 | 2024-11-08 | 2024-11-08
49980 | 740-DKR-VU117-107-LH011-20-0 | 1 | true | 16.64 | 740-DKR-VU117-107-LH011-20-0 | LV1-105638.VU117 | 369 |  |  | MC1 | LVL 4 | W23 | TR014_2 | 2024-04-28 | 2024-05-02 | 2024-05-02 |  | 2024-06-25 | 2024-06-28 | Büro | 2024-07-12 |  | 2024-07-03 | 2024-07-29 |  |  | 2024-09-30 | 1037 | 150 |  |  | 2024-10-01 | 149 | SEP | SEP | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22
49981 | 740-DKR-VU117-115-LH011-20-0 | 1 | true | 1.94 | 740-DKR-VU117-115-LH011-20-0 | LV0-105638.VU163 | 369 |  |  | MC1 | LVL 6 | W23 | TR014_2 | 2024-04-28 | 2024-05-02 | 2024-05-02 |  | 2024-06-25 | 2024-07-03 | Büro | 2024-07-12 |  | 2024-07-05 | 2024-08-28 |  |  | 2024-08-29 | 1038 | 150 |  |  | 2024-08-30 | 149 | SEP | SEP | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22
49982 | 740-DKR-VU117-119-LH011-20-0 | 1 | true | 2.1 | 740-DKR-VU117-119-LH011-20-0 | LV0-105638.VU162 | 369 |  |  | MC1 | LVL 6 | W23 | TR014_2 | 2024-04-28 | 2024-05-02 | 2024-05-02 |  | 2024-06-25 | 2024-07-02 | Büro | 2024-07-12 |  | 2024-07-05 | 2024-08-28 |  |  | 2024-09-03 | 1038 | 150 |  |  | 2024-09-03 | 149 | SEP | SEP | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22
49983 | 740-DKR-VU117-123-LH011-15-0 | 1 | false | 3.93 | 740-DKR-VU117-123-LH011-15-0 | LV0-105638.VU081 | 369 |  |  | MC1 | LVL 6 | W23 | TR014_2 | 2024-04-28 | 2024-05-02 | 2024-05-02 | [11 empty] | 1038 | 150 |  |  |  | 149 | SEP | SEP
52548 | 740-DKR-VU117-123-LH011-15-0 | 2 | true | 3.93 | 740-DKR-VU117-123-LH011-15-0 | LV0-105638.VU081 | 369 |  |  | MC1 | LVL 6 | W23 | TR024_1 | 2024-06-10 | 2024-05-02 | 2024-05-02 |  | 2024-06-25 | 2024-06-26 | Büro | 2024-07-12 |  | 2024-07-04 | 2024-09-19 |  |  | 2024-09-19 | 1038 | 150 |  |  | 2024-09-26 | 149 | SEP | SEP | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22
49984 | 740-DKR-VU117-124-LH011-15-0 | 1 | false | 1.24 | 740-DKR-VU117-124-LH011-15-0 | LV0-105638.VU081 | 369 |  |  | MC1 | LVL 6 | W23 | TR014_2 | 2024-04-28 | 2024-05-02 | 2024-05-02 | [11 empty] | 1038 | 150 |  |  |  | 149 | SEP | SEP
52549 | 740-DKR-VU117-124-LH011-15-0 | 2 | true | 1.24 | 740-DKR-VU117-124-LH011-15-0 | LV0-105638.VU081 | 369 |  |  | MC1 | LVL 6 | W23 | TR024_1 | 2024-06-10 | 2024-05-02 | 2024-05-02 |  | 2024-06-25 | 2024-06-26 | Büro | 2024-07-12 |  | 2024-07-01 | 2024-09-04 |  |  | 2024-09-10 | 1038 | 150 |  |  | 2024-09-11 | 149 | SEP | SEP | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22
49985 | 740-DKR-VU117-125-LH011-15-0 | 1 | false | 4.75 | 740-DKR-VU117-125-LH011-15-0 | LV0-105638.VU081 | 369 | 26.May.2024 |  | MC1 | LVL 6 | W23 | TR014_2 | 2024-04-28 | 2024-05-02 | 2024-05-02 |  | 2024-05-15 | 2024-05-20 | Büro | 2024-05-31 |  | 2024-05-21 | 2024-09-18 |  |  | 2024-10-02 | 1038 | 150 |  |  |  | 149 | SEP | SEP
52550 | 740-DKR-VU117-125-LH011-15-0 | 2 | true | 4.75 | 740-DKR-VU117-125-LH011-15-0 | LV0-105638.VU081 | 369 |  |  | MC1 | LVL 6 | W23 | TR024_1 | 2024-06-10 | 2024-05-02 | 2024-05-02 |  | 2024-05-15 | 2024-05-20 | Büro | 2024-05-31 |  | 2024-05-21 | 2024-09-18 |  |  | 2024-10-02 | 1038 | 150 |  |  | 2024-10-04 | 149 | SEP | SEP | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22
49986 | 740-DKR-VU117-126-LH011-15-0 | 1 | false | 2.59 | 740-DKR-VU117-126-LH011-15-0 | LV0-105638.VU081 | 369 | 26.May.2024 |  | MC1 | LVL 6 | W23 | TR014_2 | 2024-04-28 | 2024-05-02 | 2024-05-02 |  | 2024-05-15 | 2024-05-18 | Büro | 2024-05-31 |  | 2024-05-21 | 2024-09-25 |  |  | 2024-09-27 | 1038 | 150 |  |  |  | 149 | SEP | SEP
52551 | 740-DKR-VU117-126-LH011-15-0 | 2 | true | 2.59 | 740-DKR-VU117-126-LH011-15-0 | LV0-105638.VU081 | 369 |  |  | MC1 | LVL 6 | W23 | TR024_1 | 2024-06-10 | 2024-05-02 | 2024-05-02 |  | 2024-05-15 | 2024-05-18 | Büro | 2024-05-31 |  | 2024-05-21 | 2024-09-25 |  |  | 2024-09-27 | 1038 | 150 |  |  | 2024-11-06 | 149 | SEP | SEP | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22
49987 | 740-DKR-VU117-127-LH011-15-0 | 1 | false | 7.68 | 740-DKR-VU117-127-LH011-15-0 | LV0-105638.VU081 | 369 | 26.May.2024 |  | MC1 | LVL 6 | W23 | TR014_2 | 2024-04-28 | 2024-05-02 | 2024-05-02 |  | 2024-05-15 | 2024-05-18 | Büro | 2024-05-31 |  | 2024-05-21 |  |  |  | 2024-09-30 | 1038 | 150 |  |  |  | 149 | SEP | SEP
52552 | 740-DKR-VU117-127-LH011-15-0 | 2 | true | 7.68 | 740-DKR-VU117-127-LH011-15-0 | LV0-105638.VU081 | 369 |  |  | MC1 | LVL 6 | W23 | TR024_1 | 2024-06-10 | 2024-05-02 | 2024-05-02 |  | 2024-05-15 | 2024-05-18 | Büro | 2024-05-31 |  | 2024-05-21 |  |  |  | 2024-09-28 | 1038 | 150 |  |  | 2024-09-30 | 149 | SEP | SEP | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22
49988 | 740-DKR-VU117-128-LH011-15-0 | 1 | false | 1.81 | 740-DKR-VU117-128-LH011-15-0 | LV0-105638.VU081 | 369 | 26.May.2024 |  | MC1 | LVL 6 | W23 | TR014_2 | 2024-04-28 | 2024-05-02 | 2024-05-02 |  | 2024-05-15 | 2024-05-20 | Büro | 2024-05-31 |  | 2024-05-21 | 2024-09-25 |  |  | 2024-09-27 | 1038 | 150 |  |  |  | 149 | SEP | SEP
52553 | 740-DKR-VU117-128-LH011-15-0 | 2 | true | 1.81 | 740-DKR-VU117-128-LH011-15-0 | LV0-105638.VU081 | 369 |  |  | MC1 | LVL 6 | W23 | TR024_1 | 2024-06-10 | 2024-05-02 | 2024-05-02 |  | 2024-05-15 | 2024-05-20 | Büro | 2024-05-31 |  | 2024-05-21 | 2024-09-25 |  |  | 2024-09-27 | 1038 | 150 |  |  | 2024-11-06 | 149 | SEP | SEP | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22
49989 | 740-DKR-VU117-129-LH011-15-0 | 1 | false | 1.63 | 740-DKR-VU117-129-LH011-15-0 | LV0-105638.VU081 | 369 | 26.May.2024 |  | MC1 | LVL 6 | W23 | TR014_2 | 2024-04-28 | 2024-05-02 | 2024-05-02 |  | 2024-05-15 | 2024-05-20 | Büro | 2024-05-31 |  | 2024-05-23 |  |  |  | 2024-09-28 | 1038 | 150 |  |  |  | 149 | SEP | SEP
52554 | 740-DKR-VU117-129-LH011-15-0 | 2 | true | 1.63 | 740-DKR-VU117-129-LH011-15-0 | LV0-105638.VU081 | 369 |  |  | MC1 | LVL 6 | W23 | TR024_1 | 2024-06-10 | 2024-05-02 | 2024-05-02 |  | 2024-05-15 | 2024-05-20 | Büro | 2024-05-31 |  | 2024-05-23 |  |  |  | 2024-09-28 | 1038 | 150 |  |  | 2024-09-30 | 149 | SEP | SEP | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22
49990 | 740-DKR-VU117-130-LH011-15-0 | 1 | true | 3.53 | 740-DKR-VU117-130-LH011-15-0 | LV0-105638.VU081 | 369 | 26.May.2024 |  | MC1 | LVL 6 | W23 | TR014_2 | 2024-04-28 | 2024-05-02 | 2024-05-02 |  | 2024-05-15 | 2024-05-18 | Büro | 2024-05-31 |  | 2024-05-20 | 2024-07-09 |  |  | 2024-07-16 | 1038 | 150 |  | 2024-08-26 | 2024-07-29 | 149 | SEP | SEP | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22
49991 | 740-DKR-VU117-147-LH011-20-0 | 1 | true | 52.13 | 740-DKR-VU117-147-LH011-20-0 | LV1-105638.VU117 | 369 | 26.May.2024 |  | MC1 | LVL 5 | W23 | TR014_2 | 2024-04-28 | 2024-05-02 | 2024-05-02 |  | 2024-05-15 | 2024-05-24 | Büro | 2024-05-31 |  | 2024-05-28 | 2024-06-18 | 2024-06-21 |  | 2024-06-27 | 1039 | 150 |  |  | 2024-07-03 | 149 | SEP | SEP | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22
49992 | 740-DKR-VU117-148-LH011-20-0 | 1 | true | 17.44 | 740-DKR-VU117-148-LH011-20-0 | LV1-105638.VU160 | 369 |  |  | MC1 | LVL 6 | W23 | TR014_2 | 2024-04-28 | 2024-05-02 | 2024-05-02 |  | 2024-06-25 | 2024-06-27 | Büro | 2024-07-12 |  | 2024-07-01 |  |  |  | 2024-08-28 | 1038 | 150 |  |  | 2024-08-30 | 149 | SEP | SEP | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22
49993 | 740-DKR-VU117-149-LH011-15-0 | 1 | false | 3.39 | 740-DKR-VU117-149-LH011-15-0 | LV0-105633.VS673 | 369 |  |  | MC1 | LVL 6 | W23 | TR014_2 | 2024-04-28 | [13 empty] | 1038 | 150 |  |  |  | 149 | SEP | SEP
50130 | 740-DKR-VU117-149-LH011-15-0 | 2 | false | 3.39 | 740-DKR-VU117-149-LH011-15-0 | LV0-105633.VS673 | 369 |  |  | MC1 | LVL 6 | W23 | TR015_1 | 2024-04-30 | 2024-05-06 | 2024-05-06 |  | 2024-06-13 | 2024-06-18 | Büro | 2024-06-28 |  | 2024-06-20 |  |  |  | 2024-09-25 | 1038 | 150 |  |  |  | 149 | SEP | SEP
62188 | 740-DKR-VU117-149-LH011-15-0 | 3 | true | 3.39 | 740-DKR-VU117-149-LH011-15-0 | LV0-105633.VS673 | 369 |  |  | MC1 | LVL 6 | W23 | TR029_1 | 2024-07-24 | 2024-05-06 | 2024-05-06 |  | 2024-06-13 | 2024-06-18 | Büro | 2024-06-28 |  | 2024-06-20 |  |  |  | 2024-09-25 | 1038 | 150 |  |  | 2024-10-03 | 149 | SEP | SEP | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22
49994 | 740-DKR-VU117-150-LH011-15-0 | 1 | false | 3.93 | 740-DKR-VU117-150-LH011-15-0 | LV0-105633.VS672 | 369 |  |  | MC1 | LVL 6 | W23 | TR014_2 | 2024-04-28 | [13 empty] | 1038 | 150 |  |  |  | 149 | SEP | SEP
50131 | 740-DKR-VU117-150-LH011-15-0 | 2 | false | 3.93 | 740-DKR-VU117-150-LH011-15-0 | LV0-105633.VS672 | 369 |  |  | MC1 | LVL 6 | W23 | TR015_1 | 2024-04-30 | 2024-05-06 | 2024-05-06 |  | 2024-06-13 | 2024-06-18 | Büro | 2024-06-28 |  | 2024-06-20 |  |  |  | 2024-09-03 | 1038 | 150 |  |  |  | 149 | SEP | SEP
62189 | 740-DKR-VU117-150-LH011-15-0 | 3 | true | 4.1 | 740-DKR-VU117-150-LH011-15-0 | LV0-105633.VS672 | 369 |  |  | MC1 | LVL 6 | W23 | TR029_1 | 2024-07-24 | 2024-05-06 | 2024-05-06 |  | 2024-06-13 | 2024-06-18 | Büro | 2024-06-28 |  | 2024-06-20 |  |  |  | 2024-09-03 | 1038 | 150 |  |  |  | 149 | SEP | SEP | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22
49995 | 740-DKR-VU117-151-LH011-15-0 | 1 | false | 3.89 | 740-DKR-VU117-151-LH011-15-0 | LV0-105633.VS671 | 369 |  |  | MC1 | LVL 6 | W23 | TR014_2 | 2024-04-28 | [13 empty] | 1038 | 150 |  |  |  | 149 | SEP | SEP
50132 | 740-DKR-VU117-151-LH011-15-0 | 2 | false | 3.89 | 740-DKR-VU117-151-LH011-15-0 | LV0-105633.VS671 | 369 |  |  | MC1 | LVL 6 | W23 | TR015_1 | 2024-04-30 | 2024-05-06 | 2024-05-06 |  | 2024-06-13 | 2024-06-18 |  | 2024-06-28 |  | 2024-06-20 |  |  |  |  | 1038 | 150 |  |  |  | 149 | SEP | SEP
62190 | 740-DKR-VU117-151-LH011-15-0 | 3 | true | 4.1 | 740-DKR-VU117-151-LH011-15-0 | LV0-105633.VS671 | 369 |  |  | MC1 | LVL 6 | W23 | TR029_1 | 2024-07-24 | 2024-05-06 | 2024-05-06 |  | 2024-06-13 | 2024-06-18 | Büro | 2024-06-28 |  | 2024-06-20 |  |  |  | 2024-08-28 | 1038 | 150 |  |  | 2024-11-06 | 149 | SEP | SEP | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22
49996 | 740-DKR-VU117-155-LH011-20-0 | 1 | true | 1.98 | 740-DKR-VU117-155-LH011-20-0 | LV0-105638.VU161 | 369 |  |  | MC1 | LVL 6 | W23 | TR014_2 | 2024-04-28 | 2024-05-02 | 2024-05-02 |  | 2024-06-25 | 2024-07-02 | Büro | 2024-07-12 |  | 2024-07-03 | 2024-08-28 |  |  | 2024-09-10 | 1038 | 150 |  |  | 2024-09-11 | 149 | SEP | SEP | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22
49997 | 740-DKR-VU117-156-LH011-20-0 | 1 | true | 29.63 | 740-DKR-VU117-156-LH011-20-0 | LV0-105638.VU081 | 369 | 26.May.2024 |  | MC1 | LVL 5 | W23 | TR014_2 | 2024-04-28 | 2024-05-02 | 2024-05-02 |  | 2024-05-15 | 2024-05-21 | Büro | 2024-05-31 |  | 2024-05-23 | 2024-06-19 |  |  | 2024-06-21 | 1039 | 150 |  | 2024-08-26 | 2024-07-31 | 149 | SEP | SEP | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22
49998 | 740-DKR-VU117-157-LH011-20-0 | 1 | true | 23.66 | 740-DKR-VU117-157-LH011-20-0 | LV0-105638.VU081 | 369 | 26.May.2024 |  | MC1 | LVL 5 | W23 | TR014_2 | 2024-04-28 | 2024-05-02 | 2024-05-02 |  | 2024-05-15 | 2024-05-16 | Büro | 2024-05-31 |  | 2024-05-20 | 2024-09-19 | 2024-07-16 |  | 2024-09-19 | 1039 | 150 |  |  | 2024-09-26 | 149 | SEP | SEP | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22
49999 | 740-DKR-VU117-159-LH011-15-0 | 1 | false | 3.51 | 740-DKR-VU117-159-LH011-15-0 | LV0-105638.VU081 | 369 | 26.May.2024 |  | MC1 | LVL 6 | W23 | TR014_2 | 2024-04-28 | 2024-05-02 | 2024-05-02 |  | 2024-05-15 | 2024-05-21 | Büro | 2024-05-31 |  | 2024-05-22 | 2024-09-26 |  |  | 2024-09-30 | 1038 | 150 |  |  |  | 149 | SEP | SEP
52559 | 740-DKR-VU117-159-LH011-15-0 | 2 | true | 3.51 | 740-DKR-VU117-159-LH011-15-0 | LV0-105638.VU081 | 369 |  |  | MC1 | LVL 6 | W23 | TR024_1 | 2024-06-10 | 2024-05-02 | 2024-05-02 |  | 2024-05-15 | 2024-05-21 | Büro | 2024-05-31 |  | 2024-05-22 | 2024-09-26 |  |  | 2024-09-28 | 1038 | 150 |  |  | 2024-09-30 | 149 | SEP | SEP
50000 | 740-DKR-VU117-160-LH011-20-0 | 1 | true | 6.88 | 740-DKR-VU117-160-LH011-20-0 | LV1-105638.VU117 | 369 |  |  | MC1 | LVL 4 | W23 | TR014_2 | 2024-04-28 | 2024-05-02 | 2024-05-02 |  | 2024-06-25 | 2024-07-02 | Büro | 2024-07-12 |  | 2024-07-04 | 2024-09-05 |  |  | 2024-09-12 | 1037 | 150 |  |  | 2024-09-12 | 149 | SEP | SEP | 2024-11-08 | 2024-11-08 | 2024-11-08 | 2024-11-08
50001 | 740-DKR-VU117-161-LH011-20-0 | 1 | false | 9.02 | 740-DKR-VU117-161-LH011-20-0 | LV1-105638.VU117 | 369 |  |  | MC1 | LVL 4 | W23 | TR014_2 | 2024-04-28 | 2024-05-02 | 2024-05-02 | [11 empty] | 1037 | 150 |  |  |  | 149 | SEP | SEP
52264 | 740-DKR-VU117-161-LH011-20-0 | 2 | true | 9.02 | 740-DKR-VU117-161-LH011-20-0 | LV1-105638.VU117 | 369 |  |  | MC1 | LVL 4 | W23 | TR021_1 | 2024-06-04 | 2024-05-02 | 2024-05-02 |  | 2024-06-27 | 2024-06-28 | Büro | 2024-07-12 |  | 2024-07-03 | 2024-07-29 |  |  | 2024-10-03 | 1037 | 150 |  |  | 2024-10-04 | 149 | SEP | SEP | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22
50002 | 740-DKR-VU117-163-LH011-50-0 | 1 | true | 18.76 | 740-DKR-VU117-163-LH011-50-0 | LV1-105638.VU117 | 369 | 26.May.2024 |  | MC1 | LVL 4 | W23 | TR014_2 | 2024-04-28 | 2024-05-02 | 2024-05-02 |  | 2024-05-15 | 2024-05-20 | Attila Henter | 2024-05-31 |  | 2024-05-21 | 2024-06-13 |  |  | 2024-06-14 | 1037 | 150 |  | 2024-08-26 | 2024-07-29 | 149 | SEP | SEP | 2024-11-08 | 2024-11-08 | 2024-11-08 | 2024-11-08
50003 | 740-DKR-VU117-164-LH011-50-0 | 1 | true | 10.08 | 740-DKR-VU117-164-LH011-50-0 | LV1-105638.VU117 | 369 | 26.May.2024 |  | MC1 | LVL 4 | W23 | TR014_2 | 2024-04-28 | 2024-05-02 | 2024-05-02 |  | 2024-05-15 | 2024-05-21 | Attila Henter | 2024-05-31 |  | 2024-05-22 | 2024-06-13 |  |  | 2024-06-14 | 1037 | 150 |  |  | 2024-07-23 | 149 | SEP | SEP | 2024-11-08 | 2024-11-08 | 2024-11-08 | 2024-11-08 | 2024-11-08 | 2024-11-08
50004 | 740-DKR-VU117-165-LH011-50-0 | 1 | false | 52.85 | 740-DKR-VU117-165-LH011-50-0 | LV1-105638.VU117 | 369 | 26.May.2024 |  | MC1 | LVL 4 | W23 | TR014_2 | 2024-04-28 | [13 empty] | 1037 | 150 |  |  |  | 149 | SEP | SEP
50133 | 740-DKR-VU117-165-LH011-50-0 | 2 | true | 52.85 | 740-DKR-VU117-165-LH011-50-0 | LV1-105638.VU117 | 369 | 26.May.2024 |  | MC1 | LVL 4 | W23 | TR015_1 | 2024-04-30 | 2024-05-06 | 2024-05-06 |  | 2024-05-15 | 2024-05-23 | Büro | 2024-05-31 |  | 2024-05-28 | 2024-06-14 |  |  | 2024-06-20 | 1037 | 150 |  |  | 2024-07-29 | 149 | SEP | SEP | 2024-11-08 | 2024-11-08 | 2024-11-08 | 2024-11-22 | 2024-11-22 | 2024-11-22
50005 | 740-DKR-VU117-166-LH011-50-0 | 1 | true | 14.91 | 740-DKR-VU117-166-LH011-50-0 | LV1-105638.VU117 | 369 | 26.May.2024 |  | MC1 | LVL 4 | W23 | TR014_2 | 2024-04-28 | 2024-05-02 | 2024-05-02 |  | 2024-05-15 | 2024-05-17 | Büro | 2024-05-31 |  | 2024-05-18 | 2024-06-14 |  |  | 2024-06-20 | 1037 | 150 |  |  | 2024-07-18 | 149 | SEP | SEP | 2024-11-08 | 2024-11-08 | 2024-11-08 | 2024-11-08 | 2024-11-08 | 2024-11-08
50006 | 740-DKR-VU117-169-LH011-15-0 | 1 | false | 5.33 | 740-DKR-VU117-169-LH011-15-0 | LV0-105638.VU081 | 369 |  |  | MC1 | LVL 6 | W23 | TR014_2 | 2024-04-28 | 2024-05-02 | 2024-05-02 |  | 2024-06-12 | [9 empty] | 1038 | 150 |  |  |  | 149 | SEP | SEP
52560 | 740-DKR-VU117-169-LH011-15-0 | 2 | true | 5.33 | 740-DKR-VU117-169-LH011-15-0 | LV0-105638.VU081 | 369 |  |  | MC1 | LVL 6 | W23 | TR024_1 | 2024-06-10 | 2024-05-02 | 2024-05-02 |  | 2024-06-17 | 2024-06-18 | Büro | 2024-06-28 |  | 2024-06-20 | 2024-09-04 |  |  | 2024-09-10 | 1038 | 150 |  |  | 2024-09-11 | 149 | SEP | SEP | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22
50007 | 740-DKR-VU161-102-LH011-15-0 | 1 | true | 3.83 | 740-DKR-VU161-102-LH011-15-0 | LV0-105638.VU161 | 369 |  |  | MC1 | LVL 6 | W23 | TR014_2 | 2024-04-28 | 2024-05-02 | 2024-05-02 |  | 2024-06-12 | 2024-06-25 | Büro | 2024-07-12 |  | 2024-07-04 |  |  |  | 2024-08-28 | 1038 | 150 |  |  | 2024-08-30 | 149 | SEP | SEP | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22
50008 | 740-DKR-VU162-102-LH011-15-0 | 1 | true | 1.22 | 740-DKR-VU162-102-LH011-15-0 | LV0-105638.VU162 | 369 |  |  | MC1 | LVL 6 | W23 | TR014_2 | 2024-04-28 | 2024-05-02 | 2024-05-02 |  | 2024-06-12 | 2024-06-17 | Büro | 2024-06-28 |  | 2024-06-19 | 2024-08-29 |  |  | 2024-09-10 | 1038 | 150 |  |  | 2024-09-11 | 149 | SEP | SEP | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22
50009 | 740-DKR-VU163-101-LH011-15-0 | 1 | true | 3.21 | 740-DKR-VU163-101-LH011-15-0 | LV0-105638.VU163 | 369 |  |  | MC1 | LVL 6 | W23 | TR014_2 | 2024-04-28 | 2024-05-02 | 2024-05-02 |  | 2024-06-12 | 2024-06-17 | Büro | 2024-06-28 |  | 2024-06-19 | 2024-08-29 |  |  | 2024-09-10 | 1038 | 150 |  |  | 2024-09-11 | 149 | SEP | SEP | 2024-10-01 | 2024-10-14 | 2024-11-22 | 2024-11-22
50056 | 740-AB-VP001-101-LH099-25-0 | 1 | true | 0.36 | 740-AB-VP001-101-LH099-25-0 | LV1-105638.VU310 | 386 |  |  | MC1 | LVL 5 | N/A | TR014_3 | 2024-04-30 | 2024-05-02 | 2024-05-03 |  | 2024-06-12 | 2024-06-13 | Büro | 2024-06-28 |  | 2024-06-20 | 2024-09-16 |  |  | 2024-09-17 | 1018 | 150 |  | 2024-11-13 | 2024-09-25 | 149 | SEP | SEP
50057 | 740-AB-VP002-101-LH099-25-0 | 1 | true | 0.76 | 740-AB-VP002-101-LH099-25-0 | LV1-105638.VU310 | 386 |  |  | MC1 | LVL 5 | N/A | TR014_3 | 2024-04-30 | 2024-05-02 | 2024-05-03 |  | 2024-06-12 | 2024-06-13 | Büro | 2024-06-28 |  | 2024-06-14 | 2024-09-16 |  |  | 2024-09-17 | 1018 | 150 |  |  | 2024-09-25 | 149 | SEP | SEP
50058 | 740-AB-VP003-101-LH099-20-0 | 1 | true | 0.61 | 740-AB-VP003-101-LH099-20-0 | LV1-105638.VU310 | 386 |  |  | MC1 | LVL 5 | N/A | TR014_3 | 2024-04-30 | 2024-05-02 | 2024-05-03 |  | 2024-06-12 | 2024-06-13 | Büro | 2024-06-28 |  | 2024-06-14 |  |  |  | 2024-09-12 | 1018 | 150 |  |  | 2024-09-12 | 149 | SEP | SEP
50059 | 740-AB-VP004-101-LH099-20-0 | 1 | true | 0.4 | 740-AB-VP004-101-LH099-20-0 | LV1-105638.VU310 | 386 |  |  | MC1 | LVL 5 | N/A | TR014_3 | 2024-04-30 | 2024-05-02 | 2024-05-03 |  | 2024-06-12 | 2024-06-14 | Büro | 2024-06-28 |  | 2024-06-18 | 2024-09-11 |  |  | 2024-09-16 | 1018 | 150 |  |  | 2024-09-17 | 149 | SEP | SEP
50060 | 740-AB-VP031-101-LH099-25-0 | 1 | true | 0.32 | 740-AB-VP031-101-LH099-25-0 | LV1-105638.VU310 | 386 |  |  | MC1 | LVL 5 | N/A | TR014_3 | 2024-04-30 | 2024-05-02 | 2024-05-03 |  | 2024-06-12 | 2024-06-14 | Büro | 2024-06-28 |  | 2024-06-20 | 2024-09-27 |  |  | 2024-09-30 | 1018 | 150 |  |  | 2024-09-30 | 149 | SEP | SEP
50061 | 740-AB-VP032-101-LH099-25-0 | 1 | true | 0.12 | 740-AB-VP032-101-LH099-25-0 | LV1-105638.VU310 | 386 |  |  | MC1 | LVL 5 | N/A | TR014_3 | 2024-04-30 | 2024-05-02 | 2024-05-03 |  | 2024-06-12 | 2024-06-14 | Büro | 2024-06-28 |  | 2024-06-20 |  |  |  | 2024-09-28 | 1018 | 150 |  |  | 2024-09-30 | 149 | SEP | SEP
50062 | 740-AB-VP033-101-LH099-25-0 | 1 | true | 0.24 | 740-AB-VP033-101-LH099-25-0 | LV1-105638.VU310 | 386 |  |  | MC1 | LVL 5 | N/A | TR014_3 | 2024-04-30 | 2024-05-02 | 2024-05-03 |  | 2024-06-12 | 2024-06-14 | Büro | 2024-06-28 |  | 2024-06-20 |  |  |  | 2024-09-28 | 1018 | 150 |  |  | 2024-09-30 | 149 | SEP | SEP
50063 | 740-AB-VP041-101-LH099-25-0 | 1 | true | 0.42 | 740-AB-VP041-101-LH099-25-0 | LV1-105638.VU310 | 386 |  |  | MC1 | LVL 5 | N/A | TR014_3 | 2024-04-30 | 2024-05-02 | 2024-05-03 |  | 2024-06-12 | 2024-06-14 | Büro | 2024-06-28 |  | 2024-06-20 |  |  |  | 2024-10-02 | 1018 | 150 |  |  | 2024-11-14 | 149 | SEP | SEP
50064 | 740-AB-VP042-101-LH099-25-0 | 1 | true | 0.23 | 740-AB-VP042-101-LH099-25-0 | LV1-105638.VU310 | 386 |  |  | MC1 | LVL 5 | N/A | TR014_3 | 2024-04-30 | 2024-05-02 | 2024-05-03 |  | 2024-06-12 | 2024-06-13 | Büro | 2024-06-28 |  | 2024-06-17 |  |  |  | 2024-10-01 | 1018 | 150 |  |  | 2024-10-01 | 149 | SEP | SEP
50065 | 740-AB-VP043-101-LH099-25-0 | 1 | true | 0.21 | 740-AB-VP043-101-LH099-25-0 | LV1-105638.VU310 | 386 |  |  | MC1 | LVL 5 | N/A | TR014_3 | 2024-04-30 | 2024-05-02 | 2024-05-03 |  | 2024-06-12 | 2024-06-13 | Büro | 2024-06-28 |  | 2024-06-17 |  |  |  | 2024-10-01 | 1018 | 150 |  |  | 2024-10-03 | 149 | SEP | SEP
50066 | 740-AB-VP130-105-LH099-100-0 | 1 | true | 1.17 | 740-AB-VP130-105-LH099-100-0 | LV1-105638.VU310 | 386 |  |  | MC1 | LVL 5 | N/A | TR014_3 | 2024-04-30 | 2024-05-02 | 2024-05-03 |  | 2024-06-12 | 2024-06-13 | Büro | 2024-06-28 |  | 2024-06-14 | 2024-09-23 |  |  | 2024-09-25 | 1018 | 150 |  |  |  | 149 | SEP | SEP
50067 | 740-AB-VP140-105-LH099-100-0 | 1 | true | 1.17 | 740-AB-VP140-105-LH099-100-0 | LV1-105638.VU310 | 386 |  |  | MC1 | LVL 5 | N/A | TR014_3 | 2024-04-30 | 2024-05-02 | 2024-05-03 |  | 2024-06-12 | 2024-06-13 | Büro | 2024-06-28 |  | 2024-06-14 |  |  |  | 2024-09-21 | 1018 | 150 |  |  |  | 149 | SEP | SEP
50068 | 740-AB-VS020-101-LH032-50-0 | 1 | true | 0.57 | 740-AB-VS020-101-LH032-50-0 | LV1-105638.VU310 | 385 |  |  | MC1 | LVL 5 | N/A | TR014_3 | 2024-04-30 | 2024-05-02 | 2024-05-03 |  | 2024-06-12 | 2024-06-13 | Büro | 2024-06-28 |  | 2024-06-14 |  |  |  | 2024-10-07 | 1018 | 150 |  |  |  | 149 | SEP | SEP
50069 | 740-AB-VS682-101-LH032-15-0 | 1 | true | 2.49 | 740-AB-VS682-101-LH032-15-0 | LV1-105638.VU310 | 385 |  |  | MC1 | LVL 6 | N/A | TR014_3 | 2024-04-30 | 2024-05-02 | 2024-05-03 |  | 2024-06-12 | 2024-06-14 | Büro | 2024-06-28 |  | 2024-06-18 | 2024-09-24 |  |  | 2024-09-26 | 1019 | 150 |  |  | 2024-10-07 | 149 | SEP | SEP
50070 | 740-AB-VS683-101-LH032-15-0 | 1 | true | 2.2 | 740-AB-VS683-101-LH032-15-0 | LV1-105638.VU310 | 385 |  |  | MC1 | LVL 6 | N/A | TR014_3 | 2024-04-30 | 2024-05-02 | 2024-05-03 |  | 2024-06-12 | 2024-06-14 | Büro | 2024-06-28 |  | 2024-06-17 | 2024-09-24 |  |  | 2024-09-26 | 1019 | 150 |  |  | 2024-10-07 | 149 | SEP | SEP
50071 | 740-AB-VU160-101-LH032-32-0 | 1 | true | 3.91 | 740-AB-VU160-101-LH032-32-0 | LV1-105638.VU310 | 385 |  |  | MC1 | LVL 6 | N/A | TR014_3 | 2024-04-30 | 2024-05-02 | 2024-05-03 |  | 2024-06-28 | 2024-06-28 | Büro | 2024-07-12 |  | 2024-07-02 |  |  |  | 2024-09-12 | 1019 | 150 |  |  | 2024-09-12 | 149 | SEP | SEP
50072 | 740-AB-VU160-105-LH032-32-0 | 1 | true | 0.55 | 740-AB-VU160-105-LH032-32-0 | LV1-105638.VU310 | 385 |  |  | MC1 | LVL 6 | N/A | TR014_3 | 2024-04-30 | 2024-05-02 | 2024-05-03 |  | 2024-06-28 | 2024-06-28 | Attila Henter | 2024-07-12 |  | 2024-07-02 | 2024-08-29 |  |  | 2024-08-31 | 1019 | 150 |  |  | 2024-09-14 | 149 | SEP | SEP
50073 | 740-AB-VU200-119-LH032-50-0 | 1 | true | 25.98 | 740-AB-VU200-119-LH032-50-0 | LV1-105638.VU310 | 385 | 30.May.2024 |  | MC1 | LVL 5 | N/A | TR014_3 | 2024-04-30 | 2024-05-02 | 2024-05-03 |  | 2024-05-17 | 2024-05-29 | Büro | 2024-06-14 |  | 2024-06-03 | 2024-07-03 | 2024-07-10 |  | 2024-10-15 | 1018 | 150 |  |  |  | 149 | SEP | SEP
50074 | 740-AB-VU200-151-LH032-50-0 | 1 | true | 7.8 | 740-AB-VU200-151-LH032-50-0 | LV1-105638.VU310 | 385 |  |  | MC1 | LVL 5 | N/A | TR014_3 | 2024-04-30 | 2024-05-02 | 2024-05-03 |  | 2024-06-26 | 2024-07-01 | Büro | 2024-07-12 |  | 2024-07-03 | 2024-09-23 |  |  | 2024-10-11 | 1018 | 150 |  |  |  | 149 | SEP | SEP
50075 | 740-AB-VU200-155-LH032-50-0 | 1 | true | 9.28 | 740-AB-VU200-155-LH032-50-0 | LV1-105638.VU310 | 385 |  |  | MC1 | LVL 5 | N/A | TR014_3 | 2024-04-30 | 2024-05-02 | 2024-05-03 |  | 2024-06-26 | 2024-06-28 | Büro | 2024-07-12 |  | 2024-07-03 |  |  |  | 2024-10-15 | 1018 | 150 |  |  |  | 149 | SEP | SEP
50076 | 740-AB-VU200-171-LH032-50-0 | 1 | true | 22.31 | 740-AB-VU200-171-LH032-50-0 | LV1-105638.VU310 | 385 | 30.May.2024 |  | MC1 | LVL 5 | N/A | TR014_3 | 2024-04-30 | 2024-05-02 | 2024-05-03 |  | 2024-05-17 | 2024-05-24 | Büro | 2024-05-31 |  | 2024-05-28 | 2024-07-08 | 2024-07-10 |  | 2024-10-23 | 1018 | 150 |  |  | 2024-11-05 | 149 | SEP | SEP
50077 | 740-AB-VU200-184-LH032-50-0 | 1 | false | 12.52 | 740-AB-VU200-184-LH032-50-0 | LV1-105638.VU310 | 385 |  |  | MC1 | LVL 5 | N/A | TR014_3 | 2024-04-30 | 2024-05-02 | 2024-05-03 |  | 2024-06-26 | 2024-07-01 |  |  |  | 2024-07-03 |  |  |  |  | 1018 | 150 |  |  |  | 149 | SEP | SEP
56766 | 740-AB-VU200-184-LH032-50-0 | 2 | true | 12.52 | 740-AB-VU200-184-LH032-50-0 | LV1-105638.VU310 | 385 |  |  | MC1 | LVL 5 | N/A | TR027_2 | 2024-07-02 | 2024-05-02 | 2024-05-03 |  | 2024-06-26 | 2024-07-01 | Büro | 2024-07-12 |  | 2024-07-08 | 2024-08-13 |  |  | 2024-08-21 | 1018 | 150 |  | 2024-10-09 | 2024-09-02 | 149 | SEP | SEP
50078 | 740-AB-VU200-202-LH032-25-0 | 1 | true | 19.22 | 740-AB-VU200-202-LH032-25-0 | LV1-105638.VU310 | 385 |  |  | MC1 | LVL 6 | N/A | TR014_3 | 2024-04-30 | 2024-05-02 | 2024-05-03 |  | 2024-06-12 | 2024-06-25 | Büro | 2024-06-28 |  | 2024-06-26 | 2024-10-07 |  |  | 2024-10-12 | 1019 | 150 |  |  |  | 149 | SEP | SEP
50079 | 740-AB-VU200-205-LH032-25-0 | 1 | true | 10.61 | 740-AB-VU200-205-LH032-25-0 | LV1-105638.VU310 | 385 |  |  | MC1 | LVL 6 | W23 | TR014_3 | 2024-04-30 | 2024-05-02 | 2024-05-03 |  | 2024-06-26 | 2024-07-05 | Büro | 2024-07-12 |  | 2024-07-09 | 2024-10-07 |  |  | 2024-10-12 | 1019 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
50080 | 740-AB-VU200-207-LH032-25-0 | 1 | true | 8.5 | 740-AB-VU200-207-LH032-25-0 | LV1-105639.VU200 | 385 |  |  | MC1 | LVL 4 | N/A | TR014_3 | 2024-04-30 | 2024-05-02 | 2024-05-03 |  | 2024-06-12 | 2024-06-21 | Büro | 2024-06-28 |  | 2024-06-25 | 2024-09-23 |  |  | 2024-10-23 | 1040 | 150 |  |  | 2024-11-05 | 149 | SEP | SEP
50081 | 740-AB-VU200-211-LH032-25-0 | 1 | true | 9.79 | 740-AB-VU200-211-LH032-25-0 | LV1-105639.VU200 | 385 |  |  | MC1 | LVL 4 | N/A | TR014_3 | 2024-04-30 | 2024-05-02 | 2024-05-03 |  | 2024-06-12 | 2024-06-14 | Büro | 2024-06-28 |  | 2024-06-20 | 2024-09-23 |  |  | 2024-10-11 | 1040 | 150 |  |  |  | 149 | SEP | SEP
50082 | 740-AB-VU200-216-LH032-25-0 | 1 | true | 8.85 | 740-AB-VU200-216-LH032-25-0 | LV1-105639.VU200 | 385 |  |  | MC1 | LVL 4 | N/A | TR014_3 | 2024-04-30 | 2024-05-02 | 2024-05-03 |  | 2024-06-26 | 2024-06-27 | Büro | 2024-07-12 |  | 2024-07-03 | 2024-10-11 |  |  | 2024-10-15 | 1040 | 150 |  |  |  | 149 | SEP | SEP
50083 | 740-AB-VU200-218-LH032-25-0 | 1 | true | 6.39 | 740-AB-VU200-218-LH032-25-0 | LV1-105639.VU200 | 385 |  |  | MC1 | LVL 4 | N/A | TR014_3 | 2024-04-30 | 2024-05-02 | 2024-05-03 |  | 2024-06-26 | 2024-06-28 | Büro | 2024-07-12 |  | 2024-07-03 |  |  |  | 2024-10-15 | 1040 | 150 |  |  |  | 149 | SEP | SEP
50084 | 740-AB-VU200-301-LH032-65-0 | 1 | true | 31.42 | 740-AB-VU200-301-LH032-65-0 | LV1-105638.VU310 | 385 | 30.May.2024 |  | MC1 | LVL 6 | W23 | TR014_3 | 2024-04-30 | 2024-05-02 | 2024-05-03 |  | 2024-05-17 | 2024-05-17 | Büro | 2024-05-31 |  | 2024-05-21 | 2024-07-03 |  | 2024-07-10 | 2024-10-16 | 1019 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
50085 | 740-AB-VU310-101-LH032-25-0 | 1 | true | 1.06 | 740-AB-VU310-101-LH032-25-0 | LV1-105638.VU310 | 385 |  |  | MC1 | LVL 5 | N/A | TR014_3 | 2024-04-30 | 2024-05-02 | 2024-05-03 |  | 2024-06-26 | 2024-06-27 | Büro | 2024-07-12 |  | 2024-07-01 | 2024-09-16 |  |  | 2024-09-18 | 1018 | 150 |  |  | 2024-09-25 | 149 | SEP | SEP
50086 | 740-AB-VU310-102-LH032-100-0 | 1 | false | 14.6 | 740-AB-VU310-102-LH032-100-0 | LV1-105638.VU310 | 385 | 30.May.2024 |  | MC1 | LVL 6 | W23 | TR014_3 | 2024-04-30 | 2024-05-02 | 2024-05-03 |  | 2024-05-20 | 2024-05-24 | Büro | 2024-05-31 |  | 2024-05-24 | 2024-06-27 |  | 2024-06-28 |  | 1019 | 150 |  |  |  | 149 | SEP | SEP
62810 | 740-AB-VU310-102-LH032-100-0 | 2 | true | 14.6 | 740-AB-VU310-102-LH032-100-0 | LV1-105638.VU310 | 385 |  |  | MC1 | LVL 6 | W23 | TR033_1 | 2024-08-08 | 2024-05-02 | 2024-05-03 |  | 2024-05-20 | 2024-05-24 |  | 2024-05-31 |  | 2024-05-24 | 2024-06-27 |  | 2024-06-28 | 2024-08-27 | 1019 | 150 |  |  | 2024-09-03 | 149 | SEP | SEP
50087 | 740-AB-VU310-103-LH032-50-0 | 1 | true | 20.23 | 740-AB-VU310-103-LH032-50-0 | LV1-105638.VU310 | 385 |  |  | MC1 | LVL 5 | N/A | TR014_3 | 2024-04-30 | 2024-05-02 | 2024-05-03 |  | 2024-06-26 | 2024-07-02 | Büro | 2024-07-12 |  | 2024-07-08 | 2024-07-26 |  | 2024-08-06 | 2024-08-22 | 1018 | 150 |  |  | 2024-09-03 | 149 | SEP | SEP
50088 | 740-AB-VU310-104-LH032-50-0 | 1 | false | 18.09 | 740-AB-VU310-104-LH032-50-0 | LV1-105638.VU310 | 385 |  |  | MC1 | LVL 5 | N/A | TR014_3 | 2024-04-30 | 2024-05-02 | 2024-05-03 | [11 empty] | 1018 | 150 |  |  |  | 149 | SEP | SEP
51923 | 740-AB-VU310-104-LH032-50-0 | 2 | true | 18.09 | 740-AB-VU310-104-LH032-50-0 | LV1-105638.VU310 | 385 |  |  | MC1 | LVL 5 | N/A | TR019_1 | 2024-05-22 | 2024-05-02 | 2024-05-23 |  | 2024-07-01 | 2024-07-05 | Büro | 2024-07-12 |  | 2024-07-09 | 2024-09-21 |  |  | 2024-09-25 | 1018 | 150 |  |  | 2024-10-22 | 149 | SEP | SEP
50089 | 740-AB-VU310-105-LH032-50-0 | 1 | true | 18.19 | 740-AB-VU310-105-LH032-50-0 | LV1-105638.VU310 | 385 | 30.May.2024 |  | MC1 | LVL 5 | N/A | TR014_3 | 2024-04-30 | 2024-05-02 | 2024-05-03 |  | 2024-05-20 | 2024-05-20 | Büro | 2024-05-31 |  | 2024-05-23 | 2024-06-21 |  |  | 2024-06-26 | 1018 | 150 |  |  | 2024-09-03 | 149 | SEP | SEP
50090 | 740-AB-VU310-107-LH032-20-0 | 1 | true | 0.05 | 740-AB-VU310-107-LH032-20-0 | LV1-105638.VU310 | 385 |  |  | MC1 | LVL 6 | N/A | TR014_3 | 2024-04-30 | 2024-05-02 | 2024-05-03 |  | 2024-06-28 | 2024-07-01 | Büro | 2024-07-12 |  | 2024-07-04 |  |  |  | 2024-09-28 | 1019 | 150 |  |  | 2024-09-30 | 149 | SEP | SEP
50091 | 740-AB-VU310-108-LH032-100-0 | 1 | false | 18.3 | 740-AB-VU310-108-LH032-100-0 | LV1-105638.VU310 | 385 | 30.May.2024 |  | MC1 | LVL 5 | N/A | TR014_3 | 2024-04-30 | 2024-05-02 | 2024-05-03 | [11 empty] | 1018 | 150 |  |  |  | 149 | SEP | SEP
50432 | 740-AB-VU310-108-LH032-100-0 | 2 | true | 18.3 | 740-AB-VU310-108-LH032-100-0 | LV1-105638.VU310 | 385 | 30.May.2024 |  | MC1 | LVL 5 | N/A | TR015_4 | 2024-05-07 | 2024-05-14 | 2024-05-14 |  | 2024-05-20 | 2024-05-20 | Büro | 2024-05-31 |  | 2024-05-23 | 2024-06-18 |  |  | 2024-06-21 | 1018 | 150 |  | 2024-10-08 | 2024-09-03 | 149 | SEP | SEP
50092 | 740-AB-VU310-109-LH032-150-0 | 1 | false | 16.01 | 740-AB-VU310-109-LH032-150-0 | LV1-105638.VU310 | 385 | 30.May.2024 |  | MC1 | LVL 6 | N/A | TR014_3 | 2024-04-30 | 2024-05-02 | 2024-05-03 |  | 2024-05-20 | 2024-05-20 | Büro | 2024-05-31 |  | 2024-05-23 | 2024-06-07 |  | 2024-06-13 |  | 1019 | 150 |  |  |  | 149 | SEP | SEP
62811 | 740-AB-VU310-109-LH032-150-0 | 2 | true | 16.01 | 740-AB-VU310-109-LH032-150-0 | LV1-105638.VU310 | 385 |  |  | MC1 | LVL 6 | N/A | TR033_1 | 2024-08-08 | 2024-05-02 | 2024-05-03 |  | 2024-05-20 | 2024-05-20 | Büro | 2024-05-31 |  | 2024-05-23 | 2024-06-07 |  | 2024-06-13 | 2024-08-24 | 1019 | 150 |  | 2024-10-08 | 2024-09-03 | 149 | SEP | SEP
50093 | 740-AB-VU310-110-LH032-25-0 | 1 | true | 1.43 | 740-AB-VU310-110-LH032-25-0 | LV1-105638.VU310 | 385 | 30.May.2024 |  | MC1 | LVL 5 | N/A | TR014_3 | 2024-04-30 | 2024-05-02 | 2024-05-03 |  | 2024-05-20 | 2024-05-22 | Büro | 2024-05-31 |  | 2024-05-23 | 2024-09-27 |  |  | 2024-09-28 | 1018 | 150 |  |  | 2024-09-30 | 149 | SEP | SEP
50094 | 740-AB-VU310-111-LH032-25-0 | 1 | true | 0.98 | 740-AB-VU310-111-LH032-25-0 | LV1-105638.VU310 | 385 |  |  | MC1 | LVL 5 | N/A | TR014_3 | 2024-04-30 | 2024-05-02 | 2024-05-03 |  | 2024-06-26 | 2024-06-27 | Büro | 2024-07-12 |  | 2024-07-01 |  |  |  | 2024-09-30 | 1018 | 150 |  |  | 2024-10-01 | 149 | SEP | SEP
50095 | 740-AB-VU310-112-LH032-15-0 | 1 | true | 8.36 | 740-AB-VU310-112-LH032-15-0 | LV1-105638.VU310 | 385 |  |  | MC1 | LVL 5 | N/A | TR014_3 | 2024-04-30 | 2024-05-02 | 2024-05-03 |  | 2024-06-28 | 2024-07-01 | Büro | 2024-07-12 |  | 2024-07-04 |  |  |  | 2024-09-28 | 1018 | 150 |  |  | 2024-09-30 | 149 | SEP | SEP
50096 | 740-AB-VU310-113-LH032-50-0 | 1 | false | 22.62 | 740-AB-VU310-113-LH032-50-0 | LV1-105638.VU310 | 385 |  |  | MC1 | LVL 5 | W23 | TR014_3 | 2024-04-30 | 2024-05-02 | 2024-05-03 |  | 2024-06-26 | 2024-07-04 |  | 2024-07-12 |  | 2024-07-05 |  |  |  |  | 1018 | 150 |  |  |  | 149 | SEP | SEP
64664 | 740-AB-VU310-113-LH032-50-0 | 2 | false | 22.62 | 740-AB-VU310-113-LH032-50-0 | LV1-105638.VU310 | 385 |  |  | MC1 | LVL 5 | W23 | TR037_1 | 2024-09-19 | 2024-05-02 | 2024-05-03 |  | 2024-06-26 | 2024-07-04 |  | 2024-07-12 |  | 2024-07-05 |  |  |  |  | 1018 | 150 |  |  |  | 149 | SEP | SEP
64767 | 740-AB-VU310-113-LH032-50-0 | 3 | true | 22.62 | 740-AB-VU310-113-LH032-50-0 | LV1-105638.VU310 | 385 |  |  | MC1 | LVL 5 | W23 | TR038_1 | 2024-09-23 | 2024-05-02 | 2024-05-03 |  | 2024-06-26 | 2024-07-04 | Büro | 2024-07-12 |  | 2024-07-05 |  |  |  | 2024-10-15 | 1018 | 150 |  |  | 2024-10-25 | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
50097 | 740-AB-VU310-115-LH032-100-0 | 1 | true | 13.78 | 740-AB-VU310-115-LH032-100-0 | LV1-105638.VU310 | 385 | 30.May.2024 |  | MC1 | LVL 5 | N/A | TR014_3 | 2024-04-30 | 2024-05-02 | 2024-05-03 |  | 2024-05-20 | 2024-05-22 | Büro | 2024-05-31 |  | 2024-05-23 | 2024-06-11 |  |  | 2024-06-21 | 1018 | 150 |  | 2024-10-08 | 2024-10-07 | 149 | SEP | SEP
50098 | 740-AB-VU310-116-LH032-50-0 | 1 | true | 6.78 | 740-AB-VU310-116-LH032-50-0 | LV1-105638.VU310 | 385 |  |  | MC1 | LVL 5 | N/A | TR014_3 | 2024-04-30 | 2024-05-02 | 2024-05-03 |  | 2024-06-26 | 2024-07-02 | Büro | 2024-07-12 |  | 2024-07-03 | 2024-08-13 |  |  | 2024-08-21 | 1018 | 150 |  |  | 2024-09-03 | 149 | SEP | SEP
50099 | 740-AB-VU310-118-LH099-25-0 | 1 | true | 0.56 | 740-AB-VU310-118-LH099-25-0 | LV1-105638.VU310 | 386 |  |  | MC1 | LVL 5 | N/A | TR014_3 | 2024-04-30 | 2024-05-02 | 2024-05-03 |  | 2024-06-13 | 2024-06-18 | Büro | 2024-06-28 |  | 2024-06-20 | 2024-09-16 |  |  | 2024-09-18 | 1018 | 150 |  |  | 2024-09-25 | 149 | SEP | SEP
50100 | 740-AB-VU310-119-LH099-25-0 | 1 | true | 0.56 | 740-AB-VU310-119-LH099-25-0 | LV1-105638.VU310 | 386 |  |  | MC1 | LVL 5 | N/A | TR014_3 | 2024-04-30 | 2024-05-02 | 2024-05-03 |  | 2024-06-13 | 2024-06-18 | Büro | 2024-06-28 |  | 2024-06-20 | 2024-09-16 |  |  | 2024-09-18 | 1018 | 150 |  |  | 2024-09-25 | 149 | SEP | SEP
50101 | 740-AB-VU310-122-LH032-32-0 | 1 | true | 3.92 | 740-AB-VU310-122-LH032-32-0 | LV1-105638.VU310 | 385 |  |  | MC1 | LVL 6 | N/A | TR014_3 | 2024-04-30 | 2024-05-02 | 2024-05-03 |  | 2024-07-18 | 2024-07-19 | Büro | 2024-08-02 |  | 2024-07-23 |  |  |  | 2024-09-03 | 1019 | 150 |  |  | 2024-09-14 | 149 | SEP | SEP
50102 | 740-AB-VU310-123-LH032-32-0 | 1 | true | 5.72 | 740-AB-VU310-123-LH032-32-0 | LV1-105638.VU310 | 385 |  |  | MC1 | LVL 6 | N/A | TR014_3 | 2024-04-30 | 2024-05-02 | 2024-05-03 |  | 2024-07-18 | 2024-07-22 | Büro | 2024-08-02 |  | 2024-07-24 | 2024-08-29 |  |  | 2024-09-03 | 1019 | 150 |  | 2024-10-08 | 2024-09-14 | 149 | SEP | SEP
50103 | 740-AB-VU310-124-LH032-25-0 | 1 | true | 0.88 | 740-AB-VU310-124-LH032-25-0 | LV1-105638.VU310 | 385 |  |  | MC1 | LVL 5 | N/A | TR014_3 | 2024-04-30 | 2024-05-02 | 2024-05-03 |  | 2024-06-14 | 2024-06-18 | Büro | 2024-06-28 |  | 2024-06-20 |  |  |  | 2024-10-02 | 1018 | 150 |  |  | 2024-10-23 | 149 | SEP | SEP
50104 | 740-AB-VU310-125-LH032-25-0 | 1 | true | 0.84 | 740-AB-VU310-125-LH032-25-0 | LV1-105638.VU310 | 385 |  |  | MC1 | LVL 5 | N/A | TR014_3 | 2024-04-30 | 2024-05-02 | 2024-05-03 |  | 2024-06-14 | 2024-06-18 | Büro | 2024-06-28 |  | 2024-06-20 |  |  |  | 2024-10-02 | 1018 | 150 |  |  | 2024-10-23 | 149 | SEP | SEP
50105 | 740-AB-VU310-126-LH032-25-0 | 1 | true | 1.3 | 740-AB-VU310-126-LH032-25-0 | LV1-105638.VU310 | 385 |  |  | MC1 | LVL 5 | N/A | TR014_3 | 2024-04-30 | 2024-05-02 | 2024-05-03 |  | 2024-06-14 | 2024-06-19 | Büro | 2024-06-28 |  | 2024-06-21 |  |  |  | 2024-10-01 | 1018 | 150 |  |  | 2024-10-01 | 149 | SEP | SEP
50106 | 740-AB-VU310-127-LH032-25-0 | 1 | true | 0.8 | 740-AB-VU310-127-LH032-25-0 | LV1-105638.VU310 | 385 |  |  | MC1 | LVL 5 | N/A | TR014_3 | 2024-04-30 | 2024-05-02 | 2024-05-03 |  | 2024-06-14 | 2024-06-20 | Büro | 2024-06-28 |  | 2024-06-26 |  |  |  | 2024-10-01 | 1018 | 150 |  |  | 2024-10-03 | 149 | SEP | SEP
50107 | 740-AB-VU310-128-LH032-25-0 | 1 | true | 1.04 | 740-AB-VU310-128-LH032-25-0 | LV1-105638.VU310 | 385 |  |  | MC1 | LVL 5 | N/A | TR014_3 | 2024-04-30 | 2024-05-02 | 2024-05-03 |  | 2024-06-14 | 2024-06-21 | Büro | 2024-06-28 |  | 2024-06-25 | 2024-09-16 |  |  | 2024-09-18 | 1018 | 150 |  |  | 2024-09-25 | 149 | SEP | SEP
50108 | 740-AB-VU310-129-LH032-20-0 | 1 | true | 0.44 | 740-AB-VU310-129-LH032-20-0 | LV1-105638.VU310 | 385 |  |  | MC1 | LVL 5 | N/A | TR014_3 | 2024-04-30 | 2024-05-02 | 2024-05-03 |  | 2024-06-14 | 2024-06-18 | Büro | 2024-06-28 |  | 2024-06-20 | 2024-09-11 |  |  | 2024-09-16 | 1018 | 150 |  |  | 2024-09-17 | 149 | SEP | SEP
50109 | 740-AB-VU310-130-LH099-20-0 | 1 | true | 0.59 | 740-AB-VU310-130-LH099-20-0 | LV1-105638.VU310 | 386 |  |  | MC1 | LVL 5 | N/A | TR014_3 | 2024-04-30 | 2024-05-02 | 2024-05-03 |  | 2024-06-14 | 2024-06-18 | Büro | 2024-06-28 |  | 2024-06-20 | 2024-09-09 |  |  | 2024-09-12 | 1018 | 150 |  |  | 2024-09-12 | 149 | SEP | SEP
50110 | 740-AB-VU310-131-LH032-20-0 | 1 | true | 0.05 | 740-AB-VU310-131-LH032-20-0 | LV1-105638.VU310 | 385 |  |  | MC1 | LVL 6 | N/A | TR014_3 | 2024-04-30 | 2024-05-02 | 2024-05-03 |  | 2024-06-14 | 2024-06-18 | Büro | 2024-06-28 |  | 2024-06-19 |  |  |  | 2024-09-28 | 1019 | 150 |  |  | 2024-09-30 | 149 | SEP | SEP
50111 | 740-AB-VU310-132-LH032-80-0 | 1 | true | 7.19 | 740-AB-VU310-132-LH032-80-0 | LV1-105638.VU310 | 385 |  |  | MC1 | LVL 6 | W23 | TR014_3 | 2024-04-30 | 2024-05-02 | 2024-05-03 |  | 2024-06-13 | 2024-06-17 | Büro | 2024-06-28 |  | 2024-06-19 | 2024-09-09 |  |  | 2024-09-20 | 1019 | 150 |  | 2024-10-08 | 2024-10-07 | 149 | SEP | SEP
50112 | 740-AB-VU310-133-LH032-25-0 | 1 | true | 16.96 | 740-AB-VU310-133-LH032-25-0 | LV1-105638.VU310 | 385 |  |  | MC1 | LVL 6 | N/A | TR014_3 | 2024-04-30 | 2024-05-02 | 2024-05-03 |  | 2024-06-13 | 2024-06-18 |  | 2024-06-28 |  | 2024-06-20 | 2024-07-19 |  |  | 2024-07-25 | 1019 | 150 |  | 2024-10-08 | 2024-10-07 | 149 | SEP | SEP
50113 | 740-AB-VU310-134-LH099-20-0 | 1 | true | 0.64 | 740-AB-VU310-134-LH099-20-0 | LV1-105638.VU310 | 386 |  |  | MC1 | LVL 5 | N/A | TR014_3 | 2024-04-30 | 2024-05-02 | 2024-05-03 |  | 2024-06-14 | 2024-06-18 | Büro | 2024-06-28 |  | 2024-06-20 | 2024-09-11 |  |  | 2024-09-16 | 1018 | 150 |  |  | 2024-09-17 | 149 | SEP | SEP
50114 | 740-AB-VU310-135-LH032-50-0 | 1 | true | 8.51 | 740-AB-VU310-135-LH032-50-0 | LV1-105638.VU310 | 385 |  |  | MC1 | LVL 6 | N/A | TR014_3 | 2024-04-30 | 2024-05-02 | 2024-05-03 |  | 2024-06-13 | 2024-06-17 | Büro | 2024-06-28 |  | 2024-06-20 |  |  |  | 2024-08-24 | 1019 | 150 |  | 2024-10-08 | 2024-10-07 | 149 | SEP | SEP
50115 | 740-AB-VU310-137-LH099-25-0 | 1 | true | 0.88 | 740-AB-VU310-137-LH099-25-0 | LV1-105638.VU310 | 386 |  |  | MC1 | LVL 5 | N/A | TR014_3 | 2024-04-30 | 2024-05-02 | 2024-05-03 |  | 2024-06-13 | 2024-06-17 | Büro | 2024-06-28 |  | 2024-06-19 | 2024-09-27 |  |  | 2024-09-30 | 1018 | 150 |  |  | 2024-09-30 | 149 | SEP | SEP
50116 | 740-AB-VU310-138-LH099-25-0 | 1 | true | 0.56 | 740-AB-VU310-138-LH099-25-0 | LV1-105638.VU310 | 386 |  |  | MC1 | LVL 5 | N/A | TR014_3 | 2024-04-30 | 2024-05-02 | 2024-05-03 |  | 2024-06-13 | 2024-06-17 | Büro | 2024-06-28 |  | 2024-06-19 |  |  |  | 2024-10-02 | 1018 | 150 |  |  | 2024-10-03 | 149 | SEP | SEP
50117 | 740-AB-VU310-139-LH099-25-0 | 1 | true | 0.81 | 740-AB-VU310-139-LH099-25-0 | LV1-105638.VU310 | 386 |  |  | MC1 | LVL 5 | N/A | TR014_3 | 2024-04-30 | 2024-05-02 | 2024-05-03 |  | 2024-06-13 | 2024-06-17 | Büro | 2024-06-28 |  | 2024-06-19 |  |  |  | 2024-10-02 | 1018 | 150 |  |  | 2024-10-03 | 149 | SEP | SEP
50118 | 740-AB-VU310-140-LH099-25-0 | 1 | true | 0.48 | 740-AB-VU310-140-LH099-25-0 | LV1-105638.VU310 | 386 |  |  | MC1 | LVL 5 | N/A | TR014_3 | 2024-04-30 | 2024-05-02 | 2024-05-03 |  | 2024-06-13 | 2024-06-18 | Büro | 2024-06-28 |  | 2024-06-20 |  |  |  | 2024-10-01 | 1018 | 150 |  |  | 2024-10-01 | 149 | SEP | SEP
50119 | 740-AB-VU310-141-LH099-25-0 | 1 | true | 0.76 | 740-AB-VU310-141-LH099-25-0 | LV1-105638.VU310 | 386 |  |  | MC1 | LVL 5 | N/A | TR014_3 | 2024-04-30 | 2024-05-02 | 2024-05-03 |  | 2024-06-13 | 2024-06-18 | Büro | 2024-06-28 |  | 2024-06-20 |  |  |  | 2024-10-02 | 1018 | 150 |  |  | 2024-10-23 | 149 | SEP | SEP
50120 | 740-AB-VU310-142-LH099-25-0 | 1 | true | 0.55 | 740-AB-VU310-142-LH099-25-0 | LV1-105638.VU310 | 386 |  |  | MC1 | LVL 5 | N/A | TR014_3 | 2024-04-30 | 2024-05-02 | 2024-05-03 |  | 2024-06-17 | 2024-06-18 | Büro | 2024-06-28 |  | 2024-06-20 |  |  |  | 2024-10-01 | 1018 | 150 |  |  | 2024-10-03 | 149 | SEP | SEP
50121 | 740-AB-VU310-144-LH032-80-0 | 1 | true | 6.05 | 740-AB-VU310-144-LH032-80-0 | LV1-105638.VU310 | 385 |  |  | MC1 | LVL 6 | W23 | TR014_3 | 2024-04-30 | 2024-05-02 | 2024-05-03 |  | 2024-06-13 | 2024-06-21 | Büro | 2024-06-28 |  | 2024-06-25 | 2024-09-10 |  |  | 2024-09-20 | 1019 | 150 |  | 2024-10-08 | 2024-10-07 | 149 | SEP | SEP | 2024-11-08 | 2024-11-08
50122 | 740-AB-VU311-109-LH032-50-0 | 1 | true | 0.56 | 740-AB-VU311-109-LH032-50-0 | LV1-105638.VU310 | 385 |  |  | MC1 | LVL 6 | N/A | TR014_3 | 2024-04-30 | 2024-05-02 | 2024-05-03 |  | 2024-06-14 | 2024-06-14 | Büro | 2024-06-28 |  | 2024-06-18 | 2024-10-07 |  |  | 2024-10-09 | 1019 | 150 |  |  | 2024-10-09 | 149 | SEP | SEP
50123 | 740-AB-VU311-110-LH032-50-0 | 1 | true | 16.9 | 740-AB-VU311-110-LH032-50-0 | LV1-105638.VU310 | 385 |  |  | MC1 | LVL 6 | W23 | TR014_3 | 2024-04-30 | 2024-05-02 | 2024-05-03 |  | 2024-06-14 | 2024-06-17 | Büro | 2024-06-28 |  | 2024-06-19 |  |  |  | 2024-08-24 | 1019 | 150 |  |  | 2024-10-28 | 149 | SEP | SEP
50124 | 740-AB-VU321-101-LH032-50-0 | 1 | false | 14.45 | 740-AB-VU321-101-LH032-50-0 | LV1-105638.VU310 | 385 |  |  | MC1 | LVL 6 | W23 | TR014_3 | 2024-04-30 | 2024-05-02 | 2024-05-03 | [11 empty] | 1019 | 150 |  |  |  | 149 | SEP | SEP
51546 | 740-AB-VU321-101-LH032-50-0 | 3 | false | 14.45 | 740-AB-VU321-101-LH032-50-0 | LV1-105638.VU310 | 385 |  |  | MC1 | LVL 6 | W23 | TR018_2 | 2024-05-17 | 2024-05-02 | 2024-05-03 | [11 empty] | 1019 | 150 |  |  |  | 149 | SEP | SEP
51926 | 740-AB-VU321-101-LH032-50-0 | 4 | true | 14.45 | 740-AB-VU321-101-LH032-50-0 | LV1-105638.VU310 | 385 |  |  | MC1 | LVL 6 | W23 | TR019_1 | 2024-05-22 | 2024-05-02 | 2024-05-23 |  | 2024-07-01 | 2024-07-26 | Büro | 2024-08-02 |  | 2024-07-30 |  |  |  | 2024-09-23 | 1019 | 150 |  |  | 2024-09-27 | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
50125 | 740-AB-VU321-108-LH032-50-0 | 1 | true | 0.28 | 740-AB-VU321-108-LH032-50-0 | LV1-105638.VU310 | 385 |  |  | MC1 | LVL 6 | N/A | TR014_3 | 2024-04-30 | 2024-05-02 | 2024-05-03 |  | 2024-06-14 | 2024-06-17 | Büro | 2024-06-28 |  | 2024-06-19 | 2024-10-08 |  |  | 2024-10-12 | 1019 | 150 |  |  | 2024-11-07 | 149 | SEP | SEP
50126 | 740-AB-VU321-109-LH032-50-0 | 1 | true | 0.38 | 740-AB-VU321-109-LH032-50-0 | LV1-105638.VU310 | 385 |  |  | MC1 | LVL 6 | N/A | TR014_3 | 2024-04-30 | 2024-05-02 | 2024-05-03 |  | 2024-06-14 | 2024-06-17 | Büro | 2024-06-28 |  | 2024-06-19 | 2024-10-08 |  |  | 2024-10-12 | 1019 | 150 |  |  | 2024-11-07 | 149 | SEP | SEP
50127 | 740-AB-VU331-104-LH032-32-0 | 1 | true | 0.49 | 740-AB-VU331-104-LH032-32-0 | LV1-105638.VU310 | 385 |  |  | MC1 | LVL 6 | N/A | TR014_3 | 2024-04-30 | 2024-05-02 | 2024-05-03 |  | 2024-06-13 | 2024-06-14 | Büro | 2024-06-28 |  | 2024-06-18 | 2024-08-29 |  |  | 2024-08-31 | 1019 | 150 |  | 2024-09-12 | 2024-09-11 | 149 | SEP | SEP
50134 | 740-DR2-VS681-102-LH089-15-0 | 1 | true | 0.06 | 740-DR2-VS681-102-LH089-15-0 | LV0-105633.VS681 | 394 |  |  | MC1 | LVL 5 | Tt-12 | TR015_1 | 2024-04-30 | 2024-05-06 | 2024-05-06 |  | 2024-05-30 | 2024-06-06 | Büro | 2024-06-14 |  | 2024-06-06 |  |  |  | 2024-10-30 | 1005 | 150 |  | 2024-11-12 | 2024-10-31 | 149 | SEP | SEP |  |  | 2024-11-15 | 2024-11-15
50135 | 740-DR2-VS681-103-LH089-15-0 | 1 | true | 0.06 | 740-DR2-VS681-103-LH089-15-0 | LV0-105633.VS681 | 394 |  |  | MC1 | LVL 5 | Tt-12 | TR015_1 | 2024-04-30 | 2024-05-06 | 2024-05-06 |  | 2024-05-30 | 2024-06-04 | Büro | 2024-06-14 |  | 2024-06-04 |  |  |  | 2024-10-30 | 1005 | 150 |  | 2024-11-12 | 2024-10-31 | 149 | SEP | SEP |  |  | 2024-11-15 | 2024-11-15
50136 | 740-DR2-VS681-201-LH088-15-0 | 1 | true | 5.18 | 740-DR2-VS681-201-LH088-15-0 | LV0-105638.VU081 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR015_1 | 2024-04-30 | 2024-05-06 | 2024-05-06 |  | 2024-06-10 | 2024-06-12 | Dawid Mierzwa | 2024-06-14 |  | 2024-06-13 | 2024-09-23 |  |  | 2024-10-18 | 1005 | 150 |  |  | 2024-10-29 | 149 | SEP | SEP
50137 | 740-DR2-VS681-202-LH089-15-0 | 1 | true | 0.16 | 740-DR2-VS681-202-LH089-15-0 | LV0-105634.VS681 | 394 |  |  | MC1 | LVL 5 | Tt-12 | TR015_1 | 2024-04-30 | 2024-05-06 | 2024-05-06 |  | 2024-05-30 | 2024-06-04 |  | 2024-06-14 |  | 2024-06-04 |  |  |  | 2024-10-18 | 1005 | 150 |  | 2024-11-12 | 2024-10-29 | 149 | SEP | SEP
50138 | 740-DR2-VS681-203-LH089-15-0 | 1 | true | 0.16 | 740-DR2-VS681-203-LH089-15-0 | LV0-105634.VS681 | 394 |  |  | MC1 | LVL 5 | Tt-12 | TR015_1 | 2024-04-30 | 2024-05-06 | 2024-05-06 |  | 2024-06-03 | 2024-06-04 |  | 2024-06-14 |  | 2024-06-04 |  |  |  | 2024-10-18 | 1005 | 150 |  | 2024-11-12 | 2024-10-29 | 149 | SEP | SEP
50140 | 740-LP-VS681-102-LH089-25-0 | 1 | true | 2.62 | 740-LP-VS681-102-LH089-25-0 | LV0-105633.VS681 | 394 |  |  | MC1 | LVL 5 | N/A | TR015_1 | 2024-04-30 | 2024-05-06 | 2024-05-06 |  | 2024-07-18 | 2024-08-22 | Büro | 2024-08-23 |  | 2024-08-22 |  |  |  | 2024-10-30 | 929 | 150 |  | 2024-11-12 | 2024-10-31 | 149 | SEP | SEP
50141 | 740-LP-VS681-103-LH089-25-0 | 1 | true | 0.09 | 740-LP-VS681-103-LH089-25-0 | LV0-105633.VS681 | 394 |  |  | MC1 | LVL 5 | N/A | TR015_1 | 2024-04-30 | 2024-05-06 | 2024-05-06 |  | 2024-07-18 | 2024-07-22 | Büro | 2024-08-23 |  | 2024-07-22 |  |  |  | 2024-10-30 | 929 | 150 |  | 2024-11-12 | 2024-10-31 | 149 | SEP | SEP
50142 | 740-LP-VS681-202-LH089-25-0 | 1 | true | 0.45 | 740-LP-VS681-202-LH089-25-0 | LV0-105634.VS681 | 394 |  |  | MC1 | LVL 5 | N/A | TR015_1 | 2024-04-30 | 2024-05-06 | 2024-05-06 |  | 2024-07-18 | 2024-07-22 |  | 2024-08-23 |  | 2024-07-22 |  |  |  | 2024-10-18 | 929 | 150 |  | 2024-11-12 | 2024-10-28 | 149 | SEP | SEP
50144 | 740-WFI-VS671-101-LH089-40-0 | 2 | false | 1.35 | 740-WFI-VS671-101-LH089-40-0 | LV0-105633.VS671 | 394 |  |  | MC1 | LVL 6 | W23 | TR015_1 | 2024-04-30 | 2024-05-06 | 2024-05-06 |  | 2024-05-27 | 2024-05-31 |  | 2024-06-14 |  | 2024-06-05 | 2024-07-18 |  |  |  | 917 | 150 |  |  |  | 149 | SEP | SEP
62229 | 740-WFI-VS671-101-LH089-40-0 | 3 | true | 1.35 | 740-WFI-VS671-101-LH089-40-0 | LV0-105633.VS671 | 394 |  |  | MC1 | LVL 6 | W23 | TR029_1 | 2024-07-24 | 2024-05-06 | 2024-05-06 |  | 2024-05-27 | 2024-05-31 | Büro | 2024-06-14 |  | 2024-06-05 | 2024-07-18 |  | 2024-08-23 | 2024-10-01 | 917 | 150 |  | 2024-10-03 |  | 149 | SEP | SEP | 2024-09-25 |  | 2024-11-01 | 2024-11-01
50145 | 740-WFI-VS671-102-LH089-40-0 | 2 | false | 1.53 | 740-WFI-VS671-102-LH089-40-0 | LV0-105633.VS671 | 394 |  |  | MC1 | LVL 6 | W23 | TR015_1 | 2024-04-30 | 2024-05-06 | 2024-05-06 |  | 2024-05-30 | 2024-06-04 |  | 2024-06-14 |  | 2024-06-04 | 2024-07-18 |  |  | 2024-07-26 | 916 | 150 |  |  |  | 149 | SEP | SEP
62230 | 740-WFI-VS671-102-LH089-40-0 | 3 | true | 1.1 | 740-WFI-VS671-102-LH089-40-0 | LV0-105633.VS671 | 394 |  |  | MC1 | LVL 6 | W23 | TR029_1 | 2024-07-24 | 2024-05-06 | 2024-05-06 |  | 2024-05-30 | 2024-06-04 |  | 2024-06-14 |  | 2024-06-04 | 2024-07-18 |  |  | 2024-10-01 | 916 | 150 |  | 2024-10-03 |  | 149 | SEP | SEP | 2024-09-25 |  | 2024-11-01 | 2024-11-01
50146 | 740-WFI-VS671-103-LH089-40-0 | 2 | false | 1.33 | 740-WFI-VS671-103-LH089-40-0 | LV0-105633.VS671 | 394 |  |  | MC1 | LVL 6 | W23 | TR015_1 | 2024-04-30 | 2024-05-06 | 2024-05-06 |  | 2024-06-03 | 2024-06-04 | Büro | 2024-06-14 |  | 2024-06-04 | 2024-07-18 |  |  | 2024-12-03 | 918 | 150 |  |  |  | 149 | SEP | SEP
62231 | 740-WFI-VS671-103-LH089-40-0 | 3 | true | 1.33 | 740-WFI-VS671-103-LH089-40-0 | LV0-105633.VS671 | 394 |  |  | MC1 | LVL 6 | W23 | TR029_1 | 2024-07-24 | 2024-05-06 | 2024-05-06 |  | 2024-06-03 | 2024-06-04 |  | 2024-06-14 |  | 2024-06-04 | 2024-07-18 |  | 2024-08-23 | 2024-10-02 | 918 | 150 |  | 2024-10-03 |  | 149 | SEP | SEP | 2024-09-25 |  | 2024-11-01 | 2024-11-01
50147 | 740-WFI-VS672-101-LH089-40-0 | 2 | false | 1.36 | 740-WFI-VS672-101-LH089-40-0 | LV0-105633.VS672 | 394 |  |  | MC1 | LVL 6 | W23 | TR015_1 | 2024-04-30 | 2024-05-06 | 2024-05-06 |  | 2024-05-30 | 2024-05-31 |  | 2024-06-14 |  | 2024-06-03 | 2024-07-26 |  |  |  | 917 | 150 |  |  |  | 149 | SEP | SEP
62232 | 740-WFI-VS672-101-LH089-40-0 | 3 | true | 1.36 | 740-WFI-VS672-101-LH089-40-0 | LV0-105633.VS672 | 394 |  |  | MC1 | LVL 6 | W23 | TR029_1 | 2024-07-24 | 2024-05-06 | 2024-05-06 |  | 2024-05-30 | 2024-05-31 |  | 2024-06-14 |  | 2024-06-03 |  |  | 2024-08-23 | 2024-09-26 | 917 | 150 |  | 2024-10-04 | 2024-10-03 | 149 | SEP | SEP | 2024-09-25 |  | 2024-11-01 | 2024-11-01
50148 | 740-WFI-VS672-102-LH089-40-0 | 2 | false | 1.53 | 740-WFI-VS672-102-LH089-40-0 | LV0-105633.VS672 | 394 |  |  | MC1 | LVL 6 | W23 | TR015_1 | 2024-04-30 | 2024-05-06 | 2024-05-06 |  | 2024-05-30 | 2024-05-31 | Büro | 2024-06-14 |  | 2024-06-13 | 2024-07-26 |  |  | 2024-12-03 | 916 | 150 |  |  |  | 149 | SEP | SEP
62233 | 740-WFI-VS672-102-LH089-40-0 | 3 | true | 1.53 | 740-WFI-VS672-102-LH089-40-0 | LV0-105633.VS672 | 394 |  |  | MC1 | LVL 6 | W23 | TR029_1 | 2024-07-24 | 2024-05-06 | 2024-05-06 |  | 2024-05-30 | 2024-05-31 |  | 2024-06-14 |  | 2024-06-13 |  |  | 2024-08-23 | 2024-09-18 | 916 | 150 |  | 2024-10-04 | 2024-10-03 | 149 | SEP | SEP | 2024-09-25 |  | 2024-11-01 | 2024-11-01
50149 | 740-WFI-VS672-103-LH089-40-0 | 2 | false | 1.34 | 740-WFI-VS672-103-LH089-40-0 | LV0-105633.VS672 | 394 |  |  | MC1 | LVL 6 | W23 | TR015_1 | 2024-04-30 | 2024-05-06 | 2024-05-06 |  | 2024-05-30 | 2024-05-31 | Büro | 2024-06-14 |  | 2024-06-03 |  |  | 2024-08-23 | 2024-12-03 | 918 | 150 |  |  |  | 149 | SEP | SEP
62234 | 740-WFI-VS672-103-LH089-40-0 | 3 | true | 1.34 | 740-WFI-VS672-103-LH089-40-0 | LV0-105633.VS672 | 394 |  |  | MC1 | LVL 6 | W23 | TR029_1 | 2024-07-24 | 2024-05-06 | 2024-05-06 |  | 2024-05-30 | 2024-05-31 |  | 2024-06-14 |  | 2024-06-03 |  |  | 2024-08-23 | 2024-09-12 | 918 | 150 |  | 2024-10-04 | 2024-10-03 | 149 | SEP | SEP | 2024-09-25 |  | 2024-11-01 | 2024-11-01
50150 | 740-WFI-VS673-101-LH089-40-0 | 2 | false | 2.28 | 740-WFI-VS673-101-LH089-40-0 | LV0-105633.VS673 | 394 |  |  | MC1 | LVL 6 | W23 | TR015_1 | 2024-04-30 | 2024-05-06 | 2024-05-06 |  | 2024-05-29 | 2024-05-30 | Büro | 2024-06-14 |  | 2024-06-03 | 2024-07-26 |  |  | 2024-12-03 | 917 | 150 |  |  |  | 149 | SEP | SEP
62235 | 740-WFI-VS673-101-LH089-40-0 | 3 | true | 2.28 | 740-WFI-VS673-101-LH089-40-0 | LV0-105633.VS673 | 394 |  |  | MC1 | LVL 6 | W23 | TR029_1 | 2024-07-24 | 2024-05-06 | 2024-05-06 |  | 2024-05-29 | 2024-05-30 | Büro | 2024-06-14 |  | 2024-06-03 |  |  | 2024-08-30 | 2024-10-01 | 917 | 150 |  |  | 2024-10-03 | 149 | SEP | SEP | 2024-09-25 |  | 2024-11-01 | 2024-11-01
50151 | 740-WFI-VS673-102-LH089-40-0 | 2 | false | 3.11 | 740-WFI-VS673-102-LH089-40-0 | LV0-105633.VS673 | 394 |  |  | MC1 | LVL 6 | W23 | TR015_1 | 2024-04-30 | 2024-05-06 | 2024-05-06 |  | 2024-05-27 | 2024-05-31 | Büro | 2024-06-14 |  | 2024-06-05 | 2024-07-26 |  |  | 2024-12-03 | 916 | 150 |  |  |  | 149 | SEP | SEP
62236 | 740-WFI-VS673-102-LH089-40-0 | 3 | true | 2.7 | 740-WFI-VS673-102-LH089-40-0 | LV0-105633.VS673 | 394 |  |  | MC1 | LVL 6 | W23 | TR029_1 | 2024-07-24 | 2024-05-06 | 2024-05-06 |  | 2024-05-27 | 2024-05-31 | Dawid Mierzwa | 2024-06-14 |  | 2024-06-05 |  |  | 2024-08-30 |  | 916 | 150 |  |  | 2024-10-03 | 149 | SEP | SEP | 2024-09-25 |  | 2024-11-01 | 2024-11-01
50152 | 740-WFI-VS673-103-LH089-40-0 | 2 | false | 2.24 | 740-WFI-VS673-103-LH089-40-0 | LV0-105633.VS673 | 394 |  |  | MC1 | LVL 6 | W23 | TR015_1 | 2024-04-30 | 2024-05-06 | 2024-05-06 |  | 2024-05-29 | 2024-05-30 | Büro | 2024-06-14 |  | 2024-06-05 | 2024-07-26 |  |  | 2024-12-03 | 918 | 150 |  |  |  | 149 | SEP | SEP
62237 | 740-WFI-VS673-103-LH089-40-0 | 3 | true | 2.24 | 740-WFI-VS673-103-LH089-40-0 | LV0-105633.VS673 | 394 |  |  | MC1 | LVL 6 | W23 | TR029_1 | 2024-07-24 | 2024-05-06 | 2024-05-06 |  | 2024-05-29 | 2024-05-30 | Dawid Mierzwa | 2024-06-14 |  | 2024-06-05 |  |  | 2024-08-30 |  | 918 | 150 |  |  | 2024-10-03 | 149 | SEP | SEP | 2024-09-25 |  | 2024-11-01 | 2024-11-01
50223 | 740-ABkont-VP131-102-LH099-20-0 | 1 | false | 0.9 | 740-ABkont-VP131-102-LH099-20-0 | LV1-105638.VU311 | 386 |  |  | MC1 | LVL 5 | N/A | TR014_4 | 2024-05-05 | 2024-05-06 | 2024-05-07 |  | 2024-06-18 | 2024-06-18 | Satu Mare | 2024-06-28 |  | 2024-06-20 |  |  |  | 2024-10-18 | 1042 | 150 |  |  |  | 149 | SEP | SEP
56741 | 740-ABkont-VP131-102-LH099-20-0 | 2 | true | 0.9 | 740-ABkont-VP131-102-LH099-20-0 | LV1-105638.VU311 | 386 |  |  | MC1 | LVL 5 | N/A | TR027_2 | 2024-07-02 | 2024-05-06 | 2024-05-07 |  | 2024-06-18 | 2024-06-18 |  | 2024-06-28 |  | 2024-06-20 | 2024-10-18 | 2024-10-18 | 2024-10-18 | 2024-10-18 | 1042 | 150 |  |  |  | 149 | SEP | SEP
50224 | 740-ABkont-VP132-102-LH099-20-0 | 1 | false | 0.53 | 740-ABkont-VP132-102-LH099-20-0 | LV1-105638.VU311 | 386 |  |  | MC1 | LVL 5 | N/A | TR014_4 | 2024-05-05 | 2024-05-06 | 2024-05-07 |  | 2024-06-13 | 2024-06-14 | Büro | 2024-06-28 |  | 2024-06-18 |  |  |  | 2024-10-23 | 1042 | 150 |  |  |  | 149 | SEP | SEP
56742 | 740-ABkont-VP132-102-LH099-20-0 | 2 | true | 0.53 | 740-ABkont-VP132-102-LH099-20-0 | LV1-105638.VU311 | 386 |  |  | MC1 | LVL 5 | N/A | TR027_2 | 2024-07-02 | 2024-05-06 | 2024-05-07 |  | 2024-06-13 | 2024-06-14 | Büro | 2024-06-28 |  | 2024-06-18 |  |  |  | 2024-10-23 | 1042 | 150 |  | 2024-12-02 |  | 149 | SEP | SEP
50225 | 740-ABkont-VP133-102-LH099-20-0 | 1 | false | 0.66 | 740-ABkont-VP133-102-LH099-20-0 | LV1-105638.VU311 | 386 |  |  | MC1 | LVL 5 | N/A | TR014_4 | 2024-05-05 | 2024-05-06 | 2024-05-07 |  | 2024-06-18 | 2024-06-19 | Satu Mare | 2024-06-28 |  | 2024-06-21 |  |  |  | 2024-10-18 | 1042 | 150 |  |  |  | 149 | SEP | SEP
56743 | 740-ABkont-VP133-102-LH099-20-0 | 2 | true | 0.66 | 740-ABkont-VP133-102-LH099-20-0 | LV1-105638.VU311 | 386 |  |  | MC1 | LVL 5 | N/A | TR027_2 | 2024-07-02 | 2024-05-06 | 2024-05-07 |  | 2024-06-18 | 2024-06-19 |  | 2024-06-28 |  | 2024-06-21 | 2024-10-18 | 2024-10-18 | 2024-10-18 | 2024-10-18 | 1042 | 150 |  |  |  | 149 | SEP | SEP
50226 | 740-ABkont-VP134-107-LH099-15-0 | 1 | true | 0.12 | 740-ABkont-VP134-107-LH099-15-0 | LV1-105638.VU311 | 386 |  |  | MC1 | LVL 5 | N/A | TR014_4 | 2024-05-05 | 2024-05-06 | 2024-05-07 |  | 2024-06-18 | 2024-06-19 | Büro | 2024-06-28 |  | 2024-06-21 |  |  |  | 2024-10-23 | 1042 | 150 |  |  | 2024-11-05 | 149 | SEP | SEP
50227 | 740-ABkont-VP137-101-LH099-20-0 | 1 | false | 0.43 | 740-ABkont-VP137-101-LH099-20-0 | LV1-105638.VU311 | 386 |  |  | MC1 | LVL 5 | N/A | TR014_4 | 2024-05-05 | 2024-05-06 | 2024-05-07 |  | 2024-06-18 | 2024-06-19 | Büro | 2024-06-28 |  | 2024-06-21 |  |  |  | 2024-09-27 | 1042 | 150 |  |  |  | 149 | SEP | SEP
56744 | 740-ABkont-VP137-101-LH099-20-0 | 2 | true | 0.43 | 740-ABkont-VP137-101-LH099-20-0 | LV1-105638.VU311 | 386 |  |  | MC1 | LVL 5 | N/A | TR027_2 | 2024-07-02 | 2024-05-06 | 2024-05-07 |  | 2024-06-18 | 2024-06-19 | Büro | 2024-06-28 |  | 2024-06-21 | 2024-09-23 |  |  | 2024-09-27 | 1042 | 150 |  |  |  | 149 | SEP | SEP
50228 | 740-ABkont-VP141-102-LH099-20-0 | 1 | false | 1.05 | 740-ABkont-VP141-102-LH099-20-0 | LV1-105638.VU311 | 386 |  |  | MC1 | LVL 5 | N/A | TR014_4 | 2024-05-05 | 2024-05-06 | 2024-05-07 |  | 2024-06-18 | 2024-06-19 | Büro | 2024-06-28 |  | 2024-06-21 |  |  |  | 2024-09-21 | 1042 | 150 |  |  |  | 149 | SEP | SEP
56745 | 740-ABkont-VP141-102-LH099-20-0 | 2 | true | 1.05 | 740-ABkont-VP141-102-LH099-20-0 | LV1-105638.VU311 | 386 |  |  | MC1 | LVL 5 | N/A | TR027_2 | 2024-07-02 | 2024-05-06 | 2024-05-07 |  | 2024-06-18 | 2024-06-19 | Büro | 2024-06-28 |  | 2024-06-21 | 2024-09-19 |  |  | 2024-09-21 | 1042 | 150 |  |  |  | 149 | SEP | SEP
50229 | 740-ABkont-VP142-102-LH099-20-0 | 1 | false | 0.97 | 740-ABkont-VP142-102-LH099-20-0 | LV1-105638.VU311 | 386 |  |  | MC1 | LVL 5 | N/A | TR014_4 | 2024-05-05 | 2024-05-06 | 2024-05-07 |  | 2024-06-13 | 2024-06-18 | Büro |  |  | 2024-06-20 |  |  |  | 2024-09-25 | 1042 | 150 |  |  |  | 149 | SEP | SEP
56746 | 740-ABkont-VP142-102-LH099-20-0 | 2 | true | 0.97 | 740-ABkont-VP142-102-LH099-20-0 | LV1-105638.VU311 | 386 |  |  | MC1 | LVL 5 | N/A | TR027_2 | 2024-07-02 | 2024-05-06 | 2024-05-07 |  | 2024-06-13 | 2024-06-18 | Büro |  |  | 2024-06-20 | 2024-09-23 |  |  | 2024-09-25 | 1042 | 150 |  |  |  | 149 | SEP | SEP
50230 | 740-ABkont-VP143-102-LH099-20-0 | 1 | false | 0.63 | 740-ABkont-VP143-102-LH099-20-0 | LV1-105638.VU311 | 386 |  |  | MC1 | LVL 5 | N/A | TR014_4 | 2024-05-05 | 2024-05-06 | 2024-05-07 |  | 2024-06-18 | 2024-06-19 | Satu Mare | 2024-06-28 |  | 2024-06-21 |  |  |  |  | 1042 | 150 |  |  |  | 149 | SEP | SEP
56747 | 740-ABkont-VP143-102-LH099-20-0 | 2 | true | 0.63 | 740-ABkont-VP143-102-LH099-20-0 | LV1-105638.VU311 | 386 |  |  | MC1 | LVL 5 | N/A | TR027_2 | 2024-07-02 | 2024-05-06 | 2024-05-07 |  | 2024-06-18 | 2024-06-19 | Büro | 2024-06-28 |  | 2024-06-21 |  |  |  | 2024-10-04 | 1042 | 150 |  |  |  | 149 | SEP | SEP
50231 | 740-ABkont-VP144-107-LH099-15-0 | 1 | true | 0.31 | 740-ABkont-VP144-107-LH099-15-0 | LV1-105628.VP144 | 386 |  |  | MC1 | LVL 5 | N/A | TR014_4 | 2024-05-05 | 2024-05-06 | 2024-05-07 |  | 2024-06-18 | 2024-06-19 | Büro | 2024-06-28 |  | 2024-06-21 | 2024-09-23 |  |  | 2024-09-25 | 1042 | 150 |  |  |  | 149 | SEP | SEP
50232 | 740-ABkont-VP147-101-LH099-20-0 | 1 | false | 0.94 | 740-ABkont-VP147-101-LH099-20-0 | LV1-105638.VU311 | 386 |  |  | MC1 | LVL 5 | N/A | TR014_4 | 2024-05-05 | 2024-05-06 | 2024-05-07 |  | 2024-06-18 | 2024-06-19 | Attila Henter | 2024-06-28 |  | 2024-06-21 | 2024-09-18 |  |  |  | 1042 | 150 |  |  |  | 149 | SEP | SEP
56748 | 740-ABkont-VP147-101-LH099-20-0 | 2 | true | 0.94 | 740-ABkont-VP147-101-LH099-20-0 | LV1-105638.VU311 | 386 |  |  | MC1 | LVL 5 | N/A | TR027_2 | 2024-07-02 | 2024-05-06 | 2024-05-07 |  | 2024-06-18 | 2024-06-19 | Büro | 2024-06-28 |  | 2024-06-21 | 2024-09-18 |  |  | 2024-09-21 | 1042 | 150 |  |  |  | 149 | SEP | SEP
50233 | 740-ABkont-VU190-103-LH032-50-0 | 1 | false | 10.89 | 740-ABkont-VU190-103-LH032-50-0 | LV1-105638.VU190 | 385 |  |  | MC1 | LVL 5 | N/A | TR014_4 | 2024-05-05 | 2024-05-06 | 2024-05-07 |  | 2024-06-14 | 2024-06-14 | Büro | 2024-06-28 |  | 2024-06-20 | 2024-10-07 |  |  | 2024-10-16 | 1042 | 150 |  |  |  | 149 | SEP | SEP
56724 | 740-ABkont-VU190-103-LH032-50-0 | 2 | false | 10.89 | 740-ABkont-VU190-103-LH032-50-0 | LV1-105638.VU190 | 385 |  |  | MC1 | LVL 5 | N/A | TR025_2 | 2024-07-02 | 2024-05-06 | 2024-05-07 |  | 2024-06-14 | 2024-06-14 |  | 2024-06-28 |  | 2024-06-20 |  |  |  |  | 1042 | 150 |  |  |  | 149 | SEP | SEP
63293 | 740-ABkont-VU190-103-LH032-50-0 | 3 | true | 10.89 | 740-ABkont-VU190-103-LH032-50-0 | LV1-105638.VU190 | 385 |  |  | MC1 | LVL 5 | N/A | TR034_1 | 2024-08-21 | 2024-05-06 | 2024-05-07 |  | 2024-06-14 | 2024-06-14 | Büro | 2024-06-28 |  | 2024-06-20 | 2024-10-07 |  |  | 2024-10-16 | 1042 | 150 |  |  |  | 149 | SEP | SEP
50234 | 740-ABkont-VU190-104-LH032-50-0 | 1 | false | 25.05 | 740-ABkont-VU190-104-LH032-50-0 | LV1-105638.VU190 | 385 |  |  | MC1 | LVL 5 | N/A | TR014_4 | 2024-05-05 | 2024-05-06 | 2024-05-07 |  | 2024-06-14 | 2024-06-18 | Satu Mare | 2024-06-28 |  | 2024-06-21 |  |  |  |  | 1042 | 150 |  |  |  | 149 | SEP | SEP
56725 | 740-ABkont-VU190-104-LH032-50-0 | 2 | true | 25.05 | 740-ABkont-VU190-104-LH032-50-0 | LV1-105638.VU190 | 385 |  |  | MC1 | LVL 5 | N/A | TR025_2 | 2024-07-02 | 2024-05-06 | 2024-05-07 |  | 2024-06-14 | 2024-06-18 | Büro | 2024-06-28 |  | 2024-06-21 | 2024-08-05 | 2024-08-08 |  | 2024-10-15 | 1042 | 150 |  |  |  | 149 | SEP | SEP
50235 | 740-ABkont-VU190-106-LH032-50-0 | 1 | true | 5.35 | 740-ABkont-VU190-106-LH032-50-0 | LV1-105638.VU190 | 385 |  |  | MC1 | LVL 5 | N/A | TR014_4 | 2024-05-05 | 2024-05-06 | 2024-05-07 |  | 2024-06-14 | 2024-06-18 | Büro | 2024-06-28 |  | 2024-06-20 | 2024-10-02 |  |  | 2024-10-11 | 1042 | 150 |  |  |  | 149 | SEP | SEP
50236 | 740-ABkont-VU190-107-LH032-50-0 | 1 | true | 8.64 | 740-ABkont-VU190-107-LH032-50-0 | LV1-105638.VU190 | 385 |  |  | MC1 | LVL 5 | N/A | TR014_4 | 2024-05-05 | 2024-05-06 | 2024-05-07 |  | 2024-06-14 | 2024-06-19 | Büro | 2024-06-28 |  | 2024-06-20 | 2024-10-07 |  |  | 2024-10-14 | 1042 | 150 |  |  |  | 149 | SEP | SEP
50237 | 740-ABkont-VU190-205-LH032-50-0 | 1 | false | 8.74 | 740-ABkont-VU190-205-LH032-50-0 | LV1-105639.VU190 | 385 |  |  | MC1 | LVL 5 | N/A | TR014_4 | 2024-05-05 | 2024-05-06 | 2024-05-07 |  | 2024-06-14 | 2024-06-25 | Büro | 2024-06-28 |  | 2024-06-26 |  |  |  | 2024-10-12 | 1042 | 150 |  |  |  | 149 | SEP | SEP
50238 | 740-ABkont-VU190-206-LH032-50-0 | 1 | true | 8.03 | 740-ABkont-VU190-206-LH032-50-0 | LV1-105639.VU190 | 385 |  |  | MC1 | LVL 5 | N/A | TR014_4 | 2024-05-05 | 2024-05-06 | 2024-05-07 |  | 2024-06-14 | 2024-06-20 | Büro | 2024-06-28 |  | 2024-06-26 | 2024-10-07 |  |  | 2024-10-14 | 1042 | 150 |  |  |  | 149 | SEP | SEP
50239 | 740-ABkont-VU311-104-LH032-50-0 | 1 | true | 3.62 | 740-ABkont-VU311-104-LH032-50-0 | LV1-105638.VU311 | 385 |  |  | MC1 | LVL 5 | N/A | TR014_4 | 2024-05-05 | 2024-05-06 | 2024-05-07 |  | 2024-06-14 | 2024-06-25 | Büro | 2024-06-28 |  | 2024-06-26 |  |  |  | 2024-09-21 | 1042 | 150 |  |  | 2024-10-28 | 149 | SEP | SEP
50240 | 740-ABkont-VU311-105-LH032-20-0 | 1 | false | 2.96 | 740-ABkont-VU311-105-LH032-20-0 | LV1-105638.VU311 | 385 |  |  | MC1 | LVL 5 | N/A | TR014_4 | 2024-05-05 | 2024-05-06 | 2024-05-07 |  | 2024-06-17 | 2024-06-21 | Büro | 2024-06-28 |  | 2024-06-25 | 2024-09-23 |  |  | 2024-09-27 | 1042 | 150 |  |  |  | 149 | SEP | SEP
56750 | 740-ABkont-VU311-105-LH032-20-0 | 2 | true | 2.96 | 740-ABkont-VU311-105-LH032-20-0 | LV1-105638.VU311 | 385 |  |  | MC1 | LVL 5 | N/A | TR027_2 | 2024-07-02 | 2024-05-06 | 2024-05-07 |  | 2024-06-17 | 2024-06-21 | Büro | 2024-06-28 |  | 2024-06-25 | 2024-09-23 |  |  | 2024-09-27 | 1042 | 150 |  |  | 2024-10-28 | 149 | SEP | SEP
50241 | 740-ABkont-VU311-106-LH032-50-0 | 1 | true | 0.81 | 740-ABkont-VU311-106-LH032-50-0 | LV1-105638.VU311 | 385 |  |  | MC1 | LVL 6 | N/A | TR014_4 | 2024-05-05 | 2024-05-06 | 2024-05-07 |  | 2024-06-18 | 2024-06-20 | Büro | 2024-06-28 |  | 2024-06-25 |  |  |  | 2024-10-04 | 1043 | 150 |  |  |  | 149 | SEP | SEP
50242 | 740-ABkont-VU311-107-LH032-50-0 | 1 | true | 0.93 | 740-ABkont-VU311-107-LH032-50-0 | LV1-105638.VU311 | 385 |  |  | MC1 | LVL 6 | N/A | TR014_4 | 2024-05-05 | 2024-05-06 | 2024-05-07 |  | 2024-06-18 | 2024-06-20 | Büro | 2024-06-28 |  | 2024-06-25 |  |  |  | 2024-10-04 | 1043 | 150 |  |  |  | 149 | SEP | SEP
50243 | 740-ABkont-VU311-111-LH032-20-0 | 1 | false | 0.35 | 740-ABkont-VU311-111-LH032-20-0 | LV1-105638.VU311 | 385 |  |  | MC1 | LVL 5 | N/A | TR014_4 | 2024-05-05 | 2024-05-06 | 2024-05-07 |  | 2024-06-17 | 2024-06-21 | Satu Mare | 2024-06-28 |  | 2024-06-25 |  |  |  | 2024-10-18 | 1042 | 150 |  |  |  | 149 | SEP | SEP
56753 | 740-ABkont-VU311-111-LH032-20-0 | 2 | true | 0.35 | 740-ABkont-VU311-111-LH032-20-0 | LV1-105638.VU311 | 385 |  |  | MC1 | LVL 5 | N/A | TR027_2 | 2024-07-02 | 2024-05-06 | 2024-05-07 |  | 2024-06-17 | 2024-06-21 |  | 2024-06-28 |  | 2024-06-25 | 2024-10-18 | 2024-10-18 | 2024-10-18 | 2024-10-18 | 1042 | 150 |  |  | 2024-11-04 | 149 | SEP | SEP
50244 | 740-ABkont-VU311-112-LH032-40-0 | 1 | false | 0.28 | 740-ABkont-VU311-112-LH032-40-0 | LV1-105638.VU311 | 385 |  |  | MC1 | LVL 5 | N/A | TR014_4 | 2024-05-05 | 2024-05-06 | 2024-05-07 |  | 2024-06-17 | 2024-06-18 | Büro | 2024-06-28 |  | 2024-06-20 | 2024-08-05 |  |  | 2024-08-08 | 1042 | 150 |  |  |  | 149 | SEP | SEP
56754 | 740-ABkont-VU311-112-LH032-40-0 | 3 | true | 0.28 | 740-ABkont-VU311-112-LH032-40-0 | LV1-105638.VU311 | 385 |  |  | MC1 | LVL 5 | N/A | TR027_2 | 2024-07-02 | 2024-05-06 | 2024-05-07 |  | 2024-06-17 | 2024-06-18 | Büro | 2024-06-28 |  | 2024-06-20 | 2024-08-05 |  |  | 2024-08-08 | 1042 | 150 |  |  | 2024-10-28 | 149 | SEP | SEP
50245 | 740-ABkont-VU311-114-LH032-20-0 | 1 | false | 2.59 | 740-ABkont-VU311-114-LH032-20-0 | LV1-105638.VU311 | 385 |  |  | MC1 | LVL 5 | N/A | TR014_4 | 2024-05-05 | 2024-05-06 | 2024-05-07 |  | 2024-06-18 | 2024-06-27 | Satu Mare |  |  | 2024-07-01 |  |  |  |  | 1042 | 150 |  |  |  | 149 | SEP | SEP
56755 | 740-ABkont-VU311-114-LH032-20-0 | 2 | true | 2.59 | 740-ABkont-VU311-114-LH032-20-0 | LV1-105638.VU311 | 385 |  |  | MC1 | LVL 5 | N/A | TR027_2 | 2024-07-02 | 2024-05-06 | 2024-05-07 |  | 2024-06-18 | 2024-06-27 |  | 2024-07-12 |  | 2024-07-01 | 2024-10-18 |  |  | 2024-10-18 | 1042 | 150 |  |  | 2024-11-04 | 149 | SEP | SEP
50246 | 740-ABkont-VU311-115-LH032-50-0 | 1 | false | 25 | 740-ABkont-VU311-115-LH032-50-0 | LV1-105638.VU311 | 385 | 1.Jun.2024 |  | MC1 | LVL 5 | N/A | TR014_4 | 2024-05-05 | 2024-05-06 | 2024-05-07 |  | 2024-06-03 | 2024-06-07 | Büro | 2024-06-14 |  | 2024-06-07 | 2024-06-25 |  | 2024-07-01 |  | 1042 | 150 |  |  |  | 149 | SEP | SEP
56728 | 740-ABkont-VU311-115-LH032-50-0 | 2 | true | 25 | 740-ABkont-VU311-115-LH032-50-0 | LV1-105638.VU311 | 385 |  |  | MC1 | LVL 5 | N/A | TR025_2 | 2024-07-02 | 2024-05-06 | 2024-05-07 |  | 2024-06-03 | 2024-06-07 |  | 2024-06-14 |  | 2024-06-07 | 2024-06-25 |  | 2024-07-01 | 2024-07-19 | 1042 | 150 |  |  | 2024-10-28 | 149 | SEP | SEP
50247 | 740-ABkont-VU311-116-LH032-20-0 | 1 | false | 0.59 | 740-ABkont-VU311-116-LH032-20-0 | LV1-105638.VU311 | 385 |  |  | MC1 | LVL 5 | N/A | TR014_4 | 2024-05-05 | 2024-05-06 | 2024-05-07 |  | 2024-06-18 | 2024-06-28 | Satu Mare |  |  | 2024-07-02 |  |  |  |  | 1042 | 150 |  |  |  | 149 | SEP | SEP
56756 | 740-ABkont-VU311-116-LH032-20-0 | 2 | true | 0.59 | 740-ABkont-VU311-116-LH032-20-0 | LV1-105638.VU311 | 385 |  |  | MC1 | LVL 5 | N/A | TR027_2 | 2024-07-02 | 2024-05-06 | 2024-05-07 |  | 2024-06-18 | 2024-06-28 | Büro | 2024-07-12 |  | 2024-07-02 | 2024-09-19 |  |  | 2024-09-21 | 1042 | 150 |  |  |  | 149 | SEP | SEP
50248 | 740-ABkont-VU311-117-LH032-40-0 | 1 | false | 4.52 | 740-ABkont-VU311-117-LH032-40-0 | LV1-105638.VU311 | 385 | 1.Jun.2024 |  | MC1 | LVL 5 | N/A | TR014_4 | 2024-05-05 | 2024-05-06 | 2024-05-07 |  | 2024-05-21 | 2024-05-24 | Büro | 2024-05-31 |  | 2024-05-24 | 2024-06-25 |  |  | 2024-06-27 | 1042 | 150 |  |  |  | 149 | SEP | SEP
56757 | 740-ABkont-VU311-117-LH032-40-0 | 2 | true | 4.52 | 740-ABkont-VU311-117-LH032-40-0 | LV1-105638.VU311 | 385 |  |  | MC1 | LVL 5 | N/A | TR027_2 | 2024-07-02 | 2024-05-06 | 2024-05-07 |  | 2024-05-21 | 2024-05-24 |  | 2024-05-31 |  | 2024-05-24 | 2024-06-25 |  |  | 2024-06-27 | 1042 | 150 |  |  | 2024-11-06 | 149 | SEP | SEP
50249 | 740-ABkont-VU311-118-LH032-20-0 | 1 | false | 2.51 | 740-ABkont-VU311-118-LH032-20-0 | LV1-105638.VU311 | 385 |  |  | MC1 | LVL 5 | N/A | TR014_4 | 2024-05-05 | 2024-05-06 | 2024-05-07 |  | 2024-06-18 | 2024-06-28 | Satu Mare |  |  | 2024-07-03 |  |  |  |  | 1042 | 150 |  |  |  | 149 | SEP | SEP
56758 | 740-ABkont-VU311-118-LH032-20-0 | 2 | true | 2.51 | 740-ABkont-VU311-118-LH032-20-0 | LV1-105638.VU311 | 385 |  |  | MC1 | LVL 5 | N/A | TR027_2 | 2024-07-02 | 2024-05-06 | 2024-05-07 |  | 2024-06-18 | 2024-06-28 | Büro | 2024-07-12 |  | 2024-07-08 |  |  |  | 2024-10-04 | 1042 | 150 |  |  | 2024-11-06 | 149 | SEP | SEP
50250 | 740-ABkont-VU311-119-LH032-20-0 | 1 | false | 0.36 | 740-ABkont-VU311-119-LH032-20-0 | LV1-105638.VU311 | 385 |  |  | MC1 | LVL 5 | N/A | TR014_4 | 2024-05-05 | 2024-05-06 | 2024-05-07 |  | 2024-06-18 | 2024-06-28 | Satu Mare |  |  | 2024-07-02 |  |  |  |  | 1042 | 150 |  |  |  | 149 | SEP | SEP
56759 | 740-ABkont-VU311-119-LH032-20-0 | 2 | true | 0.36 | 740-ABkont-VU311-119-LH032-20-0 | LV1-105638.VU311 | 385 |  |  | MC1 | LVL 5 | N/A | TR027_2 | 2024-07-02 | 2024-05-06 | 2024-05-07 |  | 2024-06-18 | 2024-06-28 | Büro | 2024-07-12 |  | 2024-07-02 |  |  |  | 2024-09-21 | 1042 | 150 |  |  | 2024-11-06 | 149 | SEP | SEP
50251 | 740-ABkont-VU311-120-LH032-50-0 | 1 | false | 26.49 | 740-ABkont-VU311-120-LH032-50-0 | LV1-105638.VU311 | 385 | 1.Jun.2024 |  | MC1 | LVL 5 | N/A | TR014_4 | 2024-05-05 | 2024-05-06 | 2024-05-07 |  | 2024-05-21 | 2024-05-23 | Büro | 2024-05-31 |  | 2024-05-28 | 2024-06-20 | 2024-06-21 |  | 2024-06-25 | 1042 | 150 |  |  |  | 149 | SEP | SEP
56760 | 740-ABkont-VU311-120-LH032-50-0 | 3 | true | 35.3 | 740-ABkont-VU311-120-LH032-50-0 | LV1-105638.VU311 | 385 |  |  | MC1 | LVL 5 | N/A | TR027_2 | 2024-07-02 | 2024-05-06 | 2024-05-07 |  | 2024-05-21 | 2024-05-23 | Büro | 2024-05-31 |  | 2024-05-28 | 2024-06-20 | 2024-06-21 |  | 2024-10-16 | 1042 | 150 |  |  | 2024-11-07 | 149 | SEP | SEP
50288 | 740-MKWH-R-VP010-103-LH001-25-0 | 1 | true | 6.7 | 740-MKWH-R-VP010-103-LH001-25-0 | LV1-105628.VP010 | 363 |  |  | MC1 | LVL 5 | T60 | TR015_3 | 2024-05-06 | 2024-05-08 | 2024-05-08 |  | 2024-06-18 | 2024-06-25 | Büro | 2024-06-28 |  | 2024-06-26 | 2024-10-14 |  |  | 2024-10-16 | 1017 | 150 |  |  |  | 149 | SEP | SEP | 2024-11-08 | 2024-11-08 | 2024-11-08 | 2024-11-08 | 2024-11-08 | 2024-11-08
50289 | 740-MKWH-R-VU211-116-LH130-25-0 | 1 | true | 1.2 | 740-MKWH-R-VU211-116-LH130-25-0 | LV1-105638.VU211 | 362 |  |  | MC1 | LVL 6 | T60 | TR015_3 | 2024-05-06 | 2024-05-08 | 2024-05-08 |  | 2024-06-18 | 2024-06-25 | Büro | 2024-06-28 |  | 2024-06-26 | 2024-07-09 |  |  | 2024-07-09 | 804 | 150 |  | 2024-08-20 | 2024-07-16 | 149 | SEP | SEP | 2024-07-23 | 2024-09-02 | 2024-09-02 | 2024-09-02 | 2024-10-07 | 2024-10-07
50290 | 740-MKWH-S-VP010-102-LH001-25-0 | 1 | true | 5.79 | 740-MKWH-S-VP010-102-LH001-25-0 | LV1-105628.VP010 | 363 |  |  | MC1 | LVL 5 | T60 | TR015_3 | 2024-05-06 | 2024-05-08 | 2024-05-08 |  | 2024-06-18 | 2024-06-21 | Büro | 2024-06-28 |  | 2024-06-26 | 2024-10-14 |  |  | 2024-10-16 | 1017 | 150 |  |  |  | 149 | SEP | SEP | 2024-11-08 | 2024-11-08 | 2024-11-08 | 2024-11-08 | 2024-11-08 | 2024-11-08
50291 | 740-MKWH-S-VU211-106-LH130-25-0 | 1 | true | 0.5 | 740-MKWH-S-VU211-106-LH130-25-0 | LV1-105638.VU211 | 362 |  |  | MC1 | LVL 6 | T60 | TR015_3 | 2024-05-06 | 2024-05-08 | 2024-05-08 |  | 2024-06-18 | 2024-06-25 | Büro | 2024-06-28 |  | 2024-06-27 | 2024-07-09 |  |  | 2024-07-09 | 804 | 150 |  | 2024-08-20 | 2024-07-15 | 149 | SEP | SEP | 2024-07-23 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2024-10-07 | 2024-10-07
50292 | 740-SIVKont-VP131-103-LH099-50-0 | 1 | false | 0.64 | 740-SIVKont-VP131-103-LH099-50-0 | LV1-105638.VU321 | 386 |  |  | MC1 | LVL 5 | N/A | TR015_3 | 2024-05-06 | 2024-05-08 | 2024-05-08 |  | 2024-06-18 | 2024-06-19 | Büro | 2024-06-28 |  | 2024-06-20 |  |  |  | 2024-10-15 | 1243 | 150 |  |  |  | 149 | SEP | SEP
56767 | 740-SIVKont-VP131-103-LH099-50-0 | 2 | true | 0.64 | 740-SIVKont-VP131-103-LH099-50-0 | LV1-105638.VU321 | 386 |  |  | MC1 | LVL 5 | N/A | TR027_2 | 2024-07-02 | 2024-05-08 | 2024-05-08 |  | 2024-06-18 | 2024-06-19 | Büro | 2024-06-28 |  | 2024-06-20 | 2024-10-10 |  |  | 2024-10-15 | 1243 | 150 |  | 2024-12-02 |  | 149 | SEP | SEP
50293 | 740-SIVKont-VP132-103-LH099-50-0 | 1 | false | 1.13 | 740-SIVKont-VP132-103-LH099-50-0 | LV1-105638.VU321 | 386 |  |  | MC1 | LVL 5 | N/A | TR015_3 | 2024-05-06 | 2024-05-08 | 2024-05-08 |  | 2024-06-18 | 2024-06-19 | Buro | 2024-06-28 |  | 2024-06-25 | 2024-10-09 |  |  |  | 1243 | 150 |  |  |  | 149 | SEP | SEP
56768 | 740-SIVKont-VP132-103-LH099-50-0 | 2 | true | 1.13 | 740-SIVKont-VP132-103-LH099-50-0 | LV1-105638.VU321 | 386 |  |  | MC1 | LVL 5 | N/A | TR027_2 | 2024-07-02 | 2024-05-08 | 2024-05-08 |  | 2024-06-18 | 2024-06-19 | Büro | 2024-06-28 |  | 2024-06-25 | 2024-10-09 |  |  | 2024-10-11 | 1243 | 150 |  |  |  | 149 | SEP | SEP
50294 | 740-SIVKont-VP133-104-LH099-50-0 | 1 | false | 0.92 | 740-SIVKont-VP133-104-LH099-50-0 | LV1-105638.VU321 | 386 |  |  | MC1 | LVL 5 | N/A | TR015_3 | 2024-05-06 | 2024-05-08 | 2024-05-08 |  | 2024-06-18 | 2024-06-19 | Büro | 2024-06-28 |  | 2024-06-20 | 2024-10-10 |  |  | 2024-10-15 | 1243 | 150 |  |  |  | 149 | SEP | SEP
56769 | 740-SIVKont-VP133-104-LH099-50-0 | 2 | true | 0.92 | 740-SIVKont-VP133-104-LH099-50-0 | LV1-105638.VU321 | 386 |  |  | MC1 | LVL 5 | N/A | TR027_2 | 2024-07-02 | 2024-05-08 | 2024-05-08 |  | 2024-06-18 | 2024-06-19 | Büro | 2024-06-28 |  | 2024-06-20 | 2024-10-10 |  |  | 2024-10-15 | 1243 | 150 |  |  |  | 149 | SEP | SEP
50295 | 740-SIVKont-VP137-102-LH099-25-0 | 1 | false | 1.5 | 740-SIVKont-VP137-102-LH099-25-0 | LV1-105638.VU321 | 386 |  |  | MC1 | LVL 5 | N/A | TR015_3 | 2024-05-06 | 2024-05-08 | 2024-05-08 |  | 2024-06-18 | 2024-06-21 | Büro | 2024-06-28 |  | 2024-06-25 |  |  |  | 2024-09-25 | 1243 | 150 |  |  |  | 149 | SEP | SEP
56770 | 740-SIVKont-VP137-102-LH099-25-0 | 2 | true | 1.5 | 740-SIVKont-VP137-102-LH099-25-0 | LV1-105638.VU321 | 386 |  |  | MC1 | LVL 5 | N/A | TR027_2 | 2024-07-02 | 2024-05-08 | 2024-05-08 |  | 2024-06-18 | 2024-06-21 | Büro | 2024-06-28 |  | 2024-06-25 | 2024-09-23 |  |  | 2024-09-25 | 1243 | 150 |  |  |  | 149 | SEP | SEP
50296 | 740-SIVKont-VP141-103-LH099-50-0 | 1 | false | 1.21 | 740-SIVKont-VP141-103-LH099-50-0 | LV1-105638.VU321 | 386 |  |  | MC1 | LVL 5 | N/A | TR015_3 | 2024-05-06 | 2024-05-08 | 2024-05-08 |  | 2024-06-18 | 2024-06-19 |  | 2024-06-28 |  | 2024-06-20 | 2024-09-23 |  |  |  | 1243 | 150 |  |  |  | 149 | SEP | SEP
56771 | 740-SIVKont-VP141-103-LH099-50-0 | 2 | true | 1.21 | 740-SIVKont-VP141-103-LH099-50-0 | LV1-105638.VU321 | 386 |  |  | MC1 | LVL 5 | N/A | TR027_2 | 2024-07-02 | 2024-05-08 | 2024-05-08 |  | 2024-06-18 | 2024-06-19 |  | 2024-06-28 |  | 2024-06-20 |  |  |  | 2024-09-26 | 1243 | 150 |  |  |  | 149 | SEP | SEP
50297 | 740-SIVKont-VP142-103-LH099-50-0 | 1 | false | 0.85 | 740-SIVKont-VP142-103-LH099-50-0 | LV1-105638.VU321 | 386 |  |  | MC1 | LVL 5 | N/A | TR015_3 | 2024-05-06 | 2024-05-08 | 2024-05-08 |  | 2024-06-18 | 2024-06-19 | Satu Mare | 2024-06-28 |  | 2024-06-20 |  |  |  |  | 1243 | 150 |  |  |  | 149 | SEP | SEP
56772 | 740-SIVKont-VP142-103-LH099-50-0 | 2 | true | 0.85 | 740-SIVKont-VP142-103-LH099-50-0 | LV1-105638.VU321 | 386 |  |  | MC1 | LVL 5 | N/A | TR027_2 | 2024-07-02 | 2024-05-08 | 2024-05-08 |  | 2024-06-18 | 2024-06-19 | Büro | 2024-06-28 |  | 2024-06-20 | 2024-10-07 |  |  | 2024-10-10 | 1243 | 150 |  |  |  | 149 | SEP | SEP
50298 | 740-SIVKont-VP143-104-LH099-50-0 | 1 | false | 0.56 | 740-SIVKont-VP143-104-LH099-50-0 | LV1-105638.VU321 | 386 |  |  | MC1 | LVL 5 | N/A | TR015_3 | 2024-05-06 | 2024-05-08 | 2024-05-08 |  | 2024-06-18 | 2024-06-19 | Satu Mare | 2024-06-28 |  | 2024-06-20 |  |  |  |  | 1243 | 150 |  |  |  | 149 | SEP | SEP
56773 | 740-SIVKont-VP143-104-LH099-50-0 | 2 | true | 0.56 | 740-SIVKont-VP143-104-LH099-50-0 | LV1-105638.VU321 | 386 |  |  | MC1 | LVL 5 | N/A | TR027_2 | 2024-07-02 | 2024-05-08 | 2024-05-08 |  | 2024-06-18 | 2024-06-19 | Büro | 2024-06-28 |  | 2024-06-20 | 2024-10-07 |  |  | 2024-10-09 | 1243 | 150 |  |  |  | 149 | SEP | SEP
50299 | 740-SIVKont-VP147-102-LH099-25-0 | 1 | false | 0.49 | 740-SIVKont-VP147-102-LH099-25-0 | LV1-105638.VU321 | 386 |  |  | MC1 | LVL 5 | N/A | TR015_3 | 2024-05-06 | 2024-05-08 | 2024-05-08 |  | 2024-06-18 | 2024-06-20 | Büro | 2024-06-28 |  | 2024-06-25 |  |  |  | 2024-09-21 | 1243 | 150 |  |  |  | 149 | SEP | SEP
56774 | 740-SIVKont-VP147-102-LH099-25-0 | 2 | true | 0.49 | 740-SIVKont-VP147-102-LH099-25-0 | LV1-105638.VU321 | 386 |  |  | MC1 | LVL 5 | N/A | TR027_2 | 2024-07-02 | 2024-05-08 | 2024-05-08 |  | 2024-06-18 | 2024-06-20 | Büro | 2024-06-28 |  | 2024-06-25 |  |  |  | 2024-09-21 | 1243 | 150 |  |  |  | 149 | SEP | SEP
50300 | 740-SIVKont-VU321-104-LH032-50-0 | 1 | false | 3.07 | 740-SIVKont-VU321-104-LH032-50-0 | LV1-105638.VU321 | 385 |  |  | MC1 | LVL 6 | N/A | TR015_3 | 2024-05-06 | 2024-05-08 | 2024-05-08 |  |  |  | Satu Mare | [7 empty] | 1244 | 150 |  |  |  | 149 | SEP | SEP
51721 | 740-SIVKont-VU321-104-LH032-50-0 | 2 | true | 3.07 | 740-SIVKont-VU321-104-LH032-50-0 | LV1-105638.VU321 | 385 |  |  | MC1 | LVL 6 | N/A | TR018_3 | 2024-05-20 | 2024-05-08 | 2024-05-08 |  | 2024-07-02 | 2024-07-03 | Büro | 2024-07-12 |  | 2024-07-05 | 2024-10-08 |  |  | 2024-10-12 | 1244 | 150 |  |  |  | 149 | SEP | SEP
50301 | 740-SIVKont-VU321-105-LH032-100-0 | 1 | true | 22.34 | 740-SIVKont-VU321-105-LH032-100-0 | LV1-105638.VU321 | 385 | 1.Jun.2024 |  | MC1 | LVL 6 | N/A | TR015_3 | 2024-05-06 | 2024-05-08 | 2024-05-08 |  | 2024-05-20 | 2024-05-23 | Büro | 2024-05-31 |  | 2024-05-28 | 2024-06-13 |  | 2024-06-20 | 2024-09-27 | 1244 | 150 |  |  | 2024-10-23 | 149 | SEP | SEP
50302 | 740-SIVKont-VU321-106-LH032-50-0 | 1 | true | 0.12 | 740-SIVKont-VU321-106-LH032-50-0 | LV1-105638.VU321 | 385 |  |  | MC1 | LVL 6 | N/A | TR015_3 | 2024-05-06 | 2024-05-08 | 2024-05-08 |  | 2024-06-18 | 2024-06-19 | Büro | 2024-06-28 |  | 2024-06-20 | 2024-10-08 |  |  | 2024-10-12 | 1244 | 150 |  |  |  | 149 | SEP | SEP
50303 | 740-SIVKont-VU321-107-LH032-50-0 | 1 | true | 0.12 | 740-SIVKont-VU321-107-LH032-50-0 | LV1-105638.VU321 | 385 |  |  | MC1 | LVL 6 | N/A | TR015_3 | 2024-05-06 | 2024-05-08 | 2024-05-08 |  | 2024-06-18 | 2024-06-20 | Büro | 2024-06-28 |  | 2024-06-25 | 2024-10-08 |  |  | 2024-10-12 | 1244 | 150 |  |  |  | 149 | SEP | SEP
50304 | 740-SIVKont-VU321-110-LH032-100-0 | 1 | true | 13.89 | 740-SIVKont-VU321-110-LH032-100-0 | LV1-105638.VU321 | 385 | 1.Jun.2024 |  | MC1 | LVL 5 | N/A | TR015_3 | 2024-05-06 | 2024-05-08 | 2024-05-08 |  | 2024-05-20 | 2024-05-28 | Büro | 2024-05-31 |  | 2024-05-29 | 2024-06-11 | 2024-06-14 |  | 2024-06-18 | 1243 | 150 |  |  | 2024-07-18 | 149 | SEP | SEP
50305 | 740-SIVKont-VU321-111-LH032-100-0 | 1 | true | 37.86 | 740-SIVKont-VU321-111-LH032-100-0 | LV1-105638.VU321 | 385 | 1.Jun.2024 |  | MC1 | LVL 5 | N/A | TR015_3 | 2024-05-06 | 2024-05-08 | 2024-05-08 |  | 2024-05-21 | 2024-05-24 | Büro | 2024-05-31 |  | 2024-05-24 | 2024-06-11 | 2024-06-14 |  | 2024-06-18 | 1243 | 150 |  |  | 2024-07-18 | 149 | SEP | SEP
50306 | 740-SIVKont-VU321-112-LH032-50-0 | 1 | false | 2.73 | 740-SIVKont-VU321-112-LH032-50-0 | LV1-105638.VU321 | 385 | 1.Jun.2024 |  | MC1 | LVL 5 | N/A | TR015_3 | 2024-05-06 | 2024-05-08 | 2024-05-08 |  | 2024-05-21 | 2024-05-24 | Büro | 2024-05-31 |  | 2024-05-24 |  |  |  | 2024-07-04 | 1243 | 150 |  |  |  | 149 | SEP | SEP
56780 | 740-SIVKont-VU321-112-LH032-50-0 | 2 | true | 2.73 | 740-SIVKont-VU321-112-LH032-50-0 | LV1-105638.VU321 | 385 |  |  | MC1 | LVL 5 | N/A | TR027_2 | 2024-07-02 | 2024-05-08 | 2024-05-08 |  | 2024-05-21 | 2024-05-24 | Büro | 2024-05-31 |  | 2024-05-24 | 2024-07-03 |  |  | 2024-07-04 | 1243 | 150 |  |  | 2024-07-29 | 149 | SEP | SEP
50307 | 740-SIVKont-VU321-113-LH032-50-0 | 1 | false | 2.69 | 740-SIVKont-VU321-113-LH032-50-0 | LV1-105638.VU321 | 385 |  |  | MC1 | LVL 5 | N/A | TR015_3 | 2024-05-06 | 2024-05-08 | 2024-05-08 |  | 2024-06-18 | 2024-06-19 | Buro | 2024-06-28 |  | 2024-06-20 | 2024-10-09 |  |  |  | 1243 | 150 |  |  |  | 149 | SEP | SEP
56781 | 740-SIVKont-VU321-113-LH032-50-0 | 2 | true | 2.69 | 740-SIVKont-VU321-113-LH032-50-0 | LV1-105638.VU321 | 385 |  |  | MC1 | LVL 5 | N/A | TR027_2 | 2024-07-02 | 2024-05-08 | 2024-05-08 |  | 2024-06-18 | 2024-06-19 | Büro | 2024-06-28 |  | 2024-06-20 | 2024-10-09 |  |  | 2024-10-11 | 1243 | 150 |  |  | 2024-10-23 | 149 | SEP | SEP
50308 | 740-SIVKont-VU321-114-LH032-50-0 | 1 | false | 2.89 | 740-SIVKont-VU321-114-LH032-50-0 | LV1-105638.VU321 | 385 |  |  | MC1 | LVL 5 | N/A | TR015_3 | 2024-05-06 | 2024-05-08 | 2024-05-08 |  | 2024-06-18 | 2024-06-20 | Satu Mare | 2024-06-28 |  | 2024-06-25 |  |  |  |  | 1243 | 150 |  |  |  | 149 | SEP | SEP
56782 | 740-SIVKont-VU321-114-LH032-50-0 | 2 | true | 2.89 | 740-SIVKont-VU321-114-LH032-50-0 | LV1-105638.VU321 | 385 |  |  | MC1 | LVL 5 | N/A | TR027_2 | 2024-07-02 | 2024-05-08 | 2024-05-08 |  | 2024-06-18 | 2024-06-20 |  | 2024-06-28 |  | 2024-06-25 |  |  |  | 2024-07-23 | 1243 | 150 |  |  | 2024-07-29 | 149 | SEP | SEP
50309 | 740-SIVKont-VU321-116-LH032-25-0 | 1 | false | 1.29 | 740-SIVKont-VU321-116-LH032-25-0 | LV1-105638.VU321 | 385 |  |  | MC1 | LVL 5 | N/A | TR015_3 | 2024-05-06 | 2024-05-08 | 2024-05-08 |  | 2024-06-18 | 2024-06-20 | Büro | 2024-06-28 |  | 2024-06-25 | 2024-09-23 |  |  | 2024-09-25 | 1243 | 150 |  |  |  | 149 | SEP | SEP
56784 | 740-SIVKont-VU321-116-LH032-25-0 | 2 | true | 1.29 | 740-SIVKont-VU321-116-LH032-25-0 | LV1-105638.VU321 | 385 |  |  | MC1 | LVL 5 | N/A | TR027_2 | 2024-07-02 | 2024-05-08 | 2024-05-08 |  | 2024-06-18 | 2024-06-20 | Büro | 2024-06-28 |  | 2024-06-25 | 2024-09-23 |  |  | 2024-09-25 | 1243 | 150 |  |  | 2024-10-23 | 149 | SEP | SEP
50310 | 740-SIVKont-VU321-117-LH032-50-0 | 1 | false | 2.14 | 740-SIVKont-VU321-117-LH032-50-0 | LV1-105638.VU321 | 385 |  |  | MC1 | LVL 5 | N/A | TR015_3 | 2024-05-06 | 2024-05-08 | 2024-05-08 |  | 2024-06-18 | 2024-06-20 | Büro | 2024-06-28 |  | 2024-06-25 |  |  |  | 2024-09-26 | 1243 | 150 |  |  |  | 149 | SEP | SEP
56785 | 740-SIVKont-VU321-117-LH032-50-0 | 2 | true | 2.14 | 740-SIVKont-VU321-117-LH032-50-0 | LV1-105638.VU321 | 385 |  |  | MC1 | LVL 5 | N/A | TR027_2 | 2024-07-02 | 2024-05-08 | 2024-05-08 |  | 2024-06-18 | 2024-06-20 | Büro | 2024-06-28 |  | 2024-06-25 |  |  |  | 2024-09-26 | 1243 | 150 |  |  | 2024-10-23 | 149 | SEP | SEP
50311 | 740-SIVKont-VU321-118-LH032-50-0 | 1 | false | 7.22 | 740-SIVKont-VU321-118-LH032-50-0 | LV1-105638.VU321 | 385 | 1.Jun.2024 |  | MC1 | LVL 5 | N/A | TR015_3 | 2024-05-06 | 2024-05-08 | 2024-05-08 |  | 2024-05-21 | 2024-05-22 | Büro | 2024-05-31 |  | 2024-05-23 | 2024-06-18 |  |  | 2024-06-20 | 1243 | 150 |  |  |  | 149 | SEP | SEP
56786 | 740-SIVKont-VU321-118-LH032-50-0 | 2 | true | 7.22 | 740-SIVKont-VU321-118-LH032-50-0 | LV1-105638.VU321 | 385 |  |  | MC1 | LVL 5 | N/A | TR027_2 | 2024-07-02 | 2024-05-08 | 2024-05-08 |  | 2024-05-21 | 2024-05-22 |  | 2024-05-31 |  | 2024-05-23 | 2024-06-18 |  |  | 2024-06-20 | 1243 | 150 |  |  | 2024-07-29 | 149 | SEP | SEP
50312 | 740-SIVKont-VU321-119-LH032-50-0 | 1 | false | 3.34 | 740-SIVKont-VU321-119-LH032-50-0 | LV1-105638.VU321 | 385 |  |  | MC1 | LVL 5 | N/A | TR015_3 | 2024-05-06 | 2024-05-08 | 2024-05-08 |  | 2024-06-18 | 2024-06-19 | Satu Mare | 2024-06-28 |  | 2024-06-21 |  |  |  |  | 1243 | 150 |  |  |  | 149 | SEP | SEP
56787 | 740-SIVKont-VU321-119-LH032-50-0 | 2 | true | 3.34 | 740-SIVKont-VU321-119-LH032-50-0 | LV1-105638.VU321 | 385 |  |  | MC1 | LVL 5 | N/A | TR027_2 | 2024-07-02 | 2024-05-08 | 2024-05-08 |  | 2024-06-18 | 2024-06-19 | Büro | 2024-06-28 |  | 2024-06-21 | 2024-10-07 |  |  | 2024-10-09 | 1243 | 150 |  |  | 2024-10-23 | 149 | SEP | SEP
50313 | 740-SIVKont-VU321-121-LH032-25-0 | 1 | false | 4.69 | 740-SIVKont-VU321-121-LH032-25-0 | LV1-105638.VU321 | 385 |  |  | MC1 | LVL 5 | N/A | TR015_3 | 2024-05-06 | 2024-05-08 | 2024-05-08 |  | 2024-06-18 | 2024-06-20 | Büro | 2024-06-28 |  | 2024-06-25 |  |  |  | 2024-09-21 | 1243 | 150 |  |  |  | 149 | SEP | SEP
56789 | 740-SIVKont-VU321-121-LH032-25-0 | 2 | true | 4.69 | 740-SIVKont-VU321-121-LH032-25-0 | LV1-105638.VU321 | 385 |  |  | MC1 | LVL 5 | N/A | TR027_2 | 2024-07-02 | 2024-05-08 | 2024-05-08 |  | 2024-06-18 | 2024-06-20 | Büro | 2024-06-28 |  | 2024-06-25 |  |  |  | 2024-09-21 | 1243 | 150 |  |  | 2024-10-23 | 149 | SEP | SEP
50314 | 740-WBU-VU321-101-LH032-25-0 | 1 | true | 0.07 | 740-WBU-VU321-101-LH032-25-0 | LV1-105638.VU321 | 385 |  |  | MC1 | LVL 6 | N/A | TR015_3 | 2024-05-06 | 2024-05-08 | 2024-05-08 |  | 2024-06-18 | 2024-06-20 | Büro | 2024-06-28 |  | 2024-06-25 |  |  |  | 2024-10-16 | 909 | 150 |  |  | 2024-10-23 | 149 | SEP | SEP
50315 | 740-DKR-VU117-135-LH099-15-0 | 2 | true | 1.82 | 740-DKR-VU117-135-LH099-15-0 | LV0-105633.VS681 | 386 |  |  | MC1 | LVL 5 | Tt-12 | TR016_1 | 2024-05-08 | 2024-05-01 | 2024-05-01 |  | 2024-06-18 | 2024-06-20 | Büro | 2024-06-28 |  | 2024-06-25 | 2024-09-30 |  |  | 2024-10-07 | 1039 | 150 |  |  | 2024-11-06 | 149 | SEP | SEP | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22
50316 | 740-DKR-VU117-202-LH099-15-0 | 2 | false | 2.51 | 740-DKR-VU117-202-LH099-15-0 | LV0-105634.VS681 | 386 |  |  | MC1 | LVL 5 | Tt-12 | TR016_1 | 2024-05-08 | [5 empty] | Satu Mare | [7 empty] | 1039 | 150 |  |  |  | 149 | SEP | SEP
51927 | 740-DKR-VU117-202-LH099-15-0 | 3 | true | 2.51 | 740-DKR-VU117-202-LH099-15-0 | LV0-105634.VS681 | 386 |  |  | MC1 | LVL 5 | Tt-12 | TR019_1 | 2024-05-22 | 2024-05-23 | 2024-05-23 |  | 2024-06-21 | 2024-06-21 | Büro | 2024-06-28 |  | 2024-06-25 | 2024-09-30 |  |  | 2024-10-03 | 1039 | 150 |  |  | 2024-10-04 | 149 | SEP | SEP |  |  | 2024-11-30 | 2024-11-30
50433 | 740-CIP-S-VP001-101-LH089-32-0 | 1 | true | 5.94 | 740-CIP-S-VP001-101-LH089-32-0 | LV0-105634.VS681 | 394 |  |  | MC1 | LVL 5 | Tt-6 | TR015_4 | 2024-05-07 | 2024-05-14 | 2024-05-14 |  | 2024-06-03 | 2024-06-04 | Büro | 2024-06-14 |  | 2024-06-06 | 2024-09-25 |  |  | 2024-10-24 | 928 | 150 |  | 2024-11-13 | 2024-10-29 | 149 | SEP | SEP
50434 | 740-CIP-S-VP002-101-LH089-32-0 | 1 | true | 1.8 | 740-CIP-S-VP002-101-LH089-32-0 | LV0-105634.VS681 | 394 |  |  | MC1 | LVL 5 | Tt-6 | TR015_4 | 2024-05-07 | 2024-05-14 | 2024-05-14 |  | 2024-05-30 | 2024-06-06 |  | 2024-06-14 |  | 2024-06-06 | 2024-09-25 |  |  | 2024-10-18 | 928 | 150 |  |  | 2024-10-29 | 149 | SEP | SEP
50435 | 740-CIP-S-VP003-101-LH089-32-0 | 1 | true | 2.6 | 740-CIP-S-VP003-101-LH089-32-0 | LV0-105634.VS681 | 394 |  |  | MC1 | LVL 5 | Tt-6 | TR015_4 | 2024-05-07 | 2024-05-14 | 2024-05-14 |  | 2024-06-04 | 2024-06-05 | Büro | 2024-06-14 |  | 2024-06-13 | 2024-09-25 |  |  | 2024-10-24 | 928 | 150 |  | 2024-11-13 | 2024-10-29 | 149 | SEP | SEP
50436 | 740-CIP-S-VP004-101-LH089-32-0 | 1 | true | 2.07 | 740-CIP-S-VP004-101-LH089-32-0 | LV0-105634.VS681 | 394 |  |  | MC1 | LVL 5 | Tt-6 | TR015_4 | 2024-05-07 | 2024-05-14 | 2024-05-14 |  | 2024-06-04 | 2024-06-06 | Büro | 2024-06-14 |  | 2024-06-06 | 2024-09-25 |  |  | 2024-10-04 | 928 | 150 |  |  | 2024-11-08 | 149 | SEP | SEP
50437 | 740-CIP-S-VP031-113-LH089-32-0 | 1 | true | 0.9 | 740-CIP-S-VP031-113-LH089-32-0 | LV0-105633.VS681 | 394 |  |  | MC1 | LVL 5 | Tt-6 | TR015_4 | 2024-05-07 | 2024-05-14 | 2024-05-14 |  | 2024-05-30 | 2024-06-06 | Satu Mare | 2024-06-14 |  | 2024-06-06 |  |  |  | 2024-10-18 | 928 | 150 |  |  | 2024-10-29 | 149 | SEP | SEP |  |  | 2024-11-15 | 2024-11-15
50438 | 740-CIP-S-VP032-101-LH089-32-0 | 1 | true | 1.33 | 740-CIP-S-VP032-101-LH089-32-0 | LV0-105633.VS681 | 394 |  |  | MC1 | LVL 5 | Tt-6 | TR015_4 | 2024-05-07 | 2024-05-14 | 2024-05-14 |  | 2024-06-06 | 2024-06-07 | Büro | 2024-06-14 |  | 2024-06-13 | 2024-10-22 |  |  | 2024-10-24 | 928 | 150 |  |  | 2024-10-29 | 149 | SEP | SEP |  |  | 2024-11-15 | 2024-11-15
50439 | 740-CIP-S-VP033-101-LH089-32-0 | 1 | true | 1.18 | 740-CIP-S-VP033-101-LH089-32-0 | LV0-105633.VS681 | 394 |  |  | MC1 | LVL 5 | Tt-6 | TR015_4 | 2024-05-07 | 2024-05-14 | 2024-05-14 |  | 2024-06-06 | 2024-06-07 | Satu Mare | 2024-06-14 |  | 2024-06-13 |  |  |  | 2024-10-18 | 928 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-11-15 | 2024-11-15
50440 | 740-CIP-S-VP041-105-LH089-32-0 | 1 | true | 0.82 | 740-CIP-S-VP041-105-LH089-32-0 | LV0-105633.VS681 | 394 |  |  | MC1 | LVL 5 | Tt-6 | TR015_4 | 2024-05-07 | 2024-05-14 | 2024-05-14 |  | 2024-06-06 | 2024-06-07 | Büro | 2024-06-14 |  | 2024-06-13 |  |  |  | 2024-10-24 | 928 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-11-15 | 2024-11-15
50441 | 740-CIP-S-VP042-101-LH089-32-0 | 1 | true | 0.97 | 740-CIP-S-VP042-101-LH089-32-0 | LV0-105633.VS681 | 394 |  |  | MC1 | LVL 5 | Tt-6 | TR015_4 | 2024-05-07 | 2024-05-14 | 2024-05-14 |  | 2024-06-06 | 2024-06-07 | Büro | 2024-06-14 |  | 2024-06-13 |  |  |  | 2024-10-24 | 928 | 150 |  |  | 2024-10-28 | 149 | SEP | SEP |  |  | 2024-11-15 | 2024-11-15
50442 | 740-CIP-S-VP043-101-LH089-32-0 | 1 | true | 1.09 | 740-CIP-S-VP043-101-LH089-32-0 | LV0-105633.VS681 | 394 |  |  | MC1 | LVL 5 | Tt-6 | TR015_4 | 2024-05-07 | 2024-05-14 | 2024-05-14 |  | 2024-06-06 | 2024-06-07 | Büro | 2024-06-14 |  | 2024-06-13 |  |  |  | 2024-10-24 | 928 | 150 |  |  | 2024-10-28 | 149 | SEP | SEP |  |  | 2024-11-15 | 2024-11-15
50443 | 740-CIP-S-VP131-101-LH089-40-0 | 1 | true | 0.07 | 740-CIP-S-VP131-101-LH089-40-0 | LV1-105628.VP131 | 394 |  |  | MC1 | LVL 5 | Tt-6 | TR015_4 | 2024-05-07 | 2024-05-14 | 2024-05-14 |  | 2024-05-27 | 2024-05-28 | Büro | 2024-05-31 |  | 2024-05-29 | 2024-09-27 |  |  | 2024-10-04 | 928 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
50444 | 740-CIP-S-VP132-101-LH089-40-0 | 1 | true | 4.5 | 740-CIP-S-VP132-101-LH089-40-0 | LV1-105628.VP132 | 394 |  |  | MC1 | LVL 5 | Tt-6 | TR015_4 | 2024-05-07 | 2024-05-14 | 2024-05-14 |  | 2024-05-27 | 2024-05-28 | Dawid Mierzwa | 2024-05-31 |  | 2024-05-29 | 2024-09-27 |  |  | 2024-10-18 | 928 | 150 |  |  | 2024-10-29 | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
50445 | 740-CIP-S-VP133-101-LH089-40-0 | 1 | true | 1.43 | 740-CIP-S-VP133-101-LH089-40-0 | LV1-105628.VP133 | 394 |  |  | MC1 | LVL 5 | Tt-6 | TR015_4 | 2024-05-07 | 2024-05-14 | 2024-05-14 |  | 2024-05-27 | 2024-05-28 | Büro | 2024-05-31 |  | 2024-05-29 | 2024-09-27 |  |  | 2024-10-04 | 928 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
50446 | 740-CIP-S-VP141-101-LH089-40-0 | 1 | true | 0.14 | 740-CIP-S-VP141-101-LH089-40-0 | LV1-105628.VP141 | 394 |  |  | MC1 | LVL 5 | Tt-6 | TR015_4 | 2024-05-07 | 2024-05-14 | 2024-05-14 |  | 2024-05-27 | 2024-05-28 | Büro | 2024-05-31 |  | 2024-05-29 | 2024-09-27 |  |  | 2024-10-04 | 928 | 150 |  |  |  | 149 | SEP | SEP
50447 | 740-CIP-S-VP142-101-LH089-40-0 | 1 | true | 4.3 | 740-CIP-S-VP142-101-LH089-40-0 | LV1-105628.VP142 | 394 |  |  | MC1 | LVL 5 | Tt-6 | TR015_4 | 2024-05-07 | 2024-05-14 | 2024-05-14 |  | 2024-05-27 | 2024-05-28 | Büro | 2024-05-31 |  | 2024-05-29 | 2024-09-27 |  |  | 2024-10-24 | 928 | 150 |  |  | 2024-10-28 | 149 | SEP | SEP
50448 | 740-CIP-S-VP143-101-LH089-40-0 | 1 | true | 1.56 | 740-CIP-S-VP143-101-LH089-40-0 | LV1-105628.VP143 | 394 |  |  | MC1 | LVL 5 | Tt-6 | TR015_4 | 2024-05-07 | 2024-05-14 | 2024-05-14 |  | 2024-07-25 | 2024-07-30 | Büro | 2024-08-02 |  | 2024-07-30 | 2024-09-27 |  |  | 2024-10-04 | 928 | 150 |  |  |  | 149 | SEP | SEP
50449 | 740-CIP-S-VS681-127-LH089-32-0 | 1 | true | 0.08 | 740-CIP-S-VS681-127-LH089-32-0 | LV0-105633.VS681 | 394 |  |  | MC1 | LVL 5 | Tt-6 | TR015_4 | 2024-05-07 | 2024-05-14 | 2024-05-14 |  |  |  | Satu Mare | [6 empty] | 2024-10-18 | 928 | 150 |  | 2024-11-12 | 2024-10-29 | 149 | SEP | SEP |  |  | 2024-11-15 | 2024-11-15
50450 | 740-CIP-S-VS681-128-LH089-32-0 | 1 | true | 0.08 | 740-CIP-S-VS681-128-LH089-32-0 | LV0-105633.VS681 | 394 |  |  | MC1 | LVL 5 | Tt-6 | TR015_4 | 2024-05-07 | 2024-05-14 | 2024-05-14 |  |  |  | Satu Mare | [6 empty] | 2024-10-18 | 928 | 150 |  | 2024-11-12 | 2024-10-29 | 149 | SEP | SEP |  |  | 2024-11-15 | 2024-11-15
50451 | 740-CIP-S-VS681-211-LH089-32-0 | 1 | true | 0.05 | 740-CIP-S-VS681-211-LH089-32-0 | LV0-105634.VS681 | 394 |  |  | MC1 | LVL 5 | Tt-12 | TR015_4 | 2024-05-07 | 2024-05-14 | 2024-05-14 |  | 2024-09-04 |  | Dawid Mierzwa |  |  | 2024-09-06 | 2024-09-23 |  |  | 2024-10-18 | 928 | 150 |  | 2024-11-12 | 2024-10-29 | 149 | SEP | SEP
50452 | 740-CIP-S-VS681-212-LH089-32-0 | 1 | true | 0 | 740-CIP-S-VS681-212-LH089-32-0 | LV0-105634.VS681 | 394 |  |  | MC1 | LVL 5 | Tt-12 | TR015_4 | 2024-05-07 | 2024-05-14 | 2024-05-14 |  | 2024-09-04 |  | Dawid Mierzwa |  |  | 2024-09-06 | 2024-09-23 |  |  | 2024-10-18 | 928 | 150 |  | 2024-11-12 | 2024-10-29 | 149 | SEP | SEP
50453 | 740-SIV-VP001-103-LH099-50-0 | 1 | false | 0.68 | 740-SIV-VP001-103-LH099-50-0 | LV1-105638.VU320 | 386 |  |  | MC1 | LVL 5 | N/A | TR015_4 | 2024-05-07 | 2024-05-14 | 2024-05-14 |  | 2024-06-18 | 2024-06-26 | Büro | 2024-06-28 |  | 2024-06-27 |  |  |  | 2024-09-07 | 1253 | 150 |  |  |  | 149 | SEP | SEP
56791 | 740-SIV-VP001-103-LH099-50-0 | 2 | true | 0.68 | 740-SIV-VP001-103-LH099-50-0 | LV1-105638.VU320 | 386 |  |  | MC1 | LVL 5 | N/A | TR027_2 | 2024-07-02 | 2024-05-14 | 2024-05-14 |  | 2024-06-18 | 2024-06-26 | Büro | 2024-06-28 |  | 2024-06-27 | 2024-09-06 |  |  | 2024-09-07 | 1253 | 150 |  | 2024-11-13 | 2024-09-11 | 149 | SEP | SEP
50454 | 740-SIV-VP002-103-LH099-50-0 | 1 | false | 0.67 | 740-SIV-VP002-103-LH099-50-0 | LV1-105638.VU320 | 386 |  |  | MC1 | LVL 5 | N/A | TR015_4 | 2024-05-07 | 2024-05-14 | 2024-05-14 |  | 2024-06-18 | 2024-06-26 | Büro | 2024-06-28 |  | 2024-06-27 | 2024-09-05 |  |  | 2024-09-07 | 1253 | 150 |  |  |  | 149 | SEP | SEP
56792 | 740-SIV-VP002-103-LH099-50-0 | 2 | true | 0.67 | 740-SIV-VP002-103-LH099-50-0 | LV1-105638.VU320 | 386 |  |  | MC1 | LVL 5 | N/A | TR027_2 | 2024-07-02 | 2024-05-14 | 2024-05-14 |  | 2024-06-18 | 2024-06-26 | Büro | 2024-06-28 |  | 2024-06-27 | 2024-09-05 |  |  | 2024-09-07 | 1253 | 150 |  |  | 2024-09-11 | 149 | SEP | SEP
50455 | 740-SIV-VP003-103-LH099-50-0 | 1 | false | 0.54 | 740-SIV-VP003-103-LH099-50-0 | LV1-105638.VU320 | 386 |  |  | MC1 | LVL 5 | N/A | TR015_4 | 2024-05-07 | 2024-05-14 | 2024-05-14 |  | 2024-06-18 | 2024-06-26 | Satu Mare | 2024-06-28 |  | 2024-06-27 |  |  |  |  | 1253 | 150 |  |  |  | 149 | SEP | SEP
56793 | 740-SIV-VP003-103-LH099-50-0 | 2 | true | 0.54 | 740-SIV-VP003-103-LH099-50-0 | LV1-105638.VU320 | 386 |  |  | MC1 | LVL 5 | N/A | TR027_2 | 2024-07-02 | 2024-05-14 | 2024-05-14 |  | 2024-06-18 | 2024-06-26 | Büro | 2024-06-28 |  | 2024-06-27 | 2024-09-05 |  |  | 2024-09-10 | 1253 | 150 |  |  | 2024-09-11 | 149 | SEP | SEP
50456 | 740-SIV-VP004-103-LH099-50-0 | 1 | false | 0.94 | 740-SIV-VP004-103-LH099-50-0 | LV1-105638.VU320 | 386 |  |  | MC1 | LVL 5 | N/A | TR015_4 | 2024-05-07 | 2024-05-14 | 2024-05-14 |  | 2024-06-18 | 2024-06-27 | Satu Mare |  |  | 2024-07-01 |  |  |  |  | 1253 | 150 |  |  |  | 149 | SEP | SEP
56794 | 740-SIV-VP004-103-LH099-50-0 | 2 | true | 0.94 | 740-SIV-VP004-103-LH099-50-0 | LV1-105638.VU320 | 386 |  |  | MC1 | LVL 5 | N/A | TR027_2 | 2024-07-02 | 2024-05-14 | 2024-05-14 |  | 2024-06-18 | 2024-06-27 | Büro | 2024-07-12 |  | 2024-07-01 | 2024-09-03 |  |  | 2024-09-05 | 1253 | 150 |  |  | 2024-09-09 | 149 | SEP | SEP
50457 | 740-SIV-VP031-102-LH099-50-0 | 1 | false | 0.63 | 740-SIV-VP031-102-LH099-50-0 | LV1-105638.VU320 | 386 |  |  | MC1 | LVL 5 | N/A | TR015_4 | 2024-05-07 | 2024-05-14 | 2024-05-14 |  | 2024-06-18 | 2024-06-26 | Satu Mare | 2024-06-28 |  | 2024-06-27 |  |  |  |  | 1253 | 150 |  |  |  | 149 | SEP | SEP
56795 | 740-SIV-VP031-102-LH099-50-0 | 2 | true | 0.63 | 740-SIV-VP031-102-LH099-50-0 | LV1-105638.VU320 | 386 |  |  | MC1 | LVL 5 | N/A | TR027_2 | 2024-07-02 | 2024-05-14 | 2024-05-14 |  | 2024-06-18 | 2024-06-26 | Büro | 2024-06-28 |  | 2024-06-27 |  |  |  | 2024-10-01 | 1253 | 150 |  |  | 2024-10-01 | 149 | SEP | SEP
50458 | 740-SIV-VP032-102-LH099-65-0 | 1 | false | 0.54 | 740-SIV-VP032-102-LH099-65-0 | LV1-105638.VU320 | 386 |  |  | MC1 | LVL 5 | N/A | TR015_4 | 2024-05-07 | 2024-05-14 | 2024-05-14 |  | 2024-06-17 | 2024-06-20 | Satu Mare | 2024-06-28 |  | 2024-06-25 |  |  |  |  | 1253 | 150 |  |  |  | 149 | SEP | SEP
56796 | 740-SIV-VP032-102-LH099-65-0 | 2 | true | 0.54 | 740-SIV-VP032-102-LH099-65-0 | LV1-105638.VU320 | 386 |  |  | MC1 | LVL 5 | N/A | TR027_2 | 2024-07-02 | 2024-05-14 | 2024-05-14 |  | 2024-06-17 | 2024-06-20 | Büro | 2024-06-28 |  | 2024-06-25 |  |  |  | 2024-10-01 | 1253 | 150 |  |  | 2024-10-01 | 149 | SEP | SEP
50459 | 740-SIV-VP033-102-LH099-65-0 | 1 | false | 0.47 | 740-SIV-VP033-102-LH099-65-0 | LV1-105638.VU320 | 386 |  |  | MC1 | LVL 5 | N/A | TR015_4 | 2024-05-07 | 2024-05-14 | 2024-05-14 |  | 2024-06-17 | 2024-06-21 | Satu Mare | 2024-06-28 |  | 2024-06-25 |  |  |  |  | 1253 | 150 |  |  |  | 149 | SEP | SEP
56797 | 740-SIV-VP033-102-LH099-65-0 | 2 | true | 0.47 | 740-SIV-VP033-102-LH099-65-0 | LV1-105638.VU320 | 386 |  |  | MC1 | LVL 5 | N/A | TR027_2 | 2024-07-02 | 2024-05-14 | 2024-05-14 |  | 2024-06-17 | 2024-06-21 | Büro | 2024-06-28 |  | 2024-06-25 |  |  |  | 2024-10-01 | 1253 | 150 |  |  | 2024-10-01 | 149 | SEP | SEP
50460 | 740-SIV-VP041-102-LH099-50-0 | 1 | false | 0.33 | 740-SIV-VP041-102-LH099-50-0 | LV1-105638.VU320 | 386 |  |  | MC1 | LVL 5 | N/A | TR015_4 | 2024-05-07 | 2024-05-14 | 2024-05-14 |  | 2024-06-13 | 2024-06-19 | Satu Mare | 2024-06-28 |  | 2024-06-21 |  |  |  |  | 1253 | 150 |  |  |  | 149 | SEP | SEP
56798 | 740-SIV-VP041-102-LH099-50-0 | 2 | true | 0.33 | 740-SIV-VP041-102-LH099-50-0 | LV1-105638.VU320 | 386 |  |  | MC1 | LVL 5 | N/A | TR027_2 | 2024-07-02 | 2024-05-14 | 2024-05-14 |  | 2024-06-13 | 2024-06-19 | Büro | 2024-06-28 |  | 2024-06-21 | 2024-09-21 |  |  | 2024-10-01 | 1253 | 150 |  |  | 2024-10-01 | 149 | SEP | SEP
50461 | 740-SIV-VP042-102-LH099-65-0 | 1 | false | 0.85 | 740-SIV-VP042-102-LH099-65-0 | LV1-105638.VU320 | 386 |  |  | MC1 | LVL 5 | N/A | TR015_4 | 2024-05-07 | 2024-05-14 | 2024-05-14 |  | 2024-06-17 | 2024-06-20 | Satu Mare | 2024-06-28 |  | 2024-06-25 |  |  |  |  | 1253 | 150 |  |  |  | 149 | SEP | SEP
56799 | 740-SIV-VP042-102-LH099-65-0 | 2 | true | 0.85 | 740-SIV-VP042-102-LH099-65-0 | LV1-105638.VU320 | 386 |  |  | MC1 | LVL 5 | N/A | TR027_2 | 2024-07-02 | 2024-05-14 | 2024-05-14 |  | 2024-06-17 | 2024-06-20 | Büro | 2024-06-28 |  | 2024-06-25 | 2024-09-21 |  |  | 2024-09-30 | 1253 | 150 |  |  | 2024-09-30 | 149 | SEP | SEP
50462 | 740-SIV-VP043-102-LH099-65-0 | 1 | false | 0.8 | 740-SIV-VP043-102-LH099-65-0 | LV1-105638.VU320 | 386 |  |  | MC1 | LVL 5 | N/A | TR015_4 | 2024-05-07 | 2024-05-14 | 2024-05-14 |  | 2024-06-17 | 2024-06-21 | Satu Mare | 2024-06-28 |  | 2024-06-25 |  |  |  |  | 1253 | 150 |  |  |  | 149 | SEP | SEP
56800 | 740-SIV-VP043-102-LH099-65-0 | 2 | true | 0.8 | 740-SIV-VP043-102-LH099-65-0 | LV1-105638.VU320 | 386 |  |  | MC1 | LVL 5 | N/A | TR027_2 | 2024-07-02 | 2024-05-14 | 2024-05-14 |  | 2024-06-17 | 2024-06-21 | Büro | 2024-06-28 |  | 2024-06-25 | 2024-09-21 |  |  | 2024-10-02 | 1253 | 150 |  |  | 2024-10-03 | 149 | SEP | SEP
50463 | 740-SIV-VS682-102-LH032-40-0 | 1 | true | 0.25 | 740-SIV-VS682-102-LH032-40-0 | LV1-105638.VU320 | 385 |  |  | MC1 | LVL 6 | N/A | TR015_4 | 2024-05-07 | 2024-05-14 | 2024-05-14 |  | 2024-06-17 | 2024-06-21 | Büro | 2024-06-28 |  | 2024-06-25 | 2024-09-21 |  |  | 2024-09-25 | 1254 | 150 |  |  |  | 149 | SEP | SEP
50464 | 740-SIV-VS683-102-LH032-40-0 | 1 | true | 0.25 | 740-SIV-VS683-102-LH032-40-0 | LV1-105638.VU320 | 385 |  |  | MC1 | LVL 6 | N/A | TR015_4 | 2024-05-07 | 2024-05-14 | 2024-05-14 |  | 2024-06-17 | 2024-06-21 | Büro | 2024-06-28 |  | 2024-06-25 | 2024-09-21 |  |  | 2024-09-25 | 1254 | 150 |  |  |  | 149 | SEP | SEP
50465 | 740-SIV-VU320-101-LH032-100-0 | 1 | true | 26.87 | 740-SIV-VU320-101-LH032-100-0 | LV1-105638.VU320 | 385 | 7.Jun.2024 |  | MC1 | LVL 5 | N/A | TR015_4 | 2024-05-07 | 2024-05-14 | 2024-05-14 |  | 2024-05-30 | 2024-05-31 | Büro | 2024-06-14 |  | 2024-06-03 | 2024-06-21 |  |  | 2024-06-26 | 1253 | 150 |  | 2024-10-16 | 2024-07-18 | 149 | SEP | SEP
50466 | 740-SIV-VU320-102-LH032-100-0 | 1 | true | 11.27 | 740-SIV-VU320-102-LH032-100-0 | LV1-105638.VU320 | 385 | 7.Jun.2024 |  | MC1 | LVL 5 | N/A | TR015_4 | 2024-05-07 | 2024-05-14 | 2024-05-14 |  | 2024-05-30 | 2024-05-31 | Büro | 2024-06-14 |  | 2024-06-03 | 2024-06-26 |  |  | 2024-06-27 | 1253 | 150 |  | 2024-10-16 | 2024-07-03 | 149 | SEP | SEP
50467 | 740-SIV-VU320-103-LH032-100-0 | 1 | true | 11.68 | 740-SIV-VU320-103-LH032-100-0 | LV1-105638.VU320 | 385 | 7.Jun.2024 |  | MC1 | LVL 5 | N/A | TR015_4 | 2024-05-07 | 2024-05-14 | 2024-05-14 |  | 2024-05-30 | 2024-06-08 | Büro | 2024-06-14 |  | 2024-06-08 | 2024-06-28 |  |  | 2024-07-02 | 1253 | 150 |  | 2024-10-16 | 2024-07-03 | 149 | SEP | SEP
50468 | 740-SIV-VU320-104-LH032-100-0 | 1 | true | 12.67 | 740-SIV-VU320-104-LH032-100-0 | LV1-105638.VU320 | 385 | 7.Jun.2024 |  | MC1 | LVL 5 | N/A | TR015_4 | 2024-05-07 | 2024-05-14 | 2024-05-14 |  | 2024-05-30 | 2024-05-31 | Büro | 2024-06-14 |  | 2024-06-06 | 2024-06-24 |  |  | 2024-07-01 | 1253 | 150 |  | 2024-10-16 | 2024-07-03 | 149 | SEP | SEP
50469 | 740-SIV-VU320-106-LH032-80-0 | 1 | true | 9.03 | 740-SIV-VU320-106-LH032-80-0 | LV1-105638.VU320 | 385 | 7.Jun.2024 |  | MC1 | LVL 6 | N/A | TR015_4 | 2024-05-07 | 2024-05-14 | 2024-05-14 |  | 2024-05-30 | 2024-06-03 | Attila Henter | 2024-06-14 |  | 2024-06-04 | 2024-07-17 |  |  | 2024-07-23 | 1254 | 150 |  | 2024-10-16 | 2024-07-25 | 149 | SEP | SEP
50470 | 740-SIV-VU320-107-LH032-80-0 | 1 | true | 2.98 | 740-SIV-VU320-107-LH032-80-0 | LV1-105638.VU320 | 385 | 7.Jun.2024 |  | MC1 | LVL 6 | N/A | TR015_4 | 2024-05-07 | 2024-05-14 | 2024-05-14 |  | 2024-05-30 | 2024-05-31 | Attila Henter | 2024-06-14 |  | 2024-06-03 | 2024-07-17 |  |  | 2024-07-23 | 1254 | 150 |  | 2024-10-16 | 2024-07-25 | 149 | SEP | SEP
50471 | 740-SIV-VU320-109-LH032-65-0 | 1 | false | 21.57 | 740-SIV-VU320-109-LH032-65-0 | LV1-105638.VU320 | 385 | 7.Jun.2024 |  | MC1 | LVL 5 | W23 | TR015_4 | 2024-05-07 | 2024-05-14 | 2024-05-14 |  | 2024-05-30 | 2024-06-08 | Satu Mare | 2024-06-14 |  | 2024-06-08 | 2024-07-19 | 2024-07-23 |  |  | 1253 | 150 |  |  |  | 149 | SEP | SEP
64669 | 740-SIV-VU320-109-LH032-65-0 | 2 | true | 21.57 | 740-SIV-VU320-109-LH032-65-0 | LV1-105638.VU320 | 385 |  |  | MC1 | LVL 5 | W23 | TR037_1 | 2024-09-19 | 2024-05-14 | 2024-05-14 |  | 2024-05-30 | 2024-06-08 | Büro | 2024-06-14 |  | 2024-06-08 | 2024-07-19 | 2024-07-23 |  | 2024-10-15 | 1253 | 150 |  |  |  | 149 | SEP | SEP
50472 | 740-SIV-VU320-111-LH032-50-0 | 1 | false | 1.61 | 740-SIV-VU320-111-LH032-50-0 | LV1-105638.VU320 | 385 |  |  | MC1 | LVL 5 | N/A | TR015_4 | 2024-05-07 | 2024-05-14 | 2024-05-14 |  | 2024-06-13 | 2024-06-19 | Satu Mare | 2024-06-28 |  | 2024-06-21 |  |  |  |  | 1253 | 150 |  |  |  | 149 | SEP | SEP
56801 | 740-SIV-VU320-111-LH032-50-0 | 2 | true | 1.61 | 740-SIV-VU320-111-LH032-50-0 | LV1-105638.VU320 | 385 |  |  | MC1 | LVL 5 | N/A | TR027_2 | 2024-07-02 | 2024-05-14 | 2024-05-14 |  | 2024-06-13 | 2024-06-19 | Büro | 2024-06-28 |  | 2024-06-21 |  |  |  | 2024-10-01 | 1253 | 150 |  | 2024-10-16 | 2024-10-01 | 149 | SEP | SEP
50473 | 740-SIV-VU320-112-LH032-40-0 | 1 | true | 1.93 | 740-SIV-VU320-112-LH032-40-0 | LV1-105638.VU320 | 385 | 7.Jun.2024 |  | MC1 | LVL 6 | N/A | TR015_4 | 2024-05-07 | 2024-05-14 | 2024-05-14 |  | 2024-05-31 | 2024-06-03 | Satu Mare | 2024-06-14 |  | 2024-06-06 | 2024-07-18 |  |  | 2024-07-23 | 1254 | 150 |  | 2024-10-16 | 2024-07-25 | 149 | SEP | SEP
50474 | 740-SIV-VU320-113-LH032-40-0 | 1 | true | 2.2 | 740-SIV-VU320-113-LH032-40-0 | LV1-105638.VU320 | 385 | 7.Jun.2024 |  | MC1 | LVL 6 | N/A | TR015_4 | 2024-05-07 | 2024-05-14 | 2024-05-14 |  | 2024-05-31 | 2024-05-31 | Satu Mare | 2024-06-14 |  | 2024-06-06 | 2024-07-18 |  |  | 2024-07-23 | 1254 | 150 |  | 2024-10-16 | 2024-07-25 | 149 | SEP | SEP
50475 | 740-SIV-VU320-114-LH032-40-0 | 1 | true | 2.13 | 740-SIV-VU320-114-LH032-40-0 | LV1-105638.VU320 | 385 | 7.Jun.2024 |  | MC1 | LVL 6 | N/A | TR015_4 | 2024-05-07 | 2024-05-14 | 2024-05-14 |  | 2024-05-31 | 2024-06-07 | Satu Mare | 2024-06-14 |  | 2024-06-07 | 2024-07-18 |  |  | 2024-07-23 | 1254 | 150 |  | 2024-10-16 | 2024-07-25 | 149 | SEP | SEP
50476 | 740-SIV-VU320-115-LH032-50-0 | 1 | true | 14.38 | 740-SIV-VU320-115-LH032-50-0 | LV1-105638.VU320 | 385 | 7.Jun.2024 |  | MC1 | LVL 6 | N/A | TR015_4 | 2024-05-07 | 2024-05-14 | 2024-05-14 |  | 2024-05-31 | 2024-06-07 | Satu Mare | 2024-06-14 |  | 2024-06-07 | 2024-07-18 |  |  | 2024-07-23 | 1254 | 150 |  | 2024-10-16 | 2024-07-25 | 149 | SEP | SEP
50477 | 740-SIV-VU320-117-LH032-50-0 | 1 | false | 0.41 | 740-SIV-VU320-117-LH032-50-0 | LV1-105638.VU320 | 385 |  |  | MC1 | LVL 5 | N/A | TR015_4 | 2024-05-07 | 2024-05-14 | 2024-05-14 |  | 2024-06-13 | 2024-06-18 | Büro | 2024-06-28 |  | 2024-06-21 |  |  |  | 2024-09-07 | 1253 | 150 |  |  |  | 149 | SEP | SEP
56802 | 740-SIV-VU320-117-LH032-50-0 | 2 | true | 0.41 | 740-SIV-VU320-117-LH032-50-0 | LV1-105638.VU320 | 385 |  |  | MC1 | LVL 5 | N/A | TR027_2 | 2024-07-02 | 2024-05-14 | 2024-05-14 |  | 2024-06-13 | 2024-06-18 | Büro | 2024-06-28 |  | 2024-06-21 | 2024-09-06 |  |  | 2024-09-07 | 1253 | 150 |  |  | 2024-09-11 | 149 | SEP | SEP
50478 | 740-SIV-VU320-118-LH032-50-0 | 1 | false | 0.39 | 740-SIV-VU320-118-LH032-50-0 | LV1-105638.VU320 | 385 |  |  | MC1 | LVL 5 | N/A | TR015_4 | 2024-05-07 | 2024-05-14 | 2024-05-14 |  | 2024-06-17 | 2024-06-20 | Attila Henter | 2024-06-28 |  | 2024-06-25 | 2024-09-05 |  |  |  | 1253 | 150 |  |  |  | 149 | SEP | SEP
56803 | 740-SIV-VU320-118-LH032-50-0 | 2 | true | 0.39 | 740-SIV-VU320-118-LH032-50-0 | LV1-105638.VU320 | 385 |  |  | MC1 | LVL 5 | N/A | TR027_2 | 2024-07-02 | 2024-05-14 | 2024-05-14 |  | 2024-06-17 | 2024-06-20 | Büro | 2024-06-28 |  | 2024-06-25 | 2024-09-05 |  |  | 2024-09-07 | 1253 | 150 |  |  | 2024-09-11 | 149 | SEP | SEP
50479 | 740-SIV-VU320-119-LH032-50-0 | 1 | false | 0.45 | 740-SIV-VU320-119-LH032-50-0 | LV1-105638.VU320 | 385 |  |  | MC1 | LVL 5 | N/A | TR015_4 | 2024-05-07 | 2024-05-14 | 2024-05-14 |  | 2024-06-17 | 2024-06-19 | Satu Mare | 2024-06-28 |  | 2024-06-21 |  |  |  |  | 1253 | 150 |  |  |  | 149 | SEP | SEP
56804 | 740-SIV-VU320-119-LH032-50-0 | 2 | true | 0.45 | 740-SIV-VU320-119-LH032-50-0 | LV1-105638.VU320 | 385 |  |  | MC1 | LVL 5 | N/A | TR027_2 | 2024-07-02 | 2024-05-14 | 2024-05-14 |  | 2024-06-17 | 2024-06-19 | Büro | 2024-06-28 |  | 2024-06-21 | 2024-09-05 |  |  | 2024-09-10 | 1253 | 150 |  |  | 2024-09-11 | 149 | SEP | SEP
50480 | 740-SIV-VU320-120-LH032-50-0 | 1 | false | 1.69 | 740-SIV-VU320-120-LH032-50-0 | LV1-105638.VU320 | 385 |  |  | MC1 | LVL 5 | N/A | TR015_4 | 2024-05-07 | 2024-05-14 | 2024-05-14 |  | 2024-06-17 | 2024-06-19 | Satu Mare | 2024-06-28 |  | 2024-06-21 |  |  |  |  | 1253 | 150 |  |  |  | 149 | SEP | SEP
56805 | 740-SIV-VU320-120-LH032-50-0 | 2 | true | 1.69 | 740-SIV-VU320-120-LH032-50-0 | LV1-105638.VU320 | 385 |  |  | MC1 | LVL 5 | N/A | TR027_2 | 2024-07-02 | 2024-05-14 | 2024-05-14 |  | 2024-06-17 | 2024-06-19 | Büro | 2024-06-28 |  | 2024-06-21 | 2024-09-03 |  |  | 2024-09-05 | 1253 | 150 |  |  | 2024-09-09 | 149 | SEP | SEP
50481 | 740-SIV-VU320-121-LH032-40-0 | 1 | true | 0.58 | 740-SIV-VU320-121-LH032-40-0 | LV1-105638.VU320 | 385 |  |  | MC1 | LVL 6 | N/A | TR015_4 | 2024-05-07 | 2024-05-14 | 2024-05-14 |  | 2024-06-17 | 2024-06-21 | Büro | 2024-06-28 |  | 2024-06-25 | 2024-09-21 |  |  | 2024-09-25 | 1254 | 150 |  | 2024-10-16 |  | 149 | SEP | SEP
50482 | 740-SIV-VU320-122-LH032-50-0 | 1 | false | 1.76 | 740-SIV-VU320-122-LH032-50-0 | LV1-105638.VU320 | 385 |  |  | MC1 | LVL 5 | N/A | TR015_4 | 2024-05-07 | 2024-05-14 | 2024-05-14 |  | 2024-06-17 | 2024-06-19 | Büro | 2024-06-28 |  | 2024-06-21 | 2024-09-21 |  |  | 2024-10-01 | 1253 | 150 |  |  |  | 149 | SEP | SEP
56806 | 740-SIV-VU320-122-LH032-50-0 | 2 | true | 1.76 | 740-SIV-VU320-122-LH032-50-0 | LV1-105638.VU320 | 385 |  |  | MC1 | LVL 5 | N/A | TR027_2 | 2024-07-02 | 2024-05-14 | 2024-05-14 |  | 2024-06-17 | 2024-06-19 | Büro | 2024-06-28 |  | 2024-06-21 | 2024-09-21 |  |  | 2024-10-01 | 1253 | 150 |  | 2024-10-16 | 2024-10-01 | 149 | SEP | SEP
50483 | 740-SIV-VU320-123-LH032-65-0 | 1 | false | 0.81 | 740-SIV-VU320-123-LH032-65-0 | LV1-105638.VU320 | 385 |  |  | MC1 | LVL 5 | N/A | TR015_4 | 2024-05-07 | 2024-05-14 | 2024-05-14 |  | 2024-06-18 | 2024-06-19 | Satu Mare | 2024-06-28 |  | 2024-06-20 |  |  |  |  | 1253 | 150 |  |  |  | 149 | SEP | SEP
56807 | 740-SIV-VU320-123-LH032-65-0 | 2 | true | 0.81 | 740-SIV-VU320-123-LH032-65-0 | LV1-105638.VU320 | 385 |  |  | MC1 | LVL 5 | N/A | TR027_2 | 2024-07-02 | 2024-05-14 | 2024-05-14 |  | 2024-06-18 | 2024-06-19 | Büro | 2024-06-28 |  | 2024-06-20 | 2024-09-21 |  |  | 2024-10-02 | 1253 | 150 |  | 2024-10-16 | 2024-10-02 | 149 | SEP | SEP
50484 | 740-SIV-VU320-124-LH032-65-0 | 1 | false | 0.85 | 740-SIV-VU320-124-LH032-65-0 | LV1-105638.VU320 | 385 |  |  | MC1 | LVL 5 | N/A | TR015_4 | 2024-05-07 | 2024-05-14 | 2024-05-14 |  | 2024-06-18 | 2024-06-18 | Satu Mare | 2024-06-28 |  | 2024-06-20 |  |  |  |  | 1253 | 150 |  |  |  | 149 | SEP | SEP
56808 | 740-SIV-VU320-124-LH032-65-0 | 2 | true | 0.85 | 740-SIV-VU320-124-LH032-65-0 | LV1-105638.VU320 | 385 |  |  | MC1 | LVL 5 | N/A | TR027_2 | 2024-07-02 | 2024-05-14 | 2024-05-14 |  | 2024-06-18 | 2024-06-18 | Büro | 2024-06-28 |  | 2024-06-20 | 2024-09-21 |  |  | 2024-09-30 | 1253 | 150 |  | 2024-10-16 | 2024-09-30 | 149 | SEP | SEP
50485 | 740-SIV-VU320-125-LH032-65-0 | 1 | false | 0.29 | 740-SIV-VU320-125-LH032-65-0 | LV1-105638.VU320 | 385 |  |  | MC1 | LVL 5 | N/A | TR015_4 | 2024-05-07 | 2024-05-14 | 2024-05-14 |  | 2024-06-18 | 2024-06-19 | Satu Mare | 2024-06-28 |  | 2024-06-20 |  |  |  |  | 1253 | 150 |  |  |  | 149 | SEP | SEP
56809 | 740-SIV-VU320-125-LH032-65-0 | 2 | true | 0.29 | 740-SIV-VU320-125-LH032-65-0 | LV1-105638.VU320 | 385 |  |  | MC1 | LVL 5 | N/A | TR027_2 | 2024-07-02 | 2024-05-14 | 2024-05-14 |  | 2024-06-18 | 2024-06-19 | Büro | 2024-06-28 |  | 2024-06-20 |  |  |  | 2024-10-01 | 1253 | 150 |  | 2024-10-16 | 2024-10-01 | 149 | SEP | SEP
50486 | 740-SIV-VU320-126-LH032-65-0 | 1 | false | 0.33 | 740-SIV-VU320-126-LH032-65-0 | LV1-105638.VU320 | 385 |  |  | MC1 | LVL 5 | N/A | TR015_4 | 2024-05-07 | 2024-05-14 | 2024-05-14 |  | 2024-06-18 | 2024-06-18 | Satu Mare | 2024-06-28 |  | 2024-06-20 |  |  |  |  | 1253 | 150 |  |  |  | 149 | SEP | SEP
56810 | 740-SIV-VU320-126-LH032-65-0 | 2 | true | 0.33 | 740-SIV-VU320-126-LH032-65-0 | LV1-105638.VU320 | 385 |  |  | MC1 | LVL 5 | N/A | TR027_2 | 2024-07-02 | 2024-05-14 | 2024-05-14 |  | 2024-06-18 | 2024-06-18 | Büro | 2024-06-28 |  | 2024-06-20 |  |  |  | 2024-10-01 | 1253 | 150 |  | 2024-10-16 | 2024-10-01 | 149 | SEP | SEP
50487 | 740-SIV-VU320-127-LH032-100-0 | 1 | true | 15.46 | 740-SIV-VU320-127-LH032-100-0 | LV1-105638.VU320 | 385 | 7.Jun.2024 |  | MC1 | LVL 6 | W23 | TR015_4 | 2024-05-07 | 2024-05-14 | 2024-05-14 |  | 2024-05-30 | 2024-05-31 |  | 2024-06-14 |  | 2024-06-06 | 2024-06-21 |  | 2024-06-26 | 2024-08-27 | 1254 | 150 |  | 2024-10-16 | 2024-08-28 | 149 | SEP | SEP
50488 | 740-SIV-VU330-102-LH032-40-0 | 1 | true | 0.74 | 740-SIV-VU330-102-LH032-40-0 | LV1-105638.VU320 | 385 |  |  | MC1 | LVL 6 | N/A | TR015_4 | 2024-05-07 | 2024-05-14 | 2024-05-14 |  | 2024-06-17 | 2024-06-21 | Büro | 2024-06-28 |  | 2024-06-25 | 2024-09-05 |  |  | 2024-09-06 | 1254 | 150 |  | 2024-09-10 | 2024-09-09 | 149 | SEP | SEP
50489 | 740-SIV-VU331-102-LH032-40-0 | 1 | true | 0.74 | 740-SIV-VU331-102-LH032-40-0 | LV1-105638.VU320 | 385 |  |  | MC1 | LVL 6 | N/A | TR015_4 | 2024-05-07 | 2024-05-14 | 2024-05-14 |  | 2024-06-17 | 2024-06-21 | Büro | 2024-06-28 |  | 2024-06-25 | 2024-09-05 |  |  | 2024-09-06 | 1254 | 150 |  | 2024-09-12 | 2024-09-09 | 149 | SEP | SEP
50490 | 740-SIV-VU340-102-LH032-40-0 | 1 | true | 0.74 | 740-SIV-VU340-102-LH032-40-0 | LV1-105638.VU320 | 385 |  |  | MC1 | LVL 6 | N/A | TR015_4 | 2024-05-07 | 2024-05-14 | 2024-05-14 |  | 2024-06-18 | 2024-06-21 | Büro | 2024-06-28 |  | 2024-06-25 | 2024-09-05 |  |  | 2024-09-06 | 1254 | 150 |  |  | 2024-09-09 | 149 | SEP | SEP
50491 | 740-WAKont-VU311-101-LH032-25-0 | 1 | true | 18.27 | 740-WAKont-VU311-101-LH032-25-0 | LV1-105638.VU311 | 385 | 14.Jun.2024 |  | MC1 | LVL 5 | N/A | TR015_4 | 2024-05-07 | 2024-05-14 | 2024-05-14 |  | 2024-05-31 | 2024-06-08 | Büro | 2024-06-14 |  | 2024-06-08 | 2024-07-09 |  |  | 2024-08-06 | 932 | 150 |  |  |  | 149 | SEP | SEP
50492 | 740-DKR-VS001-102-LH011-20-0 | 1 | false | 1.6 | 740-DKR-VS001-102-LH011-20-0 | LV1-105633.VS001 | 369 |  |  | MC1 | LVL 5 | W23 | TR016_2 | 2024-05-07 | 2024-05-15 | 2024-05-15 |  |  |  | Satu Mare | [7 empty] | 1039 | 150 |  |  |  | 149 | SEP | SEP
50958 | 740-DKR-VS001-102-LH011-20-0 | 2 | true | 1.6 | 740-DKR-VS001-102-LH011-20-0 | LV1-105633.VS001 | 369 |  |  | MC1 | LVL 5 | W23 | TR018_1 | 2024-05-15 | 2024-05-16 | 2024-05-16 |  | 2024-06-28 | 2024-07-02 | Büro | 2024-07-12 |  | 2024-07-03 |  |  |  | 2024-10-03 | 1039 | 150 |  |  |  | 149 | SEP | SEP | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22
50493 | 740-DKR-VS020-101-LH011-15-0 | 1 | true | 2.44 | 740-DKR-VS020-101-LH011-15-0 | LV1-105633.VS020 | 369 |  |  | MC1 | LVL 5 | W23 | TR016_2 | 2024-05-07 | 2024-05-15 | 2024-05-15 |  | 2024-06-18 | 2024-06-19 | Büro | 2024-06-28 |  | 2024-06-20 |  |  |  | 2024-10-07 | 1039 | 150 |  |  |  | 149 | SEP | SEP | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22
50494 | 740-DKR-VU081-117-LH088-20-0 | 1 | false | 0.07 | 740-DKR-VU081-117-LH088-20-0 | LV0-105638.VU081 | 391 |  |  | MC1 | LVL 5 | W23 | TR016_2 | 2024-05-07 | 2024-05-15 | 2024-05-15 |  |  |  | Satu Mare | [7 empty] | 1039 | 150 |  |  |  | 149 | SEP | SEP
52541 | 740-DKR-VU081-117-LH088-20-0 | 2 | true | 0.07 | 740-DKR-VU081-117-LH088-20-0 | LV0-105638.VU081 | 391 |  |  | MC1 | LVL 5 | W23 | TR024_1 | 2024-06-10 | 2024-05-15 | 2024-05-15 |  | 2024-07-18 | 2024-07-30 |  | 2024-08-02 |  | 2024-07-30 |  |  |  | 2024-11-15 | 1039 | 150 |  |  |  | 149 | SEP | SEP | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22
50495 | 740-DKR-VU117-108-LH099-15-0 | 1 | false | 3.05 | 740-DKR-VU117-108-LH099-15-0 | LV0-105628.VP001 | 386 |  |  | MC1 | LVL 5 | Tt-12 | TR016_2 | 2024-05-07 | 2024-05-15 | 2024-05-15 |  |  |  | Satu Mare | [7 empty] | 1039 | 150 |  |  |  | 149 | SEP | SEP
52544 | 740-DKR-VU117-108-LH099-15-0 | 2 | true | 3.05 | 740-DKR-VU117-108-LH099-15-0 | LV0-105628.VP001 | 386 |  |  | MC1 | LVL 5 | Tt-12 | TR024_1 | 2024-06-10 | 2024-05-15 | 2024-05-15 |  | 2024-06-18 | 2024-06-18 | Büro | 2024-06-28 |  | 2024-06-21 | 2024-09-30 |  |  | 2024-10-02 | 1039 | 150 |  |  | 2024-10-02 | 149 | SEP | SEP |  |  | 2024-11-30 | 2024-11-30
50496 | 740-DKR-VU117-111-LH011-20-0 | 1 | false | 0.39 | 740-DKR-VU117-111-LH011-20-0 | LV1-105633.VS001 | 369 |  |  | MC1 | LVL 5 | W23 | TR016_2 | 2024-05-07 | [5 empty] | Satu Mare | [7 empty] | 1039 | 150 |  |  |  | 149 | SEP | SEP
50959 | 740-DKR-VU117-111-LH011-20-0 | 2 | true | 0.39 | 740-DKR-VU117-111-LH011-20-0 | LV1-105633.VS001 | 369 |  |  | MC1 | LVL 5 | W23 | TR018_1 | 2024-05-15 | 2024-05-16 | 2024-05-16 |  | 2024-06-28 | 2024-07-02 | Büro | 2024-07-12 |  | 2024-07-03 |  |  |  | 2024-10-03 | 1039 | 150 |  |  | 2024-11-06 | 149 | SEP | SEP | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22
50497 | 740-DKR-VU117-112-LH011-15-0 | 1 | true | 0.26 | 740-DKR-VU117-112-LH011-15-0 | LV1-105633.VS020 | 369 |  |  | MC1 | LVL 5 | W23 | TR016_2 | 2024-05-07 | 2024-05-15 | 2024-05-15 |  | 2024-06-18 | 2024-06-19 | Büro | 2024-06-28 |  | 2024-06-20 |  |  |  | 2024-10-07 | 1039 | 150 |  |  |  | 149 | SEP | SEP | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22
50498 | 740-DKR-VU117-114-LH099-15-0 | 1 | false | 2.88 | 740-DKR-VU117-114-LH099-15-0 | LV0-105628.VP003 | 386 |  |  | MC1 | LVL 5 | Tt-12 | TR016_2 | 2024-05-07 | 2024-05-15 | 2024-05-15 |  |  |  | Satu Mare | [7 empty] | 1039 | 150 |  |  |  | 149 | SEP | SEP
52545 | 740-DKR-VU117-114-LH099-15-0 | 2 | true | 2.88 | 740-DKR-VU117-114-LH099-15-0 | LV0-105628.VP003 | 386 |  |  | MC1 | LVL 5 | Tt-12 | TR024_1 | 2024-06-10 | 2024-05-15 | 2024-05-15 |  | 2024-06-18 | 2024-06-19 | Büro | 2024-06-28 |  | 2024-06-20 | 2024-09-27 |  |  | 2024-10-02 | 1039 | 150 |  |  | 2024-11-07 | 149 | SEP | SEP |  |  | 2024-11-30 | 2024-11-30
50499 | 740-DKR-VU117-117-LH099-15-0 | 1 | false | 2.74 | 740-DKR-VU117-117-LH099-15-0 | LV0-105628.VP004 | 386 |  |  | MC1 | LVL 5 | Tt-12 | TR016_2 | 2024-05-07 | 2024-05-15 | 2024-05-15 |  |  |  | Satu Mare | [7 empty] | 1039 | 150 |  |  |  | 149 | SEP | SEP
52546 | 740-DKR-VU117-117-LH099-15-0 | 2 | true | 2.74 | 740-DKR-VU117-117-LH099-15-0 | LV0-105628.VP004 | 386 |  |  | MC1 | LVL 5 | Tt-12 | TR024_1 | 2024-06-10 | 2024-05-15 | 2024-05-15 |  | 2024-06-18 | 2024-06-19 | Büro | 2024-06-28 |  | 2024-06-26 | 2024-09-27 |  |  | 2024-10-02 | 1039 | 150 |  |  | 2024-10-02 | 149 | SEP | SEP |  |  | 2024-11-30 | 2024-11-30
50500 | 740-DKR-VU117-118-LH099-15-0 | 1 | false | 3.18 | 740-DKR-VU117-118-LH099-15-0 | LV0-105628.VP002 | 386 |  |  | MC1 | LVL 5 | Tt-12 | TR016_2 | 2024-05-07 | 2024-05-15 | 2024-05-15 |  |  |  | Satu Mare | [7 empty] | 1039 | 150 |  |  |  | 149 | SEP | SEP
52547 | 740-DKR-VU117-118-LH099-15-0 | 2 | true | 3.18 | 740-DKR-VU117-118-LH099-15-0 | LV0-105628.VP002 | 386 |  |  | MC1 | LVL 5 | Tt-12 | TR024_1 | 2024-06-10 | 2024-05-15 | 2024-05-15 |  | 2024-06-18 | 2024-06-19 | Büro | 2024-06-28 |  | 2024-06-20 | 2024-09-27 |  |  | 2024-10-02 | 1039 | 150 |  |  | 2024-10-02 | 149 | SEP | SEP |  |  | 2024-11-30 | 2024-11-30
50501 | 740-DKR-VU117-143-LH099-15-0 | 1 | false | 1.22 | 740-DKR-VU117-143-LH099-15-0 | LV1-105628.VP142 | 386 |  |  | MC1 | LVL 5 | Tt-12 | TR016_2 | 2024-05-07 | 2024-05-15 | 2024-05-15 |  |  |  | Satu Mare | [7 empty] | 1039 | 150 |  |  |  | 149 | SEP | SEP
52555 | 740-DKR-VU117-143-LH099-15-0 | 2 | true | 1.22 | 740-DKR-VU117-143-LH099-15-0 | LV1-105628.VP142 | 386 |  |  | MC1 | LVL 5 | Tt-12 | TR024_1 | 2024-06-10 | 2024-05-15 | 2024-05-15 |  | 2024-06-18 | 2024-06-19 | Büro | 2024-06-28 |  | 2024-06-20 | 2024-09-30 |  |  | 2024-10-01 | 1039 | 150 |  |  | 2024-10-03 | 149 | SEP | SEP |  |  | 2024-11-30 | 2024-11-30
50502 | 740-DKR-VU117-156-LH099-15-0 | 1 | false | 1.23 | 740-DKR-VU117-156-LH099-15-0 | LV1-105628.VP132 | 386 |  |  | MC1 | LVL 5 | Tt-12 | TR016_2 | 2024-05-07 | 2024-05-15 | 2024-05-15 |  |  |  | Satu Mare | [7 empty] | 1039 | 150 |  |  |  | 149 | SEP | SEP
52558 | 740-DKR-VU117-156-LH099-15-0 | 2 | true | 1.23 | 740-DKR-VU117-156-LH099-15-0 | LV1-105628.VP132 | 386 |  |  | MC1 | LVL 5 | Tt-12 | TR024_1 | 2024-06-10 | 2024-05-15 | 2024-05-15 |  | 2024-06-17 | 2024-06-19 | Büro | 2024-06-28 |  | 2024-06-27 |  |  |  | 2024-10-03 | 1039 | 150 |  |  | 2024-11-06 | 149 | SEP | SEP |  |  | 2024-11-30 | 2024-11-30
50503 | 740-DKR-VU117-158-LH011-15-0 | 1 | false | 0.36 | 740-DKR-VU117-158-LH011-15-0 | LV0-105638.VU081 | 369 |  |  | MC1 | LVL 5 | W23 | TR016_2 | 2024-05-07 | 2024-05-15 | 2024-05-15 |  |  |  | Satu Mare | [7 empty] | 1039 | 150 |  |  |  | 149 | SEP | SEP
52182 | 740-DKR-VU117-158-LH011-15-0 | 2 | true | 0.36 | 740-DKR-VU117-158-LH011-15-0 | LV0-105638.VU081 | 369 |  |  | MC1 | LVL 5 | W23 | TR020_1 | 2024-05-29 | 2024-05-15 | 2024-05-15 |  | 2024-06-27 | 2024-06-28 | Büro | 2024-07-12 |  | 2024-07-02 |  |  |  | 2024-10-04 | 1039 | 150 |  |  | 2024-11-06 | 149 | SEP | SEP | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22
50504 | 740-DR2-VP001-101-LH088-25-0 | 1 | false | 2.19 | 740-DR2-VP001-101-LH088-25-0 | LV0-105628.VP001 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR016_2 | 2024-05-07 | 2024-05-15 | 2024-05-15 |  |  |  | Satu Mare | [7 empty] | 1005 | 150 |  |  |  | 149 | SEP | SEP
52561 | 740-DR2-VP001-101-LH088-25-0 | 2 | true | 2.19 | 740-DR2-VP001-101-LH088-25-0 | LV0-105628.VP001 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR024_1 | 2024-06-10 | 2024-05-15 | 2024-05-15 |  | 2024-07-02 | 2024-07-10 | Büro | 2024-07-12 |  | 2024-07-10 | 2024-08-28 | 2024-08-30 |  | 2024-09-06 | 1005 | 150 |  | 2024-11-13 |  | 149 | SEP | SEP |  |  | 2024-11-30 | 2024-11-30
50505 | 740-DR2-VP001-103-LH089-15-0 | 1 | true | 0.23 | 740-DR2-VP001-103-LH089-15-0 | LV0-105628.VP001 | 394 |  |  | MC1 | LVL 5 | Tt-12 | TR016_2 | 2024-05-07 | 2024-05-15 | 2024-05-15 |  | 2024-06-26 | 2024-06-28 | Büro | 2024-07-12 |  | 2024-07-05 | 2024-09-06 |  |  | 2024-10-24 | 1005 | 150 |  | 2024-11-13 | 2024-10-28 | 149 | SEP | SEP |  |  | 2024-11-30 | 2024-11-30
50506 | 740-DR2-VP002-101-LH088-25-0 | 1 | false | 2.29 | 740-DR2-VP002-101-LH088-25-0 | LV0-105628.VP002 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR016_2 | 2024-05-07 | 2024-05-15 | 2024-05-15 |  |  |  | Satu Mare | [7 empty] | 1005 | 150 |  |  |  | 149 | SEP | SEP
52562 | 740-DR2-VP002-101-LH088-25-0 | 2 | true | 2.29 | 740-DR2-VP002-101-LH088-25-0 | LV0-105628.VP002 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR024_1 | 2024-06-10 | 2024-05-15 | 2024-05-15 |  | 2024-07-03 | 2024-07-09 | Büro | 2024-07-12 |  | 2024-07-09 | 2024-08-28 |  |  | 2024-09-06 | 1005 | 150 |  | 2024-11-13 |  | 149 | SEP | SEP |  |  | 2024-11-30 | 2024-11-30
50507 | 740-DR2-VP002-102-LH088-15-0 | 1 | true | 0.58 | 740-DR2-VP002-102-LH088-15-0 | LV0-105628.VP002 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR016_2 | 2024-05-07 | 2024-05-15 | 2024-05-15 |  | 2024-07-01 | 2024-07-02 | Büro | 2024-07-12 |  | 2024-07-05 | 2024-09-06 |  |  | 2024-09-16 | 1005 | 150 |  | 2024-11-13 | 2024-09-23 | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
50508 | 740-DR2-VP002-103-LH089-15-0 | 1 | true | 0.23 | 740-DR2-VP002-103-LH089-15-0 | LV0-105628.VP002 | 394 |  |  | MC1 | LVL 5 | Tt-12 | TR016_2 | 2024-05-07 | 2024-05-15 | 2024-05-15 |  | 2024-06-28 | 2024-07-01 | Büro | 2024-07-12 |  | 2024-07-05 | 2024-09-06 |  |  | 2024-10-24 | 1005 | 150 |  |  | 2024-10-28 | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
50509 | 740-DR2-VP003-101-LH088-20-0 | 1 | false | 1.43 | 740-DR2-VP003-101-LH088-20-0 | LV0-105628.VP003 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR016_2 | 2024-05-07 | 2024-05-15 | 2024-05-15 |  |  |  | Satu Mare | [7 empty] | 1005 | 150 |  |  |  | 149 | SEP | SEP
52563 | 740-DR2-VP003-101-LH088-20-0 | 2 | true | 1.43 | 740-DR2-VP003-101-LH088-20-0 | LV0-105628.VP003 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR024_1 | 2024-06-10 | 2024-05-15 | 2024-05-15 |  | 2024-07-31 | 2024-08-01 | Büro | 2024-08-23 | [5 empty] | 2024-09-06 | 1005 | 150 |  |  | 2024-11-08 | 149 | SEP | SEP |  |  | 2024-11-30 | 2024-11-30
50510 | 740-DR2-VP003-102-LH088-15-0 | 1 | true | 0.72 | 740-DR2-VP003-102-LH088-15-0 | LV0-105628.VP003 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR016_2 | 2024-05-07 | 2024-05-15 | 2024-05-15 |  | 2024-07-01 | 2024-07-01 | Büro | 2024-07-12 |  | 2024-07-05 | 2024-09-04 |  |  | 2024-09-06 | 1005 | 150 |  |  | 2024-09-23 | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
50511 | 740-DR2-VP003-103-LH089-15-0 | 1 | true | 0.17 | 740-DR2-VP003-103-LH089-15-0 | LV0-105628.VP003 | 394 |  |  | MC1 | LVL 5 | Tt-12 | TR016_2 | 2024-05-07 | 2024-05-15 | 2024-05-15 |  | 2024-06-27 | 2024-06-28 | Büro | 2024-07-12 |  | 2024-07-05 |  |  |  | 2024-10-24 | 1005 | 150 |  |  |  | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
50512 | 740-DR2-VP004-101-LH088-20-0 | 1 | false | 1.53 | 740-DR2-VP004-101-LH088-20-0 | LV0-105628.VP004 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR016_2 | 2024-05-07 | 2024-05-15 | 2024-05-15 |  |  |  | Satu Mare | [7 empty] | 1005 | 150 |  |  |  | 149 | SEP | SEP
52564 | 740-DR2-VP004-101-LH088-20-0 | 2 | true | 1.53 | 740-DR2-VP004-101-LH088-20-0 | LV0-105628.VP004 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR024_1 | 2024-06-10 | 2024-05-15 | 2024-05-15 |  | 2024-07-30 | 2024-07-31 | Büro | 2024-08-02 |  | 2024-08-01 | 2024-08-28 |  | 2024-08-30 | 2024-09-06 | 1005 | 150 |  |  | 2024-11-11 | 149 | SEP | SEP |  |  | 2024-11-30 | 2024-11-30
50513 | 740-DR2-VP004-102-LH088-15-0 | 1 | true | 0.74 | 740-DR2-VP004-102-LH088-15-0 | LV0-105628.VP004 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR016_2 | 2024-05-07 | 2024-05-15 | 2024-05-15 |  | 2024-07-01 | 2024-07-01 | Büro | 2024-07-12 |  | 2024-07-05 | 2024-09-04 |  |  | 2024-09-06 | 1005 | 150 |  |  | 2024-09-23 | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
50514 | 740-DR2-VP004-103-LH089-15-0 | 1 | true | 0.17 | 740-DR2-VP004-103-LH089-15-0 | LV0-105628.VP004 | 394 |  |  | MC1 | LVL 5 | Tt-12 | TR016_2 | 2024-05-07 | 2024-05-15 | 2024-05-15 |  | 2024-06-27 | 2024-06-28 | Büro | 2024-07-12 |  | 2024-07-05 |  |  |  | 2024-10-24 | 1005 | 150 |  |  | 2024-10-28 | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
50515 | 740-DR2-VP132-101-LH088-25-0 | 1 | false | 4.51 | 740-DR2-VP132-101-LH088-25-0 | LV1-105628.VP132 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR016_2 | 2024-05-07 | 2024-05-15 | 2024-05-15 |  |  |  | Satu Mare | [7 empty] | 1005 | 150 |  |  |  | 149 | SEP | SEP
52565 | 740-DR2-VP132-101-LH088-25-0 | 2 | true | 4.51 | 740-DR2-VP132-101-LH088-25-0 | LV1-105628.VP132 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR024_1 | 2024-06-10 | 2024-05-15 | 2024-05-15 |  | 2024-07-30 | 2024-07-30 | Büro | 2024-08-02 |  | 2024-07-30 | 2024-10-22 |  |  | 2024-10-30 | 1005 | 150 |  |  | 2024-10-31 | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
50516 | 740-DR2-VP132-103-LH088-15-0 | 1 | true | 1.37 | 740-DR2-VP132-103-LH088-15-0 | LV1-105628.VP132 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR016_2 | 2024-05-07 | 2024-05-15 | 2024-05-15 |  | 2024-07-02 | 2024-07-10 | Büro | 2024-07-12 |  | 2024-07-10 | 2024-10-22 |  |  | 2024-10-30 | 1005 | 150 |  |  | 2024-10-31 | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
50517 | 740-DR2-VP132-104-LH089-8-0 | 1 | true | 0.28 | 740-DR2-VP132-104-LH089-8-0 | LV1-105628.VP132 | 394 |  |  | MC1 | LVL 5 | Tt-12 | TR016_2 | 2024-05-07 | 2024-05-15 | 2024-05-15 |  | 2024-06-27 | 2024-06-28 | Büro | 2024-07-12 |  | 2024-07-05 | 2024-10-22 |  |  | 2024-10-30 | 1005 | 150 |  |  | 2024-10-31 | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
50518 | 740-DR2-VP132-105-LH088-8-0 | 1 | true | 0.17 | 740-DR2-VP132-105-LH088-8-0 | LV1-105628.VP132 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR016_2 | 2024-05-07 | 2024-05-15 | 2024-05-15 |  | 2024-06-28 | 2024-07-01 | Büro | 2024-07-12 |  | 2024-07-05 | 2024-10-22 |  |  | 2024-10-30 | 1005 | 150 |  |  | 2024-10-31 | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
50519 | 740-DR2-VP142-101-LH088-25-0 | 1 | false | 4.52 | 740-DR2-VP142-101-LH088-25-0 | LV1-105628.VP142 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR016_2 | 2024-05-07 | 2024-05-15 | 2024-05-15 |  |  |  | Satu Mare | [7 empty] | 1005 | 150 |  |  |  | 149 | SEP | SEP
52566 | 740-DR2-VP142-101-LH088-25-0 | 2 | true | 4.52 | 740-DR2-VP142-101-LH088-25-0 | LV1-105628.VP142 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR024_1 | 2024-06-10 | 2024-05-15 | 2024-05-15 |  | 2024-07-18 | 2024-07-30 | Büro | 2024-08-02 |  | 2024-07-30 | 2024-10-22 |  |  | 2024-10-30 | 1005 | 150 |  |  | 2024-10-31 | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
50520 | 740-DR2-VP142-103-LH088-15-0 | 1 | true | 1.38 | 740-DR2-VP142-103-LH088-15-0 | LV1-105628.VP142 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR016_2 | 2024-05-07 | 2024-05-15 | 2024-05-15 |  | 2024-07-01 | 2024-07-02 | Büro | 2024-07-12 |  | 2024-07-05 | 2024-10-22 |  |  | 2024-10-30 | 1005 | 150 |  |  | 2024-10-31 | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
50521 | 740-DR2-VP142-104-LH089-8-0 | 1 | true | 0.25 | 740-DR2-VP142-104-LH089-8-0 | LV1-105628.VP142 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR016_2 | 2024-05-07 | 2024-05-15 | 2024-05-15 |  | 2024-06-27 | 2024-06-28 | Büro | 2024-07-12 |  | 2024-07-05 | 2024-10-22 |  |  | 2024-10-30 | 1005 | 150 |  |  | 2024-10-31 | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
50522 | 740-DR2-VP142-105-LH088-8-0 | 1 | true | 0.17 | 740-DR2-VP142-105-LH088-8-0 | LV1-105628.VP142 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR016_2 | 2024-05-07 | 2024-05-15 | 2024-05-15 |  | 2024-06-28 | 2024-07-01 | Büro | 2024-07-12 |  | 2024-07-05 | 2024-10-22 |  |  | 2024-10-30 | 1005 | 150 |  |  | 2024-10-31 | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
50523 | 740-DR2-VS001-101-LH089-15-0 | 1 | true | 0.58 | 740-DR2-VS001-101-LH089-15-0 | LV1-105633.VS001 | 394 |  |  | MC1 | LVL 5 | Tt-12 | TR016_2 | 2024-05-07 | 2024-05-15 | 2024-05-15 |  | 2024-06-27 | 2024-06-28 | Büro | 2024-07-12 |  | 2024-07-05 | 2024-10-24 |  |  | 2024-10-30 | 1005 | 150 |  |  | 2024-10-31 | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
50524 | 740-DR2-VS001-102-LH088-15-0 | 1 | true | 0.91 | 740-DR2-VS001-102-LH088-15-0 | LV1-105633.VS001 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR016_2 | 2024-05-07 | 2024-05-15 | 2024-05-15 |  | 2024-07-01 | 2024-07-02 | Büro | 2024-07-12 |  | 2024-07-05 | 2024-10-24 |  |  | 2024-10-30 | 1005 | 150 |  |  | 2024-10-31 | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
50525 | 740-DR2-VS001-103-LH089-15-0 | 1 | true | 0.41 | 740-DR2-VS001-103-LH089-15-0 | LV1-105633.VS001 | 394 |  |  | MC1 | LVL 5 | Tt-12 | TR016_2 | 2024-05-07 | 2024-05-15 | 2024-05-15 |  | 2024-06-27 | 2024-06-28 | Büro | 2024-07-12 |  | 2024-07-05 | 2024-10-24 |  |  | 2024-10-30 | 1005 | 150 |  |  | 2024-10-31 | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
50526 | 740-DR2-VS001-104-LH088-15-0 | 1 | false | 1.43 | 740-DR2-VS001-104-LH088-15-0 | LV0-105638.VU081 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR016_2 | 2024-05-07 | 2024-05-15 | 2024-05-15 |  |  |  | Satu Mare | [7 empty] | 1005 | 150 |  |  |  | 149 | SEP | SEP
52567 | 740-DR2-VS001-104-LH088-15-0 | 2 | true | 1.43 | 740-DR2-VS001-104-LH088-15-0 | LV0-105638.VU081 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR024_1 | 2024-06-10 | 2024-05-15 | 2024-05-15 |  | 2024-06-28 | 2024-07-01 | Büro | 2024-07-12 |  | 2024-07-05 | 2024-10-24 |  |  | 2024-10-30 | 1005 | 150 |  |  | 2024-10-31 | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
50527 | 740-UN-VS001-101-LH032-15-0 | 1 | true | 2.81 | 740-UN-VS001-101-LH032-15-0 | LV1-105633.VS001 | 385 |  |  | MC1 | LVL 5 | N/A | TR016_2 | 2024-05-07 | 2024-05-15 | 2024-05-15 |  | 2024-06-17 | 2024-06-19 | Büro | 2024-06-28 |  | 2024-06-26 |  |  |  | 2024-10-08 | 1255 | 150 |  |  |  | 149 | SEP | SEP
50528 | 740-UN-VU330-109-LH032-15-0 | 1 | true | 22.23 | 740-UN-VU330-109-LH032-15-0 | LV1-105638.VU330 | 385 | 14.Jun.2024 |  | MC1 | LVL 5 | N/A | TR016_2 | 2024-05-07 | 2024-05-15 | 2024-05-15 |  | 2024-05-31 | 2024-06-07 |  | 2024-06-14 |  | 2024-06-07 | 2024-07-04 |  |  | 2024-07-19 | 1255 | 150 |  | 2024-09-24 | 2024-07-25 | 149 | SEP | SEP
50925 | 740-WAn-VS671-108-LH099-40-0 | 1 | false | 1.06 | 740-WAn-VS671-108-LH099-40-0 | LV0-105633.VS671 | 386 |  |  | MC1 | LVL 6 | N/A | TR015_5 | 2024-05-15 | 2024-05-15 | 2024-05-15 |  | 2024-06-18 | 2024-06-18 | Satu Mare | 2024-06-28 |  | 2024-06-20 |  |  |  |  | 1035 | 150 |  |  |  | 149 | SEP | SEP
62239 | 740-WAn-VS671-108-LH099-40-0 | 3 | true | 1.06 | 740-WAn-VS671-108-LH099-40-0 | LV0-105633.VS671 | 386 |  |  | MC1 | LVL 6 | N/A | TR030_1 | 2024-07-25 | 2024-05-15 | 2024-05-15 |  | 2024-06-18 | 2024-06-18 | Büro | 2024-06-28 |  | 2024-06-20 |  |  |  | 2024-09-20 | 1035 | 150 |  |  | 2024-09-26 | 149 | SEP | SEP
50926 | 740-WAn-VS672-108-LH099-40-0 | 1 | false | 1.06 | 740-WAn-VS672-108-LH099-40-0 | LV0-105633.VS672 | 386 |  |  | MC1 | LVL 6 | N/A | TR015_5 | 2024-05-15 | 2024-05-15 | 2024-05-15 |  | 2024-06-18 | 2024-06-21 | Satu Mare | 2024-06-28 |  | 2024-06-25 |  |  |  |  | 1035 | 150 |  |  |  | 149 | SEP | SEP
62240 | 740-WAn-VS672-108-LH099-40-0 | 3 | true | 1.06 | 740-WAn-VS672-108-LH099-40-0 | LV0-105633.VS672 | 386 |  |  | MC1 | LVL 6 | N/A | TR030_1 | 2024-07-25 | 2024-05-15 | 2024-05-15 |  | 2024-06-18 | 2024-06-21 | Büro | 2024-06-28 |  | 2024-06-25 |  |  |  | 2024-09-20 | 1035 | 150 |  |  | 2024-09-25 | 149 | SEP | SEP
50927 | 740-WAn-VS673-108-LH099-40-0 | 1 | false | 1.06 | 740-WAn-VS673-108-LH099-40-0 | LV0-105633.VS673 | 386 |  |  | MC1 | LVL 6 | N/A | TR015_5 | 2024-05-15 | 2024-05-15 | 2024-05-15 |  | 2024-06-18 | 2024-06-25 | Satu Mare | 2024-06-28 |  | 2024-06-26 |  |  |  |  | 1035 | 150 |  |  |  | 149 | SEP | SEP
62241 | 740-WAn-VS673-108-LH099-40-0 | 3 | true | 1.06 | 740-WAn-VS673-108-LH099-40-0 | LV0-105633.VS673 | 386 |  |  | MC1 | LVL 6 | N/A | TR030_1 | 2024-07-25 | 2024-05-15 | 2024-05-15 |  | 2024-06-18 | 2024-06-25 | Büro | 2024-06-28 |  | 2024-06-26 |  |  |  | 2024-09-20 | 1035 | 150 |  |  | 2024-09-26 | 149 | SEP | SEP
50928 | 740-WAn-VS681-104-LH089-40-0 | 1 | true | 0 | 740-WAn-VS681-104-LH089-40-0 | LV0-105633.VS681 | 394 |  |  | MC1 | LVL 5 | Tt-6 | TR015_5 | 2024-05-15 | 2024-05-15 | 2024-05-15 |  | 2024-07-08 | 2024-07-09 | Büro | 2024-07-12 |  | 2024-07-09 |  |  |  | 2024-10-30 | 1036 | 150 |  | 2024-11-12 | 2024-10-31 | 149 | SEP | SEP
50929 | 740-WAn-VS681-106-LH099-40-0 | 1 | true | 0.47 | 740-WAn-VS681-106-LH099-40-0 | LV0-105633.VS681 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR015_5 | 2024-05-15 | 2024-05-15 | 2024-05-15 |  | 2024-06-18 | 2024-06-18 | Büro | 2024-06-28 |  | 2024-06-25 | 2024-10-22 |  |  | 2024-10-30 | 1036 | 150 |  | 2024-11-12 | 2024-10-31 | 149 | SEP | SEP
50930 | 740-WAn-VS681-107-LH089-40-0 | 1 | true | 0 | 740-WAn-VS681-107-LH089-40-0 | LV0-105633.VS681 | 394 |  |  | MC1 | LVL 5 | Tt-6 | TR015_5 | 2024-05-15 | 2024-05-15 | 2024-05-15 |  | 2024-07-08 | 2024-07-09 | Büro | 2024-07-12 |  | 2024-07-09 |  |  |  | 2024-10-30 | 1036 | 150 |  | 2024-11-12 | 2024-10-31 | 149 | SEP | SEP
50931 | 740-WAn-VS681-109-LH099-40-0 | 1 | true | 0.49 | 740-WAn-VS681-109-LH099-40-0 | LV0-105633.VS681 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR015_5 | 2024-05-15 | 2024-05-15 | 2024-05-15 |  | 2024-06-18 | 2024-06-19 | Büro | 2024-06-28 |  | 2024-06-26 | 2024-10-22 |  |  | 2024-10-30 | 1036 | 150 |  | 2024-11-12 | 2024-10-31 | 149 | SEP | SEP
50932 | 740-WAn-VS681-114-LH099-15-0 | 1 | true | 0.61 | 740-WAn-VS681-114-LH099-15-0 | LV0-105633.VS681 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR015_5 | 2024-05-15 | 2024-05-15 | 2024-05-15 |  | 2024-06-17 | 2024-06-19 | Büro | 2024-06-28 |  | 2024-06-26 | 2024-10-22 |  |  | 2024-10-30 | 1036 | 150 |  | 2024-11-12 | 2024-10-31 | 149 | SEP | SEP
50933 | 740-WAn-VS681-115-LH099-15-0 | 1 | true | 0.6 | 740-WAn-VS681-115-LH099-15-0 | LV0-105633.VS681 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR015_5 | 2024-05-15 | 2024-05-15 | 2024-05-15 |  | 2024-06-17 | 2024-06-19 | Büro | 2024-06-28 |  | 2024-06-21 | 2024-10-22 |  |  | 2024-10-30 | 1036 | 150 |  | 2024-11-12 | 2024-10-31 | 149 | SEP | SEP
50934 | 740-WAn-VS681-116-LH099-50-0 | 1 | true | 1.45 | 740-WAn-VS681-116-LH099-50-0 | LV0-105633.VS681 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR015_5 | 2024-05-15 | 2024-05-15 | 2024-05-15 |  | 2024-06-18 | 2024-06-25 | Büro | 2024-06-28 |  | 2024-06-27 | 2024-10-22 |  |  | 2024-10-30 | 1036 | 150 |  | 2024-11-12 | 2024-10-31 | 149 | SEP | SEP
50935 | 740-WAn-VS681-203-LH089-32-0 | 1 | true | 0.07 | 740-WAn-VS681-203-LH089-32-0 | LV0-105634.VS681 | 394 |  |  | MC1 | LVL 5 | Tt-7 | TR015_5 | 2024-05-15 | 2024-05-15 | 2024-05-15 |  | 2024-07-08 | 2024-07-09 |  | 2024-07-12 |  | 2024-07-09 | 2024-09-25 |  |  | 2024-10-18 | 1036 | 150 |  | 2024-11-12 | 2024-10-29 | 149 | SEP | SEP
50936 | 740-WAn-VS681-204-LH099-15-0 | 1 | true | 0.11 | 740-WAn-VS681-204-LH099-15-0 | LV0-105634.VS681 | 386 |  |  | MC1 | LVL 5 | Tt-8 | TR015_5 | 2024-05-15 | 2024-05-15 | 2024-05-15 |  | 2024-06-17 | 2024-06-25 | Büro | 2024-06-28 |  | 2024-06-26 | 2024-10-10 |  |  | 2024-10-17 | 1036 | 150 |  | 2024-11-12 |  | 149 | SEP | SEP
50937 | 740-WAn-VS681-205-LH099-32-0 | 1 | true | 0.42 | 740-WAn-VS681-205-LH099-32-0 | LV0-105634.VS681 | 386 |  |  | MC1 | LVL 5 | Tt-9 | TR015_5 | 2024-05-15 | 2024-05-15 | 2024-05-15 |  | 2024-06-18 | 2024-06-21 | Büro | 2024-06-28 |  | 2024-06-25 | 2024-10-10 |  |  | 2024-10-17 | 1036 | 150 |  | 2024-11-12 |  | 149 | SEP | SEP
50938 | 740-WAn-VS681-206-LH089-32-0 | 1 | true | 0.08 | 740-WAn-VS681-206-LH089-32-0 | LV0-105634.VS681 | 394 |  |  | MC1 | LVL 5 | Tt-10 | TR015_5 | 2024-05-15 | 2024-05-15 | 2024-05-15 |  | 2024-07-08 | 2024-07-09 |  | 2024-07-12 |  | 2024-07-09 | 2024-09-25 |  |  | 2024-10-18 | 1036 | 150 |  | 2024-11-12 | 2024-10-29 | 149 | SEP | SEP
50939 | 740-WAn-VS681-207-LH099-15-0 | 1 | true | 0.1 | 740-WAn-VS681-207-LH099-15-0 | LV0-105634.VS681 | 386 |  |  | MC1 | LVL 5 | Tt-11 | TR015_5 | 2024-05-15 | 2024-05-15 | 2024-05-15 |  | 2024-07-23 | 2024-07-24 | Büro | 2024-08-02 |  | 2024-07-26 | 2024-10-10 |  |  | 2024-10-17 | 1036 | 150 |  | 2024-11-12 |  | 149 | SEP | SEP
50940 | 740-WAn-VS681-208-LH099-32-0 | 1 | true | 0.42 | 740-WAn-VS681-208-LH099-32-0 | LV0-105634.VS681 | 386 |  |  | MC1 | LVL 5 | Tt-12 | TR015_5 | 2024-05-15 | 2024-05-15 | 2024-05-15 |  | 2024-07-19 | 2024-07-22 | Büro | 2024-08-02 |  | 2024-07-24 | 2024-10-10 |  |  | 2024-10-17 | 1036 | 150 |  | 2024-11-12 |  | 149 | SEP | SEP
50941 | 740-WAn-VS681-209-LH099-15-0 | 1 | true | 0.24 | 740-WAn-VS681-209-LH099-15-0 | LV0-105634.VS681 | 386 |  |  | MC1 | LVL 5 | Tt-13 | TR015_5 | 2024-05-15 | 2024-05-15 | 2024-05-15 |  | 2024-07-23 | 2024-07-24 | Büro | 2024-08-02 |  | 2024-07-26 | 2024-10-10 |  |  | 2024-10-17 | 1036 | 150 |  | 2024-11-12 |  | 149 | SEP | SEP
50942 | 740-WAn-VS681-211-LH099-15-0 | 1 | true | 0.24 | 740-WAn-VS681-211-LH099-15-0 | LV0-105634.VS681 | 386 |  |  | MC1 | LVL 5 | Tt-14 | TR015_5 | 2024-05-15 | 2024-05-15 | 2024-05-15 |  | 2024-07-23 | 2024-07-24 | Büro | 2024-08-02 |  | 2024-07-26 | 2024-10-10 |  |  | 2024-10-17 | 1036 | 150 |  | 2024-11-12 |  | 149 | SEP | SEP
50943 | 740-WAn-VS681-213-LH099-15-0 | 1 | true | 0.61 | 740-WAn-VS681-213-LH099-15-0 | LV0-105634.VS681 | 386 |  |  | MC1 | LVL 5 | Tt-15 | TR015_5 | 2024-05-15 | 2024-05-15 | 2024-05-15 |  | 2024-07-19 | 2024-07-23 | Büro | 2024-08-02 |  | 2024-07-24 | 2024-10-10 |  |  | 2024-10-17 | 1036 | 150 |  | 2024-11-12 |  | 149 | SEP | SEP
50944 | 740-WAn-VS681-214-LH099-15-0 | 1 | true | 0.59 | 740-WAn-VS681-214-LH099-15-0 | LV0-105634.VS681 | 386 |  |  | MC1 | LVL 5 | Tt-16 | TR015_5 | 2024-05-15 | 2024-05-15 | 2024-05-15 |  | 2024-07-22 | 2024-07-23 | Büro | 2024-08-02 |  | 2024-07-24 | 2024-10-10 |  |  | 2024-10-17 | 1036 | 150 |  | 2024-11-12 |  | 149 | SEP | SEP
50945 | 740-WAn-VS681-215-LH099-32-0 | 1 | true | 1.34 | 740-WAn-VS681-215-LH099-32-0 | LV0-105634.VS681 | 386 |  |  | MC1 | LVL 5 | Tt-17 | TR015_5 | 2024-05-15 | 2024-05-15 | 2024-05-15 |  | 2024-07-19 | 2024-07-22 | Büro | 2024-08-02 |  | 2024-07-23 | 2024-10-10 |  |  | 2024-10-17 | 1036 | 150 |  | 2024-11-12 |  | 149 | SEP | SEP
50946 | 740-WAn-VU200-102-LH032-25-0 | 1 | true | 8.61 | 740-WAn-VU200-102-LH032-25-0 | LV1-105638.VU320 | 385 |  |  | MC1 | LVL 5 | Tt-18 | TR015_5 | 2024-05-15 | 2024-05-15 | 2024-05-15 |  | 2024-06-26 | 2024-07-01 | Büro | 2024-07-12 |  | 2024-07-03 | 2024-10-02 |  |  | 2024-10-11 | 1034 | 150 |  |  |  | 149 | SEP | SEP
50947 | 740-WAn-VU200-111-LH099-50-0 | 1 | true | 0.54 | 740-WAn-VU200-111-LH099-50-0 | LV0-105633.VS681 | 386 |  |  | MC1 | LVL 5 | Tt-19 | TR015_5 | 2024-05-15 | 2024-05-15 | 2024-05-15 |  | 2024-06-27 | 2024-06-28 | Büro | 2024-07-12 |  | 2024-07-04 | 2024-10-22 |  |  | 2024-10-30 | 1036 | 150 |  |  | 2024-10-31 | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
50948 | 740-WAn-VU200-133-LH099-32-0 | 1 | false | 0.5 | 740-WAn-VU200-133-LH099-32-0 | LV0-105634.VS681 | 386 |  |  | MC1 | LVL 5 | Tt-20 | TR015_5 | 2024-05-15 | 2024-05-15 | 2024-05-15 |  | 2024-07-19 | 2024-07-22 | Büro | 2024-08-02 |  | 2024-07-23 | 2024-10-10 |  |  | 2024-10-17 | 1036 | 150 |  |  |  | 149 | SEP | SEP
62258 | 740-WAn-VU200-133-LH099-32-0 | 2 | true | 0.5 | 740-WAn-VU200-133-LH099-32-0 | LV0-105634.VS681 | 386 |  |  | MC1 | LVL 5 | Tt-20 | TR030_2 | 2024-07-25 | 2024-05-15 | 2024-05-15 |  | 2024-07-19 | 2024-07-22 |  |  |  | 2024-07-23 |  |  |  | 2024-10-17 | 1036 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
50949 | 740-WAn-VU310-112-LH032-25-0 | 1 | true | 9.7 | 740-WAn-VU310-112-LH032-25-0 | LV1-105638.VU310 | 385 |  |  | MC1 | LVL 5 | Tt-21 | TR015_5 | 2024-05-15 | 2024-05-15 | 2024-05-15 |  | 2024-06-26 | 2024-07-02 | Büro | 2024-07-12 |  | 2024-07-05 | 2024-10-02 |  |  | 2024-10-11 | 1034 | 150 |  |  | 2024-10-23 | 149 | SEP | SEP
50950 | 740-WAn-VU310-132-LH032-25-0 | 1 | false | 3.87 | 740-WAn-VU310-132-LH032-25-0 | LV1-105638.VU310 | 385 |  |  | MC1 | LVL 5 | Tt-22 | TR015_5 | 2024-05-15 | 2024-05-15 | 2024-05-15 |  |  |  | Satu Mare | [7 empty] | 1034 | 150 |  |  |  | 149 | SEP | SEP
51952 | 740-WAn-VU310-132-LH032-25-0 | 2 | true | 3.87 | 740-WAn-VU310-132-LH032-25-0 | LV1-105638.VU310 | 385 |  |  | MC1 | LVL 5 | Tt-22 | TR019_1 | 2024-05-22 | 2024-05-15 | 2024-05-23 |  | 2024-06-26 | 2024-06-26 | Büro | 2024-06-28 |  | 2024-06-27 | 2024-09-11 |  |  | 2024-09-18 | 1034 | 150 |  | 2024-10-08 | 2024-09-24 | 149 | SEP | SEP
50952 | 740-AWFI-VP001-101-LH089-32-0 | 1 | true | 0.16 | 740-AWFI-VP001-101-LH089-32-0 | LV0-105628.VP001 | 394 |  |  | MC1 | LVL 5 | N/A | TR016_3 | 2024-05-15 | 2024-05-15 | 2024-05-21 |  | 2024-06-10 | 2024-06-11 | Büro | 2024-06-14 |  | 2024-06-13 |  |  |  | 2024-09-06 | 937 | 150 |  | 2024-11-13 | 2024-09-23 | 149 | SEP | SEP
50953 | 740-AWFI-VP002-101-LH089-32-0 | 1 | true | 0.16 | 740-AWFI-VP002-101-LH089-32-0 | LV0-105628.VP002 | 394 |  |  | MC1 | LVL 5 | N/A | TR016_3 | 2024-05-15 | 2024-05-15 | 2024-05-21 |  | 2024-06-10 | 2024-06-11 | Büro | 2024-06-14 |  | 2024-06-13 |  |  |  | 2024-09-06 | 936 | 150 |  | 2024-11-13 | 2024-09-23 | 149 | SEP | SEP
50954 | 740-WFI-VP132-101-LH089-32-0 | 1 | true | 1.54 | 740-WFI-VP132-101-LH089-32-0 | LV1-105628.VP132 | 394 |  |  | MC1 | LVL 5 | N/A | TR016_3 | 2024-05-15 | 2024-05-15 | 2024-05-21 |  | 2024-06-10 | 2024-06-11 | Büro | 2024-06-14 |  | 2024-06-13 | 2024-10-22 |  |  | 2024-10-30 | 936 | 150 |  |  | 2024-10-31 | 149 | SEP | SEP
50955 | 740-WFI-VP142-101-LH089-32-0 | 1 | true | 1.54 | 740-WFI-VP142-101-LH089-32-0 | LV1-105628.VP142 | 394 |  |  | MC1 | LVL 5 | Tt-12 | TR016_3 | 2024-05-15 | 2024-05-15 | 2024-05-21 |  | 2024-06-10 | 2024-06-12 | Büro | 2024-06-14 |  | 2024-06-13 | 2024-10-22 |  |  | 2024-10-30 | 937 | 150 |  |  | 2024-10-31 | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
50960 | 740-DR2-VP001-102-LH088-15-0 | 2 | true | 0.58 | 740-DR2-VP001-102-LH088-15-0 | LV0-105628.VP001 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR018_1 | 2024-05-15 | 2024-05-16 | 2024-05-16 |  | 2024-06-10 | 2024-06-14 | Büro | 2024-06-28 |  | 2024-06-20 | 2024-09-06 |  |  | 2024-09-16 | 1005 | 150 |  |  | 2024-11-11 | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
50961 | 740-DR2-VS681-101-LH088-15-0 | 2 | true | 4.69 | 740-DR2-VS681-101-LH088-15-0 | LV0-105638.VU081 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR018_1 | 2024-05-15 | 2024-05-16 | 2024-05-16 |  | 2024-06-10 | 2024-06-12 | Büro | 2024-06-28 |  | 2024-06-20 |  |  |  | 2024-10-30 | 1005 | 150 |  |  | 2024-10-31 | 149 | SEP | SEP |  |  | 2024-11-15 | 2024-11-15
50962 | 740-DR2-VU081-113-LH088-65-0 | 2 | false | 10.45 | 740-DR2-VU081-113-LH088-65-0 | LV0-105638.VU081 | 391 |  |  | MC1 | LVL 6 | W23 | TR018_1 | 2024-05-15 | 2024-05-16 | 2024-05-16 |  |  |  | Satu Mare | [7 empty] | 907 | 150 |  |  |  | 149 | SEP | SEP
52571 | 740-DR2-VU081-113-LH088-65-0 | 3 | true | 10.45 | 740-DR2-VU081-113-LH088-65-0 | LV0-105638.VU081 | 391 |  |  | MC1 | LVL 6 | W23 | TR024_1 | 2024-06-10 | 2024-05-16 | 2024-05-16 |  | 2024-06-03 | 2024-06-10 | Büro | 2024-06-14 |  | 2024-06-14 | 2024-06-19 |  | 2024-06-28 | 2024-09-05 | 907 | 150 |  |  | 2024-08-13 | 149 | SEP | SEP | 2024-09-26 | 2024-10-04 | 2024-10-04 | 2024-10-04
50964 | 740-LP-VS501-101-LH099-15-0 | 1 | true | 0.05 | 740-LP-VS501-101-LH099-15-0 | LV1-105638.VU060 | 386 |  |  | MC1 | LVL 5 | N/A | TR018_1 | 2024-05-15 | 2024-05-16 | 2024-05-16 |  | 2024-07-22 | 2024-07-23 | Büro | 2024-08-02 |  | 2024-07-24 |  |  |  | 2024-09-20 | 929 | 150 |  |  |  | 149 | SEP | SEP
50977 | 740-WASH-U290-134-LH032-50 | 1 | true | 0.2 | 740-WASH-U290-134-LH032-50 | LV0-105638.290 | 385 |  |  | MC1 | LVL 5 | N/A | TR001_WASH | 2024-05-16 | 2024-05-17 | 2024-05-17 |  | 2024-05-24 | 2024-05-27 | Büro | 2024-06-14 |  | 2024-05-27 | 2024-10-03 |  |  | 2024-10-04 | 1256 | 150 |  |  |  | 149 | SEP | SEP
50978 | 740-WASH-U290-134-LH032-100 | 1 | true | 0.3 | 740-WASH-U290-134-LH032-100 | LV0-105638.290 | 385 |  |  | MC1 | LVL 5 | N/A | TR001_WASH | 2024-05-16 | 2024-05-17 | 2024-05-17 |  | 2024-05-24 | 2024-05-27 | Büro | 2024-06-14 |  | 2024-05-27 | 2024-10-03 |  |  | 2024-10-04 | 1256 | 150 |  |  |  | 149 | SEP | SEP
50979 | 740-WASH-U290-134-LH032-125 | 1 | true | 0.8 | 740-WASH-U290-134-LH032-125 | LV0-105638.290 | 385 |  |  | MC1 | LVL 5 | N/A | TR001_WASH | 2024-05-16 | 2024-05-17 | 2024-05-17 |  | 2024-06-04 | 2024-06-07 | Büro | 2024-06-14 |  | 2024-06-07 | 2024-10-03 |  |  | 2024-10-04 | 1256 | 150 |  |  |  | 149 | SEP | SEP
50980 | 740-WASH-U290-172-LH032-125 | 1 | true | 0.7 | 740-WASH-U290-172-LH032-125 | LV0-105638.290 | 385 |  |  | MC1 | LVL 5 | N/A | TR001_WASH | 2024-05-16 | 2024-05-17 | 2024-05-17 |  | 2024-06-04 | 2024-06-07 | Büro | 2024-06-14 |  | 2024-06-07 |  |  |  | 2024-10-15 | 1256 | 150 |  |  |  | 149 | SEP | SEP
50981 | 740-WASH-VU290-101-LH032-80-1 | 1 | true | 21.5 | 740-WASH-VU290-101-LH032-80-1 | LV0-105638.290 | 385 |  |  | MC1 | LVL 5 | N/A | TR001_WASH | 2024-05-16 | 2024-05-17 | 2024-05-17 |  | 2024-05-21 | 2024-05-28 | Büro | 2024-05-31 |  | 2024-05-30 | 2024-06-20 |  | 2024-06-26 | 2024-08-14 | 1256 | 150 |  |  | 2024-09-02 | 149 | SEP | SEP
50982 | 740-WASH-VU290-101-LH032-80-2 | 1 | true | 21.6 | 740-WASH-VU290-101-LH032-80-2 | LV0-105638.290 | 385 |  |  | MC1 | LVL 5 | N/A | TR001_WASH | 2024-05-16 | 2024-05-17 | 2024-05-17 |  | 2024-05-21 | 2024-05-28 | Büro | 2024-05-31 |  | 2024-05-29 | 2024-06-17 |  |  | 2024-06-26 | 1256 | 150 |  |  | 2024-09-02 | 149 | SEP | SEP
50983 | 740-WASH-VU290-103-LH032-40 | 1 | true | 4.8 | 740-WASH-VU290-103-LH032-40 | LV0-105638.290 | 385 |  |  | MC1 | LVL 5 | N/A | TR001_WASH | 2024-05-16 | 2024-05-17 | 2024-05-17 |  | 2024-05-22 | 2024-05-24 | Büro | 2024-05-31 |  | 2024-05-24 | 2024-10-21 |  |  | 2024-10-30 | 1256 | 150 |  |  | 2024-10-31 | 149 | SEP | SEP
50984 | 740-WASH-VU290-104-LH032-40 | 1 | true | 4.2 | 740-WASH-VU290-104-LH032-40 | LV0-105638.290 | 385 |  |  | MC1 | LVL 5 | N/A | TR001_WASH | 2024-05-16 | 2024-05-17 | 2024-05-17 |  | 2024-05-22 | 2024-05-24 | Büro | 2024-05-31 |  | 2024-05-28 | 2024-06-26 |  |  | 2024-07-05 | 1256 | 150 |  |  | 2024-09-02 | 149 | SEP | SEP
50985 | 740-WASH-VU290-105-LH032-40 | 1 | true | 0.7 | 740-WASH-VU290-105-LH032-40 | LV0-105638.290 | 385 |  |  | MC1 | LVL 5 | N/A | TR001_WASH | 2024-05-16 | 2024-05-17 | 2024-05-17 |  | 2024-05-23 | 2024-05-25 | Büro | 2024-05-31 |  | 2024-05-28 | 2024-06-26 |  |  | 2024-07-05 | 1256 | 150 |  |  | 2024-09-02 | 149 | SEP | SEP
50986 | 740-WASH-VU290-106-LH032-20 | 1 | true | 1 | 740-WASH-VU290-106-LH032-20 | LV0-105638.290 | 385 |  |  | MC1 | LVL 5 | N/A | TR001_WASH | 2024-05-16 | 2024-05-17 | 2024-05-17 |  | 2024-05-23 | 2024-05-28 | Büro | 2024-05-31 |  | 2024-05-29 | 2024-06-26 |  |  | 2024-07-05 | 1256 | 150 |  |  | 2024-09-02 | 149 | SEP | SEP
50987 | 740-WASH-VU290-107-LH032-40 | 1 | true | 14.5 | 740-WASH-VU290-107-LH032-40 | LV0-105638.290 | 385 |  |  | MC1 | LVL 5 | N/A | TR001_WASH | 2024-05-16 | 2024-05-17 | 2024-05-17 |  | 2024-05-21 | 2024-05-27 | Büro | 2024-05-31 |  | 2024-05-28 | 2024-07-03 |  |  | 2024-08-14 | 1256 | 150 |  |  |  | 149 | SEP | SEP
50988 | 740-WASH-VU290-108-LH032-40 | 1 | true | 4.2 | 740-WASH-VU290-108-LH032-40 | LV0-105638.290 | 385 |  |  | MC1 | LVL 5 | N/A | TR001_WASH | 2024-05-16 | 2024-05-17 | 2024-05-17 |  | 2024-05-23 | 2024-05-29 | Büro | 2024-05-31 |  | 2024-05-30 | 2024-10-21 |  |  | 2024-10-30 | 1256 | 150 |  |  |  | 149 | SEP | SEP
50989 | 740-WASH-VU290-109-LH032-40 | 1 | true | 0.9 | 740-WASH-VU290-109-LH032-40 | LV0-105638.290 | 385 |  |  | MC1 | LVL 5 | N/A | TR001_WASH | 2024-05-16 | 2024-05-17 | 2024-05-17 |  | 2024-05-24 | 2024-05-28 | Büro | 2024-06-14 |  | 2024-06-04 | 2024-10-21 |  |  | 2024-10-30 | 1256 | 150 |  |  | 2024-11-04 | 149 | SEP | SEP
50990 | 740-WASH-VU290-111-LH032-40 | 1 | true | 0.9 | 740-WASH-VU290-111-LH032-40 | LV0-105638.290 | 385 |  |  | MC1 | LVL 5 | N/A | TR001_WASH | 2024-05-16 | 2024-05-17 | 2024-05-17 |  | 2024-05-24 | 2024-05-27 | Büro | 2024-06-14 |  | 2024-06-04 | 2024-10-21 |  |  | 2024-10-31 | 1256 | 150 |  |  | 2024-11-05 | 149 | SEP | SEP
50991 | 740-WASH-VU290-112-LH032-40 | 1 | true | 0.9 | 740-WASH-VU290-112-LH032-40 | LV0-105638.290 | 385 |  |  | MC1 | LVL 5 | N/A | TR001_WASH | 2024-05-16 | 2024-05-17 | 2024-05-17 |  | 2024-05-22 | 2024-05-24 | Büro | 2024-05-31 |  | 2024-05-28 | 2024-10-21 |  |  | 2024-10-31 | 1256 | 150 |  |  | 2024-11-05 | 149 | SEP | SEP
50992 | 740-WASH-VU290-114-LH032-40 | 1 | true | 3.6 | 740-WASH-VU290-114-LH032-40 | LV0-105638.290 | 385 |  |  | MC1 | LVL 5 | N/A | TR001_WASH | 2024-05-16 | 2024-05-17 | 2024-05-17 |  | 2024-05-23 | 2024-05-24 | Büro | 2024-05-31 |  | 2024-05-29 | 2024-08-07 |  |  | 2024-08-09 | 1256 | 150 |  |  | 2024-09-02 | 149 | SEP | SEP
50993 | 740-WASH-VU290-115-LH032-40 | 1 | true | 1.1 | 740-WASH-VU290-115-LH032-40 | LV0-105638.290 | 385 |  |  | MC1 | LVL 5 | N/A | TR001_WASH | 2024-05-16 | 2024-05-17 | 2024-05-17 |  | 2024-05-24 | 2024-05-28 | Büro | 2024-06-14 |  | 2024-06-06 | 2024-08-07 |  |  | 2024-08-09 | 1256 | 150 |  |  | 2024-09-02 | 149 | SEP | SEP
50994 | 740-WASH-VU290-116-LH032-32 | 1 | true | 7.4 | 740-WASH-VU290-116-LH032-32 | LV0-105638.290 | 385 |  |  | MC1 | LVL 5 | N/A | TR001_WASH | 2024-05-16 | 2024-05-17 | 2024-05-17 |  | 2024-05-27 | 2024-05-29 | Büro | 2024-06-14 |  | 2024-06-06 | 2024-08-07 |  |  | 2024-08-12 | 1256 | 150 |  |  | 2024-09-02 | 149 | SEP | SEP
50995 | 740-WASH-VU290-117-LH032-40 | 1 | true | 14.8 | 740-WASH-VU290-117-LH032-40 | LV0-105638.290 | 385 |  |  | MC1 | LVL 5 | N/A | TR001_WASH | 2024-05-16 | 2024-05-17 | 2024-05-17 |  | 2024-05-24 | 2024-05-27 | Satu Mare | 2024-05-31 |  | 2024-05-29 | 2024-10-18 | 2024-10-18 | 2024-10-18 | 2024-10-18 | 1256 | 150 |  |  |  | 149 | SEP | SEP
50996 | 740-WASH-VU290-118-LH032-40 | 1 | true | 1.9 | 740-WASH-VU290-118-LH032-40 | LV0-105638.290 | 385 |  |  | MC1 | LVL 5 | N/A | TR001_WASH | 2024-05-16 | 2024-05-17 | 2024-05-17 |  | 2024-05-24 | 2024-05-28 | Büro | 2024-05-31 |  | 2024-05-29 | 2024-10-18 |  |  | 2024-10-23 | 1256 | 150 |  |  | 2024-10-30 | 149 | SEP | SEP
50997 | 740-WASH-VU290-119-LH032-40 | 1 | true | 14.8 | 740-WASH-VU290-119-LH032-40 | LV0-105638.290 | 385 |  |  | MC1 | LVL 5 | N/A | TR001_WASH | 2024-05-16 | 2024-05-17 | 2024-05-17 |  | 2024-05-24 | 2024-05-29 | Büro | 2024-05-31 |  | 2024-05-30 |  |  |  | 2024-10-22 | 1256 | 150 |  |  | 2024-11-04 | 149 | SEP | SEP
50998 | 740-WASH-VU290-120-LH032-40 | 1 | true | 3.4 | 740-WASH-VU290-120-LH032-40 | LV0-105638.290 | 385 |  |  | MC1 | LVL 5 | N/A | TR001_WASH | 2024-05-16 | 2024-05-17 | 2024-05-17 |  | 2024-05-22 | 2024-05-27 | Büro | 2024-05-31 |  | 2024-05-28 | 2024-10-18 |  |  | 2024-10-28 | 1256 | 150 |  |  | 2024-10-30 | 149 | SEP | SEP
50999 | 740-WASH-VU290-121-LH032-40 | 1 | true | 0.4 | 740-WASH-VU290-121-LH032-40 | LV0-105638.290 | 385 |  |  | MC1 | LVL 5 | N/A | TR001_WASH | 2024-05-16 | 2024-05-17 | 2024-05-17 |  | 2024-05-22 | 2024-05-25 | Satu Mare | 2024-05-31 |  | 2024-05-25 | 2024-10-18 | 2024-10-18 | 2024-10-18 | 2024-10-18 | 1256 | 150 |  |  |  | 149 | SEP | SEP
51000 | 740-WASH-VU290-122-LH032-40 | 1 | true | 0.6 | 740-WASH-VU290-122-LH032-40 | LV0-105638.290 | 385 |  |  | MC1 | LVL 5 | N/A | TR001_WASH | 2024-05-16 | 2024-05-17 | 2024-05-17 |  | 2024-05-22 | 2024-05-25 | Büro | 2024-05-31 |  | 2024-05-25 | 2024-10-18 |  |  | 2024-10-22 | 1256 | 150 |  |  | 2024-11-05 | 149 | SEP | SEP
51001 | 740-WASH-VU290-123-LH032-40 | 1 | true | 0.9 | 740-WASH-VU290-123-LH032-40 | LV0-105638.290 | 385 |  |  | MC1 | LVL 5 | N/A | TR001_WASH | 2024-05-16 | 2024-05-17 | 2024-05-17 |  | 2024-05-22 | 2024-05-24 | Büro | 2024-05-31 |  | 2024-05-24 | 2024-10-18 |  |  | 2024-10-22 | 1256 | 150 |  |  | 2024-11-05 | 149 | SEP | SEP
51002 | 740-WASH-VU290-124-LH032-40 | 1 | true | 1 | 740-WASH-VU290-124-LH032-40 | LV0-105638.290 | 385 |  |  | MC1 | LVL 5 | N/A | TR001_WASH | 2024-05-16 | 2024-05-17 | 2024-05-17 |  | 2024-05-22 | 2024-05-24 | Büro | 2024-05-31 |  | 2024-05-24 | 2024-10-18 |  |  | 2024-10-22 | 1256 | 150 |  |  |  | 149 | SEP | SEP
51003 | 740-WASH-VU290-125-LH032-40 | 1 | true | 1 | 740-WASH-VU290-125-LH032-40 | LV0-105638.290 | 385 |  |  | MC1 | LVL 5 | N/A | TR001_WASH | 2024-05-16 | 2024-05-17 | 2024-05-17 |  | 2024-05-22 | 2024-05-24 | Satu Mare | 2024-05-31 |  | 2024-05-24 | 2024-10-18 |  |  | 2024-10-21 | 1256 | 150 |  |  | 2024-10-29 | 149 | SEP | SEP
51004 | 740-WASH-VU290-126-LH032-20 | 1 | true | 1.4 | 740-WASH-VU290-126-LH032-20 | LV0-105638.290 | 385 |  |  | MC1 | LVL 5 | N/A | TR001_WASH | 2024-05-16 | 2024-05-17 | 2024-05-17 |  | 2024-05-22 | 2024-05-24 | Büro | 2024-05-31 |  | 2024-05-24 | 2024-10-18 |  |  | 2024-10-22 | 1256 | 150 |  |  | 2024-10-29 | 149 | SEP | SEP
51005 | 740-WASH-VU290-127-LH032-40 | 1 | true | 0.6 | 740-WASH-VU290-127-LH032-40 | LV0-105638.290 | 385 |  |  | MC1 | LVL 5 | N/A | TR001_WASH | 2024-05-16 | 2024-05-17 | 2024-05-17 |  | 2024-05-22 | 2024-05-27 | Büro | 2024-05-31 |  | 2024-05-28 | 2024-10-18 |  |  | 2024-10-22 | 1256 | 150 |  |  | 2024-11-05 | 149 | SEP | SEP
51006 | 740-WASH-VU290-128-LH032-40 | 1 | true | 0.5 | 740-WASH-VU290-128-LH032-40 | LV0-105638.290 | 385 |  |  | MC1 | LVL 5 | N/A | TR001_WASH | 2024-05-16 | 2024-05-17 | 2024-05-17 |  | 2024-05-21 | 2024-05-25 | Büro | 2024-05-31 |  | 2024-05-25 | 2024-10-18 |  |  | 2024-10-24 | 1256 | 150 |  |  |  | 149 | SEP | SEP
51007 | 740-WASH-VU290-129-LH032-40 | 1 | true | 13.5 | 740-WASH-VU290-129-LH032-40 | LV0-105638.290 | 385 |  |  | MC1 | LVL 5 | N/A | TR001_WASH | 2024-05-16 | 2024-05-17 | 2024-05-17 |  | 2024-05-21 | 2024-05-28 | Satu Mare | 2024-05-31 |  | 2024-05-29 | 2024-10-18 |  |  | 2024-10-18 | 1256 | 150 |  |  |  | 149 | SEP | SEP
51008 | 740-WASH-VU290-130-LH032-40 | 1 | true | 1 | 740-WASH-VU290-130-LH032-40 | LV0-105638.290 | 385 |  |  | MC1 | LVL 5 | N/A | TR001_WASH | 2024-05-16 | 2024-05-17 | 2024-05-17 |  | 2024-05-21 | 2024-05-22 | Satu Mare | 2024-05-31 |  | 2024-05-23 | 2024-10-18 |  |  | 2024-10-21 | 1256 | 150 |  |  | 2024-10-29 | 149 | SEP | SEP
51009 | 740-WASH-VU290-131-LH032-40 | 1 | true | 1 | 740-WASH-VU290-131-LH032-40 | LV0-105638.290 | 385 |  |  | MC1 | LVL 5 | N/A | TR001_WASH | 2024-05-16 | 2024-05-17 | 2024-05-17 |  | 2024-05-21 | 2024-05-25 | Büro | 2024-05-31 |  | 2024-05-25 | 2024-10-18 |  |  | 2024-10-22 | 1256 | 150 |  |  | 2024-10-29 | 149 | SEP | SEP
51010 | 740-WASH-VU290-132-LH032-20 | 1 | true | 1.2 | 740-WASH-VU290-132-LH032-20 | LV0-105638.290 | 385 |  |  | MC1 | LVL 5 | N/A | TR001_WASH | 2024-05-16 | 2024-05-17 | 2024-05-17 |  | 2024-05-23 | 2024-05-29 | Satu Mare | 2024-05-31 |  | 2024-05-29 | 2024-10-18 |  |  | 2024-10-21 | 1256 | 150 |  |  | 2024-10-29 | 149 | SEP | SEP
51011 | 740-WASH-VU290-133-LH032-25 | 1 | true | 3.7 | 740-WASH-VU290-133-LH032-25 | LV0-105638.290 | 385 |  |  | MC1 | LVL 5 | N/A | TR001_WASH | 2024-05-16 | 2024-05-17 | 2024-05-17 |  | 2024-05-27 | 2024-05-28 | Büro | 2024-06-14 |  | 2024-06-06 |  |  |  | 2024-11-06 | 1256 | 150 |  |  |  | 149 | SEP | SEP
51012 | 740-WASH-VU290-134-LH032-100 | 1 | true | 7.2 | 740-WASH-VU290-134-LH032-100 | LV0-105638.290 | 385 |  |  | MC1 | LVL 5 | N/A | TR001_WASH | 2024-05-16 | 2024-05-17 | 2024-05-17 |  | 2024-05-23 | 2024-05-27 | Büro | 2024-05-31 |  | 2024-05-29 | 2024-06-14 |  |  | 2024-06-18 | 1256 | 150 |  |  | 2024-09-02 | 149 | SEP | SEP
51013 | 740-WASH-VU290-135-LH032-50 | 1 | true | 2.8 | 740-WASH-VU290-135-LH032-50 | LV0-105638.290 | 385 |  |  | MC1 | LVL 5 | N/A | TR001_WASH | 2024-05-16 | 2024-05-17 | 2024-05-17 |  | 2024-05-22 | 2024-05-28 | Büro | 2024-05-31 |  | 2024-05-29 |  |  |  | 2024-11-28 | 1256 | 150 |  |  |  | 149 | SEP | SEP
51014 | 740-WASH-VU290-136-LH032-32 | 1 | true | 7.9 | 740-WASH-VU290-136-LH032-32 | LV0-105638.290 | 385 |  |  | MC1 | LVL 5 | N/A | TR001_WASH | 2024-05-16 | 2024-05-17 | 2024-05-17 |  | 2024-05-28 | 2024-06-03 | Büro | 2024-06-14 |  | 2024-06-06 |  |  |  | 2024-11-06 | 1256 | 150 |  |  |  | 149 | SEP | SEP
51015 | 740-WASH-VU290-137-LH032-25 | 1 | true | 3.7 | 740-WASH-VU290-137-LH032-25 | LV0-105638.290 | 385 |  |  | MC1 | LVL 5 | N/A | TR001_WASH | 2024-05-16 | 2024-05-17 | 2024-05-17 |  | 2024-05-28 | 2024-06-07 | Büro | 2024-06-14 |  | 2024-06-07 |  |  |  | 2024-11-06 | 1256 | 150 |  |  |  | 149 | SEP | SEP
51016 | 740-WASH-VU290-138-LH032-25 | 1 | true | 1.7 | 740-WASH-VU290-138-LH032-25 | LV0-105638.290 | 385 |  |  | MC1 | LVL 5 | N/A | TR001_WASH | 2024-05-16 | 2024-05-17 | 2024-05-17 |  | 2024-05-27 | 2024-06-07 | Büro | 2024-06-14 |  | 2024-06-07 | 2024-08-07 |  |  | 2024-08-12 | 1256 | 150 |  |  | 2024-09-02 | 149 | SEP | SEP
51017 | 740-WASH-VU290-140-LH032-25 | 1 | true | 0.6 | 740-WASH-VU290-140-LH032-25 | LV0-105638.290 | 385 |  |  | MC1 | LVL 5 | N/A | TR001_WASH | 2024-05-16 | 2024-05-17 | 2024-05-17 |  | 2024-05-27 | 2024-06-07 | Büro | 2024-06-14 |  | 2024-06-07 |  |  |  | 2024-11-06 | 1256 | 150 |  |  |  | 149 | SEP | SEP
51018 | 740-WASH-VU290-141-LH032-40 | 1 | true | 0.5 | 740-WASH-VU290-141-LH032-40 | LV0-105638.290 | 385 |  |  | MC1 | LVL 5 | N/A | TR001_WASH | 2024-05-16 | 2024-05-17 | 2024-05-17 |  | 2024-05-22 | 2024-05-24 | Büro | 2024-05-31 |  | 2024-05-24 | 2024-10-18 |  |  | 2024-10-25 | 1256 | 150 |  |  |  | 149 | SEP | SEP
51019 | 740-WASH-VU290-142-LH032-80-1 | 1 | true | 27.5 | 740-WASH-VU290-142-LH032-80-1 | LV0-105638.290 | 385 |  |  | MC1 | LVL 5 | N/A | TR001_WASH | 2024-05-16 | 2024-05-17 | 2024-05-17 |  | 2024-05-24 | 2024-05-28 | Büro | 2024-05-31 |  | 2024-05-29 | 2024-06-14 |  |  | 2024-06-21 | 1256 | 150 |  |  | 2024-09-02 | 149 | SEP | SEP
51020 | 740-WASH-VU290-142-LH032-80-2 | 1 | true | 18.7 | 740-WASH-VU290-142-LH032-80-2 | LV0-105638.290 | 385 |  |  | MC1 | LVL 5 | N/A | TR001_WASH | 2024-05-16 | 2024-05-17 | 2024-05-17 |  | 2024-05-23 | 2024-05-24 | Büro | 2024-05-31 |  | 2024-05-28 | 2024-06-18 |  | 2024-06-26 | 2024-08-13 | 1256 | 150 |  |  | 2024-09-02 | 149 | SEP | SEP
51021 | 740-WASH-VU290-144-LH032-40 | 1 | true | 0.5 | 740-WASH-VU290-144-LH032-40 | LV0-105638.290 | 385 |  |  | MC1 | LVL 5 | N/A | TR001_WASH | 2024-05-16 | 2024-05-17 | 2024-05-17 |  | 2024-05-22 | 2024-05-24 | Büro | 2024-05-31 |  | 2024-05-24 |  |  |  | 2024-10-22 | 1256 | 150 |  |  |  | 149 | SEP | SEP
51022 | 740-WASH-VU290-145-LH032-40 | 1 | true | 2.2 | 740-WASH-VU290-145-LH032-40 | LV0-105638.290 | 385 |  |  | MC1 | LVL 5 | N/A | TR001_WASH | 2024-05-16 | 2024-05-17 | 2024-05-17 |  | 2024-05-24 | 2024-06-07 | Büro | 2024-06-14 |  | 2024-06-07 |  |  |  | 2024-10-22 | 1256 | 150 |  |  |  | 149 | SEP | SEP
51023 | 740-WASH-VU290-146-LH032-25 | 1 | true | 3.3 | 740-WASH-VU290-146-LH032-25 | LV0-105638.290 | 385 |  |  | MC1 | LVL 5 | N/A | TR001_WASH | 2024-05-16 | 2024-05-17 | 2024-05-17 |  | 2024-05-28 | 2024-06-03 | Büro | 2024-06-14 |  | 2024-06-06 | 2024-10-18 |  |  | 2024-10-30 | 1256 | 150 |  |  | 2024-11-04 | 149 | SEP | SEP
51024 | 740-WASH-VU290-147-LH032-40 | 1 | true | 13.9 | 740-WASH-VU290-147-LH032-40 | LV0-105638.290 | 385 |  |  | MC1 | LVL 5 | N/A | TR001_WASH | 2024-05-16 | 2024-05-17 | 2024-05-17 |  | 2024-05-24 | 2024-05-29 | Büro | 2024-05-31 |  | 2024-05-30 | 2024-10-08 |  |  | 2024-10-15 | 1256 | 150 |  |  |  | 149 | SEP | SEP
51025 | 740-WASH-VU290-148-LH032-20 | 1 | true | 0.9 | 740-WASH-VU290-148-LH032-20 | LV0-105638.290 | 385 |  |  | MC1 | LVL 5 | N/A | TR001_WASH | 2024-05-16 | 2024-05-17 | 2024-05-17 |  | 2024-05-24 | 2024-05-27 | Büro | 2024-05-31 |  | 2024-05-28 |  |  |  | 2024-10-17 | 1256 | 150 |  |  |  | 149 | SEP | SEP
51026 | 740-WASH-VU290-149-LH032-40 | 1 | true | 0.6 | 740-WASH-VU290-149-LH032-40 | LV0-105638.290 | 385 |  |  | MC1 | LVL 5 | N/A | TR001_WASH | 2024-05-16 | 2024-05-17 | 2024-05-17 |  | 2024-05-23 | 2024-05-24 | Büro | 2024-05-31 |  | 2024-05-24 | 2024-10-08 |  |  | 2024-10-17 | 1256 | 150 |  |  |  | 149 | SEP | SEP
51027 | 740-WASH-VU290-150-LH032-40 | 1 | true | 0.5 | 740-WASH-VU290-150-LH032-40 | LV0-105638.290 | 385 |  |  | MC1 | LVL 5 | N/A | TR001_WASH | 2024-05-16 | 2024-05-17 | 2024-05-17 |  | 2024-05-24 | 2024-06-04 | Satu Mare | 2024-06-14 |  | 2024-06-04 |  |  |  | 2024-10-18 | 1256 | 150 |  |  |  | 149 | SEP | SEP
51028 | 740-WASH-VU290-151-LH032-40 | 1 | true | 0.4 | 740-WASH-VU290-151-LH032-40 | LV0-105638.290 | 385 |  |  | MC1 | LVL 5 | N/A | TR001_WASH | 2024-05-16 | 2024-05-17 | 2024-05-17 |  | 2024-05-24 | 2024-05-27 | Satu Mare | 2024-06-14 |  | 2024-06-06 | 2024-10-18 |  |  | 2024-10-18 | 1256 | 150 |  |  | 2024-11-05 | 149 | SEP | SEP
51029 | 740-WASH-VU290-152-LH032-40 | 1 | true | 2.6 | 740-WASH-VU290-152-LH032-40 | LV0-105638.290 | 385 |  |  | MC1 | LVL 5 | N/A | TR001_WASH | 2024-05-16 | 2024-05-17 | 2024-05-17 |  | 2024-05-24 | 2024-05-28 | Satu Mare | 2024-06-14 |  | 2024-06-05 | 2024-10-18 |  |  | 2024-10-21 | 1256 | 150 |  |  | 2024-10-29 | 149 | SEP | SEP
51030 | 740-WASH-VU290-153-LH032-25 | 1 | true | 4.7 | 740-WASH-VU290-153-LH032-25 | LV0-105638.290 | 385 |  |  | MC1 | LVL 5 | N/A | TR001_WASH | 2024-05-16 | 2024-05-17 | 2024-05-17 |  | 2024-05-28 | 2024-06-07 | Büro | 2024-06-14 |  | 2024-06-07 | 2024-10-18 |  |  | 2024-10-22 | 1256 | 150 |  |  |  | 149 | SEP | SEP
51031 | 740-WASH-VU290-154-LH032-25 | 1 | true | 7.7 | 740-WASH-VU290-154-LH032-25 | LV0-105638.290 | 385 |  |  | MC1 | LVL 5 | N/A | TR001_WASH | 2024-05-16 | 2024-05-17 | 2024-05-17 |  | 2024-05-27 | 2024-05-28 | Büro | 2024-06-14 |  | 2024-06-06 |  |  |  | 2024-10-11 | 1256 | 150 |  |  |  | 149 | SEP | SEP
51032 | 740-WASH-VU290-155-LH032-40 | 1 | true | 14.4 | 740-WASH-VU290-155-LH032-40 | LV0-105638.290 | 385 |  |  | MC1 | LVL 5 | N/A | TR001_WASH | 2024-05-16 | 2024-05-17 | 2024-05-17 |  | 2024-05-28 | 2024-06-07 | Büro | 2024-06-14 |  | 2024-06-07 | 2024-10-08 |  |  | 2024-10-17 | 1256 | 150 |  |  |  | 149 | SEP | SEP
51033 | 740-WASH-VU290-156-LH032-40 | 1 | true | 3.8 | 740-WASH-VU290-156-LH032-40 | LV0-105638.290 | 385 |  |  | MC1 | LVL 5 | N/A | TR001_WASH | 2024-05-16 | 2024-05-17 | 2024-05-17 |  | 2024-05-24 | 2024-06-03 |  | 2024-06-14 |  | 2024-06-04 | 2024-06-25 |  |  | 2024-07-19 | 1256 | 150 |  |  | 2024-09-02 | 149 | SEP | SEP
51034 | 740-WASH-VU290-157-LH032-40 | 1 | true | 6.2 | 740-WASH-VU290-157-LH032-40 | LV0-105638.290 | 385 |  |  | MC1 | LVL 5 | N/A | TR001_WASH | 2024-05-16 | 2024-05-17 | 2024-05-17 |  | 2024-05-28 | 2024-06-03 |  | 2024-06-14 |  | 2024-06-06 | 2024-06-25 |  |  | 2024-07-19 | 1256 | 150 |  |  | 2024-09-02 | 149 | SEP | SEP
51035 | 740-WASH-VU290-158-LH032-20 | 1 | true | 1.9 | 740-WASH-VU290-158-LH032-20 | LV0-105638.290 | 385 |  |  | MC1 | LVL 5 | N/A | TR001_WASH | 2024-05-16 | 2024-05-17 | 2024-05-17 |  | 2024-05-24 | 2024-05-27 | Büro | 2024-05-31 |  | 2024-05-28 | 2024-10-08 |  |  | 2024-10-17 | 1256 | 150 |  |  |  | 149 | SEP | SEP
51036 | 740-WASH-VU290-159-LH032-40 | 1 | false | 1.6 | 740-WASH-VU290-159-LH032-40 | LV0-105638.290 | 385 |  |  | MC1 | LVL 5 | N/A | TR001_WASH | 2024-05-16 | [5 empty] | Satu Mare | [7 empty] | 1256 | 150 |  |  |  | 149 | SEP | SEP
51054 | 740-WASH-VU290-159-LH032-40 | 2 | true | 1.6 | 740-WASH-VU290-159-LH032-40 | LV0-105638.290 | 385 |  |  | MC1 | LVL 5 | N/A | TR002_WASH | 2024-05-16 | 2024-05-17 | 2024-05-17 |  | 2024-05-28 | 2024-06-07 | Büro | 2024-06-14 |  | 2024-06-07 | 2024-10-08 |  |  | 2024-10-12 | 1256 | 150 |  |  |  | 149 | SEP | SEP
51037 | 740-WASH-VU290-160-LH032-40 | 1 | true | 1.5 | 740-WASH-VU290-160-LH032-40 | LV0-105638.290 | 385 |  |  | MC1 | LVL 5 | N/A | TR001_WASH | 2024-05-16 | 2024-05-17 | 2024-05-17 |  | 2024-05-28 | 2024-06-04 | Büro | 2024-06-14 |  | 2024-06-06 | 2024-10-08 |  |  | 2024-10-17 | 1256 | 150 |  |  |  | 149 | SEP | SEP
51038 | 740-WASH-VU290-161-LH032-40 | 1 | true | 6.1 | 740-WASH-VU290-161-LH032-40 | LV0-105638.290 | 385 |  |  | MC1 | LVL 5 | N/A | TR001_WASH | 2024-05-16 | 2024-05-17 | 2024-05-17 |  | 2024-05-28 | 2024-06-07 | Büro | 2024-06-14 |  | 2024-06-07 |  |  |  | 2024-10-24 | 1256 | 150 |  |  |  | 149 | SEP | SEP
51039 | 740-WASH-VU290-162-LH032-40 | 1 | true | 1.4 | 740-WASH-VU290-162-LH032-40 | LV0-105638.290 | 385 |  |  | MC1 | LVL 5 | N/A | TR001_WASH | 2024-05-16 | 2024-05-17 | 2024-05-17 |  | 2024-05-24 | 2024-06-04 | Büro | 2024-06-14 |  | 2024-06-06 | 2024-10-08 |  |  | 2024-10-17 | 1256 | 150 |  |  |  | 149 | SEP | SEP
51040 | 740-WASH-VU290-163-LH032-40 | 1 | true | 6.1 | 740-WASH-VU290-163-LH032-40 | LV0-105638.290 | 385 |  |  | MC1 | LVL 5 | N/A | TR001_WASH | 2024-05-16 | 2024-05-17 | 2024-05-17 |  | 2024-05-28 | 2024-06-07 | Büro | 2024-06-14 |  | 2024-06-07 | 2024-10-23 |  |  | 2024-10-28 | 1256 | 150 |  |  | 2024-10-31 | 149 | SEP | SEP
51041 | 740-WASH-VU290-166-LH032-40 | 1 | true | 6.1 | 740-WASH-VU290-166-LH032-40 | LV0-105638.290 | 385 |  |  | MC1 | LVL 5 | N/A | TR001_WASH | 2024-05-16 | 2024-05-17 | 2024-05-17 |  | 2024-05-28 | 2024-06-07 | Büro | 2024-06-14 |  | 2024-06-07 | 2024-10-23 |  |  | 2024-10-30 | 1256 | 150 |  |  | 2024-10-31 | 149 | SEP | SEP
51042 | 740-WASH-VU290-195-LH032-40 | 1 | false | 0.7 | 740-WASH-VU290-195-LH032-40 | LV0-105638.290 | 385 |  |  | MC1 | LVL 5 | N/A | TR001_WASH | 2024-05-16 | [5 empty] | Satu Mare | [7 empty] | 1256 | 150 |  |  |  | 149 | SEP | SEP
51056 | 740-WASH-VU290-195-LH032-40 | 2 | true | 0.7 | 740-WASH-VU290-195-LH032-40 | LV0-105638.290 | 385 |  |  | MC1 | LVL 5 | N/A | TR002_WASH | 2024-05-16 | 2024-05-17 | 2024-05-17 |  | 2024-05-24 | 2024-05-27 | Büro | 2024-06-14 |  | 2024-06-04 | 2024-06-26 |  |  | 2024-07-05 | 1256 | 150 |  |  | 2024-09-02 | 149 | SEP | SEP
51043 | 740-WASH-VU290-196-LH032-40 | 1 | true | 12.1 | 740-WASH-VU290-196-LH032-40 | LV0-105638.290 | 385 |  |  | MC1 | LVL 5 | N/A | TR001_WASH | 2024-05-16 | 2024-05-17 | 2024-05-17 |  | 2024-05-28 | 2024-06-07 | Büro | 2024-06-14 |  | 2024-06-07 | 2024-06-26 | 2024-06-28 |  | 2024-07-05 | 1256 | 150 |  |  | 2024-09-02 | 149 | SEP | SEP
51044 | 740-WASH-VU290-197-LH032-40 | 1 | true | 0.9 | 740-WASH-VU290-197-LH032-40 | LV0-105638.290 | 385 |  |  | MC1 | LVL 5 | N/A | TR001_WASH | 2024-05-16 | 2024-05-17 | 2024-05-17 |  | 2024-05-24 | 2024-06-04 | Büro | 2024-06-14 |  | 2024-06-04 | 2024-10-18 |  |  | 2024-10-22 | 1256 | 150 |  |  | 2024-11-05 | 149 | SEP | SEP
51045 | 740-WASH-VU290-198-LH032-40 | 1 | true | 0.9 | 740-WASH-VU290-198-LH032-40 | LV0-105638.290 | 385 |  |  | MC1 | LVL 5 | N/A | TR001_WASH | 2024-05-16 | 2024-05-17 | 2024-05-17 |  | 2024-05-24 | 2024-06-03 | Büro | 2024-06-14 |  | 2024-06-04 | 2024-10-18 |  |  | 2024-10-22 | 1256 | 150 |  |  |  | 149 | SEP | SEP
51046 | 740-WASH-VU290-199-LH032-40 | 1 | true | 0.5 | 740-WASH-VU290-199-LH032-40 | LV0-105638.290 | 385 |  |  | MC1 | LVL 5 | N/A | TR001_WASH | 2024-05-16 | 2024-05-17 | 2024-05-17 |  | 2024-05-24 | 2024-05-29 | Büro | 2024-06-14 |  | 2024-06-04 | 2024-10-18 |  |  | 2024-10-25 | 1256 | 150 |  |  |  | 149 | SEP | SEP
51047 | 740-WASH-VU290-200-LH032-40 | 1 | true | 0.4 | 740-WASH-VU290-200-LH032-40 | LV0-105638.290 | 385 |  |  | MC1 | LVL 5 | N/A | TR001_WASH | 2024-05-16 | 2024-05-17 | 2024-05-17 |  | 2024-05-24 | 2024-05-29 | Büro | 2024-06-14 |  | 2024-06-04 |  |  |  | 2024-10-16 | 1256 | 150 |  |  |  | 149 | SEP | SEP
51048 | 740-WASH-VU290-201-LH032-40 | 1 | true | 0.4 | 740-WASH-VU290-201-LH032-40 | LV0-105638.290 | 385 |  |  | MC1 | LVL 5 | N/A | TR001_WASH | 2024-05-16 | 2024-05-17 | 2024-05-17 |  | 2024-05-24 | 2024-06-04 | Satu Mare | 2024-06-14 |  | 2024-06-04 |  |  |  | 2024-10-18 | 1256 | 150 |  |  |  | 149 | SEP | SEP
51049 | 740-WASH-VU290-202-LH032-40 | 1 | false | 0.4 | 740-WASH-VU290-202-LH032-40 | LV0-105638.290 | 385 |  |  | MC1 | LVL 5 | N/A | TR001_WASH | 2024-05-16 | [5 empty] | Satu Mare | [7 empty] | 1256 | 150 |  |  |  | 149 | SEP | SEP
51055 | 740-WASH-VU290-202-LH032-40 | 2 | true | 0.4 | 740-WASH-VU290-202-LH032-40 | LV0-105638.290 | 385 |  |  | MC1 | LVL 5 | N/A | TR002_WASH | 2024-05-16 | 2024-05-17 | 2024-05-17 |  | 2024-05-24 | 2024-05-27 | Büro | 2024-06-14 |  | 2024-06-04 | 2024-10-08 |  |  | 2024-10-12 | 1256 | 150 |  |  |  | 149 | SEP | SEP
51050 | 740-WASH-VU290-203-LH032-40 | 1 | true | 7 | 740-WASH-VU290-203-LH032-40 | LV0-105638.290 | 385 |  |  | MC1 | LVL 5 | N/A | TR001_WASH | 2024-05-16 | 2024-05-17 | 2024-05-17 |  | 2024-05-28 | 2024-06-07 | Büro | 2024-06-14 |  | 2024-06-07 | 2024-10-23 |  |  | 2024-10-30 | 1256 | 150 |  |  | 2024-10-31 | 149 | SEP | SEP
51051 | 740-WASH-VU290-205-LH032-40 | 1 | true | 1 | 740-WASH-VU290-205-LH032-40 | LV0-105638.290 | 385 |  |  | MC1 | LVL 5 | N/A | TR001_WASH | 2024-05-16 | 2024-05-17 | 2024-05-17 |  | 2024-05-24 | 2024-06-04 | Satu Mare | 2024-06-14 |  | 2024-06-06 |  |  |  | 2024-10-21 | 1256 | 150 |  |  | 2024-10-29 | 149 | SEP | SEP
51052 | 740-WASH-VU290-206-LH032-40 | 1 | true | 0.5 | 740-WASH-VU290-206-LH032-40 | LV0-105638.290 | 385 |  |  | MC1 | LVL 5 | N/A | TR001_WASH | 2024-05-16 | 2024-05-17 | 2024-05-17 |  | 2024-05-28 | 2024-06-04 | Büro | 2024-06-14 |  | 2024-06-04 | 2024-10-08 |  |  | 2024-10-17 | 1256 | 150 |  |  |  | 149 | SEP | SEP
51053 | 740-WASH-VU290-210-LH032-50 | 1 | true | 0.3 | 740-WASH-VU290-210-LH032-50 | LV0-105638.290 | 385 |  |  | MC1 | LVL 5 | N/A | TR001_WASH | 2024-05-16 | 2024-05-17 | 2024-05-17 |  | 2024-05-24 | 2024-05-27 | Büro | 2024-05-31 |  | 2024-05-28 |  |  |  | 2024-11-06 | 1256 | 150 |  |  |  | 149 | SEP | SEP
51188 | 740-WAKont-VU190-211-LH032-25-0 | 1 | true | 23.75 | 740-WAKont-VU190-211-LH032-25 | LV1-105639.VU190 | 385 |  |  | MC1 | LVL 5 | N/A | TR016_4 | 2024-05-17 | 2024-05-21 | 2024-05-21 |  | 2024-06-26 | 2024-06-28 | Büro | 2024-07-12 |  | 2024-07-04 |  |  |  | 2024-10-07 | 934 | 150 |  |  |  | 149 | SEP | SEP
51542 | 740-AB-VU310-120-LH032-32-0 | 2 | true | 2.61 | 740-AB-VU310-120-LH032-32-0 | LV1-105638.VU310 | 385 |  |  | MC1 | LVL 6 | N/A | TR018_2 | 2024-05-17 | 2024-05-22 | 2024-05-22 |  | 2024-07-19 | 2024-07-23 | Büro | 2024-08-02 |  | 2024-07-25 | 2024-08-29 |  |  | 2024-09-03 | 1019 | 150 |  | 2024-10-08 | 2024-09-14 | 149 | SEP | SEP
51543 | 740-AB-VU310-121-LH032-32-0 | 2 | true | 2.51 | 740-AB-VU310-121-LH032-32-0 | LV1-105638.VU310 | 385 |  |  | MC1 | LVL 6 | N/A | TR018_2 | 2024-05-17 | 2024-05-22 | 2024-05-22 |  | 2024-07-19 | 2024-07-22 | Büro | 2024-08-02 |  | 2024-07-23 | 2024-08-29 |  |  | 2024-09-03 | 1019 | 150 |  | 2024-10-08 | 2024-09-14 | 149 | SEP | SEP
51544 | 740-AB-VU310-136-LH099-15-0 | 2 | false | 1.52 | 740-AB-VU310-136-LH099-15-0 | LV1-105638.VU310 | 386 |  |  | MC1 | LVL 5 | N/A | TR018_2 | 2024-05-17 | 2024-05-22 | 2024-05-22 | [11 empty] | 1018 | 150 |  |  |  | 149 | SEP | SEP
52272 | 740-AB-VU310-136-LH099-15-0 | 3 | true | 1.52 | 740-AB-VU310-136-LH099-15-0 | LV1-105638.VU310 | 386 |  |  | MC1 | LVL 5 | N/A | TR021_2 | 2024-06-05 | 2024-05-22 | 2024-05-22 |  | 2024-07-24 | 2024-07-25 | Büro | 2024-08-02 |  | 2024-07-26 |  |  |  | 2024-09-28 | 1018 | 150 |  |  | 2024-09-30 | 149 | SEP | SEP
51545 | 740-AB-VU310-143-LH032-100-0 | 2 | false | 27.22 | 740-AB-VU310-143-LH032-100-0 | LV1-105638.VU310 | 385 |  |  | MC1 | LVL 5 | N/A | TR018_2 | 2024-05-17 | 2024-05-22 | 2024-05-22 | [11 empty] | 1018 | 150 |  |  |  | 149 | SEP | SEP
51925 | 740-AB-VU310-143-LH032-100-0 | 3 | true | 27.22 | 740-AB-VU310-143-LH032-100-0 | LV1-105638.VU310 | 385 |  |  | MC1 | LVL 5 | N/A | TR019_1 | 2024-05-22 | 2024-05-22 | 2024-05-23 |  | 2024-07-05 | 2024-07-05 |  | 2024-07-12 |  | 2024-07-10 | 2024-07-19 |  |  | 2024-07-26 | 1018 | 150 |  |  | 2024-09-03 | 149 | SEP | SEP
51547 | 740-AB-VU330-104-LH032-32-0 | 2 | true | 0.1 | 740-AB-VU330-104-LH032-32-0 | LV1-105638.VU310 | 385 |  |  | MC1 | LVL 6 | N/A | TR018_2 | 2024-05-17 | 2024-05-22 | 2024-05-22 |  | 2024-07-19 | 2024-07-24 | Büro | 2024-08-02 |  | 2024-07-26 | 2024-08-29 |  |  | 2024-08-31 | 1019 | 150 |  | 2024-09-10 | 2024-09-11 | 149 | SEP | SEP
51548 | 740-AB-VU340-104-LH032-32-0 | 2 | true | 0.77 | 740-AB-VU340-104-LH032-32-0 | LV1-105638.VU310 | 385 |  |  | MC1 | LVL 6 | N/A | TR018_2 | 2024-05-17 | 2024-05-22 | 2024-05-22 |  | 2024-07-19 | 2024-07-24 |  | 2024-08-02 |  | 2024-07-26 |  |  |  | 2024-09-03 | 1019 | 150 |  |  | 2024-09-14 | 149 | SEP | SEP
51549 | 740-WAKont-VU190-201-LH032-50-0 | 2 | false | 16.43 | 740-WAKont-VU190-201-LH032-50-0 | LV1-105638.VU321 | 385 |  |  | MC1 | LVL 6 | W60 | TR018_2 | 2024-05-17 | 2024-05-22 | 2024-05-22 |  | 2024-06-27 | [9 empty] | 1257 | 150 |  |  |  | 149 | SEP | SEP
56821 | 740-WAKont-VU190-201-LH032-50-0 | 3 | true | 16.43 | 740-WAKont-VU190-201-LH032-50-0 | LV1-105638.VU321 | 385 |  |  | MC1 | LVL 6 | W60 | TR027_2 | 2024-07-02 | 2024-05-22 | 2024-05-22 |  | 2024-06-27 | 2024-07-04 | Büro | 2024-07-12 |  | 2024-07-08 | 2024-08-12 |  |  | 2024-08-27 | 1257 | 150 |  |  |  | 149 | SEP | SEP
51550 | 740-WAn-VS001-103-LH099-15-0 | 2 | true | 0.5 | 740-WAn-VS001-103-LH099-15-0 | LV1-105633.VS001 | 386 |  |  | MC1 | LVL 5 | W60 | TR018_2 | 2024-05-17 | 2024-05-22 | 2024-05-22 |  | 2024-07-22 | 2024-07-23 | Büro | 2024-08-02 |  | 2024-07-25 | 2024-10-17 |  |  | 2024-10-22 | 1036 | 150 |  |  | 2024-11-04 | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
51551 | 740-WAn-VS001-107-LH099-15-0 | 2 | true | 0.32 | 740-WAn-VS001-107-LH099-15-0 | LV1-105633.VS001 | 386 |  |  | MC1 | LVL 5 | W60 | TR018_2 | 2024-05-17 | 2024-05-22 | 2024-05-22 |  | 2024-07-22 | 2024-07-23 | Büro | 2024-08-02 |  | 2024-07-25 | 2024-10-17 |  |  | 2024-10-22 | 1036 | 150 |  |  | 2024-10-30 | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
51552 | 740-WAn-VS501-101-LH088-15-0 | 1 | true | 0.1 | 740-WAn-VS501-101-LH088-15-0 | LV3-105633.VS501 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR018_2 | 2024-05-17 | 2024-05-22 | 2024-05-22 |  | 2024-07-22 | 2024-07-25 | Büro | 2024-08-02 |  | 2024-07-31 |  |  |  | 2024-10-10 | 1036 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
51553 | 740-WAn-VS501-102-LH099-15-0 | 1 | true | 0.38 | 740-WAn-VS501-102-LH099-15-0 | LV3-105633.VS501 | 386 |  |  | MC1 | LVL 5 | Tt-12 | TR018_2 | 2024-05-17 | 2024-05-22 | 2024-05-22 |  | 2024-07-22 | 2024-07-23 | Büro | 2024-08-02 |  | 2024-07-26 |  |  |  | 2024-10-10 | 1036 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
51554 | 740-WAn-VU161-201-LH088-15-0 | 1 | true | 0.1 | 740-WAn-VU161-201-LH088-15-0 | LV1-105639.VU161 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR018_2 | 2024-05-17 | 2024-05-22 | 2024-05-22 |  | 2024-07-22 | 2024-07-25 | Büro | 2024-08-02 |  | 2024-07-31 |  |  |  | 2024-10-10 | 1036 | 150 |  | 2024-11-05 |  | 149 | SEP | SEP |  |  | 2024-11-01 | 2024-11-01
51555 | 740-WAn-VU161-202-LH088-15-0 | 1 | true | 0.1 | 740-WAn-VU161-202-LH088-15-0 | LV1-105639.VU161 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR018_2 | 2024-05-17 | 2024-05-22 | 2024-05-22 |  | 2024-07-18 | 2024-07-19 | Büro | 2024-08-02 |  | 2024-07-31 |  |  |  | 2024-10-10 | 1036 | 150 |  | 2024-11-05 |  | 149 | SEP | SEP |  |  | 2024-11-01 | 2024-11-01
51556 | 740-WAn-VU161-203-LH088-15-0 | 1 | true | 0.1 | 740-WAn-VU161-203-LH088-15-0 | LV1-105639.VU161 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR018_2 | 2024-05-17 | 2024-05-22 | 2024-05-22 |  | 2024-07-18 | 2024-07-19 | Büro | 2024-08-02 |  | 2024-07-31 |  |  |  | 2024-10-10 | 1036 | 150 |  | 2024-11-05 |  | 149 | SEP | SEP |  |  | 2024-11-01 | 2024-11-01
51557 | 740-WAn-VU161-204-LH099-15-0 | 1 | true | 0.38 | 740-WAn-VU161-204-LH099-15-0 | LV1-105639.VU161 | 386 |  |  | MC1 | LVL 5 | Tt-12 | TR018_2 | 2024-05-17 | 2024-05-22 | 2024-05-22 |  | 2024-07-22 | 2024-07-23 | Büro | 2024-08-02 |  | 2024-07-25 |  |  |  | 2024-10-10 | 1036 | 150 |  | 2024-11-05 |  | 149 | SEP | SEP |  |  | 2024-11-01 | 2024-11-01
51558 | 740-WAn-VU161-205-LH099-15-0 | 1 | true | 0.38 | 740-WAn-VU161-205-LH099-15-0 | LV1-105639.VU161 | 386 |  |  | MC1 | LVL 5 | Tt-12 | TR018_2 | 2024-05-17 | 2024-05-22 | 2024-05-22 |  | 2024-07-22 | 2024-07-23 | Büro | 2024-08-02 |  | 2024-07-24 |  |  |  | 2024-10-10 | 1036 | 150 |  | 2024-11-05 |  | 149 | SEP | SEP |  |  | 2024-11-01 | 2024-11-01
51559 | 740-WAn-VU161-206-LH099-15-0 | 1 | true | 0.38 | 740-WAn-VU161-206-LH099-15-0 | LV1-105639.VU161 | 386 |  |  | MC1 | LVL 5 | Tt-12 | TR018_2 | 2024-05-17 | 2024-05-22 | 2024-05-22 |  | 2024-07-22 | 2024-07-22 | Büro | 2024-08-02 |  | 2024-07-24 |  |  |  | 2024-10-10 | 1036 | 150 |  | 2024-11-05 |  | 149 | SEP | SEP |  |  | 2024-11-01 | 2024-11-01
51560 | 740-WAn-VU162-212-LH099-15-0 | 1 | true | 0.38 | 740-WAn-VU162-212-LH099-15-0 | LV1-105639.VU162 | 386 |  |  | MC1 | LVL 5 | Tt-12 | TR018_2 | 2024-05-17 | 2024-05-22 | 2024-05-22 |  | 2024-07-22 | 2024-07-23 | Büro | 2024-08-02 |  | 2024-07-24 |  |  |  | 2024-10-10 | 1036 | 150 |  | 2024-11-08 |  | 149 | SEP | SEP
51561 | 740-WAn-VU162-213-LH088-15-0 | 1 | true | 0.1 | 740-WAn-VU162-213-LH088-15-0 | LV1-105639.VU162 | 391 |  |  | MC1 | LVL 5 | Tt-6 | TR018_2 | 2024-05-17 | 2024-05-22 | 2024-05-22 |  | 2024-07-18 | 2024-07-19 | Büro | 2024-08-02 |  | 2024-07-31 |  |  |  | 2024-10-10 | 1036 | 150 |  | 2024-11-08 |  | 149 | SEP | SEP
51562 | 740-WAn-VU162-215-LH088-15-0 | 1 | true | 0.1 | 740-WAn-VU162-215-LH088-15-0 | LV1-105639.VU162 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR018_2 | 2024-05-17 | 2024-05-22 | 2024-05-22 |  | 2024-07-18 | 2024-07-19 | Büro | 2024-08-02 |  | 2024-07-31 |  |  |  | 2024-10-10 | 1036 | 150 |  | 2024-11-08 |  | 149 | SEP | SEP
51563 | 740-WAn-VU162-218-LH099-15-0 | 1 | true | 0.38 | 740-WAn-VU162-218-LH099-15-0 | LV1-105639.VU162 | 386 |  |  | MC1 | LVL 5 | Tt-12 | TR018_2 | 2024-05-17 | 2024-05-22 | 2024-05-22 |  | 2024-07-22 | 2024-07-24 | Büro | 2024-08-02 |  | 2024-07-26 | 2024-10-03 |  |  | 2024-10-12 | 1036 | 150 |  | 2024-11-08 |  | 149 | SEP | SEP
51564 | 740-WAn-VU200-110-LH099-15-0 | 1 | true | 0.46 | 740-WAn-VU200-110-LH099-15-0 | LV3-105633.VS501 | 386 |  |  | MC1 | LVL 5 | Tt-12 | TR018_2 | 2024-05-17 | 2024-05-22 | 2024-05-22 |  | 2024-07-02 |  | Büro | 2024-07-12 |  | 2024-07-05 |  |  |  | 2024-10-11 | 1036 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
51565 | 740-WAn-VU200-124-LH099-15-0 | 1 | true | 0.95 | 740-WAn-VU200-124-LH099-15-0 | LV1-105639.VU162 | 386 |  |  | MC1 | LVL 5 | Tt-12 | TR018_2 | 2024-05-17 | 2024-05-22 | 2024-05-22 |  | 2024-07-02 | 2024-07-04 | Büro | 2024-07-12 |  | 2024-07-09 | 2024-10-03 |  |  | 2024-10-12 | 1036 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
51566 | 740-WAn-VU200-125-LH099-15-0 | 1 | true | 0.88 | 740-WAn-VU200-125-LH099-15-0 | LV1-105639.VU162 | 386 |  |  | MC1 | LVL 5 | Tt-12 | TR018_2 | 2024-05-17 | 2024-05-22 | 2024-05-22 |  | 2024-07-02 | 2024-07-04 | Büro | 2024-07-12 |  | 2024-07-09 | 2024-10-03 |  |  | 2024-10-12 | 1036 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
51567 | 740-WAn-VU200-138-LH099-15-0 | 1 | true | 0.51 | 740-WAn-VU200-138-LH099-15-0 | LV1-105639.VU162 | 386 |  |  | MC1 | LVL 5 | Tt-12 | TR018_2 | 2024-05-17 | 2024-05-22 | 2024-05-22 |  | 2024-06-28 |  | Büro | 2024-07-12 |  | 2024-07-03 | 2024-08-26 |  |  | 2024-09-03 | 1036 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
51568 | 740-WAn-VU200-158-LH099-15-0 | 1 | true | 0.51 | 740-WAn-VU200-158-LH099-15-0 | LV1-105639.VU161 | 386 |  |  | MC1 | LVL 5 | Tt-12 | TR018_2 | 2024-05-17 | 2024-05-22 | 2024-05-22 |  | 2024-07-02 |  | Büro | 2024-07-12 |  | 2024-07-05 |  |  |  | 2024-10-09 | 1036 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
51569 | 740-WAn-VU200-160-LH099-15-0 | 1 | true | 0.51 | 740-WAn-VU200-160-LH099-15-0 | LV1-105639.VU161 | 386 |  |  | MC1 | LVL 5 | Tt-12 | TR018_2 | 2024-05-17 | 2024-05-22 | 2024-05-22 |  | 2024-07-02 |  | Büro | 2024-07-12 |  | 2024-07-05 |  |  |  | 2024-10-09 | 1036 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
51570 | 740-WAn-VU200-173-LH099-15-0 | 1 | true | 0.51 | 740-WAn-VU200-173-LH099-15-0 | LV1-105639.VU161 | 386 |  |  | MC1 | LVL 5 | Tt-12 | TR018_2 | 2024-05-17 | 2024-05-22 | 2024-05-22 |  | 2024-07-02 |  | Büro | 2024-07-12 |  | 2024-07-05 |  |  |  | 2024-10-09 | 1036 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
51571 | 740-WAn-VU200-226-LH099-40-0 | 1 | true | 0.67 | 740-WAn-VU200-226-LH099-40-0 | LV1-105639.VU200 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR018_2 | 2024-05-17 | 2024-05-22 | 2024-05-22 |  | 2024-06-26 | 2024-07-04 | Büro | 2024-07-12 |  | 2024-07-05 |  |  |  | 2024-10-14 | 1034 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
51572 | 740-WAn-VU200-247-LH032-25-0 | 2 | true | 2.65 | 740-WAn-VU200-247-LH032-25-0 | LV1-105639.VU200 | 385 |  |  | MC1 | LVL 5 | N/A | TR018_2 | 2024-05-17 | 2024-05-22 | 2024-05-22 |  | 2024-06-26 | 2024-07-01 | Büro | 2024-07-12 |  | 2024-07-03 | 2024-10-17 |  |  | 2024-10-23 | 1034 | 150 |  |  |  | 149 | SEP | SEP
51573 | 740-WAn-VU200-259-LH099-40-0 | 1 | false | 0.55 | 740-WAn-VU200-259-LH099-40-0 | LV1-105639.VU200 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR018_2 | 2024-05-17 | 2024-05-22 | 2024-05-22 | [11 empty] | 1034 | 150 |  |  |  | 149 | SEP | SEP
52799 | 740-WAn-VU200-259-LH099-40-0 | 2 | true | 0.55 | 740-WAn-VU200-259-LH099-40-0 | LV1-105639.VU200 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR025_1 | 2024-06-18 | 2024-05-22 | 2024-05-22 |  | 2024-07-01 | 2024-07-05 | Büro | 2024-07-12 |  | 2024-07-09 |  |  |  | 2024-10-14 | 1034 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
51574 | 740-WAn-VU200-261-LH099-40-0 | 1 | false | 0.56 | 740-WAn-VU200-261-LH099-40-0 | LV1-105639.VU200 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR018_2 | 2024-05-17 | 2024-05-22 | 2024-05-22 | [11 empty] | 1034 | 150 |  |  |  | 149 | SEP | SEP
52800 | 740-WAn-VU200-261-LH099-40-0 | 2 | true | 0.56 | 740-WAn-VU200-261-LH099-40-0 | LV1-105639.VU200 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR025_1 | 2024-06-18 | 2024-05-22 | 2024-05-22 |  | 2024-06-28 | 2024-07-02 | Büro | 2024-07-12 |  | 2024-07-04 |  |  |  | 2024-10-09 | 1034 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
51575 | 740-WAn-VU200-263-LH099-40-0 | 1 | false | 0.56 | 740-WAn-VU200-263-LH099-40-0 | LV1-105639.VU200 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR018_2 | 2024-05-17 | 2024-05-22 | 2024-05-22 | [11 empty] | 1034 | 150 |  |  |  | 149 | SEP | SEP
52801 | 740-WAn-VU200-263-LH099-40-0 | 2 | true | 0.56 | 740-WAn-VU200-263-LH099-40-0 | LV1-105639.VU200 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR025_1 | 2024-06-18 | 2024-05-22 | 2024-05-22 |  | 2024-07-01 | 2024-07-05 | Büro | 2024-07-12 |  | 2024-07-09 |  |  |  | 2024-10-09 | 1034 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
51576 | 740-WAn-VU200-266-LH099-40-0 | 2 | true | 0.66 | 740-WAn-VU200-266-LH099-40-0 | LV1-105639.VU200 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR018_2 | 2024-05-17 | 2024-05-22 | 2024-05-22 |  | 2024-07-01 | 2024-07-05 | Büro | 2024-07-12 |  | 2024-07-09 | 2024-10-17 |  |  | 2024-10-22 | 1034 | 150 |  |  | 2024-10-30 | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
51577 | 740-WAn-VU200-267-LH099-40-0 | 1 | false | 0.55 | 740-WAn-VU200-267-LH099-40-0 | LV1-105639.VU200 | 386 |  |  | MC1 | LVL 5 | N/A | TR018_2 | 2024-05-17 | 2024-05-22 | 2024-05-22 | [11 empty] | 1034 | 150 |  |  |  | 149 | SEP | SEP
52804 | 740-WAn-VU200-267-LH099-40-0 | 2 | true | 0.55 | 740-WAn-VU200-267-LH099-40-0 | LV1-105639.VU200 | 386 |  |  | MC1 | LVL 5 | N/A | TR025_1 | 2024-06-18 | 2024-05-22 | 2024-05-22 |  | 2024-06-28 | 2024-07-02 | Büro | 2024-07-12 |  | 2024-07-03 |  |  |  | 2024-10-09 | 1034 | 150 |  |  |  | 149 | SEP | SEP
51578 | 740-WAn-VU200-271-LH032-40-0 | 2 | true | 4.08 | 740-WAn-VU200-271-LH032-40-0 | LV0-105639.VU200 | 385 |  |  | MC1 | LVL 5 | N/A | TR018_2 | 2024-05-17 | 2024-05-22 | 2024-05-22 |  | 2024-06-26 | 2024-07-04 | Büro | 2024-07-12 |  | 2024-07-08 | 2024-09-21 |  |  | 2024-09-26 | 1034 | 150 |  |  |  | 149 | SEP | SEP
51579 | 740-WFI-VS501-101-LH089-15-0 | 1 | true | 0 | 740-WFI-VS501-101-LH089-15-0 | LV3-105633.VS501 | 394 |  |  | MC1 | LVL 5 | Tt-6 | TR018_2 | 2024-05-17 | 2024-05-22 | 2024-05-22 |  | 2024-06-10 |  | Dawid Mierzwa | 2024-06-28 |  | 2024-06-17 | 2024-08-28 |  |  | 2024-08-30 | 936 | 150 |  |  |  | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
51580 | 740-WFI-VS501-102-LH089-15-0 | 1 | true | 0 | 740-WFI-VS501-102-LH089-15-0 | LV3-105633.VS501 | 394 |  |  | MC1 | LVL 5 | Tt-6 | TR018_2 | 2024-05-17 | 2024-05-22 | 2024-05-22 |  |  |  | Büro | [6 empty] | 2024-09-20 | 936 | 150 |  |  |  | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
51581 | 740-WFI-VU161-207-LH089-15-0 | 1 | true | 0 | 740-WFI-VU161-207-LH089-15-0 | LV1-105639.VU161 | 394 |  |  | MC1 | LVL 5 | Tt-6 | TR018_2 | 2024-05-17 | 2024-05-22 | 2024-05-22 |  | 2024-06-17 |  | Dawid Mierzwa | 2024-06-28 |  | 2024-06-20 | 2024-08-28 |  |  | 2024-08-30 | 936 | 150 |  | 2024-10-15 |  | 149 | SEP | SEP
51582 | 740-WFI-VU161-208-LH089-15-0 | 1 | true | 0 | 740-WFI-VU161-208-LH089-15-0 | LV1-105639.VU161 | 394 |  |  | MC1 | LVL 5 | N/A | TR018_2 | 2024-05-17 | 2024-05-22 | 2024-05-22 |  | 2024-06-17 |  | Büro | 2024-06-28 |  | 2024-06-20 |  |  |  | 2024-09-20 | 936 | 150 |  | 2024-10-15 |  | 149 | SEP | SEP |  |  | 2024-11-01 | 2024-11-01
51583 | 740-WFI-VU161-209-LH089-15-0 | 1 | true | 0 | 740-WFI-VU161-209-LH089-15-0 | LV1-105639.VU161 | 394 |  |  | MC1 | LVL 5 | Tt-6 | TR018_2 | 2024-05-17 | 2024-05-22 | 2024-05-22 |  | 2024-06-17 |  | Büro | 2024-06-28 |  | 2024-06-20 |  |  |  | 2024-09-20 | 936 | 150 |  | 2024-10-15 |  | 149 | SEP | SEP |  |  | 2024-11-01 | 2024-11-01
51584 | 740-WFI-VU161-210-LH089-15-0 | 1 | true | 0 | 740-WFI-VU161-210-LH089-15-0 | LV1-105639.VU161 | 394 |  |  | MC1 | LVL 5 | Tt-6 | TR018_2 | 2024-05-17 | 2024-05-22 | 2024-05-22 |  |  |  | Büro | [6 empty] | 2024-09-20 | 936 | 150 |  | 2024-10-15 |  | 149 | SEP | SEP |  |  | 2024-11-01 | 2024-11-01
51585 | 740-WFI-VU161-211-LH089-15-0 | 1 | true | 0 | 740-WFI-VU161-211-LH089-15-0 | LV1-105639.VU161 | 394 |  |  | MC1 | LVL 5 | Tt-6 | TR018_2 | 2024-05-17 | 2024-05-22 | 2024-05-22 | [10 empty] | 2024-10-18 | 936 | 150 |  |  | 2024-10-31 | 149 | SEP | SEP |  |  | 2024-11-01 | 2024-11-01
51586 | 740-WFI-VU161-212-LH089-15-0 | 1 | true | 0 | 740-WFI-VU161-212-LH089-15-0 | LV1-105639.VU161 | 394 |  |  | MC1 | LVL 5 | Tt-6 | TR018_2 | 2024-05-17 | 2024-05-22 | 2024-05-22 | [10 empty] | 2024-10-18 | 936 | 150 |  |  | 2024-10-31 | 149 | SEP | SEP |  |  | 2024-11-01 | 2024-11-01
51587 | 740-WFI-VU162-208-LH089-15-0 | 1 | true | 0 | 740-WFI-VU162-208-LH089-15-0 | LV1-105639.VU162 | 394 |  |  | MC1 | LVL 5 | Tt-6 | TR018_2 | 2024-05-17 | 2024-05-22 | 2024-05-22 |  | 2024-06-17 |  | Büro | 2024-06-28 |  | 2024-06-20 |  |  |  | 2024-09-20 | 937 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-11-01 | 2024-11-01
51588 | 740-WFI-VU162-209-LH089-15-0 | 1 | true | 0 | 740-WFI-VU162-209-LH089-15-0 | LV1-105639.VU162 | 394 |  |  | MC1 | LVL 5 | Tt-6 | TR018_2 | 2024-05-17 | 2024-05-22 | 2024-05-22 |  | 2024-06-17 |  | Büro | 2024-06-28 |  | 2024-06-20 |  |  |  | 2024-10-10 | 937 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-11-01 | 2024-11-01
51589 | 740-WFI-VU162-210-LH089-15-0 | 1 | true | 0 | 740-WFI-VU162-210-LH089-15-0 | LV1-105639.VU162 | 394 |  |  | MC1 | LVL 5 | Tt-6 | TR018_2 | 2024-05-17 | 2024-05-22 | 2024-05-22 |  | 2024-06-17 |  | Büro | 2024-06-28 |  | 2024-06-20 |  |  |  | 2024-10-10 | 937 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-11-01 | 2024-11-01
51590 | 740-WFI-VU162-211-LH089-15-0 | 1 | true | 0 | 740-WFI-VU162-211-LH089-15-0 | LV1-105639.VU162 | 394 |  |  | MC1 | LVL 5 | Tt-6 | TR018_2 | 2024-05-17 | 2024-05-22 | 2024-05-22 | [10 empty] | 2024-10-18 | 937 | 150 |  | 2024-11-13 | 2024-10-31 | 149 | SEP | SEP |  |  | 2024-11-01 | 2024-11-01
51591 | 740-WFI-VU162-212-LH089-15-0 | 1 | true | 0 | 740-WFI-VU162-212-LH089-15-0 | LV1-105639.VU162 | 394 |  |  | MC1 | LVL 5 | Tt-6 | TR018_2 | 2024-05-17 | 2024-05-22 | 2024-05-22 | [10 empty] | 2024-10-18 | 937 | 150 |  | 2024-11-13 | 2024-10-31 | 149 | SEP | SEP |  |  | 2024-11-01 | 2024-11-01
51592 | 740-WFI-VU162-213-LH089-15-0 | 1 | true | 0 | 740-WFI-VU162-213-LH089-15-0 | LV1-105639.VU162 | 394 |  |  | MC1 | LVL 5 | Tt-6 | TR018_2 | 2024-05-17 | 2024-05-22 | 2024-05-22 | [10 empty] | 2024-10-18 | 937 | 150 |  | 2024-11-13 | 2024-10-31 | 149 | SEP | SEP |  |  | 2024-11-01 | 2024-11-01
51593 | 740-WFI-VU162-214-LH089-8-0 | 1 | true | 0.5 | 740-WFI-VU162-214-LH089-8-0 | LV1-105639.VU162 | 394 |  |  | MC1 | LVL 5 | N/A | TR018_2 | 2024-05-17 | 2024-05-22 | 2024-05-22 |  | 2024-07-25 | 2024-07-25 |  | 2024-08-02 |  | 2024-07-31 |  |  |  | 2024-11-08 | 937 | 150 |  | 2024-11-13 |  | 149 | SEP | SEP
51594 | 740-WFI-VU162-215-LH089-8-0 | 1 | true | 0.5 | 740-WFI-VU162-215-LH089-8-0 | LV1-105639.VU162 | 394 |  |  | MC1 | LVL 5 | N/A | TR018_2 | 2024-05-17 | 2024-05-22 | 2024-05-22 |  | 2024-07-25 | 2024-07-30 |  | 2024-08-02 |  | 2024-07-30 |  |  |  | 2024-11-08 | 937 | 150 |  | 2024-11-13 |  | 149 | SEP | SEP
51595 | 740-FLN-VP001-201-LH089-32-0 | 1 | true | 27.73 | 740-FLN-VP001-201-LH089-32-0 | LV1-105629.VP001 | 394 |  |  | MC1 | LVL 5 | Tt-6 | TR015_6 | 2024-05-20 | 2024-05-20 | 2024-05-20 |  | 2024-06-05 | 2024-06-06 | Büro | 2024-06-14 |  | 2024-06-13 | 2024-06-19 |  | 2024-06-21 | 2024-10-04 | 1258 | 150 |  |  | 2024-11-11 | 149 | SEP | SEP | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22
51596 | 740-FLN-VP002-201-LH089-32-0 | 1 | true | 25.64 | 740-FLN-VP002-201-LH089-32-0 | LV1-105629.VP002 | 394 |  |  | MC1 | LVL 5 | Tt-6 | TR015_6 | 2024-05-20 | 2024-05-20 | 2024-05-20 |  | 2024-06-04 | 2024-06-05 | Büro | 2024-06-14 |  | 2024-06-06 | 2024-06-19 |  | 2024-07-05 | 2024-10-04 | 1258 | 150 |  |  | 2024-11-11 | 149 | SEP | SEP | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22
51597 | 740-FLN-VP130-101-LH089-10-0 | 1 | true | 0.65 | 740-FLN-VP130-101-LH089-10-0 | LV1-105629.VP003 | 394 |  |  | MC1 | LVL 5 | Tt-6 | TR015_6 | 2024-05-20 | 2024-05-20 | 2024-05-20 |  | 2024-06-18 | 2024-06-19 | Büro | 2024-06-28 |  | 2024-06-21 | 2024-09-25 |  |  | 2024-10-30 | 1258 | 150 |  |  | 2024-10-31 | 149 | SEP | SEP |  |  | 2024-11-30 | 2024-11-30
51598 | 740-FLN-VP130-103-LH089-10-0 | 1 | true | 4.29 | 740-FLN-VP130-103-LH089-10-0 | LV1-105629.VP004 | 394 |  |  | MC1 | LVL 5 | Tt-6 | TR015_6 | 2024-05-20 | 2024-05-20 | 2024-05-20 |  | 2024-06-19 | 2024-06-20 | Büro | 2024-06-28 |  | 2024-06-21 | 2024-09-25 |  |  | 2024-10-04 | 1258 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-11-30 | 2024-11-30
51599 | 740-FLN-VP130-104-LH089-10-0 | 1 | true | 45.62 | 740-FLN-VP130-104-LH089-10-0 | LV1-105628.VP130 | 394 |  |  | MC1 | LVL 5 | Tt-6 | TR015_6 | 2024-05-20 | 2024-05-20 | 2024-05-20 |  | 2024-06-18 | 2024-06-19 | Satu Mare | 2024-06-28 |  | 2024-06-21 | 2024-07-23 | 2024-08-23 |  | 2024-10-18 | 1258 | 150 |  |  | 2024-10-29 | 149 | SEP | SEP |  |  | 2024-11-30 | 2024-11-30
51600 | 740-FLN-VP131-102-LH089-25-0 | 1 | true | 0.09 | 740-FLN-VP131-102-LH089-25-0 | LV1-105628.VP131 | 394 |  |  | MC1 | LVL 5 | Tt-6 | TR015_6 | 2024-05-20 | 2024-05-20 | 2024-05-20 |  | 2024-08-16 | 2024-08-20 | Dawid Mierzwa | 2024-08-23 |  | 2024-08-20 | 2024-11-06 |  |  | 2024-11-15 | 1258 | 150 |  |  |  | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
51601 | 740-FLN-VP131-108-LH089-10-0 | 1 | true | 0.19 | 740-FLN-VP131-108-LH089-10-0 | LV1-105628.VP131 | 394 |  |  | MC1 | LVL 5 | W23 | TR015_6 | 2024-05-20 | 2024-05-20 | 2024-05-20 |  | 2024-07-02 | 2024-07-10 | Dawid Mierzwa | 2024-07-12 |  | 2024-07-10 | 2024-11-06 |  |  | 2024-11-08 | 1258 | 150 |  |  |  | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
51602 | 740-FLN-VP131-116-LH089-25-0 | 1 | true | 0.54 | 740-FLN-VP131-116-LH089-25-0 | LV1-105628.VP051 | 394 |  |  | MC1 | LVL 5 | Tt-6 | TR015_6 | 2024-05-20 | 2024-05-20 | 2024-05-20 |  | 2024-08-16 | 2024-08-20 | Dawid Mierzwa | 2024-08-23 |  | 2024-08-20 | 2024-11-06 |  |  | 2024-11-15 | 1258 | 150 |  |  |  | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
51603 | 740-FLN-VP132-102-LH089-32-0 | 1 | true | 15.45 | 740-FLN-VP132-102-LH089-32-0 | LV1-105628.VP051 | 394 |  |  | MC1 | LVL 5 | Tt-6 | TR015_6 | 2024-05-20 | 2024-05-20 | 2024-05-20 |  | 2024-07-02 | 2024-07-03 | Dawid Mierzwa | 2024-07-12 |  | 2024-07-05 | 2024-11-06 |  | 2024-07-26 | 2024-11-15 | 1258 | 150 |  |  |  | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
51604 | 740-FLN-VP132-106-LH089-32-0 | 1 | true | 0 | 740-FLN-VP132-106-LH089-32-0 | LV1-105628.VP132 | 394 |  |  | MC1 | LVL 5 | Tt-6 | TR015_6 | 2024-05-20 | 2024-05-20 | 2024-05-20 |  | 2024-07-18 | 2024-07-30 | Dawid Mierzwa | 2024-08-02 |  | 2024-07-30 | 2024-11-06 |  |  | 2024-11-15 | 1258 | 150 |  |  |  | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
51605 | 740-FLN-VP132-116-LH089-32-0 | 1 | true | 0.46 | 740-FLN-VP132-116-LH089-32-0 | LV1-105628.VP051 | 394 |  |  | MC1 | LVL 5 | Tt-6 | TR015_6 | 2024-05-20 | 2024-05-20 | 2024-05-20 |  | 2024-06-05 | 2024-06-06 | Dawid Mierzwa | 2024-06-14 |  | 2024-06-13 | 2024-11-06 |  |  | 2024-11-15 | 1258 | 150 |  |  |  | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
51606 | 740-FLN-VP133-103-LH089-25-0 | 1 | true | 0.1 | 740-FLN-VP133-103-LH089-25-0 | LV1-105628.VP133 | 394 |  |  | MC1 | LVL 5 | Tt-6 | TR015_6 | 2024-05-20 | 2024-05-20 | 2024-05-20 |  | 2024-08-16 | 2024-08-20 | Dawid Mierzwa | 2024-08-23 |  | 2024-08-20 | 2024-11-06 |  |  | 2024-11-15 | 1258 | 150 |  |  |  | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
51607 | 740-FLN-VP133-113-LH089-25-0 | 1 | true | 7.91 | 740-FLN-VP133-113-LH089-25-0 | LV1-105628.VP051 | 394 |  |  | MC1 | LVL 5 | Tt-6 | TR015_6 | 2024-05-20 | 2024-05-20 | 2024-05-20 |  | 2024-08-02 | 2024-08-21 | Dawid Mierzwa | 2024-08-23 |  | 2024-08-21 | 2024-11-06 |  |  | 2024-11-15 | 1258 | 150 |  |  |  | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
51608 | 740-FLN-VP133-114-LH089-25-0 | 1 | true | 0.37 | 740-FLN-VP133-114-LH089-25-0 | LV1-105628.VP051 | 394 |  |  | MC1 | LVL 5 | Tt-6 | TR015_6 | 2024-05-20 | 2024-05-20 | 2024-05-20 |  | 2024-08-16 | 2024-08-20 | Dawid Mierzwa | 2024-08-23 |  | 2024-08-20 | 2024-11-06 |  |  | 2024-11-15 | 1258 | 150 |  |  |  | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
51609 | 740-FLN-VP140-101-LH089-10-0 | 1 | true | 0.46 | 740-FLN-VP140-101-LH089-10-0 | LV1-105629.VP003 | 394 |  |  | MC1 | LVL 5 | Tt-6 | TR015_6 | 2024-05-20 | 2024-05-20 | 2024-05-20 |  | 2024-06-18 | 2024-06-19 | Büro | 2024-06-28 |  | 2024-06-21 | 2024-09-25 |  |  | 2024-10-24 | 1258 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-11-30 | 2024-11-30
51610 | 740-FLN-VP140-103-LH089-10-0 | 1 | true | 4.27 | 740-FLN-VP140-103-LH089-10-0 | LV1-105629.VP004 | 394 |  |  | MC1 | LVL 5 | Tt-6 | TR015_6 | 2024-05-20 | 2024-05-20 | 2024-05-20 |  | 2024-06-18 | 2024-06-19 | Büro | 2024-06-28 |  | 2024-06-21 | 2024-09-25 |  |  | 2024-10-10 | 1258 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-11-30 | 2024-11-30
51611 | 740-FLN-VP141-102-LH089-25-0 | 1 | true | 0.05 | 740-FLN-VP141-102-LH089-25-0 | LV1-105628.VP141 | 394 |  |  | MC1 | LVL 5 | Tt-6 | TR015_6 | 2024-05-20 | 2024-05-20 | 2024-05-20 |  | 2024-08-16 | 2024-08-20 | Büro | 2024-08-23 |  | 2024-08-20 |  |  |  | 2024-10-10 | 1258 | 150 |  |  |  | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
51612 | 740-FLN-VP141-108-LH089-10-0 | 1 | true | 0.33 | 740-FLN-VP141-108-LH089-10-0 | LV1-105628.VP141 | 394 |  |  | MC1 | LVL 5 | Tt-6 | TR015_6 | 2024-05-20 | 2024-05-20 | 2024-05-20 |  | 2024-07-29 | 2024-07-30 | Büro | 2024-08-02 |  | 2024-07-30 | 2024-10-24 |  |  | 2024-10-30 | 1258 | 150 |  |  | 2024-10-31 | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
51613 | 740-FLN-VP141-114-LH089-25-0 | 1 | true | 23.22 | 740-FLN-VP141-114-LH089-25-0 | LV1-105628.VP061 | 394 |  |  | MC1 | LVL 5 | Tt-6 | TR015_6 | 2024-05-20 | 2024-05-20 | 2024-05-20 |  | 2024-08-02 | 2024-08-21 | Dawid Mierzwa | 2024-08-23 |  | 2024-08-21 | 2024-09-23 |  |  | 2024-11-08 | 1258 | 150 |  |  |  | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
51614 | 740-FLN-VP141-115-LH089-10-0 | 1 | true | 5.94 | 740-FLN-VP141-115-LH089-10-0 | LV1-105628.VP147 | 394 |  |  | MC1 | LVL 5 | Tt-6 | TR015_6 | 2024-05-20 | 2024-05-20 | 2024-05-20 |  | 2024-06-17 | 2024-06-20 | Büro | 2024-06-28 |  | 2024-06-21 | 2024-10-24 |  |  | 2024-10-30 | 1258 | 150 |  |  | 2024-10-31 | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
51615 | 740-FLN-VP141-116-LH089-25-0 | 1 | true | 0.48 | 740-FLN-VP141-116-LH089-25-0 | LV1-105628.VP061 | 394 |  |  | MC1 | LVL 5 | Tt-6 | TR015_6 | 2024-05-20 | 2024-05-20 | 2024-05-20 |  | 2024-08-16 | 2024-08-20 | Satu Mare | 2024-08-23 |  | 2024-08-20 |  |  |  | 2024-11-08 | 1258 | 150 |  |  |  | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
51616 | 740-FLN-VP142-102-LH089-32-0 | 1 | true | 17.27 | 740-FLN-VP142-102-LH089-32-0 | LV1-105628.VP061 | 394 |  |  | MC1 | LVL 5 | Tt-6 | TR015_6 | 2024-05-20 | 2024-05-20 | 2024-05-20 |  | 2024-07-03 | 2024-07-09 | Dawid Mierzwa | 2024-07-12 |  | 2024-07-09 | 2024-09-23 |  |  | 2024-11-08 | 1258 | 150 |  |  |  | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
51617 | 740-FLN-VP142-106-LH089-32-0 | 1 | true | 0.05 | 740-FLN-VP142-106-LH089-32-0 | LV1-105628.VP142 | 394 |  |  | MC1 | LVL 5 | Tt-6 | TR015_6 | 2024-05-20 | 2024-05-20 | 2024-05-20 |  | 2024-06-06 | 2024-06-07 | Büro | 2024-06-14 |  | 2024-06-13 |  |  |  | 2024-10-10 | 1258 | 150 |  |  |  | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
51618 | 740-FLN-VP142-116-LH089-32-0 | 1 | true | 0.48 | 740-FLN-VP142-116-LH089-32-0 | LV1-105628.VP061 | 394 |  |  | MC1 | LVL 5 | Tt-6 | TR015_6 | 2024-05-20 | 2024-05-20 | 2024-05-20 |  | 2024-07-18 | 2024-07-30 | Satu Mare | 2024-08-02 |  | 2024-07-30 |  |  |  | 2024-11-08 | 1258 | 150 |  |  |  | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
51619 | 740-FLN-VP143-103-LH089-25-0 | 1 | false | 0.05 | 740-FLN-VP143-103-LH089-25-0 | LV1-105628.VP143 | 394 |  |  | MC1 | LVL 5 | Tt-6 | TR015_6 | 2024-05-20 | 2024-05-20 | 2024-05-20 |  | 2024-08-16 | 2024-08-20 | Büro | 2024-08-23 |  | 2024-08-20 |  |  |  | 2024-10-10 | 1258 | 150 |  |  |  | 149 | SEP | SEP
72124 | 740-FLN-VP143-103-LH089-25-0 | 2 | true | 0.05 | 740-FLN-VP143-103-LH089-25-0 | LV1-105628.VP143 | 394 |  |  | MC1 | LVL 5 | Tt-6 | TR042_1 | 2024-12-04 | 2024-05-20 | 2024-05-20 |  | 2024-08-16 | 2024-08-20 |  | 2024-08-23 |  | 2024-08-20 |  |  |  | 2024-10-10 | 1258 | 150 |  |  |  | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
51620 | 740-FLN-VP143-112-LH089-25-0 | 1 | false | 19.65 | 740-FLN-VP143-112-LH089-25-0 | LV1-105628.VP061 | 394 |  |  | MC1 | LVL 5 | Tt-6 | TR015_6 | 2024-05-20 | 2024-05-20 | 2024-05-20 |  | 2024-08-16 | 2024-08-20 | Dawid Mierzwa | 2024-08-23 |  | 2024-08-20 | 2024-09-23 |  |  | 2024-11-08 | 1258 | 150 |  |  |  | 149 | SEP | SEP
51621 | 740-FLN-VP143-116-LH089-25-0 | 1 | false | 0.48 | 740-FLN-VP143-116-LH089-25-0 | LV1-105628.VP061 | 394 |  |  | MC1 | LVL 5 | Tt-6 | TR015_6 | 2024-05-20 | 2024-05-20 | 2024-05-20 |  | 2024-08-16 | 2024-08-20 | Satu Mare | 2024-08-23 |  | 2024-08-20 |  |  |  | 2024-11-08 | 1258 | 150 |  |  |  | 149 | SEP | SEP
72126 | 740-FLN-VP143-116-LH089-25-0 | 2 | true | 0.48 | 740-FLN-VP143-116-LH089-25-0 | LV1-105628.VP061 | 394 |  |  | MC1 | LVL 5 | Tt-6 | TR042_1 | 2024-12-04 | 2024-05-20 | 2024-05-20 |  | 2024-08-16 | 2024-08-20 |  | 2024-08-23 |  | 2024-08-20 |  |  |  | 2024-11-08 | 1258 | 150 |  |  |  | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
51622 | 740-WAn-VP001-120-LH099-15-0 | 1 | false | 0.07 | 740-WAn-VP001-120-LH099-15-0 | LV0-105628.VP001 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-07-02 | 2024-07-04 | Satu Mare | 2024-07-12 |  | 2024-07-09 |  |  |  | 2024-10-18 | 1036 | 150 |  |  |  | 149 | SEP | SEP
62244 | 740-WAn-VP001-120-LH099-15-0 | 2 | true | 0.07 | 740-WAn-VP001-120-LH099-15-0 | LV0-105628.VP001 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR030_2 | 2024-07-25 | 2024-05-20 | 2024-05-21 |  | 2024-07-02 | 2024-07-04 |  | 2024-07-12 |  | 2024-07-09 | 2024-10-18 | 2024-10-18 | 2024-10-18 | 2024-10-18 | 1036 | 150 |  | 2024-11-13 |  | 149 | SEP | SEP
51623 | 740-WAn-VP001-121-LH099-32-0 | 1 | false | 2.77 | 740-WAn-VP001-121-LH099-32-0 | LV0-105628.VP001 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-07-23 | 2024-07-24 | Satu Mare | 2024-08-02 |  | 2024-07-26 |  |  |  |  | 1036 | 150 |  |  |  | 149 | SEP | SEP
62245 | 740-WAn-VP001-121-LH099-32-0 | 2 | true | 0.1 | 740-WAn-VP001-121-LH099-32-0 | LV0-105628.VP001 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR030_2 | 2024-07-25 | 2024-05-20 | 2024-05-21 |  | 2024-07-23 | [5 empty] | 2024-10-18 | 2024-10-18 | 2024-10-18 | 2024-10-18 | 1036 | 150 |  | 2024-11-13 | 2024-11-08 | 149 | SEP | SEP
51624 | 740-WAn-VP001-122-LH099-15-0 | 1 | false | 0.23 | 740-WAn-VP001-122-LH099-15-0 | LV0-105628.VP001 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-06-20 | 2024-07-25 | Büro | 2024-07-12 |  | 2024-07-01 |  |  |  | 2024-10-17 | 1036 | 150 |  |  |  | 149 | SEP | SEP
62246 | 740-WAn-VP001-122-LH099-15-0 | 2 | true | 0.3 | 740-WAn-VP001-122-LH099-15-0 | LV0-105628.VP001 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR030_2 | 2024-07-25 | 2024-05-20 | 2024-05-21 |  | 2024-06-20 | 2024-07-25 | Büro | 2024-07-12 |  | 2024-07-01 |  |  |  | 2024-10-17 | 1036 | 150 |  | 2024-11-13 | 2024-11-08 | 149 | SEP | SEP
51625 | 740-WAn-VP001-135-LH089-32-0 | 1 | true | 0.16 | 740-WAn-VP001-135-LH089-32-0 | LV0-105628.VP001 | 394 |  |  | MC1 | LVL 5 | Tt-6 | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-07-01 | 2024-07-02 | Satu Mare | 2024-07-12 |  | 2024-07-05 |  |  | 2024-09-06 | 2024-10-18 | 1036 | 150 |  |  | 2024-10-29 | 149 | SEP | SEP
51626 | 740-WAn-VP001-140-LH099-32-0 | 1 | true | 0.14 | 740-WAn-VP001-140-LH099-32-0 | LV0-105628.VP001 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-07-24 | 2024-07-24 | Büro | 2024-08-02 |  | 2024-07-26 |  |  |  | 2024-10-14 | 1036 | 150 |  | 2024-11-13 | 2024-11-08 | 149 | SEP | SEP
51627 | 740-WAn-VP002-120-LH099-15-0 | 1 | false | 0.07 | 740-WAn-VP002-120-LH099-15-0 | LV0-105628.VP002 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-07-23 | 2024-07-24 | Attila Henter | 2024-08-02 |  | 2024-07-25 | 2024-10-15 |  |  |  | 1036 | 150 |  |  |  | 149 | SEP | SEP
62247 | 740-WAn-VP002-120-LH099-15-0 | 2 | true | 0.07 | 740-WAn-VP002-120-LH099-15-0 | LV0-105628.VP002 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR030_2 | 2024-07-25 | 2024-05-20 | 2024-05-21 |  | 2024-07-23 | 2024-07-24 | Büro |  |  | 2024-07-25 | 2024-10-15 |  |  | 2024-10-17 | 1036 | 150 |  | 2024-11-13 | 2024-11-08 | 149 | SEP | SEP
51628 | 740-WAn-VP002-121-LH099-32-0 | 1 | false | 3.49 | 740-WAn-VP002-121-LH099-32-0 | LV0-105628.VP002 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-07-18 | 2024-07-24 | Attila Henter | 2024-08-02 |  | 2024-07-24 | 2024-10-15 |  |  |  | 1036 | 150 |  |  |  | 149 | SEP | SEP
62248 | 740-WAn-VP002-121-LH099-32-0 | 2 | true | 0.1 | 740-WAn-VP002-121-LH099-32-0 | LV0-105628.VP002 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR030_2 | 2024-07-25 | 2024-05-20 | 2024-05-21 |  | 2024-07-18 |  | Büro |  |  |  | 2024-10-15 |  |  | 2024-10-17 | 1036 | 150 |  | 2024-11-13 | 2024-11-11 | 149 | SEP | SEP
51629 | 740-WAn-VP002-122-LH099-15-0 | 1 | false | 0.23 | 740-WAn-VP002-122-LH099-15-0 | LV0-105628.VP002 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-06-20 | 2024-06-25 | Attila Henter | 2024-06-28 |  | 2024-06-26 | 2024-10-15 |  |  |  | 1036 | 150 |  |  |  | 149 | SEP | SEP
62249 | 740-WAn-VP002-122-LH099-15-0 | 2 | true | 0.23 | 740-WAn-VP002-122-LH099-15-0 | LV0-105628.VP002 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR030_2 | 2024-07-25 | 2024-05-20 | 2024-05-21 |  | 2024-06-20 | 2024-06-25 | Büro | 2024-06-28 |  | 2024-06-26 | 2024-10-15 |  |  | 2024-10-17 | 1036 | 150 |  | 2024-11-13 | 2024-11-11 | 149 | SEP | SEP
51630 | 740-WAn-VP002-135-LH089-32-0 | 1 | true | 0.16 | 740-WAn-VP002-135-LH089-32-0 | LV0-105628.VP002 | 394 |  |  | MC1 | LVL 5 | Tt-6 | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-07-18 | 2024-07-30 | Satu Mare | 2024-08-02 |  | 2024-07-30 |  |  | 2024-09-06 | 2024-10-18 | 1036 | 150 |  |  | 2024-10-29 | 149 | SEP | SEP
51631 | 740-WAn-VP002-140-LH099-32-0 | 1 | true | 0.08 | 740-WAn-VP002-140-LH099-32-0 | LV0-105628.VP002 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-07-24 | 2024-07-24 | Büro | 2024-08-02 |  | 2024-07-26 | 2024-10-15 |  |  | 2024-10-17 | 1036 | 150 |  | 2024-11-13 | 2024-11-11 | 149 | SEP | SEP
51632 | 740-WAn-VP003-122-LH099-15-0 | 1 | false | 0.1 | 740-WAn-VP003-122-LH099-15-0 | LV0-105628.VP003 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-07-23 | 2024-07-23 | Satu Mare | 2024-08-02 |  | 2024-07-25 |  |  |  | 2024-10-18 | 1036 | 150 |  |  |  | 149 | SEP | SEP
62250 | 740-WAn-VP003-122-LH099-15-0 | 2 | true | 0.1 | 740-WAn-VP003-122-LH099-15-0 | LV0-105628.VP003 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR030_2 | 2024-07-25 | 2024-05-20 | 2024-05-21 |  | 2024-07-23 | 2024-07-23 |  |  |  | 2024-07-25 | 2024-10-18 | 2024-10-18 | 2024-10-18 | 2024-10-18 | 1036 | 150 |  | 2024-11-13 |  | 149 | SEP | SEP
51633 | 740-WAn-VP003-123-LH099-20-0 | 1 | false | 3.18 | 740-WAn-VP003-123-LH099-20-0 | LV0-105628.VP003 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-06-26 | 2024-07-02 | Satu Mare | 2024-07-12 |  | 2024-07-08 |  |  |  |  | 1036 | 150 |  |  |  | 149 | SEP | SEP
62251 | 740-WAn-VP003-123-LH099-20-0 | 2 | true | 0 | 740-WAn-VP003-123-LH099-20-0 | LV0-105628.VP003 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR030_2 | 2024-07-25 | 2024-05-20 | 2024-05-21 |  | 2024-06-26 | 2024-07-02 |  | 2024-07-12 |  | 2024-07-08 |  |  |  | 2024-10-29 | 1036 | 150 |  | 2024-11-13 | 2024-11-11 | 149 | SEP | SEP
51634 | 740-WAn-VP003-124-LH099-15-0 | 1 | false | 0.44 | 740-WAn-VP003-124-LH099-15-0 | LV0-105628.VP003 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-06-20 | 2024-06-26 | Satu Mare | 2024-07-12 |  | 2024-07-01 |  |  |  | 2024-10-18 | 1036 | 150 |  |  |  | 149 | SEP | SEP
62252 | 740-WAn-VP003-124-LH099-15-0 | 2 | true | 0.44 | 740-WAn-VP003-124-LH099-15-0 | LV0-105628.VP003 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR030_2 | 2024-07-25 | 2024-05-20 | 2024-05-21 |  | 2024-06-20 | 2024-06-26 |  | 2024-07-12 |  | 2024-07-01 | 2024-10-18 | 2024-10-18 | 2024-10-18 | 2024-10-18 | 1036 | 150 |  | 2024-11-13 |  | 149 | SEP | SEP
51635 | 740-WAn-VP003-138-LH089-20-0 | 1 | true | 0.47 | 740-WAn-VP003-138-LH089-20-0 | LV0-105628.VP003 | 394 |  |  | MC1 | LVL 5 | Tt-6 | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-07-03 | 2024-07-10 |  | 2024-07-12 |  | 2024-07-10 | 2024-09-10 |  |  | 2024-10-18 | 1036 | 150 |  |  | 2024-10-29 | 149 | SEP | SEP
51636 | 740-WAn-VP003-140-LH099-32-0 | 1 | true | 0.15 | 740-WAn-VP003-140-LH099-32-0 | LV0-105628.VP003 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-07-23 | 2024-07-23 | Satu Mare | 2024-08-02 |  | 2024-07-25 |  |  |  | 2024-10-18 | 1036 | 150 |  |  | 2024-11-05 | 149 | SEP | SEP
51637 | 740-WAn-VP004-122-LH099-15-0 | 1 | false | 0.06 | 740-WAn-VP004-122-LH099-15-0 | LV0-105628.VP004 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-07-23 | 2024-07-24 | attila Henter | 2024-08-02 |  | 2024-07-25 | 2024-10-16 |  |  | 2024-10-18 | 1036 | 150 |  |  |  | 149 | SEP | SEP
62253 | 740-WAn-VP004-122-LH099-15-0 | 2 | true | 0.06 | 740-WAn-VP004-122-LH099-15-0 | LV0-105628.VP004 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR030_2 | 2024-07-25 | 2024-05-20 | 2024-05-21 |  | 2024-07-23 | 2024-07-24 | Attila Henter |  |  | 2024-07-25 | 2024-10-16 | 2024-10-18 | 2024-10-18 | 2024-10-18 | 1036 | 150 |  | 2024-11-13 |  | 149 | SEP | SEP
51638 | 740-WAn-VP004-123-LH099-20-0 | 1 | false | 2.81 | 740-WAn-VP004-123-LH099-20-0 | LV0-105628.VP004 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-06-26 | 2024-07-02 | attila Henter | 2024-07-12 |  | 2024-07-05 | 2024-10-16 |  |  |  | 1036 | 150 |  |  |  | 149 | SEP | SEP
62254 | 740-WAn-VP004-123-LH099-20-0 | 2 | true | 0 | 740-WAn-VP004-123-LH099-20-0 | LV0-105628.VP004 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR030_2 | 2024-07-25 | 2024-05-20 | 2024-05-21 |  | 2024-06-26 | 2024-07-02 | Attila Henter | 2024-07-12 |  | 2024-07-05 | 2024-10-16 | 2024-10-18 | 2024-10-18 | 2024-10-18 | 1036 | 150 |  | 2024-11-13 |  | 149 | SEP | SEP
51639 | 740-WAn-VP004-124-LH099-15-0 | 1 | false | 0.22 | 740-WAn-VP004-124-LH099-15-0 | LV0-105628.VP004 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-06-26 | 2024-06-27 | attila Henter | 2024-07-12 |  | 2024-07-01 | 2024-10-16 |  |  | 2024-10-21 | 1036 | 150 |  |  |  | 149 | SEP | SEP
62255 | 740-WAn-VP004-124-LH099-15-0 | 2 | true | 0.22 | 740-WAn-VP004-124-LH099-15-0 | LV0-105628.VP004 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR030_2 | 2024-07-25 | 2024-05-20 | 2024-05-21 |  | 2024-06-26 | 2024-06-27 | Attila Henter | 2024-07-12 |  | 2024-07-01 | 2024-10-16 | 2024-10-18 | 2024-10-18 | 2024-10-18 | 1036 | 150 |  |  |  | 149 | SEP | SEP
51640 | 740-WAn-VP004-138-LH089-20-0 | 1 | true | 0.51 | 740-WAn-VP004-138-LH089-20-0 | LV0-105628.VP004 | 394 |  |  | MC1 | LVL 5 | Tt-6 | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-07-02 | 2024-07-03 | Satu Mare | 2024-07-12 |  | 2024-07-10 |  |  |  | 2024-11-04 | 1036 | 150 |  |  |  | 149 | SEP | SEP
51641 | 740-WAn-VP004-138-LH099-20-0 | 1 | true | 0.51 | 740-WAn-VP004-138-LH099-20-0 | LV0-105628.VP004 | 394 |  |  | MC1 | LVL 5 | Tt-6 | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-07-18 | 2024-07-30 |  | 2024-08-02 |  | 2024-07-30 | 2024-09-10 |  |  | 2024-10-18 | 1036 | 150 |  |  | 2024-11-04 | 149 | SEP | SEP
51642 | 740-WAn-VP004-140-LH099-32-0 | 1 | true | 0.16 | 740-WAn-VP004-140-LH099-32-0 | LV0-105628.VP004 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-07-23 | 2024-07-24 | attila Henter | 2024-08-02 |  | 2024-07-30 | 2024-10-16 |  |  | 2024-10-18 | 1036 | 150 |  | 2024-11-13 | 2024-11-11 | 149 | SEP | SEP
51643 | 740-WAn-VP132-123-LH089-15-0 | 1 | true | 0.16 | 740-WAn-VP132-123-LH089-15-0 | LV1-105628.VP132 | 394 |  |  | MC1 | LVL 5 | Tt-12 | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-07-08 | 2024-07-09 | Büro | 2024-07-12 |  | 2024-07-09 | 2024-10-22 |  |  | 2024-10-30 | 1036 | 150 |  |  | 2024-10-31 | 149 | SEP | SEP
51644 | 740-WAn-VP132-125-LH099-15-0 | 1 | true | 0.42 | 740-WAn-VP132-125-LH099-15-0 | LV1-105628.VP132 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-07-22 | 2024-07-22 | Büro | 2024-08-02 |  | 2024-07-24 | 2024-10-18 |  |  | 2024-10-25 | 1036 | 150 |  |  | 2024-11-04 | 149 | SEP | SEP
51645 | 740-WAn-VP132-128-LH099-15-0 | 1 | true | 0 | 740-WAn-VP132-128-LH099-15-0 | LV1-105628.VP132 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-06-19 |  | Büro | 2024-06-28 |  | 2024-06-20 | 2024-10-18 |  |  | 2024-10-25 | 1036 | 150 |  |  | 2024-11-04 | 149 | SEP | SEP
51646 | 740-WAn-VP142-123-LH089-15-0 | 1 | true | 0.16 | 740-WAn-VP142-123-LH089-15-0 | LV1-105628.VP142 | 394 |  |  | MC1 | LVL 5 | Tt-12 | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-06-17 | 2024-06-18 | Büro | 2024-06-28 |  | 2024-06-20 | 2024-10-22 |  |  | 2024-10-30 | 1036 | 150 |  |  | 2024-10-31 | 149 | SEP | SEP
51647 | 740-WAn-VP142-125-LH099-15-0 | 1 | true | 0.39 | 740-WAn-VP142-125-LH099-15-0 | LV1-105628.VP142 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-07-23 | 2024-07-23 | Attila Henter | 2024-08-02 |  | 2024-07-25 | 2024-10-15 |  |  | 2024-10-21 | 1036 | 150 |  |  | 2024-11-05 | 149 | SEP | SEP
51648 | 740-WAn-VP142-128-LH099-15-0 | 1 | true | 0 | 740-WAn-VP142-128-LH099-15-0 | LV1-105628.VP142 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-07-30 |  | Attila Henter | 2024-08-02 |  | 2024-07-30 | 2024-10-15 |  |  | 2024-10-21 | 1036 | 150 |  |  | 2024-11-05 | 149 | SEP | SEP
51649 | 740-WAn-VS001-102-LH099-32-0 | 1 | true | 0.88 | 740-WAn-VS001-102-LH099-32-0 | LV1-105633.VS001 | 386 |  |  | MC1 | LVL 5 | W60 | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-07-23 | 2024-07-23 | Büro | 2024-08-02 |  | 2024-07-25 | 2024-10-17 |  |  | 2024-10-22 | 1036 | 150 |  |  | 2024-11-04 | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
51650 | 740-WAn-VS001-104-LH099-32-0 | 1 | true | 0.57 | 740-WAn-VS001-104-LH099-32-0 | LV1-105633.VS001 | 386 |  |  | MC1 | LVL 5 | W60 | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-07-24 |  | Büro | 2024-08-02 |  | 2024-07-25 | 2024-10-17 |  |  | 2024-10-22 | 1036 | 150 |  |  | 2024-11-04 | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
51651 | 740-WAn-VS001-108-LH099-15-0 | 1 | true | 0.44 | 740-WAn-VS001-108-LH099-15-0 | LV1-105633.VS001 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-06-26 | 2024-07-02 | Büro | 2024-07-12 |  | 2024-07-05 | 2024-10-17 |  |  | 2024-10-22 | 1036 | 150 |  |  | 2024-11-04 | 149 | SEP | SEP
51652 | 740-WAn-VS001-109-LH099-15-0 | 1 | true | 0.1 | 740-WAn-VS001-109-LH099-15-0 | LV1-105633.VS001 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-06-26 | 2024-07-02 | Büro | 2024-07-12 |  | 2024-07-05 | 2024-10-17 |  |  | 2024-10-22 | 1036 | 150 |  |  | 2024-11-04 | 149 | SEP | SEP
51653 | 740-WAn-VS001-110-LH099-50-0 | 1 | true | 1.03 | 740-WAn-VS001-110-LH099-50-0 | LV1-105633.VS001 | 386 |  |  | MC1 | LVL 5 | W60 | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-07-23 | 2024-07-26 | Büro | 2024-08-02 |  | 2024-07-30 | 2024-10-17 |  |  | 2024-10-22 | 1036 | 150 |  |  | 2024-10-30 | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
51654 | 740-WAn-VS001-111-LH099-15-0 | 1 | true | 1.4 | 740-WAn-VS001-111-LH099-15-0 | LV1-105633.VS001 | 386 |  |  | MC1 | LVL 5 | W60 | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-06-26 | 2024-07-02 | Büro | 2024-07-12 |  | 2024-07-05 | 2024-10-17 |  |  | 2024-10-22 | 1036 | 150 |  |  | 2024-11-04 | 149 | SEP | SEP
51655 | 740-WAn-VU200-101-LH032-150-0 | 1 | false | 30.23 | 740-WAn-VU200-101-LH032-150-0 | LV1-105638.VU200 | 385 |  |  | MC1 | Shaft | W60 | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-06-26 | 2024-07-03 | Büro | 2024-07-12 |  | 2024-07-05 | 2024-09-19 |  | 2024-08-09 | 2024-09-20 | 1259 | 150 |  |  |  | 149 | SEP | SEP
62257 | 740-WAn-VU200-101-LH032-150-0 | 2 | false | 30.4 | 740-WAn-VU200-101-LH032-150-0 | LV1-105638.VU200 | 385 |  |  | MC1 | Shaft | W60 | TR030_2 | 2024-07-25 | 2024-05-20 | 2024-05-21 |  | 2024-06-26 | 2024-07-03 | Büro | 2024-07-12 |  | 2024-07-05 | 2024-09-19 |  | 2024-08-09 | 2024-09-20 | 1259 | 150 |  | 2024-10-09 | 2024-09-25 | 149 | SEP | SEP | 2024-09-27 | 2024-10-04 | 2024-10-04
65866 | 740-WAn-VU200-101-LH032-150-0 | 3 | true | 30.4 | 740-WAn-VU200-101-LH032-150-0 | LV1-105638.VU200 | 385 |  |  | MC1 | Shaft | W60 | TR038_2 | 2024-10-15 | 2024-05-20 | 2024-05-21 |  | 2024-06-26 | 2024-07-03 | Attila Henter | 2024-07-12 |  | 2024-07-05 | 2024-10-16 |  | 2024-08-09 | 2024-10-18 | 1259 | 150 |  | 2024-10-25 | 2024-09-25 | 149 | SEP | SEP | 2024-11-08 | 2024-11-08 | 2024-11-08
51656 | 740-WAn-VU200-105-LH099-40-0 | 1 | false | 0.56 | 740-WAn-VU200-105-LH099-40-0 | LV0-105628.VP032 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  |  |  | Satu Mare | [7 empty] | 1036 | 150 |  |  |  | 149 | SEP | SEP
52790 | 740-WAn-VU200-105-LH099-40-0 | 2 | true | 0.56 | 740-WAn-VU200-105-LH099-40-0 | LV0-105628.VP032 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR025_1 | 2024-06-18 | 2024-05-20 | 2024-05-21 |  | 2024-06-26 | 2024-07-04 | Attila Henter | 2024-07-12 |  | 2024-07-05 | 2024-10-16 |  |  | 2024-10-18 | 1036 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
51657 | 740-WAn-VU200-113-LH099-40-0 | 1 | true | 0.71 | 740-WAn-VU200-113-LH099-40-0 | LV2-105633.VS627 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-07-18 | 2024-07-22 | Büro | 2024-08-02 |  | 2024-07-24 | 2024-09-25 |  |  | 2024-09-27 | 1036 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
51658 | 740-WAn-VU200-117-LH032-40-0 | 1 | true | 1.91 | 740-WAn-VU200-117-LH032-40-0 | LV0-105638.VU200 | 385 |  |  | MC1 | LVL 4 | N/A | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-07-18 | 2024-07-22 | Büro | 2024-08-02 |  | 2024-07-24 | 2024-08-27 |  |  | 2024-08-28 | 914 | 150 |  |  |  | 149 | SEP | SEP
51659 | 740-WAn-VU200-118-LH099-50-0 | 1 | true | 1.3 | 740-WAn-VU200-118-LH099-50-0 | LV1-105628.VP134 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-07-23 | 2024-07-25 | Büro | 2024-08-02 |  | 2024-07-26 | 2024-10-18 |  |  | 2024-10-23 | 1036 | 150 |  |  | 2024-10-30 | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
51660 | 740-WAn-VU200-120-LH032-40-0 | 1 | true | 1.87 | 740-WAn-VU200-120-LH032-40-0 | LV0-105638.VU200 | 385 |  |  | MC1 | LVL 4 | N/A | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-07-18 | 2024-07-22 | Büro | 2024-08-02 |  | 2024-07-24 | 2024-08-27 |  |  | 2024-08-28 | 914 | 150 |  |  |  | 149 | SEP | SEP
51661 | 740-WAn-VU200-121-LH032-50-0 | 1 | true | 6.76 | 740-WAn-VU200-121-LH032-50-0 | LV0-105638.VU200 | 385 |  |  | MC1 | LVL 4 | W60 | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-07-01 | 2024-07-30 | Büro | 2024-08-02 |  | 2024-07-31 | 2024-08-26 |  |  | 2024-08-28 | 914 | 150 |  |  |  | 149 | SEP | SEP
51662 | 740-WAn-VU200-123-LH032-25-0 | 1 | true | 6.38 | 740-WAn-VU200-123-LH032-25-0 | LV0-105638.VU200 | 385 |  |  | MC1 | LVL 4 | N/A | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-06-19 | 2024-06-21 | Satu Mare | 2024-07-12 |  | 2024-07-05 | 2024-07-29 |  |  | 2024-07-31 | 914 | 150 |  |  |  | 149 | SEP | SEP
51663 | 740-WAn-VU200-132-LH032-32-0 | 1 | true | 3.75 | 740-WAn-VU200-132-LH032-32-0 | LV0-105638.VU200 | 385 |  |  | MC1 | LVL 4 | N/A | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-07-19 | 2024-07-22 | Büro | 2024-08-02 |  | 2024-07-23 | 2024-08-27 |  |  | 2024-08-28 | 914 | 150 |  |  |  | 149 | SEP | SEP
51664 | 740-WAn-VU200-134-LH032-40-0 | 1 | true | 0.49 | 740-WAn-VU200-134-LH032-40-0 | LV0-105638.VU200 | 385 |  |  | MC1 | LVL 4 | N/A | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-06-27 | 2024-07-03 | Büro | 2024-07-12 |  | 2024-07-05 | 2024-08-27 |  |  | 2024-08-28 | 914 | 150 |  |  |  | 149 | SEP | SEP
51665 | 740-WAn-VU200-136-LH032-32-0 | 1 | true | 0.5 | 740-WAn-VU200-136-LH032-32-0 | LV0-105638.VU200 | 385 |  |  | MC1 | LVL 4 | N/A | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-07-18 | 2024-07-19 | Büro | 2024-08-02 |  | 2024-07-23 | 2024-08-27 |  |  | 2024-08-28 | 914 | 150 |  |  |  | 149 | SEP | SEP
51666 | 740-WAn-VU200-140-LH099-40-0 | 1 | true | 0.66 | 740-WAn-VU200-140-LH099-40-0 | LV2-105633.VS629 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-06-19 | 2024-06-20 | Büro | 2024-07-12 |  | 2024-07-02 | 2024-09-10 |  |  | 2024-09-12 | 1036 | 150 |  |  | 2024-09-12 | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
51667 | 740-WAn-VU200-146-LH032-65-0 | 1 | true | 7.02 | 740-WAn-VU200-146-LH032-65-0 | LV0-105638.VU200 | 385 |  |  | MC1 | LVL 4 | N/A | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-06-19 | 2024-06-21 | Büro | 2024-06-28 |  | 2024-06-25 | 2024-07-11 |  |  | 2024-07-16 | 914 | 150 |  |  |  | 149 | SEP | SEP
51668 | 740-WAn-VU200-151-LH032-40-0 | 1 | true | 1.46 | 740-WAn-VU200-151-LH032-40-0 | LV0-105638.VU200 | 385 |  |  | MC1 | LVL 4 | N/A | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-06-27 | 2024-07-03 | Büro | 2024-07-12 |  | 2024-07-10 | 2024-08-05 |  |  | 2024-08-08 | 914 | 150 |  |  |  | 149 | SEP | SEP
51669 | 740-WAn-VU200-153-LH099-32-0 | 1 | false | 0.44 | 740-WAn-VU200-153-LH099-32-0 | LV0-105628.VP001 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-07-22 | 2024-07-22 | Satu Mare | 2024-08-02 |  | 2024-07-23 |  |  |  | 2024-10-18 | 1036 | 150 |  |  |  | 149 | SEP | SEP
62259 | 740-WAn-VU200-153-LH099-32-0 | 2 | true | 3.8 | 740-WAn-VU200-153-LH099-32-0 | LV0-105628.VP001 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR030_2 | 2024-07-25 | 2024-05-20 | 2024-05-21 |  | 2024-07-22 | 2024-07-22 |  |  |  | 2024-07-23 | 2024-10-18 | 2024-10-18 | 2024-10-18 | 2024-10-18 | 1036 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
51670 | 740-WAn-VU200-154-LH099-32-0 | 1 | false | 0.44 | 740-WAn-VU200-154-LH099-32-0 | LV0-105628.VP002 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-07-22 | 2024-07-22 | Büro | 2024-08-02 |  | 2024-07-23 | 2024-10-15 |  |  | 2024-10-17 | 1036 | 150 |  |  |  | 149 | SEP | SEP
62260 | 740-WAn-VU200-154-LH099-32-0 | 2 | true | 3.9 | 740-WAn-VU200-154-LH099-32-0 | LV0-105628.VP002 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR030_2 | 2024-07-25 | 2024-05-20 | 2024-05-21 |  | 2024-07-22 | 2024-07-22 | Büro |  |  | 2024-07-23 | 2024-10-15 |  |  | 2024-10-17 | 1036 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
51671 | 740-WAn-VU200-156-LH032-50-0 | 1 | true | 1.21 | 740-WAn-VU200-156-LH032-50-0 | LV0-105638.VU200 | 385 |  |  | MC1 | LVL 4 | N/A | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-06-19 | 2024-06-20 | Büro | 2024-06-28 |  | 2024-06-26 | 2024-07-15 |  |  | 2024-07-16 | 914 | 150 |  |  |  | 149 | SEP | SEP
51672 | 740-WAn-VU200-162-LH032-40-0 | 1 | true | 1.67 | 740-WAn-VU200-162-LH032-40-0 | LV0-105638.VU200 | 385 |  |  | MC1 | LVL 4 | N/A | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-06-28 | 2024-07-01 | Büro | 2024-07-12 |  | 2024-07-03 | 2024-08-05 |  |  | 2024-08-06 | 914 | 150 |  |  |  | 149 | SEP | SEP
51673 | 740-WAn-VU200-163-LH032-65-0 | 1 | true | 7.04 | 740-WAn-VU200-163-LH032-65-0 | LV0-105638.VU200 | 385 |  |  | MC1 | LVL 4 | N/A | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-06-19 | 2024-06-21 | Büro | 2024-06-28 |  | 2024-06-25 | 2024-08-28 |  |  | 2024-09-03 | 914 | 150 |  |  | 2024-09-17 | 149 | SEP | SEP
51674 | 740-WAn-VU200-167-LH099-32-0 | 1 | false | 0.48 | 740-WAn-VU200-167-LH099-32-0 | LV0-105628.VP003 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-07-22 | 2024-07-22 | Satu Mare | 2024-08-02 |  | 2024-07-23 |  |  |  | 2024-10-18 | 1036 | 150 |  |  |  | 149 | SEP | SEP
62261 | 740-WAn-VU200-167-LH099-32-0 | 2 | true | 3.4 | 740-WAn-VU200-167-LH099-32-0 | LV0-105628.VP003 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR030_2 | 2024-07-25 | 2024-05-20 | 2024-05-21 |  | 2024-07-22 | 2024-07-22 |  |  |  | 2024-07-23 |  |  |  | 2024-11-05 | 1036 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
51675 | 740-WAn-VU200-168-LH032-40-0 | 1 | true | 1.01 | 740-WAn-VU200-168-LH032-40-0 | LV0-105638.VU200 | 385 |  |  | MC1 | LVL 4 | N/A | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-06-27 | 2024-07-04 | Büro | 2024-07-12 |  | 2024-07-10 | 2024-08-08 |  |  | 2024-08-28 | 914 | 150 |  |  |  | 149 | SEP | SEP
51676 | 740-WAn-VU200-169-LH032-32-0 | 1 | true | 1 | 740-WAn-VU200-169-LH032-32-0 | LV0-105638.VU200 | 385 |  |  | MC1 | LVL 4 | N/A | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-07-18 | 2024-07-22 | Büro | 2024-08-02 |  | 2024-07-24 | 2024-09-05 |  |  | 2024-09-12 | 914 | 150 |  |  | 2024-09-12 | 149 | SEP | SEP
51677 | 740-WAn-VU200-170-LH032-32-0 | 1 | true | 0.89 | 740-WAn-VU200-170-LH032-32-0 | LV0-105638.VU200 | 385 |  |  | MC1 | LVL 4 | N/A | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-07-18 | 2024-07-19 | Büro | 2024-08-02 |  | 2024-07-22 | 2024-09-05 |  |  | 2024-09-12 | 914 | 150 |  |  | 2024-09-12 | 149 | SEP | SEP
51678 | 740-WAn-VU200-171-LH032-32-0 | 1 | true | 1.9 | 740-WAn-VU200-171-LH032-32-0 | LV0-105638.VU200 | 385 |  |  | MC1 | LVL 4 | N/A | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-07-18 | 2024-07-18 | Büro | 2024-08-02 |  | 2024-07-23 | 2024-09-05 |  |  | 2024-09-12 | 914 | 150 |  |  | 2024-09-12 | 149 | SEP | SEP
51679 | 740-WAn-VU200-172-LH032-32-0 | 1 | true | 1.01 | 740-WAn-VU200-172-LH032-32-0 | LV0-105638.VU200 | 385 |  |  | MC1 | LVL 4 | N/A | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-07-18 |  | Büro | 2024-08-02 |  |  | 2024-09-23 |  |  | 2024-10-02 | 914 | 150 |  |  | 2024-10-02 | 149 | SEP | SEP
51680 | 740-WAn-VU200-175-LH032-32-0 | 1 | true | 0.68 | 740-WAn-VU200-175-LH032-32-0 | LV0-105638.VU200 | 385 |  |  | MC1 | LVL 4 | N/A | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-07-18 | 2024-07-22 | Büro | 2024-08-02 |  | 2024-07-24 | 2024-09-23 |  |  | 2024-10-02 | 914 | 150 |  |  | 2024-10-02 | 149 | SEP | SEP
51681 | 740-WAn-VU200-177-LH032-32-0 | 1 | true | 0.91 | 740-WAn-VU200-177-LH032-32-0 | LV0-105638.VU200 | 385 |  |  | MC1 | LVL 4 | N/A | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-07-18 | 2024-07-19 | Büro | 2024-08-02 |  | 2024-07-22 | 2024-09-23 |  |  | 2024-09-27 | 914 | 150 |  |  |  | 149 | SEP | SEP
51682 | 740-WAn-VU200-179-LH032-32-0 | 1 | true | 0.93 | 740-WAn-VU200-179-LH032-32-0 | LV0-105638.VU200 | 385 |  |  | MC1 | LVL 4 | N/A | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-07-18 | 2024-07-19 | Büro | 2024-08-02 |  | 2024-07-22 | 2024-09-23 |  |  | 2024-09-27 | 914 | 150 |  |  |  | 149 | SEP | SEP
51683 | 740-WAn-VU200-180-LH032-32-0 | 1 | true | 0.95 | 740-WAn-VU200-180-LH032-32-0 | LV0-105638.VU200 | 385 |  |  | MC1 | LVL 4 | N/A | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-07-18 | 2024-07-19 | Büro | 2024-08-02 |  | 2024-07-22 | 2024-09-23 |  |  | 2024-09-27 | 914 | 150 |  |  |  | 149 | SEP | SEP
51684 | 740-WAn-VU200-184-LH032-32-0 | 1 | true | 2.1 | 740-WAn-VU200-184-LH032-32-0 | LV0-105638.VU200 | 385 |  |  | MC1 | LVL 4 | N/A | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-07-18 | 2024-07-22 | Büro | 2024-08-02 |  | 2024-07-24 | 2024-09-04 |  |  | 2024-09-05 | 914 | 150 |  |  | 2024-09-09 | 149 | SEP | SEP
51685 | 740-WAn-VU200-187-LH099-32-0 | 1 | false | 0.48 | 740-WAn-VU200-187-LH099-32-0 | LV0-105628.VP004 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-07-18 | 2024-07-19 | attila Henter | 2024-08-02 |  | 2024-07-22 | 2024-10-16 |  |  | 2024-10-18 | 1036 | 150 |  |  |  | 149 | SEP | SEP
62262 | 740-WAn-VU200-187-LH099-32-0 | 2 | true | 3.3 | 740-WAn-VU200-187-LH099-32-0 | LV0-105628.VP004 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR030_2 | 2024-07-25 | 2024-05-20 | 2024-05-21 |  | 2024-07-18 | 2024-07-19 | Attila Henter |  |  | 2024-07-22 | 2024-10-16 | 2024-10-18 | 2024-10-18 | 2024-10-18 | 1036 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
51686 | 740-WAn-VU200-188-LH032-32-0 | 1 | true | 2.22 | 740-WAn-VU200-188-LH032-32-0 | LV0-105638.VU200 | 385 |  |  | MC1 | LVL 4 | N/A | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-07-18 | 2024-07-19 | Büro | 2024-08-02 |  | 2024-07-23 | 2024-08-28 |  |  | 2024-09-03 | 914 | 150 |  |  | 2024-09-09 | 149 | SEP | SEP
51687 | 740-WAn-VU200-189-LH032-32-0 | 1 | true | 1.44 | 740-WAn-VU200-189-LH032-32-0 | LV0-105638.VU200 | 385 |  |  | MC1 | LVL 4 | N/A | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-07-19 | 2024-07-22 | Büro | 2024-08-02 |  | 2024-07-24 | 2024-08-28 |  |  | 2024-09-03 | 914 | 150 |  |  | 2024-09-09 | 149 | SEP | SEP
51688 | 740-WAn-VU200-193-LH032-15-0 | 1 | true | 1 | 740-WAn-VU200-193-LH032-15-0 | LV0-105638.VU200 | 385 |  |  | MC1 | LVL 4 | N/A | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-06-28 | 2024-07-02 | Büro | 2024-07-12 |  | 2024-07-03 | 2024-08-28 |  |  | 2024-09-03 | 914 | 150 |  |  | 2024-09-09 | 149 | SEP | SEP
51689 | 740-WAn-VU200-194-LH032-15-0 | 1 | true | 5.34 | 740-WAn-VU200-194-LH032-15-0 | LV0-105638.VU200 | 385 |  |  | MC1 | LVL 4 | N/A | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-06-19 | 2024-06-20 | Satu Mare | 2024-06-28 |  | 2024-06-26 | 2024-07-19 |  |  | 2024-07-31 | 914 | 150 |  |  |  | 149 | SEP | SEP
51690 | 740-WAn-VU200-195-LH032-15-0 | 1 | true | 4.59 | 740-WAn-VU200-195-LH032-15-0 | LV0-105638.VU200 | 385 |  |  | MC1 | LVL 4 | N/A | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-06-28 | 2024-07-02 | Büro | 2024-07-12 |  | 2024-07-03 | 2024-08-26 |  |  | 2024-09-03 | 914 | 150 |  |  | 2024-09-17 | 149 | SEP | SEP
51691 | 740-WAn-VU200-196-LH032-32-0 | 1 | true | 1.86 | 740-WAn-VU200-196-LH032-32-0 | LV0-105638.VU200 | 385 |  |  | MC1 | LVL 4 | N/A | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-07-18 | 2024-07-19 | Büro | 2024-08-02 |  | 2024-07-22 | 2024-09-23 |  |  | 2024-10-12 | 914 | 150 |  |  |  | 149 | SEP | SEP
51692 | 740-WAn-VU200-197-LH032-15-0 | 1 | true | 3.67 | 740-WAn-VU200-197-LH032-15-0 | LV0-105638.VU200 | 385 |  |  | MC1 | LVL 4 | N/A | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-06-19 | 2024-06-20 | Büro | 2024-06-28 |  | 2024-06-25 | 2024-09-23 |  |  | 2024-10-11 | 914 | 150 |  |  |  | 149 | SEP | SEP
51693 | 740-WAn-VU200-198-LH032-15-0 | 1 | true | 11.77 | 740-WAn-VU200-198-LH032-15-0 | LV0-105638.VU200 | 385 |  |  | MC1 | LVL 4 | N/A | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-06-19 | 2024-06-20 | Büro | 2024-06-28 |  | 2024-06-26 | 2024-07-29 |  |  | 2024-10-11 | 914 | 150 |  |  |  | 149 | SEP | SEP
51694 | 740-WAn-VU200-199-LH032-32-0 | 1 | true | 1.34 | 740-WAn-VU200-199-LH032-32-0 | LV0-105638.VU200 | 385 |  |  | MC1 | LVL 4 | N/A | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-07-19 | 2024-07-22 | Büro | 2024-08-02 |  | 2024-07-24 | 2024-08-26 |  |  | 2024-09-03 | 914 | 150 |  |  | 2024-09-09 | 149 | SEP | SEP
51695 | 740-WAn-VU200-201-LH032-15-0 | 1 | true | 0.82 | 740-WAn-VU200-201-LH032-15-0 | LV0-105638.VU200 | 385 |  |  | MC1 | LVL 4 | N/A | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-06-28 | 2024-07-02 | Büro | 2024-07-12 |  | 2024-07-04 | 2024-08-08 |  |  | 2024-09-03 | 914 | 150 |  |  | 2024-09-09 | 149 | SEP | SEP
51696 | 740-WAn-VU200-227-LH032-65-0 | 1 | true | 8.83 | 740-WAn-VU200-227-LH032-65-0 | LV1-105639.VU200 | 385 |  |  | MC1 | LVL 4 | N/A | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-06-19 | 2024-06-21 | Büro | 2024-06-28 |  | 2024-06-25 | 2024-07-15 |  |  | 2024-10-15 | 915 | 150 |  |  |  | 149 | SEP | SEP
51697 | 740-WAn-VU200-229-LH032-65-0 | 1 | true | 3.88 | 740-WAn-VU200-229-LH032-65-0 | LV1-105639.VU200 | 385 |  |  | MC1 | LVL 4 | N/A | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-06-19 | 2024-06-21 | Büro | 2024-06-28 |  | 2024-06-25 | 2024-09-23 |  |  | 2024-10-11 | 915 | 150 |  |  |  | 149 | SEP | SEP
51698 | 740-WAn-VU200-230-LH032-65-0 | 1 | true | 2.59 | 740-WAn-VU200-230-LH032-65-0 | LV1-105639.VU200 | 385 |  |  | MC1 | LVL 4 | N/A | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-06-19 | 2024-06-19 | Büro | 2024-06-28 |  | 2024-06-25 | 2024-08-08 |  |  | 2024-08-12 | 915 | 150 |  |  |  | 149 | SEP | SEP
51699 | 740-WAn-VU200-231-LH032-40-0 | 1 | true | 4.43 | 740-WAn-VU200-231-LH032-40-0 | LV1-105639.VU200 | 385 |  |  | MC1 | LVL 4 | N/A | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-06-28 | 2024-07-01 | Büro | 2024-07-12 |  | 2024-07-03 | 2024-08-08 |  |  | 2024-08-12 | 915 | 150 |  |  |  | 149 | SEP | SEP
51700 | 740-WAn-VU200-232-LH032-40-0 | 1 | true | 4.25 | 740-WAn-VU200-232-LH032-40-0 | LV1-105639.VU200 | 385 |  |  | MC1 | LVL 4 | N/A | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-07-01 | 2024-07-08 | Büro | 2024-07-12 |  | 2024-07-10 | 2024-08-08 |  |  | 2024-08-12 | 915 | 150 |  |  |  | 149 | SEP | SEP
51701 | 740-WAn-VU200-233-LH032-40-0 | 1 | true | 4.22 | 740-WAn-VU200-233-LH032-40-0 | LV1-105639.VU200 | 385 |  |  | MC1 | LVL 4 | N/A | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-07-01 | 2024-07-05 | Büro | 2024-07-12 |  | 2024-07-09 | 2024-09-23 |  |  | 2024-10-12 | 915 | 150 |  |  |  | 149 | SEP | SEP
51702 | 740-WAn-VU200-235-LH032-65-0 | 1 | true | 1.42 | 740-WAn-VU200-235-LH032-65-0 | LV1-105639.VU200 | 385 |  |  | MC1 | LVL 4 | N/A | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-06-19 | 2024-06-20 | Büro | 2024-06-28 |  | 2024-06-25 | 2024-08-28 |  |  | 2024-09-03 | 915 | 150 |  |  | 2024-09-17 | 149 | SEP | SEP
51703 | 740-WAn-VU200-237-LH032-65-0 | 1 | true | 1 | 740-WAn-VU200-237-LH032-65-0 | LV1-105639.VU200 | 385 |  |  | MC1 | LVL 4 | N/A | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-07-01 | 2024-07-02 | Büro | 2024-07-12 |  | 2024-07-08 | 2024-08-28 |  |  | 2024-09-03 | 915 | 150 |  |  | 2024-09-17 | 149 | SEP | SEP
51704 | 740-WAn-VU200-238-LH032-65-0 | 1 | true | 3.31 | 740-WAn-VU200-238-LH032-65-0 | LV1-105639.VU200 | 385 |  |  | MC1 | LVL 4 | N/A | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-07-01 | 2024-07-02 | Büro | 2024-07-12 |  | 2024-07-04 | 2024-09-23 |  |  | 2024-10-11 | 915 | 150 |  |  |  | 149 | SEP | SEP
51705 | 740-WAn-VU200-239-LH032-40-0 | 1 | true | 6.98 | 740-WAn-VU200-239-LH032-40-0 | LV1-105639.VU200 | 385 |  |  | MC1 | LVL 4 | N/A | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-06-20 | 2024-06-21 | Büro | 2024-06-28 |  | 2024-06-25 | 2024-09-23 |  |  | 2024-09-30 | 915 | 150 |  |  | 2024-09-30 | 149 | SEP | SEP
51706 | 740-WAn-VU200-245-LH032-65-0 | 1 | true | 1.48 | 740-WAn-VU200-245-LH032-65-0 | LV1-105639.VU200 | 385 |  |  | MC1 | LVL 4 | N/A | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-07-02 | 2024-07-09 | Büro | 2024-07-12 |  | 2024-07-11 | 2024-09-05 |  |  | 2024-09-12 | 915 | 150 |  |  | 2024-09-12 | 149 | SEP | SEP
51707 | 740-WAn-VU200-249-LH032-40-0 | 1 | false | 10.81 | 740-WAn-VU200-249-LH032-40-0 | LV1-105639.VU200 | 385 |  |  | MC1 | LVL 4 | N/A | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-06-20 | 2024-06-25 |  | 2024-06-28 |  | 2024-06-26 | 2024-07-11 |  |  | 2024-07-30 | 915 | 150 |  |  |  | 149 | SEP | SEP
63296 | 740-WAn-VU200-249-LH032-40-0 | 2 | true | 10.81 | 740-WAn-VU200-249-LH032-40-0 | LV1-105639.VU200 | 385 |  |  | MC1 | LVL 4 | N/A | TR034_1 | 2024-08-21 | 2024-05-20 | 2024-05-21 |  | 2024-06-20 | 2024-06-25 |  | 2024-06-28 |  | 2024-06-26 | 2024-07-11 |  |  | 2024-07-30 | 915 | 150 |  |  |  | 149 | SEP | SEP
51708 | 740-WAn-VU200-253-LH032-40-0 | 1 | true | 1.93 | 740-WAn-VU200-253-LH032-40-0 | LV1-105639.VU200 | 385 |  |  | MC1 | LVL 4 | N/A | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-07-01 | 2024-07-05 | Büro | 2024-07-12 |  | 2024-07-09 | 2024-08-05 |  |  | 2024-08-06 | 915 | 150 |  |  |  | 149 | SEP | SEP
51709 | 740-WAn-VU200-255-LH032-65-0 | 1 | true | 6.46 | 740-WAn-VU200-255-LH032-65-0 | LV1-105639.VU200 | 385 |  |  | MC1 | LVL 4 | N/A | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-07-02 | 2024-07-09 | Büro | 2024-07-12 |  | 2024-07-11 | 2024-08-05 |  |  | 2024-08-08 | 915 | 150 |  |  |  | 149 | SEP | SEP
51710 | 740-WAn-VU200-257-LH032-40-0 | 1 | true | 3.94 | 740-WAn-VU200-257-LH032-40-0 | LV1-105639.VU200 | 385 |  |  | MC1 | LVL 4 | N/A | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-06-28 | 2024-07-01 | Büro | 2024-07-12 |  | 2024-07-03 | 2024-08-05 |  |  | 2024-08-06 | 915 | 150 |  |  |  | 149 | SEP | SEP
51711 | 740-WAn-VU200-260-LH032-65-0 | 1 | true | 8.3 | 740-WAn-VU200-260-LH032-65-0 | LV1-105639.VU200 | 385 |  |  | MC1 | LVL 4 | N/A | TR016_5 | 2024-05-20 | 2024-05-20 | 2024-05-21 |  | 2024-07-02 | 2024-07-09 | Büro | 2024-07-12 |  | 2024-07-11 | 2024-08-05 |  |  | 2024-08-08 | 915 | 150 |  |  |  | 149 | SEP | SEP
51712 | 740-DKR-VU117-141-LH099-10-0 | 1 | true | 1.16 | 740-DKR-VU117-141-LH099-10-0 | LV1-105628.VP147 | 386 |  |  | MC1 | LVL 5 | Tt-12 | TR018_3 | 2024-05-20 | 2024-05-21 | 2024-05-21 |  | 2024-06-21 | 2024-06-25 | Büro | 2024-06-28 |  | 2024-06-27 | 2024-09-10 |  |  | 2024-09-12 | 1039 | 150 |  |  | 2024-09-12 | 149 | SEP | SEP |  |  | 2024-11-30 | 2024-11-30
51713 | 740-DKR-VU117-152-LH099-10-0 | 1 | true | 1.16 | 740-DKR-VU117-152-LH099-10-0 | LV1-105628.VP137 | 386 |  |  | MC1 | LVL 5 | Tt-12 | TR018_3 | 2024-05-20 | 2024-05-21 | 2024-05-21 |  | 2024-06-21 | 2024-06-25 | Büro | 2024-06-28 |  | 2024-06-27 | 2024-09-25 |  |  | 2024-09-27 | 1039 | 150 |  |  | 2024-11-06 | 149 | SEP | SEP |  |  | 2024-11-30 | 2024-11-30
51714 | 740-DR2-VS501-101-LH088-8-0 | 1 | true | 0.13 | 740-DR2-VS501-101-LH088-8-0 | LV0-105638.VU081 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR018_3 | 2024-05-20 | 2024-05-21 | 2024-05-21 |  | 2024-06-17 | 2024-06-19 | Büro | 2024-06-28 |  | 2024-06-20 | 2024-08-28 |  |  | 2024-09-20 | 1005 | 150 |  |  |  | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
51715 | 740-DR2-VU161-201-LH088-8-0 | 1 | true | 0.14 | 740-DR2-VU161-201-LH088-8-0 | LV0-105638.VU081 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR018_3 | 2024-05-20 | 2024-05-21 | 2024-05-21 |  | 2024-06-17 | 2024-06-19 | Dawid Mierzwa | 2024-06-28 |  | 2024-06-20 | 2024-08-28 | 2024-08-30 | 2024-08-30 | 2024-08-30 | 1005 | 150 |  | 2024-11-05 |  | 149 | SEP | SEP |  |  | 2024-11-15 | 2024-11-15
51716 | 740-DR2-VU161-202-LH088-8-0 | 1 | true | 0.16 | 740-DR2-VU161-202-LH088-8-0 | LV0-105638.VU081 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR018_3 | 2024-05-20 | 2024-05-21 | 2024-05-21 |  | 2024-06-17 | 2024-06-19 | Büro | 2024-06-28 |  | 2024-06-20 |  |  |  | 2024-09-20 | 1005 | 150 |  | 2024-11-05 |  | 149 | SEP | SEP |  |  | 2024-11-15 | 2024-11-15
51717 | 740-DR2-VU161-203-LH088-8-0 | 1 | true | 0.18 | 740-DR2-VU161-203-LH088-8-0 | LV0-105638.VU081 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR018_3 | 2024-05-20 | 2024-05-21 | 2024-05-21 |  | 2024-06-17 | 2024-06-19 | Büro | 2024-06-28 |  | 2024-06-20 |  |  |  | 2024-09-16 | 1005 | 150 |  | 2024-11-05 |  | 149 | SEP | SEP |  |  | 2024-11-15 | 2024-11-15
51718 | 740-DR2-VU162-201-LH088-8-0 | 1 | true | 0.1 | 740-DR2-VU162-201-LH088-8-0 | LV0-105638.VU081 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR018_3 | 2024-05-20 | 2024-05-21 | 2024-05-21 |  | 2024-06-17 | 2024-06-19 | Büro | 2024-06-28 |  | 2024-06-20 |  |  |  | 2024-09-16 | 1005 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-11-15 | 2024-11-15
51719 | 740-DR2-VU162-202-LH088-8-0 | 1 | true | 0.2 | 740-DR2-VU162-202-LH088-8-0 | LV0-105638.VU081 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR018_3 | 2024-05-20 | 2024-05-21 | 2024-05-21 |  | 2024-06-17 | 2024-06-19 | Büro | 2024-06-28 |  | 2024-06-20 |  |  |  | 2024-10-04 | 1005 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-11-15 | 2024-11-15
51720 | 740-DR2-VU162-203-LH088-8-0 | 1 | true | 0.17 | 740-DR2-VU162-203-LH088-8-0 | LV0-105638.VU081 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR018_3 | 2024-05-20 | 2024-05-21 | 2024-05-21 |  | 2024-06-17 | 2024-06-19 | Büro | 2024-06-28 |  | 2024-06-20 |  |  |  | 2024-10-04 | 1005 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-11-15 | 2024-11-15
51722 | 740-SIV-VU320-110-LH032-40-0 | 2 | true | 1.11 | 740-SIV-VU320-110-LH032-40-0 | LV1-105638.VU320 | 385 |  |  | MC1 | LVL 6 | N/A | TR018_3 | 2024-05-20 | 2024-05-21 | 2024-05-21 |  | 2024-06-20 | 2024-06-20 | Büro | 2024-06-28 |  | 2024-06-26 | 2024-09-21 |  |  | 2024-09-25 | 1254 | 150 |  | 2024-10-16 |  | 149 | SEP | SEP
51723 | 740-WAn-VS671-101-LH032-50-0 | 3 | false | 1.35 | 740-WAn-VS671-101-LH032-50-0 | LV0-105633.VS671 | 385 |  |  | MC1 | LVL 6 | W23 | TR018_3 | 2024-05-20 | 2024-05-21 | 2024-05-21 |  | 2024-07-02 | 2024-07-04 | Satu Mare | 2024-07-12 |  | 2024-07-10 |  |  |  |  | 1035 | 150 |  |  |  | 149 | SEP | SEP
51724 | 740-WAn-VS672-101-LH032-50-0 | 3 | false | 1.35 | 740-WAn-VS672-101-LH032-50-0 | LV0-105633.VS672 | 385 |  |  | MC1 | LVL 6 | W23 | TR018_3 | 2024-05-20 | 2024-05-21 | 2024-05-21 |  | 2024-07-01 | 2024-07-03 | Büro | 2024-07-12 |  | 2024-07-05 |  |  |  | 2024-09-17 | 1035 | 150 |  |  |  | 149 | SEP | SEP
51725 | 740-WAn-VS673-101-LH032-50-0 | 3 | false | 1.35 | 740-WAn-VS673-101-LH032-50-0 | LV0-105633.VS673 | 385 |  |  | MC1 | LVL 6 | W23 | TR018_3 | 2024-05-20 | 2024-05-21 | 2024-05-21 |  | 2024-07-01 | 2024-07-03 | Satu Mare | 2024-07-12 |  | 2024-07-05 |  |  |  |  | 1035 | 150 |  |  |  | 149 | SEP | SEP
51892 | 740-LS-VU020-142-LH023-25-0 | 1 | true | 2.35 | 740-LS-VU020-142-LH023-25-0 | LV1-105638.VU020 | 368 |  |  | MC1 | LVL 5 | N/A | TR012_2 | 2024-05-22 | 2024-05-22 | 2024-05-22 |  | 2024-06-19 | 2024-06-20 | Büro | 2024-06-28 |  | 2024-06-25 | 2024-09-11 |  |  | 2024-09-16 | 926 | 150 |  |  | 2024-09-17 | 149 | SEP | SEP
51893 | 740-LS-VU020-143-LH023-15-0 | 1 | true | 2.54 | 740-LS-VU020-143-LH023-15-0 | LV1-105638.VU020 | 368 |  |  | MC1 | LVL 5 | N/A | TR012_2 | 2024-05-22 | 2024-05-22 | 2024-05-22 |  | 2024-06-19 | 2024-06-21 | Büro | 2024-06-28 |  | 2024-06-25 | 2024-09-11 |  |  | 2024-09-16 | 926 | 150 |  |  | 2024-09-17 | 149 | SEP | SEP
51894 | 740-LS-VU020-145-LH099-15-0 | 1 | true | 0.9 | 740-LS-VU020-145-LH099-15-0 | LV1-105638.VU020 | 386 |  |  | MC1 | LVL 5 | N/A | TR012_2 | 2024-05-22 | 2024-05-22 | 2024-05-22 |  | 2024-06-21 | 2024-06-25 | Büro | 2024-06-28 |  | 2024-06-27 |  |  |  | 2024-09-17 | 926 | 150 |  |  | 2024-09-25 | 149 | SEP | SEP
51895 | 740-LS-VU020-146-LH099-15-0 | 1 | true | 3.8 | 740-LS-VU020-146-LH099-15-0 | LV1-105638.VU020 | 386 |  |  | MC1 | LVL 5 | N/A | TR012_2 | 2024-05-22 | 2024-05-22 | 2024-05-22 |  | 2024-06-21 | 2024-06-26 | Büro | 2024-07-12 |  | 2024-07-02 | 2024-09-11 |  |  | 2024-09-16 | 926 | 150 |  |  | 2024-09-17 | 149 | SEP | SEP
51896 | 740-LS-VU020-147-LH099-15-0 | 1 | true | 0.06 | 740-LS-VU020-147-LH099-15-0 | LV1-105638.VU020 | 386 |  |  | MC1 | LVL 5 | N/A | TR012_2 | 2024-05-22 | 2024-05-22 | 2024-05-22 |  | 2024-06-21 | 2024-06-25 | Büro | 2024-06-28 |  | 2024-06-27 | 2024-09-11 |  |  | 2024-09-16 | 926 | 150 |  |  | 2024-09-17 | 149 | SEP | SEP
51897 | 740-LS-VU020-148-LH099-15-0 | 1 | true | 0.06 | 740-LS-VU020-148-LH099-15-0 | LV1-105638.VU020 | 386 |  |  | MC1 | LVL 5 | N/A | TR012_2 | 2024-05-22 | 2024-05-22 | 2024-05-22 |  | 2024-06-21 | 2024-06-25 | Büro | 2024-06-28 |  | 2024-06-27 | 2024-09-11 |  |  | 2024-09-16 | 926 | 150 |  |  | 2024-09-17 | 149 | SEP | SEP
51898 | 740-LS-VU020-155-LH099-25-0 | 1 | true | 4.73 | 740-LS-VU020-155-LH099-25-0 | LV1-105638.VU020 | 386 |  |  | MC1 | LVL 5 | N/A | TR012_2 | 2024-05-22 | 2024-05-22 | 2024-05-22 |  | 2024-07-03 | 2024-07-04 | Büro | 2024-07-12 |  | 2024-07-09 | 2024-08-29 |  |  | 2024-09-03 | 926 | 150 |  |  | 2024-09-04 | 149 | SEP | SEP
51899 | 740-LS-VU020-156-LH099-15-0 | 1 | true | 4.97 | 740-LS-VU020-156-LH099-15-0 | LV1-105638.VU020 | 386 |  |  | MC1 | LVL 5 | N/A | TR012_2 | 2024-05-22 | 2024-05-22 | 2024-05-22 |  | 2024-07-03 | 2024-07-04 | Büro | 2024-07-12 |  | 2024-07-10 | 2024-08-29 |  |  | 2024-09-03 | 926 | 150 |  |  | 2024-09-03 | 149 | SEP | SEP
51900 | 740-LS-VU020-157-LH099-15-0 | 1 | true | 0.6 | 740-LS-VU020-157-LH099-15-0 | LV1-105638.VU020 | 386 |  |  | MC1 | LVL 5 | N/A | TR012_2 | 2024-05-22 | 2024-05-22 | 2024-05-22 |  | 2024-07-03 | 2024-07-04 | Büro | 2024-07-12 |  | 2024-07-09 | 2024-08-29 |  |  | 2024-09-03 | 926 | 150 |  |  | 2024-09-03 | 149 | SEP | SEP
51901 | 740-LS-VU020-158-LH099-15-0 | 1 | true | 0.15 | 740-LS-VU020-158-LH099-15-0 | LV1-105638.VU020 | 386 |  |  | MC1 | LVL 5 | N/A | TR012_2 | 2024-05-22 | 2024-05-22 | 2024-05-22 |  | 2024-07-03 | 2024-07-04 | Büro | 2024-07-12 |  | 2024-07-09 | 2024-08-29 |  |  | 2024-09-03 | 926 | 150 |  |  | 2024-09-03 | 149 | SEP | SEP
51902 | 740-LS-VU020-159-LH099-15-0 | 1 | true | 1.59 | 740-LS-VU020-159-LH099-15-0 | LV1-105638.VU020 | 386 |  |  | MC1 | LVL 5 | N/A | TR012_2 | 2024-05-22 | 2024-05-22 | 2024-05-22 |  | 2024-07-03 | 2024-07-04 | Büro | 2024-07-12 |  | 2024-07-09 | 2024-08-29 |  |  | 2024-09-03 | 926 | 150 |  |  | 2024-09-04 | 149 | SEP | SEP
51903 | 740-LS-VU020-160-LH099-15-0 | 1 | true | 4.43 | 740-LS-VU020-160-LH099-15-0 | LV1-105638.VU020 | 386 |  |  | MC1 | LVL 5 | N/A | TR012_2 | 2024-05-22 | 2024-05-22 | 2024-05-22 |  | 2024-07-03 | 2024-07-04 | Büro | 2024-07-12 |  | 2024-07-05 | 2024-08-29 |  |  | 2024-09-03 | 926 | 150 |  |  | 2024-09-04 | 149 | SEP | SEP
51904 | 740-LS-VU020-161-LH099-15-0 | 1 | true | 0.88 | 740-LS-VU020-161-LH099-15-0 | LV1-105638.VU020 | 386 |  |  | MC1 | LVL 5 | N/A | TR012_2 | 2024-05-22 | 2024-05-22 | 2024-05-22 |  | 2024-07-03 | 2024-07-04 | Büro | 2024-07-12 |  | 2024-07-05 | 2024-08-29 |  |  | 2024-09-03 | 926 | 150 |  |  | 2024-09-04 | 149 | SEP | SEP
51905 | 740-LS-VU020-162-LH023-15-0 | 1 | true | 7.93 | 740-LS-VU020-162-LH023-15-0 | LV1-105638.VU020 | 368 |  |  | MC1 | LVL 5 | N/A | TR012_2 | 2024-05-22 | 2024-05-22 | 2024-05-22 |  | 2024-07-01 | 2024-07-03 | Büro | 2024-07-12 |  | 2024-07-05 | 2024-10-09 |  |  | 2024-10-12 | 926 | 150 |  |  | 2024-10-24 | 149 | SEP | SEP
51906 | 740-LS-VU020-163-LH023-15-0 | 1 | true | 9.15 | 740-LS-VU020-163-LH023-15-0 | LV1-105638.VU020 | 368 |  |  | MC1 | LVL 5 | N/A | TR012_2 | 2024-05-22 | 2024-05-22 | 2024-05-22 |  | 2024-07-01 | 2024-07-03 | Büro | 2024-07-12 |  | 2024-07-05 | 2024-10-07 |  |  | 2024-10-09 | 926 | 150 |  |  | 2024-10-24 | 149 | SEP | SEP
51907 | 740-LS-VU020-164-LH099-15-0 | 1 | true | 6.01 | 740-LS-VU020-164-LH099-15-0 | LV1-105638.VU020 | 386 |  |  | MC1 | LVL 5 | N/A | TR012_2 | 2024-05-22 | 2024-05-22 | 2024-05-22 |  | 2024-07-03 | 2024-07-08 |  | 2024-07-12 |  | 2024-07-10 |  |  |  | 2024-10-18 | 926 | 150 |  |  | 2024-10-23 | 149 | SEP | SEP
51908 | 740-LS-VU020-165-LH099-15-0 | 1 | true | 0.68 | 740-LS-VU020-165-LH099-15-0 | LV1-105638.VU020 | 386 |  |  | MC1 | LVL 5 | N/A | TR012_2 | 2024-05-22 | 2024-05-22 | 2024-05-22 |  | 2024-07-03 | 2024-07-04 |  | 2024-07-12 |  | 2024-07-05 |  |  |  | 2024-10-18 | 926 | 150 |  |  | 2024-10-23 | 149 | SEP | SEP
51909 | 740-LS-VU020-166-LH099-15-0 | 1 | true | 1.66 | 740-LS-VU020-166-LH099-15-0 | LV1-105638.VU020 | 386 |  |  | MC1 | LVL 5 | N/A | TR012_2 | 2024-05-22 | 2024-05-22 | 2024-05-22 |  | 2024-07-03 | 2024-07-08 | Büro | 2024-07-12 |  | 2024-07-10 |  |  |  | 2024-10-16 | 926 | 150 |  |  |  | 149 | SEP | SEP
51910 | 740-LS-VU020-167-LH023-15-0 | 1 | true | 2.18 | 740-LS-VU020-167-LH023-15-0 | LV1-105638.VU020 | 368 |  |  | MC1 | LVL 5 | N/A | TR012_2 | 2024-05-22 | 2024-05-22 | 2024-05-22 |  | 2024-07-01 | 2024-07-25 | Büro | 2024-08-02 |  | 2024-07-26 | 2024-08-13 |  |  | 2024-08-14 | 926 | 150 |  |  | 2024-08-28 | 149 | SEP | SEP
51911 | 740-LS-VU020-168-LH023-15-0 | 1 | true | 1.93 | 740-LS-VU020-168-LH023-15-0 | LV1-105638.VU020 | 368 |  |  | MC1 | LVL 5 | N/A | TR012_2 | 2024-05-22 | 2024-05-22 | 2024-05-22 |  | 2024-07-02 | 2024-07-22 | Büro | 2024-08-02 |  | 2024-07-24 | 2024-08-13 |  |  | 2024-08-14 | 926 | 150 |  |  | 2024-08-28 | 149 | SEP | SEP
51912 | 740-LS-VU020-169-LH023-15-0 | 1 | true | 7.22 | 740-LS-VU020-169-LH023-15-0 | LV1-105638.VU020 | 368 |  |  | MC1 | LVL 5 | N/A | TR012_2 | 2024-05-22 | 2024-05-22 | 2024-05-22 |  | 2024-07-02 | 2024-07-23 | Büro | 2024-08-02 |  | 2024-07-25 | 2024-10-01 |  |  | 2024-10-07 | 926 | 150 |  |  | 2024-10-07 | 149 | SEP | SEP
51913 | 740-LS-VU020-170-LH023-15-0 | 1 | true | 5.53 | 740-LS-VU020-170-LH023-15-0 | LV1-105638.VU020 | 368 |  |  | MC1 | LVL 5 | N/A | TR012_2 | 2024-05-22 | 2024-05-22 | 2024-05-22 |  | 2024-07-02 | 2024-07-22 | Büro | 2024-08-02 |  | 2024-07-24 | 2024-09-30 |  |  | 2024-10-07 | 926 | 150 |  |  | 2024-10-07 | 149 | SEP | SEP
51914 | 740-LS-VU020-171-LH023-15-0 | 1 | true | 6.16 | 740-LS-VU020-171-LH023-15-0 | LV1-105638.VU020 | 368 |  |  | MC1 | LVL 5 | N/A | TR012_2 | 2024-05-22 | 2024-05-22 | 2024-05-22 |  | 2024-07-02 | 2024-07-23 | Büro | 2024-08-02 |  | 2024-07-25 | 2024-10-01 |  |  | 2024-10-07 | 926 | 150 |  |  | 2024-10-07 | 149 | SEP | SEP
51915 | 740-LS-VU020-172-LH023-15-0 | 1 | true | 6.99 | 740-LS-VU020-172-LH023-15-0 | LV1-105638.VU020 | 368 |  |  | MC1 | LVL 5 | N/A | TR012_2 | 2024-05-22 | 2024-05-22 | 2024-05-22 |  | 2024-07-02 | 2024-07-23 | Büro | 2024-08-02 |  | 2024-07-25 | 2024-09-27 |  |  | 2024-09-30 | 926 | 150 |  |  | 2024-10-01 | 149 | SEP | SEP
51916 | 740-LS-VU020-173-LH023-15-0 | 1 | true | 12.95 | 740-LS-VU020-173-LH023-15-0 | LV1-105638.VU020 | 368 |  |  | MC1 | LVL 5 | N/A | TR012_2 | 2024-05-22 | 2024-05-22 | 2024-05-22 |  | 2024-07-02 | 2024-07-04 | Büro | 2024-08-02 |  | 2024-07-25 |  |  |  | 2024-09-28 | 926 | 150 |  |  | 2024-09-30 | 149 | SEP | SEP
51917 | 740-LS-VU020-175-LH023-15-0 | 1 | true | 6.48 | 740-LS-VU020-175-LH023-15-0 | LV1-105638.VU020 | 368 |  |  | MC1 | LVL 5 | N/A | TR012_2 | 2024-05-22 | 2024-05-22 | 2024-05-22 |  | 2024-07-02 | 2024-07-22 | Büro | 2024-08-02 |  | 2024-07-24 |  |  |  | 2024-09-18 | 926 | 150 |  |  | 2024-09-23 | 149 | SEP | SEP
51918 | 740-LS-VU020-176-LH099-15-0 | 1 | true | 5.46 | 740-LS-VU020-176-LH099-15-0 | LV1-105638.VU020 | 386 |  |  | MC1 | LVL 5 | N/A | TR012_2 | 2024-05-22 | 2024-05-22 | 2024-05-22 |  | 2024-06-19 | 2024-06-20 | Büro | 2024-06-28 |  | 2024-06-26 |  |  |  | 2024-09-18 | 926 | 150 |  |  | 2024-09-23 | 149 | SEP | SEP
51919 | 740-LS-VU020-177-LH099-15-0 | 1 | true | 0.61 | 740-LS-VU020-177-LH099-15-0 | LV1-105638.VU020 | 386 |  |  | MC1 | LVL 5 | N/A | TR012_2 | 2024-05-22 | 2024-05-22 | 2024-05-22 |  | 2024-06-19 | 2024-06-20 | Büro | 2024-06-28 |  | 2024-06-25 |  |  |  | 2024-09-18 | 926 | 150 |  |  | 2024-09-23 | 149 | SEP | SEP
51920 | 740-LS-VU020-178-LH023-15-0 | 1 | true | 11.45 | 740-LS-VU020-178-LH023-15-0 | LV1-105638.VU020 | 368 |  |  | MC1 | LVL 5 | N/A | TR012_2 | 2024-05-22 | 2024-05-22 | 2024-05-22 |  | 2024-06-21 | 2024-06-25 | Büro | 2024-07-12 |  | 2024-07-01 | 2024-08-26 |  |  | 2024-08-29 | 926 | 150 |  |  | 2024-08-30 | 149 | SEP | SEP
51921 | 740-LS-VU020-180-LH023-15-0 | 1 | true | 10.43 | 740-LS-VU020-180-LH023-15-0 | LV1-105638.VU020 | 368 |  |  | MC1 | LVL 5 | N/A | TR012_2 | 2024-05-22 | 2024-05-22 | 2024-05-22 |  | 2024-06-21 | 2024-06-25 |  | 2024-06-28 |  | 2024-06-27 | 2024-07-31 |  |  | 2024-07-31 | 926 | 150 |  |  | 2024-08-28 | 149 | SEP | SEP
51922 | 740-LS-VU020-181-LH099-15-0 | 1 | true | 2.52 | 740-LS-VU020-181-LH099-15-0 | LV1-105638.VU020 | 386 |  |  | MC1 | LVL 5 | N/A | TR012_2 | 2024-05-22 | 2024-05-22 | 2024-05-22 |  | 2024-06-19 | 2024-06-20 | Büro | 2024-06-28 |  | 2024-06-26 | 2024-10-09 |  |  | 2024-10-15 | 926 | 150 |  |  | 2024-10-24 | 149 | SEP | SEP
51924 | 740-AB-VU310-117-LH032-50-0 | 2 | true | 8.36 | 740-AB-VU310-117-LH032-50-0 | LV1-105638.VU310 | 385 |  |  | MC1 | LVL 5 | N/A | TR019_1 | 2024-05-22 | 2024-05-23 | 2024-05-23 |  | 2024-07-01 | 2024-07-04 | Büro | 2024-07-12 |  | 2024-07-09 |  |  |  | 2024-10-02 | 1018 | 150 |  |  | 2024-10-03 | 149 | SEP | SEP
51928 | 740-LP-VU001-129-LH099-15-0 | 2 | true | 16.1 | 740-LP-VU001-129-LH099-15-0 | LV1-105638.VU001 | 386 |  |  | MC1 | LVL 5 | N/A | TR019_1 | 2024-05-22 | 2024-05-23 | 2024-05-23 |  | 2024-06-21 | 2024-06-25 | Büro | 2024-07-12 |  | 2024-07-01 | 2024-08-26 |  |  | 2024-09-03 | 929 | 150 |  |  | 2024-09-03 | 149 | SEP | SEP
51929 | 740-WAKont-VP131-101-LH099-32-0 | 1 | true | 0.26 | 740-WAKont-VP131-101-LH099-32-0 | LV1-105628.VP131 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR019_1 | 2024-05-22 | 2024-05-23 | 2024-05-23 |  | 2024-07-18 | 2024-07-23 |  | 2024-08-02 |  | 2024-07-25 |  |  |  | 2024-10-19 | 934 | 150 |  |  | 2024-10-30 | 149 | SEP | SEP
51930 | 740-WAKont-VP132-102-LH099-32-0 | 1 | true | 0.27 | 740-WAKont-VP132-102-LH099-32-0 | LV1-105628.VP132 | 386 |  |  | MC1 | LVL 5 | W60 | TR019_1 | 2024-05-22 | 2024-05-23 | 2024-05-23 |  | 2024-07-18 | 2024-07-23 | Büro | 2024-08-02 |  | 2024-07-25 |  |  |  | 2024-10-17 | 934 | 150 |  |  |  | 149 | SEP | SEP
51931 | 740-WAKont-VP133-102-LH099-32-0 | 1 | true | 0.19 | 740-WAKont-VP133-102-LH099-32-0 | LV1-105628.VP133 | 386 |  |  | MC1 | LVL 5 | W60 | TR019_1 | 2024-05-22 | 2024-05-23 | 2024-05-23 |  | 2024-07-18 | 2024-07-23 | Büro | 2024-08-02 |  | 2024-07-25 |  |  |  | 2024-10-17 | 934 | 150 |  |  |  | 149 | SEP | SEP
51932 | 740-WAKont-VP141-101-LH099-32-0 | 1 | true | 0.16 | 740-WAKont-VP141-101-LH099-32-0 | LV1-105628.VP141 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR019_1 | 2024-05-22 | 2024-05-23 | 2024-05-23 |  | 2024-07-18 | 2024-07-23 | Büro | 2024-08-02 |  | 2024-07-25 | 2024-10-14 |  |  | 2024-10-16 | 934 | 150 |  |  |  | 149 | SEP | SEP
51933 | 740-WAKont-VP142-102-LH099-32-0 | 1 | true | 0.27 | 740-WAKont-VP142-102-LH099-32-0 | LV1-105628.VP142 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR019_1 | 2024-05-22 | 2024-05-23 | 2024-05-23 |  | 2024-07-18 | 2024-07-23 | Büro | 2024-08-02 |  | 2024-07-25 |  |  |  | 2024-10-17 | 934 | 150 |  |  |  | 149 | SEP | SEP
51934 | 740-WAKont-VP143-102-LH099-32-0 | 1 | true | 0.19 | 740-WAKont-VP143-102-LH099-32-0 | LV1-105628.VP143 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR019_1 | 2024-05-22 | 2024-05-23 | 2024-05-23 |  | 2024-07-18 | 2024-07-23 | Büro | 2024-08-02 |  | 2024-07-25 | 2024-10-14 |  |  | 2024-10-16 | 934 | 150 |  |  |  | 149 | SEP | SEP
51935 | 740-WAKont-VS695-101-LH099-32-0 | 1 | true | 0.11 | 740-WAKont-VS695-101-LH099-32-0 | LV1-105633.VS695 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR019_1 | 2024-05-22 | 2024-05-23 | 2024-05-23 |  | 2024-07-18 | 2024-07-23 |  | 2024-08-02 |  | 2024-07-25 | 2024-10-16 |  |  | 2024-10-21 | 932 | 150 |  |  | 2024-10-29 | 149 | SEP | SEP
51936 | 740-WAKont-VS695-103-LH099-32-0 | 1 | true | 0.11 | 740-WAKont-VS695-103-LH099-32-0 | LV1-105633.VS695 | 386 |  |  | MC1 | LVL 5 | W60 | TR019_1 | 2024-05-22 | 2024-05-23 | 2024-05-23 |  | 2024-07-18 | 2024-07-22 |  | 2024-08-02 |  | 2024-07-24 | 2024-10-16 |  |  | 2024-10-21 | 934 | 150 |  |  | 2024-10-29 | 149 | SEP | SEP
51937 | 740-WAKont-VS695-105-LH099-32-0 | 1 | true | 0.03 | 740-WAKont-VS695-105-LH099-32-0 | LV1-105633.VS695 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR019_1 | 2024-05-22 | 2024-05-23 | 2024-05-23 |  | 2024-07-22 | 2024-07-22 |  | 2024-08-02 |  | 2024-07-24 | 2024-10-16 |  |  | 2024-10-21 | 932 | 150 |  |  | 2024-10-29 | 149 | SEP | SEP
51938 | 740-WAKont-VS696-101-LH099-32-0 | 1 | true | 0.11 | 740-WAKont-VS696-101-LH099-32-0 | LV1-105633.VS696 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR019_1 | 2024-05-22 | 2024-05-23 | 2024-05-23 |  | 2024-07-18 | 2024-07-23 | Büro | 2024-08-02 |  | 2024-07-25 | 2024-10-14 |  |  | 2024-10-16 | 932 | 150 |  |  | 2024-11-07 | 149 | SEP | SEP
51939 | 740-WAKont-VS696-103-LH099-32-0 | 1 | true | 0.11 | 740-WAKont-VS696-103-LH099-32-0 | LV1-105633.VS696 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR019_1 | 2024-05-22 | 2024-05-23 | 2024-05-23 |  | 2024-07-18 | 2024-07-23 | Büro | 2024-08-02 |  | 2024-07-25 | 2024-10-14 |  |  | 2024-10-16 | 934 | 150 |  |  | 2024-11-07 | 149 | SEP | SEP
51940 | 740-WAKont-VS696-105-LH099-32-0 | 1 | true | 0.03 | 740-WAKont-VS696-105-LH099-32-0 | LV1-105638.VU190 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR019_1 | 2024-05-22 | 2024-05-23 | 2024-05-23 |  | 2024-07-18 | 2024-07-22 | Büro | 2024-08-02 |  | 2024-07-24 | 2024-10-14 |  |  | 2024-10-16 | 932 | 150 |  |  |  | 149 | SEP | SEP
51943 | 740-WAKont-VU190-204-LH099-32-0 | 2 | true | 0.36 | 740-WAKont-VU190-204-LH099-32-0 | LV1-105639.VU190 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR019_1 | 2024-05-22 | 2024-05-23 | 2024-05-23 |  | 2024-07-18 | 2024-07-19 |  | 2024-08-02 |  | 2024-07-22 | 2024-10-16 |  |  | 2024-10-21 | 934 | 150 |  |  | 2024-10-29 | 149 | SEP | SEP
51944 | 740-WAKont-VU190-208-LH099-32-0 | 2 | true | 0.36 | 740-WAKont-VU190-208-LH099-32-0 | LV1-105639.VU190 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR019_1 | 2024-05-22 | 2024-05-23 | 2024-05-23 |  | 2024-07-18 | 2024-07-19 |  | 2024-08-02 |  | 2024-07-23 |  |  |  | 2024-10-19 | 934 | 150 |  |  | 2024-10-30 | 149 | SEP | SEP
51945 | 740-WAKont-VU190-209-LH099-32-0 | 2 | true | 0.58 | 740-WAKont-VU190-209-LH099-32-0 | LV1-105639.VU190 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR019_1 | 2024-05-22 | 2024-05-23 | 2024-05-23 |  | 2024-07-18 | 2024-07-19 | Büro | 2024-08-02 |  | 2024-07-23 |  |  |  | 2024-10-17 | 934 | 150 |  |  |  | 149 | SEP | SEP
51946 | 740-WAKont-VU190-210-LH099-32-0 | 2 | true | 0.48 | 740-WAKont-VU190-210-LH099-32-0 | LV1-105639.VU190 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR019_1 | 2024-05-22 | 2024-05-23 | 2024-05-23 |  | 2024-07-18 | 2024-07-19 |  | 2024-08-02 |  | 2024-07-22 |  |  |  | 2024-10-18 | 934 | 150 |  |  |  | 149 | SEP | SEP
51947 | 740-WAKont-VU190-213-LH099-32-0 | 2 | true | 0.46 | 740-WAKont-VU190-213-LH099-32-0 | LV1-105639.VU190 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR019_1 | 2024-05-22 | 2024-05-23 | 2024-05-23 |  | 2024-07-18 | 2024-07-19 | Büro | 2024-08-02 |  | 2024-07-22 | 2024-10-14 |  |  | 2024-10-16 | 934 | 150 |  |  |  | 149 | SEP | SEP
51948 | 740-WAKont-VU190-218-LH099-32-0 | 2 | true | 0.42 | 740-WAKont-VU190-218-LH099-32-0 | LV1-105639.VU190 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR019_1 | 2024-05-22 | 2024-05-23 | 2024-05-23 |  | 2024-07-18 | 2024-07-18 | Büro | 2024-08-02 |  | 2024-07-23 | 2024-10-14 |  |  | 2024-10-16 | 934 | 150 |  |  |  | 149 | SEP | SEP
51949 | 740-WAKont-VU190-219-LH099-32-0 | 2 | true | 0.58 | 740-WAKont-VU190-219-LH099-32-0 | LV1-105639.VU190 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR019_1 | 2024-05-22 | 2024-05-23 | 2024-05-23 |  | 2024-07-18 |  | Büro | 2024-08-02 | [5 empty] | 2024-10-17 | 934 | 150 |  |  |  | 149 | SEP | SEP
51950 | 740-WAKont-VU190-220-LH099-32-0 | 2 | true | 0.47 | 740-WAKont-VU190-220-LH099-32-0 | LV1-105639.VU190 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR019_1 | 2024-05-22 | 2024-05-23 | 2024-05-23 |  | 2024-07-18 | 2024-07-18 | Büro | 2024-08-02 |  | 2024-07-23 | 2024-10-14 |  |  | 2024-10-16 | 934 | 150 |  |  |  | 149 | SEP | SEP
51999 | 740-WAn-VP131-103-LH099-40-0 | 1 | true | 0.13 | 740-WAn-VP131-103-LH099-40-0 | LV1-105628.VP131 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR019_2 | 2024-05-24 | 2024-05-27 | 2024-05-27 |  | 2024-07-02 | 2024-07-03 |  | 2024-07-12 |  | 2024-07-05 |  |  |  | 2024-10-18 | 1036 | 150 |  |  |  | 149 | SEP | SEP
52000 | 740-WAn-VP133-103-LH099-32-0 | 1 | true | 0.15 | 740-WAn-VP133-103-LH099-32-0 | LV1-105628.VP133 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR019_2 | 2024-05-24 | 2024-05-27 | 2024-05-27 |  | 2024-07-18 | 2024-07-18 | Büro | 2024-08-02 |  | 2024-07-23 |  |  |  | 2024-10-17 | 1036 | 150 |  |  |  | 149 | SEP | SEP
52001 | 740-WAn-VP141-103-LH099-40-0 | 1 | true | 0.18 | 740-WAn-VP141-103-LH099-40-0 | LV1-105628.VP141 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR019_2 | 2024-05-24 | 2024-05-27 | 2024-05-27 |  | 2024-07-02 | 2024-07-03 | Büro | 2024-07-12 |  | 2024-07-05 | 2024-10-14 |  |  | 2024-10-16 | 1036 | 150 |  |  |  | 149 | SEP | SEP
52002 | 740-WAn-VP143-103-LH099-32-0 | 1 | true | 0.14 | 740-WAn-VP143-103-LH099-32-0 | LV1-105628.VP143 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR019_2 | 2024-05-24 | 2024-05-27 | 2024-05-27 |  | 2024-07-18 | 2024-07-18 | Büro | 2024-08-02 |  | 2024-07-23 | 2024-10-14 |  |  | 2024-10-16 | 1036 | 150 |  |  |  | 149 | SEP | SEP
52003 | 740-WAn-VS691-104-LH099-32-0 | 1 | false | 0.05 | 740-WAn-VS691-104-LH099-32-0 | LV0-105633.VU691 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR019_2 | 2024-05-24 | 2024-05-27 | 2024-05-27 |  | 2024-07-18 | 2024-07-23 |  |  |  | 2024-07-25 |  |  |  |  | 1036 | 150 |  |  |  | 149 | SEP | SEP
62224 | 740-WAn-VS691-104-LH099-32-0 | 2 | true | 0.05 | 740-WAn-VS691-104-LH099-32-0 | LV0-105633.VU691 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR029_1 | 2024-07-24 | 2024-05-27 | 2024-05-27 |  | 2024-07-18 | 2024-07-23 | Büro | 2024-08-02 |  | 2024-07-26 | 2024-10-10 |  |  | 2024-10-14 | 1036 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
52004 | 740-WAn-VS692-104-LH099-32-0 | 1 | true | 0.05 | 740-WAn-VS692-104-LH099-32-0 | LV0-105633.VU692 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR019_2 | 2024-05-24 | 2024-05-27 | 2024-05-27 |  | 2024-07-18 | 2024-07-23 | Büro | 2024-08-02 |  | 2024-07-25 | 2024-10-10 |  |  | 2024-10-14 | 1036 | 150 |  |  | 2024-11-07 | 149 | SEP | SEP
52005 | 740-WAn-VS693-102-LH099-32-0 | 1 | true | 0.15 | 740-WAn-VS693-102-LH099-32-0 | LV0-105633.VS693 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR019_2 | 2024-05-24 | 2024-05-27 | 2024-05-27 |  | 2024-07-18 | 2024-07-23 | Attila Henter | 2024-08-02 |  | 2024-07-25 | 2024-10-17 |  |  | 2024-10-21 | 1036 | 150 |  |  | 2024-10-29 | 149 | SEP | SEP
52006 | 740-WAn-VS694-102-LH099-32-0 | 1 | true | 0.15 | 740-WAn-VS694-102-LH099-32-0 | LV1-105633.VS694 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR019_2 | 2024-05-24 | 2024-05-27 | 2024-05-27 |  | 2024-07-18 | 2024-07-23 | Büro | 2024-08-02 |  | 2024-07-25 | 2024-10-14 |  |  | 2024-10-16 | 1036 | 150 |  |  | 2024-11-07 | 149 | SEP | SEP
52007 | 740-WAn-VS695-102-LH099-32-0 | 1 | true | 0.1 | 740-WAn-VS695-102-LH099-32-0 | LV0-105633.VS695 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR019_2 | 2024-05-24 | 2024-05-27 | 2024-05-27 |  | 2024-07-18 | 2024-07-23 |  | 2024-08-02 |  | 2024-07-25 | 2024-10-16 |  |  | 2024-10-21 | 1036 | 150 |  |  | 2024-10-29 | 149 | SEP | SEP
52008 | 740-WAn-VS696-102-LH099-32-0 | 1 | true | 0.14 | 740-WAn-VS696-102-LH099-32-0 | LV1-105633.VS696 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR019_2 | 2024-05-24 | 2024-05-27 | 2024-05-27 |  | 2024-07-18 | 2024-07-23 | Büro | 2024-08-02 |  | 2024-07-25 | 2024-10-14 |  |  | 2024-10-16 | 1036 | 150 |  |  |  | 149 | SEP | SEP
52009 | 740-WAn-VU200-106-LH099-32-0 | 1 | true | 0.37 | 740-WAn-VU200-106-LH099-32-0 | LV1-105633.VS695 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR019_2 | 2024-05-24 | 2024-05-27 | 2024-05-27 |  | 2024-07-19 | 2024-07-22 |  | 2024-08-02 |  | 2024-07-23 | 2024-10-16 |  |  | 2024-10-21 | 1036 | 150 |  |  | 2024-10-30 | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
52010 | 740-WAn-VU200-107-LH099-40-0 | 1 | false | 0.56 | 740-WAn-VU200-107-LH099-40-0 | LV0-105628.VP033 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR019_2 | 2024-05-24 | 2024-05-27 | 2024-05-27 | [11 empty] | 1036 | 150 |  |  |  | 149 | SEP | SEP
52791 | 740-WAn-VU200-107-LH099-40-0 | 2 | true | 0.56 | 740-WAn-VU200-107-LH099-40-0 | LV0-105628.VP033 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR025_1 | 2024-06-18 | 2024-05-27 | 2024-05-27 |  | 2024-07-02 | 2024-07-03 | Attila Henter | 2024-07-12 |  | 2024-07-05 | 2024-10-16 |  |  | 2024-10-18 | 1036 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
52011 | 740-WAn-VU200-108-LH099-32-0 | 1 | false | 0.52 | 740-WAn-VU200-108-LH099-32-0 | LV0-105628.VP031 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR019_2 | 2024-05-24 | 2024-05-27 | 2024-05-27 | [11 empty] | 1036 | 150 |  |  |  | 149 | SEP | SEP
52792 | 740-WAn-VU200-108-LH099-32-0 | 2 | true | 0.52 | 740-WAn-VU200-108-LH099-32-0 | LV0-105628.VP031 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR025_1 | 2024-06-18 | 2024-05-27 | 2024-05-27 |  | 2024-07-18 | 2024-07-18 | Büro | 2024-08-02 |  | 2024-07-24 | 2024-10-18 |  |  | 2024-10-22 | 1036 | 150 |  |  | 2024-10-29 | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
52012 | 740-WAn-VU200-109-LH099-15-0 | 1 | false | 0.65 | 740-WAn-VU200-109-LH099-15-0 | LV1-105628.VP051 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR019_2 | 2024-05-24 | 2024-05-27 | 2024-05-27 | [11 empty] | 1036 | 150 |  |  | 2024-09-09 | 149 | SEP | SEP
52793 | 740-WAn-VU200-109-LH099-15-0 | 2 | true | 0.65 | 740-WAn-VU200-109-LH099-15-0 | LV1-105628.VP051 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR025_1 | 2024-06-18 | 2024-05-27 | 2024-05-27 |  | 2024-06-28 | 2024-07-02 | Büro | 2024-07-12 |  | 2024-07-04 | 2024-08-08 |  |  | 2024-09-03 | 1036 | 150 |  |  | 2024-09-09 | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
52013 | 740-WAn-VU200-114-LH099-40-0 | 1 | true | 0.39 | 740-WAn-VU200-114-LH099-40-0 | LV1-105628.VP131 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR019_2 | 2024-05-24 | 2024-05-27 | 2024-05-27 |  | 2024-06-27 | 2024-07-03 |  | 2024-07-12 |  | 2024-07-05 |  |  |  | 2024-10-18 | 1036 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
52014 | 740-WAn-VU200-116-LH099-32-0 | 1 | true | 0.43 | 740-WAn-VU200-116-LH099-32-0 | LV1-105628.VP133 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR019_2 | 2024-05-24 | 2024-05-27 | 2024-05-27 |  | 2024-07-18 | 2024-07-18 |  | 2024-08-02 |  | 2024-07-23 |  |  |  | 2024-10-18 | 1036 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
52015 | 740-WAn-VU200-128-LH099-40-0 | 1 | false | 0.55 | 740-WAn-VU200-128-LH099-40-0 | LV0-105628.VP042 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR019_2 | 2024-05-24 | 2024-05-27 | 2024-05-27 | [11 empty] | 1036 | 150 |  |  |  | 149 | SEP | SEP
52794 | 740-WAn-VU200-128-LH099-40-0 | 2 | true | 0.55 | 740-WAn-VU200-128-LH099-40-0 | LV0-105628.VP042 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR025_1 | 2024-06-18 | 2024-05-27 | 2024-05-27 |  | 2024-06-27 | 2024-07-03 |  | 2024-07-12 |  | 2024-07-04 |  |  |  | 2024-10-18 | 1036 | 150 |  |  | 2024-11-05 | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
52016 | 740-WAn-VU200-129-LH099-40-0 | 1 | false | 0.6 | 740-WAn-VU200-129-LH099-40-0 | LV0-105628.VP043 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR019_2 | 2024-05-24 | 2024-05-27 | 2024-05-27 | [11 empty] | 1036 | 150 |  |  |  | 149 | SEP | SEP
52795 | 740-WAn-VU200-129-LH099-40-0 | 2 | true | 0.6 | 740-WAn-VU200-129-LH099-40-0 | LV0-105628.VP043 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR025_1 | 2024-06-18 | 2024-05-27 | 2024-05-27 |  | 2024-06-28 | 2024-07-01 | Büro | 2024-07-12 |  | 2024-07-03 |  |  |  | 2024-10-16 | 1036 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
52017 | 740-WAn-VU200-130-LH099-32-0 | 1 | false | 0.5 | 740-WAn-VU200-130-LH099-32-0 | LV0-105628.VP041 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR019_2 | 2024-05-24 | 2024-05-27 | 2024-05-27 | [11 empty] | 1036 | 150 |  |  |  | 149 | SEP | SEP
52796 | 740-WAn-VU200-130-LH099-32-0 | 2 | true | 0.5 | 740-WAn-VU200-130-LH099-32-0 | LV0-105628.VP041 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR025_1 | 2024-06-18 | 2024-05-27 | 2024-05-27 |  | 2024-07-18 | 2024-07-18 | Attila Henter | 2024-08-02 |  | 2024-07-23 | 2024-10-17 |  |  | 2024-10-18 | 1036 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
52018 | 740-WAn-VU200-131-LH099-15-0 | 1 | false | 0.65 | 740-WAn-VU200-131-LH099-15-0 | LV1-105628.VP061 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR019_2 | 2024-05-24 | 2024-05-27 | 2024-05-27 | [11 empty] | 1036 | 150 |  |  |  | 149 | SEP | SEP
52797 | 740-WAn-VU200-131-LH099-15-0 | 2 | true | 0.65 | 740-WAn-VU200-131-LH099-15-0 | LV1-105628.VP061 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR025_1 | 2024-06-18 | 2024-05-27 | 2024-05-27 |  | 2024-06-28 | 2024-07-02 | Büro | 2024-07-12 |  | 2024-07-03 | 2024-10-14 |  |  | 2024-10-16 | 1036 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
52019 | 740-WAn-VU200-141-LH099-40-0 | 1 | true | 0.39 | 740-WAn-VU200-141-LH099-40-0 | LV1-105628.VP141 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR019_2 | 2024-05-24 | 2024-05-27 | 2024-05-27 |  | 2024-06-27 | 2024-07-03 | Büro | 2024-07-12 |  | 2024-07-10 | 2024-08-08 |  |  | 2024-08-28 | 1036 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
52020 | 740-WAn-VU200-143-LH099-32-0 | 1 | true | 0.43 | 740-WAn-VU200-143-LH099-32-0 | LV1-105628.VP143 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR019_2 | 2024-05-24 | 2024-05-27 | 2024-05-27 |  | 2024-07-18 | 2024-07-22 | Büro | 2024-08-02 |  | 2024-07-24 | 2024-10-14 |  |  | 2024-10-16 | 1036 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
52021 | 740-WAn-VU200-145-LH099-32-0 | 1 | true | 0.47 | 740-WAn-VU200-145-LH099-32-0 | LV2-105633.VS691 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR019_2 | 2024-05-24 | 2024-05-27 | 2024-05-27 |  | 2024-07-18 | 2024-07-19 | Büro | 2024-08-02 |  | 2024-07-22 | 2024-10-10 |  |  | 2024-10-14 | 1036 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
52022 | 740-WAn-VU200-148-LH099-32-0 | 1 | true | 0.42 | 740-WAn-VU200-148-LH099-32-0 | LV1-105633.VS696 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR019_2 | 2024-05-24 | 2024-05-27 | 2024-05-27 |  | 2024-07-18 |  | Büro | 2024-08-02 |  | 2024-07-23 |  |  |  | 2024-10-16 | 1036 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
52023 | 740-WAn-VU200-149-LH099-32-0 | 1 | true | 0.47 | 740-WAn-VU200-149-LH099-32-0 | LV2-105633.VS692 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR019_2 | 2024-05-24 | 2024-05-27 | 2024-05-27 |  | 2024-07-18 | 2024-07-18 | Büro | 2024-08-02 |  | 2024-07-23 | 2024-10-10 |  |  | 2024-10-14 | 1036 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
52024 | 740-WAn-VU200-157-LH099-32-0 | 1 | true | 0.45 | 740-WAn-VU200-157-LH099-32-0 | LV1-105633.VS693 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR019_2 | 2024-05-24 | 2024-05-27 | 2024-05-27 |  | 2024-07-19 | 2024-07-22 | Büro | 2024-08-02 |  | 2024-07-24 | 2024-08-26 |  |  | 2024-09-03 | 1036 | 150 |  |  | 2024-09-09 | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
52025 | 740-WAn-VU200-161-LH099-32-0 | 1 | true | 0.45 | 740-WAn-VU200-161-LH099-32-0 | LV1-105633.VS694 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR019_2 | 2024-05-24 | 2024-05-27 | 2024-05-27 |  | 2024-07-19 | 2024-07-22 | Büro | 2024-08-02 |  | 2024-07-24 | 2024-10-14 |  |  | 2024-10-16 | 1036 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
52026 | 740-WAn-VU200-183-LH032-25-0 | 1 | true | 1.91 | 740-WAn-VU200-183-LH032-25-0 | LV1-105639.VU200 | 385 |  |  | MC1 | LVL 5 | N/A | TR019_2 | 2024-05-24 | 2024-05-27 | 2024-05-27 |  | 2024-07-03 | 2024-07-04 | Büro | 2024-07-12 |  | 2024-07-05 | 2024-09-11 |  |  | 2024-09-20 | 1034 | 150 |  | 2024-10-09 |  | 149 | SEP | SEP
52027 | 740-WAn-VU200-190-LH032-25-0 | 1 | true | 4.36 | 740-WAn-VU200-190-LH032-25-0 | LV1-105638.VU310 | 385 |  |  | MC1 | LVL 5 | N/A | TR019_2 | 2024-05-24 | 2024-05-27 | 2024-05-27 |  | 2024-07-03 | 2024-07-04 | Büro | 2024-07-12 |  | 2024-07-05 | 2024-10-02 |  |  | 2024-10-11 | 1034 | 150 |  |  |  | 149 | SEP | SEP
52028 | 740-WAn-VU200-291-LH032-25-0 | 1 | true | 8.56 | 740-WAn-VU200-291-LH032-25-0 | LV1-105638.VU310 | 385 |  |  | MC1 | LVL 5 | N/A | TR019_2 | 2024-05-24 | 2024-05-27 | 2024-05-27 |  | 2024-07-03 | 2024-07-04 | Büro | 2024-07-12 |  | 2024-07-05 | 2024-09-10 |  |  | 2024-09-11 | 1035 | 150 |  | 2024-10-09 | 2024-09-12 | 149 | SEP | SEP
52081 | 740-SIV-VU160-128-LH032-40-0 | 1 | true | 0.88 | 740-SIV-VU160-128-LH032-40-0 | LV1-105638.VU320 | 385 |  |  | MC1 | LVL 6 | N/A | TR015_7 | 2024-05-27 | 2024-05-28 | 2024-05-28 |  | 2024-07-02 | 2024-07-03 | Büro | 2024-07-12 |  | 2024-07-08 | 2024-09-09 |  |  | 2024-09-17 | 1254 | 150 |  |  | 2024-09-25 | 149 | SEP | SEP
52082 | 740-SIV-VU320-108-LH032-40-0 | 1 | true | 6.76 | 740-SIV-VU320-108-LH032-40-0 | LV1-105638.VU320 | 385 |  |  | MC1 | LVL 6 | N/A | TR015_7 | 2024-05-27 | 2024-05-28 | 2024-05-28 |  | 2024-07-02 | 2024-07-04 | Büro | 2024-07-12 |  | 2024-07-05 | 2024-07-26 | 2024-07-31 |  | 2024-09-17 | 1254 | 150 |  | 2024-10-16 |  | 149 | SEP | SEP
52112 | 740-SIV-VS020-102-LH032-65-0 | 1 | true | 3.25 | 740-SIV-VS020-102-LH032-65-0 | LV1-105638.VU320 | 385 |  |  | MC1 | LVL 5 | N/A | TR015_8 | 2024-05-29 | 2024-05-29 | 2024-05-29 |  | 2024-07-03 | 2024-07-08 | Büro | 2024-07-12 |  | 2024-07-11 |  |  |  | 2024-10-04 | 1253 | 150 |  |  |  | 149 | SEP | SEP
52114 | 740-DR2-VP137-101-LH088-15-0 | 1 | true | 0.41 | 740-DR2-VP137-101-LH088-15-0 | LV0-105638.VU081 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR018_4 | 2024-05-29 | 2024-05-29 | 2024-05-29 |  | 2024-06-18 | 2024-06-19 | Büro | 2024-06-28 |  | 2024-06-20 |  |  |  | 2024-09-27 | 1005 | 150 |  |  |  | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
52115 | 740-DR2-VP147-101-LH088-15-0 | 1 | true | 0.45 | 740-DR2-VP147-101-LH088-15-0 | LV0-105638.VU081 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR018_4 | 2024-05-29 | 2024-05-29 | 2024-05-29 |  | 2024-06-18 | 2024-06-19 | Büro | 2024-06-28 |  | 2024-06-20 |  |  |  | 2024-09-27 | 1005 | 150 |  |  |  | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
52146 | 740-AWFI-VP003-101-LH089-25-0 | 2 | true | 0.17 | 740-AWFI-VP003-101-LH089-25-0 | LV0-105628.VP003 | 394 |  |  | MC1 | LVL 5 | N/A | TR020_1 | 2024-05-29 | 2024-06-05 | 2024-06-05 |  | 2024-07-19 | 2024-07-22 | Büro | 2024-08-23 |  | 2024-07-22 | 2024-09-10 |  |  | 2024-09-27 | 936 | 150 |  |  | 2024-11-11 | 149 | SEP | SEP
52147 | 740-AWFI-VP004-101-LH089-25-0 | 2 | true | 0.35 | 740-AWFI-VP004-101-LH089-25-0 | LV0-105628.VP004 | 394 |  |  | MC1 | LVL 5 | N/A | TR020_1 | 2024-05-29 | 2024-06-05 | 2024-06-05 |  | 2024-07-19 | 2024-07-22 |  | 2024-08-23 |  | 2024-07-22 | 2024-09-10 |  |  | 2024-10-18 | 937 | 150 |  |  | 2024-10-29 | 149 | SEP | SEP
52148 | 740-CIP-R-VP001-103-LH088-32-0 | 1 | true | 0.35 | 740-CIP-R-VP001-103-LH088-32-0 | LV0-105628.VP001 | 391 |  |  | MC1 | LVL 5 | Tt-6 | TR020_1 | 2024-05-29 | 2024-06-05 | 2024-06-05 |  | 2024-06-18 | 2024-06-19 | Büro | 2024-06-28 |  | 2024-06-21 | 2024-10-22 |  |  | 2024-10-30 | 928 | 150 |  |  | 2024-10-31 | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
52149 | 740-CIP-R-VP002-103-LH088-32-0 | 1 | true | 3.8 | 740-CIP-R-VP002-103-LH088-32-0 | LV0-105628.VP002 | 391 |  |  | MC1 | LVL 5 | Tt-6 | TR020_1 | 2024-05-29 | 2024-06-05 | 2024-06-05 |  | 2024-06-20 | 2024-06-21 | Büro | 2024-06-28 |  | 2024-06-26 | 2024-10-22 |  |  | 2024-10-30 | 928 | 150 |  |  | 2024-10-31 | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
52150 | 740-DKR-VP031-101-LH099-15-0 | 1 | true | 0.16 | 740-DKR-VP031-101-LH099-15-0 | LV0-105628.VP031 | 386 |  |  | MC1 | LVL 5 | Tt-12 | TR020_1 | 2024-05-29 | 2024-06-05 | 2024-06-05 |  | 2024-07-24 | 2024-07-25 | Büro | 2024-08-02 |  | 2024-07-26 |  |  |  | 2024-10-04 | 1039 | 150 |  |  | 2024-11-12 | 149 | SEP | SEP |  |  | 2024-11-30 | 2024-11-30
52151 | 740-DKR-VP032-101-LH099-15-0 | 1 | true | 0.16 | 740-DKR-VP032-101-LH099-15-0 | LV0-105628.VP032 | 386 |  |  | MC1 | LVL 5 | Tt-12 | TR020_1 | 2024-05-29 | 2024-06-05 | 2024-06-05 |  | 2024-07-24 | 2024-07-25 | Büro | 2024-08-02 |  | 2024-07-26 |  |  |  | 2024-10-03 | 1039 | 150 |  |  | 2024-11-12 | 149 | SEP | SEP |  |  | 2024-11-30 | 2024-11-30
52152 | 740-DKR-VP033-101-LH099-15-0 | 1 | true | 0.21 | 740-DKR-VP033-101-LH099-15-0 | LV0-105628.VP033 | 386 |  |  | MC1 | LVL 5 | Tt-12 | TR020_1 | 2024-05-29 | 2024-06-05 | 2024-06-05 |  | 2024-07-25 | 2024-07-25 | Büro | 2024-08-02 |  | 2024-07-26 |  |  |  | 2024-10-03 | 1039 | 150 |  |  | 2024-11-13 | 149 | SEP | SEP
52153 | 740-DKR-VP041-101-LH099-15-0 | 1 | true | 0.21 | 740-DKR-VP041-101-LH099-15-0 | LV0-105628.VP041 | 386 |  |  | MC1 | LVL 5 | Tt-12 | TR020_1 | 2024-05-29 | 2024-06-05 | 2024-06-05 |  | 2024-07-25 | 2024-07-25 | Büro | 2024-08-02 |  | 2024-07-26 | 2024-09-30 |  |  | 2024-10-07 | 1039 | 150 |  |  | 2024-11-14 | 149 | SEP | SEP |  |  | 2024-11-30 | 2024-11-30
52154 | 740-DKR-VP042-101-LH099-15-0 | 1 | true | 0.3 | 740-DKR-VP042-101-LH099-15-0 | LV0-105628.VP042 | 386 |  |  | MC1 | LVL 5 | Tt-12 | TR020_1 | 2024-05-29 | 2024-06-05 | 2024-06-05 |  | 2024-07-25 |  | Büro | 2024-08-02 |  | 2024-07-26 | 2024-09-30 |  |  | 2024-10-07 | 1039 | 150 |  |  | 2024-11-14 | 149 | SEP | SEP |  |  | 2024-11-30 | 2024-11-30
52155 | 740-DKR-VP043-101-LH099-15-0 | 1 | true | 0 | 740-DKR-VP043-101-LH099-15-0 | LV0-105628.VP043 | 386 |  |  | MC1 | LVL 5 | Tt-12 | TR020_1 | 2024-05-29 | 2024-06-05 | 2024-06-05 |  | 2024-07-25 | 2024-07-25 | Büro | 2024-08-02 |  | 2024-07-29 | 2024-09-30 |  |  | 2024-10-07 | 1039 | 150 |  |  |  | 149 | SEP | SEP
52156 | 740-DKR-VP131-101-LH099-15-0 | 1 | true | 0.1 | 740-DKR-VP131-101-LH099-15-0 | LV1-105628.VP131 | 386 |  |  | MC1 | LVL 5 | Tt-12 | TR020_1 | 2024-05-29 | 2024-06-05 | 2024-06-05 |  | 2024-07-25 |  | Büro | 2024-08-02 |  | 2024-07-26 |  |  |  | 2024-10-04 | 1039 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-11-30 | 2024-11-30
52157 | 740-DKR-VP133-101-LH099-15-0 | 1 | true | 0.1 | 740-DKR-VP133-101-LH099-15-0 | LV1-105628.VP133 | 386 |  |  | MC1 | LVL 5 | Tt-12 | TR020_1 | 2024-05-29 | 2024-06-05 | 2024-06-05 |  | 2024-07-25 |  | Büro | 2024-08-02 |  | 2024-07-26 |  |  |  | 2024-10-04 | 1039 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-11-30 | 2024-11-30
52158 | 740-DKR-VP141-101-LH099-15-0 | 1 | true | 0.21 | 740-DKR-VP141-101-LH099-15-0 | LV1-105628.VP141 | 386 |  |  | MC1 | LVL 5 | Tt-12 | TR020_1 | 2024-05-29 | 2024-06-05 | 2024-06-05 |  | 2024-07-24 | 2024-07-25 | Büro | 2024-08-02 |  | 2024-07-26 | 2024-09-30 |  |  | 2024-10-01 | 1039 | 150 |  |  | 2024-10-03 | 149 | SEP | SEP |  |  | 2024-11-30 | 2024-11-30
52159 | 740-DKR-VP143-101-LH099-15-0 | 1 | true | 0.21 | 740-DKR-VP143-101-LH099-15-0 | LV1-105628.VP143 | 386 |  |  | MC1 | LVL 5 | Tt-12 | TR020_1 | 2024-05-29 | 2024-06-05 | 2024-06-05 |  | 2024-07-23 | 2024-07-24 | Büro | 2024-08-02 |  | 2024-07-29 | 2024-09-30 |  |  | 2024-10-01 | 1039 | 150 |  |  | 2024-10-03 | 149 | SEP | SEP |  |  | 2024-11-30 | 2024-11-30
52160 | 740-DKR-VU081-109-LH099-15-0 | 1 | true | 0.15 | 740-DKR-VU081-109-LH099-15-0 | LV1-105638.VU117 | 386 |  |  | MC1 | LVL 5 | Tt-12 | TR020_1 | 2024-05-29 | 2024-06-05 | 2024-06-05 |  | 2024-07-24 |  | Büro | 2024-08-02 |  | 2024-07-26 |  |  |  | 2024-10-03 | 1039 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-11-30 | 2024-11-30
52161 | 740-DKR-VU081-115-LH099-15-0 | 1 | true | 0.13 | 740-DKR-VU081-115-LH099-15-0 | LV1-105638.VU117 | 386 |  |  | MC1 | LVL 5 | Tt-12 | TR020_1 | 2024-05-29 | 2024-06-05 | 2024-06-05 |  | 2024-07-24 |  | Büro | 2024-08-02 |  | 2024-07-26 | 2024-10-01 |  |  | 2024-10-03 | 1039 | 150 |  |  | 2024-10-04 | 149 | SEP | SEP |  |  | 2024-11-30 | 2024-11-30
52162 | 740-DKR-VU081-116-LH099-15-0 | 1 | true | 0.2 | 740-DKR-VU081-116-LH099-15-0 | LV1-105638.VU117 | 386 |  |  | MC1 | LVL 5 | Tt-12 | TR020_1 | 2024-05-29 | 2024-06-05 | 2024-06-05 |  | 2024-07-24 |  | Büro | 2024-08-02 |  | 2024-07-26 | 2024-10-01 |  |  | 2024-10-03 | 1039 | 150 |  |  | 2024-10-04 | 149 | SEP | SEP |  |  | 2024-11-30 | 2024-11-30
52163 | 740-DKR-VU081-118-LH011-15-0 | 1 | true | 0.05 | 740-DKR-VU081-118-LH011-15-0 | LV0-105638.VU081 | 369 |  |  | MC1 | LVL 5 | W23 | TR020_1 | 2024-05-29 | 2024-06-05 | 2024-06-05 |  | 2024-07-24 | 2024-07-25 |  | 2024-08-02 |  | 2024-07-26 |  |  |  | 2024-11-12 | 1039 | 150 |  |  |  | 149 | SEP | SEP | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22
52164 | 740-DKR-VU081-121-LH099-15-0 | 1 | true | 0.2 | 740-DKR-VU081-121-LH099-15-0 | LV1-105638.VU117 | 386 |  |  | MC1 | LVL 5 | Tt-12 | TR020_1 | 2024-05-29 | 2024-06-05 | 2024-06-05 |  | 2024-07-23 | 2024-07-26 | Büro | 2024-08-02 |  | 2024-07-26 | 2024-09-30 |  |  | 2024-10-01 | 1039 | 150 |  |  | 2024-10-03 | 149 | SEP | SEP |  |  | 2024-11-30 | 2024-11-30
52165 | 740-DKR-VU081-122-LH099-15-0 | 1 | true | 0.2 | 740-DKR-VU081-122-LH099-15-0 | LV1-105638.VU117 | 386 |  |  | MC1 | LVL 5 | Tt-12 | TR020_1 | 2024-05-29 | 2024-06-05 | 2024-06-05 |  | 2024-07-23 | 2024-07-26 | Büro | 2024-08-02 |  | 2024-07-26 | 2024-09-30 |  |  | 2024-10-04 | 1039 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-11-30 | 2024-11-30
52166 | 740-DKR-VU081-123-LH099-15-0 | 1 | false | 0.16 | 740-DKR-VU081-123-LH099-15-0 | LV1-105638.VU117 | 386 |  |  | MC1 | LVL 5 | Tt-12 | TR020_1 | 2024-05-29 | 2024-06-05 | 2024-06-05 | [11 empty] | 1039 | 150 |  |  |  | 149 | SEP | SEP
52772 | 740-DKR-VU081-123-LH099-15-0 | 2 | true | 0.16 | 740-DKR-VU081-123-LH099-15-0 | LV1-105638.VU117 | 386 |  |  | MC1 | LVL 5 | Tt-12 | TR025_1 | 2024-06-18 | 2024-06-05 | 2024-06-05 |  | 2024-07-23 | 2024-07-26 | Büro | 2024-08-02 |  | 2024-07-26 | 2024-10-03 |  |  | 2024-10-07 | 1039 | 150 |  |  | 2024-10-07 | 149 | SEP | SEP |  |  | 2024-11-30 | 2024-11-30
52167 | 740-DKR-VU117-109-LH099-15-0 | 2 | true | 0.88 | 740-DKR-VU117-109-LH099-15-0 | LV0-105628.VP031 | 386 |  |  | MC1 | LVL 5 | Tt-12 | TR020_1 | 2024-05-29 | 2024-06-05 | 2024-06-05 |  | 2024-07-23 | 2024-07-26 | Büro | 2024-08-02 |  | 2024-07-26 |  |  |  | 2024-10-04 | 1039 | 150 |  |  | 2024-11-06 | 149 | SEP | SEP |  |  | 2024-11-30 | 2024-11-30
52168 | 740-DKR-VU117-110-LH099-15-0 | 2 | true | 1.01 | 740-DKR-VU117-110-LH099-15-0 | LV0-105628.VP032 | 386 |  |  | MC1 | LVL 5 | Tt-12 | TR020_1 | 2024-05-29 | 2024-06-05 | 2024-06-05 |  | 2024-07-23 | 2024-07-23 | Büro | 2024-08-02 |  | 2024-07-25 |  |  |  | 2024-10-03 | 1039 | 150 |  |  | 2024-11-06 | 149 | SEP | SEP |  |  | 2024-11-30 | 2024-11-30
52169 | 740-DKR-VU117-116-LH099-15-0 | 2 | true | 1.31 | 740-DKR-VU117-116-LH099-15-0 | LV1-105638.VU117 | 386 |  |  | MC1 | LVL 5 | Tt-12 | TR020_1 | 2024-05-29 | 2024-06-05 | 2024-06-05 |  | 2024-07-23 | 2024-07-24 | Büro | 2024-08-02 |  | 2024-07-25 | 2024-10-01 |  |  | 2024-10-03 | 1039 | 150 |  |  | 2024-10-04 | 149 | SEP | SEP |  |  | 2024-11-30 | 2024-11-30
52170 | 740-DKR-VU117-120-LH099-15-0 | 2 | true | 1.12 | 740-DKR-VU117-120-LH099-15-0 | LV1-105638.VU117 | 386 |  |  | MC1 | LVL 5 | Tt-12 | TR020_1 | 2024-05-29 | 2024-06-05 | 2024-06-05 |  | 2024-07-23 | 2024-07-24 | Büro | 2024-08-02 |  | 2024-07-25 | 2024-10-01 |  |  | 2024-10-03 | 1039 | 150 |  |  | 2024-10-04 | 149 | SEP | SEP |  |  | 2024-11-30 | 2024-11-30
52171 | 740-DKR-VU117-121-LH099-15-0 | 2 | true | 0.77 | 740-DKR-VU117-121-LH099-15-0 | LV1-105638.VU117 | 386 |  |  | MC1 | LVL 5 | Tt-12 | TR020_1 | 2024-05-29 | 2024-06-05 | 2024-06-05 |  | 2024-07-23 | 2024-07-24 | Büro | 2024-08-02 |  | 2024-07-26 | 2024-10-03 |  |  | 2024-10-07 | 1039 | 150 |  |  | 2024-10-07 | 149 | SEP | SEP |  |  | 2024-11-30 | 2024-11-30
52172 | 740-DKR-VU117-133-LH099-15-0 | 2 | true | 1.33 | 740-DKR-VU117-133-LH099-15-0 | LV1-105638.VU117 | 386 |  |  | MC1 | LVL 5 | Tt-12 | TR020_1 | 2024-05-29 | 2024-06-05 | 2024-06-05 |  | 2024-07-23 | 2024-07-24 | Büro | 2024-08-02 |  | 2024-07-25 | 2024-09-30 |  |  | 2024-10-04 | 1039 | 150 |  |  | 2024-11-06 | 149 | SEP | SEP |  |  | 2024-11-30 | 2024-11-30
52173 | 740-DKR-VU117-136-LH099-15-0 | 2 | true | 1.02 | 740-DKR-VU117-136-LH099-15-0 | LV0-105628.VP033 | 386 |  |  | MC1 | LVL 5 | Tt-12 | TR020_1 | 2024-05-29 | 2024-06-05 | 2024-06-05 |  | 2024-07-23 | 2024-07-24 | Büro | 2024-08-02 |  | 2024-07-25 |  |  |  | 2024-10-03 | 1039 | 150 |  |  | 2024-11-06 | 149 | SEP | SEP |  |  | 2024-11-30 | 2024-11-30
52174 | 740-DKR-VU117-137-LH099-15-0 | 2 | true | 0.83 | 740-DKR-VU117-137-LH099-15-0 | LV0-105628.VP041 | 386 |  |  | MC1 | LVL 5 | Tt-12 | TR020_1 | 2024-05-29 | 2024-06-05 | 2024-06-05 |  | 2024-07-23 | 2024-07-26 | Büro | 2024-08-02 |  | 2024-07-26 | 2024-09-30 |  |  | 2024-10-07 | 1039 | 150 |  |  | 2024-11-06 | 149 | SEP | SEP |  |  | 2024-11-30 | 2024-11-30
52175 | 740-DKR-VU117-138-LH099-15-0 | 2 | true | 1.01 | 740-DKR-VU117-138-LH099-15-0 | LV0-105628.VP042 | 386 |  |  | MC1 | LVL 5 | Tt-12 | TR020_1 | 2024-05-29 | 2024-06-05 | 2024-06-05 |  | 2024-07-23 | 2024-07-26 | Büro | 2024-08-02 |  | 2024-07-26 | 2024-09-30 |  |  | 2024-10-07 | 1039 | 150 |  |  | 2024-11-06 | 149 | SEP | SEP |  |  | 2024-11-30 | 2024-11-30
52176 | 740-DKR-VU117-139-LH099-15-0 | 2 | true | 0.83 | 740-DKR-VU117-139-LH099-15-0 | LV0-105628.VP043 | 386 |  |  | MC1 | LVL 5 | W23 | TR020_1 | 2024-05-29 | 2024-06-05 | 2024-06-05 |  | 2024-07-23 | 2024-07-26 | Büro | 2024-08-02 |  | 2024-07-26 | 2024-09-30 |  |  | 2024-10-07 | 1039 | 150 |  |  | 2024-11-06 | 149 | SEP | SEP
52177 | 740-DKR-VU117-140-LH099-15-0 | 2 | true | 1.58 | 740-DKR-VU117-140-LH099-15-0 | LV1-105638.VU117 | 386 |  |  | MC1 | LVL 5 | Tt-12 | TR020_1 | 2024-05-29 | 2024-06-05 | 2024-06-05 |  | 2024-07-23 | 2024-07-26 | Büro | 2024-08-02 |  | 2024-07-26 | 2024-09-30 |  |  | 2024-10-01 | 1039 | 150 |  |  | 2024-10-03 | 149 | SEP | SEP |  |  | 2024-11-30 | 2024-11-30
52178 | 740-DKR-VU117-142-LH099-15-0 | 2 | true | 1.04 | 740-DKR-VU117-142-LH099-15-0 | LV1-105628.VP141 | 386 |  |  | MC1 | LVL 5 | Tt-12 | TR020_1 | 2024-05-29 | 2024-06-05 | 2024-06-05 |  | 2024-07-23 | 2024-07-26 | Büro | 2024-08-02 |  | 2024-07-26 | 2024-09-30 |  |  | 2024-10-01 | 1039 | 150 |  |  | 2024-10-03 | 149 | SEP | SEP |  |  | 2024-11-30 | 2024-11-30
52179 | 740-DKR-VU117-144-LH099-15-0 | 2 | true | 0.99 | 740-DKR-VU117-144-LH099-15-0 | LV1-105628.VP143 | 386 |  |  | MC1 | LVL 5 | Tt-12 | TR020_1 | 2024-05-29 | 2024-06-05 | 2024-06-05 |  | 2024-07-22 | 2024-07-24 | Büro | 2024-08-02 |  | 2024-07-26 | 2024-09-30 |  |  | 2024-10-01 | 1039 | 150 |  |  | 2024-10-03 | 149 | SEP | SEP |  |  | 2024-11-30 | 2024-11-30
52180 | 740-DKR-VU117-145-LH099-15-0 | 2 | true | 1.57 | 740-DKR-VU117-145-LH099-15-0 | LV1-105638.VU117 | 386 |  |  | MC1 | LVL 5 | Tt-12 | TR020_1 | 2024-05-29 | 2024-06-05 | 2024-06-05 |  | 2024-07-24 | 2024-07-26 | Büro | 2024-08-02 |  | 2024-07-26 |  |  |  | 2024-10-03 | 1039 | 150 |  |  | 2024-11-06 | 149 | SEP | SEP |  |  | 2024-11-30 | 2024-11-30
52181 | 740-DKR-VU117-154-LH099-15-0 | 2 | true | 1.26 | 740-DKR-VU117-154-LH099-15-0 | LV1-105628.VP131 | 386 |  |  | MC1 | LVL 5 | W23 | TR020_1 | 2024-05-29 | 2024-06-05 | 2024-06-05 |  | 2024-07-22 | 2024-07-24 | Büro | 2024-08-02 |  | 2024-07-26 |  |  |  | 2024-10-04 | 1039 | 150 |  |  | 2024-11-06 | 149 | SEP | SEP |  |  | 2024-11-30 | 2024-11-30
52184 | 740-DR2-VP031-101-LH088-15-0 | 2 | true | 2.62 | 740-DR2-VP031-101-LH088-15-0 | LV0-105628.VP031 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR020_1 | 2024-05-29 | 2024-06-05 | 2024-06-05 |  | 2024-07-24 | 2024-07-24 | Büro | 2024-08-02 |  | 2024-07-31 | 2024-10-09 |  |  | 2024-10-24 | 1005 | 150 |  |  | 2024-10-28 | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
52185 | 740-DR2-VP031-102-LH088-25-0 | 2 | true | 0.78 | 740-DR2-VP031-102-LH088-25-0 | LV0-105638.VU081 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR020_1 | 2024-05-29 | 2024-06-05 | 2024-06-05 |  | 2024-06-18 | 2024-06-19 | Büro | 2024-06-28 |  | 2024-06-21 | 2024-10-09 |  |  | 2024-10-24 | 1005 | 150 |  |  | 2024-10-29 | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
52186 | 740-DR2-VP032-102-LH088-32-0 | 2 | true | 0.72 | 740-DR2-VP032-102-LH088-32-0 | LV0-105638.VU081 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR020_1 | 2024-05-29 | 2024-06-05 | 2024-06-05 |  | 2024-06-18 | 2024-06-19 | Büro | 2024-06-28 |  | 2024-06-21 | 2024-10-09 |  |  | 2024-10-24 | 1005 | 150 |  |  | 2024-10-29 | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
52187 | 740-DR2-VP032-103-LH088-15-0 | 2 | true | 4.12 | 740-DR2-VP032-103-LH088-15-0 | LV0-105628.VP032 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR020_1 | 2024-05-29 | 2024-06-05 | 2024-06-05 |  | 2024-07-22 | 2024-07-30 | Büro | 2024-08-02 |  | 2024-07-30 | 2024-10-09 |  |  | 2024-10-24 | 1005 | 150 |  |  | 2024-10-28 | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
52188 | 740-DR2-VP033-102-LH088-32-0 | 2 | true | 0.73 | 740-DR2-VP033-102-LH088-32-0 | LV0-105638.VU081 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR020_1 | 2024-05-29 | 2024-06-05 | 2024-06-05 |  | 2024-06-20 | 2024-06-21 | Büro | 2024-06-28 |  | 2024-06-26 |  |  |  | 2024-09-27 | 1005 | 150 |  |  | 2024-11-12 | 149 | SEP | SEP
52189 | 740-DR2-VP033-103-LH088-15-0 | 2 | true | 4.33 | 740-DR2-VP033-103-LH088-15-0 | LV0-105628.VP033 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR020_1 | 2024-05-29 | 2024-06-05 | 2024-06-05 |  | 2024-07-22 | 2024-07-30 | Büro | 2024-08-02 |  | 2024-07-30 | 2024-10-09 |  |  | 2024-10-30 | 1005 | 150 |  |  | 2024-10-31 | 149 | SEP | SEP
52190 | 740-DR2-VP041-101-LH088-15-0 | 2 | true | 3.05 | 740-DR2-VP041-101-LH088-15-0 | LV0-105628.VP041 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR020_1 | 2024-05-29 | 2024-06-05 | 2024-06-05 |  | 2024-07-23 | 2024-07-23 | Büro | 2024-08-02 |  | 2024-07-30 | 2024-10-09 |  |  | 2024-10-24 | 1005 | 150 |  |  | 2024-10-28 | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
52191 | 740-DR2-VP041-102-LH088-25-0 | 2 | true | 0.64 | 740-DR2-VP041-102-LH088-25-0 | LV0-105638.VU081 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR020_1 | 2024-05-29 | 2024-06-05 | 2024-06-05 |  | 2024-06-17 | 2024-06-18 | Büro | 2024-06-28 |  | 2024-06-20 | 2024-10-09 |  |  | 2024-10-24 | 1005 | 150 |  |  | 2024-10-29 | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
52192 | 740-DR2-VP042-102-LH088-32-0 | 2 | true | 0.73 | 740-DR2-VP042-102-LH088-32-0 | LV0-105638.VU081 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR020_1 | 2024-05-29 | 2024-06-05 | 2024-06-05 |  | 2024-06-19 | 2024-06-20 | Büro | 2024-06-28 |  | 2024-06-26 | 2024-10-09 |  |  | 2024-10-24 | 1005 | 150 |  |  | 2024-10-28 | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
52193 | 740-DR2-VP042-103-LH088-15-0 | 2 | true | 5.47 | 740-DR2-VP042-103-LH088-15-0 | LV0-105628.VP042 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR020_1 | 2024-05-29 | 2024-06-05 | 2024-06-05 |  | 2024-07-29 | 2024-07-30 | Büro | 2024-08-02 |  | 2024-07-30 | 2024-10-09 |  |  | 2024-10-24 | 1005 | 150 |  |  | 2024-10-28 | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
52194 | 740-DR2-VP043-102-LH088-32-0 | 2 | true | 1.25 | 740-DR2-VP043-102-LH088-32-0 | LV0-105638.VU081 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR020_1 | 2024-05-29 | 2024-06-05 | 2024-06-05 |  | 2024-07-01 | 2024-07-02 | Büro | 2024-07-12 |  | 2024-07-05 | 2024-10-09 |  |  | 2024-10-24 | 1005 | 150 |  |  | 2024-10-28 | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
52195 | 740-DR2-VP043-103-LH088-15-0 | 2 | true | 6.76 | 740-DR2-VP043-103-LH088-15-0 | LV0-105628.VP043 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR020_1 | 2024-05-29 | 2024-06-05 | 2024-06-05 |  | 2024-07-23 | 2024-07-30 | Büro | 2024-08-02 |  | 2024-07-30 | 2024-10-09 |  |  | 2024-10-24 | 1005 | 150 |  |  | 2024-10-28 | 149 | SEP | SEP
52196 | 740-DR2-VP131-101-LH088-25-0 | 2 | true | 5.69 | 740-DR2-VP131-101-LH088-25-0 | LV0-105638.VU081 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR020_1 | 2024-05-29 | 2024-06-05 | 2024-06-05 |  | 2024-07-25 | 2024-07-25 | Büro | 2024-08-02 |  | 2024-07-31 | 2024-10-22 |  |  | 2024-10-30 | 1005 | 150 |  |  | 2024-10-31 | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
52197 | 740-DR2-VP133-101-LH088-20-0 | 2 | true | 6.66 | 740-DR2-VP133-101-LH088-20-0 | LV0-105638.VU081 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR020_1 | 2024-05-29 | 2024-06-05 | 2024-06-05 |  | 2024-07-29 | 2024-07-30 | Büro | 2024-08-02 |  | 2024-07-30 | 2024-10-22 |  |  | 2024-10-30 | 1005 | 150 |  |  | 2024-10-31 | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
52198 | 740-DR2-VP141-101-LH088-25-0 | 2 | true | 6.88 | 740-DR2-VP141-101-LH088-25-0 | LV0-105638.VU081 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR020_1 | 2024-05-29 | 2024-06-05 | 2024-06-05 |  | 2024-07-29 | 2024-07-30 | Büro | 2024-08-02 |  | 2024-07-30 | 2024-09-25 |  |  | 2024-10-04 | 1005 | 150 |  |  |  | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
52199 | 740-DR2-VP143-101-LH088-20-0 | 2 | true | 4.02 | 740-DR2-VP143-101-LH088-20-0 | LV0-105638.VU081 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR020_1 | 2024-05-29 | 2024-06-05 | 2024-06-05 |  | 2024-07-24 | 2024-07-26 | Büro | 2024-08-02 |  | 2024-07-31 | 2024-09-25 |  |  | 2024-10-04 | 1005 | 150 |  |  |  | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
52206 | 740-LS-VU020-140-LH023-25-0 | 2 | true | 11.96 | 740-LS-VU020-140-LH023-25-0 | LV1-105638.VU020 | 368 |  |  | MC1 | LVL 5 | N/A | TR020_1 | 2024-05-29 | 2024-06-05 | 2024-06-05 |  | 2024-07-03 | 2024-07-22 | Büro | 2024-08-02 |  | 2024-07-24 | 2024-09-11 |  |  | 2024-09-16 | 926 | 150 |  |  | 2024-09-17 | 149 | SEP | SEP
52207 | 740-LS-VU020-174-LH099-15-0 | 2 | true | 2.25 | 740-LS-VU020-174-LH099-15-0 | LV1-105638.VU020 | 386 |  |  | MC1 | LVL 5 | N/A | TR020_1 | 2024-05-29 | 2024-06-05 | 2024-06-05 |  | 2024-07-03 | 2024-07-08 | Büro | 2024-07-12 |  | 2024-07-10 |  |  |  | 2024-09-28 | 926 | 150 |  |  | 2024-09-30 | 149 | SEP | SEP
52208 | 740-LS-VU020-179-LH099-15-0 | 2 | true | 3.14 | 740-LS-VU020-179-LH099-15-0 | LV1-105638.VU020 | 386 |  |  | MC1 | LVL 5 | N/A | TR020_1 | 2024-05-29 | 2024-06-05 | 2024-06-05 |  | 2024-07-03 | 2024-07-08 | Büro | 2024-07-12 |  | 2024-07-10 |  |  |  | 2024-09-03 | 926 | 150 |  |  | 2024-09-03 | 149 | SEP | SEP
52227 | 727-DMA-U341-103-LH032-40-0 | 1 | false | 25.43 | 727-DMA-U341-103-LH032-40-0 | LV1-103542-U341 | 385 |  |  | MC1 | LVL XX | N/A | TR020_2 | 2024-06-03 | 2024-06-04 | 2024-06-04 | [11 empty] | 1269 | 150 |  |  |  | 149 | SEP | SEP
52734 | 727-DMA-U341-103-LH032-40-0 | 2 | false | 25.43 | 727-DMA-U341-103-LH032-40-0 | LV1-103542-U341 | 385 |  |  | MC1 | LVL XX | N/A | TR024_2 | 2024-06-17 | 2024-06-04 | 2024-06-04 |  | 2024-07-04 | 2024-07-08 |  | 2024-07-12 |  | 2024-07-10 | 2024-07-19 |  |  | 2024-07-29 | 1269 | 150 |  |  |  | 149 | SEP | SEP
62179 | 727-DMA-U341-103-LH032-40-0 | 3 | true | 14.4 | 727-DMA-U341-103-LH032-40-0 | LV1-103542-U341 | 385 |  |  | MC1 | LVL XX | N/A | TR029_1 | 2024-07-24 | 2024-06-04 | 2024-06-04 |  | 2024-07-04 | 2024-07-08 |  | 2024-07-12 |  | 2024-07-10 | 2024-07-19 |  |  | 2024-07-29 | 1269 | 150 |  |  | 2024-09-11 | 149 | SEP | SEP
52228 | 727-SP-U331-201-LH032-40-0 | 1 | true | 26.29 | 727-SP-U331-201-LH032-40-0 | LV1-103543.U331 | 385 |  |  | MC1 | LVL XX | N/A | TR020_2 | 2024-06-03 | 2024-06-04 | 2024-06-04 |  | 2024-07-05 | 2024-07-16 | Büro | 2024-08-02 |  | 2024-07-23 | 2024-08-09 |  |  | 2024-08-13 | 1270 | 150 |  | 2024-09-13 | 2024-09-09 | 149 | SEP | SEP
52229 | 740-DMA-VU340-101-LH032-25-0 | 1 | true | 15.32 | 740-DMA-VU340-101-LH032-25-0 | LV1-103542-U341 | 385 |  |  | MC1 | LVL 6 | N/A | TR020_2 | 2024-06-03 | 2024-06-04 | 2024-06-04 |  | 2024-07-05 | 2024-07-08 | Büro | 2024-07-12 |  | 2024-07-10 | 2024-08-27 |  |  | 2024-08-28 | 903 | 150 |  |  | 2024-08-30 | 149 | SEP | SEP
52230 | 740-UN-VU330-101-LH023-25-0 | 1 | false | 14.79 | 740-UN-VU330-101-LH023-25-0 | LV1-103543.U330 | 368 |  |  | MC1 | LVL 6 | N/A | TR020_2 | 2024-06-03 | 2024-06-04 | 2024-06-04 | [11 empty] | 908 | 150 |  |  |  | 149 | SEP | SEP
52777 | 740-UN-VU330-101-LH023-25-0 | 2 | true | 14.79 | 740-UN-VU330-101-LH023-25-0 | LV1-103543.U330 | 368 |  |  | MC1 | LVL 6 | N/A | TR025_1 | 2024-06-18 | 2024-06-04 | 2024-06-04 |  | 2024-07-03 | 2024-07-05 |  | 2024-07-12 |  | 2024-07-09 | 2024-07-23 |  |  | 2024-07-24 | 908 | 150 |  | 2024-09-24 | 2024-08-22 | 149 | SEP | SEP
52231 | 740-UN-VU330-202-LH023-50-0 | 1 | true | 41.48 | 740-UN-VU330-202-LH023-50-0 | LV1-103543.U330 | 368 |  |  | MC1 | LVL XX | N/A | TR020_2 | 2024-06-03 | 2024-06-04 | 2024-06-04 |  | 2024-07-08 | 2024-07-09 | Büro | 2024-07-12 |  | 2024-07-11 | 2024-07-18 |  |  | 2024-08-08 | 1271 | 150 |  | 2024-09-24 | 2024-08-22 | 149 | SEP | SEP
52232 | 740-WAn-VS731-101-LH099-20-0 | 1 | true | 0.22 | 740-WAn-VS731-101-LH099-20-0 | LV1-105633.VS731 | 386 |  |  | MC1 | LVL 5 | Tt-12 | TR020_2 | 2024-06-03 | 2024-06-04 | 2024-06-04 |  | 2024-07-04 | 2024-07-05 | Büro | 2024-07-12 |  | 2024-07-09 | 2024-09-09 |  |  | 2024-09-16 | 1034 | 150 |  |  | 2024-09-17 | 149 | SEP | SEP
52233 | 740-WAn-VS731-102-LH099-20-0 | 1 | true | 0.22 | 740-WAn-VS731-102-LH099-20-0 | LV1-105633.VS731 | 386 |  |  | MC1 | LVL 5 | Tt-12 | TR020_2 | 2024-06-03 | 2024-06-04 | 2024-06-04 |  | 2024-07-04 | 2024-07-05 | Büro | 2024-07-12 |  | 2024-07-09 | 2024-09-09 |  |  | 2024-09-16 | 1034 | 150 |  |  | 2024-09-17 | 149 | SEP | SEP
52234 | 740-WAn-VS732-101-LH099-20-0 | 1 | true | 0.22 | 740-WAn-VS732-101-LH099-20-0 | LV1-105633.VS732 | 386 |  |  | MC1 | LVL 5 | N/A | TR020_2 | 2024-06-03 | 2024-06-04 | 2024-06-04 |  | 2024-07-04 | 2024-07-04 | Büro | 2024-07-12 |  | 2024-07-09 | 2024-09-09 |  |  | 2024-09-16 | 1034 | 150 |  |  | 2024-09-17 | 149 | SEP | SEP
52235 | 740-WAn-VS732-102-LH099-20-0 | 1 | true | 0.22 | 740-WAn-VS732-102-LH099-20-0 | LV1-105633.VS732 | 386 |  |  | MC1 | LVL 5 | N/A | TR020_2 | 2024-06-03 | 2024-06-04 | 2024-06-04 |  | 2024-07-04 | 2024-07-05 | Büro | 2024-07-12 |  | 2024-07-09 | 2024-09-09 |  |  | 2024-09-16 | 1034 | 150 |  |  | 2024-09-17 | 149 | SEP | SEP
52236 | 740-WAn-VU160-112-LH032-50-0 | 1 | true | 0.1 | 740-WAn-VU160-112-LH032-50-0 | LV1-105638.VU160 | 385 |  |  | MC1 | LVL 6 | N/A | TR020_2 | 2024-06-03 | 2024-06-04 | 2024-06-04 |  | 2024-07-03 | 2024-07-04 | Büro | 2024-07-12 |  | 2024-07-10 | 2024-09-09 |  |  | 2024-09-10 | 1035 | 150 |  |  | 2024-09-12 | 149 | SEP | SEP
52237 | 740-WAn-VU162-211-LH088-15-0 | 2 | true | 0.14 | 740-WAn-VU162-211-LH088-15-0 | LV1-105639.VU162 | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR020_2 | 2024-06-03 | 2024-06-04 | 2024-06-04 |  | 2024-07-23 | 2024-07-23 | Büro | 2024-08-02 |  | 2024-07-31 |  |  |  | 2024-10-10 | 1036 | 150 |  | 2024-11-08 |  | 149 | SEP | SEP
52238 | 740-WAn-VU162-217-LH099-15-0 | 2 | true | 0.14 | 740-WAn-VU162-217-LH099-15-0 | LV1-105639.VU162 | 386 |  |  | MC1 | LVL 5 | Tt-12 | TR020_2 | 2024-06-03 | 2024-06-04 | 2024-06-04 |  | 2024-07-22 | 2024-07-24 | Büro | 2024-08-02 |  | 2024-07-26 | 2024-10-03 |  |  | 2024-10-12 | 1036 | 150 |  | 2024-11-08 |  | 149 | SEP | SEP
52239 | 740-WAn-VU200-104-LH032-40-0 | 2 | true | 2.18 | 740-WAn-VU200-104-LH032-40-0 | LV0-105638.VU200 | 385 |  |  | MC1 | LVL 4 | N/A | TR020_2 | 2024-06-03 | 2024-06-04 | 2024-06-04 |  | 2024-07-03 | 2024-07-08 | Büro | 2024-07-12 |  | 2024-07-10 | 2024-08-05 |  |  | 2024-08-08 | 914 | 150 |  |  |  | 149 | SEP | SEP
52240 | 740-WAn-VU200-115-LH099-32-0 | 2 | false | 5.73 | 740-WAn-VU200-115-LH099-32-0 | LV1-105628.VP132 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR020_2 | 2024-06-03 | 2024-06-04 | 2024-06-04 | [11 empty] | 1036 | 150 |  |  |  | 149 | SEP | SEP
52583 | 740-WAn-VU200-115-LH099-32-0 | 3 | true | 5.73 | 740-WAn-VU200-115-LH099-32-0 | LV1-105628.VP132 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR024_1 | 2024-06-10 | 2024-06-12 | 2024-06-12 |  | 2024-07-18 | 2024-07-19 | Büro | 2024-08-02 |  | 2024-07-24 | 2024-10-18 |  |  | 2024-10-25 | 1036 | 150 |  |  | 2024-11-04 | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
52241 | 740-WAn-VU200-137-LH099-50-0 | 2 | true | 1.29 | 740-WAn-VU200-137-LH099-50-0 | LV1-105628.VP144 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR020_2 | 2024-06-03 | 2024-06-04 | 2024-06-04 |  | 2024-07-03 | 2024-07-04 | Attila Henter | 2024-07-12 |  | 2024-07-10 | 2024-10-15 |  |  | 2024-10-21 | 1036 | 150 |  |  | 2024-11-05 | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
52242 | 740-WAn-VU200-142-LH099-32-0 | 2 | false | 5.74 | 740-WAn-VU200-142-LH099-32-0 | LV1-105628.VP142 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR020_2 | 2024-06-03 | 2024-06-04 | 2024-06-04 | [11 empty] | 1036 | 150 |  |  |  | 149 | SEP | SEP
52584 | 740-WAn-VU200-142-LH099-32-0 | 3 | true | 5.74 | 740-WAn-VU200-142-LH099-32-0 | LV1-105628.VP142 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR024_1 | 2024-06-10 | 2024-06-12 | 2024-06-12 |  | 2024-07-18 | 2024-07-19 | Attila Henter | 2024-08-02 |  | 2024-07-23 | 2024-10-15 |  |  | 2024-10-21 | 1036 | 150 |  |  | 2024-11-05 | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
52243 | 740-WAn-VU200-147-LH032-15-0 | 1 | true | 0.46 | 740-WAn-VU200-147-LH032-15-0 | LV0-105638.VU200 | 385 |  |  | MC1 | LVL 4 | N/A | TR020_2 | 2024-06-03 | 2024-06-04 | 2024-06-04 |  | 2024-07-22 | 2024-07-24 | Büro | 2024-08-02 |  | 2024-07-26 | 2024-10-03 |  |  | 2024-10-07 | 914 | 150 |  |  | 2024-10-07 | 149 | SEP | SEP
52244 | 740-WAn-VU200-150-LH032-15-0 | 1 | true | 0.42 | 740-WAn-VU200-150-LH032-15-0 | LV0-105638.VU200 | 385 |  |  | MC1 | LVL 4 | N/A | TR020_2 | 2024-06-03 | 2024-06-04 | 2024-06-04 |  | 2024-07-24 | 2024-07-24 | Büro | 2024-08-02 |  | 2024-07-26 | 2024-10-03 |  |  | 2024-10-07 | 914 | 150 |  |  | 2024-10-07 | 149 | SEP | SEP
52245 | 740-WAn-VU200-166-LH032-40-0 | 2 | true | 2.88 | 740-WAn-VU200-166-LH032-40-0 | LV0-105638.VU200 | 385 |  |  | MC1 | LVL 4 | N/A | TR020_2 | 2024-06-03 | 2024-06-04 | 2024-06-04 |  | 2024-07-03 | 2024-07-08 | Büro | 2024-07-12 |  | 2024-07-10 | 2024-08-05 |  |  | 2024-08-08 | 914 | 150 |  |  |  | 149 | SEP | SEP
52246 | 740-WAn-VU200-205-LH032-25-0 | 1 | true | 10.15 | 740-WAn-VU200-205-LH032-25-0 | LV1-105633.VS732 | 385 |  |  | MC1 | LVL 4 | Tt-6 | TR020_2 | 2024-06-03 | 2024-06-04 | 2024-06-04 |  | 2024-07-08 | 2024-07-10 | Büro | 2024-07-12 |  | 2024-07-11 | 2024-08-26 |  |  | 2024-09-16 | 915 | 150 |  |  | 2024-09-17 | 149 | SEP | SEP
52248 | 740-WAn-VU200-246-LH032-25-0 | 1 | true | 9.16 | 740-WAn-VU200-246-LH032-25-0 | LV1-105633.VS731 | 385 |  |  | MC1 | LVL 4 | N/A | TR020_2 | 2024-06-03 | 2024-06-04 | 2024-06-04 |  | 2024-07-09 | 2024-07-11 | Büro | 2024-08-02 |  | 2024-07-12 | 2024-09-03 |  |  | 2024-09-16 | 915 | 150 |  |  | 2024-09-17 | 149 | SEP | SEP
52262 | 740-DKR-VS685-101-LH099-20-0 | 1 | true | 0.35 | 740-DKR-VS685-101-LH099-20-0 |  | 386 |  |  | MC1 | LVL 5 | Tt-12 | TR021_1 | 2024-06-04 | 2024-06-05 | 2024-06-05 |  | 2024-07-04 | 2024-07-05 | Büro | 2024-07-12 |  | 2024-07-09 | 2024-10-04 |  |  | 2024-10-10 | 1039 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-11-30 | 2024-11-30
52263 | 740-DKR-VU117-102-LH099-20-0 | 1 | true | 1 | 740-DKR-VU117-102-LH099-20-0 | LV1-105638.VU117 | 386 |  |  | MC1 | LVL 5 | Tt-12 | TR021_1 | 2024-06-04 | 2024-06-05 | 2024-06-05 |  | 2024-07-04 | 2024-07-05 | Büro | 2024-07-12 |  | 2024-07-09 | 2024-10-04 |  |  | 2024-10-10 | 1039 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-11-30 | 2024-11-30
52265 | 740-DR2-VS685-101-LH088-20-0 | 1 | true | 0 | 740-DR2-VS685-101-LH088-20-0 |  | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR021_1 | 2024-06-04 | 2024-06-05 | 2024-06-05 |  | 2024-07-08 | 2024-07-09 | Büro | 2024-07-12 |  | 2024-07-09 | 2024-10-24 |  |  | 2024-10-30 | 1005 | 150 |  |  | 2024-10-31 | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
52266 | 740-DR2-VS685-102-LH088-20-0 | 1 | true | 0.59 | 740-DR2-VS685-102-LH088-20-0 |  | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR021_1 | 2024-06-04 | 2024-06-05 | 2024-06-05 |  | 2024-07-05 | 2024-07-08 | Büro | 2024-07-12 |  | 2024-07-10 | 2024-10-24 |  |  | 2024-10-30 | 1005 | 150 |  |  | 2024-10-31 | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
52267 | 740-DR2-VS685-103-LH088-20-0 | 1 | false | 0.83 | 740-DR2-VS685-103-LH088-20-0 |  | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR021_1 | 2024-06-04 | 2024-06-05 | 2024-06-05 | [11 empty] | 1005 | 150 |  |  |  | 149 | SEP | SEP
52568 | 740-DR2-VS685-103-LH088-20-0 | 2 | true | 0.83 | 740-DR2-VS685-103-LH088-20-0 |  | 391 |  |  | MC1 | LVL 5 | Tt-12 | TR024_1 | 2024-06-10 | 2024-06-11 | 2024-06-11 |  | 2024-07-05 | 2024-07-10 | Büro | 2024-07-12 |  | 2024-07-10 | 2024-10-24 |  |  | 2024-10-30 | 1005 | 150 |  |  | 2024-10-31 | 149 | SEP | SEP |  |  | 2024-11-30 | 2024-11-30 | 2024-11-30 | 2024-11-30
52271 | 740-AB-VS685-101-LH099-15-0 | 1 | true | 2.38 | 740-AB-VS685-101-LH099-15-0 |  | 386 |  |  | MC1 | LVL 5 | N/A | TR021_2 | 2024-06-05 | 2024-06-05 | 2024-06-05 |  | 2024-07-24 | 2024-07-25 | Büro | 2024-08-02 |  | 2024-07-26 |  |  |  | 2024-11-06 | 1272 | 150 |  |  |  | 149 | SEP | SEP
52273 | 740-CIP-R-VS631-101-LH089-40-0 | 1 | true | 0.28 | 740-CIP-R-VS631-101-LH089-40-0 |  | 394 |  |  | MC1 | LVL 5 | Tt-6 | TR021_2 | 2024-06-05 | 2024-06-05 | 2024-06-05 |  | 2024-07-19 | 2024-07-19 | Dawid Mierzwa | 2024-08-02 |  | 2024-07-30 | 2024-10-24 |  |  | 2024-11-08 | 928 | 150 |  |  |  | 149 | SEP | SEP
52274 | 740-CIP-R-VS685-101-LH089-40-0 | 1 | true | 0 | 740-CIP-R-VS685-101-LH089-40-0 |  | 394 |  |  | MC1 | LVL 5 | Tt-6 | TR021_2 | 2024-06-05 | 2024-06-05 | 2024-06-05 |  | 2024-07-25 | 2024-07-30 | Dawid Mierzwa | 2024-08-02 |  | 2024-07-30 | 2024-10-24 |  |  | 2024-11-08 | 928 | 150 |  |  |  | 149 | SEP | SEP
52276 | 740-CIP-S-VS685-108-LH089-25-0 | 1 | true | 0.35 | 740-CIP-S-VS685-108-LH089-25-0 |  | 394 |  |  | MC1 | LVL 5 | Tt-6 | TR021_2 | 2024-06-05 | 2024-06-05 | 2024-06-05 |  | 2024-08-21 | 2024-08-22 | Büro | 2024-08-23 |  | 2024-08-22 | 2024-10-24 |  |  | 2024-10-30 | 928 | 150 |  |  | 2024-10-31 | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
52277 | 740-CIP-S-VS685-110-LH089-15-0 | 1 | false | 0.33 | 740-CIP-S-VS685-110-LH089-15-0 |  | 394 |  |  | MC1 | LVL 5 | Tt-6 | TR021_2 | 2024-06-05 | 2024-06-05 | 2024-06-05 | [11 empty] | 928 | 150 |  |  |  | 149 | SEP | SEP
52736 | 740-CIP-S-VS685-110-LH089-15-0 | 2 | true | 0.33 | 740-CIP-S-VS685-110-LH089-15-0 |  | 394 |  |  | MC1 | LVL 5 | Tt-6 | TR024_2 | 2024-06-17 | 2024-06-05 | 2024-06-05 |  | 2024-07-02 | 2024-07-10 | Büro | 2024-07-12 |  | 2024-07-10 | 2024-10-24 |  |  | 2024-10-30 | 928 | 150 |  |  | 2024-10-31 | 149 | SEP | SEP |  |  | 2024-11-15 | 2024-11-15
52279 | 740-WAn-VS631-101-LH099-40-0 | 1 | true | 3.86 | 740-WAn-VS631-101-LH099-40-0 |  | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR021_2 | 2024-06-05 | 2024-06-05 | 2024-06-05 |  | 2024-07-05 | 2024-07-08 | Büro | 2024-07-12 |  | 2024-07-11 | 2024-10-22 |  |  | 2024-10-30 | 1036 | 150 |  |  | 2024-11-04 | 149 | SEP | SEP
52280 | 740-WAn-VS631-102-LH099-40-0 | 1 | true | 0.14 | 740-WAn-VS631-102-LH099-40-0 |  | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR021_2 | 2024-06-05 | 2024-06-05 | 2024-06-05 |  | 2024-07-04 | 2024-07-05 | Büro | 2024-07-12 |  | 2024-07-09 | 2024-10-22 |  |  | 2024-10-30 | 1036 | 150 |  |  | 2024-11-04 | 149 | SEP | SEP
52281 | 740-WAn-VS685-101-LH099-15-0 | 1 | true | 0.45 | 740-WAn-VS685-101-LH099-15-0 |  | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR021_2 | 2024-06-05 | 2024-06-05 | 2024-06-05 |  | 2024-07-24 | 2024-07-25 | Buro | 2024-08-02 |  | 2024-07-26 | 2024-10-22 |  |  | 2024-12-18 | 1036 | 150 |  |  |  | 149 | SEP | SEP
52282 | 740-WAn-VS685-102-LH099-15-0 | 1 | true | 0.13 | 740-WAn-VS685-102-LH099-15-0 |  | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR021_2 | 2024-06-05 | 2024-06-05 | 2024-06-05 |  | 2024-07-22 | 2024-07-22 | Büro | 2024-08-02 |  | 2024-07-23 | 2024-10-22 |  |  | 2024-10-30 | 1036 | 150 |  |  | 2024-11-04 | 149 | SEP | SEP
52283 | 740-WAn-VS685-103-LH099-15-0 | 1 | true | 0.04 | 740-WAn-VS685-103-LH099-15-0 |  | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR021_2 | 2024-06-05 | 2024-06-05 | 2024-06-05 |  | 2024-07-22 |  | Büro | 2024-08-23 |  |  | 2024-10-22 |  |  | 2024-10-30 | 1036 | 150 |  |  | 2024-11-04 | 149 | SEP | SEP
52284 | 740-WAn-VS685-104-LH099-15-0 | 1 | true | 0.13 | 740-WAn-VS685-104-LH099-15-0 |  | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR021_2 | 2024-06-05 | 2024-06-05 | 2024-06-05 |  | 2024-07-22 | 2024-07-22 | Büro | 2024-08-02 |  | 2024-07-23 | 2024-10-22 |  |  | 2024-10-30 | 1036 | 150 |  |  | 2024-11-04 | 149 | SEP | SEP
52285 | 740-WAn-VS685-105-LH089-15-0 | 1 | true | 0.09 | 740-WAn-VS685-105-LH089-15-0 |  | 394 |  |  | MC1 | LVL 5 | Tt-6 | TR021_2 | 2024-06-05 | 2024-06-05 | 2024-06-05 |  | 2024-07-08 | 2024-07-10 | Dawid Mierzwa | 2024-07-12 |  | 2024-07-10 | 2024-10-24 |  |  | 2024-11-08 | 1036 | 150 |  |  |  | 149 | SEP | SEP
52286 | 740-WAn-VS685-106-LH099-15-0 | 1 | true | 0.17 | 740-WAn-VS685-106-LH099-15-0 |  | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR021_2 | 2024-06-05 | 2024-06-05 | 2024-06-05 |  | 2024-07-22 | 2024-07-23 | Büro | 2024-08-02 |  | 2024-07-25 | 2024-10-22 |  |  | 2024-11-06 | 1036 | 150 |  |  |  | 149 | SEP | SEP
52287 | 740-WAn-VS685-107-LH099-40-0 | 1 | true | 0.68 | 740-WAn-VS685-107-LH099-40-0 |  | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR021_2 | 2024-06-05 | 2024-06-05 | 2024-06-05 |  | 2024-07-05 | 2024-07-08 | Büro | 2024-07-12 |  | 2024-07-10 | 2024-10-22 |  |  | 2024-10-30 | 1036 | 150 |  |  | 2024-11-04 | 149 | SEP | SEP
52288 | 740-WAn-VU160-107-LH032-40-0 | 1 | true | 0.08 | 740-WAn-VU160-107-LH032-40-0 |  | 386 |  |  | MC1 | LVL 6 | N/A | TR021_2 | 2024-06-05 | 2024-06-05 | 2024-06-05 |  | 2024-07-04 | 2024-07-05 | Büro | 2024-07-12 |  | 2024-07-09 | 2024-09-09 |  |  | 2024-09-10 | 1035 | 150 |  |  | 2024-09-12 | 149 | SEP | SEP
52289 | 740-WAn-VU200-135-LH099-40-0 | 1 | true | 0.36 | 740-WAn-VU200-135-LH099-40-0 |  | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR021_2 | 2024-06-05 | 2024-06-05 | 2024-06-05 |  | 2024-07-04 | 2024-07-05 | Büro | 2024-07-12 |  | 2024-07-09 | 2024-10-22 |  |  | 2024-10-30 | 1036 | 150 |  |  | 2024-11-04 | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
52290 | 740-WAn-VU200-165-LH032-40-0 | 1 | true | 1.14 | 740-WAn-VU200-165-LH032-40-0 | LV0-105638.VU200 | 385 |  |  | MC1 | LVL 4 | N/A | TR021_2 | 2024-06-05 | 2024-06-05 | 2024-06-05 |  | 2024-07-03 | 2024-07-04 | Büro | 2024-07-12 |  | 2024-07-08 | 2024-08-05 |  |  | 2024-10-23 | 914 | 150 |  |  | 2024-11-05 | 149 | SEP | SEP
52524 | 740-LP-VS685-101-LH099-20-0 | 1 | true | 0 | 740-LP-VS685-101-LH099-20-0 | LV1-105633.VS685 | 386 |  |  | MC1 | LVL 5 | N/A | TR021_3 | 2024-06-10 | 2024-06-11 | 2024-06-11 |  | 2024-07-08 | 2024-07-09 | Büro | 2024-07-12 |  | 2024-07-09 |  |  |  | 2024-11-04 | 929 | 150 |  |  | 2024-11-05 | 149 | SEP | SEP
52525 | 740-AB-VS685-102-LH099-15-0 | 2 | true | 0.1 | 740-AB-VS685-102-LH099-15-0 | LV1-105633.VS685 | 386 |  |  | MC1 | LVL 5 | N/A | TR024_1 | 2024-06-10 | 2024-06-11 | 2024-06-11 |  | 2024-07-23 | 2024-07-24 |  | 2024-08-02 |  | 2024-07-26 | 2024-11-07 | 2024-11-07 | 2024-11-07 | 2024-11-07 | 1272 | 150 |  |  |  | 149 | SEP | SEP
52526 | 740-DKR-VP001-101-LH099-15-0 | 1 | true | 0 | 740-DKR-VP001-101-LH099-15-0 | LV0-105628.VP001 | 386 |  |  | MC1 | LVL 5 | Tt-12 | TR024_1 | 2024-06-10 | 2024-06-11 | 2024-06-11 |  | 2024-07-23 | 2024-07-23 | Büro | 2024-08-02 |  | 2024-07-30 | 2024-09-30 |  |  | 2024-10-02 | 1039 | 150 |  | 2024-11-13 | 2024-10-02 | 149 | SEP | SEP
52527 | 740-DKR-VP002-101-LH099-15-0 | 1 | true | 0 | 740-DKR-VP002-101-LH099-15-0 | LV0-105628.VP002 | 386 |  |  | MC1 | LVL 5 | Tt-12 | TR024_1 | 2024-06-10 | 2024-06-11 | 2024-06-11 |  | 2024-07-30 |  | Büro | 2024-08-02 |  | 2024-07-30 | 2024-09-27 |  |  | 2024-09-30 | 1039 | 150 |  |  | 2024-09-30 | 149 | SEP | SEP
52528 | 740-DKR-VP003-101-LH099-15-0 | 1 | true | 0 | 740-DKR-VP003-101-LH099-15-0 | LV0-105628.VP003 | 386 |  |  | MC1 | LVL 5 | Tt-12 | TR024_1 | 2024-06-10 | 2024-06-11 | 2024-06-11 |  | 2024-07-30 |  | Büro | 2024-08-02 |  | 2024-07-30 | 2024-09-27 |  |  | 2024-09-30 | 1039 | 150 |  |  | 2024-09-30 | 149 | SEP | SEP
52529 | 740-DKR-VP004-101-LH099-15-0 | 1 | true | 0 | 740-DKR-VP004-101-LH099-15-0 | LV0-105628.VP004 | 386 |  |  | MC1 | LVL 5 | Tt-12 | TR024_1 | 2024-06-10 | 2024-06-11 | 2024-06-11 |  | 2024-07-23 | 2024-07-24 | Büro | 2024-08-02 |  | 2024-07-25 | 2024-09-27 |  |  | 2024-09-30 | 1039 | 150 |  |  | 2024-09-30 | 149 | SEP | SEP |  |  | 2024-11-30 | 2024-11-30
52530 | 740-DKR-VP132-101-LH099-15-0 | 1 | true | 0.16 | 740-DKR-VP132-101-LH099-15-0 | LV1-105628.VP132 | 386 |  |  | MC1 | LVL 5 | Tt-12 | TR024_1 | 2024-06-10 | 2024-06-11 | 2024-06-11 |  | 2024-07-23 |  | Büro | 2024-08-02 |  | 2024-07-26 |  |  |  | 2024-10-03 | 1039 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-11-30 | 2024-11-30
52531 | 740-DKR-VP142-101-LH099-15-0 | 1 | true | 0.16 | 740-DKR-VP142-101-LH099-15-0 | LV1-105628.VP142 | 386 |  |  | MC1 | LVL 5 | Tt-12 | TR024_1 | 2024-06-10 | 2024-06-11 | 2024-06-11 |  | 2024-07-23 |  | Büro | 2024-08-02 |  | 2024-07-26 | 2024-09-30 |  |  | 2024-10-01 | 1039 | 150 |  |  | 2024-10-03 | 149 | SEP | SEP |  |  | 2024-11-30 | 2024-11-30
52532 | 740-DKR-VS001-101-LH099-15-0 | 1 | true | 0.25 | 740-DKR-VS001-101-LH099-15-0 | LV1-105633.VS001 | 386 |  |  | MC1 | LVL 5 | Tt-12 | TR024_1 | 2024-06-10 | 2024-06-11 | 2024-06-11 |  | 2024-07-24 | 2024-07-25 | Büro | 2024-08-02 |  | 2024-07-26 |  |  |  | 2024-10-03 | 1039 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-11-30 | 2024-11-30
52533 | 740-DKR-VU081-103-LH011-15-0 | 1 | true | 0.05 | 740-DKR-VU081-103-LH011-15-0 | LV0-105638.VU081 | 369 |  |  | MC1 | LVL 6 | W23 | TR024_1 | 2024-06-10 | 2024-06-11 | 2024-06-11 |  | 2024-07-23 | 2024-07-26 | Büro | 2024-08-02 |  | 2024-07-26 | 2024-09-26 |  |  | 2024-10-02 | 1038 | 150 |  |  | 2024-09-30 | 149 | SEP | SEP | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22
52534 | 740-DKR-VU081-104-LH011-15-0 | 1 | true | 0.1 | 740-DKR-VU081-104-LH011-15-0 | LV0-105638.VU081 | 369 |  |  | MC1 | LVL 6 | W23 | TR024_1 | 2024-06-10 | 2024-06-11 | 2024-06-11 |  | 2024-07-23 | 2024-07-25 | Büro | 2024-08-02 |  | 2024-07-26 | 2024-09-04 |  |  | 2024-09-10 | 1038 | 150 |  |  | 2024-09-11 | 149 | SEP | SEP | 2024-09-26 | 2024-11-22 | 2024-11-22 | 2024-11-22
52535 | 740-DKR-VU081-106-LH011-15-0 | 1 | true | 0.03 | 740-DKR-VU081-106-LH011-15-0 | LV0-105638.VU081 | 369 |  |  | MC1 | LVL 6 | W23 | TR024_1 | 2024-06-10 | 2024-06-11 | 2024-06-11 |  | 2024-07-23 | 2024-07-25 | Büro | 2024-08-02 |  | 2024-07-26 | 2024-09-26 |  |  | 2024-09-30 | 1038 | 150 |  |  | 2024-09-30 | 149 | SEP | SEP | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22
52536 | 740-DKR-VU081-108-LH011-15-0 | 1 | true | 0 | 740-DKR-VU081-108-LH011-15-0 | LV0-105638.VU081 | 369 |  |  | MC1 | LVL 6 | W23 | TR024_1 | 2024-06-10 | 2024-06-11 | 2024-06-11 |  |  | 2024-07-26 | Büro | 2024-08-02 |  | 2024-07-26 | 2024-09-04 |  |  | 2024-09-10 | 1038 | 150 |  |  | 2024-09-11 | 149 | SEP | SEP | 2024-09-26
52537 | 740-DKR-VU081-110-LH011-15-0 | 1 | true | 0.07 | 740-DKR-VU081-110-LH011-15-0 | LV0-105638.VU081 | 369 |  |  | MC1 | LVL 6 | W23 | TR024_1 | 2024-06-10 | 2024-06-11 | 2024-06-11 |  | 2024-07-23 | 2024-07-26 | Büro | 2024-08-02 |  | 2024-07-26 | 2024-09-19 |  |  | 2024-09-19 | 1038 | 150 |  |  |  | 149 | SEP | SEP | 2024-09-26
52538 | 740-DKR-VU081-111-LH011-15-0 | 1 | true | 0.05 | 740-DKR-VU081-111-LH011-15-0 | LV0-105638.VU081 | 369 |  |  | MC1 | LVL 6 | W23 | TR024_1 | 2024-06-10 | 2024-06-11 | 2024-06-11 |  | 2024-07-23 | 2024-07-25 | Büro | 2024-08-02 |  | 2024-07-26 | 2024-09-25 |  |  | 2024-09-27 | 1038 | 150 |  |  |  | 149 | SEP | SEP | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22
52539 | 740-DKR-VU081-112-LH011-15-0 | 1 | true | 0.14 | 740-DKR-VU081-112-LH011-15-0 | LV0-105638.VU081 | 369 |  |  | MC1 | LVL 6 | W23 | TR024_1 | 2024-06-10 | 2024-06-11 | 2024-06-11 |  | 2024-07-23 | 2024-07-25 | Büro | 2024-08-02 |  | 2024-07-26 |  |  |  | 2024-09-28 | 1038 | 150 |  |  | 2024-09-30 | 149 | SEP | SEP | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22
52540 | 740-DKR-VU081-113-LH011-15-0 | 1 | true | 0.4 | 740-DKR-VU081-113-LH011-15-0 | LV0-105638.VU081 | 369 |  |  | MC1 | LVL 6 | W23 | TR024_1 | 2024-06-10 | 2024-06-11 | 2024-06-11 |  | 2024-07-23 | 2024-07-25 | Büro | 2024-08-02 |  | 2024-07-26 |  |  |  | 2024-09-28 | 1038 | 150 |  |  | 2024-09-30 | 149 | SEP | SEP | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22
52542 | 740-DKR-VU081-120-LH011-15-0 | 1 | true | 0.27 | 740-DKR-VU081-120-LH011-15-0 | LV0-105638.VU081 | 369 |  |  | MC1 | LVL 6 | W23 | TR024_1 | 2024-06-10 | 2024-06-11 | 2024-06-11 |  | 2024-07-23 | 2024-07-25 | Büro | 2024-08-02 |  | 2024-07-26 | 2024-09-25 |  |  | 2024-09-27 | 1038 | 150 |  |  |  | 149 | SEP | SEP | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22
52543 | 740-DKR-VU081-124-LH011-20-0 | 1 | true | 0.05 | 740-DKR-VU081-124-LH011-20-0 | LV1-105638.VU117 | 369 |  |  | MC1 | LVL 5 | W23 | TR024_1 | 2024-06-10 | 2024-06-11 | 2024-06-11 |  | 2024-07-23 | 2024-07-23 | Büro | 2024-08-02 |  | 2024-07-25 |  |  |  | 2024-10-04 | 1039 | 150 |  |  |  | 149 | SEP | SEP | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22
52556 | 740-DKR-VU117-146-LH011-20-0 | 3 | true | 4.08 | 740-DKR-VU117-146-LH011-20-0 | LV1-105638.VU117 | 369 |  |  | MC1 | LVL 5 | W23 | TR024_1 | 2024-06-10 | 2024-06-11 | 2024-06-11 |  | 2024-07-08 | 2024-07-09 | Büro | 2024-07-12 |  | 2024-07-11 |  |  |  | 2024-10-03 | 1039 | 150 |  |  | 2024-10-04 | 149 | SEP | SEP | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22
52557 | 740-DKR-VU117-153-LH099-15-0 | 3 | true | 1.28 | 740-DKR-VU117-153-LH099-15-0 | LV1-105633.VS001 | 386 |  |  | MC1 | LVL 5 | Tt-12 | TR024_1 | 2024-06-10 | 2024-06-11 | 2024-06-11 |  | 2024-07-22 | 2024-07-24 | Büro | 2024-08-02 |  | 2024-07-26 |  |  |  | 2024-10-03 | 1039 | 150 |  |  | 2024-11-06 | 149 | SEP | SEP |  |  | 2024-11-30 | 2024-11-30
52575 | 740-HKK-S-VP142-101-LH099-40-0 | 2 | true | 9.76 | 740-HKK-S-VP142-101-LH099-40-0 | LV1-105629.VP142 | 386 |  |  | MC1 | LVL 5 | WK60 | TR024_1 | 2024-06-10 |  |  |  | 2024-07-03 | 2024-07-04 | Büro | 2024-07-12 |  | 2024-07-10 | 2024-09-20 |  |  | 2024-09-25 | 1006 | 150 |  |  |  | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
52576 | 740-HKK-S-VP143-101-LH099-40-0 | 2 | true | 10.33 | 740-HKK-S-VP143-101-LH099-40-0 | LV1-105629.VP143 | 386 |  |  | MC1 | LVL 5 | WK60 | TR024_1 | 2024-06-10 | 2024-06-12 | 2024-06-12 |  | 2024-07-04 | 2024-07-05 | Büro | 2024-07-12 |  | 2024-07-10 | 2024-09-03 |  |  | 2024-09-12 | 1006 | 150 |  |  | 2024-09-12 | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
52577 | 740-LP-VS685-102-LH099-20-0 | 2 | true | 1.29 | 740-LP-VS685-102-LH099-20-0 | LV1-105633.VS685 | 386 |  |  | MC1 | LVL 5 | N/A | TR024_1 | 2024-06-10 | 2024-06-12 | 2024-06-12 |  | 2024-07-24 | 2024-07-25 | Büro | 2024-08-02 |  | 2024-07-26 |  |  |  | 2024-11-04 | 929 | 150 |  |  | 2024-11-05 | 149 | SEP | SEP
52578 | 740-LP-VS685-103-LH099-15-0 | 2 | true | 1.63 | 740-LP-VS685-103-LH099-15-0 | LV1-105633.VS685 | 386 |  |  | MC1 | LVL 5 | N/A | TR024_1 | 2024-06-10 | 2024-06-12 | 2024-06-12 |  | 2024-07-24 | 2024-07-25 | Buro | 2024-08-02 |  | 2024-07-30 |  |  |  | 2024-12-18 | 929 | 150 |  |  |  | 149 | SEP | SEP
52579 | 740-LP-VS685-104-LH089-15-0 | 2 | true | 0 | 740-LP-VS685-104-LH089-15-0 | LV1-105633.VS685 | 394 |  |  | MC1 | LVL 5 | N/A | TR024_1 | 2024-06-10 | 2024-06-12 | 2024-06-12 |  | 2024-07-25 | 2024-07-23 | Buro | 2024-08-02 |  | 2024-07-31 | 2024-10-24 |  |  | 2024-12-18 | 929 | 150 |  |  |  | 149 | SEP | SEP
52580 | 740-LP-VS685-105-LH089-25-0 | 2 | true | 0 | 740-LP-VS685-105-LH089-25-0 | LV1-105633.VS685 | 394 |  |  | MC1 | LVL 5 | N/A | TR024_1 | 2024-06-10 | 2024-06-12 | 2024-06-12 |  | 2024-07-30 |  | Buro | 2024-08-02 |  | 2024-07-30 | 2024-10-24 |  |  | 2024-12-18 | 929 | 150 |  |  |  | 149 | SEP | SEP
52581 | 740-WAn-VP132-124-LH099-32-0 | 1 | true | 0.12 | 740-WAn-VP132-124-LH099-32-0 | LV1-105628.VP132 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR024_1 | 2024-06-10 | 2024-06-12 | 2024-06-12 |  | 2024-07-18 | 2024-07-18 | Büro | 2024-08-02 |  | 2024-07-23 | 2024-10-18 |  |  | 2024-10-25 | 1036 | 150 |  |  | 2024-11-04 | 149 | SEP | SEP
52582 | 740-WAn-VP142-124-LH099-32-0 | 1 | true | 0.12 | 740-WAn-VP142-124-LH099-32-0 | LV1-105628.VP142 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR024_1 | 2024-06-10 | 2024-06-12 | 2024-06-12 |  | 2024-07-18 | 2024-07-18 | Attila Henter | 2024-08-02 |  | 2024-07-23 | 2024-10-15 |  |  | 2024-10-21 | 1036 | 150 |  |  | 2024-10-29 | 149 | SEP | SEP
52585 | 740-WFI-VS001-101-LH089-40-0 | 2 | true | 1.07 | 740-WFI-VS001-101-LH089-40-0 | LV1-105633.VS001 | 394 |  |  | MC1 | LVL 5 | W23 | TR024_1 | 2024-06-10 | 2024-07-12 | 2024-07-12 |  | 2024-07-25 | 2024-07-30 | Dawid Mierzwa | 2024-08-02 |  | 2024-07-30 | 2024-10-24 |  |  | 2024-11-08 | 938 | 150 |  |  |  | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
52586 | 740-WFI-VS001-102-LH089-40-0 | 2 | true | 1.33 | 740-WFI-VS001-102-LH089-40-0 | LV1-105633.VS001 | 394 |  |  | MC1 | LVL 5 | W23 | TR024_1 | 2024-06-10 | 2024-06-12 | 2024-06-12 |  | 2024-07-22 | 2024-07-30 | Dawid Mierzwa | 2024-08-02 |  | 2024-07-30 | 2024-10-24 |  |  | 2024-11-08 | 937 | 150 |  |  |  | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
52587 | 740-WFI-VS001-103-LH089-40-0 | 1 | true | 0.67 | 740-WFI-VS001-103-LH089-40-0 | LV1-105633.VS001 | 394 |  |  | MC1 | LVL 5 | W23 | TR024_1 | 2024-06-10 | 2024-06-12 | 2024-06-12 |  | 2024-07-22 | 2024-07-30 | Dawid Mierzwa | 2024-08-02 |  | 2024-07-30 | 2024-10-24 |  |  | 2024-11-08 | 938 | 150 |  |  |  | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
52588 | 740-WFI-VS001-104-LH089-40-0 | 1 | true | 0.67 | 740-WFI-VS001-104-LH089-40-0 | LV1-105633.VS001 | 394 |  |  | MC1 | LVL 5 | W23 | TR024_1 | 2024-06-10 | 2024-06-12 | 2024-06-12 |  | 2024-07-25 | 2024-07-30 | Dawid Mierzwa | 2024-08-02 |  | 2024-07-30 | 2024-10-24 |  |  | 2024-11-08 | 937 | 150 |  |  |  | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
52713 | 740-CIP-S-VP130-102-LH089-25-0 | 1 | true | 12.95 | 740-CIP-S-VP130-102-LH089-25-0 | LV1-105633.VS682 | 394 |  |  | MC1 | LVL 5 | W23 | TR013_6 | 2024-06-17 | 2024-06-17 | 2024-06-17 |  | 2024-08-22 | 2024-08-22 | Büro | 2024-08-23 |  | 2024-08-22 |  |  | 2024-09-16 | 2024-10-04 | 928 | 150 |  |  |  | 149 | SEP | SEP | 2024-11-08 | 2024-11-08 | 2024-11-08 | 2024-11-15
52714 | 740-CIP-S-VP140-102-LH089-25-0 | 1 | true | 34.94 | 740-CIP-S-VP140-102-LH089-25-0 | LV1-105633.VS683 | 394 |  |  | MC1 | LVL 5 | W23 | TR013_6 | 2024-06-17 | 2024-06-17 | 2024-06-17 |  | 2024-08-20 | 2024-08-22 |  | 2024-08-23 |  | 2024-08-22 | 2024-09-09 |  |  | 2024-10-18 | 928 | 150 |  |  | 2024-10-29 | 149 | SEP | SEP | 2024-11-08 | 2024-11-08 | 2024-11-08 | 2024-11-15
52715 | 740-WAn-VU200-183-LH032-100-0 | 1 | true | 20.27 | 740-WAn-VU200-183-LH032-100-0 | LV0-105638.VU200 | 385 |  |  | MC1 | LVL 5 | W60 | TR013_6 | 2024-06-17 | 2024-06-17 | 2024-06-17 |  | 2024-06-26 | 2024-06-26 | Büro | 2024-06-28 |  | 2024-06-27 | 2024-07-10 |  | 2024-07-17 | 2024-08-09 | 1036 | 150 |  | 2024-10-09 |  | 149 | SEP | SEP | 2024-09-27 | 2024-10-04 | 2024-10-04
52732 | 740-CIP-S-VP137-101-LH089-40-0 | 1 | true | 2.87 | 740-CIP-S-VP137-101-LH089-40-0 | LV1-105628.VP137 | 394 |  |  | MC1 | LVL 5 | W23 | TR015_9 | 2024-06-17 | 2024-06-17 | 2024-06-17 |  | 2024-07-23 | 2024-07-24 | Dawid Mierzwa | 2024-08-02 |  | 2024-07-31 | 2024-09-27 |  |  | 2024-10-18 | 928 | 150 |  |  | 2024-10-29 | 149 | SEP | SEP |  |  | 2024-11-15 | 2024-11-15
52733 | 740-CIP-S-VP147-101-LH089-40-0 | 1 | true | 2.92 | 740-CIP-S-VP147-101-LH089-40-0 | LV1-105628.VP147 | 394 |  |  | MC1 | LVL 5 | Tt-6 | TR015_9 | 2024-06-17 | 2024-06-17 | 2024-06-17 |  | 2024-07-29 | 2024-07-25 | Büro | 2024-08-02 |  | 2024-07-25 |  |  |  | 2024-10-24 | 928 | 150 |  |  | 2024-10-28 | 149 | SEP | SEP
52735 | 740-CIP-S-VS685-109-LH089-25-0 | 2 | true | 0.36 | 740-CIP-S-VS685-109-LH089-25-0 | LV1-105633.VS685 | 394 |  |  | MC1 | LVL 5 | Tt-6 | TR024_2 | 2024-06-17 | 2024-06-17 | 2024-06-17 |  | 2024-08-21 | 2024-08-22 | Büro | 2024-08-23 |  | 2024-08-22 | 2024-10-24 |  |  | 2024-10-30 | 928 | 150 |  |  | 2024-10-31 | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
52737 | 740-N2-VP010-101-LH099-15-0 | 1 | true | 20.53 | 740-N2-VP010-101-LH099-15-0 | LV1-105638.VU060 | 386 |  |  | MC1 | LVL 5 | N/A | TR024_2 | 2024-06-17 | 2024-06-17 | 2024-06-17 |  | 2024-07-22 | 2024-07-26 | Büro | 2024-08-02 |  | 2024-07-26 | 2024-08-23 |  |  | 2024-09-03 | 930 | 150 |  | 2024-11-12 |  | 149 | SEP | SEP
52771 | 727-UN-U330-202-LH023-50-0 | 1 | false | 41.48 | 727-UN-U330-202-LH023-50-0 | LV1-103543.U330 | 368 |  |  | MC1 | LVL 5 | N/A | TR025_1 | 2024-06-18 | 2024-06-18 | 2024-06-18 |  | 2024-07-24 | 2024-07-26 |  | 2024-08-02 |  | 2024-07-31 | 2024-07-18 |  |  | 2024-08-08 | 1271 | 150 |  |  | 2024-08-22 | 149 | SEP | SEP
52774 | 740-FLN-VP131-115-LH089-10-0 | 2 | true | 6.14 | 740-FLN-VP131-115-LH089-10-0 | LV1-105628.VP137 | 394 |  |  | MC1 | LVL 5 | Tt-6 | TR025_1 | 2024-06-18 | 2024-06-18 | 2024-06-18 |  | 2024-07-29 | 2024-07-30 | Dawid Mierzwa | 2024-08-02 |  | 2024-07-30 | 2024-11-06 |  |  | 2024-11-08 | 1258 | 150 |  |  |  | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
52775 | 740-FLN-VP140-104-LH089-10-0 | 2 | true | 15.38 | 740-FLN-VP140-104-LH089-10-0 | LV1-105628.VP140 | 394 |  |  | MC1 | LVL 5 | Tt-6 | TR025_1 | 2024-06-18 | 2024-06-18 | 2024-06-18 |  | 2024-07-30 | 2024-07-30 | Büro | 2024-08-02 |  | 2024-07-31 | 2024-09-10 |  |  | 2024-09-16 | 1258 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-11-30 | 2024-11-30
52778 | 740-WAn-VP031-120-LH099-32-0 | 1 | true | 0.05 | 740-WAn-VP031-120-LH099-32-0 | LV0-105628.VP031 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR025_1 | 2024-06-18 | 2024-06-18 | 2024-06-18 |  | 2024-07-18 | 2024-07-18 | Büro | 2024-08-02 |  | 2024-07-23 | 2024-10-18 |  |  | 2024-10-22 | 1036 | 150 |  |  | 2024-10-29 | 149 | SEP | SEP
52779 | 740-WAn-VP032-122-LH099-40-0 | 1 | true | 0.05 | 740-WAn-VP032-122-LH099-40-0 | LV0-105628.VP032 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR025_1 | 2024-06-18 | 2024-06-18 | 2024-06-18 |  | 2024-07-03 | 2024-07-04 | Attila Henter | 2024-07-12 |  | 2024-07-09 | 2024-10-16 |  |  | 2024-10-18 | 1036 | 150 |  |  | 2024-11-12 | 149 | SEP | SEP
52780 | 740-WAn-VP033-120-LH099-40-0 | 1 | true | 0.05 | 740-WAn-VP033-120-LH099-40-0 | LV0-105628.VP033 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR025_1 | 2024-06-18 | 2024-06-18 | 2024-06-18 |  | 2024-07-03 | 2024-07-04 | Attila Henter | 2024-07-12 |  | 2024-07-09 | 2024-10-16 |  |  | 2024-10-18 | 1036 | 150 |  |  | 2024-11-13 | 149 | SEP | SEP
52781 | 740-WAn-VP041-120-LH099-32-0 | 1 | true | 0.05 | 740-WAn-VP041-120-LH099-32-0 | LV0-105628.VP041 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR025_1 | 2024-06-18 | 2024-06-18 | 2024-06-18 |  | 2024-07-18 | 2024-07-18 | Attila Henter | 2024-08-02 |  | 2024-07-23 | 2024-10-17 |  |  | 2024-10-18 | 1036 | 150 |  |  | 2024-11-14 | 149 | SEP | SEP
52782 | 740-WAn-VP042-122-LH099-40-0 | 1 | true | 0.09 | 740-WAn-VP042-122-LH099-40-0 | LV0-105628.VP042 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR025_1 | 2024-06-18 | 2024-06-18 | 2024-06-18 |  | 2024-07-03 | 2024-07-04 |  | 2024-07-12 |  | 2024-07-09 |  |  |  | 2024-10-18 | 1036 | 150 |  |  | 2024-11-05 | 149 | SEP | SEP
52783 | 740-WAn-VP043-120-LH099-40-0 | 1 | true | 0.09 | 740-WAn-VP043-120-LH099-40-0 | LV0-105628.VP043 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR025_1 | 2024-06-18 | 2024-06-18 | 2024-06-18 |  | 2024-07-03 | 2024-07-04 | Büro | 2024-07-12 |  | 2024-07-09 |  |  |  | 2024-10-16 | 1036 | 150 |  |  | 2024-11-14 | 149 | SEP | SEP
52784 | 740-WAn-VP051-108-LH099-15-0 | 1 | true | 0.05 | 740-WAn-VP051-108-LH099-15-0 | LV1-105628.VP051 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR025_1 | 2024-06-18 | 2024-06-18 | 2024-06-18 |  | 2024-07-22 | 2024-07-24 | Attila Henter | 2024-08-02 |  | 2024-07-26 | 2024-10-17 |  |  | 2024-10-18 | 1036 | 150 |  |  | 2024-11-05 | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
52785 | 740-WAn-VP061-108-LH099-15-0 | 1 | true | 0.05 | 740-WAn-VP061-108-LH099-15-0 | LV1-105628.VP061 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR025_1 | 2024-06-18 | 2024-06-18 | 2024-06-18 |  | 2024-07-22 | 2024-07-24 | Büro | 2024-08-02 |  | 2024-07-26 | 2024-10-14 |  |  | 2024-10-16 | 1036 | 150 |  |  | 2024-11-15 | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
52786 | 740-WAn-VS681-105-LH099-15-0 | 2 | true | 0.16 | 740-WAn-VS681-105-LH099-15-0 | LV0-105633.VS681 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR025_1 | 2024-06-18 | 2024-06-18 | 2024-06-18 |  | 2024-07-25 | 2024-07-26 | Büro | 2024-08-02 |  | 2024-07-30 | 2024-10-22 |  |  | 2024-10-30 | 1036 | 150 |  | 2024-11-12 | 2024-10-31 | 149 | SEP | SEP
52787 | 740-WAn-VS681-108-LH099-15-0 | 2 | true | 0.16 | 740-WAn-VS681-108-LH099-15-0 | LV0-105633.VS681 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR025_1 | 2024-06-18 | 2024-06-18 | 2024-06-18 |  | 2024-07-26 | 2024-07-26 | Büro | 2024-08-02 |  | 2024-07-30 | 2024-10-22 |  |  | 2024-10-30 | 1036 | 150 |  | 2024-11-12 | 2024-10-31 | 149 | SEP | SEP
52788 | 740-WAn-VS681-110-LH099-15-0 | 2 | true | 0.18 | 740-WAn-VS681-110-LH099-15-0 | LV0-105633.VS681 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR025_1 | 2024-06-18 | 2024-06-18 | 2024-06-18 |  | 2024-07-25 | 2024-07-25 | Büro | 2024-08-02 |  | 2024-07-26 | 2024-10-22 |  |  | 2024-10-30 | 1036 | 150 |  | 2024-11-12 | 2024-10-31 | 149 | SEP | SEP
52789 | 740-WAn-VS681-112-LH099-15-0 | 2 | true | 0.18 | 740-WAn-VS681-112-LH099-15-0 | LV0-105633.VS681 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR025_1 | 2024-06-18 | 2024-06-18 | 2024-06-18 |  | 2024-07-25 | 2024-07-25 | Büro | 2024-08-02 |  | 2024-07-26 | 2024-10-22 |  |  | 2024-10-30 | 1036 | 150 |  | 2024-11-12 | 2024-10-31 | 149 | SEP | SEP
52798 | 740-WAn-VU200-155-LH032-80-0 | 1 | true | 19.88 | 740-WAn-VU200-155-LH032-80-0 | LV0-105638.VU200 | 385 |  |  | MC1 | LVL 5 | W23 | TR025_1 | 2024-06-18 | 2024-06-18 | 2024-06-18 |  | 2024-07-03 | 2024-07-09 | Büro | 2024-07-12 |  | 2024-07-11 |  |  |  | 2024-10-17 | 1036 | 150 |  | 2024-10-09 |  | 149 | SEP | SEP | 2024-09-27 | 2024-10-04 | 2024-10-04 | 2024-10-04
52802 | 740-WAn-VU200-264-LH099-25-0 | 1 | false | 0.38 | 740-WAn-VU200-264-LH099-25-0 | LV1-105639.VU200 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR025_1 | 2024-06-18 | 2024-06-18 | 2024-06-18 |  | 2024-07-03 | 2024-07-04 |  | 2024-07-12 |  | 2024-07-09 |  |  |  |  | 1034 | 150 |  |  |  | 149 | SEP | SEP
52803 | 740-WAn-VU200-265-LH099-25-0 | 1 | false | 0.88 | 740-WAn-VU200-265-LH099-25-0 | LV1-105639.VU200 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR025_1 | 2024-06-18 | 2024-06-18 | 2024-06-18 |  | 2024-07-03 | 2024-07-05 |  | 2024-07-12 |  | 2024-07-09 |  |  |  |  | 1034 | 150 |  |  |  | 149 | SEP | SEP
56726 | 740-ABkont-VU311-101-LH032-25-0 | 1 | true | 3.82 | 740-ABkont-VU311-101-LH032-25-0 | LV1-105638.VU190 | 385 |  |  | MC1 | LVL 5 | N/A | TR025_2 | 2024-07-02 | 2024-07-04 | 2024-07-04 |  | 2024-07-04 | 2024-07-05 | Büro | 2024-07-12 |  | 2024-07-09 | 2024-10-07 |  |  | 2024-10-16 | 1042 | 150 |  |  |  | 149 | SEP | SEP
56727 | 740-ABkont-VU311-102-LH032-50-0 | 1 | true | 7.47 | 740-ABkont-VU311-102-LH032-50-0 | LV1-105638.VU190 | 385 |  |  | MC1 | LVL 5 | N/A | TR025_2 | 2024-07-02 | 2024-07-04 | 2024-07-04 |  | 2024-07-23 | 2024-07-23 | Büro | 2024-08-02 |  | 2024-07-25 | 2024-08-05 |  |  | 2024-08-08 | 1042 | 150 |  |  |  | 149 | SEP | SEP
56729 | 740-ABKont-VU311-128-LH032-25-0 | 1 | true | 4.24 | 740-ABKont-VU311-128-LH032-25-0 | LV1-105639.VU200 | 385 |  |  | MC1 | LVL 5 | N/A | TR025_2 | 2024-07-02 |  |  |  | 2024-07-04 | 2024-07-05 | Büro | 2024-07-12 |  | 2024-07-09 |  |  |  | 2024-10-16 | 1042 | 150 |  |  |  | 149 | SEP | SEP
56730 | 740-ABKont-VU311-129-LH032-25-0 | 1 | true | 3.69 | 740-ABKont-VU311-129-LH032-25-0 | LV1-105639.VU200 | 385 |  |  | MC1 | LVL 5 | Tt-6 | TR025_2 | 2024-07-02 |  |  |  | 2024-07-04 | 2024-07-05 | Büro | 2024-07-12 |  | 2024-07-09 | 2024-08-30 |  |  | 2024-09-03 | 1042 | 150 |  |  | 2024-09-09 | 149 | SEP | SEP
56731 | 740-ABKont-VU955-101-LH032-25-0 | 1 | false | 8.7 | 740-ABKont-VU955-101-LH032-25-0 | LV1-105639.VU200 | 385 |  |  | MC1 | LVL 5 | N/A | TR025_2 | 2024-07-02 | 2024-07-04 | 2024-07-04 |  | 2024-07-23 | 2024-07-24 | Büro | 2024-08-02 |  | 2024-07-26 | 2024-10-07 |  |  | 2024-10-16 | 1042 | 150 |  |  |  | 149 | SEP | SEP
63505 | 740-ABKont-VU955-101-LH032-25-0 | 3 | false | 8.7 | 740-ABKont-VU955-101-LH032-25-0 | LV1-105639.VU200 | 385 |  |  | MC1 | LVL 5 | N/A | TR034_VU955-M | 2024-08-30 | 2024-07-04 | 2024-07-04 |  | 2024-07-23 | 2024-07-24 |  | 2024-08-02 |  | 2024-07-26 |  |  |  |  | 1042 | 150 |  |  |  | 149 | SEP | SEP
64662 | 740-ABKont-VU955-101-LH032-25-0 | 4 | true | 8.7 | 740-ABKont-VU955-101-LH032-25-0 | LV1-105639.VU200 | 385 |  |  | MC1 | LVL 5 | N/A | TR036_2 | 2024-09-19 | 2024-07-04 | 2024-07-04 |  | 2024-07-23 | 2024-07-24 | Büro | 2024-08-02 |  | 2024-07-26 | 2024-10-07 |  |  | 2024-10-16 | 1042 | 150 |  |  |  | 149 | SEP | SEP
56732 | 740-ABKont-VU955-102-LH099-25-0 | 1 | false | 5.38 | 740-ABKont-VU955-102-LH099-25-0 | LV1-105639.VU200 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR025_2 | 2024-07-02 |  |  |  | 2024-07-04 | 2024-07-08 | Büro | 2024-07-12 |  | 2024-07-10 |  |  | 2024-09-03 |  | 1042 | 150 |  |  |  | 149 | SEP | SEP
63469 | 740-ABKont-VU955-102-LH099-25-0 | 2 | true | 5.38 | 740-ABKont-VU955-102-LH099-25-0 | LV1-105639.VU200 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR030_VU955-M | 2024-08-30 | 2024-09-03 | 2024-09-03 |  | 2024-07-04 | 2024-07-08 | Büro | 2024-07-12 |  | 2024-07-10 |  |  |  | 2024-11-12 | 1042 | 150 |  |  |  | 149 | SEP | SEP
56749 | 740-ABkont-VU311-103-LH099-20-0 | 1 | true | 0.85 | 740-ABkont-VU311-103-LH099-20-0 | LV1-105638.VU311 | 386 |  |  | MC1 | LVL 5 | N/A | TR027_2 | 2024-07-02 | 2024-07-04 | 2024-07-04 |  |  |  | Büro | [6 empty] | 2024-10-18 | 1042 | 150 |  |  |  | 149 | SEP | SEP
56751 | 740-ABkont-VU311-108-LH099-20-0 | 1 | true | 0.51 | 740-ABkont-VU311-108-LH099-20-0 | LV1-105638.VU311 | 386 |  |  | MC1 | LVL 5 | N/A | TR027_2 | 2024-07-02 | 2024-07-08 | 2024-07-08 |  | 2024-10-18 | 2024-10-18 | Büro | 2024-10-18 |  | 2024-10-18 | 2024-10-18 |  |  | 2024-10-25 | 1042 | 150 |  |  | 2024-11-06 | 149 | SEP | SEP
56752 | 740-ABkont-VU311-109-LH099-40-0 | 1 | true | 0.48 | 740-ABkont-VU311-109-LH099-40-0 | LV1-105638.VU311 | 386 |  |  | MC1 | LVL 5 | N/A | TR027_2 | 2024-07-02 | 2024-07-04 | 2024-07-04 |  |  |  | Büro | [6 empty] | 2024-10-23 | 1042 | 150 |  |  | 2024-11-06 | 149 | SEP | SEP
56761 | 740-ABkont-VU311-123-LH099-40-0 | 1 | true | 0.78 | 740-ABkont-VU311-123-LH099-40-0 | LV1-105638.VU311 | 386 |  |  | MC1 | LVL 5 | N/A | TR027_2 | 2024-07-02 | 2024-07-04 | 2024-07-04 |  |  |  | Büro |  |  |  | 2024-09-23 |  |  | 2024-09-25 | 1042 | 150 |  |  | 2024-11-06 | 149 | SEP | SEP
56762 | 740-ABkont-VU311-124-LH099-20-0 | 1 | true | 0.38 | 740-ABkont-VU311-124-LH099-20-0 | LV1-105638.VU311 | 386 |  |  | MC1 | LVL 5 | N/A | TR027_2 | 2024-07-02 | 2024-07-04 | 2024-07-04 |  |  |  | Büro |  |  |  | 2024-09-23 |  |  | 2024-09-27 | 1042 | 150 |  |  | 2024-11-06 | 149 | SEP | SEP
56763 | 740-ABkont-VU311-125-LH099-20-0 | 1 | true | 0.85 | 740-ABkont-VU311-125-LH099-20-0 | LV1-105638.VU311 | 386 |  |  | MC1 | LVL 5 | N/A | TR027_2 | 2024-07-02 | 2024-07-04 | 2024-07-04 |  |  |  | Büro |  |  |  | 2024-09-18 |  |  | 2024-09-21 | 1042 | 150 |  |  | 2024-11-06 | 149 | SEP | SEP
56764 | 740-ABkont-VU311-126-LH099-20-0 | 1 | true | 0.41 | 740-ABkont-VU311-126-LH099-20-0 | LV1-105638.VU311 | 386 |  |  | MC1 | LVL 5 | N/A | TR027_2 | 2024-07-02 | 2024-07-04 | 2024-07-04 |  |  |  | Büro | [6 empty] | 2024-10-04 | 1042 | 150 |  |  | 2024-11-07 | 149 | SEP | SEP
56765 | 740-ABkont-VU311-127-LH099-20-0 | 1 | true | 0.96 | 740-ABkont-VU311-127-LH099-20-0 | LV1-105638.VU311 | 386 |  |  | MC1 | LVL 5 | N/A | TR027_2 | 2024-07-02 | 2024-07-04 | 2024-07-04 |  |  |  | Büro |  |  |  | 2024-09-19 |  |  | 2024-09-21 | 1042 | 150 |  |  | 2024-11-07 | 149 | SEP | SEP
56775 | 740-SIVKont-VU321-101-LH099-50-0 | 1 | true | 0.77 | 740-SIVKont-VU321-101-LH099-50-0 | LV1-105638.VU321 | 386 |  |  | MC1 | LVL 5 | N/A | TR027_2 | 2024-07-02 | 2024-07-04 | 2024-07-04 |  |  |  | Büro |  |  |  | 2024-10-10 |  |  | 2024-10-15 | 1243 | 150 |  |  |  | 149 | SEP | SEP
56776 | 740-SIVKont-VU321-102-LH099-50-0 | 1 | true | 0.52 | 740-SIVKont-VU321-102-LH099-50-0 | LV1-105638.VU321 | 386 |  |  | MC1 | LVL 5 | N/A | TR027_2 | 2024-07-02 | 2024-07-04 | 2024-07-04 |  |  |  | Büro |  |  |  | 2024-10-10 |  |  | 2024-10-15 | 1243 | 150 |  |  |  | 149 | SEP | SEP
56777 | 740-SIVKont-VU321-103-LH099-50-0 | 1 | true | 1.01 | 740-SIVKont-VU321-103-LH099-50-0 | LV1-105638.VU321 | 386 |  |  | MC1 | LVL 5 | N/A | TR027_2 | 2024-07-02 | 2024-07-04 | 2024-07-04 |  |  |  | Büro |  |  |  | 2024-10-09 |  |  | 2024-10-11 | 1243 | 150 |  |  |  | 149 | SEP | SEP
56778 | 740-SIVKont-VU321-108-LH099-25-0 | 1 | true | 1.4 | 740-SIVKont-VU321-108-LH099-25-0 | LV1-105638.VU321 | 386 |  |  | MC1 | LVL 5 | N/A | TR027_2 | 2024-07-02 | 2024-07-04 | 2024-07-04 |  |  |  | Büro | [6 empty] | 2024-09-25 | 1243 | 150 |  |  | 2024-10-23 | 149 | SEP | SEP
56779 | 740-SIVKont-VU321-109-LH099-50-0 | 1 | true | 0.39 | 740-SIVKont-VU321-109-LH099-50-0 | LV1-105638.VU321 | 386 |  |  | MC1 | LVL 5 | N/A | TR027_2 | 2024-07-02 | 2024-07-04 | 2024-07-04 |  |  |  | Büro |  |  |  | 2024-10-07 |  |  | 2024-10-09 | 1243 | 150 |  |  | 2024-10-23 | 149 | SEP | SEP
56783 | 740-SIVKont-VU321-115-LH099-50-0 | 1 | true | 1.11 | 740-SIVKont-VU321-115-LH099-50-0 | LV1-105638.VU321 | 386 |  |  | MC1 | LVL 5 | N/A | TR027_2 | 2024-07-02 | 2024-07-04 | 2024-07-04 | [7 empty] | 2024-09-23 |  |  | 2024-09-26 | 1243 | 150 |  |  |  | 149 | SEP | SEP
56788 | 740-SIVKont-VU321-120-LH099-50-0 | 1 | true | 0.7 | 740-SIVKont-VU321-120-LH099-50-0 | LV1-105638.VU321 | 386 |  |  | MC1 | LVL 5 | N/A | TR027_2 | 2024-07-02 | 2024-07-04 | 2024-07-04 |  |  |  | Büro |  |  |  | 2024-10-07 |  |  | 2024-10-10 | 1243 | 150 |  |  | 2024-10-23 | 149 | SEP | SEP
56790 | 740-SIVKont-VU321-122-LH099-25-0 | 1 | true | 0.39 | 740-SIVKont-VU321-122-LH099-25-0 | LV1-105638.VU321 | 386 |  |  | MC1 | LVL 5 | N/A | TR027_2 | 2024-07-02 | 2024-07-04 | 2024-07-04 |  |  |  | Büro |  |  |  | 2024-09-18 |  |  | 2024-09-21 | 1243 | 150 |  |  | 2024-10-23 | 149 | SEP | SEP
56811 | 740-SIV-VU320-128-LH099-50-0 | 1 | true | 0.58 | 740-SIV-VU320-128-LH099-50-0 | LV1-105638.VU320 | 386 |  |  | MC1 | LVL 5 | N/A | TR027_2 | 2024-07-02 | 2024-07-04 | 2024-07-04 |  |  |  | Büro | [6 empty] | 2024-10-01 | 1253 | 150 |  | 2024-10-16 |  | 149 | SEP | SEP
56812 | 740-SIV-VU320-129-LH099-65-0 | 1 | true | 0.37 | 740-SIV-VU320-129-LH099-65-0 | LV1-105638.VU320 | 386 |  |  | MC1 | LVL 5 | N/A | TR027_2 | 2024-07-02 | 2024-07-04 | 2024-07-04 |  |  |  | Büro | [6 empty] | 2024-10-01 | 1253 | 150 |  | 2024-10-16 |  | 149 | SEP | SEP
56813 | 740-SIV-VU320-130-LH099-65-0 | 1 | true | 0.44 | 740-SIV-VU320-130-LH099-65-0 | LV1-105638.VU320 | 386 |  |  | MC1 | LVL 5 | N/A | TR027_2 | 2024-07-02 | 2024-07-04 | 2024-07-04 |  |  |  | Büro | [6 empty] | 2024-10-01 | 1253 | 150 |  | 2024-10-16 |  | 149 | SEP | SEP
56814 | 740-SIV-VU320-131-LH099-65-0 | 1 | true | 0.69 | 740-SIV-VU320-131-LH099-65-0 | LV1-105638.VU320 | 386 |  |  | MC1 | LVL 5 | N/A | TR027_2 | 2024-07-02 | 2024-07-04 | 2024-07-04 |  |  |  | Büro |  |  |  | 2024-09-21 |  |  | 2024-09-30 | 1253 | 150 |  | 2024-10-16 |  | 149 | SEP | SEP
56815 | 740-SIV-VU320-132-LH099-65-0 | 1 | true | 0.56 | 740-SIV-VU320-132-LH099-65-0 | LV1-105638.VU320 | 386 |  |  | MC1 | LVL 5 | N/A | TR027_2 | 2024-07-02 | 2024-07-04 | 2024-07-04 |  |  |  | Büro |  |  |  | 2024-09-21 |  |  | 2024-10-02 | 1253 | 150 |  | 2024-10-16 |  | 149 | SEP | SEP
56816 | 740-SIV-VU320-133-LH099-50-0 | 1 | true | 0.33 | 740-SIV-VU320-133-LH099-50-0 | LV1-105638.VU320 | 386 |  |  | MC1 | LVL 5 | N/A | TR027_2 | 2024-07-02 | 2024-07-04 | 2024-07-04 |  |  |  | Büro |  |  |  | 2024-09-21 |  |  | 2024-10-01 | 1253 | 150 |  | 2024-10-16 |  | 149 | SEP | SEP
56817 | 740-SIV-VU320-134-LH099-50-0 | 1 | true | 0.54 | 740-SIV-VU320-134-LH099-50-0 | LV1-105638.VU320 | 386 |  |  | MC1 | LVL 5 | N/A | TR027_2 | 2024-07-02 | 2024-07-04 | 2024-07-04 |  |  |  | Büro |  |  |  | 2024-09-06 |  |  | 2024-09-07 | 1253 | 150 |  |  |  | 149 | SEP | SEP
56818 | 740-SIV-VU320-135-LH099-50-0 | 1 | true | 0.58 | 740-SIV-VU320-135-LH099-50-0 | LV1-105638.VU320 | 386 |  |  | MC1 | LVL 5 | N/A | TR027_2 | 2024-07-02 | 2024-07-04 | 2024-07-04 |  |  |  | Büro |  |  |  | 2024-09-05 |  |  | 2024-09-07 | 1253 | 150 |  |  | 2024-09-12 | 149 | SEP | SEP
56819 | 740-SIV-VU320-136-LH099-50-0 | 1 | true | 0.45 | 740-SIV-VU320-136-LH099-50-0 | LV1-105638.VU320 | 386 |  |  | MC1 | LVL 5 | N/A | TR027_2 | 2024-07-02 | 2024-07-04 | 2024-07-04 |  |  |  | Büro |  |  |  | 2024-09-05 |  |  | 2024-09-10 | 1253 | 150 |  |  | 2024-09-12 | 149 | SEP | SEP
56820 | 740-SIV-VU320-137-LH099-50-0 | 1 | true | 0.79 | 740-SIV-VU320-137-LH099-50-0 | LV1-105638.VU320 | 386 |  |  | MC1 | LVL 5 | N/A | TR027_2 | 2024-07-02 | 2024-07-04 | 2024-07-04 |  | 2024-06-25 | 2024-06-27 | Büro | 2024-07-12 |  | 2024-07-08 | 2024-09-03 |  |  | 2024-09-05 | 1253 | 150 |  |  | 2024-09-06 | 149 | SEP | SEP
56823 | 740-WAKont-VU190-207-LH032-100-0 | 1 | false | 51.71 | 740-WAKont-VU190-207-LH032-100-0 | LV1-105639.VU190 | 385 |  |  | MC1 | LVL 1 | N/A | TR027_2 | 2024-07-02 | 2024-07-04 | 2024-07-04 |  | 2024-07-09 | 2024-07-09 |  | 2024-07-12 |  | 2024-07-10 |  |  |  |  | 1281 | 150 |  |  |  | 149 | SEP | SEP
62243 | 740-WAKont-VU190-207-LH032-100-0 | 2 | false | 28.5 | 740-WAKont-VU190-207-LH032-100-0 | LV1-105639.VU190 | 385 |  |  | MC1 | LVL 1 | N/A | TR030_2 | 2024-07-25 | 2024-07-04 | 2024-07-04 |  | 2024-07-09 | 2024-07-09 |  | 2024-07-12 |  | 2024-07-10 |  |  |  |  | 1281 | 150 |  |  |  | 149 | SEP | SEP
62813 | 740-WAKont-VU190-207-LH032-100-0 | 3 | false | 28.5 | 740-WAKont-VU190-207-LH032-100-0 | LV1-105639.VU190 | 385 |  | true | MC1 | LVL 1 | N/A | TR033_1 | 2024-08-08 | 2024-07-04 | 2024-07-04 |  | 2024-07-09 | 2024-07-09 |  | 2024-07-12 |  | 2024-07-10 |  |  |  |  | 1281 | 150 |  |  |  | 149 | SEP | SEP
62814 | 740-WAKont-VU190-207-LH032-100-0 | 3 | false | 51.71 | 740-WAKont-VU190-207-LH032-100-0 | LV1-105639.VU190 | 385 |  |  | MC1 | LVL 1 | N/A | TR033_1 | 2024-08-08 | 2024-08-08 | 2024-08-08 |  |  |  |  | 2024-07-12 |  | 2024-07-10 |  |  |  |  | 1281 | 150 |  |  |  | 149 | SEP | SEP
65869 | 740-WAKont-VU190-207-LH032-100-0 | 4 | true | 51.71 | 740-WAKont-VU190-207-LH032-100-0 | LV1-105639.VU190 | 385 |  |  | MC1 | LVL 1 | N/A | TR035_1 | 2024-10-15 | 2024-08-08 | 2024-08-08 |  |  |  | Büro | 2024-07-12 |  | 2024-07-10 | 2024-10-17 |  |  | 2024-10-30 | 1281 | 150 |  |  |  | 149 | SEP | SEP
57051 | 740-WAKont-VP134-126-LH099-50-0 | 1 | true | 0.43 | 740-WAKont-VP134-126-LH099-50-0 | LV1-105628.VP134 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR028_1 | 2024-07-05 | 2024-07-24 | 2024-07-24 |  | 2024-07-25 | 2024-07-30 | Büro | 2024-08-02 |  | 2024-07-31 | 2024-10-18 |  |  | 2024-10-23 | 934 | 150 |  |  | 2024-10-30 | 149 | SEP | SEP
57052 | 740-WAKont-VP144-126-LH099-50-0 | 1 | true | 0.43 | 740-WAKont-VP144-126-LH099-50-0 | LV1-105628.VP144 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR028_1 | 2024-07-05 | 2024-07-24 | 2024-07-24 |  | 2024-07-25 | 2024-07-30 | Attila Henter | 2024-08-02 |  | 2024-07-31 | 2024-10-15 |  |  | 2024-10-21 | 934 | 150 |  |  | 2024-10-29 | 149 | SEP | SEP
57053 | 740-WAKont-VS627-106-LH099-40-0 | 1 | true | 2.36 | 740-WAKont-VS627-106-LH099-40-0 | LV2-105633.VS627 | 386 |  |  | MC1 | LVL 5 | W60 | TR028_1 | 2024-07-05 | 2024-07-24 | 2024-07-24 |  | 2024-07-24 | 2024-07-26 |  | 2024-08-02 |  | 2024-07-30 | 2024-09-04 |  |  | 2024-11-07 | 934 | 150 |  |  |  | 149 | SEP | SEP
57054 | 740-WAKont-VS629-106-LH099-40-0 | 1 | true | 2.37 | 740-WAKont-VS629-106-LH099-40-0 | LV2-105633.VS629 | 386 |  |  | MC1 | LVL 5 | W60 | TR028_1 | 2024-07-05 | 2024-07-24 | 2024-07-24 |  | 2024-07-24 | 2024-07-29 | Büro | 2024-08-02 |  | 2024-07-31 | 2024-09-04 |  |  | 2024-09-16 | 934 | 150 |  |  | 2024-09-17 | 149 | SEP | SEP
57055 | 740-WAKont-VU190-206-LH099-50-0 | 1 | true | 0.65 | 740-WAKont-VU190-206-LH099-50-0 | LV1-105639.VU190 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR028_1 | 2024-07-05 | 2024-07-24 | 2024-07-24 |  | 2024-07-25 |  | Büro | 2024-08-02 |  | 2024-07-31 | 2024-10-18 |  |  | 2024-10-23 | 934 | 150 |  |  | 2024-10-30 | 149 | SEP | SEP
57056 | 740-WAKont-VU190-216-LH099-50-0 | 1 | true | 0.65 | 740-WAKont-VU190-216-LH099-50-0 | LV1-105639.VU190 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR028_1 | 2024-07-05 | 2024-07-24 | 2024-07-24 |  | 2024-07-25 |  | Attila Henter | 2024-08-02 |  | 2024-07-31 | 2024-10-15 |  |  | 2024-10-21 | 934 | 150 |  |  | 2024-11-05 | 149 | SEP | SEP
57057 | 740-WAKont-VU190-225-LH032-40-0 | 1 | true | 1.2 | 740-WAKont-VU190-225-LH032-40-0 | LV1-105639.VU190 | 385 |  |  | MC1 | LVL 5 | N/A | TR028_1 | 2024-07-05 | 2024-07-24 | 2024-07-24 |  | 2024-07-24 | 2024-07-26 | Büro | 2024-08-02 |  | 2024-07-30 | 2024-09-04 |  |  | 2024-09-12 | 933 | 150 |  |  | 2024-09-12 | 149 | SEP | SEP
57058 | 740-WAKont-VU190-231-LH032-40-0 | 1 | true | 1.37 | 740-WAKont-VU190-231-LH032-40-0 | LV1-105639.VU190 | 385 |  |  | MC1 | LVL 5 | N/A | TR028_1 | 2024-07-05 | 2024-07-24 | 2024-07-24 |  | 2024-07-24 | 2024-07-26 | Büro | 2024-08-02 |  | 2024-07-30 | 2024-09-04 |  |  | 2024-09-12 | 933 | 150 |  |  | 2024-09-12 | 149 | SEP | SEP
57062 | 740-DK-VU116-101-LH011-40-0 | 1 | true | 1.2 | 740-DK-VU116-101-LH011-40-0 | LV0-105633.VS671 | 369 |  |  | MC1 | LVL 6 | W23 | TR028_2 | 2024-07-05 | 2024-07-09 | 2024-07-10 |  | 2024-07-10 | 2024-07-11 | Büro | 2024-08-02 |  | 2024-07-11 | 2024-09-17 |  |  | 2024-09-23 | 987 | 150 |  | 2024-10-25 |  | 149 | SEP | SEP |  |  | 2024-11-01 | 2024-11-01
57063 | 740-DK-VU116-103-LH011-40-0 | 1 | true | 1.2 | 740-DK-VU116-103-LH011-40-0 | LV0-105633.VS672 | 369 |  |  | MC1 | LVL 6 | W23 | TR028_2 | 2024-07-05 | 2024-07-09 | 2024-07-10 |  | 2024-07-10 | 2024-07-10 | Büro | 2024-07-12 |  | 2024-07-11 | 2024-09-17 |  |  | 2024-09-23 | 987 | 150 |  | 2024-10-25 |  | 149 | SEP | SEP |  |  | 2024-11-01 | 2024-11-01
57068 | 740-DK-VU116-115-LH011-40-0 | 1 | true | 3.8 | 740-DK-VU116-115-LH011-40-0 | LV1-105638.VU116 | 369 |  |  | MC1 | LVL 5 | W23 | TR028_2 | 2024-07-05 | 2024-07-08 | 2024-07-08 |  | 2024-07-10 | 2024-07-10 | Büro | 2024-07-12 |  | 2024-07-11 | 2024-07-18 |  |  | 2024-08-08 | 986 | 150 |  | 2024-10-25 |  | 149 | SEP | SEP |  |  | 2024-11-01 | 2024-11-01
57069 | 740-MKWH-R-VS731-104-LH130-25-0 | 1 | true | 1.1 | 740-MKWH-R-VS731-104-LH130-25-0 | LV1-105633.VS731 | 362 |  |  | MC1 | LVL 6 | T60 | TR028_2 | 2024-07-05 | 2024-07-08 | 2024-07-08 |  | 2024-07-10 | 2024-07-10 | Büro | 2024-07-12 |  | 2024-07-11 | 2024-10-01 |  |  | 2024-10-04 | 804 | 150 |  |  |  | 149 | SEP | SEP | 2024-10-25 | 2024-10-25 | 2024-10-25 | 2024-10-25
57070 | 740-MKWH-R-VS731-108-LH130-25-0 | 1 | true | 1.21 | 740-MKWH-R-VS731-108-LH130-25-0 | LV1-105633.VS731 | 362 |  |  | MC1 | LVL 6 | T60 | TR028_2 | 2024-07-05 | 2024-07-09 | 2024-07-09 |  | 2024-07-10 | 2024-07-10 | Büro |  |  | 2024-07-11 | 2024-10-01 |  |  | 2024-10-02 | 804 | 150 |  |  |  | 149 | SEP | SEP | 2024-10-25 | 2024-10-25 | 2024-10-25 | 2024-10-25
57071 | 740-MKWH-R-VS732-104-LH130-20-0 | 1 | true | 1.22 | 740-MKWH-R-VS732-104-LH130-20-0 | LV1-105633.VS732 | 362 |  |  | MC1 | LVL 6 | T60 | TR028_2 | 2024-07-05 | 2024-07-08 | 2024-07-08 |  | 2024-07-10 | 2024-07-11 | Büro | 2024-07-12 |  | 2024-07-11 | 2024-10-01 |  |  | 2024-10-04 | 804 | 150 |  |  |  | 149 | SEP | SEP | 2024-10-25 | 2024-10-25 | 2024-10-25 | 2024-10-25
57072 | 740-MKWH-R-VS732-108-LH130-20-0 | 1 | true | 1.12 | 740-MKWH-R-VS732-108-LH130-20-0 | LV1-105633.VS732 | 362 |  |  | MC1 | LVL 6 | T60 | TR028_2 | 2024-07-05 | 2024-07-09 | 2024-07-09 |  | 2024-07-10 | 2024-07-11 | Büro | 2024-08-02 |  | 2024-07-12 | 2024-10-01 |  |  | 2024-10-02 | 804 | 150 |  |  |  | 149 | SEP | SEP | 2024-10-25 | 2024-10-25 | 2024-10-25 | 2024-10-25
57073 | 740-MKWH-R-VU211-206-LH130-32-0 | 1 | true | 10.66 | 740-MKWH-R-VU211-206-LH130-32-0 | LV1-105639.VU211 | 362 |  |  | MC1 | LVL 6 | T60 | TR028_2 | 2024-07-05 | 2024-07-08 | 2024-07-08 |  | 2024-07-10 | 2024-07-10 |  | 2024-07-12 |  | 2024-07-11 | 2024-07-18 |  |  | 2024-07-26 | 804 | 150 |  | 2024-08-20 | 2024-07-16 | 149 | SEP | SEP | 2024-08-19 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2024-10-07 | 2024-10-07
57074 | 740-MKWH-S-VS731-101-LH130-25-0 | 1 | true | 2.03 | 740-MKWH-S-VS731-101-LH130-25-0 | LV1-105639.VU211 | 362 |  |  | MC1 | LVL 6 | T60 | TR028_2 | 2024-07-05 | 2024-07-08 | 2024-07-08 |  | 2024-07-10 | 2024-07-11 | Büro | 2024-08-02 |  | 2024-07-11 | 2024-10-01 |  |  | 2024-10-07 | 804 | 150 |  |  |  | 149 | SEP | SEP | 2024-10-25 | 2024-10-25 | 2024-10-25 | 2024-10-25
57075 | 740-MKWH-S-VS731-105-LH130-25-0 | 1 | true | 1.97 | 740-MKWH-S-VS731-105-LH130-25-0 | LV1-105639.VU211 | 362 |  |  | MC1 | LVL 6 | T60 | TR028_2 | 2024-07-05 | 2024-07-08 | 2024-07-08 |  | 2024-07-10 | 2024-07-11 | Büro | 2024-08-02 |  | 2024-07-12 | 2024-10-01 |  |  | 2024-10-03 | 804 | 150 |  |  |  | 149 | SEP | SEP | 2024-10-25 | 2024-10-25 | 2024-10-25 | 2024-10-25
57076 | 740-MKWH-S-VS732-101-LH130-20-0 | 1 | true | 1.85 | 740-MKWH-S-VS732-101-LH130-20-0 | LV1-105639.VU211 | 362 |  |  | MC1 | LVL 6 | T60 | TR028_2 | 2024-07-05 | 2024-07-08 | 2024-07-08 |  | 2024-07-10 | 2024-07-10 | Büro | 2024-07-12 |  | 2024-07-11 | 2024-10-01 |  |  | 2024-10-07 | 804 | 150 |  |  |  | 149 | SEP | SEP | 2024-10-25 | 2024-10-25 | 2024-10-25 | 2024-10-25
57077 | 740-MKWH-S-VS732-105-LH130-20-0 | 1 | true | 1.74 | 740-MKWH-S-VS732-105-LH130-20-0 | LV1-105639.VU211 | 362 |  |  | MC1 | LVL 6 | T60 | TR028_2 | 2024-07-05 | 2024-07-08 | 2024-07-08 |  | 2024-07-10 | 2024-07-10 | Büro | 2024-07-12 |  | 2024-07-11 | 2024-10-01 |  |  | 2024-10-03 | 804 | 150 |  |  |  | 149 | SEP | SEP | 2024-10-25 | 2024-10-25 | 2024-10-25 | 2024-10-25
57078 | 740-MKWH-S-VU211-201-LH130-32-0 | 1 | true | 9.89 | 740-MKWH-S-VU211-201-LH130-32-0 | LV1-105639.VU211 | 362 |  |  | MC1 | LVL 6 | T60 | TR028_2 | 2024-07-05 | 2024-07-09 | 2024-07-09 |  | 2024-07-10 | 2024-07-11 |  | 2024-08-02 |  | 2024-07-11 | 2024-07-18 |  |  | 2024-07-26 | 804 | 150 |  | 2024-08-20 | 2024-07-16 | 149 | SEP | SEP | 2024-08-19 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2024-10-07 | 2024-10-07
62180 | 727-DMA-U341-105-LH032-25-0 | 1 | false | 20.4 | 727-DMA-U341-105-LH032-25-0 | LV1-103542.U330 | 385 |  |  | MC1 | LVL 1 | N/A | TR029_1 | 2024-07-24 | 2024-07-25 | 2024-07-25 |  | 2024-07-26 | 2024-07-31 |  | 2024-08-02 |  | 2024-07-31 |  |  |  |  | 1285 | 150 |  |  |  | 149 | SEP | SEP
62808 | 727-DMA-U341-105-LH032-25-0 | 2 | true | 20.4 | 727-DMA-U341-105-LH032-25-0 | LV1-103542.U330 | 385 |  |  | MC1 | LVL 1 | N/A | TR033_1 | 2024-08-08 | 2024-07-25 | 2024-07-25 |  | 2024-07-26 | 2024-07-31 | Büro | 2024-08-02 |  | 2024-07-31 | 2024-10-23 |  |  | 2024-10-30 | 1285 | 150 |  |  |  | 149 | SEP | SEP
62181 | 740-CIP-R-VS692-106-LH088-32-0 | 1 | true | 0.07 | 740-CIP-R-VS692-106-LH088-32-0 | LV2-105633.VS692 | 391 |  |  | MC1 | LVL 5 | Tt-6 | TR029_1 | 2024-07-24 | 2024-07-25 | 2024-07-25 |  | 2024-07-30 | 2024-07-31 | Büro | 2024-08-02 |  | 2024-07-31 | 2024-10-22 |  |  | 2024-10-24 | 928 | 150 |  |  | 2024-10-28 | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
62182 | 740-CIP-R-VS692-107-LH088-32-0 | 1 | true | 0.28 | 740-CIP-R-VS692-107-LH088-32-0 | LV2-105633.VS692 | 391 |  |  | MC1 | LVL 5 | Tt-6 | TR029_1 | 2024-07-24 | 2024-07-25 | 2024-07-25 |  | 2024-07-30 | 2024-07-31 |  | 2024-08-02 |  | 2024-07-31 | 2024-09-25 |  |  | 2024-10-18 | 928 | 150 |  |  | 2024-10-29 | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
62183 | 740-CIP-R-VS695-102-LH088-32-0 | 1 | true | 2.82 | 740-CIP-R-VS695-102-LH088-32-0 | LV1-105633.VS695 | 391 |  |  | MC1 | LVL 5 | Tt-6 | TR029_1 | 2024-07-24 | 2024-07-25 | 2024-07-25 |  | 2024-07-30 | 2024-07-31 | Dawid Mierzwa | 2024-08-02 |  | 2024-07-31 | 2024-10-24 |  |  | 2024-11-08 | 928 | 150 |  |  |  | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
62184 | 740-CIP-R-VS696-102-LH088-32-0 | 1 | true | 0.8 | 740-CIP-R-VS696-102-LH088-32-0 | LV1-105633.VS696 | 391 |  |  | MC1 | LVL 5 | Tt-6 | TR029_1 | 2024-07-24 | 2024-07-25 | 2024-07-25 |  | 2024-07-29 |  | Büro | 2024-08-02 |  | 2024-07-31 | 2024-10-24 |  |  | 2024-10-30 | 928 | 150 |  |  | 2024-10-31 | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
62185 | 740-DKR-VS671-101-LH011-15-0 | 1 | true | 0.08 | 740-DKR-VS671-101-LH011-15-0 | LV0-105633.VS671 | 369 |  |  | MC1 | LVL 6 | W23 | TR029_1 | 2024-07-24 | 2024-05-06 | 2024-05-06 |  | 2024-06-13 | 2024-06-18 | Büro | 2024-06-28 |  | 2024-07-20 |  |  |  | 2024-10-01 | 1038 | 150 |  | 2024-10-03 | 2024-10-03 | 149 | SEP | SEP | 2024-09-25 |  | 2024-11-01 | 2024-11-01
62186 | 740-DKR-VS672-101-LH011-15-0 | 1 | true | 0.08 | 740-DKR-VS672-101-LH011-15-0 | LV0-105633.VS672 | 369 |  |  | MC1 | LVL 6 | W23 | TR029_1 | 2024-07-24 | 2024-05-06 | 2024-05-06 |  | 2024-06-13 | 2024-06-18 | Büro | 2024-06-28 |  | 2024-07-20 |  |  |  | 2024-10-16 | 1038 | 150 |  | 2024-10-29 | 2024-10-03 | 149 | SEP | SEP | 2024-09-25 |  | 2024-11-01 | 2024-11-01
62187 | 740-DKR-VS673-101-LH011-15-0 | 1 | true | 0.08 | 740-DKR-VS673-101-LH011-15-0 | LV0-105633.VS673 | 369 |  |  | MC1 | LVL 6 | W23 | TR029_1 | 2024-07-24 | 2024-05-06 | 2024-05-06 |  | 2024-06-13 | 2024-06-18 | Büro | 2024-06-28 |  | 2024-07-20 |  |  |  | 2024-09-25 | 1038 | 150 |  |  |  | 149 | SEP | SEP | 2024-09-25 |  | 2024-11-01 | 2024-11-01
62191 | 740-DMA-VS671-102-LH032-15-0 | 1 | true | 0.2 | 740-DMA-VS671-102-LH032-15-0 | LV1-105638.VU340 | 385 |  |  | MC1 | LVL 6 | N/A | TR029_1 | 2024-07-24 | 2024-03-23 | 2024-03-23 |  | 2024-06-04 | 2024-06-07 | Büro | 2024-06-14 |  | 2024-06-07 |  |  |  | 2024-09-04 | 903 | 150 |  |  | 2024-09-09 | 149 | SEP | SEP
62192 | 740-DMA-VS672-102-LH032-15-0 | 1 | true | 0.2 | 740-DMA-VS672-102-LH032-15-0 | LV1-105638.VU340 | 385 |  |  | MC1 | LVL 6 | N/A | TR029_1 | 2024-07-24 | 2024-04-04 | 2024-04-07 |  | 2024-05-31 | 2024-06-07 |  | 2024-06-14 |  | 2024-06-07 |  |  |  | 2024-09-14 | 903 | 150 |  |  | 2024-09-14 | 149 | SEP | SEP
62193 | 740-DMA-VS673-102-LH032-15-0 | 1 | true | 0.2 | 740-DMA-VS673-102-LH032-15-0 | LV1-105638.VU340 | 385 |  |  | MC1 | LVL 6 | N/A | TR029_1 | 2024-07-24 | 2024-03-23 | 2024-03-23 |  | 2024-06-04 | 2024-06-08 |  | 2024-06-14 |  | 2024-06-08 |  |  |  | 2024-09-14 | 903 | 150 |  |  | 2024-09-14 | 149 | SEP | SEP
62200 | 740-SP-VS671-102-LH032-15-0 | 1 | true | 0.11 | 740-SP-VS671-102-LH032-15-0 | LV1-105638.VU331 | 385 |  |  | MC1 | LVL 6 | N/A | TR029_1 | 2024-07-24 | 2024-03-23 | 2024-03-23 |  | 2024-05-31 | 2024-06-07 | Büro | 2024-06-14 |  | 2024-06-07 | 2024-08-07 |  |  | 2024-08-13 | 906 | 150 |  |  | 2024-09-09 | 149 | SEP | SEP
62201 | 740-SP-VS672-102-LH032-15-0 | 1 | true | 0.11 | 740-SP-VS672-102-LH032-15-0 | LV1-105638.VU331 | 385 |  |  | MC1 | LVL 6 | N/A | TR029_1 | 2024-07-24 | 2024-03-23 | 2024-03-23 |  | 2024-05-31 | 2024-06-07 | Büro | 2024-06-14 |  | 2024-06-07 | 2024-08-07 |  |  | 2024-08-12 | 906 | 150 |  |  | 2024-09-09 | 149 | SEP | SEP
62202 | 740-SP-VS673-102-LH032-15-0 | 1 | true | 0.11 | 740-SP-VS673-102-LH032-15-0 | LV1-105638.VU331 | 385 |  |  | MC1 | LVL 6 | N/A | TR029_1 | 2024-07-24 | 2024-03-23 | 2024-03-23 |  | 2024-05-31 | 2024-06-07 | Büro | 2024-06-14 |  | 2024-06-07 | 2024-08-07 |  |  | 2024-08-08 | 906 | 150 |  |  | 2024-09-09 | 149 | SEP | SEP
62206 | 740-UN-VS671-102-LH032-15-0 | 1 | true | 0.11 | 740-UN-VS671-102-LH032-15-0 | LV1-105638.VU330 | 385 |  |  | MC1 | LVL 6 | N/A | TR029_1 | 2024-07-24 | 2024-03-26 | 2024-03-26 |  | 2024-06-03 | 2024-06-07 |  | 2024-06-14 |  | 2024-06-07 |  |  |  | 2024-09-14 | 908 | 150 |  |  | 2024-09-14 | 149 | SEP | SEP
62207 | 740-UN-VS672-102-LH032-15-0 | 1 | true | 0.11 | 740-UN-VS672-102-LH032-15-0 | LV1-105638.VU330 | 385 |  |  | MC1 | LVL 6 | N/A | TR029_1 | 2024-07-24 | 2024-03-26 | 2024-03-26 |  | 2024-06-03 | 2024-06-07 | Büro | 2024-06-14 |  | 2024-06-07 |  |  |  | 2024-09-05 | 908 | 150 |  |  | 2024-09-09 | 149 | SEP | SEP
62208 | 740-UN-VS673-102-LH032-15-0 | 1 | true | 0.11 | 740-UN-VS673-102-LH032-15-0 | LV1-105638.VU330 | 385 |  |  | MC1 | LVL 6 | N/A | TR029_1 | 2024-07-24 | 2024-03-26 | 2024-03-26 |  | 2024-06-03 | 2024-06-07 | Büro | 2024-06-14 |  | 2024-06-07 |  |  |  | 2024-09-04 | 908 | 150 |  |  | 2024-09-09 | 149 | SEP | SEP
62215 | 740-WAn-VS671-117-LH032-50-0 | 1 | true | 1.35 | 740-WAn-VS671-117-LH032-50-0 | LV0-105633.VS671 | 385 |  |  | MC1 | LVL 6 | W23 | TR029_1 | 2024-07-24 | 2024-05-21 | 2024-05-21 |  | 2024-07-02 | 2024-07-04 | Büro | 2024-07-12 |  | 2024-07-10 | 2024-09-12 |  |  | 2024-09-17 | 1035 | 150 |  |  | 2024-09-24 | 149 | SEP | SEP | 2024-09-25
62219 | 740-WAn-VS672-117-LH032-50-0 | 1 | true | 1.35 | 740-WAn-VS672-117-LH032-50-0 | LV0-105633.VS672 | 385 |  |  | MC1 | LVL 6 | W23 | TR029_1 | 2024-07-24 | 2024-05-21 | 2024-05-21 |  | 2024-07-01 | 2024-07-03 | Büro | 2024-07-12 |  | 2024-07-05 |  |  |  | 2024-09-17 | 1035 | 150 |  |  | 2024-09-24 | 149 | SEP | SEP | 2024-09-25
62223 | 740-WAn-VS673-117-LH032-50-0 | 1 | true | 1.35 | 740-WAn-VS673-117-LH032-50-0 | LV0-105633.VS673 | 385 |  |  | MC1 | LVL 6 | W23 | TR029_1 | 2024-07-24 | 2024-05-21 | 2024-05-21 |  | 2024-07-01 | 2024-07-03 | Büro | 2024-07-12 |  | 2024-07-05 |  |  |  | 2024-09-17 | 1035 | 150 |  |  | 2024-09-25 | 149 | SEP | SEP | 2024-09-25
62225 | 740-WAn-VU081-101-LH001-15-0 | 1 | true | 1.26 | 740-WAn-VU081-101-LH001-15-0 | LV0-105638.VU081 | 363 |  |  | MC1 | LVL 6 | T60 | TR029_1 | 2024-07-24 | 2024-04-29 | 2024-04-29 |  | 2024-06-25 | 2024-07-26 |  | 2024-07-12 |  | 2024-07-01 |  |  |  | 2024-11-15 | 1035 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
62242 | 727-N2-U060-101-LH023-25-0 | 1 | false | 33.98 | 727-N2-U060-101-LH023-25-0 | LV1-103542.U060 | 368 |  |  | MC1 | L1 | N/A | TR029_2 | 2024-07-25 | 2024-07-25 | 2024-07-25 | [11 empty] | 1286 | 150 |  |  |  | 149 | SEP | SEP
62809 | 727-N2-U060-101-LH023-25-0 | 2 | false | 33.98 | 727-N2-U060-101-LH023-25-0 | LV1-103542.U060 | 368 |  |  | MC1 | L1 | N/A | TR033_1 | 2024-08-07 | 2024-07-25 | 2024-07-25 |  | 2024-08-12 | 2024-08-14 | Büro | 2024-08-23 |  | 2024-08-14 | 2024-10-21 |  |  | 2024-10-30 | 1286 | 150 |  |  |  | 149 | SEP | SEP
62256 | 740-WAn-VU190-233-LH032-100-0 | 2 | false | 0.06 | 740-WAn-VU190-233-LH032-100-0 | LV1-105639.VU190 | 385 |  |  | MC1 | LXX | W60 | TR030_2 | 2024-07-25 | 2024-07-26 | 2024-07-26 |  | 2024-07-29 | 2024-08-14 |  | 2024-08-23 |  | 2024-08-14 |  |  |  | 2024-10-18 | 1259 | 150 |  |  |  | 149 | SEP | SEP
66064 | 740-WAn-VU190-233-LH032-100-0 | 4 | true | 0.06 | 740-WAn-VU190-233-LH032-100-0 | LV1-105639.VU190 | 385 |  |  | MC1 | LXX | W60 | TR035_2 | 2024-10-16 | 2024-07-26 | 2024-07-26 |  | 2024-07-29 | 2024-08-14 |  | 2024-08-23 |  | 2024-08-14 | 2024-10-18 | 2024-10-18 | 2024-10-18 | 2024-10-18 | 1259 | 150 |  |  |  | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
62263 | 740-WAn-VU955-101-LH032-80-0 | 2 | true | 8.47 | 740-WAn-VU955-101-LH032-80-0 | LV1-105638.VU955 | 385 |  |  | MC1 | L4 | N/A | TR030_2 | 2024-07-25 | 2024-07-26 | 2024-07-26 |  | 2024-07-29 | 2024-07-29 | Büro | 2024-08-02 |  | 2024-07-31 | 2024-10-18 |  |  | 2024-10-22 | 915 | 150 |  |  | 2024-10-30 | 149 | SEP | SEP
62769 | 727-MKWE-R-U241-116-LH001-150-0 | 3 | true | 24.3 | 727-MKWE-R-U241-116-LH001-150-0 | LV1-103542.U241 | 363 |  |  | MC1 | LVL XX | K51 | TR029_3 | 2024-08-07 | 2024-08-08 | 2024-08-12 | [10 empty] | 2024-05-22 | 802 | 150 |  | 2024-08-21 | 2024-09-09 | 149 | SEP | SEP | 2024-08-19 | 2024-09-13 | 2024-09-13
62770 | 727-MKWE-S-U241-118-LH001-150-0 | 3 | true | 24.35 | 727-MKWE-S-U241-118-LH001-150-0 | LV1-103542.U241 | 363 |  |  | MC1 | LVL XX | K51 | TR029_3 | 2024-08-07 | 2024-08-08 | 2024-08-12 | [10 empty] | 2024-05-22 | 802 | 150 |  | 2024-08-21 | 2024-09-09 | 149 | SEP | SEP | 2024-08-19 | 2024-09-13 | 2024-09-13 | 2024-09-20
62778 | 740-MKWH-S-VU211-110-LH130-40-0 | 1 | true | 1.6 | 740-MKWH-S-VU211-110-LH130-40-0 | LV1-105638.VU211 | 362 |  |  | MC1 | LVL 6 | T60 | TR029_3 | 2024-08-07 | 2024-08-08 | 2024-08-12 | [10 empty] | 2024-07-18 | 804 | 150 |  | 2024-08-20 | 2024-07-15 | 149 | SEP | SEP | 2024-08-19 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-10-07 | 2024-10-07
62779 | 740-SIV-VS731-101-LH032-32-0 | 1 | true | 0.55 | 740-SIV-VS731-101-LH032-32-0 | LV1-105633.VS731 | 385 |  |  | MC1 | LVL 6 | N/A | TR029_3 | 2024-08-07 | 2024-08-08 | 2024-08-12 |  |  |  | Büro |  |  |  | 2024-10-07 |  |  | 2024-10-09 | 1254 | 150 |  |  | 2024-10-09 | 149 | SEP | SEP
62780 | 740-SIV-VS731-102-LH032-32-0 | 1 | true | 0.58 | 740-SIV-VS731-102-LH032-32-0 | LV1-105633.VS731 | 385 |  |  | MC1 | LVL 6 | N/A | TR029_3 | 2024-08-07 | 2024-08-08 | 2024-08-12 |  |  |  | Büro |  |  |  | 2024-10-07 |  |  | 2024-10-11 | 1254 | 150 |  |  |  | 149 | SEP | SEP
62781 | 740-SIV-VS732-101-LH032-50-0 | 1 | false | 12.09 | 740-SIV-VS732-101-LH032-50-0 | LV1-105633.VS732 | 385 |  | true | MC1 | LVL 6 | N/A | TR029_3 | 2024-08-07 | 2024-08-08 | [12 empty] | 1254 | 150 |  |  |  | 149 | SEP | SEP
62812 | 740-SIV-VS732-101-LH032-50-0 | 2 | true | 12.09 | 740-SIV-VS732-101-LH032-50-0 | LV1-105633.VS732 | 385 |  |  | MC1 | LVL 6 | N/A | TR033_1 | 2024-08-08 | 2024-08-08 | 2024-08-08 |  | 2024-08-12 | 2024-08-14 | Büro | 2024-08-23 |  | 2024-08-14 | 2024-10-07 |  |  | 2024-10-15 | 1254 | 150 |  |  |  | 149 | SEP | SEP
62782 | 740-SIV-VS732-102-LH032-50-0 | 1 | true | 1.92 | 740-SIV-VS732-102-LH032-50-0 | LV1-105633.VS732 | 385 |  |  | MC1 | LVL 6 | N/A | TR029_3 | 2024-08-07 | 2024-08-08 | 2024-08-12 |  |  |  | Büro |  |  |  | 2024-10-07 |  |  | 2024-10-12 | 1254 | 150 |  |  |  | 149 | SEP | SEP
62815 | 740-CIP-R-VP003-103-LH088-32-0 | 2 | true | 0.45 | 740-CIP-R-VP003-103-LH088-32-0 | LV0-105628.VP003 | 391 |  |  | MC1 | LVL 5 | Tt-6 | TR032_1 | 2024-08-08 | 2024-08-08 | 2024-08-08 |  | 2024-08-16 | 2024-08-20 | Büro | 2024-08-23 |  | 2024-08-20 | 2024-10-22 |  |  | 2024-10-24 | 928 | 150 |  |  | 2024-10-28 | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
62816 | 740-CIP-R-VP004-103-LH088-32-0 | 2 | true | 3.13 | 740-CIP-R-VP004-103-LH088-32-0 | LV0-105628.VP004 | 391 |  |  | MC1 | LVL 5 | Tt-6 | TR032_1 | 2024-08-08 | 2024-08-08 | 2024-08-08 |  | 2024-08-16 | 2024-08-20 |  | 2024-08-23 |  | 2024-08-20 | 2024-09-25 |  |  | 2024-10-18 | 928 | 150 |  |  | 2024-10-29 | 149 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
62817 | 740-WAKont-VU321-101-LH032-50-0 | 3 | true | 0.13 | 740-WAKont-VU321-101-LH032-50-0 | LV1-105638.VU321 | 385 |  |  | MC1 | LVL 6 | N/A | TR032_1 | 2024-08-08 | 2024-08-08 | 2024-08-08 |  | 2024-08-12 | 2024-08-14 | Büro | 2024-08-23 |  | 2024-08-14 | 2024-10-08 |  |  | 2024-10-12 | 1257 | 150 |  |  | 2024-11-07 | 149 | SEP | SEP
63284 | 727-DK-U172-511-LH011-25-0 | 1 | true | 10.2 | 727-DK-U172-511-LH011-25-0 | LV1-103542.U116 | 369 |  |  | MC1 | LVL 1 | W23 | WP Gen 4 DK;D3 | 2024-08-20 | 2024-08-20 | [11 empty] | 2024-09-02 | 1292 | 150 |  |  | 2024-09-09 | 149 | SEP | SEP
63283 | 727-D3-U111-504-LC008-32-0 | 1 | true | 10.1 | 727-D3-U111-504-LC008-32-0 | LV1-103542.U111 | 388 |  |  | MC1 | LVL 0 | W23 | WP Gen 4 DK;D3 | 2024-08-20 | 2024-08-20 | [11 empty] | 2024-09-17 | 1293 | 150 |  |  |  | 149 | SEP | SEP
63294 | 740-WAn-VU162-214-LH099-40-0 | 1 | true | 0.43 | 740-WAn-VU162-214-LH099-40-0 | LV1-105639.VU162 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR034_1 | 2024-08-21 | 2024-08-21 |  |  |  |  | Büro | [6 empty] | 2024-10-17 | 1034 | 150 |  | 2024-11-08 |  | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
63295 | 740-WAn-VU162-216-LH099-40-0 | 1 | true | 0.43 | 740-WAn-VU162-216-LH099-40-0 | LV1-105639.VU162 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR034_1 | 2024-08-21 | 2024-08-21 |  |  |  |  | Büro | [6 empty] | 2024-10-17 | 1034 | 150 |  | 2024-11-08 |  | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
63297 | 740-WAn-VU200-264-LH099-40-0 | 1 | true | 0.38 | 740-WAn-VU200-264-LH099-40-0 | LV1-105639.VU200 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR034_1 | 2024-08-21 | 2024-08-21 |  |  |  |  | Büro |  |  |  | 2024-10-03 |  |  | 2024-10-08 | 1034 | 150 |  |  | 2024-10-09 | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
63298 | 740-WAn-VU200-265-LH099-40-0 | 1 | true | 0.88 | 740-WAn-VU200-265-LH099-40-0 | LV1-105639.VU200 | 386 |  |  | MC1 | LVL 5 | Tt-6 | TR034_1 | 2024-08-21 | 2024-08-21 |  |  |  |  | Büro |  |  |  | 2024-10-03 |  |  | 2024-10-08 | 1034 | 150 |  |  | 2024-10-09 | 149 | SEP | SEP |  |  | 2024-12-13 | 2024-12-13
63510 | 740-AB-VU310-114-LH032-20-0 | 1 | true | 0.44 | 740-AB-VU310-114-LH032-20-0 | LV1-105638.VU310 | 385 |  |  | MC1 | LVL 5 | N/A | TR014_5 | 2024-09-03 | 2024-09-03 | 2024-09-03 |  | 2024-09-03 |  | Büro |  |  |  | 2024-09-09 |  |  | 2024-09-12 | 1018 | 150 |  |  | 2024-09-12 | 150 | SEP | SEP
63721 | 740-FLN-VP131-114-LH089-25-0 | 1 | true | 10.78 | 740-FLN-VP131-114-LH089-25-0 | LV1-105628.VP051 | 394 |  |  | MC1 | LVL5 | Tt-6 | TR036_1 | 2024-09-06 | 2024-09-19 | 2024-09-19 |  |  |  | Dawid Mierzwa |  |  |  | 2024-11-06 |  |  | 2024-11-15 | 1258 | 150 |  |  |  | 150 | PED | PED | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
63723 | 740-WAn-VU310-145-LH032-25-0 | 1 | false | 4.13 | 740-WAn-VU310-145-LH032-25-0 | LV1-105638.VU310 | 385 |  |  | MC1 | LVL5 | N/A | TR036_1 | 2024-09-06 | 2024-09-19 | 2024-09-19 | [11 empty] | 1034 | 150 |  |  |  | 150 | SEP | SEP
64663 | 740-WAn-VU310-145-LH032-25-0 | 2 | true | 4.13 | 740-WAn-VU310-145-LH032-25-0 | LV1-105638.VU310 | 385 |  |  | MC1 | LVL5 | N/A | TR036_2 | 2024-09-19 | 2024-09-19 | 2024-09-19 |  |  |  | Büro | [6 empty] | 2024-09-26 | 1034 | 150 |  | 2024-10-08 | 2024-10-07 | 150 | SEP | SEP
64665 | 740-MKWP-R-VS651-201-LH099-25-0 | 2 | true | 0 | 740-MKWP-R-VS651-201-LH099-25-0 | LV1-105633.VS651 | 363 |  |  | MC1 | LVL 5 | N/A | TR037_1 | 2024-09-19 | 2024-09-19 | 2024-09-19 |  |  |  | Büro | [6 empty] | 2024-11-28 | 860 | 150 |  |  |  | 150 | SEP | SEP
64666 | 740-MKWP-R-VS652-201-LH099-25-0 | 2 | true | 0 | 740-MKWP-R-VS652-201-LH099-25-0 | LV1-105633.VS652 | 363 |  |  | MC1 | LVL 5 | N/A | TR037_1 | 2024-09-19 | 2024-09-19 | 2024-09-19 |  |  |  | Büro | [6 empty] | 2024-11-28 | 860 | 150 |  |  |  | 150 | SEP | SEP
64667 | 740-MKWP-S-VS651-202-LH099-25-0 | 2 | true | 0 | 740-MKWP-S-VS651-202-LH099-25-0 | LV1-105633.VS651 | 363 |  |  | MC1 | LVL 5 | N/A | TR037_1 | 2024-09-19 | 2024-09-19 | 2024-09-19 |  |  |  | Büro | [6 empty] | 2024-11-28 | 860 | 150 |  |  |  | 150 | SEP | SEP
64668 | 740-MKWP-S-VS652-202-LH099-25-0 | 2 | true | 0 | 740-MKWP-S-VS652-202-LH099-25-0 | LV1-105633.VS652 | 363 |  |  | MC1 | LVL 5 | N/A | TR037_1 | 2024-09-19 | 2024-09-19 | 2024-09-19 |  |  |  | Büro | [6 empty] | 2024-11-28 | 860 | 150 |  |  |  | 150 | SEP | SEP
65867 | 740-WAn-VU200-292-LH032-100-0 | 1 | true | 5.48 | 740-WAn-VU200-292-LH032-100-0 | LV1-105638.VU200 | 385 |  |  | MC1 |  | W60 | TR038_2 | 2024-10-15 | [5 empty] | Büro |  |  |  | 2024-10-16 |  |  | 2024-10-15 | 1259 | 150 |  | 2024-10-25 |  | 150 | SEP | SEP
65870 | 740-WAn-VU190-234-LH032-80-0 | 1 | true | 8.47 | 740-WAn-VU190-234-LH032-80-0 | LV1-105638.VU955 | 385 |  |  | MC1 |  | N/A | TR035_1 | 2024-10-15 | [12 empty] | 2024-11-25 | 915 | 150 |  |  |  | 150 | SEP | SEP
69710 | 727-AB-U261-102-LH032-50-0 | 2 | false | 3.22 | 727-AB-U261-102-LH032-50-0 |  | 385 |  |  | MC1 |  | N/A | TR041_2 | 2024-11-13 | [13 empty] | 1331 | 150 |  |  |  | 150 | SEP | SEP
70048 | 727-MKWP-R-U231-522-LH001-25-0 | 1 | false | 3.17 | 727-MKWP-R-U231-522-LH001-25-0 |  | 363 |  |  | MC1 | LVL 6 | T60 | TR041_2 | 2024-11-13 | [13 empty] | 828 | 150 |  |  |  | 150 | SEP | SEP
70049 | 727-MKWP-S-U231-523-LH001-25-0 | 1 | false | 3.17 | 727-MKWP-S-U231-523-LH001-25-0 |  | 363 |  |  | MC1 | LVL 6 | T60 | TR041_2 | 2024-11-13 | [13 empty] | 828 | 150 |  |  |  | 150 | SEP | SEP
72125 | 740-FLN-VP143-113-LH089-25-0 | 2 | true | 19.65 | 740-FLN-VP143-113-LH089-25-0 | LV1-105628.VP061 | 394 |  |  | MC1 | LVL 5 | Tt-6 | TR042_1 | 2024-12-04 | 2024-05-20 | 2024-05-20 |  | 2024-08-16 | 2024-08-20 |  | 2024-08-23 |  | 2024-08-20 | 2024-09-23 |  |  | 2024-11-08 | 1258 | 150 |  |  |  | 150 | SEP | SEP | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-12-06
93658 | 727-N2-U060-511-LH023-25-0 | 3 | true | 34.94 | 727-N2-U060-511-LH023-25-0 | LV1-103542.U060 | 368 |  |  | MC1 | L1 | N/A | TR044 | 2025-02-13 | 2024-07-25 | 2024-07-25 |  | 2024-08-12 | 2024-08-14 |  | 2024-08-23 |  |  | 2024-10-21 |  |  | 2024-10-30 | 1286 | 150 |  |  |  | 149 | SEP | SEP