## ag-grid
Id | Line No. | Rev. | Latest Rev. | Length | Name | PId | Pipe class | Building | Floor | Insulation | Transmittal No. | Date Rec. | Spooling | Iss. to prefab | Prefab remarks | Prefab start | Welded | Latest location | Sent to site | Work package | Prefab compl. | Install start | Install 50 | Install 90 | Install compl. | Area | Company | Site remarks | As built | Site checked | Prefab Company | Ped Cat | Ped Cat | Insulated | Insulated | Cladding | Cladding | Prios | Room No. | System Name
66104 | DH_F02-PCWR-004-DN450-I16C00_R0 | 0 | true | 80.04 | DH_F02-PCWR-004-DN450-I16C00_R0 | LPP6A-M-501-XX-EX | 1129 | Datahall | F02 | N/A | TBH-ZAT-2024-10-18 | 2024-10-14 | 2024-10-26 | 2024-11-06 |  | 2024-12-10 | 2025-01-14 | Office 08.03.2025 | 2025-01-15 |  | 2025-01-15 | 2025-02-03 | 2025-02-06 | 2025-02-10 | 2025-03-22 | 1352 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2024-11-11 | 2-500 | System PCW 01
66105 | DH_F02-PCWR-005-DN150-I16C00_R0 | 0 | true | 93.77 | DH_F02-PCWR-005-DN150-I16C00_R0 |  | 1129 | Datahall | F02 | N/A | TBH-ZAT-2024-10-18 | 2024-10-14 | 2024-10-26 | 2024-11-06 |  | 2024-11-09 | 2024-11-20 | Office 31.03.2025 | 2024-12-03 |  | 2024-11-23 | 2024-12-11 | 2024-12-12 | 2025-02-07 | 2025-03-22 | 1352 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2024-12-11 | 2-500 | System PCW 01
66106 | DH_F02-PCWR-006-DN450-I16C00_R0 | 0 | true | 80.04 | DH_F02-PCWR-006-DN450-I16C00_R0 |  | 1129 | Datahall | F02 | N/A | TBH-ZAT-2024-10-18 | 2024-10-14 | 2024-10-26 | 2024-11-06 |  | 2024-12-16 | 2025-01-15 | Office 12.03.2025 | 2025-01-22 |  | 2025-01-19 | 2025-02-03 | 2025-02-14 | 2025-03-22 | 2025-03-22 | 1352 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2024-11-11 | 2-500 | System PCW 01
66107 | DH_F02-PCWR-007-DN025-I16C00_R0 | 0 | true | 11.37 | DH_F02-PCWR-007-DN025-I16C00_R0 |  | 1129 | Datahall | F02 | N/A | TBH-ZAT-2024-10-18 | 2024-10-14 | 2024-10-25 | 2024-11-06 |  | 2024-12-10 | 2024-12-18 | Office 04/03/2025 | 2025-01-07 |  | 2024-12-19 | 2025-03-03 | 2025-03-03 | 2025-03-04 | 2025-03-22 | 1352 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 29.11.2024 00:00:00 | 2-500 | System PCW 01
66108 | DH_F02-PCWR-009-DN250-I16C00_R0 | 0 | false | 5.69 | DH_F02-PCWR-009-DN250-I16C00_R0 | LPP6A-M-503-01-DH | 1129 | Datahall | F02 | N/A | TBH-ZAT-2024-10-18 | 2024-10-14 | 2024-10-25 | [12 empty] | 1352 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-500
66109 | DH_F02-PCWR-010-DN250-I16C00_R0 | 0 | false | 4.28 | DH_F02-PCWR-010-DN250-I16C00_R0 | LPP6A-M-503-01-DH | 1129 | Datahall | F02 | N/A | TBH-ZAT-2024-10-18 | 2024-10-14 | 2024-10-25 | 2024-11-30 | [11 empty] | 1352 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-500
66110 | DH_F02-PCWR-013-DN150-I16C00_R0 | 0 | false | 6.88 | DH_F02-PCWR-013-DN150-I16C00_R0 | LPP6A-M-503-01-DH | 1129 | Datahall | F02 | N/A | TBH-ZAT-2024-10-18 | 2024-10-14 | 2024-11-05 | [12 empty] | 1352 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-500
66111 | DH_F02-PCWR-014-DN150-I16C00_R0 | 0 | false | 6.23 | DH_F02-PCWR-014-DN150-I16C00_R0 | LPP6A-M-503-01-DH | 1129 | Datahall | F02 | N/A | TBH-ZAT-2024-10-18 | 2024-10-14 | 2024-10-26 | [12 empty] | 1352 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-500
66112 | DH_F02-PCWR-022-DN150-I16C00_R0 | 0 | true | 90.7 | DH_F02-PCWR-022-DN150-I16C00_R0 | LPP6A-M-503-01-DH | 1129 | Datahall | F02 | N/A | TBH-ZAT-2024-10-18 | 2024-10-14 | 2024-10-26 | 2024-11-06 |  | 2024-11-09 | 2024-11-20 | Office 22.03.2025 | 2024-12-03 |  | 2024-11-23 | 2024-12-16 | 2024-12-17 | 2025-02-07 | 2025-03-22 | 1352 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 20.11.2024 00:00:00 | 2-500 | System PCW 01
66113 | DH_F02-PCWR-030-DN150-I16C00_R0 | 0 | true | 97.02 | DH_F02-PCWR-030-DN150-I16C00_R0 |  | 1129 | Datahall | F02 | N/A | TBH-ZAT-2024-10-18 | 2024-10-14 | 2024-11-01 | 2024-11-06 |  | 2024-11-09 | 2024-11-23 | Office 31.03.2025 | 2024-12-03 |  | 2024-11-23 | 2024-12-11 | 2024-12-17 | 2025-02-07 | 2025-03-22 | 1352 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 13.11.2024 00:00:00 | 2-500 | System PCW 01
66114 | DH_F02-PCWR-031-DN150-I16C00_R0 | 0 | true | 97.06 | DH_F02-PCWR-031-DN150-I16C00_R0 |  | 1129 | Datahall | F02 | N/A | TBH-ZAT-2024-10-18 | 2024-10-14 | 2024-10-27 | 2024-11-06 |  | 2024-11-11 | 2024-11-24 | Office 31.03.2025 | 2024-12-03 |  | 2024-12-02 | 2024-12-17 | 2024-12-17 | 2025-02-07 | 2025-03-22 | 1352 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 14.11.2024 00:00:00 | 2-500 | System PCW 01
66115 | DH_F02-PCWR-032-DN150-I16C00_R0 | 0 | true | 96.94 | DH_F02-PCWR-032-DN150-I16C00_R0 |  | 1129 | Datahall | F02 | N/A | TBH-ZAT-2024-10-18 | 2024-10-14 | 2024-11-01 | 2024-11-06 |  | 2024-11-17 | 2024-11-26 | Office 22.03.2025 | 2024-12-03 |  | 2024-12-02 | 2025-01-22 | 2025-01-22 | 2025-02-07 | 2025-03-22 | 1352 | 193 | Line used for DH_F02-PCWR-034-DN150-I16C00 |  |  | 194 | SEP | SEP |  |  |  |  | 15.11.2024 00:00:00 | 2-500 | System PCW 01
66116 | DH_F02-PCWR-033-DN150-I16C00_R0 | 0 | true | 97.02 | DH_F02-PCWR-033-DN150-I16C00_R0 |  | 1129 | Datahall | F02 | N/A | TBH-ZAT-2024-10-18 | 2024-10-14 | 2024-11-01 | 2024-11-06 |  | 2024-11-17 | 2024-12-02 | Office 31.03.2025 | 2024-12-11 |  | 2024-12-04 | 2024-12-16 | 2025-01-14 | 2025-02-07 | 2025-03-22 | 1352 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 16.11.2024 00:00:00 | 2-500 | System PCW 01
66117 | DH_F02-PCWR-034-DN150-I16C00_R0 | 0 | true | 96.98 | DH_F02-PCWR-034-DN150-I16C00_R0 |  | 1129 | Datahall | F02 | N/A | TBH-ZAT-2024-10-18 | 2024-10-14 | 2024-11-01 | 2024-11-06 |  | 2024-11-26 | 2025-01-06 | Anto Andrijanic 27.03.2025 | 2025-01-15 |  | 2025-01-09 | 2025-02-03 | 2025-02-06 | 2025-02-07 | 2025-03-22 | 1352 | 193 | Line used for DH_F02-PCWR-032-DN150-I16C00 |  |  | 194 | SEP | SEP |  |  |  |  | 17.11.2024 00:00:00 | 2-500 | System PCW 01
66118 | DH_F02-PCWR-035-DN150-I16C00_R0 | 0 | true | 96.94 | DH_F02-PCWR-035-DN150-I16C00_R0 |  | 1129 | Datahall | F02 | N/A | TBH-ZAT-2024-10-18 | 2024-10-14 | 2024-11-09 | 2024-11-06 |  | 2024-11-26 | 2024-12-10 | Office 22.03.2025 | 2024-12-11 |  | 2024-12-11 | 2024-12-16 | 2025-01-14 | 2025-02-07 | 2025-03-22 | 1352 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 18.11.2024 00:00:00 | 2-500 | System PCW 01
66119 | DH_F02-PCWR-036-DN150-I16C00_R0 | 0 | true | 97.02 | DH_F02-PCWR-036-DN150-I16C00_R0 |  | 1129 | Datahall | F02 | N/A | TBH-ZAT-2024-10-18 | 2024-10-14 | 2024-11-13 | 2024-11-06 |  | 2024-11-26 | 2024-12-10 | Office 22.03.2025 | 2024-12-11 |  | 2024-12-11 | 2024-12-16 | 2025-01-14 | 2025-02-07 | 2025-03-22 | 1352 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 19.11.2024 00:00:00 | 2-500 | System PCW 01
66120 | DH_F02-PCWS-004-DN450-I16C00_R0 | 0 | true | 80.12 | DH_F02-PCWS-004-DN450-I16C00_R0 |  | 1129 | Datahall | F02 | N/A | TBH-ZAT-2024-10-18 | 2024-10-14 | 2024-10-26 | 2024-11-06 |  | 2024-12-10 | 2025-01-06 | Office 08.03.2025 | 2025-01-15 |  | 2025-01-09 | 2025-02-01 | 2025-02-03 | 2025-02-05 | 2025-03-22 | 1352 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 18.11.2024 00:00:00 | 2-500 | System PCW 01
66121 | DH_F02-PCWS-005-DN150-I16C00_R0 | 0 | true | 90.57 | DH_F02-PCWS-005-DN150-I16C00_R0 |  | 1129 | Datahall | F02 | FoamInside | TBH-ZAT-2024-10-18 | 2024-10-14 | 2024-11-10 | 2024-11-06 |  | 2024-11-18 | 2024-12-02 | Office 31.03.2025 | 2024-12-03 |  | 2024-12-03 | 2024-12-10 | 2024-12-15 | 2025-02-07 | 2025-03-22 | 1352 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2024-12-11 | 2-500 | System PCW 01
66122 | DH_F02-PCWS-006-DN450-I16C00_R0 | 0 | true | 80.16 | DH_F02-PCWS-006-DN450-I16C00_R0 |  | 1129 | Datahall | F02 | N/A | TBH-ZAT-2024-10-18 | 2024-10-14 | 2024-10-26 | 2024-11-06 |  | 2024-12-16 | 2025-01-15 | Office 12.03.2025 | 2025-01-22 |  | 2025-01-19 | 2025-02-03 | 2025-02-14 | 2025-03-22 | 2025-03-22 | 1352 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 18.11.2024 00:00:00 | 2-500 | System PCW 01
66123 | DH_F02-PCWS-007-DN025-I16C00_R0 | 0 | true | 10.23 | DH_F02-PCWS-007-DN025-I16C00_R0 |  | 1129 | Datahall | F02 | N/A | TBH-ZAT-2024-10-18 | 2024-10-14 | 2024-10-26 | 2024-11-06 |  | 2024-12-10 | 2024-12-18 | Office 04/03/2025 | 2025-01-07 |  | 2024-12-19 | 2025-03-01 | 2025-03-03 | 2025-03-04 | 2025-03-22 | 1352 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 29.11.2024 00:00:00 | 2-500 | System PCW 01
66124 | DH_F02-PCWS-008-DN150-I16C00_R0 | 0 | false | 4.85 | DH_F02-PCWS-008-DN150-I16C00_R0 | LPP6A-M-503-01-DH | 1129 | Datahall | F02 | N/A | TBH-ZAT-2024-10-18 | 2024-10-14 | 2024-10-26 | [12 empty] | 1352 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-500
66125 | DH_F02-PCWS-009-DN150-I16C00_R0 | 0 | false | 4.1 | DH_F02-PCWS-009-DN150-I16C00_R0 | LPP6A-M-503-01-DH | 1129 | Datahall | F02 | N/A | TBH-ZAT-2024-10-18 | 2024-10-14 | [13 empty] | 1352 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-500
66126 | DH_F02-PCWS-017-DN150-I16C00_R0 | 0 | true | 93.32 | DH_F02-PCWS-017-DN150-I16C00_R0 | LPP6A-M-503-01-DH | 1129 | Datahall | F02 | FoamInside | TBH-ZAT-2024-10-18 | 2024-10-15 | 2024-11-05 | 2024-11-06 |  | 2024-11-30 | 2024-12-09 | Office 22.03.2025 | 2024-12-11 |  | 2024-12-10 | 2024-12-16 | 2024-12-19 | 2025-02-07 | 2025-02-25 | 1352 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 20.11.2024 00:00:00 | 2-500 | System PCW 01
66127 | DH_F02-PCWS-025-DN150-I16C00_R0 | 0 | true | 97.04 | DH_F02-PCWS-025-DN150-I16C00_R0 |  | 1129 | Datahall | F02 | FoamInside | TBH-ZAT-2024-10-18 | 2024-10-14 | 2024-11-05 | 2024-11-06 |  | 2024-11-18 | 2024-12-06 | Office 22.03.2025 | 2024-12-11 |  | 2024-12-09 | 2024-12-16 | 2025-01-20 | 2025-02-07 | 2025-03-26 | 1352 | 193 | Line used for DH_F02-PCWS-029-DN150-I16C00 |  |  | 194 | SEP | SEP |  |  |  |  | 13.11.2024 00:00:00 | 2-500 | System PCW 01
66128 | DH_F02-PCWS-026-DN150-I16C00_R0 | 0 | true | 97.08 | DH_F02-PCWS-026-DN150-I16C00_R0 |  | 1129 | Datahall | F02 | FoamInside | TBH-ZAT-2024-10-18 | 2024-10-14 | 2024-11-04 | 2024-11-06 |  | 2024-11-19 | 2024-12-06 | Office 31.03.2025 | 2024-12-11 |  | 2024-12-09 | 2024-12-16 | 2025-01-21 | 2025-02-07 | 2025-03-26 | 1352 | 193 | Line used for DH_F02-PCWS-028-DN150-I16C00 |  |  | 194 | SEP | SEP |  |  |  |  | 14.11.2024 00:00:00 | 2-500 | System PCW 01
66129 | DH_F02-PCWS-027-DN150-I16C00_R0 | 0 | true | 97.04 | DH_F02-PCWS-027-DN150-I16C00_R0 |  | 1129 | Datahall | F02 | FoamInside | TBH-ZAT-2024-10-18 | 2024-10-14 | 2024-11-04 | 2024-11-06 |  | 2024-11-19 | 2024-12-06 | Office 22.03.2025 | 2024-12-11 |  | 2024-12-09 | 2024-12-16 | 2025-01-15 | 2025-02-07 | 2025-03-24 | 1352 | 193 | Line used for DH_F02-PCWS-031-DN150-I16C00 |  |  | 194 | SEP | SEP |  |  |  |  | 15.11.2024 00:00:00 | 2-500 | System PCW 01
66130 | DH_F02-PCWS-028-DN150-I16C00_R0 | 0 | true | 97.04 | DH_F02-PCWS-028-DN150-I16C00_R0 |  | 1129 | Datahall | F02 | FoamInside | TBH-ZAT-2024-10-18 | 2024-10-14 | 2024-11-03 | 2024-11-06 |  | 2024-11-23 | 2024-12-16 | Office 31.03.2025 | 2025-01-07 |  | 2024-12-18 | 2025-01-20 | 2025-02-06 | 2025-02-07 | 2025-03-22 | 1352 | 193 | Line used for DH_F02-PCWS-026-DN150-I16C00 |  |  | 194 | SEP | SEP |  |  |  |  | 16.11.2024 00:00:00 | 2-500 | System PCW 01
66131 | DH_F02-PCWS-029-DN150-I16C00_R0 | 0 | true | 97.08 | DH_F02-PCWS-029-DN150-I16C00_R0 |  | 1129 | Datahall | F02 | FoamInside | TBH-ZAT-2024-10-18 | 2024-10-14 | 2024-11-05 | 2024-11-06 |  | 2024-11-23 | 2025-01-06 | Office 27.03.2025 | 2025-01-15 |  | 2025-01-09 | 2025-02-03 | 2025-02-06 | 2025-02-07 | 2025-03-22 | 1352 | 193 | Line used for DH_F02-PCWS-025-DN150-I16C00 |  |  | 194 | SEP | SEP |  |  |  |  | 17.11.2024 00:00:00 | 2-500 | System PCW 01
66132 | DH_F02-PCWS-030-DN150-I16C00_R0 | 0 | true | 97.04 | DH_F02-PCWS-030-DN150-I16C00_R0 |  | 1129 | Datahall | F02 | FoamInside | TBH-ZAT-2024-10-18 | 2024-10-14 | 2024-11-05 | 2024-11-06 |  | 2024-11-30 | 2024-12-09 | Office 22.03.2025 | 2024-12-11 |  | 2024-12-10 | 2024-12-16 | 2025-01-14 | 2025-02-07 | 2025-03-22 | 1352 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 18.11.2024 00:00:00 | 2-500 | System PCW 01
66133 | DH_F02-PCWS-031-DN150-I16C00_R0 | 0 | true | 97.12 | DH_F02-PCWS-031-DN150-I16C00_R0 |  | 1129 | Datahall | F02 | FoamInside | TBH-ZAT-2024-10-18 | 2024-10-14 | 2024-11-05 | 2024-11-06 |  | 2024-11-30 | 2024-12-12 | Office 27.03.2025 | 2025-01-07 |  | 2024-12-18 | 2025-01-20 | 2025-02-06 | 2025-02-07 | 2025-03-22 | 1352 | 193 | Line used for DH_F02-PCWS-027-DN150-I16C00 |  |  | 194 | SEP | SEP |  |  |  |  | 19.11.2024 00:00:00 | 2-500 | System PCW 01
67254 | DH_F02-PCWR-009-DN250-I16C00_R1 | 1 | true | 5.69 | DH_F02-PCWR-009-DN250-I16C00_R1 |  | 1129 | Datahall | F02 | N/A | TBH-ZAT-2024-10-25 | 2024-10-25 | 2024-11-12 | 2024-11-06 |  | 2024-12-23 | 2025-01-06 | Office 17.03.2025 | 2025-01-15 |  | 2025-01-09 | 2025-03-15 | 2025-03-15 | 2025-03-15 | 2025-03-15 | 1352 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 29.11.2024 00:00:00 | 2-500 | System PCW 01
67255 | DH_F02-PCWR-010-DN250-I16C00_R1 | 1 | true | 4.28 | DH_F02-PCWR-010-DN250-I16C00_R1 |  | 1129 | Datahall | F02 | N/A | TBH-ZAT-2024-10-25 | 2024-10-25 | 2024-11-12 | 2024-11-06 |  | 2024-12-23 | 2025-01-06 | Office 06/03/2025 | 2025-01-15 |  | 2025-01-09 | 2025-03-04 | 2025-03-04 | 2025-03-04 | 2025-03-22 | 1352 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 29.11.2024 00:00:00 | 2-500 | System PCW 01
67256 | DH_F02-PCWR-013-DN150-I16C00_R1 | 0 | false | 6.88 | DH_F02-PCWR-013-DN150-I16C00_R1 | LPP6A-M-503-01-DH | 1129 | Datahall | F02 | N/A | TBH-ZAT-2024-10-25 | 2024-10-25 | 2024-11-05 | [12 empty] | 1352 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-500
67257 | DH_F02-PCWR-014-DN150-I16C00_R1 | 1 | true | 6.23 | DH_F02-PCWR-014-DN150-I16C00_R1 | LPP6A-M-503-01-DH | 1129 | Datahall | F02 | N/A | TBH-ZAT-2024-10-25 | 2024-10-25 | 2024-11-13 | 2024-11-06 |  | 2025-01-02 | 2025-01-19 | Office 06/03/2025 | 2025-01-29 |  | 2025-01-23 | 2025-03-01 | 2025-03-01 | 2025-03-03 | 2025-03-22 | 1352 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 29.11.2024 00:00:00 | 2-500 | System PCW 01/System PCW 02
67258 | DH_F02-PCWS-008-DN150-I16C00_R1 | 0 | false | 4.85 | DH_F02-PCWS-008-DN150-I16C00_R1 | LPP6A-M-503-01-DH | 1129 | Datahall | F02 | N/A | TBH-ZAT-2024-10-25 | 2024-10-25 | 2024-11-05 | [12 empty] | 1352 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-500
67259 | DH_F02-PCWS-009-DN150-I16C00_R1 | 1 | true | 4.1 | DH_F02-PCWS-009-DN150-I16C00_R1 | LPP6A-M-503-01-DH | 1129 | Datahall | F02 | N/A | TBH-ZAT-2024-10-25 | 2024-10-25 | 2024-11-13 | 2024-11-06 |  | 2025-01-02 | 2025-01-19 | Office 06/03/2025 | 2025-01-29 |  | 2025-01-22 | 2025-02-26 | 2025-02-27 | 2025-03-03 | 2025-03-22 | 1352 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 29.11.2024 00:00:00 | 2-500 | System PCW 01/System PCW 02
67260 | EB_F02-CHWR-211-DN020-I16C00_1_R0 | 0 | true | 4.52 | EB_F02-CHWR-211-DN020-I16C00_1_R0 |  | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-25 | 2024-10-25 | 2024-11-06 | 2024-11-06 |  | 2024-11-25 | 2024-12-03 | Office 27/02/2025 | 2024-12-03 |  | 2024-12-03 | 2024-12-10 | 2024-12-17 | 2025-03-07 | 2025-03-10 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 14.11.2024 00:00:00 | 2-304 | System CHW and LTHW FIRST FLOOR
67261 | EB_F02-CHWR-212-DN020-I16C00_1_R0 | 0 | true | 7.19 | EB_F02-CHWR-212-DN020-I16C00_1_R0 |  | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-25 | 2024-10-25 | 2024-11-06 | 2024-11-06 |  | 2024-11-25 | 2024-12-02 | Office 27/02/2025 | 2024-12-03 |  | 2024-12-03 | 2024-12-11 | 2024-12-17 | 2025-03-19 | 2025-03-19 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 14.11.2024 00:00:00 | 2-304 | System CHW and LTHW FIRST FLOOR
67262 | EB_F02-CHWR-213-DN020-I16C00_1_R0 | 0 | true | 9.86 | EB_F02-CHWR-213-DN020-I16C00_1_R0 |  | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-25 | 2024-10-25 | 2024-11-06 | 2024-11-06 |  | 2024-11-25 | 2024-12-02 | Office 27/02/2025 | 2024-12-03 |  | 2024-12-03 | 2024-12-12 | 2024-12-17 | 2025-03-08 | 2025-03-22 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 14.11.2024 00:00:00 | 2-304 | System CHW and LTHW FIRST FLOOR
67263 | EB_F02-CHWR-214-DN020-I16C00_1_R0 | 0 | true | 12.47 | EB_F02-CHWR-214-DN020-I16C00_1_R0 |  | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-25 | 2024-10-25 | 2024-11-06 | 2024-11-06 |  | 2024-11-25 | 2024-12-02 | Office 27/02/2025 | 2024-12-03 |  | 2024-12-03 | 2024-12-12 | 2024-12-17 | 2025-03-10 | 2025-03-10 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 14.11.2024 00:00:00 | 2-304 | System CHW and LTHW FIRST FLOOR
67264 | EB_F02-CHWR-215-DN020-I16C00_1_R0 | 0 | true | 4.45 | EB_F02-CHWR-215-DN020-I16C00_1_R0 |  | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-25 | 2024-10-25 | 2024-11-06 | 2024-11-06 |  | 2024-11-25 | 2024-12-02 | Office 27/02/2025 | 2024-12-03 |  | 2024-12-03 | 2024-12-15 | 2024-12-17 | 2025-03-22 | 2025-03-22 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 14.11.2024 00:00:00 | 2-303 | System CHW and LTHW FIRST FLOOR
67265 | EB_F02-CHWR-216-DN020-I16C00_1_R0 | 0 | true | 7.23 | EB_F02-CHWR-216-DN020-I16C00_1_R0 |  | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-25 | 2024-10-25 | 2024-11-06 | 2024-11-06 |  | 2024-11-25 | 2024-12-03 | Office 27/02/2025 | 2024-12-03 |  | 2024-12-03 | 2024-12-16 | 2024-12-16 | 2025-03-22 | 2025-03-22 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 14.11.2024 00:00:00 | 2-303 | System CHW and LTHW FIRST FLOOR
67266 | EB_F02-CHWR-217-DN020-I16C00_1_R0 | 0 | true | 9.93 | EB_F02-CHWR-217-DN020-I16C00_1_R0 |  | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-25 | 2024-10-25 | 2024-11-05 | 2024-11-06 |  | 2024-11-25 | 2024-12-02 | Office 27/02/2025 | 2024-12-03 |  | 2024-12-03 | 2024-12-17 | 2024-12-17 | 2025-03-12 | 2025-03-22 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 14.11.2024 00:00:00 | 2-303 | System CHW and LTHW FIRST FLOOR
67267 | EB_F02-CHWR-218-DN020-I16C00_1_R0 | 0 | true | 12.25 | EB_F02-CHWR-218-DN020-I16C00_1_R0 |  | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-25 | 2024-10-25 | 2024-11-05 | 2024-11-06 |  | 2024-11-25 | 2024-12-03 | Office 27/02/2025 | 2024-12-03 |  | 2024-12-03 | 2024-12-17 | 2024-12-17 | 2025-03-22 | 2025-03-22 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 14.11.2024 00:00:00 | 2-303 | System CHW and LTHW FIRST FLOOR
67268 | EB_F02-CHWR-219-DN025-I16C00_1_R0 | 0 | true | 11.81 | EB_F02-CHWR-219-DN025-I16C00_1_R0 |  | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-25 | 2024-10-25 | 2024-11-05 | 2024-11-06 |  | 2024-11-25 | 2024-12-03 | Office 05/03/2025 | 2024-12-03 |  | 2024-12-03 | 2025-02-26 | 2025-02-28 | 2025-03-22 | 2025-03-22 | 1359 | 193 | Additional Support installed per Client request |  |  | 194 | SEP | SEP |  |  |  |  | 14.11.2024 00:00:00 | 2-302 | System CHW and LTHW FIRST FLOOR
67269 | EB_F02-CHWR-220-DN025-I16C00_1_R0 | 0 | true | 7.4 | EB_F02-CHWR-220-DN025-I16C00_1_R0 |  | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-25 | 2024-10-25 | 2024-11-04 | 2024-11-20 |  | 2024-11-25 | 2024-12-03 | Office 05/03/2025 | 2024-12-11 |  | 2024-12-04 | 2025-03-03 | 2025-03-04 | 2025-03-22 | 2025-03-22 | 1359 | 193 | Additional Support installed per Client request |  |  | 194 | SEP | SEP |  |  |  |  | 14.11.2024 00:00:00 | 2-302 | System CHW and LTHW FIRST FLOOR
67270 | EB_F02-CHWS-211-DN020-I16C00_2_R0 | 0 | true | 4.32 | EB_F02-CHWS-211-DN020-I16C00_2_R0 |  | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-25 | 2024-10-25 | 2024-11-04 | 2024-11-20 |  | 2024-11-25 | 2024-12-02 | Office 27/02/2025 | 2024-12-03 |  | 2024-12-03 | 2024-12-09 | 2024-12-17 | 2025-03-07 | 2025-03-10 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 14.11.2024 00:00:00 | 2-235 | System CHW and LTHW FIRST FLOOR
67271 | EB_F02-CHWS-212-DN020-I16C00_2_R0 | 0 | true | 6.99 | EB_F02-CHWS-212-DN020-I16C00_2_R0 |  | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-25 | 2024-10-25 | 2024-11-04 | 2024-11-20 |  | 2024-11-25 | 2024-12-02 | Office 27/02/2025 | 2024-12-03 |  | 2024-12-03 | 2024-12-12 | 2024-12-17 | 2025-03-11 | 2025-03-11 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 14.11.2024 00:00:00 | 2-235 | System CHW and LTHW FIRST FLOOR
67272 | EB_F02-CHWS-213-DN020-I16C00_2_R0 | 0 | true | 9.66 | EB_F02-CHWS-213-DN020-I16C00_2_R0 |  | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-25 | 2024-10-25 | 2024-11-04 | 2024-11-20 |  | 2024-11-25 | 2024-12-03 | Office 27/02/2025 | 2024-12-11 |  | 2024-12-04 | 2025-02-21 | 2025-02-21 | 2025-03-11 | 2025-03-11 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 14.11.2024 00:00:00 | 2-235 | System CHW and LTHW FIRST FLOOR
67273 | EB_F02-CHWS-214-DN020-I16C00_2_R0 | 0 | true | 12.25 | EB_F02-CHWS-214-DN020-I16C00_2_R0 |  | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-25 | 2024-10-25 | 2024-11-04 | 2024-11-20 |  | 2024-11-25 | 2024-12-03 | Office 27/02/2025 | 2024-12-03 |  | 2024-12-03 | 2024-12-13 | 2024-12-17 | 2025-03-19 | 2025-03-19 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 14.11.2024 00:00:00 | 2-235 | System CHW and LTHW FIRST FLOOR
67274 | EB_F02-CHWS-215-DN020-I16C00_2_R0 | 0 | true | 4.22 | EB_F02-CHWS-215-DN020-I16C00_2_R0 |  | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-25 | 2024-10-25 | 2024-11-03 | 2024-11-20 |  | 2024-11-25 | 2024-12-03 | Office 27/02/2025 | 2024-12-03 |  | 2024-12-03 | 2024-12-15 | 2024-12-17 | 2025-03-22 | 2025-03-22 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 14.11.2024 00:00:00 | 2-235 | System CHW and LTHW FIRST FLOOR
67275 | EB_F02-CHWS-216-DN020-I16C00_2_R0 | 0 | true | 6.98 | EB_F02-CHWS-216-DN020-I16C00_2_R0 |  | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-25 | 2024-10-25 | 2024-11-03 | 2024-11-20 |  | 2024-11-25 | 2024-12-03 | Office 27/02/2025 | 2024-12-11 |  | 2024-12-04 | 2025-02-19 | 2025-02-21 | 2025-03-22 | 2025-03-22 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 14.11.2024 00:00:00 | 2-235 | System CHW and LTHW FIRST FLOOR
67276 | EB_F02-CHWS-217-DN020-I16C00_2_R0 | 0 | true | 9.68 | EB_F02-CHWS-217-DN020-I16C00_2_R0 |  | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-25 | 2024-10-26 | 2024-11-04 | 2024-11-20 |  | 2024-11-25 | 2024-12-03 | Office 27/02/2025 | 2024-12-03 |  | 2024-12-03 | 2024-12-16 | 2024-12-16 | 2025-03-12 | 2025-03-22 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 14.11.2024 00:00:00 | 2-235 | System CHW and LTHW FIRST FLOOR
67277 | EB_F02-CHWS-218-DN020-I16C00_2_R0 | 0 | true | 11.7 | EB_F02-CHWS-218-DN020-I16C00_2_R0 |  | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-25 | 2024-10-25 | 2024-11-05 | 2024-11-20 |  | 2024-11-25 | 2024-12-10 | Office 27/02/2025 | 2024-12-11 |  | 2024-12-11 | 2025-02-19 | 2025-02-19 | 2025-03-22 | 2025-03-22 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-235 | System CHW and LTHW FIRST FLOOR
67278 | EB_F02-CHWS-219-DN025-I16C00_2_R0 | 0 | true | 11.89 | EB_F02-CHWS-219-DN025-I16C00_2_R0 |  | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-25 | 2024-10-25 | 2024-11-05 | 2024-11-20 |  | 2024-11-26 | 2024-12-06 | Office 05/03/2025 | 2024-12-11 |  | 2024-12-08 | 2025-02-25 | 2025-02-26 | 2025-03-01 | 2025-03-22 | 1359 | 193 | Additional Support installed per Client request |  |  | 194 | SEP | SEP |  |  |  |  | 14.11.2024 00:00:00 | 2-235 | System CHW and LTHW FIRST FLOOR
67279 | EB_F02-CHWS-220-DN025-I16C00_2_R0 | 0 | true | 7.18 | EB_F02-CHWS-220-DN025-I16C00_2_R0 |  | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-25 | 2024-10-25 | 2024-11-05 | 2024-11-20 |  | 2024-11-26 | 2024-12-10 | Office 05/03/2025 | 2024-12-11 |  | 2024-12-11 | 2025-03-04 | 2025-03-04 | 2025-03-22 | 2025-03-22 | 1359 | 193 | Additional Support installed per Client request |  |  | 194 | SEP | SEP | [5 empty] | 2-235 | System CHW and LTHW FIRST FLOOR
67280 | EB_F02-LTHWR-211-DN015-I16C00_1_R0 | 0 | true | 4.17 | EB_F02-LTHWR-211-DN015-I16C00_1_R0 |  | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-25 | 2024-10-25 | 2024-11-05 | 2024-11-20 |  | 2024-11-11 | 2024-11-18 | Office 27/02/2025 | 2024-12-03 |  | 2024-11-23 | 2025-02-25 | 2025-02-25 | 2025-03-06 | 2025-03-22 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 14.11.2024 00:00:00 | 2-304 | System CHW and LTHW FIRST FLOOR
67281 | EB_F02-LTHWR-212-DN015-I16C00_1_R0 | 0 | true | 6.86 | EB_F02-LTHWR-212-DN015-I16C00_1_R0 |  | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-25 | 2024-10-25 | 2024-11-05 | 2024-11-06 |  | 2024-11-11 | 2024-11-18 | Office 27/02/2025 | 2024-12-03 |  | 2024-11-23 | 2024-12-12 | 2024-12-17 | 2025-03-19 | 2025-03-19 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-304 | System CHW and LTHW FIRST FLOOR
67282 | EB_F02-LTHWR-213-DN015-I16C00_1_R0 | 0 | true | 9.51 | EB_F02-LTHWR-213-DN015-I16C00_1_R0 |  | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-25 | 2024-10-25 | 2024-11-05 | 2024-11-06 |  | 2024-11-11 | 2024-11-18 | Office 27/02/2025 | 2024-12-03 |  | 2024-11-23 | 2024-12-12 | 2024-12-17 | 2025-03-08 | 2025-03-22 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 14.11.2024 00:00:00 | 2-304 | System CHW and LTHW FIRST FLOOR
67283 | EB_F02-LTHWR-214-DN015-I16C00_1_R0 | 0 | true | 12.17 | EB_F02-LTHWR-214-DN015-I16C00_1_R0 |  | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-25 | 2024-10-25 | 2024-11-05 | 2024-11-06 |  | 2024-11-11 | 2024-11-18 | Office 27/02/2025 | 2024-12-03 |  | 2024-11-23 | 2024-12-12 | 2024-12-17 | 2025-03-06 | 2025-03-22 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-304 | System CHW and LTHW FIRST FLOOR
67284 | EB_F02-LTHWR-215-DN015-I16C00_1_R0 | 0 | true | 4.15 | EB_F02-LTHWR-215-DN015-I16C00_1_R0 |  | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-25 | 2024-10-25 | 2024-11-05 | 2024-11-06 |  | 2024-11-11 | 2024-11-18 | Office 27/02/2025 | 2024-12-03 |  | 2024-11-23 | 2024-12-15 | 2024-12-17 | 2025-03-11 | 2025-03-11 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 14.11.2024 00:00:00 | 2-303 | System CHW and LTHW FIRST FLOOR
67285 | EB_F02-LTHWR-216-DN015-I16C00_1_R0 | 0 | true | 6.9 | EB_F02-LTHWR-216-DN015-I16C00_1_R0 |  | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-25 | 2024-10-25 | 2024-11-05 | 2024-11-06 |  | 2024-11-11 | 2024-11-18 | Office 27/02/2025 | 2024-12-03 |  | 2024-11-23 | 2024-12-16 | 2024-12-16 | 2025-03-22 | 2025-03-22 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-303 | System CHW and LTHW FIRST FLOOR
67286 | EB_F02-LTHWR-217-DN015-I16C00_1_R0 | 0 | true | 9.59 | EB_F02-LTHWR-217-DN015-I16C00_1_R0 |  | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-25 | 2024-10-25 | 2024-11-05 | 2024-11-06 |  | 2024-11-13 | 2024-11-18 | Office 27/02/2025 | 2024-12-03 |  | 2024-11-23 | 2024-12-16 | 2024-12-16 | 2025-03-12 | 2025-03-22 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 14.11.2024 00:00:00 | 2-303 | System CHW and LTHW FIRST FLOOR
67287 | EB_F02-LTHWR-218-DN015-I16C00_1_R0 | 0 | true | 12.71 | EB_F02-LTHWR-218-DN015-I16C00_1_R0 |  | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-25 | 2024-10-25 | 2024-11-05 | 2024-11-06 |  | 2024-11-13 | 2024-11-18 | Office 27/02/2025 | 2024-12-03 |  | 2024-11-23 | 2024-12-17 | 2024-12-17 | 2025-03-14 | 2025-03-22 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 14.11.2024 00:00:00 | 2-303 | System CHW and LTHW FIRST FLOOR
67288 | EB_F02-LTHWR-219-DN015-I16C00_1_R0 | 0 | true | 12.49 | EB_F02-LTHWR-219-DN015-I16C00_1_R0 |  | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-25 | 2024-10-25 | 2024-11-05 | 2024-11-06 |  | 2024-11-13 | 2024-12-02 | Office 05/03/2025 | 2024-12-03 |  | 2024-12-03 | 2025-02-26 | 2025-02-27 | 2025-03-06 | 2025-03-07 | 1360 | 193 | Additional Support installed per Client request |  |  | 194 | SEP | SEP |  |  |  |  | 14.11.2024 00:00:00 | 2-302 | System CHW and LTHW FIRST FLOOR
67289 | EB_F02-LTHWR-220-DN015-I16C00_1_R0 | 0 | true | 8.15 | EB_F02-LTHWR-220-DN015-I16C00_1_R0 |  | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-25 | 2024-10-25 | 2024-11-05 | 2024-11-06 |  | 2024-11-13 | 2024-12-02 | Office 05/03/2025 | 2024-12-03 |  | 2024-12-03 | 2025-03-07 | 2025-03-07 | 2025-03-22 | 2025-03-22 | 1360 | 193 | Additional Support installed per Client request |  |  | 194 | SEP | SEP |  |  |  |  | 14.11.2024 00:00:00 | 2-302 | System CHW and LTHW FIRST FLOOR
67290 | EB_F02-LTHWS-211-DN015-I16C00_2_R0 | 0 | true | 4.04 | EB_F02-LTHWS-211-DN015-I16C00_2_R0 |  | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-25 | 2024-10-25 | 2024-11-05 | 2024-11-06 |  | 2024-11-18 | 2024-12-02 | Office 27/02/2025 | 2024-12-03 |  | 2024-12-03 | 2024-12-10 | 2024-12-17 | 2025-03-08 | 2025-03-08 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 14.11.2024 00:00:00 | 2-235 | System CHW and LTHW FIRST FLOOR
67291 | EB_F02-LTHWS-212-DN015-I16C00_2_R0 | 0 | true | 6.7 | EB_F02-LTHWS-212-DN015-I16C00_2_R0 |  | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-25 | 2024-10-25 | 2024-11-03 | 2024-11-04 |  | 2024-11-13 | 2024-12-02 | Office 27/02/2025 | 2024-12-03 |  | 2024-12-03 | 2024-12-12 | 2024-12-17 | 2025-03-11 | 2025-03-11 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 14.11.2024 00:00:00 | 2-235 | System CHW and LTHW FIRST FLOOR
67292 | EB_F02-LTHWS-213-DN015-I16C00_2_R0 | 0 | true | 9.37 | EB_F02-LTHWS-213-DN015-I16C00_2_R0 |  | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-25 | 2024-10-25 | 2024-11-04 | 2024-11-04 |  | 2024-11-13 | 2024-12-02 | Office 27/02/2025 | 2024-12-03 |  | 2024-12-03 | 2024-12-12 | 2024-12-17 | 2025-03-11 | 2025-03-11 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 14.11.2024 00:00:00 | 2-235 | System CHW and LTHW FIRST FLOOR
67293 | EB_F02-LTHWS-214-DN015-I16C00_2_R0 | 0 | true | 12 | EB_F02-LTHWS-214-DN015-I16C00_2_R0 |  | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-25 | 2024-10-25 | 2024-11-04 | 2024-11-04 |  | 2024-11-13 | 2024-12-02 | Office 27/02/2025 | 2024-12-03 |  | 2024-12-03 | 2024-12-12 | 2024-12-17 | 2025-03-19 | 2025-03-19 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 14.11.2024 00:00:00 | 2-235 | System CHW and LTHW FIRST FLOOR
67294 | EB_F02-LTHWS-215-DN015-I16C00_2_R0 | 0 | true | 3.98 | EB_F02-LTHWS-215-DN015-I16C00_2_R0 |  | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-25 | 2024-10-25 | 2024-11-04 | 2024-11-04 |  | 2024-11-13 | 2024-11-18 | Office 27/02/2025 | 2024-12-03 |  | 2024-11-23 | 2024-12-15 | 2024-12-17 | 2025-03-11 | 2025-03-22 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 14.11.2024 00:00:00 | 2-235 | System CHW and LTHW FIRST FLOOR
67295 | EB_F02-LTHWS-216-DN015-I16C00_2_R0 | 0 | false | 6.82 | EB_F02-LTHWS-216-DN015-I16C00_2_R0 | LPP6A-M-518-01-FSA | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-25 | 2024-10-25 | [13 empty] | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-235
67296 | EB_F02-LTHWS-217-DN015-I16C00_2_R0 | 0 | true | 9.42 | EB_F02-LTHWS-217-DN015-I16C00_2_R0 | LPP6A-M-518-01-FSA | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-25 | 2024-10-25 | 2024-11-04 | 2024-11-04 |  | 2024-11-13 | 2024-11-18 | Office 27/02/2025 | 2024-12-03 |  | 2024-11-23 | 2024-12-16 | 2024-12-16 | 2025-03-12 | 2025-03-22 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 14.11.2024 00:00:00 | 2-235 | System CHW and LTHW FIRST FLOOR
67297 | EB_F02-LTHWS-218-DN015-I16C00_2_R0 | 0 | true | 12.88 | EB_F02-LTHWS-218-DN015-I16C00_2_R0 |  | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-25 | 2024-10-25 | 2024-11-04 | 2024-11-04 |  | 2024-11-13 | 2024-12-02 | Office 27/02/2025 | 2024-12-03 |  | 2024-12-03 | 2024-12-17 | 2024-12-17 | 2025-03-22 | 2025-03-22 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 14.11.2024 00:00:00 | 2-235 | System CHW and LTHW FIRST FLOOR
67298 | EB_F02-LTHWS-219-DN015-I16C00_2_R0 | 0 | true | 12.37 | EB_F02-LTHWS-219-DN015-I16C00_2_R0 |  | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-25 | 2024-10-25 | 2024-11-04 | 2024-11-04 |  | 2024-11-13 | 2024-12-02 | Office 05/03/2025 | 2024-12-03 |  | 2024-12-03 | 2025-02-26 | 2025-02-27 | 2025-03-07 | 2025-03-07 | 1360 | 193 | Additional Support installed per Client request |  |  | 194 | SEP | SEP |  |  |  |  | 14.11.2024 00:00:00 | 2-235 | System CHW and LTHW FIRST FLOOR
67299 | EB_F02-LTHWS-220-DN015-I16C00_2_R0 | 0 | true | 7.76 | EB_F02-LTHWS-220-DN015-I16C00_2_R0 |  | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-25 | 2024-10-25 | 2024-11-06 | 2024-11-06 |  | 2024-11-13 | 2024-12-02 | Office 05/03/2025 | 2024-12-03 |  | 2024-12-03 | 2025-03-01 | 2025-03-03 | 2025-03-04 | 2025-03-22 | 1360 | 193 | Additional Support installed per Client request |  |  | 194 | SEP | SEP |  |  |  |  | 14.11.2024 00:00:00 | 2-235 | System CHW and LTHW FIRST FLOOR
67300 | PB_PCWR-001-DN600-I16C00_R0 | 0 | true | 328.26 | PB_PCWR-001-DN600-I16C00_R0 |  | 1129 | Tressels / PipeBridge | N/A | FoamOutside | TBH-ZAT-2024-10-25 | 2024-10-25 | 2024-11-01 | 2024-11-03 |  | 2024-11-06 | 2024-11-14 | Office 09.04.2025 | 2024-12-05 |  | 2024-11-14 | 2024-12-06 | 2025-02-26 | 2025-04-06 | 2025-04-06 | 1343 | 193 |  |  |  |  | SEP | SEP | [5 empty] | PipeRack | System PCW 01
67301 | PB_PCWR-002-DN600-I16C00_R0 | 0 | true | 235.32 | PB_PCWR-002-DN600-I16C00_R0 |  | 1129 | Tressels / PipeBridge | N/A | FoamOutside | TBH-ZAT-2024-10-25 | 2024-10-25 | 2024-11-01 | 2024-11-06 |  | 2024-11-06 |  | Office 20/05/2025 | 2025-02-17 |  | 2025-02-17 | 2025-02-17 | 2025-05-03 | 2025-05-22 | 2025-05-22 | 1343 | 193 |  |  |  |  | SEP | SEP | [5 empty] | PipeRack | System PCW 01
67302 | PB_PCWS-001-DN600-I16C00_R0 | 0 | true | 333.48 | PB_PCWS-001-DN600-I16C00_R0 |  | 1129 | Tressels / PipeBridge | N/A | FoamOutside | TBH-ZAT-2024-10-25 | 2024-10-25 | 2024-11-01 | 2024-11-06 |  | 2024-11-06 | 2024-11-14 | Office 09.04.2025 | 2024-12-05 |  | 2024-11-14 | 2024-12-06 | 2025-02-25 | 2025-04-05 | 2025-04-05 | 1343 | 193 |  |  |  |  | SEP | SEP | [5 empty] | PipeRack | System PCW 01
67303 | PB_PCWS-002-DN600-I16C00_R0 | 0 | true | 230.17 | PB_PCWS-002-DN600-I16C00_R0 |  | 1129 | Tressels / PipeBridge | N/A | FoamOutside | TBH-ZAT-2024-10-25 | 2024-10-25 | 2024-11-01 | 2024-11-06 |  | 2024-11-06 |  | Office 18.12.2024 | 2025-03-17 |  | 2025-02-17 | 2025-02-17 | 2025-05-03 | 2025-05-22 | 2025-05-22 | 1343 | 193 |  |  |  |  | SEP | SEP | [5 empty] | PipeRack | System PCW 01
67684 | CUB2_PCWR-018-DN065-I16C00_R0 | 0 | true | 5.48 | CUB2_PCWR-018-DN065-I16C00_R0 |  | 1129 | CUB2 | F01 | N/A | TBH-ZAT-2024-10-31_no prefab | 2024-10-31 | 2024-12-09 | 2025-05-19 |  | 2025-05-19 | 2025-05-19 | Office 12/06/2025 | 2025-05-26 |  | 2025-05-19 | 2025-05-19 | 2025-05-19 | 2025-05-26 | 2025-05-26 | 1361 | 193 |  |  |  |  | SEP | SEP | [5 empty] | CUB2 | PCWR CUB2
67685 | CUB2_PCWR-019-DN065-I16C00_R0 | 0 | true | 5.48 | CUB2_PCWR-019-DN065-I16C00_R0 |  | 1129 | CUB2 | F01 | N/A | TBH-ZAT-2024-10-31_no prefab | 2024-10-31 | 2024-12-09 | 2025-05-19 |  | 2025-05-19 | 2025-05-19 | Office 12/06/2025 | 2025-05-26 |  | 2025-05-19 | 2025-05-19 | 2025-05-19 | 2025-05-26 | 2025-05-26 | 1361 | 193 |  |  |  |  | SEP | SEP | [5 empty] | CUB2 | PCWR CUB2
67686 | CUB2_PCWR-020-DN065-I16C00_R0 | 0 | true | 3.99 | CUB2_PCWR-020-DN065-I16C00_R0 |  | 1129 | CUB2 | F01 | N/A | TBH-ZAT-2024-10-31_no prefab | 2024-10-31 | 2024-12-09 | [11 empty] | 2025-05-27 | 1361 | 193 | Line removed (one less Expansion Vessel) |  |  |  | SEP | SEP | [5 empty] | CUB2 | NO TESTING REQUIRED
67687 | CUB2_PCWR-021-DN065-I16C00_R0 | 0 | true | 3.99 | CUB2_PCWR-021-DN065-I16C00_R0 |  | 1129 | CUB2 | F01 | N/A | TBH-ZAT-2024-10-31_no prefab | 2024-10-31 | 2024-12-09 |  |  |  |  | Office 12/06/2025 |  |  |  | 2025-05-19 | 2025-05-19 | 2025-05-20 | 2025-05-20 | 1361 | 193 |  |  |  |  | SEP | SEP | [5 empty] | CUB2 | NO TESTING REQUIRED
67688 | CUB2_PCWR-022-DN065-I16C00_R0 | 0 | true | 3.99 | CUB2_PCWR-022-DN065-I16C00_R0 |  | 1129 | CUB2 | F01 | N/A | TBH-ZAT-2024-10-31_no prefab | 2024-10-31 | 2024-12-09 |  |  |  |  | Office 12/06/2025 |  |  |  | 2025-05-21 | 2025-05-21 | 2025-05-22 | 2025-05-22 | 1361 | 193 |  |  |  |  | SEP | SEP | [5 empty] | CUB2 | NO TESTING REQUIRED
67689 | CUB2_PCWR-023-DN065-I16C00_R0 | 0 | true | 3.99 | CUB2_PCWR-023-DN065-I16C00_R0 |  | 1129 | CUB2 | F01 | N/A | TBH-ZAT-2024-10-31_no prefab | 2024-10-31 | 2024-12-09 | [11 empty] | 2025-05-27 | 1361 | 193 | Line removed (one less Expansion Vessel) |  |  |  | SEP | SEP | [5 empty] | CUB2 | NO TESTING REQUIRED
67690 | CUB2_PCWR-024-DN065-I16C00_R0 | 0 | true | 3.99 | CUB2_PCWR-024-DN065-I16C00_R0 |  | 1129 | CUB2 | F01 | N/A | TBH-ZAT-2024-10-31_no prefab | 2024-10-31 | 2024-12-09 |  |  |  |  | Office 12/06/2025 |  |  |  | 2025-05-20 | 2025-05-20 | 2025-05-21 | 2025-05-21 | 1361 | 193 |  |  |  |  | SEP | SEP | [5 empty] | CUB2 | NO TESTING REQUIRED
67691 | CUB2_PCWR-025-DN065-I16C00_R0 | 0 | true | 3.99 | CUB2_PCWR-025-DN065-I16C00_R0 |  | 1129 | CUB2 | F01 | N/A | TBH-ZAT-2024-10-31_no prefab | 2024-10-31 | 2024-12-09 |  |  |  |  | Office 12/06/2025 |  |  |  | 2025-05-23 | 2025-05-23 | 2025-05-23 | 2025-05-23 | 1361 | 193 |  |  |  |  | SEP | SEP | [5 empty] | CUB2 | NO TESTING REQUIRED
67692 | CUB4_PCWR-003-DN450-I16C00_ADDED_R0 | 0 | true | 1.89 | CUB4_PCWR-003-DN450-I16C00_ADDED_R0 |  | 1129 | CUB4 | F01 | N/A | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-19 | 2024-11-20 |  | 2024-12-19 | 2025-01-06 | Office 09.04.2025 | 2025-01-15 |  | 2025-01-09 | 2025-01-27 | 2025-01-28 | 2025-01-29 | 2025-03-22 | 1361 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 18.11.2024 00:00:00 | CUB4 | System PCW 01
67693 | CUB4_PCWS-003-DN450-I16C00_ADDED_R0 | 0 | true | 1.89 | CUB4_PCWS-003-DN450-I16C00_ADDED_R0 |  | 1129 | CUB4 | F01 | N/A | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-19 | 2024-11-20 |  | 2024-12-19 | 2025-01-06 | Office 09.04.2025 | 2025-01-15 |  | 2025-01-09 | 2025-01-27 | 2025-01-28 | 2025-01-29 | 2025-03-22 | 1361 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 18.11.2024 00:00:00 | CUB4 | System PCW 01
67718 | DH_F01-PCWR-001-DN600-I16C00_R0 | 0 | true | 74.6 | DH_F01-PCWR-001-DN600-I16C00_R0 |  | 1129 | Datahall | F01 | N/A | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-19 | 2024-12-03 |  | 2025-01-02 | 2025-01-19 | Office 04.04.2025 | 2025-01-28 |  | 2025-01-23 | 2025-03-20 | 2025-03-20 | 2025-04-03 | 2025-05-13 | 1352 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2025-01-01 | 1-500 | System PCW 01
67719 | DH_F01-PCWR-002-DN600-I16C00_R0 | 0 | true | 74.49 | DH_F01-PCWR-002-DN600-I16C00_R0 |  | 1129 | Datahall | F01 | N/A | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-19 | 2024-12-03 |  | 2025-01-02 | 2025-02-04 | Nikola Colic 18.02.2025 | 2025-02-11 |  | 2025-02-11 | 2025-03-01 | 2025-03-05 | 2025-04-03 | 2025-04-07 | 1352 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2025-01-01 | 1-500 | System PCW 01
67720 | DH_F01-PCWR-003-DN150-I16C00_R0 | 0 | true | 93.26 | DH_F01-PCWR-003-DN150-I16C00_R0 |  | 1129 | Datahall | F01 | N/A | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-23 | 2024-12-03 |  | 2025-01-02 | 2025-01-15 | Office 11.04.2025 | 2025-01-29 |  | 2025-01-19 | 2025-02-07 | 2025-02-14 | 2025-04-03 | 2025-04-03 | 1352 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2025-04-01 | 1-500 | System PCW 01
67721 | DH_F01-PCWR-012-DN150-I16C00_R0 | 0 | true | 97.02 | DH_F01-PCWR-012-DN150-I16C00_R0 |  | 1129 | Datahall | F01 | N/A | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-23 | 2024-12-03 |  | 2025-01-02 | 2025-01-19 | Office 11.04.2025 | 2025-01-29 |  | 2025-01-23 | 2025-02-14 | 2025-02-17 | 2025-04-03 | 2025-04-04 | 1352 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2025-04-01 | 1-500 | System PCW 01
67722 | DH_F01-PCWR-023-DN150-I16C00_R0 | 0 | true | 97.02 | DH_F01-PCWR-023-DN150-I16C00_R0 |  | 1129 | Datahall | F01 | N/A | TBH-ZAT-2024-10-31 | 2024-11-01 | 2024-11-24 | 2024-12-03 |  | 2025-01-02 | 2025-01-22 | Office 11.04.2025 | 2025-01-29 |  | 2025-01-23 | 2025-02-07 | 2025-02-13 | 2025-04-03 | 2025-04-03 | 1352 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2025-03-01 | 1-500 | System PCW 01
67723 | DH_F01-PCWR-024-DN150-I16C00_R0 | 0 | true | 96.94 | DH_F01-PCWR-024-DN150-I16C00_R0 |  | 1129 | Datahall | F01 | N/A | TBH-ZAT-2024-10-31 | 2024-11-02 | 2024-11-24 | 2024-12-03 |  | 2025-01-12 | 2025-02-20 | Office 11.04.2025 | 2025-02-26 |  | 2025-02-20 | 2025-03-10 | 2025-03-12 | 2025-04-03 | 2025-04-07 | 1352 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2025-03-01 | 1-500 | System PCW 01
67724 | DH_F01-PCWR-025-DN150-I16C00_R0 | 0 | true | 97.01 | DH_F01-PCWR-025-DN150-I16C00_R0 |  | 1129 | Datahall | F01 | N/A | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-26 | 2024-12-03 |  | 2025-01-12 | 2025-02-07 | Office 11.04.2025 | 2025-02-12 |  | 2025-02-14 | 2025-02-26 | 2025-03-27 | 2025-03-28 | 2025-04-08 | 1352 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2025-02-01 | 1-500 | System PCW 01
67725 | DH_F01-PCWR-026-DN150-I16C00_R0 | 0 | true | 97.01 | DH_F01-PCWR-026-DN150-I16C00_R0 |  | 1129 | Datahall | F01 | N/A | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-26 | 2024-12-03 |  | 2025-01-12 | 2025-02-10 | Office 11.04.2025 | 2025-02-12 |  | 2025-02-12 | 2025-02-25 | 2025-02-26 | 2025-02-26 | 2025-04-09 | 1352 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2025-02-01 | 1-500 | System PCW 01
67726 | DH_F01-PCWR-027-DN150-I16C00_R0 | 0 | true | 97.02 | DH_F01-PCWR-027-DN150-I16C00_R0 |  | 1129 | Datahall | F01 | N/A | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-25 | 2024-12-03 |  | 2025-01-13 | 2025-01-30 | Office 11.04.2025 | 2025-02-05 |  | 2025-01-31 | 2025-02-24 | 2025-02-25 | 2025-02-26 | 2025-04-10 | 1352 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2025-02-01 | 1-500 | System PCW 01
67727 | DH_F01-PCWR-028-DN150-I16C00_R0 | 0 | true | 97.02 | DH_F01-PCWR-028-DN150-I16C00_R0 |  | 1129 | Datahall | F01 | N/A | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-25 | 2024-12-03 |  | 2025-01-13 | 2025-01-30 | Office 11.04.2025 | 2025-02-05 |  | 2025-01-31 | 2025-02-10 | 2025-02-20 | 2025-02-25 | 2025-04-10 | 1352 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2025-01-01 | 1-500 | System PCW 01
67728 | DH_F01-PCWR-029-DN150-I16C00_R0 | 0 | true | 90.45 | DH_F01-PCWR-029-DN150-I16C00_R0 |  | 1129 | Datahall | F01 | N/A | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-26 | 2024-12-03 |  | 2025-01-13 | 2025-01-31 | Office 11.04.2025 | 2025-02-05 |  | 2025-01-31 | 2025-02-20 | 2025-02-20 | 2025-04-03 | 2025-04-10 | 1352 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2025-01-01 | 1-500 | System PCW 01
67729 | DH_F01-PCWS-001-DN600-I16C00_R0 | 0 | true | 74.57 | DH_F01-PCWS-001-DN600-I16C00_R0 |  | 1129 | Datahall | F01 | N/A | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-19 | 2024-12-03 |  | 2024-12-19 | 2025-01-19 | Office 04.04.2025 | 2025-01-28 |  | 2025-01-23 | 2025-03-17 | 2025-03-20 | 2025-04-03 | 2025-05-13 | 1352 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2025-01-01 | 1-500 | System PCW 01
67730 | DH_F01-PCWS-002-DN600-I16C00_R0 | 0 | true | 74.49 | DH_F01-PCWS-002-DN600-I16C00_R0 |  | 1129 | Datahall | F01 | N/A | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-20 | 2024-12-03 |  | 2025-01-02 | 2025-01-30 | Nikola Colic 18.02.2025 | 2025-02-11 |  | 2025-01-31 | 2025-02-24 | 2025-03-03 | 2025-04-03 | 2025-04-04 | 1352 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2025-01-01 | 1-500 | System PCW 01
67731 | DH_F01-PCWS-003-DN150-I16C00_R0 | 0 | true | 90.53 | DH_F01-PCWS-003-DN150-I16C00_R0 |  | 1129 | Datahall | F01 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-17 | 2024-12-03 |  | 2025-01-06 | 2025-01-22 | Office 11.04.2025 | 2025-01-29 |  | 2025-01-23 | 2025-02-12 | 2025-02-14 | 2025-04-03 | 2025-04-03 | 1352 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2025-04-01 | 1-500 | System PCW 01
67732 | DH_F01-PCWS-007-DN150-I16C00_R0 | 0 | true | 97.04 | DH_F01-PCWS-007-DN150-I16C00_R0 |  | 1129 | Datahall | F01 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-17 | 2024-12-03 |  | 2025-01-06 | 2025-01-22 | Office 11.04.2025 | 2025-01-29 |  | 2025-01-23 | 2025-02-15 | 2025-02-18 | 2025-04-03 | 2025-04-03 | 1352 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2025-04-01 | 1-500 | System PCW 01
67733 | DH_F01-PCWS-009-DN150-I16C00_R0 | 0 | true | 97.04 | DH_F01-PCWS-009-DN150-I16C00_R0 |  | 1129 | Datahall | F01 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-20 | 2024-12-03 |  | 2025-01-06 | 2025-01-26 | Office 11.04.2025 | 2025-01-29 |  | 2025-01-27 | 2025-02-07 | 2025-02-12 | 2025-04-03 | 2025-04-07 | 1352 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2025-03-01 | 1-500 | System PCW 01
67734 | DH_F01-PCWS-018-DN150-I16C00_R0 | 0 | true | 97.27 | DH_F01-PCWS-018-DN150-I16C00_R0 |  | 1129 | Datahall | F01 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-17 | 2024-12-03 |  | 2025-02-03 | 2025-02-20 | Office 11.04.2025 | 2025-02-26 |  | 2025-02-20 | 2025-03-10 | 2025-03-12 | 2025-03-18 | 2025-04-04 | 1352 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2025-03-01 | 1-500 | System PCW 01
67735 | DH_F01-PCWS-019-DN150-I16C00_R0 | 0 | true | 96.97 | DH_F01-PCWS-019-DN150-I16C00_R0 |  | 1129 | Datahall | F01 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-17 | 2024-12-03 |  | 2025-02-03 | 2025-02-25 | Office 11.04.2025 | 2025-02-26 |  | 2025-02-27 | 2025-03-07 | 2025-03-11 | 2025-04-03 | 2025-04-05 | 1352 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2025-02-01 | 1-500 | System PCW 01
67736 | DH_F01-PCWS-021-DN150-I16C00_R0 | 0 | true | 97.04 | DH_F01-PCWS-021-DN150-I16C00_R0 |  | 1129 | Datahall | F01 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-23 | 2024-12-03 |  | 2025-02-03 | 2025-02-25 | Office 11.04.2025 | 2025-02-26 |  | 2025-02-27 | 2025-03-06 | 2025-03-07 | 2025-03-31 | 2025-04-08 | 1352 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2025-02-01 | 1-500 | System PCW 01
67737 | DH_F01-PCWS-022-DN150-I16C00_R0 | 0 | true | 97.04 | DH_F01-PCWS-022-DN150-I16C00_R0 |  | 1129 | Datahall | F01 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-24 | 2024-12-03 |  | 2025-01-16 | 2025-01-31 | Office 11.04.2025 | 2025-02-05 |  | 2025-01-31 | 2025-02-12 | 2025-03-20 | 2025-02-25 | 2025-04-09 | 1352 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2025-02-01 | 1-500 | System PCW 01
67738 | DH_F01-PCWS-023-DN150-I16C00_R0 | 0 | true | 97.07 | DH_F01-PCWS-023-DN150-I16C00_R0 |  | 1129 | Datahall | F01 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-24 | 2024-12-03 |  | 2025-01-16 | 2025-02-03 | Office 11.04.2025 | 2025-02-05 |  | 2025-02-06 | 2025-02-20 | 2025-02-21 | 2025-04-03 | 2025-04-10 | 1352 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2025-01-01 | 1-500 | System PCW 01
67739 | DH_F01-PCWS-024-DN150-I16C00_R0 | 0 | true | 93.28 | DH_F01-PCWS-024-DN150-I16C00_R0 |  | 1129 | Datahall | F01 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-24 | 2024-12-03 |  | 2025-01-16 | 2025-02-04 | Office 11.04.2025 | 2025-02-05 |  | 2025-02-06 | 2025-02-17 | 2025-02-19 | 2025-04-03 | 2025-04-10 | 1352 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2025-01-01 | 1-500 | System PCW 01
67740 | EB_F01-CHWR-130-DN025-I16C00_1_R0 | 0 | true | 8.15 | EB_F01-CHWR-130-DN025-I16C00_1_R0 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-19 | 2024-11-16 |  | 2024-11-30 | 2024-12-06 | Office 07.04.2025 | 2024-12-11 |  | 2024-12-08 | 2025-03-27 | 2025-03-27 | 2025-03-27 | 2025-03-27 | 1359 | 193 | Additional Support installed per Client request |  |  | 194 | SEP | SEP |  |  |  |  | 26.11.2024 00:00:00 | 1-302 | System CHW and LTHW GROUND FLOOR
67741 | EB_F01-CHWR-131-DN025-I16C00_1_R0 | 0 | true | 12.5 | EB_F01-CHWR-131-DN025-I16C00_1_R0 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-19 | 2024-11-16 |  | 2024-11-30 | 2024-12-06 | Office 07.04.2025 | 2024-12-11 |  | 2024-12-08 | 2025-03-28 | 2025-03-28 | 2025-03-28 | 2025-03-28 | 1359 | 193 | Additional Support installed per Client request |  |  | 194 | SEP | SEP |  |  |  |  | 26.11.2024 00:00:00 | 1-302 | System CHW and LTHW GROUND FLOOR
67742 | EB_F01-CHWR-132-DN020-I16C00_1_R0 | 0 | true | 13.1 | EB_F01-CHWR-132-DN020-I16C00_1_R0 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-10 | 2024-11-16 |  | 2024-11-30 | 2024-12-09 | Office 12.03.2025 | 2024-12-11 |  | 2024-12-10 | 2025-03-07 | 2025-03-07 | 2025-03-19 | 2025-03-20 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 26.11.2024 00:00:00 | 1-303 | System CHW and LTHW GROUND FLOOR
67743 | EB_F01-CHWR-133-DN020-I16C00_1_R0 | 0 | true | 11.56 | EB_F01-CHWR-133-DN020-I16C00_1_R0 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-11 | 2024-11-16 |  | 2024-11-30 | 2024-12-06 | Office 12.03.2025 | 2024-12-11 |  | 2024-12-08 | 2025-03-10 | 2025-03-11 | 2025-03-22 | 2025-03-22 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 26.11.2024 00:00:00 | 1-303 | System CHW and LTHW GROUND FLOOR
67744 | EB_F01-CHWR-134-DN020-I16C00_1_R0 | 0 | true | 8.8 | EB_F01-CHWR-134-DN020-I16C00_1_R0 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-11 | 2024-11-16 |  | 2024-11-30 | 2024-12-06 | Office 12.03.2025 | 2024-12-11 |  | 2024-12-08 | 2025-03-10 | 2025-03-12 | 2025-03-19 | 2025-03-19 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 26.11.2024 00:00:00 | 1-303 | System CHW and LTHW GROUND FLOOR
67745 | EB_F01-CHWR-135-DN020-I16C00_1_R0 | 0 | true | 6.21 | EB_F01-CHWR-135-DN020-I16C00_1_R0 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-11 | 2024-11-16 |  | 2024-11-30 | 2024-12-06 | Office 12.03.2025 | 2024-12-11 |  | 2024-12-08 | 2025-03-12 | 2025-03-12 | 2025-03-20 | 2025-03-21 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 26.11.2024 00:00:00 | 1-303 | System CHW and LTHW GROUND FLOOR
67746 | EB_F01-CHWR-137-DN020-I16C00_1_R0 | 0 | true | 14.2 | EB_F01-CHWR-137-DN020-I16C00_1_R0 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-12 | 2024-11-16 |  | 2024-11-30 | 2024-12-06 | Office 22.03.2025 | 2024-12-11 |  | 2024-12-08 | 2025-03-17 | 2025-03-17 | 2025-03-21 | 2025-03-21 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 26.11.2024 00:00:00 | 1-304 | System CHW and LTHW GROUND FLOOR
67747 | EB_F01-CHWR-138-DN020-I16C00_1_R0 | 0 | true | 11.6 | EB_F01-CHWR-138-DN020-I16C00_1_R0 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-12 | 2024-11-16 |  | 2024-11-30 | 2024-12-06 | Office 22.03.2025 | 2024-12-11 |  | 2024-12-08 | 2025-03-20 | 2025-03-20 | 2025-03-20 | 2025-03-20 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 26.11.2024 00:00:00 | 1-304 | System CHW and LTHW GROUND FLOOR
67748 | EB_F01-CHWR-139-DN020-I16C00_1_R0 | 0 | true | 8.83 | EB_F01-CHWR-139-DN020-I16C00_1_R0 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-12 | 2024-11-16 |  | 2024-11-30 | 2024-12-06 | Office 22.03.2025 | 2024-12-11 |  | 2024-12-08 | 2025-03-14 | 2025-03-14 | 2025-03-20 | 2025-03-20 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 26.11.2024 00:00:00 | 1-304 | System CHW and LTHW GROUND FLOOR
67749 | EB_F01-CHWR-140-DN020-I16C00_1_R0 | 0 | true | 6.24 | EB_F01-CHWR-140-DN020-I16C00_1_R0 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-12 | 2024-11-16 |  | 2024-11-30 | 2024-12-06 | Office 22.03.2025 | 2024-12-11 |  | 2024-12-08 | 2025-03-18 | 2025-03-18 | 2025-03-19 | 2025-03-19 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 26.11.2024 00:00:00 | 1-304 | System CHW and LTHW GROUND FLOOR
67750 | EB_F01-CHWS-130-DN025-I16C00_2_R0 | 0 | true | 8.38 | EB_F01-CHWS-130-DN025-I16C00_2_R0 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-19 | 2024-11-16 |  | 2024-11-30 | 2024-12-10 | Office 07.04.2025 | 2024-12-11 |  | 2024-12-11 | 2025-03-27 | 2025-03-27 | 2025-03-27 | 2025-03-27 | 1359 | 193 | Additional Support installed per Client request |  |  | 194 | SEP | SEP |  |  |  |  | 26.11.2024 00:00:00 | 1-306 | System CHW and LTHW GROUND FLOOR
67751 | EB_F01-CHWS-131-DN025-I16C00_2_R0 | 0 | true | 12.59 | EB_F01-CHWS-131-DN025-I16C00_2_R0 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-19 | 2024-11-16 |  | 2024-11-30 | 2024-12-11 | Office 07.04.2025 | 2024-12-11 |  | 2024-12-11 | 2025-03-28 | 2025-03-28 | 2025-03-28 | 2025-03-28 | 1359 | 193 | Additional Support installed per Client request |  |  | 194 | SEP | SEP |  |  |  |  | 26.11.2024 00:00:00 | 1-306 | System CHW and LTHW GROUND FLOOR
67752 | EB_F01-CHWS-132-DN020-I16C00_2_R0 | 0 | true | 12.22 | EB_F01-CHWS-132-DN020-I16C00_2_R0 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-10 | 2024-11-16 |  | 2024-11-30 | 2024-12-06 | Office 12.03.2025 | 2024-12-11 |  | 2024-12-08 | 2025-03-05 | 2025-03-06 | 2025-03-20 | 2025-03-19 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 26.11.2024 00:00:00 | 1-306 | System CHW and LTHW GROUND FLOOR
67753 | EB_F01-CHWS-133-DN020-I16C00_2_R0 | 0 | true | 10.32 | EB_F01-CHWS-133-DN020-I16C00_2_R0 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-11 | 2024-11-16 |  | 2024-11-30 | 2024-12-08 | Office 12.03.2025 | 2024-12-11 |  | 2024-12-09 | 2025-03-06 | 2025-03-06 | 2025-03-22 | 2025-03-22 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 26.11.2024 00:00:00 | 1-306 | System CHW and LTHW GROUND FLOOR
67754 | EB_F01-CHWS-134-DN020-I16C00_2_R0 | 0 | true | 7.56 | EB_F01-CHWS-134-DN020-I16C00_2_R0 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-11 | 2024-11-16 |  | 2024-11-30 | 2024-12-06 | Office 12.03.2025 | 2024-12-11 |  | 2024-12-08 | 2025-03-05 | 2025-03-06 | 2025-03-19 | 2025-03-19 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 26.11.2024 00:00:00 | 1-306 | System CHW and LTHW GROUND FLOOR
67755 | EB_F01-CHWS-135-DN020-I16C00_2_R0 | 0 | true | 4.98 | EB_F01-CHWS-135-DN020-I16C00_2_R0 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-11 | 2024-11-16 |  | 2024-11-30 | 2024-12-06 | Office 12.03.2025 | 2024-12-11 |  | 2024-12-08 | 2025-03-06 | 2025-03-06 | 2025-03-20 | 2025-03-21 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 26.11.2024 00:00:00 | 1-306 | System CHW and LTHW GROUND FLOOR
67756 | EB_F01-CHWS-137-DN020-I16C00_2_R0 | 0 | true | 12.96 | EB_F01-CHWS-137-DN020-I16C00_2_R0 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-12 | 2024-11-16 |  | 2024-11-30 | 2024-12-08 | Office 22.03.2025 | 2024-12-11 |  | 2024-12-09 | 2025-03-13 | 2025-03-13 | 2025-03-21 | 2025-03-21 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 26.11.2024 00:00:00 | 1-306 | System CHW and LTHW GROUND FLOOR
67757 | EB_F01-CHWS-138-DN020-I16C00_2_R0 | 0 | true | 10.35 | EB_F01-CHWS-138-DN020-I16C00_2_R0 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-12 | 2024-11-16 |  | 2024-11-30 | 2024-12-06 | Office 22.03.2025 | 2024-12-11 |  | 2024-12-08 | 2025-03-13 | 2025-03-13 | 2025-03-20 | 2025-03-20 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 26.11.2024 00:00:00 | 1-306 | System CHW and LTHW GROUND FLOOR
67758 | EB_F01-CHWS-139-DN020-I16C00_2_R0 | 0 | true | 7.6 | EB_F01-CHWS-139-DN020-I16C00_2_R0 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-12 | 2024-11-16 |  | 2024-11-30 | 2024-12-06 | Office 22.03.2025 | 2024-12-11 |  | 2024-12-08 | 2025-03-13 | 2025-03-13 | 2025-03-20 | 2025-03-20 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 26.11.2024 00:00:00 | 1-306 | System CHW and LTHW GROUND FLOOR
67759 | EB_F01-CHWS-140-DN020-I16C00_2_R0 | 0 | true | 5.02 | EB_F01-CHWS-140-DN020-I16C00_2_R0 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-12 | 2024-11-16 |  | 2024-11-30 | 2024-12-06 | Office 22.03.2025 | 2024-12-11 |  | 2024-12-08 | 2025-03-13 | 2025-03-13 | 2025-03-19 | 2025-03-19 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 26.11.2024 00:00:00 | 1-306 | System CHW and LTHW GROUND FLOOR
67760 | EB_F01-LTHWR-130-DN020-I16C00_1_R0 | 0 | true | 8.24 | EB_F01-LTHWR-130-DN020-I16C00_1_R0 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-19 | 2024-11-16 |  | 2024-12-03 | 2024-12-06 | Office 07.04.2025 | 2024-12-11 |  | 2024-12-08 | 2025-03-27 | 2025-03-27 | 2025-03-27 | 2025-03-27 | 1360 | 193 | Additional Support installed per Client request |  |  | 194 | SEP | SEP |  |  |  |  | 26.11.2024 00:00:00 | 1-302 | System CHW and LTHW GROUND FLOOR
67761 | EB_F01-LTHWR-131-DN020-I16C00_1_R0 | 0 | true | 12.61 | EB_F01-LTHWR-131-DN020-I16C00_1_R0 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-19 | 2024-11-16 |  | 2024-12-03 | 2024-12-08 | Office 07.04.2025 | 2024-12-11 |  | 2024-12-09 | 2025-03-28 | 2025-03-28 | 2025-03-28 | 2025-03-28 | 1360 | 193 | Additional Support installed per Client request |  |  | 194 | SEP | SEP |  |  |  |  | 26.11.2024 00:00:00 | 1-302 | System CHW and LTHW GROUND FLOOR
67762 | EB_F01-LTHWR-132-DN020-I16C00_1_R0 | 0 | true | 13.64 | EB_F01-LTHWR-132-DN020-I16C00_1_R0 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-10 | 2024-11-16 |  | 2024-12-03 | 2024-12-08 | Office 12.03.2025 | 2024-12-11 |  | 2024-12-09 | 2025-03-10 | 2025-03-10 | 2025-03-22 | 2025-03-22 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 26.11.2024 00:00:00 | 1-303 | System CHW and LTHW GROUND FLOOR
67763 | EB_F01-LTHWR-133-DN020-I16C00_1_R0 | 0 | true | 10.65 | EB_F01-LTHWR-133-DN020-I16C00_1_R0 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-11 | 2024-11-16 |  | 2024-12-03 | 2024-12-06 | Office 12.03.2025 | 2024-12-11 |  | 2024-12-08 | 2025-03-10 | 2025-03-10 | 2025-03-22 | 2025-03-22 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 26.11.2024 00:00:00 | 1-303 | System CHW and LTHW GROUND FLOOR
67764 | EB_F01-LTHWR-134-DN020-I16C00_1_R0 | 0 | true | 7.89 | EB_F01-LTHWR-134-DN020-I16C00_1_R0 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-11 | 2024-11-16 |  | 2024-12-03 | 2024-12-10 | Office 12.03.2025 | 2024-12-11 |  | 2024-12-11 | 2025-03-10 | 2025-03-10 | 2025-03-17 | 2025-03-17 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 26.11.2024 00:00:00 | 1-303 | System CHW and LTHW GROUND FLOOR
67765 | EB_F01-LTHWR-135-DN020-I16C00_1_R0 | 0 | true | 5.31 | EB_F01-LTHWR-135-DN020-I16C00_1_R0 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-11 | 2024-11-16 |  | 2024-12-03 | 2024-12-08 | Office 12.03.2025 | 2024-12-11 |  | 2024-12-09 | 2025-03-10 | 2025-03-10 | 2025-03-20 | 2025-03-21 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 26.11.2024 00:00:00 | 1-303 | System CHW and LTHW GROUND FLOOR
67766 | EB_F01-LTHWR-137-DN020-I16C00_1_R0 | 0 | true | 13.32 | EB_F01-LTHWR-137-DN020-I16C00_1_R0 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-12 | 2024-11-16 |  | 2024-12-03 | 2024-12-08 | Office 22.03.2025 | 2024-12-11 |  | 2024-12-09 | 2025-03-15 | 2025-03-17 | 2025-03-21 | 2025-03-21 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 26.11.2024 00:00:00 | 1-304 | System CHW and LTHW GROUND FLOOR
67767 | EB_F01-LTHWR-138-DN020-I16C00_1_R0 | 0 | true | 10.71 | EB_F01-LTHWR-138-DN020-I16C00_1_R0 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-12 | 2024-11-16 |  | 2024-12-03 | 2024-12-08 | Office 22.03.2025 | 2024-12-11 |  | 2024-12-09 | 2025-03-15 | 2025-03-15 | 2025-03-21 | 2025-03-21 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 26.11.2024 00:00:00 | 1-304 | System CHW and LTHW GROUND FLOOR
67768 | EB_F01-LTHWR-139-DN020-I16C00_1_R0 | 0 | true | 7.95 | EB_F01-LTHWR-139-DN020-I16C00_1_R0 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-12 | 2024-11-16 |  | 2024-12-03 | 2024-12-10 | Office 22.03.2025 | 2024-12-11 |  | 2024-12-11 | 2025-03-17 | 2025-03-17 | 2025-03-20 | 2025-03-20 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 26.11.2024 00:00:00 | 1-304 | System CHW and LTHW GROUND FLOOR
67769 | EB_F01-LTHWR-140-DN020-I16C00_1_R0 | 0 | true | 5.36 | EB_F01-LTHWR-140-DN020-I16C00_1_R0 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-12 | 2024-11-16 |  | 2024-12-03 | 2024-12-08 | Office 22.03.2025 | 2024-12-11 |  | 2024-12-09 | 2025-03-15 | 2025-03-17 | 2025-03-20 | 2025-03-20 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 26.11.2024 00:00:00 | 1-304 | System CHW and LTHW GROUND FLOOR
67770 | EB_F01-LTHWS-130-DN020-I16C00_2_R0 | 0 | true | 8.02 | EB_F01-LTHWS-130-DN020-I16C00_2_R0 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-19 | 2024-11-16 |  | 2024-12-03 | 2024-12-08 | Office 07.04.2025 | 2024-12-11 |  | 2024-12-09 | 2025-03-27 | 2025-03-27 | 2025-03-27 | 2025-03-27 | 1360 | 193 | Additional Support installed per Client request |  |  | 194 | SEP | SEP |  |  |  |  | 26.11.2024 00:00:00 | 1-306 | System CHW and LTHW GROUND FLOOR
67771 | EB_F01-LTHWS-131-DN020-I16C00_2_R0 | 0 | true | 12.41 | EB_F01-LTHWS-131-DN020-I16C00_2_R0 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-19 | 2024-11-16 |  | 2024-12-03 | 2024-12-09 | Office 07.04.2025 | 2024-12-11 |  | 2024-12-10 | 2025-03-28 | 2025-03-28 | 2025-03-28 | 2025-03-28 | 1360 | 193 | Additional Support installed per Client request |  |  | 194 | SEP | SEP |  |  |  |  | 26.11.2024 00:00:00 | 1-306 | System CHW and LTHW GROUND FLOOR
67772 | EB_F01-LTHWS-132-DN020-I16C00_2_R0 | 0 | true | 14.29 | EB_F01-LTHWS-132-DN020-I16C00_2_R0 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-10 | 2024-11-16 |  | 2024-12-03 | 2024-12-09 | Office 12.03.2025 | 2024-12-11 |  | 2024-12-10 | 2025-03-11 | 2025-03-11 | 2025-03-22 | 2025-03-22 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 26.11.2024 00:00:00 | 1-306 | System CHW and LTHW GROUND FLOOR
67773 | EB_F01-LTHWS-133-DN020-I16C00_2_R0 | 0 | true | 10.34 | EB_F01-LTHWS-133-DN020-I16C00_2_R0 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-11 | 2024-11-16 |  | 2024-12-03 | 2024-12-08 | Office 12.03.2025 | 2024-12-11 |  | 2024-12-09 | 2025-03-07 | 2025-03-07 | 2025-03-22 | 2025-03-22 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 26.11.2024 00:00:00 | 1-306 | System CHW and LTHW GROUND FLOOR
67774 | EB_F01-LTHWS-134-DN020-I16C00_2_R0 | 0 | true | 7.58 | EB_F01-LTHWS-134-DN020-I16C00_2_R0 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-11 | 2024-11-16 |  | 2024-12-03 | 2024-12-08 | Office 12.03.2025 | 2024-12-11 |  | 2024-12-09 | 2025-03-07 | 2025-03-07 | 2025-03-19 | 2025-03-19 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 26.11.2024 00:00:00 | 1-306 | System CHW and LTHW GROUND FLOOR
67775 | EB_F01-LTHWS-135-DN020-I16C00_2_R0 | 0 | true | 5 | EB_F01-LTHWS-135-DN020-I16C00_2_R0 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-11 | 2024-11-16 |  | 2024-12-03 | 2024-12-08 | Office 12.03.2025 | 2024-12-11 |  | 2024-12-09 | 2025-03-07 | 2025-03-07 | 2025-03-20 | 2025-03-21 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 26.11.2024 00:00:00 | 1-306 | System CHW and LTHW GROUND FLOOR
67776 | EB_F01-LTHWS-137-DN020-I16C00_2_R0 | 0 | true | 12.95 | EB_F01-LTHWS-137-DN020-I16C00_2_R0 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-12 | 2024-11-16 |  | 2024-12-03 | 2024-12-09 | Office 22.03.2025 | 2024-12-11 |  | 2024-12-10 | 2025-03-12 | 2025-03-14 | 2025-03-21 | 2025-03-21 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 26.11.2024 00:00:00 | 1-306 | System CHW and LTHW GROUND FLOOR
67777 | EB_F01-LTHWS-138-DN020-I16C00_2_R0 | 0 | true | 10.34 | EB_F01-LTHWS-138-DN020-I16C00_2_R0 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-12 | 2024-11-16 |  | 2024-12-03 | 2024-12-09 | Office 22.03.2025 | 2024-12-11 |  | 2024-12-10 | 2025-03-12 | 2025-03-12 | 2025-03-21 | 2025-03-21 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 26.11.2024 00:00:00 | 1-306 | System CHW and LTHW GROUND FLOOR
67778 | EB_F01-LTHWS-139-DN020-I16C00_2_R0 | 0 | true | 7.58 | EB_F01-LTHWS-139-DN020-I16C00_2_R0 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-12 | 2024-11-16 |  | 2024-12-03 | 2024-12-08 | Office 22.03.2025 | 2024-12-11 |  | 2024-12-09 | 2025-03-12 | 2025-03-14 | 2025-03-19 | 2025-03-19 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 26.11.2024 00:00:00 | 1-306 | System CHW and LTHW GROUND FLOOR
67779 | EB_F01-LTHWS-140-DN020-I16C00_2_R0 | 0 | true | 4.99 | EB_F01-LTHWS-140-DN020-I16C00_2_R0 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-12 | 2024-11-16 |  | 2024-12-03 | 2024-12-08 | Office 22.03.2025 | 2024-12-11 |  | 2024-12-09 | 2025-03-15 | 2025-03-15 | 2025-03-19 | 2025-03-19 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 26.11.2024 00:00:00 | 1-306 | System CHW and LTHW GROUND FLOOR
67780 | EB_F02-CHWR-012-DN150-I16C00_R0 | 0 | false | 40.35 | EB_F02-CHWR-012-DN150-I16C00_R0 | LPP6A-M-513-01-FSA | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | [13 empty] | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-235
67781 | EB_F02-CHWR-210-DN015-I16C00_R0 | 0 | true | 2.84 | EB_F02-CHWR-210-DN015-I16C00_R0 | LPP6A-M-513-01-FSA | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-16 | 2024-11-16 |  | 2024-11-26 | 2024-12-10 | Office 12.04.2025 | 2024-12-11 |  | 2024-12-11 | 2025-04-09 | 2025-04-09 | 2025-07-21 | 2025-07-21 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 27.11.2024 00:00:00 | 2-235 | System CHW and LTHW FIRST FLOOR
67782 | EB_F02-CHWR-211-DN020-I16C00_2_R0 | 0 | true | 6.7 | EB_F02-CHWR-211-DN020-I16C00_2_R0 |  | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-12 | 2024-11-16 |  | 2024-11-26 | 2024-12-03 | Office 27/02/2025 | 2024-12-11 |  | 2024-12-04 | 2025-02-22 | 2025-02-24 | 2025-02-24 | 2025-03-07 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 17.11.2024 00:00:00 | 2-235 | System CHW and LTHW FIRST FLOOR
67783 | EB_F02-CHWR-212-DN020-I16C00_2_R0 | 0 | true | 5.11 | EB_F02-CHWR-212-DN020-I16C00_2_R0 |  | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-12 | 2024-11-16 |  | 2024-11-26 | 2024-12-03 | Office 27/02/2025 | 2024-12-11 |  | 2024-12-04 | 2025-02-24 | 2025-02-24 | 2025-02-24 | 2025-03-19 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 17.11.2024 00:00:00 | 2-235 | System CHW and LTHW FIRST FLOOR
67784 | EB_F02-CHWR-213-DN020-I16C00_2_R0 | 0 | true | 4.14 | EB_F02-CHWR-213-DN020-I16C00_2_R0 |  | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-12 | 2024-11-16 |  | 2024-11-26 | 2024-12-03 | Office 27/02/2025 | 2024-12-11 |  | 2024-12-04 | 2025-02-24 | 2025-02-25 | 2025-02-26 | 2025-03-08 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 17.11.2024 00:00:00 | 2-235 | System CHW and LTHW FIRST FLOOR
67785 | EB_F02-CHWR-214-DN020-I16C00_2_R0 | 0 | true | 2.49 | EB_F02-CHWR-214-DN020-I16C00_2_R0 |  | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-12 | 2024-11-16 |  | 2024-11-26 | 2024-12-03 | Office 27/02/2025 | 2024-12-11 |  | 2024-12-04 | 2025-02-26 | 2025-02-26 | 2025-02-26 | 2025-03-10 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 17.11.2024 00:00:00 | 2-235 | System CHW and LTHW FIRST FLOOR
67786 | EB_F02-CHWR-215-DN020-I16C00_2_R0 | 0 | true | 9.1 | EB_F02-CHWR-215-DN020-I16C00_2_R0 |  | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-12 | 2024-11-16 |  | 2024-11-26 | 2024-12-03 | Office 27/02/2025 | 2024-12-11 |  | 2024-12-04 | 2025-02-25 | 2025-02-25 | 2025-02-26 | 2025-03-22 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 17.11.2024 00:00:00 | 2-235 | System CHW and LTHW FIRST FLOOR
67787 | EB_F02-CHWR-216-DN020-I16C00_2_R0 | 0 | true | 7.73 | EB_F02-CHWR-216-DN020-I16C00_2_R0 |  | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-12 | 2024-11-16 |  | 2024-11-26 | 2024-12-03 | Office 27/02/2025 | 2024-12-11 |  | 2024-12-04 | 2025-02-25 | 2025-02-25 | 2025-02-25 | 2025-03-22 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 17.11.2024 00:00:00 | 2-235 | System CHW and LTHW FIRST FLOOR
67788 | EB_F02-CHWR-217-DN020-I16C00_2_R0 | 0 | true | 6.54 | EB_F02-CHWR-217-DN020-I16C00_2_R0 |  | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-19 | 2024-11-16 |  | 2024-11-26 | 2024-12-03 | Office 27/02/2025 | 2024-12-11 |  | 2024-12-04 | 2025-02-25 | 2025-02-25 | 2025-02-25 | 2025-03-12 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 17.11.2024 00:00:00 | 2-235 | System CHW and LTHW FIRST FLOOR
67789 | EB_F02-CHWR-218-DN020-I16C00_2_R0 | 0 | true | 4.3 | EB_F02-CHWR-218-DN020-I16C00_2_R0 |  | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-12 | 2024-11-16 |  | 2024-11-26 | 2024-12-02 | Office 27/02/2025 | 2024-12-03 |  | 2024-12-03 | 2025-02-22 | 2025-02-22 | 2025-02-22 | 2025-03-22 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 17.11.2024 00:00:00 | 2-235 | System CHW and LTHW FIRST FLOOR
67790 | EB_F02-CHWR-219-DN025-I16C00_2_R0 | 0 | true | 4.31 | EB_F02-CHWR-219-DN025-I16C00_2_R0 |  | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-11 | 2024-11-16 |  | 2024-11-26 | 2024-12-02 | Office 05/03/2025 | 2024-12-03 |  | 2024-12-03 | 2025-02-13 | 2025-02-27 | 2025-02-28 | 2025-03-22 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 17.11.2024 00:00:00 | 2-235 | System CHW and LTHW FIRST FLOOR
67791 | EB_F02-CHWR-220-DN025-I16C00_2_R0 | 0 | true | 2.48 | EB_F02-CHWR-220-DN025-I16C00_2_R0 |  | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-11 | 2024-11-16 |  | 2024-12-03 | 2024-12-11 | Office 05/03/2025 | 2024-12-11 |  | 2024-12-11 | 2025-02-27 | 2025-02-27 | 2025-03-03 | 2025-03-08 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 26.11.2024 00:00:00 | 2-235 | System CHW and LTHW FIRST FLOOR
67792 | EB_F02-CHWS-012-DN150-I16C00_R0 | 0 | false | 42.23 | EB_F02-CHWS-012-DN150-I16C00_R0 | LPP6A-M-513-01-FSA | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | [13 empty] | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-235
67793 | EB_F02-CHWS-210-DN015-I16C00_R0 | 0 | true | 3.14 | EB_F02-CHWS-210-DN015-I16C00_R0 | LPP6A-M-513-01-FSA | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-16 | 2024-11-16 |  | 2024-11-26 | 2024-12-10 | Office 12.04.2025 | 2024-12-11 |  | 2024-12-11 | 2025-04-09 | 2025-04-09 | 2025-07-21 | 2025-07-21 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 27.11.2024 00:00:00 | 2-235 | System CHW and LTHW FIRST FLOOR
67794 | EB_F02-CHWS-211-DN020-I16C00_1_R0 | 0 | true | 5.28 | EB_F02-CHWS-211-DN020-I16C00_1_R0 |  | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-12 | 2024-11-16 |  | 2024-12-03 | 2024-12-09 | Office 27/02/2025 | 2024-12-11 |  | 2024-12-10 | 2025-02-15 | 2025-02-20 | 2025-02-21 | 2025-03-08 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 26.11.2024 00:00:00 | 2-304 | System CHW and LTHW FIRST FLOOR
67795 | EB_F02-CHWS-212-DN020-I16C00_1_R0 | 0 | true | 3.79 | EB_F02-CHWS-212-DN020-I16C00_1_R0 |  | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-12 | 2024-11-16 |  | 2024-11-26 | 2024-12-02 | Office 27/02/2025 | 2024-12-03 |  | 2024-12-03 | 2025-02-15 | 2025-02-25 | 2025-02-26 | 2025-03-11 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 17.11.2024 00:00:00 | 2-304 | System CHW and LTHW FIRST FLOOR
67796 | EB_F02-CHWS-213-DN020-I16C00_1_R0 | 0 | true | 2.72 | EB_F02-CHWS-213-DN020-I16C00_1_R0 |  | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-12 | 2024-11-16 |  | 2024-11-26 | 2024-12-02 | Office 27/02/2025 | 2024-12-03 |  | 2024-12-03 | 2025-02-15 | 2025-02-22 | 2025-02-22 | 2025-03-11 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 17.11.2024 00:00:00 | 2-304 | System CHW and LTHW FIRST FLOOR
67797 | EB_F02-CHWS-214-DN020-I16C00_1_R0 | 0 | true | 1.18 | EB_F02-CHWS-214-DN020-I16C00_1_R0 |  | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-19 | 2024-11-16 |  | 2024-11-26 | 2024-12-06 | Office 27/02/2025 | 2024-12-11 |  | 2024-12-08 | 2025-02-15 | 2025-02-20 | 2025-02-23 | 2025-03-19 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 17.11.2024 00:00:00 | 2-304 | System CHW and LTHW FIRST FLOOR
67798 | EB_F02-CHWS-215-DN020-I16C00_1_R0 | 0 | true | 7.86 | EB_F02-CHWS-215-DN020-I16C00_1_R0 |  | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-12 | 2024-11-16 |  | 2024-11-26 | 2024-12-03 | Office 27/02/2025 | 2024-12-11 |  | 2024-12-04 | 2025-02-14 | 2025-02-21 | 2025-02-21 | 2025-03-22 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 17.11.2024 00:00:00 | 2-303 | System CHW and LTHW FIRST FLOOR
67799 | EB_F02-CHWS-216-DN020-I16C00_1_R0 | 0 | true | 6.48 | EB_F02-CHWS-216-DN020-I16C00_1_R0 |  | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-12 | 2024-11-16 |  | 2024-11-26 | 2024-12-06 | Office 27/02/2025 | 2024-12-11 |  | 2024-12-08 | 2025-02-14 | 2025-02-21 | 2025-02-21 | 2025-03-22 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 17.11.2024 00:00:00 | 2-303 | System CHW and LTHW FIRST FLOOR
67800 | EB_F02-CHWS-217-DN020-I16C00_1_R0 | 0 | true | 5.19 | EB_F02-CHWS-217-DN020-I16C00_1_R0 |  | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-12 | 2024-11-16 |  | 2024-11-26 | 2024-12-03 | Office 27/02/2025 | 2024-12-11 |  | 2024-12-04 | 2025-02-13 | 2025-02-21 | 2025-02-22 | 2025-03-22 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 17.11.2024 00:00:00 | 2-303 | System CHW and LTHW FIRST FLOOR
67801 | EB_F02-CHWS-218-DN020-I16C00_1_R0 | 0 | true | 3.79 | EB_F02-CHWS-218-DN020-I16C00_1_R0 |  | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-12 | 2024-11-16 |  | 2024-11-26 | 2024-12-03 | Office 27/02/2025 | 2024-12-11 |  | 2024-12-04 | 2025-02-13 | 2025-02-13 | 2025-02-20 | 2025-03-22 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 17.11.2024 00:00:00 | 2-303 | System CHW and LTHW FIRST FLOOR
67802 | EB_F02-CHWS-219-DN025-I16C00_1_R0 | 0 | true | 4 | EB_F02-CHWS-219-DN025-I16C00_1_R0 |  | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-11 | 2024-11-16 |  | 2024-11-26 | 2024-12-03 | Office 05/03/2025 | 2024-12-11 |  | 2024-12-04 | 2025-02-26 | 2025-02-27 | 2025-02-28 | 2025-03-22 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 17.11.2024 00:00:00 | 2-302 | System CHW and LTHW FIRST FLOOR
67803 | EB_F02-CHWS-220-DN025-I16C00_1_R0 | 0 | true | 1.75 | EB_F02-CHWS-220-DN025-I16C00_1_R0 |  | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-11 | 2024-11-16 |  | 2024-11-26 | 2024-12-03 | Office 05/03/2025 | 2024-12-11 |  | 2024-12-04 | 2025-02-26 | 2025-02-26 | 2025-03-03 | 2025-03-22 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 17.11.2024 00:00:00 | 2-302 | System CHW and LTHW FIRST FLOOR
67804 | EB_F02-LTHWR-008-DN100-I16C00_R0 | 0 | false | 41.45 | EB_F02-LTHWR-008-DN100-I16C00_R0 | LPP6A-M-518-01-FSA | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | [13 empty] | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-235
67805 | EB_F02-LTHWR-210-DN020-I16C00_R0 | 0 | true | 2.7 | EB_F02-LTHWR-210-DN020-I16C00_R0 | LPP6A-M-518-01-FSA | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-16 | 2024-11-16 |  | 2024-12-03 | 2024-12-10 | Office 12.04.2025 | 2024-12-11 |  | 2024-12-11 | 2025-04-07 | 2025-04-10 | 2025-07-21 | 2025-07-21 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 27.11.2024 00:00:00 | 2-235 | System CHW and LTHW FIRST FLOOR
67806 | EB_F02-LTHWR-211-DN015-I16C00_2_R0 | 0 | true | 6.45 | EB_F02-LTHWR-211-DN015-I16C00_2_R0 |  | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-12 | 2024-11-16 |  | 2024-11-26 | 2024-12-03 | Office 27/02/2025 | 2024-12-11 |  | 2024-12-04 | 2025-02-24 | 2025-02-25 | 2025-02-25 | 2025-03-22 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 17.11.2024 00:00:00 | 2-235 | System CHW and LTHW FIRST FLOOR
67807 | EB_F02-LTHWR-212-DN015-I16C00_2_R0 | 0 | true | 4.96 | EB_F02-LTHWR-212-DN015-I16C00_2_R0 |  | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-12 | 2024-11-16 |  | 2024-11-26 | 2024-12-03 | Office 27/02/2025 | 2024-12-11 |  | 2024-12-04 | 2025-02-26 | 2025-02-26 | 2025-02-26 | 2025-03-19 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 17.11.2024 00:00:00 | 2-235 | System CHW and LTHW FIRST FLOOR
67808 | EB_F02-LTHWR-213-DN015-I16C00_2_R0 | 0 | true | 3.6 | EB_F02-LTHWR-213-DN015-I16C00_2_R0 |  | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-12 | 2024-11-16 |  | 2024-11-26 | 2024-12-03 | Office 27/02/2025 | 2024-12-11 |  | 2024-12-04 | 2025-02-24 | 2025-02-25 | 2025-02-25 | 2025-03-08 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 17.11.2024 00:00:00 | 2-235 | System CHW and LTHW FIRST FLOOR
67809 | EB_F02-LTHWR-214-DN015-I16C00_2_R0 | 0 | true | 2.35 | EB_F02-LTHWR-214-DN015-I16C00_2_R0 |  | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-12 | 2024-11-16 |  | 2024-11-26 | 2024-12-03 | Office 27/02/2025 | 2024-12-11 |  | 2024-12-04 | 2025-02-24 | 2025-02-26 | 2025-02-26 | 2025-03-22 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 17.11.2024 00:00:00 | 2-235 | System CHW and LTHW FIRST FLOOR
67810 | EB_F02-LTHWR-215-DN015-I16C00_2_R0 | 0 | true | 8.88 | EB_F02-LTHWR-215-DN015-I16C00_2_R0 |  | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-12 | 2024-11-16 |  | 2024-11-26 | 2024-12-11 | Office 27/02/2025 | 2024-12-11 |  | 2024-12-11 | 2025-02-24 | 2025-02-24 | 2025-02-24 | 2025-03-11 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 17.11.2024 00:00:00 | 2-235 | System CHW and LTHW FIRST FLOOR
67811 | EB_F02-LTHWR-216-DN015-I16C00_2_R0 | 0 | true | 7.6 | EB_F02-LTHWR-216-DN015-I16C00_2_R0 |  | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-12 | 2024-11-16 |  | 2024-11-26 | 2024-12-10 | Office 27/02/2025 | 2024-12-11 |  | 2024-12-11 | 2025-02-24 | 2025-02-25 | 2025-02-25 | 2025-03-22 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 17.11.2024 00:00:00 | 2-235 | System CHW and LTHW FIRST FLOOR
67812 | EB_F02-LTHWR-217-DN015-I16C00_2_R0 | 0 | true | 6.3 | EB_F02-LTHWR-217-DN015-I16C00_2_R0 |  | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-12 | 2024-11-16 |  | 2024-11-26 | 2024-12-10 | Office 27/02/2025 | 2024-12-11 |  | 2024-12-11 | 2025-02-24 | 2025-02-24 | 2025-02-24 | 2025-03-22 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 17.11.2024 00:00:00 | 2-235 | System CHW and LTHW FIRST FLOOR
67813 | EB_F02-LTHWR-218-DN015-I16C00_2_R0 | 0 | true | 5.27 | EB_F02-LTHWR-218-DN015-I16C00_2_R0 |  | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-12 | 2024-11-16 |  | 2024-11-26 | 2024-12-10 | Office 27/02/2025 | 2024-12-11 |  | 2024-12-11 | 2025-02-24 | 2025-02-24 | 2025-02-24 | 2025-03-22 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 17.11.2024 00:00:00 | 2-235 | System CHW and LTHW FIRST FLOOR
67814 | EB_F02-LTHWR-219-DN015-I16C00_2_R0 | 0 | true | 4.24 | EB_F02-LTHWR-219-DN015-I16C00_2_R0 |  | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-11 | 2024-11-16 |  | 2024-11-27 | 2024-12-05 | Office 05/03/2025 | 2024-12-11 |  | 2024-12-08 | 2025-02-26 | 2025-02-27 | 2025-02-28 | 2025-03-07 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 17.11.2024 00:00:00 | 2-235 | System CHW and LTHW FIRST FLOOR
67815 | EB_F02-LTHWR-220-DN015-I16C00_2_R0 | 0 | true | 2.43 | EB_F02-LTHWR-220-DN015-I16C00_2_R0 |  | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-11 | 2024-11-16 |  | 2024-11-27 | 2024-12-06 | Office 05/03/2025 | 2024-12-11 |  | 2024-12-08 | 2025-02-26 | 2025-02-27 | 2025-03-06 | 2025-03-22 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 17.11.2024 00:00:00 | 2-235 | System CHW and LTHW FIRST FLOOR
67816 | EB_F02-LTHWS-008-DN100-I16C00_R0 | 0 | false | 42.03 | EB_F02-LTHWS-008-DN100-I16C00_R0 | LPP6A-M-518-01-FSA | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | [13 empty] | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-235
67817 | EB_F02-LTHWS-210-DN020-I16C00_R0 | 0 | true | 2.9 | EB_F02-LTHWS-210-DN020-I16C00_R0 | LPP6A-M-518-01-FSA | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-16 | 2024-11-16 |  | 2024-12-03 | 2024-12-10 | Office 12.04.2025 | 2024-12-11 |  | 2024-12-11 | 2025-04-10 | 2025-04-10 | 2025-07-21 | 2025-07-21 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 27.11.2024 00:00:00 | 2-235 | System CHW and LTHW FIRST FLOOR
67818 | EB_F02-LTHWS-211-DN015-I16C00_1_R0 | 0 | true | 6.05 | EB_F02-LTHWS-211-DN015-I16C00_1_R0 |  | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-12 | 2024-11-16 |  | 2024-11-27 | 2024-12-05 | Office 27/02/2025 | 2024-12-11 |  | 2024-12-08 | 2025-02-20 | 2025-02-25 | 2025-02-25 | 2025-02-25 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 17.11.2024 00:00:00 | 2-304 | System CHW and LTHW FIRST FLOOR
67819 | EB_F02-LTHWS-212-DN015-I16C00_1_R0 | 0 | true | 4.54 | EB_F02-LTHWS-212-DN015-I16C00_1_R0 |  | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-12 | 2024-11-16 |  | 2024-11-27 | 2024-12-10 | Office 27/02/2025 | 2024-12-11 |  | 2024-12-11 | 2025-02-21 | 2025-02-22 | 2025-02-22 | 2025-03-11 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 17.11.2024 00:00:00 | 2-304 | System CHW and LTHW FIRST FLOOR
67820 | EB_F02-LTHWS-213-DN015-I16C00_1_R0 | 0 | true | 3.49 | EB_F02-LTHWS-213-DN015-I16C00_1_R0 |  | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-12 | 2024-11-16 |  | 2024-11-27 | 2024-12-05 | Office 27/02/2025 | 2024-12-11 |  | 2024-12-08 | 2025-02-20 | 2025-02-21 | 2025-02-25 | 2025-03-11 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 17.11.2024 00:00:00 | 2-304 | System CHW and LTHW FIRST FLOOR
67821 | EB_F02-LTHWS-214-DN015-I16C00_1_R0 | 0 | true | 1.93 | EB_F02-LTHWS-214-DN015-I16C00_1_R0 |  | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-12 | 2024-11-16 |  | 2024-11-27 | 2024-12-05 | Office 27/02/2025 | 2024-12-11 |  | 2024-12-08 | 2025-02-24 | 2025-02-24 | 2025-02-24 | 2025-03-19 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 17.11.2024 00:00:00 | 2-304 | System CHW and LTHW FIRST FLOOR
67822 | EB_F02-LTHWS-215-DN015-I16C00_1_R0 | 0 | true | 8.6 | EB_F02-LTHWS-215-DN015-I16C00_1_R0 |  | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-12 | 2024-11-16 |  | 2024-11-27 | 2024-12-11 | Office 27/02/2025 | 2024-12-11 |  | 2024-12-11 | 2025-02-23 | 2025-02-23 | 2025-02-23 | 2025-03-11 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 17.11.2024 00:00:00 | 2-303 | System CHW and LTHW FIRST FLOOR
67823 | EB_F02-LTHWS-216-DN015-I16C00_1_R0 | 0 | true | 7.22 | EB_F02-LTHWS-216-DN015-I16C00_1_R0 |  | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-12 | 2024-11-16 |  | 2024-11-27 | 2024-12-06 | Office 27/02/2025 | 2024-12-11 |  | 2024-12-08 | 2025-02-23 | 2025-02-23 | 2025-02-23 | 2025-03-22 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 17.11.2024 00:00:00 | 2-303 | System CHW and LTHW FIRST FLOOR
67824 | EB_F02-LTHWS-216-DN015-I16C00_2_R1 | 1 | true | 6.74 | EB_F02-LTHWS-216-DN015-I16C00_2_R1 |  | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-04 | 2024-11-16 |  | 2024-11-27 | 2024-12-05 | Office 27/02/2025 | 2024-12-11 |  | 2024-12-08 | 2025-02-19 | 2025-02-23 | 2025-03-22 | 2025-03-22 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 17.11.2024 00:00:00 | 2-235 | System CHW and LTHW FIRST FLOOR
67825 | EB_F02-LTHWS-217-DN015-I16C00_1_R0 | 0 | true | 5.93 | EB_F02-LTHWS-217-DN015-I16C00_1_R0 |  | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-12 | 2024-11-16 |  | 2024-11-27 | 2024-12-05 | Dejan Todorovski 18.02.2025 | 2024-12-11 |  | 2024-12-08 | 2025-02-20 | 2025-03-12 | 2025-03-22 | 2025-03-22 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 17.11.2024 00:00:00 | 2-303 | System CHW and LTHW FIRST FLOOR
67826 | EB_F02-LTHWS-218-DN015-I16C00_1_R0 | 0 | true | 5.36 | EB_F02-LTHWS-218-DN015-I16C00_1_R0 |  | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-12 | 2024-11-16 |  | 2024-11-27 | 2024-12-05 | Office 27/02/2025 | 2024-12-11 |  | 2024-12-08 | 2025-02-25 | 2025-02-25 | 2025-02-25 | 2025-03-22 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 17.11.2024 00:00:00 | 2-303 | System CHW and LTHW FIRST FLOOR
67827 | EB_F02-LTHWS-219-DN015-I16C00_1_R0 | 0 | true | 4.3 | EB_F02-LTHWS-219-DN015-I16C00_1_R0 |  | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-11 | 2024-11-16 |  | 2024-11-27 | 2024-12-10 | Office 05/03/2025 | 2024-12-11 |  | 2024-12-11 | 2025-02-26 | 2025-02-27 | 2025-02-28 | 2025-03-07 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 17.11.2024 00:00:00 | 2-302 | System CHW and LTHW FIRST FLOOR
67828 | EB_F02-LTHWS-220-DN015-I16C00_1_R0 | 0 | true | 1.52 | EB_F02-LTHWS-220-DN015-I16C00_1_R0 |  | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-10-31 | 2024-10-31 | 2024-11-11 | 2024-11-16 |  | 2024-11-27 | 2024-12-05 | Office 05/03/2025 | 2024-12-11 |  | 2024-12-08 | 2025-02-25 | 2025-02-27 | 2025-03-03 | 2025-03-22 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 17.11.2024 00:00:00 | 2-302 | System CHW and LTHW FIRST FLOOR
67925 | DH_F02-PCWR-013-DN150-I16C00_R2 | 2 | true | 6.89 | DH_F02-PCWR-013-DN150-I16C00_R2 |  | 1129 | Datahall | F02 | N/A | TBH-ZAT-2024-11-05 | 2024-11-01 | 2024-11-12 | 2024-11-16 |  | 2024-12-08 | 2025-01-23 | Office 20.03.2025 | 2025-01-29 |  | 2025-01-23 | 2025-03-17 | 2025-03-18 | 2025-03-19 | 2025-03-19 | 1352 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 29.11.2024 00:00:00 | 2-500 | System PCW 01/System PCW 02
67926 | DH_F02-PCWS-008-DN150-I16C00_R2 | 2 | true | 4.86 | DH_F02-PCWS-008-DN150-I16C00_R2 |  | 1129 | Datahall | F02 | N/A | TBH-ZAT-2024-11-05 | 2024-11-01 | 2024-11-13 | 2024-11-16 |  | 2024-12-08 | 2025-01-23 | Office 20.03.2025 | 2025-01-29 |  | 2025-01-23 | 2025-03-17 | 2025-03-17 | 2025-03-19 | 2025-03-19 | 1352 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 29.11.2024 00:00:00 | 2-500 | System PCW 01/System PCW 02
67947 | CUB5_PCWR-004-DN150-I16C00_R0 | 0 | true | 7.26 | CUB5_PCWR-004-DN150-I16C00_R0 |  | 1129 | CUB5 | F01 | N/A | TBH-ZAT-2024-11-08_no prefab | 2024-11-05 | 2025-01-05 | 2025-02-05 |  | 2025-04-15 | 2025-04-25 | Office 12.06.2025 | 2025-04-15 |  | 2025-04-15 | 2025-04-15 | 2025-04-25 | 2025-05-28 | 2025-05-28 | 1361 | 193 |  |  |  |  | SEP | SEP | [5 empty] | CUB5 | System PCW Sidestream Filter Skid/System PCW 01
67948 | CUB5_PCWR-005-DN150-I16C00_R0 | 0 | true | 1.69 | CUB5_PCWR-005-DN150-I16C00_R0 |  | 1129 | CUB5 | F01 | N/A | TBH-ZAT-2024-11-08_no prefab | 2024-11-05 | 2025-01-05 | 2025-02-05 |  | 2025-02-07 | 2025-02-07 | Office 12.06.2025 | 2025-02-07 |  | 2025-02-07 | 2025-02-07 | 2025-02-10 | 2025-02-10 | 2025-03-05 | 1361 | 193 |  |  |  |  | SEP | SEP | [5 empty] | CUB5 | System PCW Sidestream Filter Skid
67949 | CUB5_PCWR-006-DN150-I16C00_R0 | 0 | true | 1.07 | CUB5_PCWR-006-DN150-I16C00_R0 |  | 1129 | CUB5 | F01 | N/A | TBH-ZAT-2024-11-08_no prefab | 2024-11-05 | 2025-01-05 | 2025-02-05 |  | 2025-02-06 | 2025-02-08 | Office 12.06.2025 | 2025-02-06 |  | 2025-02-06 | 2025-02-06 | 2025-02-06 | 2025-02-07 | 2025-02-08 | 1361 | 193 |  |  |  |  | SEP | SEP | [5 empty] | CUB5 | System PCW Sidestream Filter Skid
67950 | CUB5_PCWR-007-DN150-I16C00_R0 | 0 | true | 10.3 | CUB5_PCWR-007-DN150-I16C00_R0 |  | 1129 | CUB5 | F01 | N/A | TBH-ZAT-2024-11-08_no prefab | 2024-11-05 | 2025-01-05 | 2025-02-05 |  | 2025-04-16 | 2025-04-17 | Office 12.06.2025 | 2025-04-16 |  | 2025-04-16 | 2025-04-16 | 2025-04-26 | 2025-05-23 | 2025-05-27 | 1361 | 193 |  |  |  |  | SEP | SEP | [5 empty] | CUB5 | System PCW Sidestream Filter Skid/System PCW 01
67951 | CUB5_PCWR-008-DN150-I16C00_R0 | 0 | true | 0.53 | CUB5_PCWR-008-DN150-I16C00_R0 |  | 1129 | CUB5 | F01 | N/A | TBH-ZAT-2024-11-08_no prefab | 2024-11-05 | 2025-01-05 | 2025-02-05 |  | 2025-02-10 | 2025-02-12 | Office 12.06.2025 | 2025-02-10 |  | 2025-02-10 | 2025-02-06 | 2025-02-10 | 2025-02-12 | 2025-02-12 | 1361 | 193 |  |  |  |  | SEP | SEP | [5 empty] | CUB5 | System PCW Sidestream Filter Skid
67952 | CUB5_PCWR-009-DN150-I16C00_R0 | 0 | true | 1.49 | CUB5_PCWR-009-DN150-I16C00_R0 |  | 1129 | CUB5 | F01 | N/A | TBH-ZAT-2024-11-08_no prefab | 2024-11-05 | 2025-01-05 | 2025-02-05 |  | 2025-02-05 | 2025-02-12 | Office 12.06.2025 | 2025-02-10 |  | 2025-02-10 | 2025-02-10 | 2025-02-11 | 2025-02-11 | 2025-02-12 | 1361 | 193 |  |  |  |  | SEP | SEP | [5 empty] | CUB5 | System PCW Sidestream Filter Skid
67953 | CUB5_PCWR-010-DN40-I16C00_R0 | 0 | true | 0 | CUB5_PCWR-010-DN40-I16C00_R0 |  | 1129 | CUB5 | F01 | N/A | TBH-ZAT-2024-11-08_no prefab | 2024-11-05 | 2025-01-05 | 2025-02-05 |  | 2025-02-11 | 2025-02-11 | Office 12.06.2025 | 2025-02-11 |  | 2025-02-11 | 2025-02-11 | 2025-02-11 | 2025-02-11 | 2025-02-11 | 1361 | 193 |  |  |  |  | SEP | SEP | [5 empty] | CUB5 | System PCW Sidestream Filter Skid
67954 | CUB5_PCWR-011-DN40-I16C00_R0 | 0 | true | 0 | CUB5_PCWR-011-DN40-I16C00_R0 |  | 1129 | CUB5 | F01 | N/A | TBH-ZAT-2024-11-08_no prefab | 2024-11-05 | 2025-01-05 | 2025-02-05 |  | 2025-04-26 | 2025-04-26 | Office 12.06.2025 | 2025-04-26 |  | 2025-04-26 | 2025-04-26 | 2025-04-26 | 2025-04-26 | 2025-04-26 | 1361 | 193 |  |  |  |  | SEP | SEP | [5 empty] | CUB5 | System PCW Sidestream Filter Skid
67955 | EB_F01-CHWR-005-DN150-I16C00_R0 | 0 | false | 26.04 | EB_F01-CHWR-005-DN150-I16C00_R0 | LPP6A-M-511-00-FSA | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-25 | 2024-11-20 |  | 2024-12-08 | 2025-01-06 | Office 21.01.2025 | 2025-01-15 |  | 2025-01-09 |  |  |  |  | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2024-10-12 | 1-306
67956 | EB_F01-CHWR-130-DN025-I16C00_2_R0 | 0 | true | 2.03 | EB_F01-CHWR-130-DN025-I16C00_2_R0 | LPP6A-M-511-00-FSA | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-18 | 2024-11-20 |  | 2024-12-03 | 2024-12-09 | Office 07.04.2025 | 2024-12-11 |  | 2024-12-10 | 2025-03-27 | 2025-03-27 | 2025-03-27 | 2025-03-27 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2024-10-12 | 1-306 | System CHW and LTHW GROUND FLOOR
67957 | EB_F01-CHWR-131-DN025-I16C00_2_R0 | 0 | true | 3.31 | EB_F01-CHWR-131-DN025-I16C00_2_R0 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-18 | 2024-11-20 |  | 2024-12-03 | 2024-12-09 | Office 07.04.2025 | 2024-12-11 |  | 2024-12-10 | 2025-03-28 | 2025-03-28 | 2025-03-28 | 2025-03-28 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2024-10-12 | 1-306 | System CHW and LTHW GROUND FLOOR
67958 | EB_F01-CHWR-132-DN020-I16C00_2_R0 | 0 | true | 1.18 | EB_F01-CHWR-132-DN020-I16C00_2_R0 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-18 | 2024-11-20 |  | 2024-12-03 | 2024-12-11 | Office 12.03.2025 | 2024-12-11 |  | 2024-12-11 | 2025-03-07 | 2025-03-07 | 2025-03-07 | 2025-03-07 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2024-10-12 | 1-306 | System CHW and LTHW GROUND FLOOR
67959 | EB_F01-CHWR-133-DN020-I16C00_2_R0 | 0 | true | 2.55 | EB_F01-CHWR-133-DN020-I16C00_2_R0 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-18 | 2024-11-20 |  | 2024-12-03 | 2024-12-09 | Office 12.03.2025 | 2024-12-11 |  | 2024-12-10 | 2025-03-11 | 2025-03-11 | 2025-03-11 | 2025-03-11 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2024-10-12 | 1-306 | System CHW and LTHW GROUND FLOOR
67960 | EB_F01-CHWR-134-DN020-I16C00_2_R0 | 0 | true | 3.85 | EB_F01-CHWR-134-DN020-I16C00_2_R0 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-18 | 2024-11-20 |  | 2024-12-03 | 2024-12-09 | Office 12.03.2025 | 2024-12-11 |  | 2024-12-10 | 2025-02-11 | 2025-02-11 | 2025-03-12 | 2025-03-12 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2024-10-12 | 1-306 | System CHW and LTHW GROUND FLOOR
67961 | EB_F01-CHWR-135-DN020-I16C00_2_R0 | 0 | true | 5.18 | EB_F01-CHWR-135-DN020-I16C00_2_R0 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-18 | 2024-11-20 |  | 2024-12-03 | 2024-12-09 | Office 12.03.2025 | 2024-12-11 |  | 2024-12-10 | 2025-03-11 | 2025-03-11 | 2025-03-12 | 2025-03-12 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2024-10-12 | 1-306 | System CHW and LTHW GROUND FLOOR
67962 | EB_F01-CHWR-137-DN020-I16C00_2_R0 | 0 | true | 0.75 | EB_F01-CHWR-137-DN020-I16C00_2_R0 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-18 | 2024-11-20 |  | 2024-12-03 | 2024-12-09 | Office 22.03.2025 | 2024-12-11 |  | 2024-12-10 | 2025-03-17 | 2025-03-17 | 2025-03-17 | 2025-03-17 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2024-10-12 | 1-306 | System CHW and LTHW GROUND FLOOR
67963 | EB_F01-CHWR-138-DN020-I16C00_2_R0 | 0 | true | 2.04 | EB_F01-CHWR-138-DN020-I16C00_2_R0 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-18 | 2024-11-20 |  | 2024-12-03 | 2024-12-11 | Office 22.03.2025 | 2024-12-11 |  | 2024-12-11 | 2025-03-20 | 2025-03-20 | 2025-03-20 | 2025-03-20 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2024-10-12 | 1-306 | System CHW and LTHW GROUND FLOOR
67964 | EB_F01-CHWR-139-DN020-I16C00_2_R0 | 0 | true | 3.44 | EB_F01-CHWR-139-DN020-I16C00_2_R0 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-18 | 2024-11-20 |  | 2024-12-03 | 2024-12-10 | Office 22.03.2025 | 2024-12-11 |  | 2024-12-11 | 2025-03-19 | 2025-03-19 | 2025-03-19 | 2025-03-19 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2024-10-12 | 1-306 | System CHW and LTHW GROUND FLOOR
67965 | EB_F01-CHWR-140-DN020-I16C00_2_R0 | 0 | true | 4.85 | EB_F01-CHWR-140-DN020-I16C00_2_R0 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-18 | 2024-11-20 |  | 2024-12-03 | 2024-12-10 | Office 22.03.2025 | 2024-12-11 |  | 2024-12-11 | 2025-03-18 | 2025-03-18 | 2025-03-18 | 2025-03-18 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2024-10-12 | 1-306 | System CHW and LTHW GROUND FLOOR
67966 | EB_F01-CHWS-012-DN150-I16C00_R0 | 0 | false | 27.35 | EB_F01-CHWS-012-DN150-I16C00_R0 | LPP6A-M-511-00-FSA | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-18 | 2024-11-20 |  | 2024-12-08 | 2025-01-06 | Office 21.01.2025 | 2025-01-15 |  | 2025-01-09 |  |  |  |  | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2024-10-12 | 1-306
67967 | EB_F01-CHWS-130-DN025-I16C00_1_R0 | 0 | true | 1.69 | EB_F01-CHWS-130-DN025-I16C00_1_R0 | LPP6A-M-511-00-FSA | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-18 | 2024-11-20 |  | 2024-12-03 | 2024-12-09 | Office 07.04.2025 | 2024-12-11 |  | 2024-12-10 | 2025-03-27 | 2025-03-27 | 2025-03-27 | 2025-03-27 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2024-10-12 | 1-302 | System CHW and LTHW GROUND FLOOR
67968 | EB_F01-CHWS-131-DN025-I16C00_1_R0 | 0 | true | 2.85 | EB_F01-CHWS-131-DN025-I16C00_1_R0 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-18 | 2024-11-20 |  | 2024-12-03 | 2024-12-09 | Office 07.04.2025 | 2024-12-11 |  | 2024-12-10 | 2025-03-28 | 2025-03-28 | 2025-03-28 | 2025-03-28 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2024-10-12 | 1-302 | System CHW and LTHW GROUND FLOOR
67969 | EB_F01-CHWS-132-DN020-I16C00_1_R0 | 0 | true | 0.81 | EB_F01-CHWS-132-DN020-I16C00_1_R0 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-18 | 2024-11-20 |  | 2024-12-03 | 2024-12-11 | Office 12.03.2025 | 2024-12-11 |  | 2024-12-11 | 2025-03-06 | 2025-03-06 | 2025-03-06 | 2025-03-20 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2024-10-12 | 1-303 | System CHW and LTHW GROUND FLOOR
67970 | EB_F01-CHWS-133-DN020-I16C00_1_R0 | 0 | true | 2.25 | EB_F01-CHWS-133-DN020-I16C00_1_R0 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-18 | 2024-11-20 |  | 2024-12-03 | 2024-12-09 | Office 12.03.2025 | 2024-12-11 |  | 2024-12-10 | 2025-03-06 | 2025-03-06 | 2025-03-06 | 2025-03-06 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2024-10-12 | 1-303 | System CHW and LTHW GROUND FLOOR
67971 | EB_F01-CHWS-134-DN020-I16C00_1_R0 | 0 | true | 3.54 | EB_F01-CHWS-134-DN020-I16C00_1_R0 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-18 | 2024-11-20 |  | 2024-12-03 | 2024-12-11 | Office 12.03.2025 | 2024-12-11 |  | 2024-12-11 | 2025-03-06 | 2025-03-06 | 2025-03-06 | 2025-03-06 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2024-10-12 | 1-303 | System CHW and LTHW GROUND FLOOR
67972 | EB_F01-CHWS-135-DN020-I16C00_1_R0 | 0 | true | 4.86 | EB_F01-CHWS-135-DN020-I16C00_1_R0 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-18 | 2024-11-20 |  | 2024-12-03 | 2024-12-11 | Office 12.03.2025 | 2024-12-11 |  | 2024-12-11 | 2025-03-06 | 2025-03-06 | 2025-03-06 | 2025-03-06 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2024-10-12 | 1-303 | System CHW and LTHW GROUND FLOOR
67973 | EB_F01-CHWS-137-DN020-I16C00_1_R0 | 0 | true | 0.32 | EB_F01-CHWS-137-DN020-I16C00_1_R0 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-18 | 2024-11-20 |  | 2024-12-03 | 2024-12-10 | Office 22.03.2025 | 2024-12-11 |  | 2024-12-11 | 2025-03-13 | 2025-03-13 | 2025-03-13 | 2025-03-13 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2024-10-12 | 1-304 | System CHW and LTHW GROUND FLOOR
67974 | EB_F01-CHWS-138-DN020-I16C00_1_R0 | 0 | true | 1.61 | EB_F01-CHWS-138-DN020-I16C00_1_R0 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-18 | 2024-11-20 |  | 2024-12-03 | 2024-12-10 | Office 22.03.2025 | 2024-12-11 |  | 2024-12-11 | 2025-03-13 | 2025-03-13 | 2025-03-13 | 2025-03-13 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2024-10-12 | 1-304 | System CHW and LTHW GROUND FLOOR
67975 | EB_F01-CHWS-139-DN020-I16C00_1_R0 | 0 | true | 3.01 | EB_F01-CHWS-139-DN020-I16C00_1_R0 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-19 | 2024-11-20 |  | 2024-12-03 | 2024-12-09 | Office 22.03.2025 | 2024-12-11 |  | 2024-12-10 | 2025-03-13 | 2025-03-13 | 2025-03-13 | 2025-03-13 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2024-10-12 | 1-304 | System CHW and LTHW GROUND FLOOR
67976 | EB_F01-CHWS-140-DN020-I16C00_1_R0 | 0 | true | 4.42 | EB_F01-CHWS-140-DN020-I16C00_1_R0 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-18 | 2024-11-20 |  | 2024-12-03 | 2024-12-10 | Office 22.03.2025 | 2024-12-11 |  | 2024-12-11 | 2025-03-13 | 2025-03-13 | 2025-03-13 | 2025-03-13 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2024-10-12 | 1-304 | System CHW and LTHW GROUND FLOOR
67977 | EB_F01-LTHWR-008-DN100-I16C00_R0 | 0 | true | 26.85 | EB_F01-LTHWR-008-DN100-I16C00_R0 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-18 | 2024-11-20 |  | 2024-12-09 | 2025-01-08 | Office 17.04.2025 | 2025-01-22 |  | 2025-01-09 | 2025-03-14 | 2025-04-03 | 2025-04-15 | 2025-04-15 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2024-10-12 | 1-306 | System CHW and LTHW GROUND FLOOR
67978 | EB_F01-LTHWR-130-DN020-I16C00_2_R0 | 0 | true | 2.42 | EB_F01-LTHWR-130-DN020-I16C00_2_R0 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-18 | 2024-11-20 |  | 2024-12-05 | 2024-12-11 | Office 07.04.2025 | 2024-12-11 |  | 2024-12-11 | 2025-03-27 | 2025-03-27 | 2025-03-27 | 2025-03-27 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2024-10-12 | 1-306 | System CHW and LTHW GROUND FLOOR
67979 | EB_F01-LTHWR-131-DN020-I16C00_2_R0 | 0 | true | 3.58 | EB_F01-LTHWR-131-DN020-I16C00_2_R0 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-18 | 2024-11-20 |  | 2024-12-05 | 2024-12-10 | Office 07.05.2025 | 2024-12-11 |  | 2024-12-11 | 2025-03-28 | 2025-03-28 | 2025-03-28 | 2025-03-28 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2024-10-12 | 1-306 | System CHW and LTHW GROUND FLOOR
67980 | EB_F01-LTHWR-132-DN020-I16C00_2_R0 | 0 | true | 1.87 | EB_F01-LTHWR-132-DN020-I16C00_2_R0 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-18 | 2024-11-20 |  | 2024-12-05 | 2024-12-10 | Office 12.03.2025 | 2024-12-11 |  | 2024-12-11 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2024-10-12 | 1-306 | System CHW and LTHW GROUND FLOOR
67981 | EB_F01-LTHWR-133-DN020-I16C00_2_R0 | 0 | true | 2.88 | EB_F01-LTHWR-133-DN020-I16C00_2_R0 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-18 | 2024-11-20 |  | 2024-12-05 | 2024-12-10 | Office 12.03.2025 | 2024-12-11 |  | 2024-12-11 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2024-10-12 | 1-306 | System CHW and LTHW GROUND FLOOR
67982 | EB_F01-LTHWR-134-DN020-I16C00_2_R0 | 0 | true | 4.18 | EB_F01-LTHWR-134-DN020-I16C00_2_R0 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-18 | 2024-11-20 |  | 2024-12-05 | 2024-12-10 | Office 12.03.2025 | 2024-12-11 |  | 2024-12-11 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2024-10-12 | 1-306 | System CHW and LTHW GROUND FLOOR
67983 | EB_F01-LTHWR-135-DN020-I16C00_2_R0 | 0 | true | 5.49 | EB_F01-LTHWR-135-DN020-I16C00_2_R0 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-18 | 2024-11-20 |  | 2024-12-05 | 2024-12-10 | Office 12.03.2025 | 2024-12-11 |  | 2024-12-11 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2024-10-12 | 1-306 | System CHW and LTHW GROUND FLOOR
67984 | EB_F01-LTHWR-137-DN020-I16C00_2_R0 | 0 | true | 0.98 | EB_F01-LTHWR-137-DN020-I16C00_2_R0 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-18 | 2024-11-20 |  | 2024-12-05 | 2024-12-10 | Office 22.03.2025 | 2024-12-11 |  | 2024-12-11 | 2025-03-17 | 2025-03-17 | 2025-03-17 | 2025-03-17 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2024-10-12 | 1-306 | System CHW and LTHW GROUND FLOOR
67985 | EB_F01-LTHWR-138-DN020-I16C00_2_R0 | 0 | true | 2.27 | EB_F01-LTHWR-138-DN020-I16C00_2_R0 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-18 | 2024-11-20 |  | 2024-12-05 | 2024-12-11 | Office 22.03.2025 | 2024-12-11 |  | 2024-12-11 | 2025-03-17 | 2025-03-17 | 2025-03-17 | 2025-03-17 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2024-10-12 | 1-306 | System CHW and LTHW GROUND FLOOR
67986 | EB_F01-LTHWR-139-DN020-I16C00_2_R0 | 0 | true | 3.67 | EB_F01-LTHWR-139-DN020-I16C00_2_R0 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-18 | 2024-11-20 |  | 2024-12-05 | 2024-12-11 | Office 22.03.2025 | 2024-12-11 |  | 2024-12-11 | 2025-03-17 | 2025-03-17 | 2025-03-17 | 2025-03-17 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2024-10-12 | 1-306 | System CHW and LTHW GROUND FLOOR
67987 | EB_F01-LTHWR-140-DN020-I16C00_2_R0 | 0 | true | 5.09 | EB_F01-LTHWR-140-DN020-I16C00_2_R0 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-18 | 2024-11-20 |  | 2024-12-05 | 2024-12-10 | Office 22.03.2025 | 2024-12-11 |  | 2024-12-11 | 2025-03-17 | 2025-03-17 | 2025-03-17 | 2025-03-17 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2024-10-12 | 1-306 | System CHW and LTHW GROUND FLOOR
67988 | EB_F01-LTHWS-008-DN100-I16C00_R0 | 0 | true | 28.72 | EB_F01-LTHWS-008-DN100-I16C00_R0 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-18 | 2024-11-20 |  | 2024-12-09 | 2025-01-07 | Office 17.04.2025 | 2025-01-29 |  | 2025-01-09 | 2025-03-13 | 2025-03-13 | 2025-04-03 | 2025-04-15 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2024-10-12 | 1-306 | System CHW and LTHW GROUND FLOOR
67989 | EB_F01-LTHWS-130-DN020-I16C00_1_R0 | 0 | true | 2.18 | EB_F01-LTHWS-130-DN020-I16C00_1_R0 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-18 | 2024-11-20 |  | 2024-12-05 | 2024-12-10 | Office 07.04.2025 | 2024-12-11 |  | 2024-12-11 | 2025-03-27 | 2025-03-27 | 2025-03-27 | 2025-03-27 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2024-10-12 | 1-302 | System CHW and LTHW GROUND FLOOR
67990 | EB_F01-LTHWS-131-DN020-I16C00_1_R0 | 0 | true | 3.44 | EB_F01-LTHWS-131-DN020-I16C00_1_R0 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-18 | 2024-11-20 |  | 2024-12-05 | 2024-12-10 | Office 07.04.2025 | 2024-12-11 |  | 2024-12-11 | 2025-03-28 | 2025-03-28 | 2025-03-28 | 2025-03-28 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2024-10-12 | 1-302 | System CHW and LTHW GROUND FLOOR
67991 | EB_F01-LTHWS-132-DN020-I16C00_1_R0 | 0 | true | 1.62 | EB_F01-LTHWS-132-DN020-I16C00_1_R0 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-18 | 2024-11-20 |  | 2024-12-05 | 2024-12-10 | Office 12.03.2025 | 2024-12-11 |  | 2024-12-11 | 2025-03-11 | 2025-03-11 | 2025-03-11 | 2025-03-11 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2024-10-12 | 1-303 | System CHW and LTHW GROUND FLOOR
67992 | EB_F01-LTHWS-133-DN020-I16C00_1_R0 | 0 | true | 2.69 | EB_F01-LTHWS-133-DN020-I16C00_1_R0 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-18 | 2024-11-20 |  | 2024-12-05 | 2024-12-10 | Office 12.03.2025 | 2024-12-11 |  | 2024-12-11 | 2025-03-07 | 2025-03-07 | 2025-03-07 | 2025-03-07 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2024-10-12 | 1-303 | System CHW and LTHW GROUND FLOOR
67993 | EB_F01-LTHWS-134-DN020-I16C00_1_R0 | 0 | true | 3.98 | EB_F01-LTHWS-134-DN020-I16C00_1_R0 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-18 | 2024-11-20 |  | 2024-12-05 | 2024-12-10 | Office 12.03.2025 | 2024-12-11 |  | 2024-12-11 | 2025-03-07 | 2025-03-07 | 2025-03-08 | 2025-03-08 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2024-10-12 | 1-303 | System CHW and LTHW GROUND FLOOR
67994 | EB_F01-LTHWS-135-DN020-I16C00_1_R0 | 0 | true | 5.32 | EB_F01-LTHWS-135-DN020-I16C00_1_R0 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-18 | 2024-11-20 |  | 2024-12-05 | 2024-12-10 | Office 12.03.2025 | 2024-12-11 |  | 2024-12-11 | 2025-03-07 | 2025-03-08 | 2025-03-08 | 2025-03-08 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2024-10-12 | 1-303 | System CHW and LTHW GROUND FLOOR
67995 | EB_F01-LTHWS-137-DN020-I16C00_1_R0 | 0 | true | 0.84 | EB_F01-LTHWS-137-DN020-I16C00_1_R0 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-18 | 2024-11-20 |  | 2024-12-05 | 2024-12-10 | Office 22.03.2025 | 2024-12-11 |  | 2024-12-11 | 2025-03-14 | 2025-03-14 | 2025-03-14 | 2025-03-14 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2024-10-12 | 1-304 | System CHW and LTHW GROUND FLOOR
67996 | EB_F01-LTHWS-138-DN020-I16C00_1_R0 | 0 | true | 2.12 | EB_F01-LTHWS-138-DN020-I16C00_1_R0 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-18 | 2024-11-20 |  | 2024-12-05 | 2024-12-10 | Office 22.03.2025 | 2024-12-11 |  | 2024-12-11 | 2025-03-14 | 2025-03-14 | 2025-03-14 | 2025-03-14 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2024-10-12 | 1-304 | System CHW and LTHW GROUND FLOOR
67997 | EB_F01-LTHWS-139-DN020-I16C00_1_R0 | 0 | true | 3.53 | EB_F01-LTHWS-139-DN020-I16C00_1_R0 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-18 | 2024-11-20 |  | 2024-12-05 | 2024-12-10 | Office 22.03.2025 | 2024-12-11 |  | 2024-12-11 | 2025-03-14 | 2025-03-14 | 2025-03-14 | 2025-03-14 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2024-10-12 | 1-304 | System CHW and LTHW GROUND FLOOR
67998 | EB_F01-LTHWS-140-DN020-I16C00_1_R0 | 0 | true | 4.95 | EB_F01-LTHWS-140-DN020-I16C00_1_R0 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-18 | 2024-11-20 |  | 2024-12-05 | 2024-12-10 | Office 22.03.2025 | 2024-12-11 |  | 2024-12-11 | 2025-03-15 | 2025-03-15 | 2025-03-15 | 2025-03-15 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2024-10-12 | 1-304 | System CHW and LTHW GROUND FLOOR
67999 | EB_F01-PHTGR-005-DN200-I16C00_R0 | 0 | false | 29.31 | EB_F01-PHTGR-005-DN200-I16C00_R0 | LPP6A-M-504-XX-FSA | 1129 | EB | F01 | N/A | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-16 | 2024-11-16 | Branch for Flushing Valve incorrect | [10 empty] | 1368 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-306
68000 | EB_F01-PHTGS-006-DN200-I16C00_R0 | 0 | false | 29.59 | EB_F01-PHTGS-006-DN200-I16C00_R0 | LPP6A-M-504-XX-FSA | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-16 | 2024-11-16 | Branch for Flushing Valve incorrect | [10 empty] | 1368 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 27.11.2024 00:00:00 | 1-306
68001 | EB_F02-CHWR-012-DN150-I16C00_R1 | 1 | true | 40.41 | EB_F02-CHWR-012-DN150-I16C00_R1 | LPP6A-M-504-XX-FSA | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-13 | 2024-11-16 |  | 2024-12-10 | 2025-01-20 | Office 07.04.2025. | 2025-01-22 |  | 2025-01-22 | 2025-03-17 | 2025-03-18 | 2025-03-18 | 2025-03-19 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 17.11.2024 00:00:00 | 2-235 | System CHW and LTHW FIRST FLOOR
68002 | EB_F02-CHWS-012-DN150-I16C00_R1 | 1 | true | 42.29 | EB_F02-CHWS-012-DN150-I16C00_R1 |  | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-13 | 2024-11-16 |  | 2024-12-10 | 2025-01-15 | Office 07.04.2025 | 2025-01-22 |  | 2025-01-19 | 2025-02-18 | 2025-02-19 | 2025-03-22 | 2025-03-22 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 26.11.2024 00:00:00 | 2-235 | System CHW and LTHW FIRST FLOOR
68003 | EB_F02-LTHWR-008-DN100-I16C00_R1 | 1 | true | 41.51 | EB_F02-LTHWR-008-DN100-I16C00_R1 |  | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-13 | 2024-11-16 |  | 2025-01-02 | 2025-01-15 | Office 07.04.2025 | 2025-01-22 |  | 2025-01-19 | 2025-02-18 | 2025-02-19 | 2025-03-22 | 2025-03-22 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 17.11.2024 00:00:00 | 2-235 | System CHW and LTHW FIRST FLOOR
68004 | EB_F02-LTHWS-008-DN100-I16C00_R1 | 1 | true | 42.09 | EB_F02-LTHWS-008-DN100-I16C00_R1 |  | 1129 | EB | F02 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-16 | 2024-11-16 |  | 2025-01-08 | 2025-01-16 | Todorovski 30.01.25 | 2025-01-22 |  | 2025-01-19 | 2025-02-18 | 2025-02-19 | 2025-03-22 | 2025-03-22 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 17.11.2024 00:00:00 | 2-235 | System CHW and LTHW FIRST FLOOR
68005 | FSA_F02_1-CHWR-229-DN025-I16C00_R0 | 0 | true | 4.84 | FSA_F02_1-CHWR-229-DN025-I16C00_R0 |  | 1129 | CCNR AHU Room | F02 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-26 | 2024-12-03 |  | 2024-12-04 | 2024-12-11 | Office 02.04.2025 | 2024-12-11 |  | 2024-12-11 | 2025-03-18 | 2025-03-19 | 2025-03-26 | 2025-03-26 | 1359 | 193 | Mechanical A 2-212 |  |  | 194 | SEP | SEP |  |  |  |  | 2024-05-12 | 2-212 | System CHW and LTHW FIRST FLOOR
68006 | FSA_F02_1-CHWR-230-DN020-I16C00_R0 | 0 | true | 3.69 | FSA_F02_1-CHWR-230-DN020-I16C00_R0 |  | 1129 | CCNR AHU Room | F02 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-26 | 2024-12-03 |  | 2024-12-04 | 2024-12-09 | Office 02.04.2025 | 2024-12-11 |  | 2024-12-10 | 2025-03-26 | 2025-03-26 | 2025-04-10 | 2025-04-10 | 1359 | 193 | Mechanical A 2-212 |  |  | 194 | SEP | SEP |  |  |  |  | 2024-05-12 | 2-212 | System CHW and LTHW FIRST FLOOR
68007 | FSA_F02_1-CHWR-231-DN020-I16C00_R0 | 0 | true | 6.14 | FSA_F02_1-CHWR-231-DN020-I16C00_R0 |  | 1129 | CCNR AHU Room | F02 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-26 | 2024-12-03 |  | 2024-12-04 | 2024-12-10 | Office 02.04.2025 | 2024-12-11 |  | 2024-12-11 | 2025-03-26 | 2025-03-26 | 2025-04-03 | 2025-04-03 | 1359 | 193 | Mechanical A 2-212 |  |  | 194 | SEP | SEP |  |  |  |  | 2024-05-12 | 2-212 | System CHW and LTHW FIRST FLOOR
68008 | FSA_F02_1-CHWR-233-DN025-I16C00_R0 | 0 | true | 5.66 | FSA_F02_1-CHWR-233-DN025-I16C00_R0 |  | 1129 | CCNR AHU Room | F02 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-26 | 2024-12-03 |  | 2024-12-04 | 2024-12-09 | Office 04.04.2025 | 2024-12-11 |  | 2024-12-10 | 2025-03-28 | 2025-03-28 | 2025-03-31 | 2025-03-31 | 1359 | 193 | Mechanical A 2-212 |  |  | 194 | SEP | SEP |  |  |  |  | 2024-05-12 | 2-212 | System CHW and LTHW FIRST FLOOR
68009 | FSA_F02_1-CHWR-234-DN020-I16C00_R0 | 0 | true | 4.15 | FSA_F02_1-CHWR-234-DN020-I16C00_R0 |  | 1129 | CCNR AHU Room | F02 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-26 | 2024-12-03 |  | 2024-12-04 | 2024-12-11 | Office 04.04.2025 | 2024-12-11 |  | 2024-12-11 | 2025-04-03 | 2025-04-03 | 2025-04-10 | 2025-04-10 | 1359 | 193 | Mechanical A 2-212 |  |  | 194 | SEP | SEP |  |  |  |  | 2024-05-12 | 2-212 | System CHW and LTHW FIRST FLOOR
68010 | FSA_F02_1-CHWR-235-DN020-I16C00_R0 | 0 | true | 6.24 | FSA_F02_1-CHWR-235-DN020-I16C00_R0 |  | 1129 | CCNR AHU Room | F02 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-26 | 2024-12-03 |  | 2024-12-04 | 2024-12-11 | Office 04.04.2025 | 2024-12-11 |  | 2024-12-11 | 2025-04-02 | 2025-04-02 | 2025-04-09 | 2025-04-09 | 1359 | 193 | Mechanical A 2-212 |  |  | 194 | SEP | SEP |  |  |  |  | 2024-05-12 | 2-212 | System CHW and LTHW FIRST FLOOR
68011 | FSA_F02_1-CHWR-237-DN025-I16C00_R0 | 0 | true | 5.61 | FSA_F02_1-CHWR-237-DN025-I16C00_R0 |  | 1129 | CCNR AHU Room | F02 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-26 | 2024-12-03 |  | 2024-12-04 | 2024-12-09 | Office 01.04.2025 | 2024-12-11 |  | 2024-12-10 | 2025-03-27 | 2025-03-27 | 2025-03-27 | 2025-03-27 | 1359 | 193 | Mechanical B 2-213 |  |  | 194 | SEP | SEP |  |  |  |  | 2024-05-12 | 2-213 | System CHW and LTHW FIRST FLOOR
68012 | FSA_F02_1-CHWR-238-DN020-I16C00_R0 | 0 | true | 4.66 | FSA_F02_1-CHWR-238-DN020-I16C00_R0 |  | 1129 | CCNR AHU Room | F02 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-26 | 2024-12-03 |  | 2024-12-04 | 2024-12-11 | Office 01.04.2025 | 2024-12-11 |  | 2024-12-11 | 2025-03-29 | 2025-03-29 | 2025-04-02 | 2025-04-02 | 1359 | 193 | Mechanical B 2-213 |  |  | 194 | SEP | SEP |  |  |  |  | 2024-05-12 | 2-213 | System CHW and LTHW FIRST FLOOR
68013 | FSA_F02_1-CHWR-239-DN020-I16C00_R0 | 0 | true | 5.9 | FSA_F02_1-CHWR-239-DN020-I16C00_R0 |  | 1129 | CCNR AHU Room | F02 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-26 | 2024-12-03 |  | 2024-12-04 | 2024-12-10 | Office 01.04.2025 | 2024-12-11 |  | 2024-12-11 | 2025-03-28 | 2025-03-28 | 2025-04-08 | 2025-04-08 | 1359 | 193 | Mechanical B 2-213 |  |  | 194 | SEP | SEP |  |  |  |  | 2024-05-12 | 2-213 | System CHW and LTHW FIRST FLOOR
68014 | FSA_F02_1-CHWR-240-DN025-I16C00_R0 | 0 | true | 4.84 | FSA_F02_1-CHWR-240-DN025-I16C00_R0 |  | 1129 | CCNR AHU Room | F02 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-26 | 2024-12-03 |  | 2024-12-04 | 2024-12-10 | Office 01.04.2025 | 2024-12-11 |  | 2024-12-11 | 2025-03-25 | 2025-03-25 | 2025-03-25 | 2025-03-25 | 1359 | 193 | Mechanical B 2-213 |  |  | 194 | SEP | SEP |  |  |  |  | 2024-05-12 | 2-213 | System CHW and LTHW FIRST FLOOR
68015 | FSA_F02_1-CHWR-241-DN020-I16C00_R0 | 0 | true | 3.01 | FSA_F02_1-CHWR-241-DN020-I16C00_R0 |  | 1129 | CCNR AHU Room | F02 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-26 | 2024-12-03 |  | 2024-12-04 | 2024-12-09 | Office 01.04.2025 | 2024-12-11 |  | 2024-12-10 | 2025-03-25 | 2025-03-25 | 2025-04-01 | 2025-04-01 | 1359 | 193 | Mechanical B 2-213 |  |  | 194 | SEP | SEP |  |  |  |  | 2024-05-12 | 2-213 | System CHW and LTHW FIRST FLOOR
68016 | FSA_F02_1-CHWR-242-DN020-I16C00_R0 | 0 | true | 7.36 | FSA_F02_1-CHWR-242-DN020-I16C00_R0 |  | 1129 | CCNR AHU Room | F02 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-26 | 2024-12-03 |  | 2024-12-04 | 2024-12-10 | Office 01.04.2025 | 2024-12-11 |  | 2024-12-11 | 2025-03-25 | 2025-03-25 | 2025-03-31 | 2025-03-31 | 1359 | 193 | Mechanical B 2-213 |  |  | 194 | SEP | SEP |  |  |  |  | 2024-05-12 | 2-213 | System CHW and LTHW FIRST FLOOR
68017 | FSA_F02_1-CHWS-229-DN025-I16C00_R0 | 0 | true | 5.19 | FSA_F02_1-CHWS-229-DN025-I16C00_R0 |  | 1129 | CCNR AHU Room | F02 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-24 | 2024-12-03 |  | 2024-12-04 | 2024-12-10 | Office 02.04.2025 | 2024-12-11 |  | 2024-12-11 | 2025-03-19 | 2025-03-21 | 2025-03-26 | 2025-03-26 | 1359 | 193 | Mechanical A 2-212 |  |  | 194 | SEP | SEP |  |  |  |  | 2024-05-12 | 2-212 | System CHW and LTHW FIRST FLOOR
68018 | FSA_F02_1-CHWS-230-DN020-I16C00_R0 | 0 | true | 4.16 | FSA_F02_1-CHWS-230-DN020-I16C00_R0 |  | 1129 | CCNR AHU Room | F02 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-24 | 2024-12-03 |  | 2024-12-04 | 2024-12-11 | Office 02.04.2025 | 2024-12-11 |  | 2024-12-11 | 2025-03-27 | 2025-03-27 | 2025-04-10 | 2025-04-10 | 1359 | 193 | Mechanical A 2-212 |  |  | 194 | SEP | SEP |  |  |  |  | 2024-05-12 | 2-212 | System CHW and LTHW FIRST FLOOR
68019 | FSA_F02_1-CHWS-231-DN020-I16C00_R0 | 0 | true | 6.33 | FSA_F02_1-CHWS-231-DN020-I16C00_R0 |  | 1129 | CCNR AHU Room | F02 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-24 | 2024-12-03 |  | 2024-12-04 | 2024-12-10 | Office 02.04.2025 | 2024-12-11 |  | 2024-12-11 | 2025-03-26 | 2025-03-26 | 2025-04-03 | 2025-04-03 | 1359 | 193 | Mechanical A 2-212 |  |  | 194 | SEP | SEP |  |  |  |  | 2024-05-12 | 2-212 | System CHW and LTHW FIRST FLOOR
68020 | FSA_F02_1-CHWS-233-DN025-I16C00_R0 | 0 | true | 6.16 | FSA_F02_1-CHWS-233-DN025-I16C00_R0 |  | 1129 | CCNR AHU Room | F02 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-26 | 2024-12-03 |  | 2024-12-04 | 2024-12-09 | Office 04.04.2025 | 2024-12-11 |  | 2024-12-10 | 2025-03-28 | 2025-03-28 | 2025-03-31 | 2025-03-31 | 1359 | 193 | Mechanical A 2-212 |  |  | 194 | SEP | SEP |  |  |  |  | 2024-05-12 | 2-212 | System CHW and LTHW FIRST FLOOR
68021 | FSA_F02_1-CHWS-234-DN020-I16C00_R0 | 0 | true | 4.72 | FSA_F02_1-CHWS-234-DN020-I16C00_R0 |  | 1129 | CCNR AHU Room | F02 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-27 | 2024-12-03 |  | 2024-12-04 | 2024-12-09 | Office 04.04.2025 | 2024-12-11 |  | 2024-12-10 | 2025-04-03 | 2025-04-03 | 2025-04-10 | 2025-04-10 | 1359 | 193 | Mechanical A 2-212 |  |  | 194 | SEP | SEP |  |  |  |  | 2024-05-12 | 2-212 | System CHW and LTHW FIRST FLOOR
68022 | FSA_F02_1-CHWS-235-DN020-I16C00_R0 | 0 | true | 6.17 | FSA_F02_1-CHWS-235-DN020-I16C00_R0 |  | 1129 | CCNR AHU Room | F02 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-27 | 2024-12-03 |  | 2024-12-04 | 2024-12-11 | Office 04.04.2025 | 2024-12-11 |  | 2024-12-11 | 2025-04-02 | 2025-04-02 | 2025-04-09 | 2025-04-09 | 1359 | 193 | Mechanical A 2-212 |  |  | 194 | SEP | SEP |  |  |  |  | 2024-05-12 | 2-212 | System CHW and LTHW FIRST FLOOR
68023 | FSA_F02_1-CHWS-237-DN025-I16C00_R0 | 0 | true | 5.96 | FSA_F02_1-CHWS-237-DN025-I16C00_R0 |  | 1129 | CCNR AHU Room | F02 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-27 | 2024-12-03 |  | 2024-12-04 | 2024-12-10 | Office 01.04.2025 | 2024-12-11 |  | 2024-12-11 | 2025-03-27 | 2025-03-27 | 2025-03-27 | 2025-03-27 | 1359 | 193 | Mechanical B 2-213 |  |  | 194 | SEP | SEP |  |  |  |  | 2024-05-12 | 2-213 | System CHW and LTHW FIRST FLOOR
68024 | FSA_F02_1-CHWS-238-DN020-I16C00_R0 | 0 | true | 5.12 | FSA_F02_1-CHWS-238-DN020-I16C00_R0 |  | 1129 | CCNR AHU Room | F02 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-27 | 2024-12-03 |  | 2024-12-04 | 2024-12-10 | Office 01.04.2025 | 2024-12-11 |  | 2024-12-11 | 2025-03-29 | 2025-03-29 | 2025-04-02 | 2025-04-02 | 1359 | 193 | Mechanical B 2-213 |  |  | 194 | SEP | SEP |  |  |  |  | 2024-05-12 | 2-213 | System CHW and LTHW FIRST FLOOR
68025 | FSA_F02_1-CHWS-239-DN020-I16C00_R0 | 0 | true | 6.07 | FSA_F02_1-CHWS-239-DN020-I16C00_R0 |  | 1129 | CCNR AHU Room | F02 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-27 | 2024-12-03 |  | 2024-12-04 | 2024-12-10 | Office 01.04.2025 | 2024-12-11 |  | 2024-12-11 | 2025-03-28 | 2025-03-28 | 2025-04-08 | 2025-04-08 | 1359 | 193 | Mechanical B 2-213 |  |  | 194 | SEP | SEP |  |  |  |  | 2024-05-12 | 2-213 | System CHW and LTHW FIRST FLOOR
68026 | FSA_F02_1-CHWS-240-DN025-I16C00_R0 | 0 | true | 5.35 | FSA_F02_1-CHWS-240-DN025-I16C00_R0 |  | 1129 | CCNR AHU Room | F02 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-27 | 2024-12-03 |  | 2024-12-04 | 2024-12-10 | Office 01.04.2025 | 2024-12-11 |  | 2024-12-11 | 2025-03-25 | 2025-03-25 | 2025-03-25 | 2025-03-25 | 1359 | 193 | Mechanical B 2-213 |  |  | 194 | SEP | SEP |  |  |  |  | 2024-05-12 | 2-213 | System CHW and LTHW FIRST FLOOR
68027 | FSA_F02_1-CHWS-241-DN020-I16C00_R0 | 0 | true | 3.7 | FSA_F02_1-CHWS-241-DN020-I16C00_R0 |  | 1129 | CCNR AHU Room | F02 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-27 | 2024-12-03 |  | 2024-12-04 | 2024-12-11 | Office 01.04.2025 | 2024-12-11 |  | 2024-12-11 | 2025-03-25 | 2025-03-25 | 2025-04-01 | 2025-04-01 | 1359 | 193 | Mechanical B 2-213 |  |  | 194 | SEP | SEP |  |  |  |  | 2024-05-12 | 2-213 | System CHW and LTHW FIRST FLOOR
68028 | FSA_F02_1-CHWS-242-DN020-I16C00_R0 | 0 | true | 7.01 | FSA_F02_1-CHWS-242-DN020-I16C00_R0 |  | 1129 | CCNR AHU Room | F02 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-27 | 2024-12-03 |  | 2024-12-04 | 2024-12-11 | Office 01.04.2025 | 2024-12-11 |  | 2024-12-11 | 2025-03-25 | 2025-03-25 | 2025-04-01 | 2025-04-01 | 1359 | 193 | Mechanical B 2-213 |  |  | 194 | SEP | SEP |  |  |  |  | 2024-05-12 | 2-213 | System CHW and LTHW FIRST FLOOR
68029 | FSA_F02_1-LTHWR-229-DN020-I16C00_R0 | 0 | true | 5.51 | FSA_F02_1-LTHWR-229-DN020-I16C00_R0 |  | 1129 | CCNR AHU Room | F02 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-26 | 2024-12-03 |  | 2024-12-04 | 2024-12-10 | Office 02.04.2025 | 2024-12-11 |  | 2024-12-11 | 2025-03-21 | 2025-03-22 | 2025-03-26 | 2025-03-26 | 1360 | 193 | Mechanical A 2-212 |  |  | 194 | SEP | SEP |  |  |  |  | 2024-05-12 | 2-212 | System CHW and LTHW FIRST FLOOR
68030 | FSA_F02_1-LTHWR-230-DN020-I16C00_R0 | 0 | true | 3.3 | FSA_F02_1-LTHWR-230-DN020-I16C00_R0 |  | 1129 | CCNR AHU Room | F02 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-26 | 2024-12-03 |  | 2024-12-04 | 2024-12-11 | Office 02.04.2025 | 2024-12-11 |  | 2024-12-11 | 2025-03-27 | 2025-03-27 | 2025-04-10 | 2025-04-10 | 1360 | 193 | Mechanical A 2-212 |  |  | 194 | SEP | SEP |  |  |  |  | 2024-05-12 | 2-212 | System CHW and LTHW FIRST FLOOR
68031 | FSA_F02_1-LTHWR-231-DN020-I16C00_R0 | 0 | true | 6.01 | FSA_F02_1-LTHWR-231-DN020-I16C00_R0 |  | 1129 | CCNR AHU Room | F02 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-26 | 2024-12-03 |  | 2024-12-04 | 2024-12-10 | Office 02.04.2025 | 2024-12-11 |  | 2024-12-11 | 2025-03-26 | 2025-03-27 | 2025-04-03 | 2025-04-03 | 1360 | 193 | Mechanical A 2-212 |  |  | 194 | SEP | SEP |  |  |  |  | 2024-05-12 | 2-212 | System CHW and LTHW FIRST FLOOR
68032 | FSA_F02_1-LTHWR-233-DN020-I16C00_R0 | 0 | true | 6.05 | FSA_F02_1-LTHWR-233-DN020-I16C00_R0 |  | 1129 | CCNR AHU Room | F02 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-26 | 2024-12-03 |  | 2024-12-04 | 2024-12-10 | Office 04.04.2025 | 2024-12-11 |  | 2024-12-11 | 2025-03-28 | 2025-03-28 | 2025-04-01 | 2025-04-01 | 1360 | 193 | Mechanical A 2-212 |  |  | 194 | SEP | SEP |  |  |  |  | 2024-05-12 | 2-212 | System CHW and LTHW FIRST FLOOR
68033 | FSA_F02_1-LTHWR-234-DN020-I16C00_R0 | 0 | true | 3.08 | FSA_F02_1-LTHWR-234-DN020-I16C00_R0 |  | 1129 | CCNR AHU Room | F02 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-26 | 2024-12-03 |  | 2024-12-04 | 2024-12-09 | Office 04.04.2025 | 2024-12-11 |  | 2024-12-10 | 2025-04-03 | 2025-04-03 | 2025-04-10 | 2025-04-10 | 1360 | 193 | Mechanical A 2-212 |  |  | 194 | SEP | SEP |  |  |  |  | 2024-05-12 | 2-212 | System CHW and LTHW FIRST FLOOR
68034 | FSA_F02_1-LTHWR-235-DN020-I16C00_R0 | 0 | true | 6.42 | FSA_F02_1-LTHWR-235-DN020-I16C00_R0 |  | 1129 | CCNR AHU Room | F02 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-26 | 2024-12-03 |  | 2024-12-04 | 2024-12-11 | Office 04.04.2025 | 2024-12-11 |  | 2024-12-11 | 2025-04-02 | 2025-04-02 | 2025-04-09 | 2025-04-09 | 1360 | 193 | Mechanical A 2-212 |  |  | 194 | SEP | SEP |  |  |  |  | 2024-05-12 | 2-212 | System CHW and LTHW FIRST FLOOR
68035 | FSA_F02_1-LTHWR-237-DN020-I16C00_R0 | 0 | true | 6.28 | FSA_F02_1-LTHWR-237-DN020-I16C00_R0 |  | 1129 | CCNR AHU Room | F02 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-26 | 2024-12-03 |  | 2024-12-04 | 2024-12-10 | Office 01.04.2025 | 2024-12-11 |  | 2024-12-11 | 2025-03-27 | 2025-03-27 | 2025-03-27 | 2025-03-27 | 1360 | 193 | Mechanical B 2-213 |  |  | 194 | SEP | SEP |  |  |  |  | 2024-05-12 | 2-213 | System CHW and LTHW FIRST FLOOR
68036 | FSA_F02_1-LTHWR-238-DN020-I16C00_R0 | 0 | true | 4.23 | FSA_F02_1-LTHWR-238-DN020-I16C00_R0 |  | 1129 | CCNR AHU Room | F02 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-26 | 2024-12-03 |  | 2024-12-04 | 2024-12-11 | Office 01.04.2025 | 2024-12-11 |  | 2024-12-11 | 2025-03-29 | 2025-03-29 | 2025-04-02 | 2025-04-02 | 1360 | 193 | Mechanical B 2-213 |  |  | 194 | SEP | SEP |  |  |  |  | 2024-05-12 | 2-213 | System CHW and LTHW FIRST FLOOR
68037 | FSA_F02_1-LTHWR-239-DN020-I16C00_R0 | 0 | true | 5.75 | FSA_F02_1-LTHWR-239-DN020-I16C00_R0 |  | 1129 | CCNR AHU Room | F02 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-25 | 2024-12-03 |  | 2024-12-04 | 2024-12-10 | Office 01.04.2025 | 2024-12-11 |  | 2024-12-11 | 2025-03-28 | 2025-03-28 | 2025-04-08 | 2025-04-08 | 1360 | 193 | Mechanical B 2-213 |  |  | 194 | SEP | SEP |  |  |  |  | 2024-05-12 | 2-213 | System CHW and LTHW FIRST FLOOR
68038 | FSA_F02_1-LTHWR-240-DN020-I16C00_R0 | 0 | true | 5.23 | FSA_F02_1-LTHWR-240-DN020-I16C00_R0 |  | 1129 | CCNR AHU Room | F02 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-25 | 2024-12-03 |  | 2024-12-04 | 2024-12-10 | Office 01.04.2025 | 2024-12-11 |  | 2024-12-11 | 2025-03-25 | 2025-03-25 | 2025-03-25 | 2025-03-25 | 1360 | 193 | Mechanical B 2-213 |  |  | 194 | SEP | SEP |  |  |  |  | 2024-05-12 | 2-213 | System CHW and LTHW FIRST FLOOR
68039 | FSA_F02_1-LTHWR-241-DN020-I16C00_R0 | 0 | true | 1.91 | FSA_F02_1-LTHWR-241-DN020-I16C00_R0 |  | 1129 | CCNR AHU Room | F02 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-25 | 2024-12-03 |  | 2024-12-04 | 2024-12-10 | Office 01.04.2025 | 2024-12-11 |  | 2024-12-11 | 2025-03-25 | 2025-03-25 | 2025-04-01 | 2025-04-01 | 1360 | 193 | Mechanical B 2-213 |  |  | 194 | SEP | SEP |  |  |  |  | 2024-05-12 | 2-213 | System CHW and LTHW FIRST FLOOR
68040 | FSA_F02_1-LTHWR-242-DN020-I16C00_R0 | 0 | true | 7.62 | FSA_F02_1-LTHWR-242-DN020-I16C00_R0 |  | 1129 | CCNR AHU Room | F02 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-25 | 2024-12-03 |  | 2024-12-04 | 2024-12-11 | Office 01.04.2025 | 2024-12-11 |  | 2024-12-11 | 2025-03-25 | 2025-03-25 | 2025-03-31 | 2025-03-31 | 1360 | 193 | Mechanical B 2-213 |  |  | 194 | SEP | SEP |  |  |  |  | 2024-05-12 | 2-213 | System CHW and LTHW FIRST FLOOR
68041 | FSA_F02_1-LTHWS-229-DN020-I16C00_R0 | 0 | true | 5.46 | FSA_F02_1-LTHWS-229-DN020-I16C00_R0 |  | 1129 | CCNR AHU Room | F02 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-25 | 2024-12-03 |  | 2024-12-04 | 2024-12-10 | Office 02.04.2025 | 2024-12-11 |  | 2024-12-11 | 2025-03-20 | 2025-03-21 | 2025-03-26 | 2025-03-26 | 1360 | 193 | Mechanical A 2-212 |  |  | 194 | SEP | SEP |  |  |  |  | 2024-05-12 | 2-212 | System CHW and LTHW FIRST FLOOR
68042 | FSA_F02_1-LTHWS-230-DN020-I16C00_R0 | 0 | true | 3.49 | FSA_F02_1-LTHWS-230-DN020-I16C00_R0 |  | 1129 | CCNR AHU Room | F02 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-25 | 2024-12-03 |  | 2024-12-04 | 2024-12-10 | Office 02.04.2025 | 2024-12-11 |  | 2024-12-11 | 2025-03-27 | 2025-03-27 | 2025-04-10 | 2025-04-10 | 1360 | 193 | Mechanical A 2-212 |  |  | 194 | SEP | SEP |  |  |  |  | 2024-05-12 | 2-212 | System CHW and LTHW FIRST FLOOR
68043 | FSA_F02_1-LTHWS-231-DN020-I16C00_R0 | 0 | true | 6.07 | FSA_F02_1-LTHWS-231-DN020-I16C00_R0 |  | 1129 | CCNR AHU Room | F02 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-25 | 2024-12-03 |  | 2024-12-04 | 2024-12-10 | Office 02.04.2025 | 2024-12-11 |  | 2024-12-11 | 2025-03-26 | 2025-03-27 | 2025-04-03 | 2025-04-03 | 1360 | 193 | Mechanical A 2-212 |  |  | 194 | SEP | SEP |  |  |  |  | 2024-05-12 | 2-212 | System CHW and LTHW FIRST FLOOR
68044 | FSA_F02_1-LTHWS-233-DN020-I16C00_R0 | 0 | true | 6.12 | FSA_F02_1-LTHWS-233-DN020-I16C00_R0 |  | 1129 | CCNR AHU Room | F02 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-25 | 2024-12-03 |  | 2024-12-04 | 2024-12-10 | Office 04.04.2025 | 2024-12-11 |  | 2024-12-11 | 2025-03-28 | 2025-03-28 | 2025-04-01 | 2025-04-01 | 1360 | 193 | Mechanical A 2-212 |  |  | 194 | SEP | SEP |  |  |  |  | 2024-05-12 | 2-212 | System CHW and LTHW FIRST FLOOR
68045 | FSA_F02_1-LTHWS-234-DN020-I16C00_R0 | 0 | true | 3.46 | FSA_F02_1-LTHWS-234-DN020-I16C00_R0 |  | 1129 | CCNR AHU Room | F02 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-25 | 2024-12-03 |  | 2024-12-04 | 2024-12-10 | Office 04.04.2025 | 2024-12-11 |  | 2024-12-11 | 2025-04-03 | 2025-04-03 | 2025-04-10 | 2025-04-10 | 1360 | 193 | Mechanical A 2-212 |  |  | 194 | SEP | SEP |  |  |  |  | 2024-05-12 | 2-212 | System CHW and LTHW FIRST FLOOR
68046 | FSA_F02_1-LTHWS-235-DN020-I16C00_R0 | 0 | true | 6.29 | FSA_F02_1-LTHWS-235-DN020-I16C00_R0 |  | 1129 | CCNR AHU Room | F02 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-25 | 2024-12-03 |  | 2024-12-04 | 2024-12-11 | Office 04.04.2025 | 2024-12-11 |  | 2024-12-11 | 2025-04-02 | 2025-04-02 | 2025-04-09 | 2025-04-09 | 1360 | 193 | Mechanical A 2-212 |  |  | 194 | SEP | SEP |  |  |  |  | 2024-05-12 | 2-212 | System CHW and LTHW FIRST FLOOR
68047 | FSA_F02_1-LTHWS-237-DN020-I16C00_R0 | 0 | true | 6.23 | FSA_F02_1-LTHWS-237-DN020-I16C00_R0 |  | 1129 | CCNR AHU Room | F02 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-25 | 2024-12-03 |  | 2024-12-04 | 2024-12-10 | Office 01.04.2025 | 2024-12-11 |  | 2024-12-11 | 2025-03-27 | 2025-03-27 | 2025-03-27 | 2025-03-27 | 1360 | 193 | Mechanical B 2-213 |  |  | 194 | SEP | SEP |  |  |  |  | 2024-05-12 | 2-213 | System CHW and LTHW FIRST FLOOR
68048 | FSA_F02_1-LTHWS-238-DN020-I16C00_R0 | 0 | true | 4.42 | FSA_F02_1-LTHWS-238-DN020-I16C00_R0 |  | 1129 | CCNR AHU Room | F02 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-25 | 2024-12-03 |  | 2024-12-04 | 2024-12-10 | Office 01.04.2025 | 2024-12-11 |  | 2024-12-11 | 2025-03-29 | 2025-03-29 | 2025-04-02 | 2025-04-02 | 1360 | 193 | Mechanical B 2-213 |  |  | 194 | SEP | SEP |  |  |  |  | 2024-05-12 | 2-213 | System CHW and LTHW FIRST FLOOR
68049 | FSA_F02_1-LTHWS-239-DN020-I16C00_R0 | 0 | true | 5.88 | FSA_F02_1-LTHWS-239-DN020-I16C00_R0 |  | 1129 | CCNR AHU Room | F02 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-25 | 2024-12-03 |  | 2024-12-04 | 2024-12-10 | Office 01.04.2025 | 2024-12-11 |  | 2024-12-11 | 2025-03-28 | 2025-03-28 | 2025-04-08 | 2025-04-08 | 1360 | 193 | Mechanical B 2-213 |  |  | 194 | SEP | SEP |  |  |  |  | 2024-05-12 | 2-213 | System CHW and LTHW FIRST FLOOR
68050 | FSA_F02_1-LTHWS-240-DN020-I16C00_R0 | 0 | true | 5.31 | FSA_F02_1-LTHWS-240-DN020-I16C00_R0 |  | 1129 | CCNR AHU Room | F02 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-25 | 2024-12-03 |  | 2024-12-04 | 2024-12-11 | Office 01.04.2025 | 2024-12-11 |  | 2024-12-11 | 2025-03-25 | 2025-03-25 | 2025-03-25 | 2025-03-25 | 1360 | 193 | Mechanical B 2-213 |  |  | 194 | SEP | SEP |  |  |  |  | 2024-05-12 | 2-213 | System CHW and LTHW FIRST FLOOR
68051 | FSA_F02_1-LTHWS-242-DN020-I16C00_R0 | 0 | true | 7.32 | FSA_F02_1-LTHWS-242-DN020-I16C00_R0 |  | 1129 | CCNR AHU Room | F02 | FoamInside | TBH-ZAT-2024-11-08 | 2024-11-05 | 2024-11-25 | 2024-12-03 |  | 2024-12-04 | 2024-12-11 | Office 01.04.2025 | 2024-12-11 |  | 2024-12-11 | 2025-03-25 | 2025-03-25 | 2025-04-01 | 2025-04-01 | 1360 | 193 | Mechanical B 2-213 |  |  | 194 | SEP | SEP |  |  |  |  | 2024-05-12 | 2-213 | System CHW and LTHW FIRST FLOOR
68052 | FSA_F02_1-PCWR-014-DN100-I16C00_R0 | 0 | false | 23.11 | FSA_F02_1-PCWR-014-DN100-I16C00_R0 | LPP6A-M-544-XX-FSA | 1129 | CCNR AHU Room | F02 | N/A | TBH-ZAT-2024-11-08 | 2024-11-05 |  | 2024-12-10 | Revision will be issued | [10 empty] | 1352 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-212
68053 | FSA_F02_1-PCWR-015-DN100-I16C00_R0 | 0 | false | 23.22 | FSA_F02_1-PCWR-015-DN100-I16C00_R0 | LPP6A-M-544-XX-FSA | 1129 | CCNR AHU Room | F02 | N/A | TBH-ZAT-2024-11-08 | 2024-11-05 |  | 2024-12-10 | Revision will be issued | [10 empty] | 1352 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-213
68054 | FSA_F02_1-PCWR-016-DN100-I16C00_R0 | 0 | false | 23.32 | FSA_F02_1-PCWR-016-DN100-I16C00_R0 | LPP6A-M-544-XX-FSA | 1129 | CCNR AHU Room | F02 | N/A | TBH-ZAT-2024-11-08 | 2024-11-05 |  | 2024-12-10 | Revision will be issued | [10 empty] | 1352 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-213
68055 | FSA_F02_1-PCWR-017-DN100-I16C00_R0 | 0 | false | 23.71 | FSA_F02_1-PCWR-017-DN100-I16C00_R0 | LPP6A-M-544-XX-FSA | 1129 | CCNR AHU Room | F02 | N/A | TBH-ZAT-2024-11-08 | 2024-11-05 |  | 2024-12-10 | Revision will be issued | [10 empty] | 1352 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-212
68056 | FSA_F02_1-PCWR-018-DN065-I16C00_R0 | 0 | false | 11.79 | FSA_F02_1-PCWR-018-DN065-I16C00_R0 | LPP6A-M-544-XX-FSA | 1129 | CCNR AHU Room | F02 | N/A | TBH-ZAT-2024-11-08 | 2024-11-05 |  |  | Revision will be issued | [10 empty] | 1352 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-212
68057 | FSA_F02_1-PCWR-019-DN065-I16C00_R0 | 0 | false | 11.89 | FSA_F02_1-PCWR-019-DN065-I16C00_R0 | LPP6A-M-544-XX-FSA | 1129 | CCNR AHU Room | F02 | N/A | TBH-ZAT-2024-11-08 | 2024-11-05 |  |  | Revision will be issued | [10 empty] | 1352 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-213
68058 | FSA_F02_1-PCWR-020-DN065-I16C00_R0 | 0 | false | 11.8 | FSA_F02_1-PCWR-020-DN065-I16C00_R0 | LPP6A-M-544-XX-FSA | 1129 | CCNR AHU Room | F02 | N/A | TBH-ZAT-2024-11-08 | 2024-11-05 |  |  | Revision will be issued | [10 empty] | 1352 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-213
68059 | FSA_F02_1-PCWR-021-DN065-I16C00_R0 | 0 | false | 11.93 | FSA_F02_1-PCWR-021-DN065-I16C00_R0 | LPP6A-M-544-XX-FSA | 1129 | CCNR AHU Room | F02 | N/A | TBH-ZAT-2024-11-08 | 2024-11-05 |  |  | Revision will be issued | [10 empty] | 1352 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-212
68060 | FSA_F02_1-PCWS-009-DN100-I16C00_R0 | 0 | false | 18.36 | FSA_F02_1-PCWS-009-DN100-I16C00_R0 | LPP6A-M-544-XX-FSA | 1129 | CCNR AHU Room | F02 | N/A | TBH-ZAT-2024-11-08 | 2024-11-05 |  | 2024-12-10 | Revision will be issued | [10 empty] | 1352 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-213
68061 | FSA_F02_1-PCWS-010-DN100-I16C00_R0 | 0 | false | 18.58 | FSA_F02_1-PCWS-010-DN100-I16C00_R0 | LPP6A-M-544-XX-FSA | 1129 | CCNR AHU Room | F02 | N/A | TBH-ZAT-2024-11-08 | 2024-11-05 |  |  | Revision will be issued | [10 empty] | 1352 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-213
68062 | FSA_F02_1-PCWS-011-DN100-I16C00_R0 | 0 | false | 18.38 | FSA_F02_1-PCWS-011-DN100-I16C00_R0 | LPP6A-M-544-XX-FSA | 1129 | CCNR AHU Room | F02 | N/A | TBH-ZAT-2024-11-08 | 2024-11-05 |  |  | Revision will be issued | [10 empty] | 1352 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-212
68063 | FSA_F02_1-PCWS-012-DN100-I16C00_R0 | 0 | false | 19.41 | FSA_F02_1-PCWS-012-DN100-I16C00_R0 | LPP6A-M-544-XX-FSA | 1129 | CCNR AHU Room | F02 | N/A | TBH-ZAT-2024-11-08 | 2024-11-05 |  |  | Revision will be issued | [10 empty] | 1352 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-212
68064 | FSA_F02_1-PCWS-013-DN065-I16C00_R0 | 0 | false | 11.58 | FSA_F02_1-PCWS-013-DN065-I16C00_R0 | LPP6A-M-544-XX-FSA | 1129 | CCNR AHU Room | F02 | N/A | TBH-ZAT-2024-11-08 | 2024-11-05 |  |  | Revision will be issued | [10 empty] | 1352 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-212
68065 | FSA_F02_1-PCWS-014-DN065-I16C00_R0 | 0 | false | 11.69 | FSA_F02_1-PCWS-014-DN065-I16C00_R0 | LPP6A-M-544-XX-FSA | 1129 | CCNR AHU Room | F02 | N/A | TBH-ZAT-2024-11-08 | 2024-11-05 |  |  | Revision will be issued | [10 empty] | 1352 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-213
68066 | FSA_F02_1-PCWS-015-DN065-I16C00_R0 | 0 | false | 11.59 | FSA_F02_1-PCWS-015-DN065-I16C00_R0 | LPP6A-M-544-XX-FSA | 1129 | CCNR AHU Room | F02 | N/A | TBH-ZAT-2024-11-08 | 2024-11-05 |  |  | Revision will be issued | [10 empty] | 1352 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-213
68067 | FSA_F02_1-PCWS-016-DN065-I16C00_R0 | 0 | false | 11.69 | FSA_F02_1-PCWS-016-DN065-I16C00_R0 | LPP6A-M-544-XX-FSA | 1129 | CCNR AHU Room | F02 | N/A | TBH-ZAT-2024-11-08 | 2024-11-05 |  |  | Revision will be issued | [10 empty] | 1352 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-212
70541 | FSA_F02_1-CHWR-005-DN150-I16C00 | 0 | false | 59.75 | FSA_F02_1-CHWR-005-DN150-I16C00 | LPP6A-M-513-01-FSA | 1129 | FSA Corridor | F02 | FoamInside | TBH-ZAT-2024-11-22 | 2024-11-19 | [13 empty] | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-200
70542 | FSA_F02_1-CHWR-006-DN150-I16C00 | 0 | true | 11.34 | FSA_F02_1-CHWR-006-DN150-I16C00 | LPP6A-M-513-01-FSA | 1129 | FSA Corridor | F02 | FoamInside | TBH-ZAT-2024-11-22 | 2024-11-19 | 2024-11-25 | 2024-12-03 |  | 2024-12-09 | 2024-12-15 | Office 09.04.2025 | 2025-01-07 |  | 2024-12-18 | 2025-03-19 | 2025-03-19 | 2025-03-19 | 2025-05-27 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2024-01-12 | 2-200 | System CHW and LTHW FIRST FLOOR
70543 | FSA_F02_1-CHWR-209-DN020-I16C00 | 0 | true | 1.79 | FSA_F02_1-CHWR-209-DN020-I16C00 | LPP6A-M-513-01-FSA | 1129 | FSA_South Side | F02 | FoamInside | TBH-ZAT-2024-11-22 | 2024-11-19 | 2024-12-04 | 2024-12-10 |  | 2024-12-11 | 2024-12-18 | Office 15.01.2025 | 2025-01-07 |  | 2024-12-19 | 2025-04-08 | 2025-04-26 | 2025-07-21 | 2025-07-21 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-200 | System CHW and LTHW FIRST FLOOR
70544 | FSA_F02_1-CHWR-221-DN020-I16C00 | 0 | true | 6.25 | FSA_F02_1-CHWR-221-DN020-I16C00 | LPP6A-M-513-01-FSA | 1129 | FSA_South Side | F02 | FoamInside | TBH-ZAT-2024-11-22 | 2024-11-19 | 2024-12-04 | 2024-12-10 |  | 2024-12-18 | 2025-01-12 | Office 12.04.2025 | 2025-01-22 |  | 2025-01-12 | 2025-04-08 | 2025-04-08 | 2025-07-21 | 2025-07-21 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-200 | System CHW and LTHW FIRST FLOOR
70545 | FSA_F02_1-CHWR-222-DN020-I16C00 | 0 | false | 6.61 | FSA_F02_1-CHWR-222-DN020-I16C00 | LPP6A-M-513-01-FSA | 1129 | FSA_South Side | F02 | FoamInside | TBH-ZAT-2024-11-22 | 2024-11-19 |  |  | To be revised do to wrong height | [10 empty] | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-300
70546 | FSA_F02_1-CHWR-223-DN020-I16C00 | 0 | false | 12.42 | FSA_F02_1-CHWR-223-DN020-I16C00 | LPP6A-M-513-01-FSA | 1129 | FSA_South Side | F02 | FoamInside | TBH-ZAT-2024-11-22 | 2024-11-19 |  |  | To be revised do to wrong height | [10 empty] | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-301
70547 | FSA_F02_1-CHWR-224-DN020-I16C00 | 0 | true | 17.2 | FSA_F02_1-CHWR-224-DN020-I16C00 | LPP6A-M-513-01-FSA | 1129 | FSA_South Side | F02 | FoamInside | TBH-ZAT-2024-11-22 | 2024-11-19 | 2024-12-09 | 2024-12-10 |  | 2024-12-18 | 2025-01-08 | Office 15.03.2025 | 2025-01-29 |  | 2025-01-09 | 2025-03-04 | 2025-03-07 | 2025-03-14 | 2025-03-22 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 24.12.2024 00:00:00 | 2-301 | System CHW and LTHW FIRST FLOOR
70548 | FSA_F02_1-CHWR-225-DN020-I16C00 | 0 | true | 29.44 | FSA_F02_1-CHWR-225-DN020-I16C00 | LPP6A-M-513-01-FSA | 1129 | FSA_South Side | F02 | FoamInside | TBH-ZAT-2024-11-22 | 2024-11-19 | 2024-12-05 | 2024-12-10 |  | 2024-12-18 | 2025-01-12 | Office 20.03.2025 | 2025-01-22 |  | 2025-01-12 | 2025-03-10 | 2025-03-11 | 2025-03-13 | 2025-03-13 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 25.12.2024 00:00:00 | 2-200 | System CHW and LTHW FIRST FLOOR
70549 | FSA_F02_1-CHWR-226-DN020-I16C00 | 0 | false | 29.22 | FSA_F02_1-CHWR-226-DN020-I16C00 | LPP6A-M-513-01-FSA | 1129 | FSA_South Side | F02 | FoamInside | TBH-ZAT-2024-11-22 | 2024-11-19 |  |  | To be revised do to wrong height | [10 empty] | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-210
70550 | FSA_F02_1-CHWR-227-DN020-I16C00 | 0 | false | 20.47 | FSA_F02_1-CHWR-227-DN020-I16C00 | LPP6A-M-513-01-FSA | 1129 | FSA_South Side | F02 | FoamInside | TBH-ZAT-2024-11-22 | 2024-11-19 |  |  | To be revised do to wrong height | [10 empty] | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-211
70551 | FSA_F02_1-CHWR-228-DN020-I16C00 | 0 | true | 9.12 | FSA_F02_1-CHWR-228-DN020-I16C00 | LPP6A-M-513-01-FSA | 1129 | FSA_South Side | F02 | FoamInside | TBH-ZAT-2024-11-22 | 2024-11-19 | 2024-12-08 | 2024-12-10 |  | 2024-12-18 | 2025-01-06 | Office 18.03.2025 | 2025-01-22 |  | 2025-01-07 | 2025-03-15 | 2025-03-15 | 2025-03-17 | 2025-03-17 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-211 | System CHW and LTHW FIRST FLOOR
70552 | FSA_F02_1-CHWR-232-DN020-I16C00 | 0 | true | 1.83 | FSA_F02_1-CHWR-232-DN020-I16C00 | LPP6A-M-513-01-FSA | 1129 | FSA_South Side | F02 | FoamInside | TBH-ZAT-2024-11-22 | 2024-11-19 | 2024-12-09 | 2024-12-10 |  | 2024-12-11 | 2024-12-18 | Office 12.04.2025 | 2025-01-07 |  | 2024-12-19 | 2025-04-03 | 2025-04-03 | 2025-07-21 | 2025-07-21 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-200 | System CHW and LTHW FIRST FLOOR
70553 | FSA_F02_1-CHWR-236-DN020-I16C00 | 0 | true | 1.85 | FSA_F02_1-CHWR-236-DN020-I16C00 | LPP6A-M-513-01-FSA | 1129 | FSA_South Side | F02 | FoamInside | TBH-ZAT-2024-11-22 | 2024-11-19 | 2024-12-09 | 2024-12-10 |  | 2024-12-11 | 2024-12-18 | Office 12.04.2025 | 2025-01-07 |  | 2024-12-19 | 2025-04-01 | 2025-04-01 | 2025-07-21 |  | 1359 | 193 | Install of FCU on hold |  |  | 194 | SEP | SEP | [5 empty] | 2-200 | System CHW and LTHW FIRST FLOOR
70554 | FSA_F02_1-CHWR-243-DN020-I16C00 | 0 | true | 1.33 | FSA_F02_1-CHWR-243-DN020-I16C00 | LPP6A-M-513-01-FSA | 1129 | FSA_South Side | F02 | FoamInside | TBH-ZAT-2024-11-22 | 2024-11-19 | 2024-12-08 | 2024-12-10 |  | 2024-12-11 | 2024-12-18 | Office 12.04.2025 | 2025-01-07 |  | 2024-12-19 | 2025-04-02 | 2025-04-02 | 2025-07-21 | 2025-07-21 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-200 | System CHW and LTHW FIRST FLOOR
70555 | FSA_F02_1-CHWS-012-DN150-I16C00 | 0 | false | 59.74 | FSA_F02_1-CHWS-012-DN150-I16C00 | LPP6A-M-513-01-FSA | 1129 | FSA Corridor | F02 | FoamInside | TBH-ZAT-2024-11-22 | 2024-11-19 | [13 empty] | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-200
70556 | FSA_F02_1-CHWS-013-DN150-I16C00 | 0 | true | 10.98 | FSA_F02_1-CHWS-013-DN150-I16C00 | LPP6A-M-513-01-FSA | 1129 | FSA Corridor | F02 | FoamInside | TBH-ZAT-2024-11-22 | 2024-11-19 | 2024-11-25 | 2024-12-03 |  | 2024-12-09 | 2024-12-15 | Office 09.04.2025 | 2025-01-07 |  | 2024-12-18 | 2025-03-18 | 2025-03-18 | 2025-03-18 | 2025-05-27 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2024-01-12 | 2-200 | System CHW and LTHW FIRST FLOOR
70557 | FSA_F02_1-CHWS-209-DN020-I16C00 | 0 | true | 2.03 | FSA_F02_1-CHWS-209-DN020-I16C00 | LPP6A-M-513-01-FSA | 1129 | FSA_South Side | F02 | FoamInside | TBH-ZAT-2024-11-22 | 2024-11-19 | 2024-12-04 | 2024-12-10 |  | 2024-12-11 | 2024-12-18 | Office 15.01.2025 | 2025-01-07 |  | 2024-12-19 | 2025-04-08 | 2025-04-26 | 2025-07-21 | 2025-07-21 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-200 | System CHW and LTHW FIRST FLOOR
70558 | FSA_F02_1-CHWS-221-DN020-I16C00 | 0 | true | 6.33 | FSA_F02_1-CHWS-221-DN020-I16C00 | LPP6A-M-513-01-FSA | 1129 | FSA_South Side | F02 | FoamInside | TBH-ZAT-2024-11-22 | 2024-11-19 | 2024-12-04 | 2024-12-10 |  | 2024-12-18 | 2025-01-06 | Office 12.04.2025 | 2025-01-22 |  | 2025-01-07 | 2025-04-09 | 2025-04-09 | 2025-07-21 | 2025-07-21 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-200 | System CHW and LTHW FIRST FLOOR
70559 | FSA_F02_1-CHWS-222-DN020-I16C00 | 0 | false | 6.96 | FSA_F02_1-CHWS-222-DN020-I16C00 | LPP6A-M-513-01-FSA | 1129 | FSA_South Side | F02 | FoamInside | TBH-ZAT-2024-11-22 | 2024-11-19 |  |  | To be revised do to wrong height | [10 empty] | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-300
70560 | FSA_F02_1-CHWS-223-DN020-I16C00 | 0 | false | 12.26 | FSA_F02_1-CHWS-223-DN020-I16C00 | LPP6A-M-513-01-FSA | 1129 | FSA_South Side | F02 | FoamInside | TBH-ZAT-2024-11-22 | 2024-11-19 |  |  | To be revised do to wrong height | [10 empty] | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-301
70561 | FSA_F02_1-CHWS-224-DN020-I16C00 | 0 | true | 16.83 | FSA_F02_1-CHWS-224-DN020-I16C00 | LPP6A-M-513-01-FSA | 1129 | FSA_South Side | F02 | FoamInside | TBH-ZAT-2024-11-22 | 2024-11-19 | 2024-11-26 | 2024-12-10 |  | 2024-12-18 | 2024-12-29 | Office 15.03.2025 | 2025-01-22 |  | 2025-01-06 | 2025-03-03 | 2025-03-06 | 2025-03-14 | 2025-03-22 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 24.12.2024 00:00:00 | 2-301 | System CHW and LTHW FIRST FLOOR
70562 | FSA_F02_1-CHWS-225-DN020-I16C00 | 0 | true | 29.89 | FSA_F02_1-CHWS-225-DN020-I16C00 | LPP6A-M-513-01-FSA | 1129 | FSA_South Side | F02 | FoamInside | TBH-ZAT-2024-11-22 | 2024-11-19 | 2024-12-08 | 2024-12-10 |  | 2024-12-18 | 2025-01-13 | Office 20.03.2025 | 2025-01-22 |  | 2025-01-22 | 2025-03-10 | 2025-03-11 | 2025-03-20 | 2025-03-20 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 25.12.2024 00:00:00 | 2-200 | System CHW and LTHW FIRST FLOOR
70563 | FSA_F02_1-CHWS-226-DN020-I16C00 | 0 | false | 29 | FSA_F02_1-CHWS-226-DN020-I16C00 | LPP6A-M-513-01-FSA | 1129 | FSA_South Side | F02 | FoamInside | TBH-ZAT-2024-11-22 | 2024-11-19 |  |  | To be revised do to wrong height | [10 empty] | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-210
70564 | FSA_F02_1-CHWS-227-DN020-I16C00 | 0 | false | 20.98 | FSA_F02_1-CHWS-227-DN020-I16C00 | LPP6A-M-513-01-FSA | 1129 | FSA_South Side | F02 | FoamInside | TBH-ZAT-2024-11-22 | 2024-11-19 |  |  | To be revised do to wrong height | [10 empty] | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-211
70565 | FSA_F02_1-CHWS-228-DN020-I16C00 | 0 | true | 8.9 | FSA_F02_1-CHWS-228-DN020-I16C00 | LPP6A-M-513-01-FSA | 1129 | FSA_South Side | F02 | FoamInside | TBH-ZAT-2024-11-22 | 2024-11-19 | 2024-11-26 | 2024-12-10 |  | 2024-12-18 | 2025-01-06 | Office 18.03.2025 | 2025-01-22 |  | 2025-01-07 | 2025-03-15 | 2025-03-15 | 2025-03-17 | 2025-03-17 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-211 | System CHW and LTHW FIRST FLOOR
70566 | FSA_F02_1-CHWS-232-DN020-I16C00 | 0 | true | 1.58 | FSA_F02_1-CHWS-232-DN020-I16C00 | LPP6A-M-513-01-FSA | 1129 | FSA_South Side | F02 | FoamInside | TBH-ZAT-2024-11-22 | 2024-11-19 | 2024-11-26 | 2024-12-10 |  | 2024-12-11 | 2024-12-18 | Office 12.04.2025 | 2025-01-07 |  | 2024-12-19 | 2025-04-03 | 2025-04-03 | 2025-07-21 | 2025-07-21 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-200 | System CHW and LTHW FIRST FLOOR
70567 | FSA_F02_1-CHWS-236-DN020-I16C00 | 0 | true | 1.55 | FSA_F02_1-CHWS-236-DN020-I16C00 | LPP6A-M-513-01-FSA | 1129 | FSA_South Side | F02 | FoamInside | TBH-ZAT-2024-11-22 | 2024-11-19 | 2024-12-09 | 2024-12-10 |  | 2024-12-11 | 2024-12-18 | Office 12.04.2025 | 2025-01-07 |  | 2024-12-19 | 2025-04-02 | 2025-04-03 | 2025-07-21 |  | 1359 | 193 | Install of FCU on hold |  |  | 194 | SEP | SEP | [5 empty] | 2-200 | System CHW and LTHW FIRST FLOOR
70568 | FSA_F02_1-CHWS-243-DN020-I16C00 | 0 | true | 1.41 | FSA_F02_1-CHWS-243-DN020-I16C00 | LPP6A-M-513-01-FSA | 1129 | FSA_South Side | F02 | FoamInside | TBH-ZAT-2024-11-22 | 2024-11-19 | 2024-11-27 | 2024-12-10 |  | 2024-12-11 | 2024-12-18 | Office 12.04.2025 | 2025-01-07 |  | 2024-12-19 | 2025-04-02 | 2025-04-02 | 2025-07-21 | 2025-07-21 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-200 | System CHW and LTHW FIRST FLOOR
70569 | FSA_F02_1-LTHWR-008-DN100-I16C00 | 0 | false | 60.82 | FSA_F02_1-LTHWR-008-DN100-I16C00 | LPP6A-M-518-01-FSA | 1129 | FSA Corridor | F02 | FoamInside | TBH-ZAT-2024-11-22 | 2024-11-19 | [13 empty] | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-200
70570 | FSA_F02_1-LTHWR-009-DN100-I16C00 | 0 | true | 12.41 | FSA_F02_1-LTHWR-009-DN100-I16C00 | LPP6A-M-518-01-FSA | 1129 | FSA Corridor | F02 | FoamInside | TBH-ZAT-2024-11-22 | 2024-11-19 | 2024-11-25 | 2024-12-03 |  | 2024-12-08 | 2024-12-18 | Office 09.04.2025 | 2025-01-07 |  | 2024-12-19 | 2025-03-19 | 2025-03-20 | 2025-03-20 | 2025-05-29 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2024-01-12 | 2-200 | System CHW and LTHW GROUND FLOOR/System CHW and LTHW FIRST FLOOR
70571 | FSA_F02_1-LTHWR-209-DN020-I16C00 | 0 | true | 1.76 | FSA_F02_1-LTHWR-209-DN020-I16C00 | LPP6A-M-518-01-FSA | 1129 | FSA_South Side | F02 | FoamInside | TBH-ZAT-2024-11-22 | 2024-11-19 | 2024-12-05 | 2024-12-10 |  | 2024-12-11 | 2024-12-18 | Office 15.01.2025 | 2025-01-07 |  | 2024-12-19 | 2025-04-08 | 2025-04-08 | 2025-07-21 | 2025-07-21 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-200 | System CHW and LTHW FIRST FLOOR
70572 | FSA_F02_1-LTHWR-221-DN020-I16C00 | 0 | true | 6.13 | FSA_F02_1-LTHWR-221-DN020-I16C00 | LPP6A-M-518-01-FSA | 1129 | FSA_South Side | F02 | FoamInside | TBH-ZAT-2024-11-22 | 2024-11-19 | 2024-12-05 | 2024-12-10 |  | 2024-12-18 | 2025-01-06 | Office 12.04.2025 | 2025-01-22 |  | 2025-01-07 | 2025-04-08 | 2025-04-09 | 2025-07-21 | 2025-07-21 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-200 | System CHW and LTHW FIRST FLOOR
70573 | FSA_F02_1-LTHWR-222-DN015-I16C00 | 0 | false | 5.88 | FSA_F02_1-LTHWR-222-DN015-I16C00 | LPP6A-M-518-01-FSA | 1129 | FSA_South Side | F02 | FoamInside | TBH-ZAT-2024-11-22 | 2024-11-19 |  |  | To be revised do to wrong height | [10 empty] | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-300
70574 | FSA_F02_1-LTHWR-223-DN020-I16C00 | 0 | false | 11.77 | FSA_F02_1-LTHWR-223-DN020-I16C00 | LPP6A-M-518-01-FSA | 1129 | FSA_South Side | F02 | FoamInside | TBH-ZAT-2024-11-22 | 2024-11-19 |  |  | To be revised do to wrong height | [10 empty] | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-301
70575 | FSA_F02_1-LTHWR-224-DN020-I16C00 | 0 | true | 17.23 | FSA_F02_1-LTHWR-224-DN020-I16C00 | LPP6A-M-518-01-FSA | 1129 | FSA_South Side | F02 | FoamInside | TBH-ZAT-2024-11-22 | 2024-11-19 | 2024-12-09 | 2024-12-10 |  | 2024-12-18 | 2025-01-06 | Office 15.03.2025 | 2025-01-22 |  | 2025-01-07 | 2025-03-04 | 2025-03-06 | 2025-03-14 | 2025-03-22 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-301 | System CHW and LTHW FIRST FLOOR
70576 | FSA_F02_1-LTHWR-225-DN020-I16C00 | 0 | true | 28.19 | FSA_F02_1-LTHWR-225-DN020-I16C00 | LPP6A-M-518-01-FSA | 1129 | FSA_South Side | F02 | FoamInside | TBH-ZAT-2024-11-22 | 2024-11-19 | 2024-11-26 | 2024-12-10 |  | 2024-12-18 | 2024-12-29 | Office 20.03.2025 | 2025-01-22 |  | 2025-01-06 | 2025-03-10 | 2025-03-11 | 2025-03-13 | 2025-03-13 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 25.12.2024 00:00:00 | 2-200 | System CHW and LTHW FIRST FLOOR
70577 | FSA_F02_1-LTHWR-226-DN020-I16C00 | 0 | false | 28.91 | FSA_F02_1-LTHWR-226-DN020-I16C00 | LPP6A-M-518-01-FSA | 1129 | FSA_South Side | F02 | FoamInside | TBH-ZAT-2024-11-22 | 2024-11-19 |  |  | To be revised do to wrong height | [10 empty] | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-210
70578 | FSA_F02_1-LTHWR-227-DN020-I16C00 | 0 | false | 20.12 | FSA_F02_1-LTHWR-227-DN020-I16C00 | LPP6A-M-518-01-FSA | 1129 | FSA_South Side | F02 | FoamInside | TBH-ZAT-2024-11-22 | 2024-11-19 |  |  | To be revised do to wrong height | [10 empty] | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-211
70579 | FSA_F02_1-LTHWR-228-DN015-I16C00 | 0 | true | 8.93 | FSA_F02_1-LTHWR-228-DN015-I16C00 | LPP6A-M-518-01-FSA | 1129 | FSA_South Side | F02 | FoamInside | TBH-ZAT-2024-11-22 | 2024-11-19 | 2024-11-26 | 2024-12-10 |  | 2024-12-11 | 2024-12-22 | Office 18.03.2025 | 2025-01-07 |  | 2024-12-22 | 2025-03-15 | 2025-03-15 | 2025-03-17 | 2025-03-17 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-211 | System CHW and LTHW FIRST FLOOR
70580 | FSA_F02_1-LTHWR-232-DN020-I16C00 | 0 | true | 2.28 | FSA_F02_1-LTHWR-232-DN020-I16C00 | LPP6A-M-518-01-FSA | 1129 | FSA_South Side | F02 | FoamInside | TBH-ZAT-2024-11-22 | 2024-11-19 | 2024-12-09 | 2024-12-10 |  | 2024-12-11 | 2024-12-18 | Office 12.04.2025 | 2025-01-07 |  | 2024-12-19 | 2025-04-03 | 2025-04-03 | 2025-07-21 | 2025-07-21 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-200 | System CHW and LTHW FIRST FLOOR
70581 | FSA_F02_1-LTHWR-236-DN020-I16C00 | 0 | true | 2.35 | FSA_F02_1-LTHWR-236-DN020-I16C00 | LPP6A-M-518-01-FSA | 1129 | FSA_South Side | F02 | FoamInside | TBH-ZAT-2024-11-22 | 2024-11-19 | 2024-12-09 | 2024-12-10 |  | 2024-12-11 | 2024-12-18 | Office 12.04.2025 | 2025-01-07 |  | 2024-12-19 | 2025-04-01 | 2025-04-01 | 2025-07-21 |  | 1360 | 193 | Install of FCU on hold |  |  | 194 | SEP | SEP | [5 empty] | 2-200 | System CHW and LTHW FIRST FLOOR
70582 | FSA_F02_1-LTHWR-243-DN020-I16C00 | 0 | true | 0.87 | FSA_F02_1-LTHWR-243-DN020-I16C00 | LPP6A-M-518-01-FSA | 1129 | FSA_South Side | F02 | FoamInside | TBH-ZAT-2024-11-22 | 2024-11-19 | 2024-12-09 | 2024-12-10 |  | 2024-12-11 | 2024-12-18 | Office 12.04.2025 | 2025-01-07 |  | 2024-12-19 | 2025-04-02 | 2025-04-02 | 2025-07-21 | 2025-07-21 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-200 | System CHW and LTHW FIRST FLOOR
70583 | FSA_F02_1-LTHWS-008-DN100-I16C00 | 0 | false | 60.57 | FSA_F02_1-LTHWS-008-DN100-I16C00 | LPP6A-M-518-01-FSA | 1129 | FSA Corridor | F02 | FoamInside | TBH-ZAT-2024-11-22 | 2024-11-19 | [13 empty] | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-200
70584 | FSA_F02_1-LTHWS-009-DN100-I16C00 | 0 | true | 12.12 | FSA_F02_1-LTHWS-009-DN100-I16C00 | LPP6A-M-518-01-FSA | 1129 | FSA Corridor | F02 | FoamInside | TBH-ZAT-2024-11-22 | 2024-11-19 | 2024-11-26 | 2024-12-03 |  | 2024-12-08 | 2024-12-18 | Office 09.04.2025 | 2025-01-07 |  | 2024-12-19 | 2025-03-19 | 2025-03-21 | 2025-03-21 | 2025-05-29 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2024-01-12 | 2-200 | System CHW and LTHW GROUND FLOOR/System CHW and LTHW FIRST FLOOR
70585 | FSA_F02_1-LTHWS-209-DN020-I16C00 | 0 | true | 2.05 | FSA_F02_1-LTHWS-209-DN020-I16C00 | LPP6A-M-518-01-FSA | 1129 | FSA_South Side | F02 | FoamInside | TBH-ZAT-2024-11-22 | 2024-11-19 | 2024-12-05 | 2024-12-10 |  | 2024-12-11 | 2024-12-18 | Office 15.01.2025 | 2025-01-07 |  | 2024-12-19 | 2025-04-08 | 2025-04-26 | 2025-07-21 | 2025-07-21 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-200 | System CHW and LTHW FIRST FLOOR
70586 | FSA_F02_1-LTHWS-221-DN020-I16C00 | 0 | true | 6.04 | FSA_F02_1-LTHWS-221-DN020-I16C00 | LPP6A-M-518-01-FSA | 1129 | FSA_South Side | F02 | FoamInside | TBH-ZAT-2024-11-22 | 2024-11-19 | 2024-12-05 | 2024-12-10 |  | 2024-12-18 | 2025-01-06 | Office 12.04.2025 | 2025-01-22 |  | 2025-01-07 | 2025-04-09 | 2025-04-09 | 2025-07-21 | 2025-07-21 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-200 | System CHW and LTHW FIRST FLOOR
70587 | FSA_F02_1-LTHWS-222-DN015-I16C00 | 0 | false | 5.85 | FSA_F02_1-LTHWS-222-DN015-I16C00 | LPP6A-M-518-01-FSA | 1129 | FSA_South Side | F02 | FoamInside | TBH-ZAT-2024-11-22 | 2024-11-19 |  |  | To be revised do to wrong height | [10 empty] | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-300
70588 | FSA_F02_1-LTHWS-223-DN020-I16C00 | 0 | false | 11.4 | FSA_F02_1-LTHWS-223-DN020-I16C00 | LPP6A-M-518-01-FSA | 1129 | FSA_South Side | F02 | FoamInside | TBH-ZAT-2024-11-22 | 2024-11-19 |  |  | To be revised do to wrong height | [10 empty] | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-301
70589 | FSA_F02_1-LTHWS-224-DN020-I16C00 | 0 | true | 17.23 | FSA_F02_1-LTHWS-224-DN020-I16C00 | LPP6A-M-518-01-FSA | 1129 | FSA_South Side | F02 | FoamInside | TBH-ZAT-2024-11-22 | 2024-11-19 | 2024-12-08 | 2024-12-10 |  | 2024-12-18 | 2025-01-08 | Office 15.03.2025 | 2025-01-29 |  | 2025-01-09 | 2025-03-03 | 2025-03-06 | 2025-03-14 | 2025-03-22 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 24.12.2024 00:00:00 | 2-301 | System CHW and LTHW FIRST FLOOR
70590 | FSA_F02_1-LTHWS-225-DN020-I16C00 | 0 | true | 28.57 | FSA_F02_1-LTHWS-225-DN020-I16C00 | LPP6A-M-518-01-FSA | 1129 | FSA_South Side | F02 | FoamInside | TBH-ZAT-2024-11-22 | 2024-11-19 | 2024-12-08 | 2024-12-10 |  | 2024-12-18 | 2025-01-12 | Office 20.03.2025 | 2025-01-22 |  | 2025-01-12 | 2025-03-10 | 2025-03-12 | 2025-03-20 | 2025-03-20 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-200 | System CHW and LTHW FIRST FLOOR
70591 | FSA_F02_1-LTHWS-226-DN020-I16C00 | 0 | false | 28.31 | FSA_F02_1-LTHWS-226-DN020-I16C00 | LPP6A-M-518-01-FSA | 1129 | FSA_South Side | F02 | FoamInside | TBH-ZAT-2024-11-22 | 2024-11-19 |  |  | To be revised do to wrong height | [10 empty] | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-210
70592 | FSA_F02_1-LTHWS-227-DN020-I16C00 | 0 | false | 20.49 | FSA_F02_1-LTHWS-227-DN020-I16C00 | LPP6A-M-518-01-FSA | 1129 | FSA_South Side | F02 | FoamInside | TBH-ZAT-2024-11-22 | 2024-11-19 |  |  | To be revised do to wrong height | [10 empty] | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-211
70593 | FSA_F02_1-LTHWS-228-DN015-I16C00 | 0 | true | 8.5 | FSA_F02_1-LTHWS-228-DN015-I16C00 | LPP6A-M-518-01-FSA | 1129 | FSA_South Side | F02 | FoamInside | TBH-ZAT-2024-11-22 | 2024-11-19 | 2024-12-08 | 2024-12-10 |  | 2024-12-11 | 2024-12-18 | Office 18.03.2025 | 2025-01-07 |  | 2024-12-19 | 2025-03-15 | 2025-03-15 | 2025-03-17 | 2025-03-17 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-211 | System CHW and LTHW FIRST FLOOR
70594 | FSA_F02_1-LTHWS-232-DN020-I16C00 | 0 | true | 1.64 | FSA_F02_1-LTHWS-232-DN020-I16C00 | LPP6A-M-518-01-FSA | 1129 | FSA_South Side | F02 | FoamInside | TBH-ZAT-2024-11-22 | 2024-11-19 | 2024-12-09 | 2024-12-10 |  | 2024-12-12 | 2024-12-22 | Office 12.04.2025 | 2025-01-07 |  | 2024-12-22 | 2025-04-03 | 2025-04-03 | 2025-07-21 | 2025-07-21 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-200 | System CHW and LTHW FIRST FLOOR
70595 | FSA_F02_1-LTHWS-236-DN020-I16C00 | 0 | true | 1.68 | FSA_F02_1-LTHWS-236-DN020-I16C00 | LPP6A-M-518-01-FSA | 1129 | FSA_South Side | F02 | FoamInside | TBH-ZAT-2024-11-22 | 2024-11-19 | 2024-12-09 | 2024-12-10 |  | 2024-12-12 | 2024-12-18 | Office 12.04.2025 | 2025-01-07 |  | 2024-12-19 | 2025-04-01 | 2025-04-01 | 2025-07-21 |  | 1360 | 193 | Install of FCU on hold |  |  | 194 | SEP | SEP | [5 empty] | 2-200 | System CHW and LTHW FIRST FLOOR
70596 | FSA_F02_1-LTHWS-243-DN020-I16C00 | 0 | true | 0.69 | FSA_F02_1-LTHWS-243-DN020-I16C00 | LPP6A-M-518-01-FSA | 1129 | FSA_South Side | F02 | FoamInside | TBH-ZAT-2024-11-22 | 2024-11-19 | 2024-12-08 | 2024-12-10 |  | 2024-12-12 | 2024-12-18 | Office 12.04.2025 | 2025-01-07 |  | 2024-12-19 | 2025-04-02 | 2025-04-02 | 2025-07-21 | 2025-07-21 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-200 | System CHW and LTHW FIRST FLOOR
70597 | FSA_F02_1-PCWR-007-DN025-I16C00 | 0 | true | 10.4 | FSA_F02_1-PCWR-007-DN025-I16C00 | LPP6A-M-503-01-DH | 1129 | To Coupon Rack | F02 | N/A | TBH-ZAT-2024-11-22 | 2024-11-19 | 2024-11-28 | 2024-12-10 |  | 2024-12-12 | 2024-12-22 | Office 31.03.2025 | 2025-01-07 |  | 2024-12-22 | 2025-03-25 | 2025-03-25 | 2025-03-26 | 2025-03-26 | 1352 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-200 | System PCW 01
70598 | FSA_F02_1-PCWR-009-DN250-I16C00 | 0 | false | 53.24 | FSA_F02_1-PCWR-009-DN250-I16C00 | LPP6A-M-503-01-DH | 1129 | FSA Corridor | F02 | N/A | TBH-ZAT-2024-11-22 | 2024-11-19 |  | 2024-11-30 | [11 empty] | 1352 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-223
70599 | FSA_F02_1-PCWR-010-DN250-I16C00 | 0 | false | 32.83 | FSA_F02_1-PCWR-010-DN250-I16C00 | LPP6A-M-503-01-DH | 1129 | FSA Corridor | F02 | N/A | TBH-ZAT-2024-11-22 | 2024-11-19 | [13 empty] | 1352 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-200
70600 | FSA_F02_1-PCWR-013-DN150-I16C00 | 0 | true | 77.48 | FSA_F02_1-PCWR-013-DN150-I16C00 | LPP6A-M-503-01-DH | 1129 | FSA Corridor | F02 | N/A | TBH-ZAT-2024-11-22 | 2024-11-19 | 2024-11-26 | 2024-12-03 |  | 2024-12-10 | 2024-12-18 | Office 14.05.2025 | 2025-01-07 |  | 2024-12-19 | 2025-02-08 | 2025-02-17 | 2025-03-22 | 2025-03-22 | 1352 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2024-01-12 | 2-200 | System PCW 02
70601 | FSA_F02_1-PCWR-014-DN100-I16C00 | 1 | true | 21.59 | FSA_F02_1-PCWR-014-DN100-I16C00 | LPP6A-M-544-XX-FSA | 1129 | CCNR AHU Room | F02 | N/A | TBH-ZAT-2024-11-22 | 2024-11-19 | 2024-11-26 | 2024-12-10 |  | 2024-12-23 | 2025-01-22 | Office 10.04.2025 | 2025-01-29 |  | 2025-01-23 | 2025-03-07 | 2025-03-22 | 2025-03-22 | 2025-05-30 | 1352 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2024-02-12 | 2-212 | System PCW 02
70602 | FSA_F02_1-PCWR-015-DN100-I16C00 | 1 | true | 21.71 | FSA_F02_1-PCWR-015-DN100-I16C00 | LPP6A-M-544-XX-FSA | 1129 | CCNR AHU Room | F02 | N/A | TBH-ZAT-2024-11-22 | 2024-11-19 | 2024-11-28 | 2024-12-10 |  | 2025-01-05 | 2025-01-22 | Office 10.04.2025 | 2025-01-29 |  | 2025-01-23 | 2025-03-07 | 2025-03-22 | 2025-03-22 | 2025-05-30 | 1352 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2024-02-12 | 2-213 | System PCW 02
70603 | FSA_F02_1-PCWR-016-DN100-I16C00 | 1 | true | 21.64 | FSA_F02_1-PCWR-016-DN100-I16C00 | LPP6A-M-544-XX-FSA | 1129 | CCNR AHU Room | F02 | N/A | TBH-ZAT-2024-11-22 | 2024-11-19 | 2024-11-28 | 2024-12-10 |  | 2025-01-06 | 2025-01-23 | Office 10.04.2025 | 2025-01-29 |  | 2025-01-23 | 2025-03-07 | 2025-03-22 | 2025-03-22 | 2025-05-30 | 1352 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2024-02-12 | 2-213 | System PCW 02
70604 | FSA_F02_1-PCWR-017-DN100-I16C00 | 1 | true | 22.45 | FSA_F02_1-PCWR-017-DN100-I16C00 | LPP6A-M-544-XX-FSA | 1129 | CCNR AHU Room | F02 | N/A | TBH-ZAT-2024-11-22 | 2024-11-19 | 2024-11-28 | 2024-11-30 |  | 2025-01-06 | 2025-01-26 | Office 10.04.2025 | 2025-01-29 |  | 2025-01-27 | 2025-03-12 | 2025-03-22 | 2025-03-22 | 2025-05-30 | 1352 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2024-02-12 | 2-212 | System PCW 02
70605 | FSA_F02_1-PCWR-018-DN065-I16C00 | 1 | true | 10.63 | FSA_F02_1-PCWR-018-DN065-I16C00 | LPP6A-M-544-XX-FSA | 1129 | CCNR AHU Room | F02 | N/A | TBH-ZAT-2024-11-22 | 2024-11-19 | 2024-12-10 | 2024-12-10 |  | 2024-12-11 | 2025-02-03 | Office 02.04.2025 | 2025-02-05 |  | 2025-02-06 | 2025-03-18 | 2025-03-19 | 2025-03-22 | 2025-03-29 | 1352 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2024-05-12 | 2-212 | System PCW 02
70606 | FSA_F02_1-PCWR-019-DN065-I16C00 | 1 | true | 10.72 | FSA_F02_1-PCWR-019-DN065-I16C00 | LPP6A-M-544-XX-FSA | 1129 | CCNR AHU Room | F02 | N/A | TBH-ZAT-2024-11-22 | 2024-11-19 | 2024-12-10 | 2024-12-10 |  | 2024-12-11 | 2025-01-13 | Office 02.04.2025 | 2025-01-29 |  | 2025-01-26 | 2025-03-17 | 2025-03-22 | 2025-03-22 | 2025-03-28 | 1352 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2024-05-12 | 2-213 | System PCW 02
70607 | FSA_F02_1-PCWR-020-DN065-I16C00 | 1 | true | 10.61 | FSA_F02_1-PCWR-020-DN065-I16C00 | LPP6A-M-544-XX-FSA | 1129 | CCNR AHU Room | F02 | N/A | TBH-ZAT-2024-11-22 | 2024-11-19 | 2024-12-10 | 2024-12-10 |  | 2024-12-11 | 2025-01-13 | Office 02.04.2025 | 2025-01-29 |  | 2025-01-26 | 2025-03-17 | 2025-03-22 | 2025-03-22 | 2025-03-29 | 1352 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2024-05-12 | 2-213 | System PCW 02
70608 | FSA_F02_1-PCWR-021-DN065-I16C00 | 1 | true | 11.19 | FSA_F02_1-PCWR-021-DN065-I16C00 | LPP6A-M-544-XX-FSA | 1129 | CCNR AHU Room | F02 | N/A | TBH-ZAT-2024-11-22 | 2024-11-19 | 2024-12-10 | 2024-11-30 |  | 2024-12-11 | 2025-01-13 | Office 02.04.2025 | 2025-01-29 |  | 2025-01-26 | 2025-03-18 | 2025-03-22 | 2025-03-22 | 2025-03-31 | 1352 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2024-05-12 | 2-212 | System PCW 02
70609 | FSA_F02_1-PCWS-007-DN025-I16C00 | 0 | true | 10.71 | FSA_F02_1-PCWS-007-DN025-I16C00 | LPP6A-M-503-01-DH | 1129 | To Coupon Rack | F02 | N/A | TBH-ZAT-2024-11-22 | 2024-11-19 | 2024-11-28 | 2024-12-10 |  | 2024-12-11 | 2024-12-22 | Office 31.03.2025 | 2025-01-07 |  | 2024-12-22 | 2025-03-25 | 2025-03-25 | 2025-03-26 | 2025-03-26 | 1352 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-200 | System PCW 01
70610 | FSA_F02_1-PCWS-008-DN150-I16C00 | 0 | true | 76.76 | FSA_F02_1-PCWS-008-DN150-I16C00 | LPP6A-M-503-01-DH | 1129 | FSA Corridor | F02 | N/A | TBH-ZAT-2024-11-22 | 2024-11-19 | 2024-11-26 | 2024-12-03 |  | 2024-12-10 | 2024-12-18 | Office 14.05.2025 | 2025-01-07 |  | 2024-12-19 | 2025-02-11 | 2025-02-15 | 2025-02-28 | 2025-05-13 | 1352 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2024-01-12 | 2-200 | System PCW 02
70611 | FSA_F02_1-PCWS-009-DN100-I16C00 | 1 | true | 19.47 | FSA_F02_1-PCWS-009-DN100-I16C00 | LPP6A-M-544-XX-FSA | 1129 | CCNR AHU Room | F02 | N/A | TBH-ZAT-2024-11-22 | 2024-11-19 | 2024-11-28 | 2024-12-10 |  | 2024-12-23 | 2025-01-19 | Office 10.04.2025 | 2025-01-29 |  | 2025-01-22 | 2025-03-07 | 2025-03-22 | 2025-03-22 | 2025-05-30 | 1352 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2024-02-12 | 2-213 | System PCW 02
70612 | FSA_F02_1-PCWS-010-DN100-I16C00 | 1 | true | 19.6 | FSA_F02_1-PCWS-010-DN100-I16C00 | LPP6A-M-544-XX-FSA | 1129 | CCNR AHU Room | F02 | N/A | TBH-ZAT-2024-11-22 | 2024-11-19 | 2024-11-28 | 2024-12-10 |  | 2025-01-05 | 2025-01-23 | Office 10.04.2025 | 2025-01-29 |  | 2025-01-23 | 2025-03-07 | 2025-03-22 | 2025-03-22 | 2025-05-30 | 1352 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2024-02-12 | 2-213 | System PCW 02
70613 | FSA_F02_1-PCWS-011-DN100-I16C00 | 1 | true | 19.42 | FSA_F02_1-PCWS-011-DN100-I16C00 | LPP6A-M-544-XX-FSA | 1129 | CCNR AHU Room | F02 | N/A | TBH-ZAT-2024-11-22 | 2024-11-19 | 2024-11-28 | 2024-12-10 |  | 2025-01-06 | 2025-01-26 | Office 10.04.2025 | 2025-01-29 |  | 2025-01-27 | 2025-03-07 | 2025-03-22 | 2025-03-22 | 2025-05-30 | 1352 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2024-02-12 | 2-212 | System PCW 02
70614 | FSA_F02_1-PCWS-012-DN100-I16C00 | 1 | true | 20.36 | FSA_F02_1-PCWS-012-DN100-I16C00 | LPP6A-M-544-XX-FSA | 1129 | CCNR AHU Room | F02 | N/A | TBH-ZAT-2024-11-22 | 2024-11-19 | 2024-11-26 | 2024-12-10 |  | 2025-01-06 | 2025-01-26 | Office 10.04.2025 | 2025-01-29 |  | 2025-01-27 | 2025-03-22 | 2025-03-24 | 2025-03-31 | 2025-05-30 | 1352 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2024-02-12 | 2-212 | System PCW 02
70615 | FSA_F02_1-PCWS-013-DN065-I16C00 | 1 | true | 13.3 | FSA_F02_1-PCWS-013-DN065-I16C00 | LPP6A-M-544-XX-FSA | 1129 | CCNR AHU Room | F02 | N/A | TBH-ZAT-2024-11-22 | 2024-11-19 | 2024-12-11 | 2024-12-10 |  | 2025-01-07 | 2025-02-03 | Office 02.04.2025 | 2025-02-05 |  | 2025-02-06 | 2025-03-18 | 2025-03-19 | 2025-03-22 | 2025-03-28 | 1352 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2024-05-12 | 2-212 | System PCW 02
70616 | FSA_F02_1-PCWS-014-DN065-I16C00 | 1 | true | 13.39 | FSA_F02_1-PCWS-014-DN065-I16C00 | LPP6A-M-544-XX-FSA | 1129 | CCNR AHU Room | F02 | N/A | TBH-ZAT-2024-11-22 | 2024-11-19 | 2024-12-11 | 2024-12-10 |  | 2025-01-07 | 2025-02-03 | Office 02.04.2025 | 2025-02-05 |  | 2025-02-06 | 2025-03-19 | 2025-03-20 | 2025-03-22 | 2025-05-30 | 1352 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2024-05-12 | 2-213 | System PCW 02
70617 | FSA_F02_1-PCWS-015-DN065-I16C00 | 1 | true | 13.3 | FSA_F02_1-PCWS-015-DN065-I16C00 | LPP6A-M-544-XX-FSA | 1129 | CCNR AHU Room | F02 | N/A | TBH-ZAT-2024-11-22 | 2024-11-19 | 2024-12-11 | 2024-12-10 |  | 2025-01-07 | 2025-02-03 | Office 02.04.2025 | 2025-02-05 |  | 2025-02-06 | 2025-03-19 | 2025-03-20 | 2025-03-22 | 2025-03-29 | 1352 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2024-05-12 | 2-213 | System PCW 02
70618 | FSA_F02_1-PCWS-016-DN065-I16C00 | 1 | true | 13.44 | FSA_F02_1-PCWS-016-DN065-I16C00 | LPP6A-M-544-XX-FSA | 1129 | CCNR AHU Room | F02 | N/A | TBH-ZAT-2024-11-22 | 2024-11-19 | 2024-12-11 | 2024-12-10 |  | 2025-01-07 | 2025-02-03 | Office 02.04.2025 | 2025-02-05 |  | 2025-02-06 | 2025-03-18 | 2025-03-22 | 2025-03-22 | 2025-05-30 | 1352 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2024-05-12 | 2-212 | System PCW 02
70619 | FSA_F02_1-PHTGR-014-DN150-I16C00 | 0 | false | 55.15 | FSA_F02_1-PHTGR-014-DN150-I16C00 | LPP6A-M-504-XX-FSA | 1129 | FSA Corridor | F02 | N/A | TBH-ZAT-2024-11-22 | 2024-11-19 | 2024-11-30 | 2024-12-03 |  | 2024-12-10 | 2024-12-15 | Office 27.02.2025 | 2025-01-07 |  | 2024-12-18 | 2025-01-31 |  |  |  | 1352 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2024-01-12 | 2-200
70620 | FSA_F02_1-PHTGS-030-DN150-I16C00 | 0 | false | 56.12 | FSA_F02_1-PHTGS-030-DN150-I16C00 | LPP6A-M-504-XX-FSA | 1129 | FSA Corridor | F02 | FoamInside | TBH-ZAT-2024-11-22 | 2024-11-19 | [13 empty] | 1368 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-200
70621 | FSA_F02_2-PCWR-009-DN250-I16C00 | 0 | true | 56.58 | FSA_F02_2-PCWR-009-DN250-I16C00 | LPP6A-M-503-01-DH | 1129 | FSA Corridor | F02 | N/A | TBH-ZAT-2024-11-22 | 2024-11-19 | 2024-11-26 | 2024-12-03 |  | 2025-01-05 | 2025-01-19 | Office 15.03.2025 | 2025-01-28 |  | 2025-01-23 | 2025-02-28 | 2025-03-06 | 2025-03-14 | 2025-03-15 | 1352 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2024-01-12 | 2-223 | System PCW 01
70622 | FSA_F02_2-PCWR-013-DN150-I16C00 | 0 | true | 59.56 | FSA_F02_2-PCWR-013-DN150-I16C00 | LPP6A-M-503-01-DH | 1129 | FSA Corridor | F02 | N/A | TBH-ZAT-2024-11-22 | 2024-11-19 | 2024-11-26 | 2024-12-03 |  | 2024-12-10 | 2024-12-15 | Office 18.03.2025 | 2025-01-07 |  | 2024-12-18 | 2025-03-04 | 2025-03-08 | 2025-03-14 | 2025-03-18 | 1352 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2024-01-12 | 2-223 | System PCW 02
70623 | FSA_F02_2-PCWS-008-DN150-I16C00 | 0 | true | 58.79 | FSA_F02_2-PCWS-008-DN150-I16C00 | LPP6A-M-503-01-DH | 1129 | FSA Corridor | F02 | N/A | TBH-ZAT-2024-11-22 | 2024-11-19 | 2024-11-26 | 2024-12-03 |  | 2024-12-10 | 2024-12-18 | Office 18.03.2025 | 2025-01-07 |  | 2024-12-19 | 2025-03-04 | 2025-03-08 | 2025-03-17 | 2025-03-18 | 1352 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2024-01-12 | 2-223 | System PCW 02
70629 | EB_F01-PHTGR-005-DN200-I16C00_R1 | 1 | false | 29.31 | EB_F01-PHTGR-005-DN200-I16C00_R1 | LPP6A-M-504-XX-FSA | 1129 | EB | F01 | FoamOutside | TBH-ZAT-2024-11-26 | 2024-11-23 | 2024-11-27 | 2024-12-03 |  | 2025-01-05 | 2025-01-15 |  | 2025-01-29 |  | 2025-01-19 |  |  |  |  | 1368 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2024-01-12 | 1-306
70630 | EB_F01-PHTGS-006-DN200-I16C00_R1 | 1 | false | 29.59 | EB_F01-PHTGS-006-DN200-I16C00_R1 | LPP6A-M-504-XX-FSA | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-11-26 | 2024-11-23 | 2024-11-27 | 2024-12-03 |  | 2025-01-05 | 2025-01-15 |  | 2025-01-29 |  | 2025-01-19 |  |  |  |  | 1368 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2024-01-12 | 1-306
70631 | FSA_F02_1-CHWR-005-DN150-I16C00_R1 | 1 | false | 59.75 | FSA_F02_1-CHWR-005-DN150-I16C00_R1 | LPP6A-M-513-01-FSA | 1129 | FSA Corridor | F02 | FoamInside | TBH-ZAT-2024-11-26 | 2024-11-23 | 2024-11-27 | 2024-12-03 |  | 2024-12-10 | 2024-12-18 | Office 26.02.2025 | 2025-01-07 |  | 2024-12-19 | 2025-02-20 | 2025-02-22 | 2025-02-25 |  | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2024-01-12 | 2-200
91483 | FSA_F02_1-CHWR-005-DN150-I16C00_R1 | 1 | false | 59.75 | FSA_F02_1-CHWR-005-DN150-I16C00_R1 | LPP6A-M-513-01-FSA | 1129 | FSA Corridor | F02 | FoamInside | TBH-ZAT-2025-01-24 | 2025-01-22 | 2024-11-27 | 2024-12-03 |  | 2024-12-10 | 2024-12-18 | Office 11.04.2025 | 2025-01-07 |  | 2024-12-19 |  |  |  |  | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-200
70632 | FSA_F02_1-CHWR-222-DN020-I16C00_R1 | 1 | true | 6.43 | FSA_F02_1-CHWR-222-DN020-I16C00_R1 | LPP6A-M-513-01-FSA | 1129 | FSA_South Side | F02 | FoamInside | TBH-ZAT-2024-11-26 | 2024-11-23 | 2024-12-04 | 2024-12-10 |  | 2024-12-22 | 2025-01-08 | Office 17.03.2025 | 2025-01-29 |  | 2025-01-09 | 2025-03-03 | 2025-03-17 | 2025-03-19 | 2025-03-19 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 24.12.2024 00:00:00 | 2-300 | System CHW and LTHW FIRST FLOOR
70633 | FSA_F02_1-CHWR-223-DN020-I16C00_R1 | 1 | true | 12.15 | FSA_F02_1-CHWR-223-DN020-I16C00_R1 |  | 1129 | FSA_South Side | F02 | FoamInside | TBH-ZAT-2024-11-26 | 2024-11-23 | 2024-12-09 | 2024-12-10 |  | 2024-12-22 | 2025-01-09 | Office 15.03.2025 | 2025-01-22 |  | 2025-01-09 | 2025-03-05 | 2025-03-13 | 2025-03-22 | 2025-03-22 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 24.12.2024 00:00:00 | 2-301 | System CHW and LTHW FIRST FLOOR
70634 | FSA_F02_1-CHWR-226-DN020-I16C00_R1 | 1 | true | 29.1 | FSA_F02_1-CHWR-226-DN020-I16C00_R1 |  | 1129 | FSA_South Side | F02 | FoamInside | TBH-ZAT-2024-11-26 | 2024-11-23 | 2024-12-08 | 2024-12-10 |  | 2024-12-22 | 2025-01-12 | Office 20.03.2025 | 2025-01-29 |  | 2025-01-12 | 2025-03-08 | 2025-03-10 | 2025-03-18 | 2025-03-18 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 25.12.2024 00:00:00 | 2-210 | System CHW and LTHW FIRST FLOOR
70635 | FSA_F02_1-CHWR-227-DN020-I16C00_R1 | 1 | true | 20.57 | FSA_F02_1-CHWR-227-DN020-I16C00_R1 |  | 1129 | FSA_South Side | F02 | FoamInside | TBH-ZAT-2024-11-26 | 2024-11-23 | 2024-12-08 | 2024-12-10 |  | 2024-12-22 | 2025-01-06 | Office 20.03.2025 | 2025-01-22 |  | 2025-01-07 | 2025-03-08 | 2025-03-13 | 2025-03-18 | 2025-03-18 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-211 | System CHW and LTHW FIRST FLOOR
70636 | FSA_F02_1-CHWS-012-DN150-I16C00_R1 | 1 | false | 59.75 | FSA_F02_1-CHWS-012-DN150-I16C00_R1 | LPP6A-M-513-01-FSA | 1129 | FSA Corridor | F02 | FoamInside | TBH-ZAT-2024-11-26 | 2024-11-23 | 2024-11-27 | 2024-12-03 |  | 2024-12-10 | 2024-12-16 | Office 26.02.2025 | 2025-01-07 |  | 2024-12-18 | 2025-02-20 | 2025-02-22 | 2025-02-25 |  | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2024-01-12 | 2-200
91485 | FSA_F02_1-CHWS-012-DN150-I16C00_R1 | 1 | false | 59.75 | FSA_F02_1-CHWS-012-DN150-I16C00_R1 | LPP6A-M-513-01-FSA | 1129 | FSA Corridor | F02 | FoamInside | TBH-ZAT-2025-01-24 | 2025-01-22 | 2024-11-27 | 2024-12-03 |  | 2024-12-10 | 2024-12-16 |  | 2025-01-07 |  | 2024-12-18 |  |  |  |  | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-200
70637 | FSA_F02_1-CHWS-222-DN020-I16C00_R1 | 1 | true | 6.52 | FSA_F02_1-CHWS-222-DN020-I16C00_R1 | LPP6A-M-513-01-FSA | 1129 | FSA_South Side | F02 | FoamInside | TBH-ZAT-2024-11-26 | 2024-11-23 | 2024-12-04 | 2024-12-10 |  | 2024-12-22 | 2025-01-08 | Office 17.03.2025 | 2025-01-29 |  | 2025-01-09 | 2025-03-17 | 2025-03-17 | 2025-03-18 | 2025-03-18 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 24.12.2024 00:00:00 | 2-300 | System CHW and LTHW FIRST FLOOR
70638 | FSA_F02_1-CHWS-223-DN020-I16C00_R1 | 1 | true | 11.86 | FSA_F02_1-CHWS-223-DN020-I16C00_R1 |  | 1129 | FSA_South Side | F02 | FoamInside | TBH-ZAT-2024-11-26 | 2024-11-23 | 2024-11-26 | 2024-12-10 |  | 2024-12-22 | 2025-01-09 | Office 15.03.2025 | 2025-01-22 |  | 2025-01-09 | 2025-03-05 | 2025-03-13 | 2025-03-22 | 2025-03-22 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 24.12.2024 00:00:00 | 2-301 | System CHW and LTHW FIRST FLOOR
70639 | FSA_F02_1-CHWS-226-DN020-I16C00_R1 | 1 | true | 28.89 | FSA_F02_1-CHWS-226-DN020-I16C00_R1 |  | 1129 | FSA_South Side | F02 | FoamInside | TBH-ZAT-2024-11-26 | 2024-11-23 | 2024-12-08 | 2024-12-10 |  | 2024-12-22 | 2025-01-12 | Office 20.03.2025 | 2025-01-29 |  | 2025-01-12 | 2025-02-05 | 2025-03-10 | 2025-03-14 | 2025-03-14 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-210 | System CHW and LTHW FIRST FLOOR
70640 | FSA_F02_1-CHWS-227-DN020-I16C00_R1 | 1 | true | 21.06 | FSA_F02_1-CHWS-227-DN020-I16C00_R1 |  | 1129 | FSA_South Side | F02 | FoamInside | TBH-ZAT-2024-11-26 | 2024-11-23 | 2024-12-08 | 2024-12-10 |  | 2024-12-22 | 2025-01-13 | Office 20.03.2025 | 2025-01-29 |  | 2025-01-26 | 2025-03-08 | 2025-03-13 | 2025-03-19 | 2025-03-19 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 25.12.2024 00:00:00 | 2-211 | System CHW and LTHW FIRST FLOOR
70641 | FSA_F02_1-LTHWR-008-DN100-I16C00_R1 | 1 | false | 60.58 | FSA_F02_1-LTHWR-008-DN100-I16C00_R1 | LPP6A-M-518-01-FSA | 1129 | FSA_South Side | F02 | FoamInside | TBH-ZAT-2024-11-26 | 2024-11-23 | 2024-11-30 | 2024-12-03 |  | 2024-12-08 | 2025-01-07 | Dejan Todorovski 15.02.2025 | 2025-01-29 |  | 2025-01-09 |  |  |  |  | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2024-01-12 | 2-200
70642 | FSA_F02_1-LTHWR-222-DN015-I16C00_R1 | 1 | true | 5.92 | FSA_F02_1-LTHWR-222-DN015-I16C00_R1 | LPP6A-M-518-01-FSA | 1129 | FSA_South Side | F02 | FoamInside | TBH-ZAT-2024-11-26 | 2024-11-23 | 2024-12-05 | 2024-12-10 |  | 2024-12-12 | 2024-12-18 | Office 17.03.2025 | 2025-01-07 |  | 2024-12-19 | 2025-03-17 | 2025-03-17 | 2025-03-18 | 2025-03-18 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 24.12.2024 00:00:00 | 2-300 | System CHW and LTHW FIRST FLOOR
70643 | FSA_F02_1-LTHWR-223-DN020-I16C00_R1 | 1 | true | 11.81 | FSA_F02_1-LTHWR-223-DN020-I16C00_R1 |  | 1129 | FSA_South Side | F02 | FoamInside | TBH-ZAT-2024-11-26 | 2024-11-23 | 2024-11-26 | 2024-12-10 |  | 2024-12-22 | 2025-01-09 | Office 15.03.2025 | 2025-01-22 |  | 2025-01-09 | 2025-03-05 | 2025-03-13 | 2025-03-22 | 2025-03-22 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 24.12.2024 00:00:00 | 2-301 | System CHW and LTHW FIRST FLOOR
70644 | FSA_F02_1-LTHWR-226-DN020-I16C00_R1 | 1 | true | 29.11 | FSA_F02_1-LTHWR-226-DN020-I16C00_R1 |  | 1129 | FSA_South Side | F02 | FoamInside | TBH-ZAT-2024-11-26 | 2024-11-23 | 2024-11-26 | 2024-12-10 |  | 2024-12-22 | 2025-01-12 | Office 20.03.2025 | 2025-01-29 |  | 2025-01-12 | 2025-03-08 | 2025-03-10 | 2025-03-17 | 2025-03-17 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 25.12.2024 00:00:00 | 2-210 | System CHW and LTHW FIRST FLOOR
70645 | FSA_F02_1-LTHWR-227-DN020-I16C00_R1 | 1 | true | 20.23 | FSA_F02_1-LTHWR-227-DN020-I16C00_R1 |  | 1129 | FSA_South Side | F02 | FoamInside | TBH-ZAT-2024-11-26 | 2024-11-23 | 2024-11-26 | 2024-12-10 |  | 2024-12-22 | 2025-01-13 | Office 20.03.2025 | 2025-01-29 |  | 2025-01-26 | 2025-03-08 | 2025-03-13 | 2025-03-18 | 2025-03-18 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 25.12.2024 00:00:00 | 2-211 | System CHW and LTHW FIRST FLOOR
70646 | FSA_F02_1-LTHWS-008-DN100-I16C00_R1 | 1 | false | 60.57 | FSA_F02_1-LTHWS-008-DN100-I16C00_R1 | LPP6A-M-518-01-FSA | 1129 | FSA_South Side | F02 | FoamInside | TBH-ZAT-2024-11-26 | 2024-11-23 | 2024-11-30 | 2024-12-03 |  | 2024-12-08 | 2025-01-07 | Office 09.04.2025 | 2025-01-29 |  | 2025-01-09 |  |  |  |  | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2024-01-12 | 2-200
70647 | FSA_F02_1-LTHWS-222-DN015-I16C00_R1 | 1 | true | 6.11 | FSA_F02_1-LTHWS-222-DN015-I16C00_R1 | LPP6A-M-518-01-FSA | 1129 | FSA_South Side | F02 | FoamInside | TBH-ZAT-2024-11-26 | 2024-11-23 | 2024-12-05 | 2024-12-10 |  | 2024-12-11 | 2024-12-22 | Office 17.03.2025 | 2025-01-07 |  | 2024-12-22 | 2025-03-03 | 2025-03-17 | 2025-03-18 | 2025-03-18 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 24.12.2024 00:00:00 | 2-300 | System CHW and LTHW FIRST FLOOR
70648 | FSA_F02_1-LTHWS-223-DN020-I16C00_R1 | 1 | true | 11.32 | FSA_F02_1-LTHWS-223-DN020-I16C00_R1 |  | 1129 | FSA_South Side | F02 | FoamInside | TBH-ZAT-2024-11-26 | 2024-11-23 | 2024-12-09 | 2024-12-10 |  | 2024-12-22 | 2025-01-09 | Office 15.03.2025 | 2025-01-29 |  | 2025-01-09 | 2025-03-05 | 2025-03-13 | 2025-03-22 | 2025-03-22 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 24.12.2024 00:00:00 | 2-301 | System CHW and LTHW FIRST FLOOR
70649 | FSA_F02_1-LTHWS-226-DN020-I16C00_R1 | 1 | true | 28.58 | FSA_F02_1-LTHWS-226-DN020-I16C00_R1 |  | 1129 | FSA_South Side | F02 | FoamInside | TBH-ZAT-2024-11-26 | 2024-11-23 | 2024-12-08 | 2024-12-10 |  | 2024-12-22 | 2025-01-29 | Office 20.03.2025 | 2025-02-05 |  | 2025-01-29 | 2025-03-08 | 2025-03-10 | 2025-03-17 | 2025-03-17 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 25.12.2024 00:00:00 | 2-210 | System CHW and LTHW FIRST FLOOR
70650 | FSA_F02_1-LTHWS-227-DN020-I16C00_R1 | 1 | true | 20.55 | FSA_F02_1-LTHWS-227-DN020-I16C00_R1 |  | 1129 | FSA_South Side | F02 | FoamInside | TBH-ZAT-2024-11-26 | 2024-11-23 | 2024-12-08 | 2024-12-10 |  | 2024-12-22 | 2025-01-13 | Office 20.03.2025 | 2025-01-29 |  | 2025-01-26 | 2025-03-08 | 2025-03-13 | 2025-03-18 | 2025-03-18 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 25.12.2024 00:00:00 | 2-211 | System CHW and LTHW FIRST FLOOR
70651 | FSA_F02_1-PCWR-009-DN250-I16C00_R1 | 1 | true | 53.24 | FSA_F02_1-PCWR-009-DN250-I16C00_R1 |  | 1129 | FSA Corridor | F02 | N/A | TBH-ZAT-2024-11-26 | 2024-11-23 | 2024-11-30 | 2024-12-03 |  | 2025-01-05 | 2025-01-15 | Office 15.02.2025 | 2025-01-28 |  | 2025-01-19 | 2025-02-05 | 2025-02-06 | 2025-02-15 | 2025-03-22 | 1352 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2024-01-12 | 2-200 | System PCW 01
70652 | FSA_F02_1-PCWR-010-DN250-I16C00_R1 | 1 | true | 32.83 | FSA_F02_1-PCWR-010-DN250-I16C00_R1 |  | 1129 | FSA Corridor | F02 | N/A | TBH-ZAT-2024-11-26 | 2024-11-23 | 2024-11-30 | 2024-12-03 |  | 2025-01-05 | 2025-01-22 | Office 14.02.2025 | 2025-01-28 |  | 2025-01-23 | 2025-02-12 | 2025-02-13 | 2025-02-13 | 2025-03-22 | 1352 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 2024-01-12 | 2-200 | .
70653 | FSA_F02_1-PHTGS-030-DN150-I16C00_R1 | 1 | false | 56.12 | FSA_F02_1-PHTGS-030-DN150-I16C00_R1 | LPP6A-M-504-XX-FSA | 1129 | FSA Corridor | F02 | FoamInside | TBH-ZAT-2024-11-26 | 2024-11-23 | 2024-11-30 | 2024-12-03 |  | 2024-12-10 | 2024-12-15 | Dejan Todorovski 18.01.2025 | 2025-01-07 |  | 2024-12-18 | 2025-01-31 |  |  |  | 1368 | 193 | Spool 4 missing |  |  | 194 | SEP | SEP |  |  |  |  | 2024-01-12 | 2-200
72090 | EB_F01-CHWR-136-DN020-I16C00_R0 | 0 | true | 4.32 | EB_F01-CHWR-136-DN020-I16C00_R0 | LPP6A-M-504-XX-FSA | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-11-29 | 2024-11-27 | 2024-12-09 | 2024-12-10 |  | 2024-12-23 | 2025-01-09 | Office 24/04/2025 | 2025-01-22 |  | 2025-01-09 | 2025-04-24 | 2025-04-24 | 2025-06-13 | 2025-06-13 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-306 | System CHW and LTHW GROUND FLOOR
72091 | EB_F01-CHWS-136-DN020-I16C00_R0 | 0 | true | 4.44 | EB_F01-CHWS-136-DN020-I16C00_R0 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-11-29 | 2024-11-27 | 2024-12-09 | 2024-12-10 |  | 2024-12-23 | 2025-01-09 | Office 24/04/2025 | 2025-01-22 |  | 2025-01-09 | 2025-04-24 | 2025-04-24 | 2025-06-13 | 2025-06-13 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-306 | System CHW and LTHW GROUND FLOOR
72092 | EB_F01-LTHWR-136-DN020-I16C00_R0 | 0 | true | 4.39 | EB_F01-LTHWR-136-DN020-I16C00_R0 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-11-29 | 2024-11-27 | 2024-12-09 | 2024-12-10 |  | 2024-12-23 | 2025-01-09 | Office 06/02/2025 | 2025-01-29 |  | 2025-01-09 | 2025-04-24 | 2025-04-24 | 2025-06-13 | 2025-06-13 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-306 | System CHW and LTHW GROUND FLOOR
72093 | EB_F01-LTHWS-136-DN020-I16C00_R0 | 0 | true | 4.07 | EB_F01-LTHWS-136-DN020-I16C00_R0 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2024-11-29 | 2024-11-27 | 2024-12-09 | 2024-12-10 |  | 2024-12-23 | 2025-01-09 | Office 06/02/2025 | 2025-01-29 |  | 2025-01-09 | 2025-04-24 | 2025-04-24 | 2025-06-13 | 2025-06-13 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-306 | System CHW and LTHW GROUND FLOOR
72094 | FSA_F01-CHWR-003-DN150-I16C00_2_R0 | 0 | true | 15.2 | FSA_F01-CHWR-003-DN150-I16C00_2_R0 |  | 1129 | FSA Riser South | Riser | FoamInside | TBH-ZAT-2024-11-29 | 2024-11-27 | 2024-12-11 | 2024-12-10 |  | 2024-12-12 | 2024-12-29 | Office 27.05.2025 | 2025-01-22 |  | 2025-01-06 | 2025-05-20 | 2025-05-20 | 2025-05-27 | 2025-05-27 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 20.12.2024 00:00:00 | 1-200 | System CHW and LTHW GROUND FLOOR
72095 | FSA_F01-CHWR-004-DN150-I16C00_2_R0 | 0 | true | 13.42 | FSA_F01-CHWR-004-DN150-I16C00_2_R0 |  | 1129 | FSA Riser South | Riser | FoamInside | TBH-ZAT-2024-11-29 | 2024-11-27 | 2024-12-11 | 2024-12-10 |  | 2024-12-12 | 2024-12-29 | Office 26/05/2025 | 2025-01-22 |  | 2025-01-06 | 2025-05-22 | 2025-05-22 | 2025-05-22 | 2025-05-23 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 20.12.2024 00:00:00 | 1-200 | System CHW and LTHW GROUND FLOOR
72096 | FSA_F01-CHWR-006-DN150-I16C00_R0 | 0 | false | 20.16 | FSA_F01-CHWR-006-DN150-I16C00_R0 | LPP6A-M-511/513-00/01-FSA | 1129 | FSA Riser South | Riser | FoamInside | TBH-ZAT-2024-11-29 | 2024-11-27 | 2024-12-03 | 2024-12-10 |  | 2024-12-12 | 2024-12-29 | Office 04.03.2025 | 2025-01-22 |  | 2025-01-06 |  |  |  |  | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 20.12.2024 00:00:00 | 1-200
72097 | FSA_F01-CHWS-009-DN150-I16C00_1_R0 | 0 | true | 13.29 | FSA_F01-CHWS-009-DN150-I16C00_1_R0 | LPP6A-M-511/513-00/01-FSA | 1129 | FSA Riser South | Riser | FoamInside | TBH-ZAT-2024-11-29 | 2024-11-27 | 2024-12-11 | 2024-12-10 |  | 2024-12-12 | 2024-12-29 | Office 26/05/2025 | 2025-01-22 |  | 2025-01-06 | 2025-05-19 | 2025-05-19 | 2025-05-20 | 2025-05-25 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 20.12.2024 00:00:00 | 1-200 | System CHW and LTHW GROUND FLOOR
72098 | FSA_F01-CHWS-010-DN150-I16C00_1_R0 | 0 | true | 13.04 | FSA_F01-CHWS-010-DN150-I16C00_1_R0 |  | 1129 | FSA Riser South | Riser | FoamInside | TBH-ZAT-2024-11-29 | 2024-11-27 | 2024-12-11 | 2024-12-10 |  | 2024-12-12 | 2024-12-29 | Office 26/05/2025 | 2025-01-22 |  | 2025-01-06 | 2025-05-21 | 2025-05-21 | 2025-05-23 | 2025-05-23 | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 20.12.2024 00:00:00 | 1-200 | System CHW and LTHW GROUND FLOOR
72099 | FSA_F01-CHWS-013-DN150-I16C00_R0 | 0 | false | 20.34 | FSA_F01-CHWS-013-DN150-I16C00_R0 | LPP6A-M-511/513-00/01-FSA | 1129 | FSA Riser South | Riser | FoamInside | TBH-ZAT-2024-11-29 | 2024-11-27 | 2024-12-03 | 2024-12-10 |  | 2024-12-15 | 2024-12-29 |  | 2025-01-22 |  | 2025-01-06 |  |  |  |  | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 20.12.2024 00:00:00 | 1-200
72100 | FSA_F01-LTHWR-009-DN100-I16C00_R0 | 0 | false | 21.95 | FSA_F01-LTHWR-009-DN100-I16C00_R0 | LPP6A-M-515/518-00/01-FSA | 1129 | FSA Riser South | Riser | FoamInside | TBH-ZAT-2024-11-29 | 2024-11-27 | 2024-12-05 | 2024-12-10 |  | 2024-12-23 |  |  | 2025-01-29 |  | 2025-01-09 |  |  |  |  | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 20.12.2024 00:00:00 | 1-200
72101 | FSA_F01-LTHWS-009-DN100-I16C00_R0 | 0 | false | 22.08 | FSA_F01-LTHWS-009-DN100-I16C00_R0 | LPP6A-M-515/518-00/01-FSA | 1129 | FSA Riser South | Riser | FoamInside | TBH-ZAT-2024-11-29 | 2024-11-27 | 2024-12-05 | 2024-12-10 |  | 2024-12-23 | 2025-01-30 |  |  |  | 2025-01-30 |  |  |  |  | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 20.12.2024 00:00:00 | 1-200
72102 | FSA_F01-PCWR-009-DN250-I16C00_2_R0 | 0 | true | 7.33 | FSA_F01-PCWR-009-DN250-I16C00_2_R0 | LPP6A-M-515/518-00/01-FSA | 1129 | FSA Riser South | Riser | N/A | TBH-ZAT-2024-11-29 | 2024-11-27 | 2024-12-11 | 2024-12-10 |  | 2025-01-05 | 2025-01-15 | Office 05.04.2025 | 2025-01-28 |  | 2025-01-19 | 2025-04-03 | 2025-04-03 | 2025-04-03 | 2025-04-03 | 1352 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 20.12.2024 00:00:00 | 1-200 | System PCW 01
72103 | FSA_F01-PCWR-010-DN250-I16C00_1_R0 | 0 | true | 7.33 | FSA_F01-PCWR-010-DN250-I16C00_1_R0 |  | 1129 | FSA Riser South | Riser | N/A | TBH-ZAT-2024-11-29 | 2024-11-27 | 2024-12-11 | 2024-12-10 |  | 2025-01-05 | 2025-01-15 | Office 05.04.2025 | 2025-01-28 |  | 2025-01-19 | 2025-04-04 | 2025-04-04 | 2025-04-04 | 2025-04-04 | 1352 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 20.12.2024 00:00:00 | 2-200 | System PCW 01
72104 | FSA_F01-PHTGR-008-DN100-I16C00_1_R0 | 0 | false | 6.72 | FSA_F01-PHTGR-008-DN100-I16C00_1_R0 | LPP6A-M-504-XX-FSA | 1129 | FSA Riser South | Riser | N/A | TBH-ZAT-2024-11-29 | 2024-11-27 | 2024-12-11 | 2024-12-10 |  | 2024-12-15 | 2024-12-29 |  | 2025-01-22 |  | 2025-01-06 |  |  |  |  | 1368 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 20.12.2024 00:00:00 | 1-200
72105 | FSA_F01-PHTGS-015-DN150-I16C00_2_R0 | 0 | true | 6.73 | FSA_F01-PHTGS-015-DN150-I16C00_2_R0 | LPP6A-M-504-XX-FSA | 1129 | FSA Riser South | Riser | FoamInside | TBH-ZAT-2024-11-29 | 2024-11-27 | 2024-12-11 | 2024-12-10 |  | 2024-12-15 | 2024-12-29 | Office 20/05/2025 | 2025-01-22 |  | 2025-01-06 | 2025-05-19 | 2025-05-19 | 2025-05-19 | 2025-05-19 | 1368 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 20.12.2024 00:00:00 | 1-200 | System PHTG
72106 | FSA_F02_1-CHWR-023-DN080-I16C00_R0 | 0 | false | 8.62 | FSA_F02_1-CHWR-023-DN080-I16C00_R0 | LPP6A-M-513-01-FSA | 1129 | FSA Riser South | Riser | FoamInside | TBH-ZAT-2024-11-29 | 2024-11-27 | 2024-12-08 | 2024-12-10 |  | 2025-01-02 | 2025-02-03 |  |  |  | 2025-02-06 |  |  |  |  | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 20.12.2024 00:00:00 | Riser to Roof no No.
72107 | FSA_F02_1-CHWS-023-DN080-I16C00_R0 | 0 | false | 8.71 | FSA_F02_1-CHWS-023-DN080-I16C00_R0 | LPP6A-M-513-01-FSA | 1129 | FSA Riser South | Riser | FoamInside | TBH-ZAT-2024-11-29 | 2024-11-27 | 2024-12-08 | 2024-12-10 |  | 2025-01-02 | 2025-01-30 |  |  |  | 2025-01-30 |  |  |  |  | 1359 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 20.12.2024 00:00:00 | Riser to Roof no No.
72108 | FSA_F02_1-PHTGR-008-DN100-I16C00_R0 | 0 | true | 5.69 | FSA_F02_1-PHTGR-008-DN100-I16C00_R0 | LPP6A-M-513-01-FSA | 1129 | FSA Riser South | Riser | N/A | TBH-ZAT-2024-11-29 | 2024-11-27 | 2024-12-05 | 2024-12-10 |  | 2025-01-05 | 2025-01-23 | Office 27/05/2025 | 2025-01-29 |  | 2025-01-23 | 2025-05-16 | 2025-05-26 | 2025-05-26 | 2025-05-26 | 1368 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 20.12.2024 00:00:00 | 2-200 | System PHTG
72109 | FSA_F02_1-PHTGS-015-DN150-I16C00_R0 | 0 | true | 5.71 | FSA_F02_1-PHTGS-015-DN150-I16C00_R0 |  | 1129 | FSA Riser South | Riser | FoamInside | TBH-ZAT-2024-11-29 | 2024-11-27 | 2024-12-05 | 2024-12-10 |  | 2025-01-05 | 2025-01-23 | Office 27/05/2025 | 2025-01-29 |  | 2025-01-23 | 2025-05-16 | 2025-05-26 | 2025-05-26 | 2025-05-26 | 1368 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 20.12.2024 00:00:00 | 2-200 | System PHTG
72187 | CCNR_F02-PHTGR-014-DN150-I16C00_R0 | 0 | true | 9.06 | CCNR_F02-PHTGR-014-DN150-I16C00_R0 |  | 1129 | FSA Riser North AHU | F02 | N/A | TBH-ZAT-2024-12-03 | 2024-12-01 | 2024-12-08 | 2024-12-10 |  | 2024-12-15 | 2024-12-29 | Office 23.06.2025 | 2025-01-22 |  | 2025-01-06 | 2025-03-24 | 2025-03-24 | 2025-06-12 | 2025-06-13 | 1368 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 20.12.2024 00:00:00 | 2-209 | System PHTG
72188 | CCNR_F02-PHTGS-030-DN150-I16C00_R0 | 0 | true | 10.37 | CCNR_F02-PHTGS-030-DN150-I16C00_R0 |  | 1129 | FSA Riser North AHU | F02 | FoamInside | TBH-ZAT-2024-12-03 | 2024-12-01 | 2024-12-08 | 2024-12-10 |  | 2024-12-15 | 2024-12-29 | Office 23.06.2025 | 2025-01-22 |  | 2025-01-06 | 2025-03-26 | 2025-03-26 | 2025-06-11 | 2025-06-13 | 1368 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 20.12.2024 00:00:00 | 2-209 | System PHTG
72189 | FSA_F02_1-LTHWS-241-DN020-I16C00_R0 | 0 | true | 2.51 | FSA_F02_1-LTHWS-241-DN020-I16C00_R0 |  | 1129 | CCNR AHU Room | F02 | FoamInside | TBH-ZAT-2024-12-03 | 2024-12-01 | 2024-12-08 | 2024-12-10 |  | 2025-01-02 | 2025-01-12 | Office 01.04.2025 | 2025-01-29 |  | 2025-01-12 | 2025-03-25 | 2025-03-25 | 2025-04-01 | 2025-04-01 | 1360 | 193 | Mechanical B 2-213 |  |  | 194 | SEP | SEP | [5 empty] | 2-213 | System CHW and LTHW FIRST FLOOR
72190 | FSA_F02_2-CHWR-005-DN050-I16C00_R0 | 0 | false | 26.43 | FSA_F02_2-CHWR-005-DN050-I16C00_R0 | LPP6A-M-514-01-FSA | 1129 | FSA Corridor | F02 | FoamInside | TBH-ZAT-2024-12-03 | 2024-12-01 |  |  | To be revised branches and parts missing | [10 empty] | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-320
72191 | FSA_F02_2-CHWS-012-DN050-I16C00_R0 | 0 | false | 25.14 | FSA_F02_2-CHWS-012-DN050-I16C00_R0 | LPP6A-M-514-01-FSA | 1129 | FSA Corridor | F02 | FoamInside | TBH-ZAT-2024-12-03 | 2024-12-01 |  |  | To be revised branches and parts missing | [10 empty] | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-320
72192 | FSA_F02_2-LTHWR-008-DN100-I16C00_R0 | 0 | false | 28.61 | FSA_F02_2-LTHWR-008-DN100-I16C00_R0 | LPP6A-M-517/518-01/01-FSA | 1129 | FSA Corridor | F02 | FoamInside | TBH-ZAT-2024-12-03 | 2024-12-01 |  |  | To be revised branches and parts missing | [10 empty] | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-320
72193 | FSA_F02_2-LTHWS-008-DN100-I16C00_R0 | 0 | false | 27.31 | FSA_F02_2-LTHWS-008-DN100-I16C00_R0 | LPP6A-M-517/518-01/01-FSA | 1129 | FSA Corridor | F02 | FoamInside | TBH-ZAT-2024-12-03 | 2024-12-01 | 2024-12-08 | 2024-12-10 |  | 2025-01-07 | 2025-01-26 | Office 09.04.2025 | 2025-01-29 |  | 2025-01-27 |  |  |  |  | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 20.12.2024 00:00:00 | 2-320
72212 | CUB5_PCWR-001-DN600-I16C00_R0 | 0 | false | 56.41 | CUB5_PCWR-001-DN600-I16C00_R0 | LPP6A-M-540-XX-CUB | 1129 | CUB5 | F01 | N/A | TBH-ZAT-2024-12-06 | 2024-12-04 |  |  | To be revised | [10 empty] | 1361 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | CUB5
72213 | CUB5_PCWR-002-DN600-I16C00_R0 | 0 | false | 31.01 | CUB5_PCWR-002-DN600-I16C00_R0 | LPP6A-M-540-XX-CUB | 1129 | CUB5 | F01 | N/A | TBH-ZAT-2024-12-06 | 2024-12-04 |  |  | To be revised | [10 empty] | 1361 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | CUB5
72214 | CUB5_PCWR-003-DN450-I16C00_R0 | 0 | false | 16.01 | CUB5_PCWR-003-DN450-I16C00_R0 | LPP6A-M-540-XX-CUB | 1129 | CUB5 | F01 | N/A | TBH-ZAT-2024-12-06 | 2024-12-04 |  |  | To be revised | [10 empty] | 1361 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | CUB5
72215 | CUB5_PCWR-026-DN50-I16C00_R0 | 0 | false | 1.23 | CUB5_PCWR-026-DN50-I16C00_R0 | LPP6A-M-540-XX-CUB | 1129 | CUB5 | F01 | N/A | TBH-ZAT-2024-12-06 | 2024-12-04 | [13 empty] | 1361 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | CUB5
72216 | CUB5_PCWS-001-DN600-I16C00_R0 | 0 | false | 58.64 | CUB5_PCWS-001-DN600-I16C00_R0 | LPP6A-M-540-XX-CUB | 1129 | CUB5 | F01 | N/A | TBH-ZAT-2024-12-06 | 2024-12-04 |  |  | To be revised | [10 empty] | 1361 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | CUB5
72217 | CUB5_PCWS-002-DN600-I16C00_R0 | 0 | false | 30.02 | CUB5_PCWS-002-DN600-I16C00_R0 | LPP6A-M-540-XX-CUB | 1129 | CUB5 | F01 | N/A | TBH-ZAT-2024-12-06 | 2024-12-04 |  |  | To be revised | [10 empty] | 1361 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | CUB5
72218 | CUB5_PCWS-003-DN450-I16C00_R0 | 0 | false | 14.4 | CUB5_PCWS-003-DN450-I16C00_R0 | LPP6A-M-540-XX-CUB | 1129 | CUB5 | F01 | N/A | TBH-ZAT-2024-12-06 | 2024-12-04 |  |  | To be revised | [10 empty] | 1361 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | CUB5
72219 | FSA_F02_2-CHWR-005-DN050-I16C00_R1 | 1 | false | 26.15 | FSA_F02_2-CHWR-005-DN050-I16C00_R1 | LPP6A-M-511/513-00/01-FSA | 1129 | FSA Corridor | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2024-12-16 | 2024-12-19 |  | 2025-01-09 |  |  |  |  | 2025-03-27 |  |  |  |  | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-320
72220 | FSA_F02_2-CHWS-012-DN050-I16C00_R1 | 1 | false | 24.87 | FSA_F02_2-CHWS-012-DN050-I16C00_R1 | LPP6A-M-511/513-00/01-FSA | 1129 | FSA Corridor | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2024-12-16 | 2024-12-19 |  | 2025-01-09 |  |  |  |  | 2025-01-31 |  |  |  |  | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-320
72221 | FSA_F02_2-LTHWR-008-DN100-I16C00_R1 | 1 | false | 28.44 | FSA_F02_2-LTHWR-008-DN100-I16C00_R1 | LPP6A-M-517/518-01/01-FSA | 1129 | FSA Corridor | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2024-12-16 | 2024-12-19 |  | 2025-01-22 | 2025-02-03 | Office 11.04.2025 | 2025-02-05 |  | 2025-02-06 |  |  |  |  | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-320
72222 | FSA_F02_2-CHWR-181-DN040-I16C00_R0 | 0 | true | 30.76 | FSA_F02_2-CHWR-181-DN040-I16C00_R0 | LPP6A-M-517/518-01/01-FSA | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2025-01-10 | 2025-01-14 |  | 2025-01-21 | 2025-04-02 | Office 06.06.2025 | 2025-04-09 |  | 2025-03-31 | 2025-04-22 | 2025-04-26 | 2025-04-30 | 2025-05-01 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-220 | System CHW and LTHW FIRST FLOOR
72223 | FSA_F02_2-CHWR-182-DN020-I16C00_R0 | 0 | true | 2.78 | FSA_F02_2-CHWR-182-DN020-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2025-01-10 | 2025-01-14 |  | 2025-01-15 | 2025-01-29 | Office 29/04/2025 | 2025-02-05 |  | 2025-01-30 | 2025-04-28 | 2025-04-28 | 2025-07-21 | 2025-07-21 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-320 | System CHW and LTHW FIRST FLOOR
72224 | FSA_F02_2-CHWR-183-DN020-I16C00_R0 | 0 | true | 4.17 | FSA_F02_2-CHWR-183-DN020-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2025-01-10 | 2025-01-14 |  | 2025-01-15 | 2025-01-31 | Office 08.05.2025 | 2025-02-05 |  | 2025-01-31 | 2025-05-05 | 2025-05-05 | 2025-05-06 | 2025-05-06 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-220 | System CHW and LTHW FIRST FLOOR
72225 | FSA_F02_2-CHWR-184-DN020-I16C00_R0 | 0 | true | 4.09 | FSA_F02_2-CHWR-184-DN020-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2025-01-10 | 2025-01-14 |  | 2025-01-15 | 2025-01-27 | Office 09/05/2025 | 2025-02-05 |  | 2025-01-27 | 2025-05-08 | 2025-05-08 | 2025-05-08 | 2025-05-08 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-220 | System CHW and LTHW FIRST FLOOR
72226 | FSA_F02_2-CHWR-185-DN020-I16C00_R0 | 0 | true | 4.13 | FSA_F02_2-CHWR-185-DN020-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2025-01-10 | 2025-01-14 |  | 2025-01-15 | 2025-01-27 | Office 15.05.2025 | 2025-02-05 |  | 2025-01-27 | 2025-05-15 | 2025-05-15 | 2025-05-15 | 2025-05-15 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-220 | System CHW and LTHW FIRST FLOOR
72227 | FSA_F02_2-CHWR-186-DN020-I16C00_R0 | 0 | true | 4.18 | FSA_F02_2-CHWR-186-DN020-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2025-01-10 | 2025-01-14 |  | 2025-01-15 | 2025-01-27 | Office 14/05/2025 | 2025-02-05 |  | 2025-01-27 | 2025-05-12 | 2025-05-12 | 2025-05-13 | 2025-05-13 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-220 | System CHW and LTHW FIRST FLOOR
72228 | FSA_F02_2-CHWR-187-DN020-I16C00_R0 | 0 | true | 4.14 | FSA_F02_2-CHWR-187-DN020-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2025-01-10 | 2025-01-14 |  | 2025-01-15 | 2025-01-27 | Office 20/05/2025 | 2025-02-05 |  | 2025-01-27 | 2025-05-16 | 2025-05-16 | 2025-05-16 | 2025-05-16 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-220 | System CHW and LTHW FIRST FLOOR
72229 | FSA_F02_2-CHWR-188-DN020-I16C00_R0 | 0 | true | 5.12 | FSA_F02_2-CHWR-188-DN020-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2025-01-10 | 2025-01-14 |  | 2025-01-15 | 2025-01-27 | Office 23.06.2025 | 2025-02-05 |  | 2025-01-27 | 2025-05-13 | 2025-05-13 | 2025-05-13 | 2025-05-13 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-225 | System CHW and LTHW FIRST FLOOR
72230 | FSA_F02_2-CHWR-189-DN020-I16C00_R0 | 0 | true | 5.22 | FSA_F02_2-CHWR-189-DN020-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2025-01-10 | 2025-01-14 |  | 2025-01-15 | 2025-01-27 | Office 23.06.2025 | 2025-02-05 |  | 2025-01-27 | 2025-05-14 | 2025-05-14 | 2025-05-14 | 2025-05-14 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-226 | System CHW and LTHW FIRST FLOOR
72231 | FSA_F02_2-CHWR-190-DN020-I16C00_R0 | 0 | false | 13.6 | FSA_F02_2-CHWR-190-DN020-I16C00_R0 | LPP6A-M-514-01-FSA | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2025-01-10 | 2025-01-14 |  | 2025-01-15 | [9 empty] | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-217
72232 | FSA_F02_2-CHWR-191-DN020-I16C00_R0 | 0 | true | 7.59 | FSA_F02_2-CHWR-191-DN020-I16C00_R0 | LPP6A-M-514-01-FSA | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2025-01-10 | 2025-01-14 |  | 2025-01-15 | 2025-01-29 | Office 03.04.2025 | 2025-02-05 |  | 2025-01-30 | 2025-03-27 | 2025-03-27 | 2025-03-27 | 2025-03-27 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-217 | System CHW and LTHW FIRST FLOOR
72233 | FSA_F02_2-CHWR-192-DN020-I16C00_R0 | 0 | true | 6.11 | FSA_F02_2-CHWR-192-DN020-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2025-01-10 | 2025-01-14 |  | 2025-01-15 | 2025-01-27 | Office 03.04.2025 | 2025-02-05 |  | 2025-01-27 | 2025-03-29 | 2025-04-02 | 2025-04-03 |  | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-320 | System CHW and LTHW FIRST FLOOR
72234 | FSA_F02_2-CHWR-193-DN040-I16C00_R0 | 0 | false | 55.84 | FSA_F02_2-CHWR-193-DN040-I16C00_R0 | LPP6A-M-514-01-FSA | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | [13 empty] | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-223
72235 | FSA_F02_2-CHWR-194-DN020-I16C00_R0 | 0 | true | 4.32 | FSA_F02_2-CHWR-194-DN020-I16C00_R0 | LPP6A-M-514-01-FSA | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2025-01-10 | 2025-01-14 |  | 2025-01-15 | 2025-01-26 | Office 18.04.2025 | 2025-02-05 |  | 2025-01-27 | 2025-04-17 | 2025-04-17 | 2025-07-21 | 2025-07-21 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-223 | System CHW and LTHW FIRST FLOOR
72236 | FSA_F02_2-CHWR-195-DN015-I16C00_R0 | 0 | true | 13.44 | FSA_F02_2-CHWR-195-DN015-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2025-01-10 | 2025-01-14 |  | 2025-01-15 | 2025-01-26 | Office 01/07/2025 | 2025-02-05 |  | 2025-01-27 | 2025-04-17 | 2025-05-30 | 2025-06-12 |  | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-223 | System CHW and LTHW FIRST FLOOR
72237 | FSA_F02_2-CHWR-196-DN020-I16C00_R0 | 0 | true | 2.95 | FSA_F02_2-CHWR-196-DN020-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2025-01-10 | 2025-01-14 |  | 2025-01-15 | 2025-01-29 | Office 23/04/2025 | 2025-02-05 |  | 2025-01-30 | 2025-04-18 | 2025-04-18 | 2025-07-21 | 2025-07-21 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-223 | System CHW and LTHW FIRST FLOOR
72238 | FSA_F02_2-CHWR-197-DN020-I16C00_R0 | 0 | true | 3.07 | FSA_F02_2-CHWR-197-DN020-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2025-01-10 | 2025-01-14 |  | 2025-01-15 | 2025-01-29 | Office 19.03.2025 | 2025-02-05 |  | 2025-01-30 | 2025-04-23 | 2025-04-23 | 2025-07-21 | 2025-07-21 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-223 | System CHW and LTHW FIRST FLOOR
72239 | FSA_F02_2-CHWR-198-DN020-I16C00_R0 | 0 | true | 3.92 | FSA_F02_2-CHWR-198-DN020-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2025-01-10 | 2025-01-14 |  | 2025-01-15 | 2025-01-27 | Office 25/04/2025 | 2025-02-05 |  | 2025-01-27 | 2025-04-24 | 2025-04-24 | 2025-07-21 | 2025-07-21 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-223 | System CHW and LTHW FIRST FLOOR
72240 | FSA_F02_2-CHWR-199-DN025-I16C00_R0 | 0 | true | 10.82 | FSA_F02_2-CHWR-199-DN025-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2025-01-09 | 2025-01-14 |  | 2025-01-15 | 2025-01-26 | Office 23/04/2025 | 2025-02-05 |  | 2025-01-27 | 2025-04-15 | 2025-04-15 | 2025-04-18 | 2025-04-18 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-205 | System CHW and LTHW FIRST FLOOR
72241 | FSA_F02_2-CHWR-200-DN020-I16C00_R0 | 0 | true | 2.36 | FSA_F02_2-CHWR-200-DN020-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2025-01-09 | 2025-01-14 |  | 2025-01-19 | 2025-01-29 | Office 06.06.2025 | 2025-02-05 |  | 2025-01-30 | 2025-05-16 | 2025-05-29 | 2025-05-29 | 2025-05-29 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-205 | System CHW and LTHW FIRST FLOOR
72242 | FSA_F02_2-CHWR-201-DN020-I16C00_R0 | 0 | true | 4.39 | FSA_F02_2-CHWR-201-DN020-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2025-01-09 | 2025-01-14 |  | 2025-01-19 | 2025-01-26 | Office 23.06.2025 | 2025-02-05 |  | 2025-01-27 | 2025-05-16 | 2025-06-02 | 2025-06-02 | 2025-06-02 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-205 | System CHW and LTHW FIRST FLOOR
72243 | FSA_F02_2-CHWR-202-DN020-I16C00_R0 | 0 | true | 2.52 | FSA_F02_2-CHWR-202-DN020-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2025-01-09 | 2025-01-14 |  | 2025-01-19 | 2025-01-27 | Office 06.06.2025 | 2025-02-05 |  | 2025-01-27 | 2025-05-16 | 2025-05-20 | 2025-06-02 | 2025-06-02 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-205 | System CHW and LTHW FIRST FLOOR
72244 | FSA_F02_2-CHWR-203-DN020-I16C00_R0 | 0 | true | 2.7 | FSA_F02_2-CHWR-203-DN020-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2025-01-09 | 2025-01-14 |  | 2025-01-19 | 2025-01-26 | Office 29/04/2025 | 2025-02-05 |  | 2025-01-27 | 2025-04-25 | 2025-04-25 | 2025-05-07 | 2025-05-07 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-223 | System CHW and LTHW FIRST FLOOR
72245 | FSA_F02_2-CHWR-204-DN020-I16C00_R0 | 0 | true | 2.61 | FSA_F02_2-CHWR-204-DN020-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2025-01-09 | 2025-01-14 |  | 2025-01-19 | 2025-01-26 | Office 29/04/2025 | 2025-02-05 |  | 2025-01-27 | 2025-04-26 | 2025-04-26 | 2025-05-08 | 2025-05-08 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-223 | System CHW and LTHW FIRST FLOOR
72246 | FSA_F02_2-CHWR-205-DN020-I16C00_R0 | 0 | true | 3.7 | FSA_F02_2-CHWR-205-DN020-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2025-01-09 | 2025-01-14 |  | 2025-01-19 | 2025-01-27 | Ivan Tatomirovic 08.05.2025 | 2025-02-05 |  | 2025-01-27 | 2025-04-24 | 2025-04-24 | 2025-05-09 | 2025-05-09 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-223 | System CHW and LTHW FIRST FLOOR
72247 | FSA_F02_2-CHWR-244-DN025-I16C00_R0 | 0 | false | 0.64 | FSA_F02_2-CHWR-244-DN025-I16C00_R0 | LPP6A-M-513-01-FSA | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2025-01-09 | 2025-01-14 |  | 2025-01-19 | 2025-01-29 | Office 03.03.2025 | 2025-02-05 |  | 2025-01-30 |  |  |  |  | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-320
72248 | FSA_F02_2-CHWR-245-DN020-I16C00_R0 | 0 | false | 2.26 | FSA_F02_2-CHWR-245-DN020-I16C00_R0 | LPP6A-M-513-01-FSA | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2025-01-09 | 2025-01-14 |  | 2025-01-19 | 2025-01-29 | Office 03.03.2025 | 2025-02-05 |  | 2025-01-30 |  |  |  |  | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-320
72249 | FSA_F02_2-CHWR-246-DN025-I16C00_R0 | 0 | false | 9.26 | FSA_F02_2-CHWR-246-DN025-I16C00_R0 | LPP6A-M-513-01-FSA | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2025-01-09 | 2025-01-14 |  | 2025-01-19 | 2025-01-27 | Office 03.03.2025 | 2025-02-05 |  | 2025-01-27 |  |  |  |  | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-209
72250 | FSA_F02_2-CHWR-247-DN020-I16C00_R0 | 0 | true | 6.24 | FSA_F02_2-CHWR-247-DN020-I16C00_R0 | LPP6A-M-513-01-FSA | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2025-01-09 | 2025-01-14 |  | 2025-01-19 | 2025-01-29 | Office 02.04.2025 | 2025-02-05 |  | 2025-01-30 | 2025-03-28 | 2025-03-28 | 2025-03-28 | 2025-03-28 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-320 | System CHW and LTHW FIRST FLOOR
72251 | FSA_F02_2-CHWS-181-DN040-I16C00_R0 | 0 | true | 31.13 | FSA_F02_2-CHWS-181-DN040-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2025-01-09 | 2025-01-14 |  | 2025-01-21 | 2025-04-02 | Office 06.06.2025 | 2025-04-09 |  | 2025-03-31 | 2025-04-22 | 2025-04-26 | 2025-04-30 | 2025-05-01 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-220 | System CHW and LTHW FIRST FLOOR
72252 | FSA_F02_2-CHWS-182-DN020-I16C00_R0 | 0 | true | 2.85 | FSA_F02_2-CHWS-182-DN020-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2025-01-09 | 2025-01-14 |  | 2025-01-19 | 2025-01-27 | Office 29/04/2025 | 2025-02-05 |  | 2025-01-27 | 2025-04-28 | 2025-04-28 | 2025-07-21 | 2025-07-21 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-320 | System CHW and LTHW FIRST FLOOR
72253 | FSA_F02_2-CHWS-183-DN020-I16C00_R0 | 0 | true | 4.04 | FSA_F02_2-CHWS-183-DN020-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2025-01-09 | 2025-01-14 |  | 2025-01-19 | 2025-01-26 | Office 08.05.2025 | 2025-02-05 |  | 2025-01-27 | 2025-05-05 | 2025-05-05 | 2025-05-06 | 2025-05-06 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-220 | System CHW and LTHW FIRST FLOOR
72254 | FSA_F02_2-CHWS-184-DN020-I16C00_R0 | 0 | true | 4.57 | FSA_F02_2-CHWS-184-DN020-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2025-01-09 | 2025-01-14 |  | 2025-01-19 | 2025-01-27 | Office 09/05/2025 | 2025-02-05 |  | 2025-01-27 | 2025-05-08 | 2025-05-08 | 2025-05-08 | 2025-05-08 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-220 | System CHW and LTHW FIRST FLOOR
72255 | FSA_F02_2-CHWS-185-DN020-I16C00_R0 | 0 | true | 4.39 | FSA_F02_2-CHWS-185-DN020-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2025-01-09 | 2025-01-14 |  | 2025-01-19 | 2025-01-26 | Office 15.05.2025 | 2025-02-05 |  | 2025-01-27 | 2025-05-15 | 2025-05-15 | 2025-05-15 | 2025-05-15 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-220 | System CHW and LTHW FIRST FLOOR
72256 | FSA_F02_2-CHWS-186-DN020-I16C00_R0 | 0 | true | 4.05 | FSA_F02_2-CHWS-186-DN020-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2025-01-09 | 2025-01-14 |  | 2025-01-19 | 2025-01-27 | Office 14/05/2025 | 2025-02-05 |  | 2025-01-27 | 2025-05-12 | 2025-05-12 | 2025-05-13 | 2025-05-13 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-220 | System CHW and LTHW FIRST FLOOR
72257 | FSA_F02_2-CHWS-187-DN020-I16C00_R0 | 0 | true | 4.39 | FSA_F02_2-CHWS-187-DN020-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2025-01-09 | 2025-01-14 |  | 2025-01-19 | 2025-01-31 | Office 20/05/2025 | 2025-02-05 |  | 2025-01-31 | 2025-05-16 | 2025-05-16 | 2025-05-16 | 2025-05-16 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-220 | System CHW and LTHW FIRST FLOOR
72258 | FSA_F02_2-CHWS-188-DN020-I16C00_R0 | 0 | true | 5.39 | FSA_F02_2-CHWS-188-DN020-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2025-01-09 | 2025-01-14 |  | 2025-01-20 | 2025-01-26 | Office 23.06.2025 | 2025-02-05 |  | 2025-01-27 | 2025-05-13 | 2025-05-13 | 2025-05-13 | 2025-05-13 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-225 | System CHW and LTHW FIRST FLOOR
72259 | FSA_F02_2-CHWS-189-DN020-I16C00_R0 | 0 | true | 5.46 | FSA_F02_2-CHWS-189-DN020-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2025-01-09 | 2025-01-14 |  | 2025-01-20 | 2025-01-26 | Office 23.06.2025 | 2025-02-05 |  | 2025-01-27 | 2025-05-14 | 2025-05-14 | 2025-05-14 | 2025-05-14 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-226 | System CHW and LTHW FIRST FLOOR
72260 | FSA_F02_2-CHWS-190-DN020-I16C00_R0 | 0 | false | 13.63 | FSA_F02_2-CHWS-190-DN020-I16C00_R0 | LPP6A-M-514-01-FSA | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2025-01-09 | 2025-01-14 |  | 2025-01-20 | [9 empty] | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-217
72261 | FSA_F02_2-CHWS-191-DN020-I16C00_R0 | 0 | true | 7.29 | FSA_F02_2-CHWS-191-DN020-I16C00_R0 | LPP6A-M-514-01-FSA | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2025-01-09 | 2025-01-14 |  | 2025-01-20 | 2025-01-27 | Office 02.04.2025 | 2025-02-05 |  | 2025-01-27 | 2025-03-27 | 2025-03-27 | 2025-03-27 | 2025-03-27 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-217 | System CHW and LTHW FIRST FLOOR
72262 | FSA_F02_2-CHWS-192-DN020-I16C00_R0 | 0 | true | 5.48 | FSA_F02_2-CHWS-192-DN020-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2025-01-09 | 2025-01-14 |  | 2025-01-20 | 2025-01-27 | Office 02.04.2025 | 2025-02-05 |  | 2025-01-27 | 2025-03-29 | 2025-03-29 | 2025-07-21 | 2025-07-21 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-320 | System CHW and LTHW FIRST FLOOR
72263 | FSA_F02_2-CHWS-193-DN040-I16C00_R0 | 0 | false | 55.54 | FSA_F02_2-CHWS-193-DN040-I16C00_R0 | LPP6A-M-514-01-FSA | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | [13 empty] | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-223
72264 | FSA_F02_2-CHWS-194-DN020-I16C00_R0 | 0 | true | 4.22 | FSA_F02_2-CHWS-194-DN020-I16C00_R0 | LPP6A-M-514-01-FSA | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2025-01-09 | 2025-01-14 |  | 2025-01-20 | 2025-01-26 | Office 18.04.2025 | 2025-02-05 |  | 2025-01-27 | 2025-04-17 | 2025-04-17 | 2025-07-21 | 2025-07-21 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-223 | System CHW and LTHW FIRST FLOOR
72265 | FSA_F02_2-CHWS-195-DN015-I16C00_R0 | 0 | true | 13.4 | FSA_F02_2-CHWS-195-DN015-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2025-01-09 | 2025-01-14 |  | 2025-01-20 | 2025-01-26 | Office 01/07/2025 | 2025-02-05 |  | 2025-01-27 | 2025-04-17 | 2025-05-30 | 2025-06-13 |  | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-223 | System CHW and LTHW FIRST FLOOR
72266 | FSA_F02_2-CHWS-196-DN020-I16C00_R0 | 0 | true | 2.78 | FSA_F02_2-CHWS-196-DN020-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2025-01-09 | 2025-01-14 |  | 2025-01-20 | 2025-01-31 | Office 23/04/2025 | 2025-02-05 |  | 2025-01-31 | 2025-04-18 | 2025-04-18 | 2025-07-21 | 2025-07-21 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-223 | System CHW and LTHW FIRST FLOOR
72267 | FSA_F02_2-CHWS-197-DN020-I16C00_R0 | 0 | true | 2.98 | FSA_F02_2-CHWS-197-DN020-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2025-01-08 | 2025-01-14 |  | 2025-01-20 | 2025-01-31 | Office 19.03.2025 | 2025-02-05 |  | 2025-01-31 | 2025-04-23 | 2025-04-23 | 2025-07-21 | 2025-07-21 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-223 | System CHW and LTHW FIRST FLOOR
72268 | FSA_F02_2-CHWS-198-DN020-I16C00_R0 | 0 | true | 4.22 | FSA_F02_2-CHWS-198-DN020-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2025-01-08 | 2025-01-14 |  | 2025-01-20 | 2025-01-27 | Office 25/04/2025 | 2025-02-05 |  | 2025-01-27 | 2025-04-24 | 2025-04-24 | 2025-07-21 | 2025-07-21 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-223 | System CHW and LTHW FIRST FLOOR
72269 | FSA_F02_2-CHWS-199-DN025-I16C00_R0 | 0 | true | 10.85 | FSA_F02_2-CHWS-199-DN025-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2025-01-08 | 2025-01-14 |  | 2025-01-20 | 2025-03-11 | Office 23/04/2025 | 2025-03-28 |  | 2025-03-12 | 2025-04-14 | 2025-04-18 | 2025-04-18 | 2025-04-18 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-205 | System CHW and LTHW FIRST FLOOR
72270 | FSA_F02_2-CHWS-200-DN020-I16C00_R0 | 0 | true | 2.27 | FSA_F02_2-CHWS-200-DN020-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2025-01-08 | 2025-01-14 |  | 2025-01-20 | 2025-01-26 | Office 06.06.2025 | 2025-02-05 |  | 2025-01-27 | 2025-05-16 | 2025-05-29 | 2025-05-29 | 2025-05-29 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-205 | System CHW and LTHW FIRST FLOOR
72271 | FSA_F02_2-CHWS-201-DN020-I16C00_R0 | 0 | true | 4.85 | FSA_F02_2-CHWS-201-DN020-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2025-01-08 | 2025-01-14 |  | 2025-01-20 | 2025-01-26 | Office 23.06.2025 | 2025-02-05 |  | 2025-01-27 | 2025-05-16 | 2025-06-03 | 2025-06-03 | 2025-06-03 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-205 | System CHW and LTHW FIRST FLOOR
72272 | FSA_F02_2-CHWS-202-DN020-I16C00_R0 | 0 | true | 2.75 | FSA_F02_2-CHWS-202-DN020-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2025-01-08 | 2025-01-14 |  | 2025-01-20 | 2025-01-31 | Office 06.06.2025 | 2025-02-05 |  | 2025-01-31 | 2025-05-16 | 2025-05-20 | 2025-06-02 | 2025-06-02 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-205 | System CHW and LTHW FIRST FLOOR
72273 | FSA_F02_2-CHWS-203-DN020-I16C00_R0 | 0 | true | 2.95 | FSA_F02_2-CHWS-203-DN020-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2025-01-08 | 2025-01-14 |  | 2025-01-20 | 2025-01-31 | Office 29/04/2025 | 2025-02-05 |  | 2025-01-31 | 2025-04-26 | 2025-04-26 | 2025-05-07 | 2025-05-07 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-223 | System CHW and LTHW FIRST FLOOR
72274 | FSA_F02_2-CHWS-204-DN020-I16C00_R0 | 0 | true | 2.86 | FSA_F02_2-CHWS-204-DN020-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2025-01-08 | 2025-01-14 |  | 2025-01-20 | 2025-01-31 | Office 29/04/2025 | 2025-02-05 |  | 2025-01-31 | 2025-04-26 | 2025-04-26 | 2025-05-08 | 2025-05-08 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-223 | System CHW and LTHW FIRST FLOOR
72275 | FSA_F02_2-CHWS-205-DN020-I16C00_R0 | 0 | true | 4.26 | FSA_F02_2-CHWS-205-DN020-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2025-01-08 | 2025-01-14 |  | 2025-01-20 | 2025-01-27 | Ivan Tatomirovic 08.05.2025 | 2025-02-05 |  | 2025-01-27 | 2025-04-24 | 2025-04-24 | 2025-05-09 | 2025-05-09 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-223 | System CHW and LTHW FIRST FLOOR
72276 | FSA_F02_2-CHWS-244-DN025-I16C00_R0 | 0 | false | 0.99 | FSA_F02_2-CHWS-244-DN025-I16C00_R0 | LPP6A-M-513-01-FSA | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2025-01-08 | 2025-01-14 |  | 2025-01-21 | 2025-01-29 | Office 03.03.2025 | 2025-02-05 |  | 2025-01-30 |  |  |  |  | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-320
72277 | FSA_F02_2-CHWS-245-DN020-I16C00_R0 | 0 | false | 2.13 | FSA_F02_2-CHWS-245-DN020-I16C00_R0 | LPP6A-M-513-01-FSA | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2025-01-08 | 2025-01-14 |  | 2025-01-21 | 2025-01-29 | Office 03.03.2025 | 2025-02-05 |  | 2025-01-30 |  |  |  |  | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-320
72278 | FSA_F02_2-CHWS-246-DN025-I16C00_R0 | 0 | false | 9.19 | FSA_F02_2-CHWS-246-DN025-I16C00_R0 | LPP6A-M-513-01-FSA | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2025-01-08 | 2025-01-14 |  | 2025-01-21 | 2025-01-29 | Office 03.03.2025 | 2025-02-05 |  | 2025-01-30 |  |  |  |  | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-209
72279 | FSA_F02_2-CHWS-247-DN020-I16C00_R0 | 0 | true | 6.25 | FSA_F02_2-CHWS-247-DN020-I16C00_R0 | LPP6A-M-513-01-FSA | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2025-01-08 | 2025-01-14 |  | 2025-01-21 | 2025-01-29 | Office 02.04.2025 | 2025-02-05 |  | 2025-01-30 | 2025-03-28 | 2025-03-28 | 2025-03-28 | 2025-03-28 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-320 | System CHW and LTHW FIRST FLOOR
72280 | FSA_F02_2-LTHWR-181-DN032-I16C00_R0 | 0 | true | 29.98 | FSA_F02_2-LTHWR-181-DN032-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2025-01-08 | 2025-01-14 |  | 2025-01-31 | 2025-04-02 | Office 06.06.2025 | 2025-04-09 |  | 2025-03-31 | 2025-04-24 | 2025-04-25 | 2025-04-30 | 2025-05-01 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-220 | System CHW and LTHW FIRST FLOOR
72281 | FSA_F02_2-LTHWR-182-DN020-I16C00_R0 | 0 | true | 2.51 | FSA_F02_2-LTHWR-182-DN020-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2025-01-08 | 2025-01-14 |  | 2025-01-21 | 2025-01-30 | Office 29/04/2025 | 2025-02-05 |  | 2025-01-29 | 2025-04-28 | 2025-04-28 | 2025-07-21 | 2025-07-21 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-320 | System CHW and LTHW FIRST FLOOR
72282 | FSA_F02_2-LTHWR-183-DN020-I16C00_R0 | 0 | true | 4.27 | FSA_F02_2-LTHWR-183-DN020-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2025-01-08 | 2025-01-14 |  | 2025-01-21 | 2025-01-30 | Office 08.05.2025 | 2025-02-05 |  | 2025-01-29 | 2025-05-05 | 2025-05-05 | 2025-05-06 | 2025-05-06 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-220 | System CHW and LTHW FIRST FLOOR
72283 | FSA_F02_2-LTHWR-184-DN020-I16C00_R0 | 0 | true | 3.33 | FSA_F02_2-LTHWR-184-DN020-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2025-01-08 | 2025-01-14 |  | 2025-01-21 | 2025-01-30 | Office 09/05/2025 | 2025-02-05 |  | 2025-01-30 | 2025-05-09 | 2025-05-09 | 2025-05-09 | 2025-05-09 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-220 | System CHW and LTHW FIRST FLOOR
72284 | FSA_F02_2-LTHWR-185-DN020-I16C00_R0 | 0 | true | 3.41 | FSA_F02_2-LTHWR-185-DN020-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2025-01-08 | 2025-01-14 |  | 2025-01-21 | 2025-01-30 | Office 15.05.2025 | 2025-02-05 |  | 2025-01-30 | 2025-05-14 | 2025-05-14 | 2025-05-14 | 2025-05-14 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-220 | System CHW and LTHW FIRST FLOOR
72285 | FSA_F02_2-LTHWR-186-DN020-I16C00_R0 | 0 | true | 4.27 | FSA_F02_2-LTHWR-186-DN020-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2025-01-08 | 2025-01-14 |  | 2025-01-21 | 2025-01-30 | Office 14/05/2025 | 2025-02-05 |  | 2025-01-30 | 2025-05-13 | 2025-05-13 | 2025-05-14 | 2025-05-14 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-220 | System CHW and LTHW FIRST FLOOR
72286 | FSA_F02_2-LTHWR-187-DN020-I16C00_R0 | 0 | true | 3.42 | FSA_F02_2-LTHWR-187-DN020-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2025-01-08 | 2025-01-14 |  | 2025-01-21 | 2025-01-30 | Office 20/05/2025 | 2025-02-05 |  | 2025-01-30 | 2025-05-16 | 2025-05-16 | 2025-05-16 | 2025-05-16 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-220 | System CHW and LTHW FIRST FLOOR
72287 | FSA_F02_2-LTHWR-188-DN015-I16C00_R0 | 0 | true | 4.76 | FSA_F02_2-LTHWR-188-DN015-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2025-01-08 | 2025-01-14 |  | 2025-01-21 | 2025-01-30 | Office 23.06.2025 | 2025-02-05 |  | 2025-01-30 | 2025-05-13 | 2025-05-13 | 2025-05-13 | 2025-05-13 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-225 | System CHW and LTHW FIRST FLOOR
72288 | FSA_F02_2-LTHWR-189-DN015-I16C00_R0 | 0 | true | 4.81 | FSA_F02_2-LTHWR-189-DN015-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2025-01-08 | 2025-01-14 |  | 2025-01-21 | 2025-01-30 | Office 23.06.2025 | 2025-02-05 |  | 2025-01-30 | 2025-05-14 | 2025-05-14 | 2025-05-14 | 2025-05-14 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-226 | System CHW and LTHW FIRST FLOOR
72289 | FSA_F02_2-LTHWR-190-DN020-I16C00_R0 | 0 | true | 14.18 | FSA_F02_2-LTHWR-190-DN020-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2025-01-08 | 2025-01-14 |  | 2025-01-21 | 2025-01-30 | Office 02.04.2025 | 2025-02-05 |  | 2025-01-30 | 2025-03-25 | 2025-03-26 | 2025-03-27 | 2025-03-27 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-217 | System CHW and LTHW FIRST FLOOR
72290 | FSA_F02_2-LTHWR-191-DN020-I16C00_R0 | 0 | true | 8.28 | FSA_F02_2-LTHWR-191-DN020-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2025-01-08 | 2025-01-14 |  | 2025-01-21 | 2025-01-30 | Office 02.04.2025 | 2025-02-05 |  | 2025-01-29 | 2025-03-27 | 2025-03-27 | 2025-03-27 | 2025-03-27 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-217 | System CHW and LTHW FIRST FLOOR
72291 | FSA_F02_2-LTHWR-192-DN020-I16C00_R0 | 0 | true | 7.72 | FSA_F02_2-LTHWR-192-DN020-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2025-01-08 | 2025-01-14 |  | 2025-01-21 | 2025-01-30 | Office 02.04.2025 | 2025-02-05 |  | 2025-01-29 | 2025-03-28 | 2025-03-28 | 2025-07-21 | 2025-07-21 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-320 | System CHW and LTHW FIRST FLOOR
72292 | FSA_F02_2-LTHWR-193-DN040-I16C00_R0 | 0 | false | 56.78 | FSA_F02_2-LTHWR-193-DN040-I16C00_R0 | LPP6A-M-517-01-FSA | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | [13 empty] | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-223
72293 | FSA_F02_2-LTHWR-194-DN020-I16C00_R0 | 0 | true | 4.42 | FSA_F02_2-LTHWR-194-DN020-I16C00_R0 | LPP6A-M-517-01-FSA | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2024-12-16 | 2024-12-19 |  | 2024-12-19 | 2024-12-29 | Office 18.04.2025 | 2025-01-22 |  | 2025-01-06 | 2025-04-17 | 2025-04-17 | 2025-07-21 | 2025-07-21 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-223 | System CHW and LTHW FIRST FLOOR
72294 | FSA_F02_2-LTHWR-195-DN015-I16C00_R0 | 0 | true | 13.63 | FSA_F02_2-LTHWR-195-DN015-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2024-12-16 | 2024-12-19 |  | 2024-12-19 | 2025-01-06 | Office 01/07/2025 | 2025-01-22 |  | 2025-01-07 | 2025-04-17 | 2025-05-30 | 2025-06-13 |  | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-223 | System CHW and LTHW FIRST FLOOR
72295 | FSA_F02_2-LTHWR-196-DN020-I16C00_R0 | 0 | true | 3.6 | FSA_F02_2-LTHWR-196-DN020-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2024-12-16 | 2024-12-19 |  | 2024-12-19 | 2024-12-29 | Office 23/04/2025 | 2025-01-22 |  | 2025-01-06 | 2025-04-18 | 2025-04-18 | 2025-07-21 | 2025-07-21 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-223 | System CHW and LTHW FIRST FLOOR
72296 | FSA_F02_2-LTHWR-197-DN020-I16C00_R0 | 0 | true | 3.16 | FSA_F02_2-LTHWR-197-DN020-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2024-12-16 | 2024-12-19 |  | 2024-12-19 | 2025-01-06 | Office 19.03.2025 | 2025-01-22 |  | 2025-01-07 | 2025-04-23 | 2025-04-23 | 2025-07-21 | 2025-07-21 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-223 | System CHW and LTHW FIRST FLOOR
72297 | FSA_F02_2-LTHWR-198-DN020-I16C00_R0 | 0 | true | 3.2 | FSA_F02_2-LTHWR-198-DN020-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2024-12-16 | 2024-12-19 |  | 2024-12-19 | 2025-01-09 | Office 25/04/2025 | 2025-01-22 |  | 2025-01-09 | 2025-04-24 | 2025-04-24 | 2025-07-21 | 2025-07-21 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-223 | System CHW and LTHW FIRST FLOOR
72298 | FSA_F02_2-LTHWR-199-DN025-I16C00_R0 | 0 | true | 10.68 | FSA_F02_2-LTHWR-199-DN025-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2024-12-16 | 2024-12-19 |  | 2024-12-19 | 2025-01-06 | Office 23/04/2025 | 2025-01-22 |  | 2025-01-07 | 2025-04-15 | 2025-04-15 | 2025-04-18 | 2025-04-18 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-205 | System CHW and LTHW FIRST FLOOR
72299 | FSA_F02_2-LTHWR-200-DN015-I16C00_R0 | 0 | true | 2.53 | FSA_F02_2-LTHWR-200-DN015-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2024-12-16 | 2024-12-19 |  | 2024-12-19 | 2025-01-06 | Office 06.06.2025 | 2025-01-22 |  | 2025-01-07 | 2025-05-16 | 2025-05-29 | 2025-05-29 | 2025-05-29 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-205 | System CHW and LTHW FIRST FLOOR
72300 | FSA_F02_2-LTHWR-201-DN015-I16C00_R0 | 0 | true | 3.46 | FSA_F02_2-LTHWR-201-DN015-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2024-12-16 | 2024-12-19 |  | 2024-12-19 | 2025-01-06 | Office 23.06.2025 | 2025-01-22 |  | 2025-01-07 | 2025-05-16 | 2025-06-03 | 2025-06-03 | 2025-06-03 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-205 | System CHW and LTHW FIRST FLOOR
72301 | FSA_F02_2-LTHWR-202-DN015-I16C00_R0 | 0 | true | 2.45 | FSA_F02_2-LTHWR-202-DN015-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2024-12-16 | 2024-12-19 |  | 2024-12-19 | 2025-01-06 | Office 06.06.2025 | 2025-01-22 |  | 2025-01-07 | 2025-05-16 | 2025-05-20 | 2025-06-03 | 2025-06-03 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-205 | System CHW and LTHW FIRST FLOOR
72302 | FSA_F02_2-LTHWR-203-DN020-I16C00_R0 | 0 | true | 1.97 | FSA_F02_2-LTHWR-203-DN020-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2024-12-16 | 2024-12-19 |  | 2024-12-19 | 2025-01-12 | Office 29/04/2025 | 2025-01-22 |  | 2025-01-12 | 2025-04-25 | 2025-04-25 | 2025-05-06 | 2025-05-06 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-223 | System CHW and LTHW FIRST FLOOR
72303 | FSA_F02_2-LTHWR-204-DN020-I16C00_R0 | 0 | true | 1.88 | FSA_F02_2-LTHWR-204-DN020-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2024-12-16 | 2024-12-19 |  | 2024-12-19 | 2025-01-06 | Office 29/04/2025 | 2025-01-22 |  | 2025-01-07 | 2025-04-26 | 2025-04-26 | 2025-05-07 | 2025-05-07 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-223 | System CHW and LTHW FIRST FLOOR
72304 | FSA_F02_2-LTHWR-205-DN020-I16C00_R0 | 0 | true | 2.39 | FSA_F02_2-LTHWR-205-DN020-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2024-12-16 | 2024-12-19 |  | 2024-12-19 | 2025-01-06 | Ivan Tatomirovic 08.05.2025 | 2025-01-22 |  | 2025-01-07 | 2025-04-24 | 2025-04-24 | 2025-05-09 | 2025-05-09 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-223 | System CHW and LTHW FIRST FLOOR
72305 | FSA_F02_2-LTHWR-244-DN025-I16C00_R0 | 0 | false | 1.19 | FSA_F02_2-LTHWR-244-DN025-I16C00_R0 | LPP6A-M-518-01-FSA | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2024-12-16 | 2024-12-22 |  | 2025-01-02 | 2025-01-12 | Office 03.03.2025 | 2025-01-29 |  | 2025-01-12 |  |  |  |  | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-320
72306 | FSA_F02_2-LTHWR-245-DN020-I16C00_R0 | 0 | false | 2.45 | FSA_F02_2-LTHWR-245-DN020-I16C00_R0 | LPP6A-M-518-01-FSA | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2024-12-16 | 2024-12-22 |  | 2025-01-02 | 2025-01-12 | Office 03.03.2025 | 2025-01-29 |  | 2025-01-12 |  |  |  |  | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-320
72307 | FSA_F02_2-LTHWR-246-DN020-I16C00_R0 | 0 | false | 9.14 | FSA_F02_2-LTHWR-246-DN020-I16C00_R0 | LPP6A-M-518-01-FSA | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2024-12-15 | 2024-12-22 |  | 2025-01-02 | 2025-01-12 | Office 04.03.2025 | 2025-01-29 |  | 2025-01-12 |  |  |  |  | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-209
72308 | FSA_F02_2-LTHWR-247-DN015-I16C00_R0 | 0 | true | 6.08 | FSA_F02_2-LTHWR-247-DN015-I16C00_R0 | LPP6A-M-518-01-FSA | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2024-12-15 | 2024-12-22 |  | 2025-01-02 | 2025-01-12 | Office 02.04.2025 | 2025-01-29 |  | 2025-01-12 | 2025-03-28 | 2025-03-28 | 2025-03-28 | 2025-03-28 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-320 | System CHW and LTHW FIRST FLOOR
72309 | FSA_F02_2-LTHWS-181-DN032-I16C00_R0 | 0 | true | 30.41 | FSA_F02_2-LTHWS-181-DN032-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2025-01-08 | 2025-01-14 |  | 2025-01-31 | 2025-04-02 | Office 06.06.2025 | 2025-04-09 |  | 2025-03-31 | 2025-04-25 | 2025-04-26 | 2025-04-30 | 2025-05-01 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-220 | System CHW and LTHW FIRST FLOOR
72310 | FSA_F02_2-LTHWS-182-DN020-I16C00_R0 | 0 | true | 2.7 | FSA_F02_2-LTHWS-182-DN020-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2024-12-15 | 2024-12-22 |  | 2025-01-02 | 2025-01-12 | Office 29/04/2025 | 2025-01-29 |  | 2025-01-12 | 2025-04-28 | 2025-04-28 | 2025-07-21 | 2025-07-21 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-320 | System CHW and LTHW FIRST FLOOR
72311 | FSA_F02_2-LTHWS-183-DN020-I16C00_R0 | 0 | true | 4.12 | FSA_F02_2-LTHWS-183-DN020-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2024-12-15 | 2024-12-22 |  | 2025-01-02 | 2025-01-12 | Office 08.05.2025 | 2025-01-29 |  | 2025-01-12 | 2025-05-05 | 2025-05-05 | 2025-05-07 | 2025-05-07 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-220 | System CHW and LTHW FIRST FLOOR
72312 | FSA_F02_2-LTHWS-184-DN020-I16C00_R0 | 0 | true | 3.74 | FSA_F02_2-LTHWS-184-DN020-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2024-12-15 | 2024-12-22 |  | 2025-01-02 | 2025-01-12 | Office 09/05/2025 | 2025-01-29 |  | 2025-01-12 | 2025-05-09 | 2025-05-09 | 2025-05-09 | 2025-05-09 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-220 | System CHW and LTHW FIRST FLOOR
72313 | FSA_F02_2-LTHWS-185-DN020-I16C00_R0 | 0 | true | 3.66 | FSA_F02_2-LTHWS-185-DN020-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2024-12-15 | 2024-12-22 |  | 2025-01-02 | 2025-01-12 | Office 15.05.2025 | 2025-01-29 |  | 2025-01-12 | 2025-05-14 | 2025-05-14 | 2025-05-14 | 2025-05-14 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-220 | System CHW and LTHW FIRST FLOOR
72314 | FSA_F02_2-LTHWS-186-DN020-I16C00_R0 | 0 | true | 4.12 | FSA_F02_2-LTHWS-186-DN020-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2024-12-15 | 2024-12-22 |  | 2025-01-02 | 2025-01-12 | Office 14/05/2025 | 2025-01-29 |  | 2025-01-12 | 2025-05-13 | 2025-05-13 | 2025-05-13 | 2025-05-13 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-220 | System CHW and LTHW FIRST FLOOR
72315 | FSA_F02_2-LTHWS-187-DN020-I16C00_R0 | 0 | true | 3.68 | FSA_F02_2-LTHWS-187-DN020-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2024-12-15 | 2024-12-22 |  | 2025-01-02 | 2025-01-12 | Office 20/05/2025 | 2025-01-29 |  | 2025-01-12 | 2025-05-16 | 2025-05-16 | 2025-05-16 | 2025-05-16 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-220 | System CHW and LTHW FIRST FLOOR
72316 | FSA_F02_2-LTHWS-188-DN015-I16C00_R0 | 0 | true | 4.91 | FSA_F02_2-LTHWS-188-DN015-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2024-12-15 | 2024-12-22 |  | 2025-01-02 | 2025-01-27 | Office 23.06.2025 | 2025-02-05 |  | 2025-01-27 | 2025-05-13 | 2025-05-13 | 2025-05-13 | 2025-05-13 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-225 | System CHW and LTHW FIRST FLOOR
72317 | FSA_F02_2-LTHWS-189-DN015-I16C00_R0 | 0 | true | 5.03 | FSA_F02_2-LTHWS-189-DN015-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2024-12-15 | 2024-12-22 |  | 2025-01-02 | 2025-01-26 | Office 23.06.2025 | 2025-02-05 |  | 2025-01-27 | 2025-05-14 | 2025-05-14 | 2025-05-14 | 2025-05-14 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-226 | System CHW and LTHW FIRST FLOOR
72318 | FSA_F02_2-LTHWS-190-DN020-I16C00_R0 | 0 | true | 13.95 | FSA_F02_2-LTHWS-190-DN020-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2024-12-15 | 2024-12-15 |  | 2025-01-05 | 2025-01-27 | Office 02.04.2025 | 2025-02-05 |  | 2025-01-27 | 2025-03-25 | 2025-03-26 | 2025-03-27 | 2025-03-27 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-217 | System CHW and LTHW FIRST FLOOR
72319 | FSA_F02_2-LTHWS-191-DN020-I16C00_R0 | 0 | true | 7.86 | FSA_F02_2-LTHWS-191-DN020-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2024-12-15 | 2024-12-15 |  | 2025-01-05 | 2025-01-27 | Office 02.04.2025 | 2025-02-05 |  | 2025-01-27 | 2025-03-26 | 2025-03-26 | 2025-03-27 | 2025-03-27 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-217 | System CHW and LTHW FIRST FLOOR
72320 | FSA_F02_2-LTHWS-192-DN020-I16C00_R0 | 0 | true | 6.89 | FSA_F02_2-LTHWS-192-DN020-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2024-12-15 | 2024-12-15 |  | 2025-01-05 | 2025-01-27 | Office 02.04.2025 | 2025-02-05 |  | 2025-01-27 | 2025-03-29 | 2025-03-29 | 2025-07-21 | 2025-07-21 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-320 | System CHW and LTHW FIRST FLOOR
72321 | FSA_F02_2-LTHWS-193-DN040-I16C00_R0 | 0 | false | 56.32 | FSA_F02_2-LTHWS-193-DN040-I16C00_R0 | LPP6A-M-517-01-FSA | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | [13 empty] | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-223
72322 | FSA_F02_2-LTHWS-194-DN020-I16C00_R0 | 0 | true | 4.31 | FSA_F02_2-LTHWS-194-DN020-I16C00_R0 | LPP6A-M-517-01-FSA | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2024-12-15 | 2024-12-15 |  | 2025-01-05 | 2025-01-30 | Office 18.04.2025 | 2025-02-05 |  | 2025-01-29 | 2025-04-17 | 2025-04-17 | 2025-07-21 | 2025-07-21 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-223 | System CHW and LTHW FIRST FLOOR
72323 | FSA_F02_2-LTHWS-195-DN015-I16C00_R0 | 0 | true | 13.53 | FSA_F02_2-LTHWS-195-DN015-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2024-12-15 | 2024-12-15 |  | 2025-01-05 | 2025-01-27 | Office 01/07/2025 | 2025-02-05 |  | 2025-01-27 | 2025-04-17 | 2025-05-30 | 2025-06-14 |  | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-223 | System CHW and LTHW FIRST FLOOR
72324 | FSA_F02_2-LTHWS-196-DN020-I16C00_R0 | 0 | true | 3.5 | FSA_F02_2-LTHWS-196-DN020-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2024-12-15 | 2024-12-15 |  | 2025-01-05 | 2025-01-30 | Office 23/04/2025 | 2025-02-05 |  | 2025-01-29 | 2025-04-18 | 2025-04-18 | 2025-07-21 | 2025-07-21 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-223 | System CHW and LTHW FIRST FLOOR
72325 | FSA_F02_2-LTHWS-197-DN020-I16C00_R0 | 0 | true | 3.05 | FSA_F02_2-LTHWS-197-DN020-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2025-01-08 | 2025-01-14 |  | 2025-01-21 | 2025-01-30 | Office 19.03.2025 | 2025-02-05 |  | 2025-01-30 | 2025-04-23 | 2025-04-23 | 2025-07-21 | 2025-07-21 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-223 | System CHW and LTHW FIRST FLOOR
72326 | FSA_F02_2-LTHWS-198-DN020-I16C00_R0 | 0 | true | 3.5 | FSA_F02_2-LTHWS-198-DN020-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2024-12-15 | 2024-12-15 |  | 2025-01-05 | 2025-01-30 | Office 25/04/2025 | 2025-02-05 |  | 2025-01-29 | 2025-04-24 | 2025-04-24 | 2025-07-21 | 2025-07-21 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-223 | System CHW and LTHW FIRST FLOOR
72327 | FSA_F02_2-LTHWS-199-DN025-I16C00_R0 | 0 | true | 10.73 | FSA_F02_2-LTHWS-199-DN025-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2024-12-15 | 2024-12-15 |  | 2025-01-05 | 2025-02-26 | Office 23/04/2025 | 2025-03-28 |  | 2025-02-27 | 2025-04-14 | 2025-04-14 | 2025-04-19 | 2025-04-19 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-205 | System CHW and LTHW FIRST FLOOR
72328 | FSA_F02_2-LTHWS-200-DN015-I16C00_R0 | 0 | true | 2.43 | FSA_F02_2-LTHWS-200-DN015-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2024-12-15 | 2024-12-19 |  | 2025-01-06 | 2025-01-30 | Office 06.06.2025 | 2025-02-05 |  | 2025-01-29 | 2025-05-16 | 2025-05-29 | 2025-05-29 | 2025-05-29 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-205 | System CHW and LTHW FIRST FLOOR
72329 | FSA_F02_2-LTHWS-201-DN015-I16C00_R0 | 0 | true | 3.86 | FSA_F02_2-LTHWS-201-DN015-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2024-12-15 | 2024-12-19 |  | 2025-01-06 | 2025-01-26 | Office 23.06.2025 | 2025-02-05 |  | 2025-01-27 | 2025-05-16 | 2025-06-03 | 2025-06-03 | 2025-06-03 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-205 | System CHW and LTHW FIRST FLOOR
72330 | FSA_F02_2-LTHWS-202-DN015-I16C00_R0 | 0 | true | 2.62 | FSA_F02_2-LTHWS-202-DN015-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2024-12-15 | 2024-12-19 |  | 2025-01-06 | 2025-01-30 | Office 06.06.2025 | 2025-02-05 |  | 2025-01-29 | 2025-05-16 | 2025-05-20 | 2025-06-02 | 2025-06-02 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-205 | System CHW and LTHW FIRST FLOOR
72331 | FSA_F02_2-LTHWS-203-DN020-I16C00_R0 | 0 | true | 2.24 | FSA_F02_2-LTHWS-203-DN020-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2024-12-15 | 2024-12-19 |  | 2025-01-06 | 2025-01-30 | Office 29/04/2025 | 2025-02-05 |  | 2025-01-29 | 2025-04-25 | 2025-04-25 | 2025-05-06 | 2025-05-06 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-223 | System CHW and LTHW FIRST FLOOR
72332 | FSA_F02_2-LTHWS-204-DN020-I16C00_R0 | 0 | true | 2.15 | FSA_F02_2-LTHWS-204-DN020-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2024-12-15 | 2024-12-19 |  | 2025-01-06 | 2025-01-31 | Office 29/04/2025 | 2025-02-05 |  | 2025-01-31 | 2025-04-26 | 2025-04-26 | 2025-05-07 | 2025-05-07 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-223 | System CHW and LTHW FIRST FLOOR
72333 | FSA_F02_2-LTHWS-205-DN020-I16C00_R0 | 0 | true | 3.01 | FSA_F02_2-LTHWS-205-DN020-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2024-12-15 | 2024-12-19 |  | 2025-01-06 | 2025-01-30 | Ivan Tatomirovic 08.05.2025 | 2025-02-05 |  | 2025-01-29 | 2025-04-24 | 2025-04-24 | 2025-05-09 | 2025-05-09 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-223 | System CHW and LTHW FIRST FLOOR
72334 | FSA_F02_2-LTHWS-244-DN025-I16C00_R0 | 0 | false | 1.23 | FSA_F02_2-LTHWS-244-DN025-I16C00_R0 | LPP6A-M-518-01-FSA | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2024-12-15 | 2024-12-19 |  | 2025-01-06 | 2025-01-29 |  | 2025-02-05 |  | 2025-01-29 |  |  |  |  | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-320
72335 | FSA_F02_2-LTHWS-245-DN020-I16C00_R0 | 0 | false | 2.43 | FSA_F02_2-LTHWS-245-DN020-I16C00_R0 | LPP6A-M-518-01-FSA | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2024-12-15 | 2024-12-19 |  | 2025-01-06 | 2025-01-29 | Office 04.03.2025 | 2025-02-05 |  | 2025-01-29 |  |  |  |  | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-209
72336 | FSA_F02_2-LTHWS-246-DN020-I16C00_R0 | 0 | false | 9.02 | FSA_F02_2-LTHWS-246-DN020-I16C00_R0 | LPP6A-M-518-01-FSA | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2024-12-15 | 2024-12-19 |  | 2025-01-06 | 2025-01-30 | Office 04.03.2025 | 2025-02-05 |  | 2025-01-29 |  |  |  |  | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-209
72337 | FSA_F02_2-LTHWS-247-DN015-I16C00_R0 | 0 | true | 6.5 | FSA_F02_2-LTHWS-247-DN015-I16C00_R0 | LPP6A-M-518-01-FSA | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-06 | 2024-12-04 | 2024-12-16 | 2024-12-19 |  | 2025-01-06 | 2025-01-26 | Office 02.04.2025 | 2025-02-05 |  | 2025-01-27 | 2025-03-28 | 2025-03-28 | 2025-03-28 | 2025-03-28 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-320 | System CHW and LTHW FIRST FLOOR
72492 | CUB5_PCWR-001-DN600-I16C00_R1 | 1 | true | 55.41 | CUB5_PCWR-001-DN600-I16C00_R1 |  | 1129 | CUB5 | F01 | N/A | TBH-ZAT-2024-12-10 | 2024-12-08 | 2024-12-11 | 2024-12-19 |  | 2025-01-30 | 2025-02-13 | Office 20/05/2025 | 2025-02-19 |  | 2025-02-14 | 2025-03-01 | 2025-03-14 | 2025-03-22 | 2025-04-17 | 1361 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 20.01.2025 00:00:00 | CUB5 | System PCW 01
72493 | CUB5_PCWR-002-DN600-I16C00_R1 | 1 | true | 31.01 | CUB5_PCWR-002-DN600-I16C00_R1 |  | 1129 | CUB5 | F01 | N/A | TBH-ZAT-2024-12-10 | 2024-12-08 | 2024-12-11 | 2024-12-19 |  | 2025-02-11 | 2025-02-20 | Zeljko Milisa 04.03.2025 | 2025-02-26 |  | 2025-02-20 | 2025-04-08 | 2025-04-17 |  | 2025-03-22 | 1361 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 22.01.2025 00:00:00 | CUB5 | System PCW 01
72494 | CUB5_PCWR-003-DN450-I16C00_R1 | 1 | true | 16.01 | CUB5_PCWR-003-DN450-I16C00_R1 |  | 1129 | CUB5 | F01 | N/A | TBH-ZAT-2024-12-10 | 2024-12-08 | 2024-12-12 | 2024-12-19 |  | 2025-02-06 | 2025-02-13 | Zeljko Milisa 25.02.2025 | 2025-02-19 |  | 2025-02-14 | 2025-03-03 | 2025-03-13 | 2025-04-26 |  | 1361 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 24.01.2025 00:00:00 | CUB5 | System PCW 01/System PCW CUB5
72495 | CUB5_PCWR-026-DN50-I16C00_R1 | 1 | true | 1.23 | CUB5_PCWR-026-DN50-I16C00_R1 |  | 1129 | CUB5 | F01 | N/A | TBH-ZAT-2024-12-10 | 2024-12-08 | 2024-12-12 | 2024-12-19 |  | 2025-01-06 | 2025-01-29 | Zeljko Milisa 09.04.2025 | 2025-02-05 |  | 2025-01-30 |  | 2025-03-22 |  |  | 1361 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | CUB5 | System PCW 01
72496 | CUB5_PCWS-001-DN600-I16C00_R1 | 1 | true | 57.64 | CUB5_PCWS-001-DN600-I16C00_R1 |  | 1129 | CUB5 | F01 | N/A | TBH-ZAT-2024-12-10 | 2024-12-08 | 2024-12-12 | 2024-12-19 |  | 2025-02-03 | 2025-02-07 | Office 17.02.2025 | 2025-02-12 |  | 2025-02-14 | 2025-03-01 | 2025-03-14 | 2025-03-22 | 2025-04-17 | 1361 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 20.01.2025 00:00:00 | CUB5 | System PCW 01
72497 | CUB5_PCWS-002-DN600-I16C00_R1 | 1 | true | 30.02 | CUB5_PCWS-002-DN600-I16C00_R1 |  | 1129 | CUB5 | F01 | N/A | TBH-ZAT-2024-12-10 | 2024-12-08 | 2024-12-12 | 2024-12-19 |  | 2025-02-11 | 2025-02-28 | Office 20/05/2025 | 2025-03-05 |  | 2025-02-28 | 2025-04-05 | 2025-04-17 | 2025-05-08 | 2025-03-22 | 1361 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 22.01.2025 00:00:00 | CUB5 | System PCW 01
72498 | CUB5_PCWS-003-DN450-I16C00_R1 | 1 | true | 14.4 | CUB5_PCWS-003-DN450-I16C00_R1 |  | 1129 | CUB5 | F01 | N/A | TBH-ZAT-2024-12-10 | 2024-12-08 | 2024-12-12 | 2024-12-19 | Prefabricated on site | 2025-02-11 |  | Zeljko Milisa 10.02.2025 | 2025-02-10 |  | 2025-02-10 | 2025-02-10 | 2025-02-25 | 2025-04-17 |  | 1361 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 24.01.2025 00:00:00 | CUB5 | System PCW 01/System PCW CUB5
72499 | FSA_F02_2-CHWR-193-DN040-I16C00_R1 | 1 | true | 56.26 | FSA_F02_2-CHWR-193-DN040-I16C00_R1 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-10 | 2024-12-08 | 2025-01-05 | 2024-12-19 |  | 2025-01-08 | 2025-04-02 | Office 01/05/2025 | 2025-04-09 |  | 2025-03-31 | 2025-04-14 | 2025-04-21 | 2025-04-24 | 2025-05-01 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-223 | System CHW and LTHW FIRST FLOOR
72500 | FSA_F02_2-CHWS-193-DN040-I16C00_R1 | 1 | true | 56.4 | FSA_F02_2-CHWS-193-DN040-I16C00_R1 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-10 | 2024-12-08 | 2025-01-05 | 2024-12-19 |  | 2025-01-08 | 2025-04-02 | Office 01/05/2025 | 2025-04-09 |  | 2025-03-31 | 2025-04-16 | 2025-04-22 | 2025-04-24 | 2025-04-30 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-223 | System CHW and LTHW FIRST FLOOR
72501 | FSA_F02_2-LTHWR-193-DN040-I16C00_R1 | 1 | true | 55.93 | FSA_F02_2-LTHWR-193-DN040-I16C00_R1 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-10 | 2024-12-08 | 2025-01-05 | 2024-12-19 |  | 2025-01-08 | 2025-04-02 | Office 01/05/2025 | 2025-04-09 |  | 2025-03-31 | 2025-04-14 | 2025-04-21 | 2025-04-16 | 2025-04-30 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-223 | System CHW and LTHW FIRST FLOOR
72502 | FSA_F02_2-LTHWS-193-DN040-I16C00_R1 | 1 | true | 56.02 | FSA_F02_2-LTHWS-193-DN040-I16C00_R1 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-10 | 2024-12-08 | 2025-01-05 | 2024-12-19 |  | 2025-01-08 | 2025-04-02 | Office 01/05/2025 | 2025-04-09 |  | 2025-03-31 | 2025-04-14 | 2025-04-19 | 2025-04-22 | 2025-04-30 | 1360 | 193 |  |  |  | 194 | SEP | SEP |  |  |  |  | 25.12.2024 00:00:00 | 2-223 | System CHW and LTHW FIRST FLOOR
72686 | FSA_F02_1-LTHWR-272-DN015-I16C00_R0 | 0 | true | 5.81 | FSA_F02_1-LTHWR-272-DN015-I16C00_R0 |  | 1129 | FSA South | F02 | FoamInside | TBH-ZAT-2024-12-13 | 2024-12-11 | 2025-01-08 | 2025-01-14 |  | 2025-01-21 | 2025-01-30 | Office 26/04/2025 | 2025-02-05 |  | 2025-01-29 | 2025-04-10 | 2025-04-10 | 2025-04-26 | 2025-05-30 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-011 | System CHW and LTHW FIRST FLOOR
72687 | FSA_F02_1-LTHWR-273-DN015-I16C00_R0 | 0 | true | 10.84 | FSA_F02_1-LTHWR-273-DN015-I16C00_R0 |  | 1129 | FSA South | F02 | FoamInside | TBH-ZAT-2024-12-13 | 2024-12-11 | 2025-01-08 | 2025-01-14 |  | 2025-01-21 | 2025-01-30 | Office 26/04/2025 | 2025-02-05 |  | 2025-01-30 | 2025-04-14 | 2025-04-18 | 2025-04-26 | 2025-05-30 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-201 | System CHW and LTHW FIRST FLOOR
72688 | FSA_F02_1-LTHWS-272-DN015-I16C00_R0 | 0 | true | 5.46 | FSA_F02_1-LTHWS-272-DN015-I16C00_R0 |  | 1129 | FSA South | F02 | FoamInside | TBH-ZAT-2024-12-13 | 2024-12-11 | 2025-01-08 | 2025-01-14 |  | 2025-01-21 | 2025-02-03 | Office 26/04/2025 | 2025-02-05 |  | 2025-02-06 | 2025-04-10 | 2025-04-10 | 2025-04-26 | 2025-05-30 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-011 | System CHW and LTHW FIRST FLOOR
72689 | FSA_F02_1-LTHWS-273-DN015-I16C00_R0 | 0 | true | 10.03 | FSA_F02_1-LTHWS-273-DN015-I16C00_R0 |  | 1129 | FSA South | F02 | FoamInside | TBH-ZAT-2024-12-13 | 2024-12-11 | 2025-01-10 | 2025-01-14 |  | 2025-01-21 | 2025-01-30 | Office 26/04/2025 | 2025-02-05 |  | 2025-01-30 | 2025-04-14 | 2025-04-18 | 2025-04-26 | 2025-05-30 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-201 | System CHW and LTHW FIRST FLOOR
72690 | FSA_F02_2-LTHWR-269-DN015-I16C00_R0 | 0 | true | 13.92 | FSA_F02_2-LTHWR-269-DN015-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-13 | 2024-12-11 | 2025-01-08 | 2025-01-14 |  | 2025-01-21 | 2025-01-30 | Office 01/07/2025 | 2025-02-05 |  | 2025-01-30 | 2025-04-17 | 2025-05-14 | 2025-05-14 | 2025-05-30 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-234 | System CHW and LTHW FIRST FLOOR
72691 | FSA_F02_2-LTHWS-269-DN015-I16C00_R0 | 0 | true | 13.47 | FSA_F02_2-LTHWS-269-DN015-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2024-12-13 | 2024-12-11 | 2025-01-08 | 2025-01-14 |  | 2025-01-21 | 2025-01-30 | Office 01/07/2025 | 2025-02-05 |  | 2025-01-30 | 2025-04-17 | 2025-05-14 | 2025-05-15 | 2025-05-30 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-234 | System CHW and LTHW FIRST FLOOR
72694 | CUB4_CWR-001-DN450-GFSDR17_R0 | 0 | false | 18.9 | CUB4_CWR-001-DN450-GFSDR17_R0 | LPP6A-M-543-XX-CUB | 1272 | CUB4 | F01 | N/A | TBH-ZAT-2024-12-16 | 2024-12-14 | [13 empty] | 1629 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | CUB4
72695 | CUB4_CWR-005-DN450-GFSDR17_R0 | 0 | false | 12.57 | CUB4_CWR-005-DN450-GFSDR17_R0 | LPP6A-M-543-XX-CUB | 1272 | CUB4 | F01 | N/A | TBH-ZAT-2024-12-16 | 2024-12-14 | [13 empty] | 1629 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | CUB4
72696 | CUB4_CWR-005-DN500-GFSDR17_R0 | 0 | false | 20.44 | CUB4_CWR-005-DN500-GFSDR17_R0 | LPP6A-M-543-XX-CUB | 1272 | CUB4 | F01 | N/A | TBH-ZAT-2024-12-16 | 2024-12-14 | [13 empty] | 1629 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | CUB4
72697 | CUB4_CWR-007-DN025-GFSDR11_R0 | 0 | true | 11.48 | CUB4_CWR-007-DN025-GFSDR11_R0 | LPP6A-M-543-XX-CUB | 1273 | CUB4 | F01 | N/A | TBH-ZAT-2024-12-16 | 2024-12-14 | [5 empty] | Adrijan Vuckovic 16.04.2025 | [7 empty] | 1629 | 193 | Line on Hold |  |  | 194 | SEP | SEP | [5 empty] | CUB4 | NO TESTING REQUIRED
72698 | CUB4_CWR-026-DN020-GFSDR11_R0 | 0 | false | 1.31 | CUB4_CWR-026-DN020-GFSDR11_R0 | LPP6A-M-543-XX-CUB | 1273 | CUB4 | F01 | N/A | TBH-ZAT-2024-12-16 | 2024-12-14 | [13 empty] | 1629 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | CUB4
72699 | CUB4_CWR-027-DN020-GFSDR11_R0 | 0 | true | 2.21 | CUB4_CWR-027-DN020-GFSDR11_R0 | LPP6A-M-543-XX-CUB | 1273 | CUB4 | F01 | N/A | TBH-ZAT-2024-12-16 | 2024-12-14 | [5 empty] | Adrijan Vuckovic 16.04.2025 | [7 empty] | 1629 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | CUB4 | NO TESTING REQUIRED
72700 | CUB4_CWS-002-DN900-GFSDR33_R0 | 0 | true | 6.01 | CUB4_CWS-002-DN900-GFSDR33_R0 |  | 1274 | CUB4 | F01 | N/A | TBH-ZAT-2024-12-16 | 2024-12-14 | [5 empty] | Adrijan Vuckovic 16.04.2025 |  |  |  | 2025-06-15 | 2025-06-15 |  |  | 1629 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | CUB4 | NO TESTING REQUIRED
72701 | CUB4_CWS-003-DN900-GFSDR33_R0 | 0 | true | 6.01 | CUB4_CWS-003-DN900-GFSDR33_R0 |  | 1274 | CUB4 | F01 | N/A | TBH-ZAT-2024-12-16 | 2024-12-14 | [5 empty] | Adrijan Vuckovic 16.04.2025 |  |  |  | 2025-06-15 | 2025-06-15 | 2025-06-15 |  | 1629 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | CUB4 | NO TESTING REQUIRED
72702 | CUB4_CWS-007-DN300-GFSDR17_R0 | 0 | true | 4.37 | CUB4_CWS-007-DN300-GFSDR17_R0 |  | 1272 | CUB4 | F01 | N/A | TBH-ZAT-2024-12-16 | 2024-12-14 | [5 empty] | Adrijan Vuckovic 16.04.2025 | [5 empty] | 2025-04-17 |  | 1629 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | CUB4 | NO TESTING REQUIRED
72703 | CUB4_CWS-008-DN300-GFSDR17_R0 | 0 | true | 4.38 | CUB4_CWS-008-DN300-GFSDR17_R0 |  | 1272 | CUB4 | F01 | N/A | TBH-ZAT-2024-12-16 | 2024-12-14 | [5 empty] | Adrijan Vuckovic 16.04.2025 | [5 empty] | 2025-04-17 |  | 1629 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | CUB4 | NO TESTING REQUIRED
72704 | CUB5_CWR-001-DN500-GFSDR17_R0 | 0 | false | 20.7 | CUB5_CWR-001-DN500-GFSDR17_R0 | LPP6A-M-543-XX-CUB | 1272 | CUB5 | F01 | N/A | TBH-ZAT-2024-12-16 | 2024-12-14 | [13 empty] | 1629 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | CUB5
72705 | CUB5_CWR-004-DN450-GFSDR17_R0 | 0 | true | 19.28 | CUB5_CWR-004-DN450-GFSDR17_R0 | LPP6A-M-543-XX-CUB | 1272 | CUB5 | F01 | N/A | TBH-ZAT-2024-12-16 | 2024-12-14 | [5 empty] | Adrijan Vuckovic 16.04.2025 | [5 empty] | 2025-06-19 |  | 1629 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | CUB5 | NO TESTING REQUIRED
72706 | CUB5_CWR-005-DN450-GFSDR17_R0 | 0 | true | 12.46 | CUB5_CWR-005-DN450-GFSDR17_R0 |  | 1272 | CUB5 | F01 | N/A | TBH-ZAT-2024-12-16 | 2024-12-14 | [5 empty] | Adrijan Vuckovic 16.04.2025 | [5 empty] | 2025-06-19 |  | 1629 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | CUB5 | NO TESTING REQUIRED
72707 | CUB5_CWR-006-DN025-GFSDR11_R0 | 0 | true | 11.51 | CUB5_CWR-006-DN025-GFSDR11_R0 |  | 1273 | CUB5 | F01 | N/A | TBH-ZAT-2024-12-16 | 2024-12-14 | [5 empty] | Adrijan Vuckovic 16.04.2025 | [7 empty] | 1629 | 193 | Line on Hold |  |  | 194 | SEP | SEP | [5 empty] | CUB5 | NO TESTING REQUIRED
72708 | CUB5_CWR-026-DN020-GFSDR11_R0 | 0 | true | 2.22 | CUB5_CWR-026-DN020-GFSDR11_R0 |  | 1273 | CUB5 | F01 | N/A | TBH-ZAT-2024-12-16 | 2024-12-14 | [5 empty] | Adrijan Vuckovic 16.04.2025 | [7 empty] | 1629 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | CUB5 | NO TESTING REQUIRED
72709 | CUB5_CWR-028-DN020-GFSDR17_R0 | 0 | true | 1.32 | CUB5_CWR-028-DN020-GFSDR17_R0 |  | 1273 | CUB5 | F01 | N/A | TBH-ZAT-2024-12-16 | 2024-12-14 | [5 empty] | Adrijan Vuckovic 16.04.2025 | [7 empty] | 1629 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | CUB5 | NO TESTING REQUIRED
72710 | CUB4_CWS-001-DN600-GFSDR17_R0 | 0 | true | 6.1 | CUB4_CWS-001-DN600-GFSDR17_R0 |  | 1272 | CUB5 | F01 | N/A | TBH-ZAT-2024-12-16 | 2024-12-14 | [5 empty] | Adrijan Vuckovic 16.04.2025 |  |  |  | 2025-04-17 | 2025-04-26 |  | 2025-03-22 | 1629 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | CUB5 | NO TESTING REQUIRED
72711 | CUB5_CWS-002-DN600-GFSDR17_R0 | 0 | true | 10.01 | CUB5_CWS-002-DN600-GFSDR17_R0 |  | 1272 | CUB5 | F01 | N/A | TBH-ZAT-2024-12-16 | 2024-12-14 | [5 empty] | Adrijan Vuckovic 16.04.2025 | [7 empty] | 1629 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | CUB5 | NO TESTING REQUIRED
72712 | CUB5_CWS-003-DN200-GFSDR17_R0 | 0 | false | 1.74 | CUB5_CWS-003-DN200-GFSDR17_R0 | LPP6A-M-543-XX-CUB | 1272 | CUB5 | F01 | N/A | TBH-ZAT-2024-12-16 | 2024-12-14 |  |  | TO BE DELETED | [10 empty] | 1629 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | CUB5
72713 | CUB5_CWS-003-DN900-GFSDR33_R0 | 0 | true | 6.02 | CUB5_CWS-003-DN900-GFSDR33_R0 | LPP6A-M-543-XX-CUB | 1274 | CUB5 | F01 | N/A | TBH-ZAT-2024-12-16 | 2024-12-14 | [5 empty] | Adrijan Vuckovic 16.04.2025 |  |  |  | 2025-06-15 | 2025-06-15 |  |  | 1629 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | CUB5 | NO TESTING REQUIRED
72714 | CUB5_CWS-004-DN900-GFSDR33_R0 | 0 | true | 6.02 | CUB5_CWS-004-DN900-GFSDR33_R0 |  | 1274 | CUB5 | F01 | N/A | TBH-ZAT-2024-12-16 | 2024-12-14 | [5 empty] | Adrijan Vuckovic 16.04.2025 |  |  |  | 2025-06-15 | 2025-06-15 |  |  | 1629 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | CUB5 | NO TESTING REQUIRED
72715 | CUB5_CWS-007-DN300-GFSDR17_R0 | 0 | true | 3.3 | CUB5_CWS-007-DN300-GFSDR17_R0 |  | 1272 | CUB5 | F01 | N/A | TBH-ZAT-2024-12-16 | 2024-12-14 | [5 empty] | Adrijan Vuckovic 16.04.2025 | [5 empty] | 2025-04-17 |  | 1629 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | CUB5 | NO TESTING REQUIRED
72716 | CUB5_CWS-008-DN300-GFSDR17_R0 | 0 | true | 4.39 | CUB5_CWS-008-DN300-GFSDR17_R0 |  | 1272 | CUB5 | F01 | N/A | TBH-ZAT-2024-12-16 | 2024-12-14 | [5 empty] | Adrijan Vuckovic 16.04.2025 | [5 empty] | 2025-04-17 |  | 1629 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | CUB5 | NO TESTING REQUIRED
72717 | FSA_ROF-CHWR-003-DN150-I16C00_R0 | 0 | false | 14.02 | FSA_ROF-CHWR-003-DN150-I16C00_R0 | LPP6A-M-506-XX-FSA | 1129 | FSA Roof | Roof | FoamOutside | TBH-ZAT-2024-12-16 | 2024-12-14 | 2025-01-06 | 2025-01-14 | [11 empty] | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | External Roof South
72718 | FSA_ROF-CHWR-023-DN080-I16C00_R0 | 0 | true | 15.91 | FSA_ROF-CHWR-023-DN080-I16C00_R0 | LPP6A-M-506-XX-FSA | 1129 | FSA Roof | Roof | FoamOutside | TBH-ZAT-2024-12-16 | 2024-12-14 | 2025-01-08 | 2025-01-14 |  | 2025-01-22 | 2025-02-07 | Office 23.06.2025 | 2025-03-28 |  | 2025-02-14 | 2025-05-12 | 2025-05-12 | 2025-05-13 | 2025-05-30 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | External Roof South | System CHW and LTHW FIRST FLOOR
72719 | FSA_ROF-CHWS-009-DN150-I16C00_R0 | 0 | false | 16.88 | FSA_ROF-CHWS-009-DN150-I16C00_R0 | LPP6A-M-506-XX-FSA | 1129 | FSA Roof | Roof | FoamOutside | TBH-ZAT-2024-12-16 | 2024-12-14 | 2025-01-10 | 2025-01-14 | [11 empty] | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | External Roof South
72720 | FSA_ROF-CHWS-023-DN080-I16C00_R0 | 0 | true | 15.5 | FSA_ROF-CHWS-023-DN080-I16C00_R0 | LPP6A-M-506-XX-FSA | 1129 | FSA Roof | Roof | FoamOutside | TBH-ZAT-2024-12-16 | 2024-12-14 | 2025-01-10 | 2025-01-14 |  | 2025-01-22 | 2025-02-03 | Office 23.06.2025 | 2025-02-05 |  | 2025-02-06 | 2025-04-26 | 2025-04-28 | 2025-04-28 | 2025-05-30 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | External Roof South | System CHW and LTHW FIRST FLOOR
72721 | FSA_ROF-PHTGR-008-DN100-I16C00_R0 | 0 | true | 8.3 | FSA_ROF-PHTGR-008-DN100-I16C00_R0 |  | 1129 | FSA Roof | Roof | FoamInside | TBH-ZAT-2024-12-16 | 2024-12-14 | 2025-01-10 | 2025-01-14 |  | 2025-01-22 | 2025-02-07 | Office 23.06.2025 | 2025-03-28 |  | 2025-02-14 | 2025-04-23 | 2025-04-24 | 2025-04-26 | 2025-05-30 | 1368 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | External Roof South | System PHTG
72722 | FSA_ROF-PHTGS-015-DN150-I16C00_R0 | 0 | true | 8.27 | FSA_ROF-PHTGS-015-DN150-I16C00_R0 |  | 1129 | FSA Roof | Roof | FoamInside | TBH-ZAT-2024-12-16 | 2024-12-14 | 2025-01-10 | 2025-01-14 |  | 2025-01-22 | 2025-02-07 | Office 23.06.2025 | 2025-03-28 |  | 2025-02-14 | 2025-04-23 | 2025-04-25 | 2025-04-25 | 2025-04-29 | 1368 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | External Roof South | System PHTG
72822 | CUB4_TWMU-001-DN200-GFSDR11_R0 | 0 | false | 11.76 | CUB4_TWMU-001-DN200-GFSDR11_R0 | LPP6A-M-543-XX-CUB | 1273 | CUB4 | F01 | N/A | TBH-ZAT-2024-12-18 | 2024-12-16 | [13 empty] | 1630 | 193 |  |  |  |  | SEP | SEP | [5 empty] | CUB4
72823 | CUB5_TWMU-001-DN200-GFSDR11_R0 | 0 | false | 17.1 | CUB5_TWMU-001-DN200-GFSDR11_R0 | LPP6A-M-543-XX-CUB | 1273 | CUB5 | F01 | N/A | TBH-ZAT-2024-12-18 | 2024-12-16 | [13 empty] | 1630 | 193 |  |  |  |  | SEP | SEP | [5 empty] | CUB5
72824 | FSA_F01-CHWR-007-DN150-I16C00_R0 | 0 | false | 24.86 | FSA_F01-CHWR-007-DN150-I16C00_R0 | LPP6A-M-511-00-FSA | 1129 | FSA South Corridor | F01 | FoamInside | TBH-ZAT-2024-12-20 | 2024-12-18 | [13 empty] | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-200
72825 | FSA_F01-CHWS-014-DN150-I16C00_R0 | 0 | false | 28 | FSA_F01-CHWS-014-DN150-I16C00_R0 | LPP6A-M-511-00-FSA | 1129 | FSA South Corridor | F01 | FoamInside | TBH-ZAT-2024-12-20 | 2024-12-18 | [13 empty] | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-200
72826 | FSA_F01-LTHWR-008-DN100-I16C00_R0 | 0 | false | 32.07 | FSA_F01-LTHWR-008-DN100-I16C00_R0 | LPP6A-M-515-00-FSA | 1129 | FSA South Corridor | F01 | FoamInside | TBH-ZAT-2024-12-20 | 2024-12-18 | [13 empty] | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-200
72827 | FSA_F01-LTHWS-008-DN100-I16C00_R0 | 0 | false | 32.58 | FSA_F01-LTHWS-008-DN100-I16C00_R0 | LPP6A-M-515-00-FSA | 1129 | FSA South Corridor | F01 | FoamInside | TBH-ZAT-2024-12-20 | 2024-12-18 | [13 empty] | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-200
72828 | FSA_F01-PCWR-007-DN250-I16C00_R0 | 0 | false | 8.22 | FSA_F01-PCWR-007-DN250-I16C00_R0 | LPP6A-M-504-XX-FSA | 1129 | FSA Mech Wet Room | F01 | N/A | TBH-ZAT-2024-12-20 | 2024-12-18 | [13 empty] | 1352 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308
72829 | FSA_F01-PCWR-008-DN250-I16C00_R0 | 0 | false | 2.33 | FSA_F01-PCWR-008-DN250-I16C00_R0 | LPP6A-M-504-XX-FSA | 1129 | FSA Mech Wet Room | F01 | N/A | TBH-ZAT-2024-12-20 | 2024-12-18 | [13 empty] | 1352 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308
72830 | FSA_F01-PCWR-009-DN250-I16C00_R0 | 0 | false | 32.03 | FSA_F01-PCWR-009-DN250-I16C00_R0 | LPP6A-M-504-XX-FSA | 1129 | FSA Mech Wet Room | F01 | N/A | TBH-ZAT-2024-12-20 | 2024-12-18 | [13 empty] | 1352 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-200
72831 | FSA_F01-PCWR-010-DN250-I16C00_R0 | 0 | false | 30.82 | FSA_F01-PCWR-010-DN250-I16C00_R0 | LPP6A-M-504-XX-FSA | 1129 | FSA Mech Wet Room | F01 | N/A | TBH-ZAT-2024-12-20 | 2024-12-17 | 2025-01-16 | 2025-01-19 | [11 empty] | 1352 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308
72832 | FSA_F01-PCWR-011-DN250-I16C00_R0 | 0 | true | 1.75 | FSA_F01-PCWR-011-DN250-I16C00_R0 | LPP6A-M-504-XX-FSA | 1129 | FSA Mech Wet Room | F01 | N/A | TBH-ZAT-2024-12-20 | 2024-12-17 | 2025-01-16 | 2025-01-19 |  | 2025-01-31 | 2025-03-07 | Office 09.04.2025 | 2025-03-12 |  | 2025-03-10 | 2025-04-05 | 2025-04-07 | 2025-04-07 | 2025-04-08 | 1352 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System PCW 01
72833 | FSA_ROF-CHWR-004-DN150-I16C00_R0 | 0 | true | 13.17 | FSA_ROF-CHWR-004-DN150-I16C00_R0 |  | 1129 | FSA Roof | Roof | FoamInside | TBH-ZAT-2024-12-20 | 2024-12-17 | 2025-01-14 | 2025-01-19 |  | 2025-01-27 | 2025-03-25 | Office 22/05/2025 | 2025-03-28 |  | 2025-03-27 | 2025-05-19 | 2025-05-20 | 2025-05-21 | 2025-05-21 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | External Roof South | System CHW and LTHW GROUND FLOOR
72834 | FSA_ROF-CHWS-010-DN150-I16C00_R0 | 0 | true | 15.17 | FSA_ROF-CHWS-010-DN150-I16C00_R0 |  | 1129 | FSA Roof | Roof | FoamInside | TBH-ZAT-2024-12-20 | 2024-12-17 | 2025-01-14 | 2025-01-19 |  | 2025-01-27 | 2025-03-26 | Office 22/05/2025 | 2025-03-28 |  | 2025-03-27 | 2025-05-19 | 2025-05-19 | 2025-05-21 | 2025-05-21 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | External Roof South | System CHW and LTHW GROUND FLOOR
72835 | FSA_ROF-PHTGR-014-DN150-I16C00_R0 | 0 | false | 7.58 | FSA_ROF-PHTGR-014-DN150-I16C00_R0 | LPP6A-M-504-XX-FSA | 1129 | FSA Roof | Roof | FoamInside | TBH-ZAT-2024-12-20 | 2024-12-18 | [13 empty] | 1368 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-200
72836 | FSA_ROF-PHTGR-015-DN100-I16C00_R0 | 0 | true | 11.07 | FSA_ROF-PHTGR-015-DN100-I16C00_R0 | LPP6A-M-504-XX-FSA | 1129 | FSA Roof | Roof | FoamInside | TBH-ZAT-2024-12-20 | 2024-12-17 | 2025-01-14 | 2025-01-19 |  | 2025-01-23 | 2025-02-10 | Office 16.05.2025 | 2025-03-28 |  | 2025-02-14 | 2025-04-01 | 2025-04-03 | 2025-05-07 | 2025-05-12 | 1368 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | External Roof North | System PHTG
72837 | FSA_ROF-PHTGR-016-DN080-I16C00_R0 | 0 | true | 15.43 | FSA_ROF-PHTGR-016-DN080-I16C00_R0 |  | 1129 | FSA Roof | Roof | FoamInside | TBH-ZAT-2024-12-20 | 2024-12-17 | 2025-01-14 | 2025-01-19 |  | 2025-01-23 | 2025-02-07 | Office 16.05.2025 | 2025-03-28 |  | 2025-03-27 | 2025-04-23 | 2025-04-24 | 2025-05-06 | 2025-05-09 | 1368 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | External Roof North | System PHTG
72838 | FSA_ROF-PHTGR-017-DN100-I16C00_R0 | 0 | true | 16.76 | FSA_ROF-PHTGR-017-DN100-I16C00_R0 |  | 1129 | FSA Roof | Roof | FoamInside | TBH-ZAT-2024-12-20 | 2024-12-17 | 2025-01-13 | 2025-01-19 |  | 2025-01-23 | 2025-02-12 | Office 13/05/2025 | 2025-03-28 |  | 2025-02-14 | 2025-05-07 | 2025-05-13 | 2025-05-13 | 2025-05-13 | 1368 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | External Roof North | System PHTG
72839 | FSA_ROF-PHTGR-018-DN080-I16C00_R0 | 0 | true | 14.8 | FSA_ROF-PHTGR-018-DN080-I16C00_R0 |  | 1129 | FSA Roof | Roof | FoamInside | TBH-ZAT-2024-12-20 | 2024-12-17 | 2025-01-14 | 2025-01-19 |  | 2025-01-23 | 2025-02-10 | Office 08.05.2025 | 2025-03-28 |  | 2025-02-14 | 2025-04-03 | 2025-04-04 | 2025-05-08 | 2025-05-30 | 1368 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | External Roof North | System PHTG
72840 | FSA_ROF-PHTGS-018-DN100-I16C00_R0 | 0 | true | 8.83 | FSA_ROF-PHTGS-018-DN100-I16C00_R0 |  | 1129 | FSA Roof | Roof | FoamInside | TBH-ZAT-2024-12-20 | 2024-12-17 | 2025-01-13 | 2025-01-19 |  | 2025-01-23 | 2025-02-11 | Office 16.05.2025 | 2025-03-28 |  | 2025-02-14 | 2025-04-29 | 2025-05-01 | 2025-05-01 | 2025-05-12 | 1368 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | External Roof North | System PHTG
72841 | FSA_ROF-PHTGS-019-DN080-I16C00_R0 | 0 | true | 11.44 | FSA_ROF-PHTGS-019-DN080-I16C00_R0 |  | 1129 | FSA Roof | Roof | FoamInside | TBH-ZAT-2024-12-20 | 2024-12-17 | 2025-01-15 | 2025-01-19 |  | 2025-01-23 | 2025-02-07 | Office 16.05.2025 | 2025-03-28 |  | 2025-03-27 | 2025-04-18 | 2025-04-24 | 2025-05-09 | 2025-05-09 | 1368 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | External Roof North | System PHTG
72842 | FSA_ROF-PHTGS-030-DN150-I16C00_R0 | 0 | false | 9.3 | FSA_ROF-PHTGS-030-DN150-I16C00_R0 | LPP6A-M-504-XX-FSA | 1129 | FSA Roof | Roof | FoamInside | TBH-ZAT-2024-12-20 | 2024-12-17 | 2025-01-15 | 2025-01-19 |  | 2025-01-27 | [9 empty] | 1368 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-200
72843 | FSA_ROF-PHTGS-031-DN100-I16C00_R0 | 0 | true | 14.19 | FSA_ROF-PHTGS-031-DN100-I16C00_R0 | LPP6A-M-504-XX-FSA | 1129 | FSA Roof | Roof | FoamInside | TBH-ZAT-2024-12-20 | 2024-12-17 | 2025-01-13 | 2025-01-19 |  | 2025-01-23 | 2025-02-11 | Office 08.05.2025 | 2025-03-28 |  | 2025-02-14 | 2025-04-04 | 2025-04-05 | 2025-05-07 | 2025-05-30 | 1368 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | External Roof North | System PHTG
72844 | FSA_ROF-PHTGS-032-DN080-I16C00_R0 | 0 | true | 11.64 | FSA_ROF-PHTGS-032-DN080-I16C00_R0 |  | 1129 | FSA Roof | Roof | FoamInside | TBH-ZAT-2024-12-20 | 2024-12-17 | 2025-01-16 | 2025-01-19 |  | 2025-01-23 | 2025-02-07 | Office 27.05.2025 | 2025-03-28 |  | 2025-03-27 | 2025-04-07 | 2025-04-08 | 2025-04-08 | 2025-05-01 | 1368 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | External Roof North | System PHTG
81798 | FSA_F01-CHWR-001-DN150-I16C00_R0 | 0 | false | 2.76 | FSA_F01-CHWR-001-DN150-I16C00_R0 | LPP6A-M-506-XX-FSA | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-01-17 | 2025-01-15 | [13 empty] | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308
81799 | FSA_F01-CHWR-002-DN150-I16C00_R0 | 0 | true | 2.58 | FSA_F01-CHWR-002-DN150-I16C00_R0 | LPP6A-M-506-XX-FSA | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-01-17 | 2025-01-15 | 2025-02-19 | 2025-02-24 |  | 2025-03-07 | 2025-03-25 | Dejan Todorovski 16.04.2025 |  |  | 2025-03-27 | 2025-03-25 | 2025-03-31 | 2025-04-14 | 2025-04-14 | 1359 | 193 | Working ISO delivered 14.04.25 - Spools to be checked |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System CHW and LTHW GROUND FLOOR
81800 | FSA_F01-CHWR-009-DN20-I16C00_R0 | 0 | true | 0 | FSA_F01-CHWR-009-DN20-I16C00_R0 |  | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-01-17 | 2025-01-15 | 2025-02-13 | 2025-02-24 | To be sent to site | 2025-03-06 | 2025-03-06 |  | 2025-03-06 |  | 2025-03-06 | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System CHW and LTHW GROUND FLOOR
81801 | FSA_F01-CHWR-017-DN100-I16C00_R0 | 0 | true | 0 | FSA_F01-CHWR-017-DN100-I16C00_R0 |  | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-01-17 | 2025-01-15 | 2025-02-13 | 2025-02-24 | To be delivered to Site | 2025-03-06 | 2025-03-06 |  | 2025-03-06 |  | 2025-03-06 |  |  |  | 2025-05-30 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System CHW and LTHW GROUND FLOOR
81802 | FSA_F01-CHWS-001-DN150-I16C00_R0 | 0 | false | 4.23 | FSA_F01-CHWS-001-DN150-I16C00_R0 | LPP6A-M-506-XX-FSA | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-01-17 | 2025-01-15 | [13 empty] | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308
81803 | FSA_F01-CHWS-002-DN150-I16C00_R0 | 0 | false | 2.52 | FSA_F01-CHWS-002-DN150-I16C00_R0 | LPP6A-M-506-XX-FSA | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-01-17 | 2025-01-15 | [13 empty] | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308
81804 | FSA_F01-CHWS-003-DN150-I16C00_R0 | 0 | false | 3.38 | FSA_F01-CHWS-003-DN150-I16C00_R0 | LPP6A-M-506-XX-FSA | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-01-17 | 2025-01-15 | [13 empty] | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308
81805 | FSA_F01-CHWS-004-DN150-I16C00_R0 | 0 | true | 1.62 | FSA_F01-CHWS-004-DN150-I16C00_R0 | LPP6A-M-506-XX-FSA | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-01-17 | 2025-01-15 | 2025-02-17 | 2025-02-24 |  | 2025-03-07 | 2025-03-31 | Office 26/04/2025 | 2025-04-09 |  | 2025-03-31 | 2025-04-17 | 2025-04-17 | 2025-04-24 | 2025-04-26 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System CHW and LTHW GROUND FLOOR
81806 | FSA_F01-CHWS-005-DN150-I16C00_R0 | 0 | true | 1.62 | FSA_F01-CHWS-005-DN150-I16C00_R0 |  | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-01-17 | 2025-01-15 | 2025-02-19 | 2025-02-24 |  | 2025-03-07 | 2025-03-31 | Office 26/04/2025 | 2025-04-09 |  | 2025-03-31 | 2025-04-17 | 2025-04-17 | 2025-04-24 | 2025-04-25 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System CHW and LTHW GROUND FLOOR
81807 | FSA_F01-CHWS-006-DN150-I16C00_R0 | 0 | true | 2.99 | FSA_F01-CHWS-006-DN150-I16C00_R0 |  | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-01-17 | 2025-01-15 | 2025-02-19 | 2025-02-24 |  | 2025-03-07 | 2025-03-31 | Office 26/04/2025 | 2025-04-09 |  | 2025-03-31 | 2025-04-17 | 2025-04-17 | 2025-04-25 | 2025-04-26 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System CHW and LTHW GROUND FLOOR
81808 | FSA_F01-CHWS-007-DN150-I16C00_R0 | 0 | false | 3.23 | FSA_F01-CHWS-007-DN150-I16C00_R0 | LPP6A-M-506-XX-FSA | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-01-17 | 2025-01-15 | [13 empty] | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308
81809 | FSA_F01-CHWS-008-DN150-I16C00_R0 | 0 | true | 2.99 | FSA_F01-CHWS-008-DN150-I16C00_R0 | LPP6A-M-506-XX-FSA | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-01-17 | 2025-01-15 | 2025-02-19 | 2025-02-24 |  | 2025-03-07 | 2025-03-31 | Office 26/04/2025 | 2025-04-09 |  | 2025-03-31 | 2025-04-17 | 2025-04-17 | 2025-04-17 | 2025-04-25 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System CHW and LTHW GROUND FLOOR
81810 | FSA_F01-CHWS-010-DN150-I16C00_2_R0 | 0 | false | 1.65 | FSA_F01-CHWS-010-DN150-I16C00_2_R0 | LPP6A-M-506-XX-FSA | 1129 | FSA Mech Wet Room | Riser | FoamInside | TBH-ZAT-2025-01-17 | 2025-01-15 | [13 empty] | 1359 | 193 | Got a new Name Is DN20 instead of DN150 |  |  | 194 | SEP | SEP | [5 empty] | 1-308
91620 | FSA_F01-CHWS-010-DN150-I16C00_2_R0 | 0 | true | 20.78 | FSA_F01-CHWS-010-DN150-I16C00_2_R0 | LPP6A-M-506-XX-FSA | 1129 | FSA Mech Wet Room | Riser | FoamInside | TBH-ZAT-2025-01-28 | 2025-01-26 | 2025-02-06 | 2025-02-06 |  | 2025-02-11 | 2025-02-28 | Office 16/04/2025 | 2025-03-12 |  | 2025-02-28 | 2025-03-28 | 2025-04-03 | 2025-04-11 | 2025-05-30 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System CHW and LTHW GROUND FLOOR
81811 | FSA_F01-CHWS-011-DN150-I16C00_R0 | 0 | true | 2.97 | FSA_F01-CHWS-011-DN150-I16C00_R0 | LPP6A-M-506-XX-FSA | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-01-17 | 2025-01-15 | 2025-02-19 | 2025-02-24 |  | 2025-03-03 | 2025-03-13 | Office 11.04.2025 | 2025-03-19 |  | 2025-03-14 | 2025-04-08 | 2025-04-08 | 2025-04-08 | 2025-04-08 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System CHW and LTHW GROUND FLOOR
81812 | FSA_F01-CHWS-017-DN100-I16C00_R0 | 0 | true | 0 | FSA_F01-CHWS-017-DN100-I16C00_R0 |  | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-01-17 | 2025-01-15 | 2025-02-13 | 2025-02-24 |  | 2025-03-06 | 2025-03-06 |  | 2025-03-06 |  | 2025-03-06 |  |  |  | 2025-05-30 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System CHW and LTHW GROUND FLOOR
81813 | FSA_F01-CHWR-007-DN150-I16C00_R1 | 1 | false | 24.7 | FSA_F01-CHWR-007-DN150-I16C00_R1 | LPP6A-M-515-00-FSA | 1129 | FSA South Corridor | F01 | FoamInside | TBH-ZAT-2025-01-17 | 2025-01-15 | [13 empty] | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-200
81814 | FSA_F01-CHWS-014-DN150-I16C00_R1 | 1 | false | 27.97 | FSA_F01-CHWS-014-DN150-I16C00_R1 | LPP6A-M-515-00-FSA | 1129 | FSA South Corridor | F01 | FoamInside | TBH-ZAT-2025-01-17 | 2025-01-15 | [13 empty] | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-200
91437 | FSA_F01-CHWS-014-DN150-I16C00_R1 | 2 | false | 27.97 | FSA_F01-CHWS-014-DN150-I16C00_R1 | LPP6A-M-515-00-FSA | 1129 | FSA South Corridor | F01 | FoamInside | TBH-ZAT-2025-01-24 | 2025-01-22 | [13 empty] | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-200
81815 | FSA_F01-PCWR-007-DN250-I16C00_R1 | 1 | true | 8.23 | FSA_F01-PCWR-007-DN250-I16C00_R1 | LPP6A-M-515-00-FSA | 1129 | FSA Mech Wet Room | F01 | N/A | TBH-ZAT-2025-01-17 | 2025-01-15 | 2025-02-19 | 2025-02-24 |  | 2025-03-06 | 2025-03-13 | Office 16.04.2025 | 2025-03-19 |  | 2025-03-14 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 2025-04-07 | 1352 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System PCW 01
81816 | FSA_F01-PCWR-008-DN250-I16C00_R1 | 1 | true | 2.33 | FSA_F01-PCWR-008-DN250-I16C00_R1 |  | 1129 | FSA Mech Wet Room | F01 | N/A | TBH-ZAT-2025-01-17 | 2025-01-15 | 2025-02-19 | 2025-02-24 |  | 2025-03-06 | 2025-03-13 | Office 16.04.2025 | 2025-03-19 |  | 2025-03-14 | 2025-03-31 | 2025-03-31 | 2025-04-07 | 2025-04-16 | 1352 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System PCW 01
81817 | FSA_F01-PCWR-009-DN250-I16C00_1_R1 | 1 | false | 32.11 | FSA_F01-PCWR-009-DN250-I16C00_1_R1 | LPP6A-M-504-XX-FSA | 1129 | FSA Mech Wet Room | F01 | N/A | TBH-ZAT-2025-01-17 | 2025-01-15 | [13 empty] | 1352 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-200
81818 | FSA_F01-PCWR-010-DN250-I16C00_2_R1 | 1 | false | 30.82 | FSA_F01-PCWR-010-DN250-I16C00_2_R1 | LPP6A-M-504-XX-FSA | 1129 | FSA Mech Wet Room | F01 | N/A | TBH-ZAT-2025-01-17 | 2025-01-15 | [13 empty] | 1352 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308
81819 | FSA_F01-PHTGR-008-DN100-I16C00_1_R1 | 1 | true | 6.72 | FSA_F01-PHTGR-008-DN100-I16C00_1_R1 | LPP6A-M-504-XX-FSA | 1129 | FSA Riser South | Riser | N/A | TBH-ZAT-2025-01-17 | 2025-01-15 | 2025-02-19 | 2025-02-24 |  | 2025-03-03 | 2025-03-13 | Office 20/05/2025 | 2025-03-19 |  | 2025-03-14 | 2025-05-16 | 2025-05-16 | 2025-05-16 | 2025-05-16 | 1368 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-200 | System PHTG
81820 | FSA_ROF-PHTGR-014-DN150-I16C00_R1 | 1 | false | 7.58 | FSA_ROF-PHTGR-014-DN150-I16C00_R1 | LPP6A-M-504-XX-FSA | 1129 | FSA Roof | Roof | FoamInside | TBH-ZAT-2025-01-17 | 2025-01-15 | [13 empty] | 1368 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-200
91410 | FSA_F01-PCWR-009-DN250-I16C00_1_R2 | 2 | true | 32.11 | FSA_F01-PCWR-009-DN250-I16C00_1_R2 | LPP6A-M-504-XX-FSA | 1129 | FSA Mech Wet Room | F01 | N/A | TBH-ZAT-2025-01-23 | 2025-01-21 | 2025-01-30 | 2025-02-06 |  | 2025-03-06 | 2025-03-13 | Office 16.04.2025 | 2025-03-19 |  | 2025-03-14 | 2025-03-31 | 2025-04-01 | 2025-04-05 | 2025-04-07 | 1352 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-200 | System PCW 01
91411 | FSA_F01-PCWR-010-DN250-I16C00_2_R2 | 2 | true | 30.56 | FSA_F01-PCWR-010-DN250-I16C00_2_R2 |  | 1129 | FSA Mech Wet Room | F01 | N/A | TBH-ZAT-2025-01-23 | 2025-01-21 | 2025-01-30 | 2025-02-06 |  | 2025-03-06 | 2025-03-13 | Office 16.04.2025 | 2025-03-19 |  | 2025-03-14 | 2025-03-29 | 2025-04-01 | 2025-04-05 | 2025-04-07 | 1352 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | .
91412 | EB_F01-CHWR-005-DN150-I16C00_R1 | 1 | true | 26.04 | EB_F01-CHWR-005-DN150-I16C00_R1 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2025-01-24 | 2025-01-22 | 2024-11-25 | 2024-11-20 |  | 2024-12-08 | 2025-01-06 | Office 07.04.2025 | 2025-01-15 |  | 2025-01-09 | 2025-03-14 | 2025-03-14 | 2025-04-03 | 2025-04-03 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-306 | System CHW and LTHW GROUND FLOOR/System CHW and LTHW FIRST FLOOR
91413 | EB_F01-CHWS-012-DN150-I16C00_R1 | 1 | true | 27.35 | EB_F01-CHWS-012-DN150-I16C00_R1 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2025-01-24 | 2025-01-22 | 2024-11-18 | 2024-11-20 |  | 2024-12-08 | 2025-01-06 | Office 17.04.2025 | 2025-01-15 |  | 2025-01-09 | 2025-03-14 | 2025-03-14 | 2025-04-03 | 2025-04-03 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-306 | System CHW and LTHW GROUND FLOOR/System CHW and LTHW FIRST FLOOR
91414 | FSA_F01-CHWR-001-DN150-I16C00_R1 | 1 | false | 2.76 | FSA_F01-CHWR-001-DN150-I16C00_R1 | LPP6A-M-506-XX-FSA | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-01-24 | 2025-01-22 | [13 empty] | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308
91415 | FSA_F01-CHWR-003-DN150-I16C00_1_R0 | 0 | false | 18.67 | FSA_F01-CHWR-003-DN150-I16C00_1_R0 | LPP6A-M-506-XX-FSA | 1129 | FSA South Corridor | F01 | FoamInside | TBH-ZAT-2025-01-24 | 2025-01-22 | [13 empty] | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-200
91416 | FSA_F01-CHWR-004-DN150-I16C00_1_R0 | 0 | false | 18.65 | FSA_F01-CHWR-004-DN150-I16C00_1_R0 | LPP6A-M-506-XX-FSA | 1129 | FSA South Corridor | F01 | FoamInside | TBH-ZAT-2025-01-24 | 2025-01-22 | [13 empty] | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-200
91417 | FSA_F01-CHWR-005-DN150-I16C00_R0 | 0 | false | 82.15 | FSA_F01-CHWR-005-DN150-I16C00_R0 | LPP6A-M-511/512-00/00-FSA | 1129 | FSA North Corridor | F01 | FoamInside | TBH-ZAT-2025-01-24 | 2025-01-22 | [13 empty] | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-200
91418 | FSA_F01-CHWR-006-DN150-I16C00_R1 | 1 | false | 20.16 | FSA_F01-CHWR-006-DN150-I16C00_R1 | LPP6A-M-511/513-00/01-FSA | 1129 | FSA Riser South | Riser | FoamInside | TBH-ZAT-2025-01-24 | 2025-01-22 | [13 empty] | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-200
91419 | FSA_F01-CHWR-007-DN150-I16C00_R2 | 2 | false | 24.7 | FSA_F01-CHWR-007-DN150-I16C00_R2 | LPP6A-M-511-00-FSA | 1129 | FSA South Corridor | F01 | FoamInside | TBH-ZAT-2025-01-24 | 2025-01-22 | [13 empty] | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-200
91420 | FSA_F01-CHWR-151-DN020-I16C00_R0 | 0 | true | 9.24 | FSA_F01-CHWR-151-DN020-I16C00_R0 | LPP6A-M-511-00-FSA | 1129 | FSA North | F01 | N/A | TBH-ZAT-2025-01-24 | 2025-01-22 | 2025-02-04 | 2025-02-06 |  | 2025-02-07 | 2025-02-27 | Office 30.05.2025 | 2025-03-28 |  | 2025-02-27 | 2025-05-28 | 2025-05-28 | 2025-06-24 | 2025-06-24 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-124 | System CHW and LTHW GROUND FLOOR
91421 | FSA_F01-CHWR-152-DN020-I16C00_R0 | 0 | true | 2.68 | FSA_F01-CHWR-152-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | N/A | TBH-ZAT-2025-01-24 | 2025-01-22 | 2025-02-04 | 2025-02-06 |  | 2025-02-07 | 2025-02-20 | Office 30.05.2025 | 2025-03-28 |  | 2025-02-20 | 2025-05-29 | 2025-05-29 | 2025-06-23 | 2025-06-23 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-124 | System CHW and LTHW GROUND FLOOR
91422 | FSA_F01-CHWR-153-DN020-I16C00_R0 | 0 | true | 3.94 | FSA_F01-CHWR-153-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | N/A | TBH-ZAT-2025-01-24 | 2025-01-22 | 2025-02-04 | 2025-02-06 |  | 2025-02-07 | 2025-02-17 | Office 23/05/2025 | 2025-03-28 |  | 2025-02-18 | 2025-05-23 | 2025-05-23 | 2025-06-18 | 2025-06-18 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-238 | System CHW and LTHW GROUND FLOOR
91423 | FSA_F01-CHWR-154-DN025-I16C00_R0 | 0 | true | 12.61 | FSA_F01-CHWR-154-DN025-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-01-24 | 2025-01-22 | 2025-02-18 | 2025-02-24 |  | 2025-02-25 | 2025-02-27 | Office 17/06/2025 | 2025-03-28 |  | 2025-02-27 | 2025-05-30 | 2025-05-30 | 2025-06-12 | 2025-06-12 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-228 | System CHW and LTHW GROUND FLOOR
91424 | FSA_F01-CHWR-157-DN025-I16C00_R0 | 0 | true | 5.75 | FSA_F01-CHWR-157-DN025-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-01-24 | 2025-01-22 | 2025-02-18 | 2025-02-24 |  | 2025-02-25 | 2025-02-27 | Office 17/06/2025 | 2025-03-28 |  | 2025-02-27 | 2025-06-09 | 2025-06-09 | 2025-06-11 | 2025-06-11 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-210 | System CHW and LTHW GROUND FLOOR
91425 | FSA_F01-CHWR-164-DN020-I16C00_R0 | 0 | true | 2.26 | FSA_F01-CHWR-164-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-01-24 | 2025-01-22 | 2025-02-18 | 2025-02-24 |  | 2025-02-25 | 2025-02-27 | Office 09.06.2025 | 2025-03-28 |  | 2025-02-27 | 2025-05-30 | 2025-06-04 | 2025-07-21 |  | 1359 | 193 | Install of FCU on hold |  |  | 194 | SEP | SEP | [5 empty] | 1-221 | System Loading Dock 01
91426 | FSA_F01-CHWR-166-DN020-I16C00_R0 | 0 | true | 4.72 | FSA_F01-CHWR-166-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-01-24 | 2025-01-22 | 2025-02-04 | 2025-02-06 |  | 2025-02-07 | 2025-02-18 | Office 27/05/2025 | 2025-03-28 |  | 2025-02-18 | 2025-05-26 | 2025-05-26 | 2025-06-05 | 2025-06-05 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-221 | System Loading Dock 01
91427 | FSA_F01-CHWR-167-DN020-I16C00_R0 | 0 | true | 4.38 | FSA_F01-CHWR-167-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-01-24 | 2025-01-22 | 2025-02-04 | 2025-02-06 |  | 2025-02-07 | 2025-02-17 | Office 27.05.2025 | 2025-03-28 |  | 2025-02-18 | 2025-05-27 | 2025-05-27 | 2025-06-04 | 2025-06-04 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-221 | System Loading Dock 01
91428 | FSA_F01-CHWR-171-DN020-I16C00_R0 | 0 | true | 3.55 | FSA_F01-CHWR-171-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-01-24 | 2025-01-22 | 2025-02-04 | 2025-02-06 |  | 2025-02-07 | 2025-02-20 | Office 30.05.2025 | 2025-03-28 |  | 2025-02-20 | 2025-05-29 | 2025-05-29 | 2025-06-03 | 2025-06-03 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-221 | System Loading Dock 01
91429 | FSA_F01-CHWR-172-DN020-I16C00_R0 | 0 | true | 2.95 | FSA_F01-CHWR-172-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-01-24 | 2025-01-22 | 2025-02-04 | 2025-02-06 |  | 2025-02-07 | 2025-02-20 | Office 27/05/2025 | 2025-03-28 |  | 2025-02-20 | 2025-05-23 | 2025-05-23 | 2025-06-02 | 2025-06-02 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-230 | System Loading Dock 01
91430 | FSA_F01-CHWR-175-DN020-I16C00_R0 | 0 | true | 3.52 | FSA_F01-CHWR-175-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-01-24 | 2025-01-22 | 2025-02-14 | 2025-02-24 |  | 2025-02-25 | 2025-02-27 | Office 17/06/2025 | 2025-03-28 |  | 2025-02-27 | 2025-06-12 | 2025-06-12 | 2025-06-18 | 2025-06-18 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-220 | System CHW and LTHW GROUND FLOOR
91431 | FSA_F01-CHWR-176-DN020-I16C00_R0 | 0 | true | 2.88 | FSA_F01-CHWR-176-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-01-24 | 2025-01-22 | 2025-02-14 | 2025-02-24 |  | 2025-02-25 | 2025-02-27 | Office 17/06/2025 | 2025-03-28 |  | 2025-02-27 | 2025-06-12 | 2025-06-12 | 2025-06-24 | 2025-06-24 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-220 | System CHW and LTHW GROUND FLOOR
91432 | FSA_F01-CHWR-177-DN020-I16C00_R0 | 0 | true | 3.58 | FSA_F01-CHWR-177-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-01-24 | 2025-01-22 | 2025-02-18 | 2025-02-24 |  | 2025-02-25 | 2025-02-28 | Office 17/06/2025 | 2025-03-28 |  | 2025-02-28 | 2025-06-13 | 2025-06-13 | 2025-06-18 | 2025-06-19 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-220 | System CHW and LTHW GROUND FLOOR
91433 | FSA_F01-CHWR-178-DN020-I16C00_R0 | 0 | true | 2.88 | FSA_F01-CHWR-178-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-01-24 | 2025-01-22 | 2025-02-04 | 2025-02-06 |  | 2025-02-07 | 2025-02-20 | Office 17/06/2025 | 2025-03-28 |  | 2025-02-20 | 2025-06-12 | 2025-06-12 | 2025-06-24 | 2025-06-24 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-220 | System CHW and LTHW GROUND FLOOR
91434 | FSA_F01-CHWR-179-DN020-I16C00_R0 | 0 | true | 4.57 | FSA_F01-CHWR-179-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-01-24 | 2025-01-22 | 2025-02-04 | 2025-02-06 |  | 2025-02-07 | 2025-02-13 | Office 20/06/2025 | 2025-03-28 |  | 2025-02-14 | 2025-06-19 | 2025-06-19 | 2025-07-21 | 2025-07-21 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-225 | System CHW and LTHW GROUND FLOOR
91435 | FSA_F01-CHWS-012-DN150-I16C00_R0 | 0 | false | 79.53 | FSA_F01-CHWS-012-DN150-I16C00_R0 | LPP6A-M-511/512-00/00-FSA | 1129 | FSA North Corridor | F01 | FoamInside | TBH-ZAT-2025-01-24 | 2025-01-22 | [13 empty] | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-200
91436 | FSA_F01-CHWS-013-DN150-I16C00_R1 | 1 | false | 20.34 | FSA_F01-CHWS-013-DN150-I16C00_R1 | LPP6A-M-511/513-00/01-FSA | 1129 | FSA Riser South | Riser | FoamInside | TBH-ZAT-2025-01-24 | 2025-01-22 | [13 empty] | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-200
91438 | FSA_F01-CHWS-151-DN020-I16C00_R0 | 0 | true | 9.77 | FSA_F01-CHWS-151-DN020-I16C00_R0 | LPP6A-M-511/513-00/01-FSA | 1129 | FSA North | F01 | N/A | TBH-ZAT-2025-01-24 | 2025-01-22 | 2025-02-05 | 2025-02-06 |  | 2025-02-07 | 2025-02-20 | Office 30.05.2025 | 2025-03-28 |  | 2025-02-20 | 2025-05-28 | 2025-05-28 | 2025-06-24 | 2025-06-24 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-124 | System CHW and LTHW GROUND FLOOR
91439 | FSA_F01-CHWS-152-DN020-I16C00_R0 | 0 | true | 2.74 | FSA_F01-CHWS-152-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | N/A | TBH-ZAT-2025-01-24 | 2025-01-22 | 2025-02-05 | 2025-02-06 |  | 2025-02-07 | 2025-02-18 | Office 30.05.2025 | 2025-03-28 |  | 2025-02-18 | 2025-05-29 | 2025-05-29 | 2025-06-23 | 2025-06-23 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-124 | System CHW and LTHW GROUND FLOOR
91440 | FSA_F01-CHWS-153-DN020-I16C00_R0 | 0 | true | 4.42 | FSA_F01-CHWS-153-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | N/A | TBH-ZAT-2025-01-24 | 2025-01-22 | 2025-02-05 | 2025-02-06 |  | 2025-02-07 | 2025-02-20 | Office 23/05/2025 | 2025-03-28 |  | 2025-02-20 | 2025-05-22 | 2025-05-22 | 2025-06-18 | 2025-06-18 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-238 | System CHW and LTHW GROUND FLOOR
91441 | FSA_F01-CHWS-154-DN025-I16C00_R0 | 0 | true | 13.24 | FSA_F01-CHWS-154-DN025-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-01-24 | 2025-01-22 | 2025-02-18 | 2025-02-24 |  | 2025-02-25 | 2025-03-06 | Office 17/06/2025 | 2025-03-28 |  | 2025-03-10 | 2025-05-30 | 2025-05-30 | 2025-06-12 | 2025-06-12 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-228 | System CHW and LTHW GROUND FLOOR
91442 | FSA_F01-CHWS-157-DN025-I16C00_R0 | 0 | true | 6.06 | FSA_F01-CHWS-157-DN025-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-01-24 | 2025-01-22 | 2025-02-18 | 2025-02-24 |  | 2025-02-25 | 2025-02-28 | Office 17/06/2025 | 2025-03-28 |  | 2025-02-28 | 2025-06-09 | 2025-06-09 | 2025-06-11 | 2025-06-11 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-210 | System CHW and LTHW GROUND FLOOR
91443 | FSA_F01-CHWS-164-DN020-I16C00_R0 | 0 | true | 2.58 | FSA_F01-CHWS-164-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-01-24 | 2025-01-22 | 2025-02-18 | 2025-02-24 |  | 2025-02-25 | 2025-02-27 | Office 09.06.2025 | 2025-03-28 |  | 2025-02-27 | 2025-05-30 | 2025-06-04 | 2025-07-21 |  | 1359 | 193 | Install of FCU on hold |  |  | 194 | SEP | SEP | [5 empty] | 1-221 | System Loading Dock 01
91444 | FSA_F01-CHWS-166-DN020-I16C00_R0 | 0 | true | 4.92 | FSA_F01-CHWS-166-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-01-24 | 2025-01-22 | 2025-02-05 | 2025-02-06 |  | 2025-02-07 | 2025-02-14 | Office 27/05/2025 | 2025-03-28 |  | 2025-02-14 | 2025-05-26 | 2025-05-26 | 2025-06-05 | 2025-06-05 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-221 | System Loading Dock 01
91445 | FSA_F01-CHWS-167-DN020-I16C00_R0 | 0 | true | 4.59 | FSA_F01-CHWS-167-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-01-24 | 2025-01-22 | 2025-02-05 | 2025-02-06 |  | 2025-02-07 | 2025-02-17 | Office 27.05.2025 | 2025-03-28 |  | 2025-02-18 | 2025-05-27 | 2025-05-27 | 2025-06-04 | 2025-06-04 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-221 | System Loading Dock 01
91446 | FSA_F01-CHWS-171-DN020-I16C00_R0 | 0 | true | 4.11 | FSA_F01-CHWS-171-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-01-24 | 2025-01-22 | 2025-02-05 | 2025-02-06 |  | 2025-02-07 | 2025-02-18 | Office 30.05.2025 | 2025-03-28 |  | 2025-02-18 | 2025-05-29 | 2025-05-29 | 2025-06-03 | 2025-06-03 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-221 | System Loading Dock 01
91447 | FSA_F01-CHWS-172-DN020-I16C00_R0 | 0 | true | 3.48 | FSA_F01-CHWS-172-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-01-24 | 2025-01-22 | 2025-02-05 | 2025-02-06 |  | 2025-02-07 | 2025-02-20 | Office 27/05/2025 | 2025-03-28 |  | 2025-02-20 | 2025-05-23 | 2025-05-23 | 2025-06-02 | 2025-06-02 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-230 | System Loading Dock 01
91448 | FSA_F01-CHWS-175-DN020-I16C00_R0 | 0 | true | 3.9 | FSA_F01-CHWS-175-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-01-24 | 2025-01-22 | 2025-02-14 | 2025-02-24 |  | 2025-02-25 | 2025-02-28 | Office 17/06/2025 | 2025-03-28 |  | 2025-02-28 | 2025-06-12 | 2025-06-12 | 2025-06-18 | 2025-06-18 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-220 | System CHW and LTHW GROUND FLOOR
91449 | FSA_F01-CHWS-176-DN020-I16C00_R0 | 0 | true | 2.74 | FSA_F01-CHWS-176-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-01-24 | 2025-01-22 | 2025-02-14 | 2025-02-24 |  | 2025-02-25 | 2025-02-27 | Office 17/06/2025 | 2025-03-28 |  | 2025-02-27 | 2025-06-12 | 2025-06-12 | 2025-06-24 | 2025-06-24 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-220 | System CHW and LTHW GROUND FLOOR
91450 | FSA_F01-CHWS-177-DN020-I16C00_R0 | 0 | true | 3.85 | FSA_F01-CHWS-177-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-01-24 | 2025-01-22 | 2025-02-13 | 2025-02-24 |  | 2025-02-25 | 2025-02-27 | Office 17/06/2025 | 2025-03-28 |  | 2025-02-27 | 2025-06-13 | 2025-06-13 | 2025-06-18 | 2025-06-19 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-220 | System CHW and LTHW GROUND FLOOR
91451 | FSA_F01-CHWS-178-DN020-I16C00_R0 | 0 | true | 2.74 | FSA_F01-CHWS-178-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-01-24 | 2025-01-22 | 2025-02-05 | 2025-02-06 |  | 2025-02-07 | 2025-02-20 | Office 17/06/2025 | 2025-03-28 |  | 2025-02-20 | 2025-06-13 | 2025-06-13 | 2025-06-24 | 2025-06-24 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-220 | System CHW and LTHW GROUND FLOOR
91452 | FSA_F01-CHWS-179-DN020-I16C00_R0 | 0 | true | 4.6 | FSA_F01-CHWS-179-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-01-24 | 2025-01-22 | 2025-02-05 | 2025-02-06 |  | 2025-02-07 | 2025-02-17 | Office 20/06/2025 | 2025-03-28 |  | 2025-02-18 | 2025-06-19 | 2025-06-20 | 2025-07-21 | 2025-07-21 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-225 | System CHW and LTHW GROUND FLOOR
91453 | FSA_F01-LTHWR-151-DN020-I16C00_R0 | 0 | true | 8.1 | FSA_F01-LTHWR-151-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | N/A | TBH-ZAT-2025-01-24 | 2025-01-22 | 2025-02-06 | 2025-02-06 |  | 2025-02-07 | 2025-02-27 | Office 30.05.2025 | 2025-03-28 |  | 2025-02-27 | 2025-05-28 | 2025-05-28 | 2025-06-24 | 2025-06-24 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-124 | System CHW and LTHW GROUND FLOOR
91454 | FSA_F01-LTHWR-152-DN020-I16C00_R0 | 0 | true | 2.53 | FSA_F01-LTHWR-152-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | N/A | TBH-ZAT-2025-01-24 | 2025-01-22 | 2025-02-06 | 2025-02-06 |  | 2025-02-07 | 2025-02-27 | Office 30.05.2025 | 2025-03-28 |  | 2025-02-27 | 2025-05-29 | 2025-05-29 | 2025-06-23 | 2025-06-23 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-124 | System CHW and LTHW GROUND FLOOR
91455 | FSA_F01-LTHWR-153-DN020-I16C00_R0 | 0 | true | 4.58 | FSA_F01-LTHWR-153-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | N/A | TBH-ZAT-2025-01-24 | 2025-01-22 | 2025-02-06 | 2025-02-06 |  | 2025-02-10 | 2025-02-18 | Office 23/05/2025 | 2025-03-28 |  | 2025-02-18 | 2025-05-22 | 2025-05-22 | 2025-06-18 | 2025-06-18 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-238 | System CHW and LTHW GROUND FLOOR
91456 | FSA_F01-LTHWR-154-DN020-I16C00_R0 | 0 | true | 13.55 | FSA_F01-LTHWR-154-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-01-24 | 2025-01-22 | 2025-02-18 | 2025-02-24 |  | 2025-02-25 | 2025-02-27 | Office 17/06/2025 | 2025-03-28 |  | 2025-02-27 | 2025-05-30 | 2025-05-30 | 2025-06-12 | 2025-06-12 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-228 | System CHW and LTHW GROUND FLOOR
91457 | FSA_F01-LTHWR-157-DN020-I16C00_R0 | 0 | true | 5.63 | FSA_F01-LTHWR-157-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-01-24 | 2025-01-22 | 2025-02-18 | 2025-02-24 |  | 2025-02-25 | 2025-02-28 | Office 17/06/2025 | 2025-03-28 |  | 2025-02-28 | 2025-06-09 | 2025-06-09 | 2025-06-11 | 2025-06-11 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-210 | System CHW and LTHW GROUND FLOOR
91458 | FSA_F01-LTHWR-164-DN020-I16C00_R0 | 0 | true | 1.83 | FSA_F01-LTHWR-164-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-01-24 | 2025-01-22 | 2025-02-14 | 2025-02-24 |  | 2025-02-25 | 2025-02-27 | Office 09.06.2025 | 2025-03-28 |  | 2025-02-27 | 2025-05-30 | 2025-06-04 | 2025-07-21 | 2025-07-21 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-221 | System Loading Dock 01
91459 | FSA_F01-LTHWR-166-DN020-I16C00_R0 | 0 | true | 3.65 | FSA_F01-LTHWR-166-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-01-24 | 2025-01-22 | 2025-02-06 | 2025-02-06 |  | 2025-02-10 | 2025-02-17 | Office 27/05/2025 | 2025-03-28 |  | 2025-02-18 | 2025-05-26 | 2025-05-26 | 2025-06-05 | 2025-06-05 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-221 | System Loading Dock 01
91460 | FSA_F01-LTHWR-167-DN020-I16C00_R0 | 0 | true | 3.31 | FSA_F01-LTHWR-167-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-01-24 | 2025-01-22 | 2025-02-06 | 2025-02-06 |  | 2025-02-10 | 2025-02-20 | Office 27.05.2025 | 2025-03-28 |  | 2025-02-20 | 2025-05-27 | 2025-05-27 | 2025-06-04 | 2025-06-04 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-221 | System Loading Dock 01
91461 | FSA_F01-LTHWR-171-DN020-I16C00_R0 | 0 | true | 2.1 | FSA_F01-LTHWR-171-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-01-24 | 2025-01-22 | 2025-02-06 | 2025-02-06 |  | 2025-02-10 | 2025-02-20 | Office 30.05.2025 | 2025-03-28 |  | 2025-02-20 | 2025-05-29 | 2025-05-29 | 2025-06-03 | 2025-06-03 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-221 | System Loading Dock 01
91462 | FSA_F01-LTHWR-172-DN020-I16C00_R0 | 0 | true | 2.09 | FSA_F01-LTHWR-172-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-01-24 | 2025-01-22 | 2025-02-06 | 2025-02-06 |  | 2025-02-10 | 2025-02-26 | Office 27/05/2025 | 2025-03-28 |  | 2025-02-27 | 2025-05-23 | 2025-05-23 | 2025-06-02 | 2025-06-02 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-230 | System Loading Dock 01
91463 | FSA_F01-LTHWR-175-DN020-I16C00_R0 | 0 | true | 2.81 | FSA_F01-LTHWR-175-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-01-24 | 2025-01-22 | 2025-02-14 | 2025-02-24 |  | 2025-02-25 | 2025-02-27 | Office 17/06/2025 | 2025-03-28 |  | 2025-02-27 | 2025-06-12 | 2025-06-12 | 2025-06-18 | 2025-06-18 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-220 | System CHW and LTHW GROUND FLOOR
91464 | FSA_F01-LTHWR-176-DN020-I16C00_R0 | 0 | true | 2.95 | FSA_F01-LTHWR-176-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-01-24 | 2025-01-22 | 2025-02-14 | 2025-02-24 |  | 2025-02-25 | 2025-02-27 | Office 17/06/2025 | 2025-03-28 |  | 2025-02-27 | 2025-06-12 | 2025-06-12 | 2025-06-24 | 2025-06-24 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-220 | System CHW and LTHW GROUND FLOOR
91465 | FSA_F01-LTHWR-177-DN020-I16C00_R0 | 0 | true | 2.88 | FSA_F01-LTHWR-177-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-01-24 | 2025-01-22 | 2025-02-13 | 2025-02-24 |  | 2025-02-25 | 2025-02-27 | Office 17/06/2025 | 2025-03-28 |  | 2025-02-27 | 2025-06-13 | 2025-06-13 | 2025-06-18 | 2025-06-19 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-220 | System CHW and LTHW GROUND FLOOR
91466 | FSA_F01-LTHWR-178-DN020-I16C00_R0 | 0 | true | 2.94 | FSA_F01-LTHWR-178-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-01-24 | 2025-01-22 | 2025-02-06 | 2025-02-06 |  | 2025-02-10 | 2025-02-20 | Office 17/06/2025 | 2025-03-28 |  | 2025-02-20 | 2025-06-13 | 2025-06-13 | 2025-06-24 | 2025-06-24 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-220 | System CHW and LTHW GROUND FLOOR
91467 | FSA_F01-LTHWR-179-DN015-I16C00_R0 | 0 | true | 4.76 | FSA_F01-LTHWR-179-DN015-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-01-24 | 2025-01-22 | 2025-02-06 | 2025-02-06 |  | 2025-02-10 | 2025-02-14 | Office 20/06/2025 | 2025-03-28 |  | 2025-02-14 | 2025-06-19 | 2025-06-19 | 2025-07-21 | 2025-07-21 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-225 | System CHW and LTHW GROUND FLOOR
91468 | FSA_F01-LTHWS-151-DN020-I16C00_R0 | 0 | true | 8.62 | FSA_F01-LTHWS-151-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | N/A | TBH-ZAT-2025-01-24 | 2025-01-22 | 2025-02-06 | 2025-02-06 |  | 2025-02-10 | 2025-02-18 | Office 30.05.2025 | 2025-03-28 |  | 2025-02-18 | 2025-05-28 | 2025-05-28 | 2025-06-24 | 2025-06-24 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-124 | System CHW and LTHW GROUND FLOOR
91469 | FSA_F01-LTHWS-152-DN020-I16C00_R0 | 0 | true | 2.58 | FSA_F01-LTHWS-152-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | N/A | TBH-ZAT-2025-01-24 | 2025-01-22 | 2025-02-06 | 2025-02-06 |  | 2025-02-10 | 2025-02-20 | Office 30.05.2025 | 2025-03-28 |  | 2025-02-20 | 2025-05-29 | 2025-05-29 | 2025-06-23 | 2025-06-23 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-124 | System CHW and LTHW GROUND FLOOR
91470 | FSA_F01-LTHWS-153-DN020-I16C00_R0 | 0 | true | 4.68 | FSA_F01-LTHWS-153-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | N/A | TBH-ZAT-2025-01-24 | 2025-01-22 | 2025-02-06 | 2025-02-06 |  | 2025-02-10 | 2025-02-14 | Office 23/05/2025 | 2025-03-28 |  | 2025-02-14 | 2025-05-23 | 2025-05-23 | 2025-06-18 | 2025-06-18 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-238 | System CHW and LTHW GROUND FLOOR
91471 | FSA_F01-LTHWS-154-DN020-I16C00_R0 | 0 | true | 13.75 | FSA_F01-LTHWS-154-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-01-24 | 2025-01-22 | 2025-02-18 | 2025-02-24 |  | 2025-02-25 | 2025-02-28 | Office 17/06/2025 | 2025-03-28 |  | 2025-02-28 | 2025-05-30 | 2025-05-30 | 2025-06-12 | 2025-06-12 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-228 | System CHW and LTHW GROUND FLOOR
91472 | FSA_F01-LTHWS-157-DN020-I16C00_R0 | 0 | true | 5.87 | FSA_F01-LTHWS-157-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-01-24 | 2025-01-22 | 2025-02-18 | 2025-02-24 |  | 2025-02-25 | 2025-02-28 | Office 17/06/2025 | 2025-03-28 |  | 2025-02-28 | 2025-06-09 | 2025-06-09 | 2025-06-11 | 2025-06-11 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-210 | System CHW and LTHW GROUND FLOOR
91473 | FSA_F01-LTHWS-164-DN020-I16C00_R0 | 0 | true | 2.02 | FSA_F01-LTHWS-164-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-01-24 | 2025-01-22 | 2025-02-14 | 2025-02-24 |  | 2025-02-25 | 2025-02-27 | Office 09.06.2025 | 2025-03-28 |  | 2025-02-27 | 2025-05-30 | 2025-06-04 | 2025-07-21 | 2025-07-21 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-221 | System Loading Dock 01
91474 | FSA_F01-LTHWS-166-DN020-I16C00_R0 | 0 | true | 4.06 | FSA_F01-LTHWS-166-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-01-24 | 2025-01-22 | 2025-02-06 | 2025-02-06 |  | 2025-02-10 | 2025-02-18 | Office 27/05/2025 | 2025-03-28 |  | 2025-02-18 | 2025-05-26 | 2025-05-26 | 2025-06-05 | 2025-06-05 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-221 | System Loading Dock 01
91475 | FSA_F01-LTHWS-167-DN020-I16C00_R0 | 0 | true | 3.72 | FSA_F01-LTHWS-167-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-01-24 | 2025-01-22 | 2025-02-06 | 2025-02-06 |  | 2025-02-10 | 2025-02-17 | Office 27.05.2025 | 2025-03-28 |  | 2025-02-18 | 2025-05-27 | 2025-05-27 | 2025-06-04 | 2025-06-04 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-221 | System Loading Dock 01
91476 | FSA_F01-LTHWS-171-DN020-I16C00_R0 | 0 | true | 2.74 | FSA_F01-LTHWS-171-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-01-24 | 2025-01-22 | 2025-02-07 | 2025-02-06 |  | 2025-02-10 | 2025-02-20 | Office 30.05.2025 | 2025-03-28 |  | 2025-02-20 | 2025-05-29 | 2025-05-29 | 2025-06-03 | 2025-06-03 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-221 | System Loading Dock 01
91477 | FSA_F01-LTHWS-172-DN020-I16C00_R0 | 0 | true | 2.57 | FSA_F01-LTHWS-172-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-01-24 | 2025-01-22 | 2025-02-07 | 2025-02-06 |  | 2025-02-10 | 2025-02-20 | Office 27/05/2025 | 2025-03-28 |  | 2025-02-20 | 2025-05-23 | 2025-05-23 | 2025-06-02 | 2025-06-02 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-230 | System Loading Dock 01
91478 | FSA_F01-LTHWS-175-DN020-I16C00_R0 | 0 | true | 3.19 | FSA_F01-LTHWS-175-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-01-24 | 2025-01-22 | 2025-02-14 | 2025-02-24 |  | 2025-02-25 | 2025-02-28 | Office 17/06/2025 | 2025-03-28 |  | 2025-02-28 | 2025-06-12 | 2025-06-12 | 2025-06-18 | 2025-06-18 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-220 | System CHW and LTHW GROUND FLOOR
91479 | FSA_F01-LTHWS-176-DN020-I16C00_R0 | 0 | true | 2.82 | FSA_F01-LTHWS-176-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-01-24 | 2025-01-22 | 2025-02-14 | 2025-02-24 |  | 2025-02-25 | 2025-02-28 | Office 17/06/2025 | 2025-03-28 |  | 2025-02-28 | 2025-06-12 | 2025-06-12 | 2025-06-24 | 2025-06-24 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-220 | System CHW and LTHW GROUND FLOOR
91480 | FSA_F01-LTHWS-177-DN020-I16C00_R0 | 0 | true | 3.14 | FSA_F01-LTHWS-177-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-01-24 | 2025-01-22 | 2025-02-14 | 2025-02-24 |  | 2025-02-25 | 2025-02-28 | Office 17/06/2025 | 2025-03-28 |  | 2025-02-28 | 2025-06-13 | 2025-06-13 | 2025-06-18 | 2025-06-18 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-220 | System CHW and LTHW GROUND FLOOR
91481 | FSA_F01-LTHWS-178-DN020-I16C00_R0 | 0 | true | 2.83 | FSA_F01-LTHWS-178-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-01-24 | 2025-01-22 | 2025-02-07 | 2025-02-06 |  | 2025-02-10 | 2025-02-20 | Office 17/06/2025 | 2025-03-28 |  | 2025-02-20 | 2025-06-13 | 2025-06-13 | 2025-06-24 | 2025-06-24 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-220 | System CHW and LTHW GROUND FLOOR
91482 | FSA_F01-LTHWS-179-DN015-I16C00_R0 | 0 | true | 4.77 | FSA_F01-LTHWS-179-DN015-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-01-24 | 2025-01-22 | 2025-02-07 | 2025-02-06 |  | 2025-02-10 | 2025-02-14 | Office 20/06/2025 | 2025-03-28 |  | 2025-02-14 | 2025-06-19 | 2025-06-20 | 2025-07-21 | 2025-07-21 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-225 | System CHW and LTHW GROUND FLOOR
91484 | FSA_F02_1-CHWR-023-DN080-I16C00_R1 | 1 | true | 8.62 | FSA_F02_1-CHWR-023-DN080-I16C00_R1 |  | 1129 | FSA Riser South | F02 | FoamInside | TBH-ZAT-2025-01-24 | 2025-01-22 | 2024-12-08 | 2024-12-10 |  | 2025-01-02 | 2025-01-29 | Office 30.05.2025 | 2025-02-05 |  | 2025-02-05 | 2025-05-28 | 2025-05-29 | 2025-05-29 | 2025-05-29 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | Riser to Roof no No. | System CHW and LTHW FIRST FLOOR
91486 | FSA_F02_1-CHWS-023-DN080-I16C00_R1 | 1 | true | 8.71 | FSA_F02_1-CHWS-023-DN080-I16C00_R1 |  | 1129 | FSA Riser South | F02 | FoamInside | TBH-ZAT-2025-01-24 | 2025-01-22 | 2024-12-08 | 2024-12-10 |  | 2025-01-02 | 2025-01-29 | Office 30.05.2025 | 2025-02-05 |  | 2025-02-05 | 2025-05-28 | 2025-05-29 | 2025-05-29 | 2025-05-29 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | Riser to Roof no No. | System CHW and LTHW FIRST FLOOR
91487 | FSA_F02_2-CHWR-005-DN050-I16C00_R2 | 2 | false | 26.15 | FSA_F02_2-CHWR-005-DN050-I16C00_R2 | LPP6A-M-511/513-00/01-FSA | 1129 | FSA Corridor | F02 | FoamInside | TBH-ZAT-2025-01-24 | 2025-01-22 | [13 empty] | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-320
91488 | FSA_F02_2-CHWR-190-DN020-I16C00_R1 | 1 | true | 13.9 | FSA_F02_2-CHWR-190-DN020-I16C00_R1 | LPP6A-M-511/513-00/01-FSA | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2025-01-24 | 2025-01-22 | 2025-01-28 | 2025-01-28 |  | 2025-01-28 | 2025-01-28 | Office 03.04.2025 | 2025-02-05 |  | 2025-01-29 | 2025-03-25 | 2025-03-27 | 2025-03-27 | 2025-03-27 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-217 | System CHW and LTHW FIRST FLOOR
91489 | FSA_F02_2-CHWS-012-DN050-I16C00_R2 | 2 | false | 24.87 | FSA_F02_2-CHWS-012-DN050-I16C00_R2 | LPP6A-M-511/513-00/01-FSA | 1129 | FSA Corridor | F02 | FoamInside | TBH-ZAT-2025-01-24 | 2025-01-22 |  | 2025-01-31 |  | 2025-01-31 | 2025-01-31 | [8 empty] | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-320
91490 | FSA_F02_2-CHWS-190-DN020-I16C00_R1 | 1 | true | 13.93 | FSA_F02_2-CHWS-190-DN020-I16C00_R1 | LPP6A-M-511/513-00/01-FSA | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2025-01-24 | 2025-01-22 | 2025-01-28 | 2025-01-28 |  | 2025-01-28 | 2025-01-28 | Office 02.04.2025 | 2025-02-05 |  | 2025-01-29 | 2025-03-25 | 2025-03-26 | 2025-03-27 | 2025-03-27 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-217 | System CHW and LTHW FIRST FLOOR
91491 | FSA_ROF-CHWR-003-DN150-I16C00_R1 | 1 | true | 14.01 | FSA_ROF-CHWR-003-DN150-I16C00_R1 |  | 1129 | FSA Roof | Roof | FoamInside | TBH-ZAT-2025-01-24 | 2025-01-22 | 2025-01-06 | 2025-01-14 |  |  |  | Office 20/05/2025 |  |  |  | 2025-05-05 | 2025-05-05 | 2025-05-10 | 2025-05-16 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | External Roof South | System CHW and LTHW GROUND FLOOR
91492 | FSA_ROF-CHWS-009-DN150-I16C00_R1 | 1 | true | 16.87 | FSA_ROF-CHWS-009-DN150-I16C00_R1 |  | 1129 | FSA Roof | Roof | FoamInside | TBH-ZAT-2025-01-24 | 2025-01-22 | 2025-01-10 | 2025-01-14 |  |  |  | Office 20/05/2025 |  |  |  | 2025-05-05 | 2025-05-08 | 2025-05-16 | 2025-05-16 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | External Roof South | System CHW and LTHW GROUND FLOOR
91610 | FSA_F01-CHWR-001-DN150-I16C00_R2 | 2 | true | 2.76 | FSA_F01-CHWR-001-DN150-I16C00_R2 |  | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-01-28 | 2025-01-27 | 2025-02-05 | 2025-02-06 |  | 2025-02-11 | 2025-02-27 | Office 24/03/25 | 2025-03-12 |  | 2025-02-28 | 2025-03-21 | 2025-03-22 | 2025-03-22 | 2025-05-13 | 1359 | 193 | Shear lugs to be welded |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System CHW and LTHW GROUND FLOOR
91611 | FSA_F01-CHWR-003-DN150-I16C00_1_R1 | 1 | true | 18.67 | FSA_F01-CHWR-003-DN150-I16C00_1_R1 |  | 1129 | FSA South Corridor | F01 | FoamInside | TBH-ZAT-2025-01-28 | 2025-01-27 | 2025-02-05 | 2025-02-06 |  | 2025-02-11 | 2025-02-27 | Office 16/04/2025 | 2025-03-12 |  | 2025-02-28 | 2025-03-25 | 2025-03-28 | 2025-04-11 | 2025-05-13 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-200 | System CHW and LTHW GROUND FLOOR
91612 | FSA_F01-CHWR-004-DN150-I16C00_1_R1 | 1 | true | 18.65 | FSA_F01-CHWR-004-DN150-I16C00_1_R1 |  | 1129 | FSA South Corridor | F01 | FoamInside | TBH-ZAT-2025-01-28 | 2025-01-27 | 2025-02-05 | 2025-02-06 |  | 2025-02-11 | 2025-02-27 | Office 16/04/2025 | 2025-03-12 |  | 2025-02-28 | 2025-03-25 | 2025-03-28 | 2025-04-11 | 2025-05-13 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-200 | System CHW and LTHW GROUND FLOOR
91613 | FSA_F01-CHWR-006-DN150-I16C00_R2 | 2 | true | 20.16 | FSA_F01-CHWR-006-DN150-I16C00_R2 |  | 1129 | FSA Riser South | Riser | FoamInside | TBH-ZAT-2025-01-28 | 2025-01-27 | 2024-12-03 | 2024-12-10 |  | 2024-12-12 | 2024-12-29 | Office 30.05.2025 | 2025-01-22 |  | 2025-01-06 | 2025-04-14 | 2025-04-14 | 2025-04-14 | 2025-05-30 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-200 | System CHW and LTHW FIRST FLOOR
91614 | FSA_F01-CHWR-007-DN150-I16C00_R3 | 3 | true | 24.7 | FSA_F01-CHWR-007-DN150-I16C00_R3 |  | 1129 | FSA South Corridor | F01 | FoamInside | TBH-ZAT-2025-01-28 | 2025-01-27 | 2025-02-05 | 2025-02-06 |  | 2025-02-11 | 2025-02-27 | Office 09.04.2025 | 2025-03-12 |  | 2025-02-28 | 2025-03-28 | 2025-04-03 | 2025-04-03 | 2025-04-03 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-200 | System CHW and LTHW GROUND FLOOR
91615 | FSA_F01-CHWS-001-DN150-I16C00_R1 | 1 | true | 4.23 | FSA_F01-CHWS-001-DN150-I16C00_R1 |  | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-01-28 | 2025-01-27 | 2025-02-05 | 2025-02-06 |  | 2025-02-11 | 2025-03-06 | Office 12.04.2025 | 2025-03-12 |  | 2025-03-07 | 2025-04-10 | 2025-04-10 | 2025-04-10 | 2025-04-10 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System CHW and LTHW GROUND FLOOR
91616 | FSA_F01-CHWS-002-DN150-I16C00_R1 | 1 | true | 2.52 | FSA_F01-CHWS-002-DN150-I16C00_R1 |  | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-01-28 | 2025-01-27 | 2025-02-05 | 2025-02-06 |  | 2025-02-11 | 2025-02-28 | Office 02.04.2025 | 2025-03-12 |  | 2025-02-28 | 2025-03-25 | 2025-03-26 | 2025-03-27 | 2025-03-27 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System CHW and LTHW GROUND FLOOR
91617 | FSA_F01-CHWS-003-DN150-I16C00_R1 | 1 | true | 3.38 | FSA_F01-CHWS-003-DN150-I16C00_R1 |  | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-01-28 | 2025-01-27 | 2025-02-05 | 2025-02-06 |  | 2025-02-11 | 2025-02-28 | Office 02.04.2025 | 2025-03-12 |  | 2025-02-28 | 2025-03-25 | 2025-03-26 | 2025-03-27 | 2025-03-28 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System CHW and LTHW GROUND FLOOR
91618 | FSA_F01-CHWS-007-DN150-I16C00_R1 | 1 | true | 3.23 | FSA_F01-CHWS-007-DN150-I16C00_R1 |  | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-01-28 | 2025-01-27 | 2025-02-05 | 2025-02-06 |  | 2025-02-11 | 2025-02-28 | Office 24/03/25 | 2025-03-12 |  | 2025-02-28 | 2025-03-21 | 2025-03-21 | 2025-03-22 | 2025-04-17 | 1359 | 193 | Shear lugs to be welded |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System CHW and LTHW GROUND FLOOR
91619 | FSA_F01-CHWS-009-DN150-I16C00_2_R0 | 0 | true | 21.2 | FSA_F01-CHWS-009-DN150-I16C00_2_R0 |  | 1129 | FSA Riser South | Riser | FoamInside | TBH-ZAT-2025-01-28 | 2025-01-26 | 2025-02-06 | 2025-02-06 |  | 2025-02-11 | 2025-02-28 | Office 16/04/2025 | 2025-03-12 |  | 2025-02-28 | 2025-03-28 | 2025-04-03 | 2025-04-11 | 2025-05-30 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-200 | System CHW and LTHW GROUND FLOOR
91621 | FSA_F01-CHWS-013-DN150-I16C00_R2 | 2 | true | 20.34 | FSA_F01-CHWS-013-DN150-I16C00_R2 |  | 1129 | FSA Riser South | Riser | FoamInside | TBH-ZAT-2025-01-28 | 2025-01-26 | 2024-12-03 | 2024-12-10 |  | 2024-12-15 | 2024-12-29 | Office 30.05.2025 | 2025-01-22 |  | 2025-01-06 | 2025-04-12 | 2025-04-12 | 2025-04-12 | 2025-05-30 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-200 | System CHW and LTHW FIRST FLOOR
91622 | FSA_F01-CHWS-014-DN150-I16C00_R2 | 2 | true | 27.97 | FSA_F01-CHWS-014-DN150-I16C00_R2 |  | 1129 | FSA South Corridor | F01 | FoamInside | TBH-ZAT-2025-01-28 | 2025-01-27 | 2025-02-06 | 2025-02-06 |  | 2025-02-11 | 2025-03-06 | Office 09.04.2025 | 2025-03-12 |  | 2025-03-11 | 2025-03-27 | 2025-04-03 | 2025-04-03 | 2025-04-03 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-200 | System CHW and LTHW GROUND FLOOR
91623 | FSA_F01-CHWS-099-DN25-I16C00_R1 | 1 | true | 1.65 | FSA_F01-CHWS-099-DN25-I16C00_R1 |  | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-01-28 | 2025-01-27 | 2025-02-06 | 2025-02-06 |  | 2025-02-10 | 2025-02-18 | Office 24/05/2025 | 2025-03-28 |  | 2025-02-18 | 2025-05-23 | 2025-05-23 | 2025-05-23 | 2025-05-23 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | NO TESTING REQUIRED
91624 | FSA_F01-LTHWR-009-DN100-I16C00_R1 | 1 | true | 21.95 | FSA_F01-LTHWR-009-DN100-I16C00_R1 |  | 1129 | FSA Riser South | Riser | FoamInside | TBH-ZAT-2025-01-28 | 2025-01-26 | 2024-12-05 | 2024-12-10 |  | 2024-12-23 |  | Office 30.05.2025 | 2025-01-29 |  | 2025-01-09 | 2025-04-14 | 2025-04-14 | 2025-04-16 | 2025-05-30 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-200 | System CHW and LTHW GROUND FLOOR
91625 | FSA_F01-LTHWS-009-DN100-I16C00_R1 | 1 | true | 22.08 | FSA_F01-LTHWS-009-DN100-I16C00_R1 |  | 1129 | FSA Riser South | Riser | FoamInside | TBH-ZAT-2025-01-28 | 2025-01-26 | 2024-12-05 | 2024-12-10 |  | 2024-12-23 | 2025-01-30 | Office 30.05.2025 | 2025-02-05 |  | 2025-02-05 |  | 2025-05-16 | 2025-05-29 | 2025-05-30 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-200 | System CHW and LTHW GROUND FLOOR
91626 | FSA_F02_1-CHWR-005-DN150-I16C00_R2 | 2 | true | 59.75 | FSA_F02_1-CHWR-005-DN150-I16C00_R2 |  | 1129 | FSA Corridor | F02 | FoamInside | TBH-ZAT-2025-01-28 | 2025-01-26 | 2024-11-27 | 2024-12-03 |  | 2024-12-10 | 2024-12-18 | Office 11.03.2025 | 2025-01-07 |  | 2024-12-19 | 2025-02-14 | 2025-02-22 | 2025-02-25 | 2025-03-22 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-200 | System CHW and LTHW FIRST FLOOR
91627 | FSA_F02_1-CHWS-012-DN150-I16C00_R2 | 2 | true | 59.75 | FSA_F02_1-CHWS-012-DN150-I16C00_R2 |  | 1129 | FSA Corridor | F02 | FoamInside | TBH-ZAT-2025-01-28 | 2025-01-26 | 2024-11-27 | 2024-12-03 |  | 2024-12-10 | 2024-12-16 | Office 07.04.2025. | 2025-01-07 |  | 2024-12-18 | 2025-02-14 | 2025-02-24 | 2025-02-25 | 2025-03-22 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-200 | System CHW and LTHW FIRST FLOOR
91628 | FSA_F02_2-CHWR-005-DN050-I16C00_R3 | 3 | true | 26.15 | FSA_F02_2-CHWR-005-DN050-I16C00_R3 |  | 1129 | FSA Corridor | F02 | FoamInside | TBH-ZAT-2025-01-28 | 2025-01-26 | 2024-12-16 | 2024-12-19 |  | 2025-01-09 | 2025-02-20 | Office 11.04.2025 | 2025-03-28 |  | 2025-03-27 | 2025-04-02 | 2025-04-02 | 2025-04-02 | 2025-04-02 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-320 | System CHW and LTHW FIRST FLOOR
91629 | FSA_F02_2-CHWS-012-DN050-I16C00_R3 | 3 | true | 24.87 | FSA_F02_2-CHWS-012-DN050-I16C00_R3 |  | 1129 | FSA Corridor | F02 | FoamInside | TBH-ZAT-2025-01-28 | 2025-01-26 | 2024-12-16 | 2024-12-19 |  | 2025-01-09 | 2025-02-03 | Office 11.04.2025 | 2025-02-05 |  | 2025-02-03 | 2025-03-25 | 2025-03-25 | 2025-03-26 | 2025-03-26 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-320 | System CHW and LTHW FIRST FLOOR
91630 | FSA_F02_2-LTHWR-008-DN100-I16C00_R2 | 2 | false | 28.44 | FSA_F02_2-LTHWR-008-DN100-I16C00_R2 | LPP6A-M-517/518-01/01-FSA | 1129 | FSA Corridor | F02 | FoamInside | TBH-ZAT-2025-01-28 | 2025-01-26 | 2024-12-16 | 2024-12-19 |  | 2025-01-22 | [9 empty] | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-320
91631 | FSA_ROF-PHTGR-014-DN150-I16C00_R2 | 2 | false | 7.58 | FSA_ROF-PHTGR-014-DN150-I16C00_R2 | LPP6A-M-504-XX-FSA | 1129 | FSA Roof | Roof | FoamInside | TBH-ZAT-2025-01-28 | 2025-01-27 |  |  | Fixpoint missing ==> Must be revised. | [10 empty] | 1368 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-200
92071 | FSA_ROF-PHTGR-014-DN150-I16C00_R2 | 3 | true | 7.58 | FSA_ROF-PHTGR-014-DN150-I16C00_R2 | LPP6A-M-504-XX-FSA | 1129 | FSA Roof | Roof | FoamInside | TBH-ZAT-2025-01-31 | 2025-01-30 | 2025-02-20 | 2025-02-24 | Wrong Revision should be Rev.3 | 2025-03-03 | 2025-03-13 | Office 23.06.2025 | 2025-03-19 |  | 2025-03-14 | 2025-05-07 | 2025-06-13 | 2025-06-16 | 2025-06-17 | 1368 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-200 | System PHTG
91993 | EB_F01-PHTGR-005-DN200-I16C00_R2 | 2 | true | 29.27 | EB_F01-PHTGR-005-DN200-I16C00_R2 | LPP6A-M-504-XX-FSA | 1129 | EB | F01 | N/A | TBH-ZAT-2025-01-31 | 2025-01-30 | 2024-11-28 | 2024-12-04 |  | 2025-01-06 | 2025-01-16 | Office 12.06.2025 | 2025-01-30 |  | 2025-01-20 | 2025-04-04 | 2025-04-04 | 2025-06-04 | 2025-06-04 | 1368 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-306 | NO TESTING REQUIRED
91994 | EB_F01-PHTGS-006-DN200-I16C00_R2 | 2 | true | 29.59 | EB_F01-PHTGS-006-DN200-I16C00_R2 |  | 1129 | EB | F01 | FoamInside | TBH-ZAT-2025-01-31 | 2025-01-30 | 2024-11-28 | 2024-12-04 |  | 2025-01-06 | 2025-01-16 | Office 12.06.2025 | 2025-01-30 |  | 2025-01-20 | 2025-04-03 | 2025-04-03 | 2025-06-05 | 2025-06-05 | 1368 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-306 | NO TESTING REQUIRED
91995 | FSA_F01-CHWR-005-DN150-I16C00_R1 | 1 | true | 82.15 | FSA_F01-CHWR-005-DN150-I16C00_R1 |  | 1129 | FSA Corridor | F01 | FoamInside | TBH-ZAT-2025-01-31 | 2025-01-30 | 2025-02-12 | 2025-02-13 |  | 2025-02-18 | 2025-03-06 | Office 16.05.2025 | 2025-03-12 |  | 2025-03-11 | 2025-03-28 | 2025-04-30 | 2025-05-06 | 2025-05-15 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-200 | System Loading Dock 01/System CHW and LTHW GROUND FLOOR/System CHW and LTHW FIRST FLOOR
91996 | FSA_F01-CHWR-008-DN015-I16C00_R0 | 0 | true | 8.11 | FSA_F01-CHWR-008-DN015-I16C00_R0 |  | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-01-31 | 2025-01-30 | 2025-02-18 | 2025-02-24 |  | 2025-02-26 | 2025-03-25 | Office 24/05/2025 | 2025-03-28 |  | 2025-03-27 | 2025-05-23 | 2025-05-23 | 2025-05-23 | 2025-05-23 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System CHW and LTHW GROUND FLOOR
91997 | FSA_F01-CHWR-010-DN020-I16C00_R0 | 0 | false | 2.35 | FSA_F01-CHWR-010-DN020-I16C00_R0 | LPP6A-M-506-XX-FSA | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-01-31 | 2025-01-30 |  | 2025-05-27 | To be revised | 2025-05-27 | 2025-05-27 | Office 28.05.2025 | 2025-05-27 |  | 2025-05-27 | 2025-05-27 | 2025-05-27 | 2025-05-27 | 2025-05-27 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System CHW and LTHW GROUND FLOOR
91998 | FSA_F01-CHWR-011-DN025-I16C00_R0 | 0 | false | 5.55 | FSA_F01-CHWR-011-DN025-I16C00_R0 | LPP6A-M-506-XX-FSA | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-01-31 | 2025-01-30 | 2025-05-28 | 2025-05-28 | To be revised | 2025-05-28 | 2025-05-29 | Office 03.06.2025 | 2025-05-28 |  | 2025-05-28 | 2025-05-28 | 2025-05-28 | 2025-05-29 | 2025-05-29 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System CHW and LTHW GROUND FLOOR
91999 | FSA_F01-CHWR-158-DN020-I16C00_R0 | 0 | true | 11.43 | FSA_F01-CHWR-158-DN020-I16C00_R0 | LPP6A-M-506-XX-FSA | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-01-31 | 2025-01-30 | 2025-02-18 | 2025-02-24 |  | 2025-02-26 | 2025-02-27 | Office 15.05.2025 | 2025-03-28 |  | 2025-02-27 | 2025-05-14 | 2025-05-14 | 2025-05-21 | 2025-05-21 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-211 | System CHW and LTHW GROUND FLOOR
92000 | FSA_F01-CHWR-159-DN020-I16C00_R0 | 0 | true | 13.92 | FSA_F01-CHWR-159-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-01-31 | 2025-01-30 | 2025-02-18 | 2025-02-24 |  | 2025-02-26 | 2025-03-07 | Office 15.05.2025 | 2025-03-28 |  | 2025-03-10 | 2025-05-12 | 2025-05-13 |  | 2025-05-30 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-211 | System CHW and LTHW GROUND FLOOR
92001 | FSA_F01-CHWR-160-DN020-I16C00_R0 | 0 | true | 16.17 | FSA_F01-CHWR-160-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-01-31 | 2025-01-30 | 2025-02-18 | 2025-02-24 |  | 2025-02-26 | 2025-02-28 | Office 15.05.2025 | 2025-03-28 |  | 2025-02-28 | 2025-05-08 | 2025-05-08 | 2025-05-23 | 2025-05-23 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-211 | System CHW and LTHW GROUND FLOOR
92002 | FSA_F01-CHWR-163-DN025-I16C00_R0 | 0 | true | 2.72 | FSA_F01-CHWR-163-DN025-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-01-31 | 2025-01-30 | 2025-02-19 | 2025-02-24 |  | 2025-02-26 | 2025-02-27 | Office 09.06.2025 | 2025-03-28 |  | 2025-02-27 | 2025-05-13 | 2025-05-13 | 2025-05-13 | 2025-06-03 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-221 | System Loading Dock 01
92003 | FSA_F01-CHWR-165-DN020-I16C00_R0 | 0 | true | 8.87 | FSA_F01-CHWR-165-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-01-31 | 2025-01-30 | 2025-02-19 | 2025-02-24 |  | 2025-02-26 | 2025-03-06 | Office 09.06.2025 | 2025-03-28 |  | 2025-03-10 | 2025-05-13 | 2025-06-04 | 2025-06-19 | 2025-06-19 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-221 | System Loading Dock 01
92004 | FSA_F01-CHWR-169-DN020-I16C00_R0 | 0 | true | 1.07 | FSA_F01-CHWR-169-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-01-31 | 2025-01-30 | 2025-02-13 | 2025-02-13 |  | 2025-02-14 | 2025-02-26 | Office 28.05.2025 | 2025-03-28 |  | 2025-02-27 | 2025-05-28 | 2025-05-28 | 2025-06-03 | 2025-06-03 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-221 | System Loading Dock 01
92005 | FSA_F01-CHWR-170-DN025-I16C00_R0 | 0 | true | 2.56 | FSA_F01-CHWR-170-DN025-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-01-31 | 2025-01-30 | 2025-02-13 | 2025-02-13 |  | 2025-02-14 | 2025-02-25 | Office 18.04.2025 | 2025-03-28 |  | 2025-02-27 | 2025-04-15 | 2025-04-15 | 2025-04-15 | 2025-04-15 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-221 | System Loading Dock 01
92006 | FSA_F01-CHWR-248-DN020-I16C00_R0 | 0 | true | 7.8 | FSA_F01-CHWR-248-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | N/A | TBH-ZAT-2025-01-31 | 2025-01-30 | 2025-02-13 | 2025-02-13 |  | 2025-02-14 | 2025-02-25 | Office 18.04.2025 | 2025-03-28 |  | 2025-02-27 | 2025-04-14 | 2025-04-14 | 2025-06-02 | 2025-06-02 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-221 | System Loading Dock 01
92007 | FSA_F01-CHWS-012-DN150-I16C00_R1 | 1 | true | 79.53 | FSA_F01-CHWS-012-DN150-I16C00_R1 |  | 1129 | FSA Corridor | F01 | FoamInside | TBH-ZAT-2025-01-31 | 2025-01-30 | 2025-02-13 | 2025-02-13 |  | 2025-02-18 | 2025-03-06 | Office 16.05.2025 | 2025-03-12 |  | 2025-03-11 | 2025-03-26 | 2025-04-26 | 2025-05-05 | 2025-05-15 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-200 | System Loading Dock 01/System CHW and LTHW GROUND FLOOR/System CHW and LTHW FIRST FLOOR
92008 | FSA_F01-CHWS-015-DN150-I16C00_R0 | 0 | true | 1.56 | FSA_F01-CHWS-015-DN150-I16C00_R0 |  | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-01-31 | 2025-01-30 | 2025-02-13 | 2025-02-13 |  | 2025-02-14 | 2025-02-25 | Office 12.04.2025 | 2025-03-28 |  | 2025-02-27 | 2025-04-11 | 2025-04-11 | 2025-04-11 |  | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System CHW and LTHW GROUND FLOOR
92009 | FSA_F01-CHWS-016-DN150-I16C00_R0 | 0 | true | 1.63 | FSA_F01-CHWS-016-DN150-I16C00_R0 |  | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-01-31 | 2025-01-30 |  | 2025-03-11 |  | 2025-03-17 | 2025-03-24 | Office 18.04.2025 |  |  | 2025-03-24 | 2025-04-15 | 2025-04-15 | 2025-04-15 | 2025-04-15 | 1359 | 193 | Working ISO delivered 14.04.25 - Spools to be checked |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System CHW and LTHW GROUND FLOOR
92010 | FSA_F01-CHWS-018-DN020-I16C00_R0 | 0 | true | 5.41 | FSA_F01-CHWS-018-DN020-I16C00_R0 |  | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-01-31 | 2025-01-30 | 2025-02-19 | 2025-02-24 |  | 2025-02-26 | 2025-02-28 | Office 28.05.2025 | 2025-03-28 |  | 2025-02-28 | 2025-05-26 | 2025-05-26 | 2025-05-27 | 2025-05-27 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System CHW and LTHW GROUND FLOOR
92011 | FSA_F01-CHWS-019-DN020-I16C00_R0 | 0 | false | 5.36 | FSA_F01-CHWS-019-DN020-I16C00_R0 | LPP6A-M-506-XX-FSA | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-01-31 | 2025-01-30 |  |  | To be revised | [10 empty] | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308
92012 | FSA_F01-CHWS-020-DN032-I16C00_R0 | 0 | true | 5.05 | FSA_F01-CHWS-020-DN032-I16C00_R0 | LPP6A-M-506-XX-FSA | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-01-31 | 2025-01-30 | 2025-02-19 | 2025-02-24 |  | 2025-02-26 | 2025-04-03 | Office 23/05/2025 | 2025-04-09 |  | 2025-03-31 | 2025-05-20 | 2025-05-21 | 2025-05-21 | 2025-05-21 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System CHW and LTHW GROUND FLOOR
92013 | FSA_F01-CHWS-021-DN032-I16C00_R0 | 0 | true | 3.54 | FSA_F01-CHWS-021-DN032-I16C00_R0 |  | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-01-31 | 2025-01-30 | 2025-02-17 | 2025-02-24 |  | 2025-02-26 | 2025-03-25 | Office 23/05/2025 | 2025-03-28 |  | 2025-03-27 | 2025-05-21 | 2025-05-21 | 2025-05-21 | 2025-05-21 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System CHW and LTHW GROUND FLOOR
92014 | FSA_F01-CHWS-022-DN032-I16C00_R0 | 0 | true | 0.27 | FSA_F01-CHWS-022-DN032-I16C00_R0 |  | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-01-31 | 2025-01-30 | 2025-02-19 | 2025-02-24 |  | 2025-02-26 | 2025-03-24 | Office 23/05/2025 | 2025-03-28 |  | 2025-03-24 | 2025-05-21 | 2025-05-21 | 2025-05-21 | 2025-05-21 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System CHW and LTHW GROUND FLOOR
92015 | FSA_F01-CHWS-158-DN020-I16C00_R0 | 0 | true | 12.28 | FSA_F01-CHWS-158-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-01-31 | 2025-01-30 | 2025-02-19 | 2025-02-24 |  | 2025-02-26 | 2025-03-07 | Office 15.05.2025 | 2025-03-28 |  | 2025-03-10 | 2025-05-14 | 2025-05-14 | 2025-05-21 | 2025-05-21 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-211 | System CHW and LTHW GROUND FLOOR
92016 | FSA_F01-CHWS-159-DN020-I16C00_R0 | 0 | true | 14.73 | FSA_F01-CHWS-159-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-01-31 | 2025-01-30 | 2025-02-19 | 2025-02-24 |  | 2025-02-26 | 2025-03-06 | Office 15.05.2025 | 2025-03-28 |  | 2025-03-10 | 2025-05-12 | 2025-05-13 |  | 2025-05-30 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-211 | System CHW and LTHW GROUND FLOOR
92017 | FSA_F01-CHWS-160-DN020-I16C00_R0 | 0 | true | 17 | FSA_F01-CHWS-160-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-01-31 | 2025-01-30 | 2025-02-19 | 2025-02-24 |  | 2025-02-26 | 2025-03-06 | Office 15.05.2025 | 2025-03-28 |  | 2025-03-10 | 2025-05-08 | 2025-05-08 | 2025-05-23 | 2025-05-23 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-211 | System CHW and LTHW GROUND FLOOR
92018 | FSA_F01-CHWS-163-DN025-I16C00_R0 | 0 | true | 2.82 | FSA_F01-CHWS-163-DN025-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-01-31 | 2025-01-30 | 2025-02-19 | 2025-02-24 |  | 2025-02-26 | 2025-03-06 | Office 09.06.2025 | 2025-03-28 |  | 2025-03-10 | 2025-05-13 | 2025-05-13 | 2025-05-13 | 2025-06-03 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-221 | System Loading Dock 01
92019 | FSA_F01-CHWS-165-DN020-I16C00_R0 | 0 | true | 8.99 | FSA_F01-CHWS-165-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-01-31 | 2025-01-30 | 2025-02-19 | 2025-02-24 |  | 2025-02-26 | 2025-02-28 | Office 09.06.2025 | 2025-03-28 |  | 2025-02-28 | 2025-05-13 | 2025-06-04 | 2025-06-19 | 2025-06-19 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-221 | System Loading Dock 01
92020 | FSA_F01-CHWS-169-DN020-I16C00_R0 | 0 | true | 1.27 | FSA_F01-CHWS-169-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-01-31 | 2025-01-30 | 2025-02-13 | 2025-02-13 |  | 2025-02-14 | 2025-02-25 | Office 28.05.2025 | 2025-03-28 |  | 2025-02-27 | 2025-05-28 | 2025-05-28 | 2025-06-03 | 2025-06-03 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-221 | System Loading Dock 01
92021 | FSA_F01-CHWS-170-DN025-I16C00_R0 | 0 | true | 2.44 | FSA_F01-CHWS-170-DN025-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-01-31 | 2025-01-30 | 2025-02-13 | 2025-02-13 |  | 2025-02-14 | 2025-02-26 | Office 18.04.2025 | 2025-03-28 |  | 2025-02-27 | 2025-04-15 | 2025-04-15 | 2025-04-15 | 2025-04-16 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-221 | System Loading Dock 01
92022 | FSA_F01-CHWS-248-DN020-I16C00_R0 | 0 | true | 7.74 | FSA_F01-CHWS-248-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | N/A | TBH-ZAT-2025-01-31 | 2025-01-30 | 2025-02-13 | 2025-02-13 |  | 2025-02-14 | 2025-02-25 | Office 18.04.2025 | 2025-03-28 |  | 2025-02-27 | 2025-04-14 | 2025-04-14 | 2025-06-02 | 2025-06-02 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-221 | System Loading Dock 01
92023 | FSA_F01-LTHWR-158-DN020-I16C00_R0 | 0 | true | 11.38 | FSA_F01-LTHWR-158-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-01-31 | 2025-01-30 | 2025-02-19 | 2025-02-24 |  | 2025-02-26 | 2025-03-07 | Office 15.05.2025 | 2025-03-28 |  | 2025-03-10 | 2025-05-14 | 2025-05-14 | 2025-05-21 | 2025-05-21 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-211 | System CHW and LTHW GROUND FLOOR
92024 | FSA_F01-LTHWR-159-DN020-I16C00_R0 | 0 | true | 13.88 | FSA_F01-LTHWR-159-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-01-31 | 2025-01-30 | 2025-02-19 | 2025-02-24 |  | 2025-02-26 | 2025-03-07 | Office 15.05.2025 | 2025-03-28 |  | 2025-03-10 | 2025-05-12 | 2025-05-13 |  | 2025-05-30 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-211 | System CHW and LTHW GROUND FLOOR
92025 | FSA_F01-LTHWR-160-DN020-I16C00_R0 | 0 | true | 16.15 | FSA_F01-LTHWR-160-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-01-31 | 2025-01-30 | 2025-02-19 | 2025-02-24 |  | 2025-02-27 | 2025-03-07 | Office 15.05.2025 | 2025-03-28 |  | 2025-03-10 | 2025-05-08 | 2025-05-08 | 2025-05-23 | 2025-05-23 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-211 | System CHW and LTHW GROUND FLOOR
92026 | FSA_F01-LTHWR-163-DN025-I16C00_R0 | 0 | true | 8.13 | FSA_F01-LTHWR-163-DN025-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-01-31 | 2025-01-30 | 2025-02-14 | 2025-02-24 |  | 2025-02-27 | 2025-03-06 | Office 09.06.2025 | 2025-03-28 |  | 2025-03-10 | 2025-05-13 | 2025-05-13 | 2025-05-13 | 2025-06-04 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-221 | System Loading Dock 01
92027 | FSA_F01-LTHWR-165-DN020-I16C00_R0 | 0 | true | 2.34 | FSA_F01-LTHWR-165-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-01-31 | 2025-01-30 | 2025-02-14 | 2025-02-24 |  | 2025-02-27 | 2025-03-07 | Office 09.06.2025 | 2025-03-28 |  | 2025-03-10 | 2025-05-13 | 2025-06-04 | 2025-06-19 | 2025-06-19 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-221 | System Loading Dock 01
92028 | FSA_F01-LTHWR-169-DN020-I16C00_R0 | 0 | true | 0.91 | FSA_F01-LTHWR-169-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-01-31 | 2025-01-30 | 2025-02-13 | 2025-02-13 |  | 2025-02-14 | 2025-02-25 | Office 28.05.2025 | 2025-03-28 |  | 2025-02-27 | 2025-05-28 | 2025-05-28 | 2025-06-03 | 2025-06-03 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-221 | System Loading Dock 01
92029 | FSA_F01-LTHWR-170-DN020-I16C00_R0 | 0 | true | 2.93 | FSA_F01-LTHWR-170-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-01-31 | 2025-01-30 | 2025-02-13 | 2025-02-13 |  | 2025-02-14 | 2025-02-25 | Office 18.04.2025 | 2025-03-28 |  | 2025-02-27 | 2025-04-16 | 2025-04-16 | 2025-04-16 | 2025-04-16 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-221 | System Loading Dock 01
92030 | FSA_F01-LTHWR-248-DN020-I16C00_R0 | 0 | true | 8.2 | FSA_F01-LTHWR-248-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | N/A | TBH-ZAT-2025-01-31 | 2025-01-30 | 2025-02-13 | 2025-02-13 |  | 2025-02-17 | 2025-02-25 | Office 18.04.2025 | 2025-03-28 |  | 2025-02-27 | 2025-04-15 | 2025-04-15 | 2025-06-02 | 2025-06-02 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-221 | System Loading Dock 01
92031 | FSA_F01-LTHWS-158-DN020-I16C00_R0 | 0 | true | 11.77 | FSA_F01-LTHWS-158-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-01-31 | 2025-01-30 | 2025-02-20 | 2025-02-24 |  | 2025-02-27 | 2025-03-06 | Office 15.05.2025 | 2025-03-28 |  | 2025-03-10 | 2025-05-14 | 2025-05-14 | 2025-05-21 | 2025-05-21 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-211 | System CHW and LTHW GROUND FLOOR
92032 | FSA_F01-LTHWS-159-DN020-I16C00_R0 | 0 | true | 14.29 | FSA_F01-LTHWS-159-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-01-31 | 2025-01-30 | 2025-02-20 | 2025-02-24 |  | 2025-02-27 | 2025-03-06 | Office 15.05.2025 | 2025-03-28 |  | 2025-03-10 | 2025-05-12 | 2025-05-14 |  | 2025-05-30 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-211 | System CHW and LTHW GROUND FLOOR
92033 | FSA_F01-LTHWS-160-DN020-I16C00_R0 | 0 | true | 16.54 | FSA_F01-LTHWS-160-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-01-31 | 2025-01-30 | 2025-02-20 | 2025-02-24 |  | 2025-02-27 | 2025-03-06 | Office 15.05.2025 | 2025-03-28 |  | 2025-03-10 | 2025-05-08 | 2025-05-08 | 2025-05-23 | 2025-05-23 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-211 | System CHW and LTHW GROUND FLOOR
92034 | FSA_F01-LTHWS-163-DN025-I16C00_R0 | 0 | true | 8.5 | FSA_F01-LTHWS-163-DN025-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-01-31 | 2025-01-30 | 2025-02-14 | 2025-02-24 |  | 2025-02-27 | 2025-03-06 | Office 09.06.2025 | 2025-03-28 |  | 2025-03-10 | 2025-05-13 | 2025-05-13 | 2025-05-13 | 2025-06-04 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-221 | System Loading Dock 01
92035 | FSA_F01-LTHWS-165-DN020-I16C00_R0 | 0 | true | 2.29 | FSA_F01-LTHWS-165-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-01-31 | 2025-01-30 | 2025-02-14 | 2025-02-24 |  | 2025-02-27 | 2025-03-06 | Office 09.06.2025 | 2025-03-28 |  | 2025-03-10 | 2025-05-13 | 2025-06-04 | 2025-06-19 | 2025-06-19 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-221 | System Loading Dock 01
92036 | FSA_F01-LTHWS-169-DN020-I16C00_R0 | 0 | true | 0.96 | FSA_F01-LTHWS-169-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-01-31 | 2025-01-30 | 2025-02-13 | 2025-02-13 |  | 2025-02-14 | 2025-02-26 | Office 28.05.2025 | 2025-03-28 |  | 2025-02-27 | 2025-05-28 | 2025-05-28 | 2025-06-03 | 2025-06-03 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-221 | System Loading Dock 01
92037 | FSA_F01-LTHWS-170-DN020-I16C00_R0 | 0 | true | 2.74 | FSA_F01-LTHWS-170-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-01-31 | 2025-01-30 | 2025-02-14 | 2025-02-13 |  | 2025-02-14 | 2025-02-25 | Office 18.04.2025 | 2025-03-28 |  | 2025-02-27 | 2025-04-16 | 2025-04-16 | 2025-04-16 | 2025-04-16 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-221 | System Loading Dock 01
92038 | FSA_F01-LTHWS-248-DN020-I16C00_R0 | 0 | true | 8.04 | FSA_F01-LTHWS-248-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | N/A | TBH-ZAT-2025-01-31 | 2025-01-30 | 2025-02-14 | 2025-02-13 |  | 2025-02-14 | 2025-02-25 | Office 18.04.2025 | 2025-03-28 |  | 2025-02-27 | 2025-04-15 | 2025-04-15 | 2025-06-02 | 2025-06-02 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-221 | System Loading Dock 01
92039 | FSA_F01-PHTGR-001-DN150-I16C00_R0 | 0 | true | 9.13 | FSA_F01-PHTGR-001-DN150-I16C00_R0 |  | 1129 | FSA Mech Wet Room | F01 | N/A | TBH-ZAT-2025-01-31 | 2025-01-30 | 2025-02-13 | 2025-02-13 |  | 2025-03-03 | 2025-03-13 | Office 18.04.2025 | 2025-03-19 |  | 2025-03-14 | 2025-04-09 | 2025-04-11 | 2025-04-11 | 2025-04-14 | 1368 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System PHTG
92040 | FSA_F01-PHTGR-002-DN080-I16C00_R0 | 0 | true | 2.18 | FSA_F01-PHTGR-002-DN080-I16C00_R0 |  | 1129 | FSA Mech Wet Room | F01 | N/A | TBH-ZAT-2025-01-31 | 2025-01-30 | 2025-02-13 | 2025-02-13 |  | 2025-02-14 | 2025-02-25 | Office 18.04.2025 | 2025-03-28 |  | 2025-02-27 | 2025-04-12 | 2025-04-12 | 2025-04-14 | 2025-04-14 | 1368 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System PHTG
92041 | FSA_F01-PHTGR-003-DN080-I16C00_R0 | 0 | true | 2.2 | FSA_F01-PHTGR-003-DN080-I16C00_R0 |  | 1129 | FSA Mech Wet Room | F01 | N/A | TBH-ZAT-2025-01-31 | 2025-01-30 | 2025-02-13 | 2025-02-13 |  | 2025-02-14 | 2025-02-27 | Office 18.04.2025 | 2025-03-28 |  | 2025-02-27 | 2025-04-12 | 2025-04-12 | 2025-04-14 | 2025-04-14 | 1368 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System PHTG
92042 | FSA_F01-PHTGR-004-DN200-I16C00_R0 | 0 | true | 7.68 | FSA_F01-PHTGR-004-DN200-I16C00_R0 |  | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-01-31 | 2025-01-30 | 2025-02-12 | 2025-02-13 |  | 2025-02-25 | 2025-03-06 | Office 02.06.2025 | 2025-03-12 |  | 2025-03-11 | 2025-03-25 | 2025-03-26 | 2025-03-27 | 2025-05-08 | 1368 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System PHTG
92043 | FSA_F01-PHTGR-005-DN200-I16C00_R0 | 0 | true | 30.04 | FSA_F01-PHTGR-005-DN200-I16C00_R0 |  | 1129 | FSA Corridor | F01 | N/A | TBH-ZAT-2025-01-31 | 2025-01-30 | 2025-02-12 | 2025-02-13 |  | 2025-02-25 | 2025-03-06 | Office 05.04.2025 | 2025-03-12 |  | 2025-03-11 | 2025-03-20 | 2025-03-20 | 2025-03-25 | 2025-04-04 | 1368 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-200 | NO TESTING REQUIRED
92044 | FSA_F01-PHTGR-006-DN200-I16C00_R0 | 0 | true | 10.77 | FSA_F01-PHTGR-006-DN200-I16C00_R0 |  | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-01-31 | 2025-01-30 | 2025-02-13 | 2025-02-13 |  | 2025-02-25 | 2025-03-06 | Office 09.04.2025 | 2025-03-12 |  | 2025-03-11 | 2025-04-04 | 2025-04-04 | 2025-04-05 | 2025-04-05 | 1368 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System PHTG
92045 | FSA_F01-PHTGR-007-DN150-I16C00_R0 | 0 | true | 3.49 | FSA_F01-PHTGR-007-DN150-I16C00_R0 |  | 1129 | FSA Mech Wet Room | F01 | N/A | TBH-ZAT-2025-01-31 | 2025-01-30 | 2025-02-20 | 2025-02-24 |  | 2025-03-03 | 2025-03-13 | Office 11.04.2025 | 2025-03-19 |  | 2025-03-14 | 2025-04-08 | 2025-04-09 | 2025-04-09 | 2025-04-09 | 1368 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System PHTG
92046 | FSA_F01-PHTGR-008-DN100-I16C00_2_R0 | 0 | true | 32.15 | FSA_F01-PHTGR-008-DN100-I16C00_2_R0 |  | 1129 | FSA Riser South | F01 | N/A | TBH-ZAT-2025-01-31 | 2025-01-30 | 2025-02-10 | 2025-02-13 |  | 2025-02-18 | 2025-03-06 | Office 11.04.2025 | 2025-03-12 |  | 2025-03-11 | 2025-04-07 | 2025-04-08 | 2025-04-09 | 2025-05-13 | 1368 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-200 | System PHTG
92047 | FSA_F01-PHTGR-010-DN050-I16C00_R0 | 0 | true | 2.06 | FSA_F01-PHTGR-010-DN050-I16C00_R0 |  | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-01-31 | 2025-01-30 | 2025-02-20 | 2025-02-24 |  | 2025-02-27 | 2025-03-27 | Vojica Erkic 12.05.2025 | 2025-03-28 |  | 2025-03-27 |  |  |  | 2025-05-30 | 1368 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System PHTG
92048 | FSA_F01-PHTGR-011-DN032-I16C00_R0 | 0 | true | 0.39 | FSA_F01-PHTGR-011-DN032-I16C00_R0 |  | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-01-31 | 2025-01-30 | 2025-02-20 | 2025-02-24 |  | 2025-02-27 | 2025-04-01 | Vojica Erkic 12.05.2025 | 2025-04-09 |  | 2025-03-31 |  |  |  | 2025-05-30 | 1368 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System PHTG
92049 | FSA_F01-PHTGR-012-DN050-I16C00_R0 | 0 | true | 3.15 | FSA_F01-PHTGR-012-DN050-I16C00_R0 |  | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-01-31 | 2025-01-30 | 2025-02-20 | 2025-02-24 |  | 2025-02-27 | 2025-04-03 | Vojica Erkic 12.05.2025 | 2025-04-09 |  | 2025-03-31 |  |  |  | 2025-05-30 | 1368 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System PHTG
92050 | FSA_F01-PHTGR-013-DN020-I16C00_R0 | 0 | false | 3.1 | FSA_F01-PHTGR-013-DN020-I16C00_R0 | LPP6A-M-504-XX-FSA | 1129 | FSA Mech Wet Room | F01 | N/A | TBH-ZAT-2025-01-31 | 2025-01-30 |  |  | TO be revised | [10 empty] | 1368 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308
92051 | FSA_F01-PHTGS-001-DN080-I16C00_R0 | 0 | true | 13.05 | FSA_F01-PHTGS-001-DN080-I16C00_R0 | LPP6A-M-504-XX-FSA | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-01-31 | 2025-01-30 | 2025-02-13 | 2025-02-13 |  | 2025-03-03 | 2025-03-13 | Office 18.04.2025 | 2025-03-19 |  | 2025-03-14 | 2025-04-12 | 2025-04-15 | 2025-04-15 | 2025-05-13 | 1368 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System PHTG
92052 | FSA_F01-PHTGS-002-DN080-I16C00_R0 | 0 | true | 1.9 | FSA_F01-PHTGS-002-DN080-I16C00_R0 |  | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-01-31 | 2025-01-30 | 2025-02-13 | 2025-02-13 |  | 2025-02-14 | 2025-02-25 | Office 14.05.2025 | 2025-03-28 |  | 2025-02-27 | 2025-04-16 | 2025-04-16 | 2025-04-16 | 2025-04-16 | 1368 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System PHTG
92053 | FSA_F01-PHTGS-003-DN080-I16C00_R0 | 0 | true | 2.88 | FSA_F01-PHTGS-003-DN080-I16C00_R0 |  | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-01-31 | 2025-01-30 | 2025-02-13 | 2025-02-13 |  | 2025-02-14 | 2025-03-24 | Office 18.04.2025 | 2025-03-28 |  | 2025-03-24 | 2025-04-12 | 2025-04-12 | 2025-04-14 | 2025-04-15 | 1368 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System PHTG
92054 | FSA_F01-PHTGS-004-DN150-I16C00_R0 | 0 | true | 9.07 | FSA_F01-PHTGS-004-DN150-I16C00_R0 |  | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-01-31 | 2025-01-30 | 2025-02-13 | 2025-02-13 |  | 2025-03-03 | 2025-03-13 | Office 18.04.2025 | 2025-03-19 |  | 2025-03-14 | 2025-03-28 | 2025-04-03 | 2025-04-14 | 2025-05-13 | 1368 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System PHTG
92055 | FSA_F01-PHTGS-005-DN200-I16C00_R0 | 0 | true | 8.38 | FSA_F01-PHTGS-005-DN200-I16C00_R0 |  | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-01-31 | 2025-01-30 | 2025-02-12 | 2025-02-13 |  | 2025-02-25 | 2025-03-13 | Office 02.06.2025 | 2025-03-19 |  | 2025-03-14 | 2025-03-25 | 2025-03-26 | 2025-03-27 | 2025-05-08 | 1368 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System PHTG
92056 | FSA_F01-PHTGS-006-DN200-I16C00_R0 | 0 | true | 29.99 | FSA_F01-PHTGS-006-DN200-I16C00_R0 |  | 1129 | FSA Corridor | F01 | FoamInside | TBH-ZAT-2025-01-31 | 2025-01-30 | 2025-02-12 | 2025-02-13 |  | 2025-02-25 | 2025-03-13 | Office 05.04.2025 | 2025-03-19 |  | 2025-03-14 | 2025-03-24 | 2025-03-25 | 2025-03-25 | 2025-04-03 | 1368 | 193 | Only Spool 3 delivered |  |  | 194 | SEP | SEP | [5 empty] | 1-200 | NO TESTING REQUIRED
92057 | FSA_F01-PHTGS-007-DN200-I16C00_R0 | 0 | true | 9.8 | FSA_F01-PHTGS-007-DN200-I16C00_R0 |  | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-01-31 | 2025-01-30 | 2025-02-13 | 2025-02-13 |  | 2025-02-25 | 2025-03-13 | Office 09.04.2025 | 2025-03-19 |  | 2025-03-14 | 2025-04-07 | 2025-04-08 | 2025-04-08 | 2025-05-30 | 1368 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System PHTG
92058 | FSA_F01-PHTGS-008-DN100-I16C00_R0 | 0 | true | 2.84 | FSA_F01-PHTGS-008-DN100-I16C00_R0 |  | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-01-31 | 2025-01-30 | 2025-02-20 | 2025-02-24 |  | 2025-02-27 | 2025-04-02 | Office 26/04/2025 | 2025-04-09 |  | 2025-03-31 | 2025-04-24 | 2025-04-24 | 2025-04-25 | 2025-04-26 | 1368 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System PHTG
92059 | FSA_F01-PHTGS-009-DN100-I16C00_R0 | 0 | true | 1.31 | FSA_F01-PHTGS-009-DN100-I16C00_R0 |  | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-01-31 | 2025-01-30 | 2025-02-20 | 2025-02-24 |  | 2025-02-27 | 2025-04-02 | Office 26/04/2025 | 2025-04-09 |  | 2025-03-31 | 2025-04-23 | 2025-04-24 | 2025-04-24 | 2025-04-26 | 1368 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System PHTG
92060 | FSA_F01-PHTGS-010-DN150-I16C00_R0 | 0 | true | 1.4 | FSA_F01-PHTGS-010-DN150-I16C00_R0 |  | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-01-31 | 2025-01-30 | 2025-02-20 | 2025-02-24 |  | 2025-03-07 | 2025-03-31 | Office 26/04/2025 | 2025-04-09 |  | 2025-03-31 | 2025-04-24 | 2025-04-24 | 2025-04-25 | 2025-04-25 | 1368 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System PHTG
92061 | FSA_F01-PHTGS-011-DN150-I16C00_R0 | 0 | true | 1.56 | FSA_F01-PHTGS-011-DN150-I16C00_R0 |  | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-01-31 | 2025-01-30 | 2025-02-20 | 2025-02-24 |  | 2025-03-07 | 2025-03-31 | Office 26/04/2025 | 2025-04-09 |  | 2025-03-31 | 2025-04-24 | 2025-04-24 | 2025-04-24 | 2025-04-25 | 1368 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System PHTG
92062 | FSA_F01-PHTGS-014-DN100-I16C00_R0 | 0 | true | 1.61 | FSA_F01-PHTGS-014-DN100-I16C00_R0 |  | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-01-31 | 2025-01-30 | 2025-02-20 | 2025-02-24 |  | 2025-03-13 | 2025-03-31 | Office 26/04/2025 | 2025-04-09 |  | 2025-03-31 | 2025-04-23 | 2025-04-23 | 2025-04-24 | 2025-04-26 | 1368 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System PHTG
92063 | FSA_F01-PHTGS-015-DN150-I16C00_1_R0 | 0 | true | 31.68 | FSA_F01-PHTGS-015-DN150-I16C00_1_R0 |  | 1129 | FSA Riser South | F01 | FoamInside | TBH-ZAT-2025-01-31 | 2025-01-30 | 2025-02-12 | 2025-02-13 |  | 2025-03-03 | 2025-03-13 | Office 26/04/2025 | 2025-03-19 |  | 2025-03-14 | 2025-04-02 | 2025-04-10 | 2025-04-24 | 2025-04-25 | 1368 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-200 | System PHTG
92064 | FSA_F01-PHTGS-016-DN150-I16C00_R0 | 0 | true | 1.21 | FSA_F01-PHTGS-016-DN150-I16C00_R0 |  | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-01-31 | 2025-01-30 | 2025-02-12 | 2025-02-13 |  | 2025-03-03 | 2025-03-13 | Office 14.05.2025 | 2025-03-19 |  | 2025-03-14 | 2025-04-23 | 2025-04-24 | 2025-04-24 | 2025-04-24 | 1368 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System PHTG
92065 | FSA_F01-PHTGS-026-DN020-I16C00_R0 | 0 | false | 2.81 | FSA_F01-PHTGS-026-DN020-I16C00_R0 | LPP6A-M-504-XX-FSA | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-01-31 | 2025-01-30 | [13 empty] | 1368 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308
92066 | FSA_F01-PHTGS-027-DN015-I16C00_R0 | 0 | false | 19.8 | FSA_F01-PHTGS-027-DN015-I16C00_R0 | LPP6A-M-504-XX-FSA | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-01-31 | 2025-01-30 | [13 empty] | 1368 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308
92067 | FSA_F01-PHTGS-028-DN025-I16C00_R0 | 0 | false | 5.94 | FSA_F01-PHTGS-028-DN025-I16C00_R0 | LPP6A-M-504-XX-FSA | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-01-31 | 2025-01-30 | [13 empty] | 1368 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308
92068 | FSA_F01-PHTGS-029-DN020-I16C00_R0 | 0 | false | 4.26 | FSA_F01-PHTGS-029-DN020-I16C00_R0 | LPP6A-M-504-XX-FSA | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-01-31 | 2025-01-30 | [13 empty] | 1368 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308
92069 | FSA_F02_1-PHTGR-014-DN150-I16C00_R1 | 1 | true | 55.15 | FSA_F02_1-PHTGR-014-DN150-I16C00_R1 | LPP6A-M-504-XX-FSA | 1129 | FSA Corridor | F02 | N/A | TBH-ZAT-2025-01-31 | 2025-01-30 | 2024-12-01 | 2024-12-04 |  | 2024-12-11 | 2024-12-16 | Office 02.04.2025 | 2025-01-08 |  | 2024-12-19 | 2025-01-31 | 2025-02-22 | 2025-03-22 | 2025-03-22 | 1368 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-200 | System PHTG
92070 | FSA_F02_1-PHTGS-030-DN150-I16C00_R2 | 2 | true | 56.11 | FSA_F02_1-PHTGS-030-DN150-I16C00_R2 |  | 1129 | FSA Corridor | F02 | FoamInside | TBH-ZAT-2025-01-31 | 2025-01-30 | 2024-12-01 | 2024-12-04 |  | 2024-12-11 | 2024-12-16 | Office 02.04.2025 | 2025-01-08 |  | 2024-12-19 | 2025-01-31 | 2025-03-22 | 2025-03-25 | 2025-05-30 | 1368 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-200 | System PHTG
92072 | FSA_ROF-PHTGS-030-DN150-I16C00_R1 | 1 | true | 9.3 | FSA_ROF-PHTGS-030-DN150-I16C00_R1 |  | 1129 | FSA Roof | Roof | FoamInside | TBH-ZAT-2025-01-31 | 2025-01-30 | 2025-01-16 | 2025-02-13 |  | 2025-02-13 | 2025-02-13 | Office 23.06.2025 | 2025-03-28 |  | 2025-03-10 | 2025-05-09 | 2025-05-09 | 2025-05-09 | 2025-06-17 | 1368 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | External Roof North | System PHTG
93442 | FSA_F01-CHWR-100-DN032-I16C00_R0 | 0 | true | 15.8 | FSA_F01-CHWR-100-DN032-I16C00_R0 |  | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-04 | 2025-03-11 |  | 2025-03-12 | 2025-04-03 | Office 24/05/2025 | 2025-04-09 |  | 2025-03-31 | 2025-05-08 | 2025-05-08 | 2025-05-13 | 2025-05-13 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System CHW and LTHW GROUND FLOOR
93443 | FSA_F01-CHWR-101-DN020-I16C00_R0 | 0 | true | 3.44 | FSA_F01-CHWR-101-DN020-I16C00_R0 |  | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-04 | 2025-03-11 |  | 2025-03-12 | 2025-03-19 | Office 24/05/2025 | 2025-03-28 |  | 2025-03-21 | 2025-05-14 | 2025-05-14 | 2025-05-28 | 2025-05-28 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System CHW and LTHW GROUND FLOOR
93444 | FSA_F01-CHWR-102-DN020-I16C00_R0 | 0 | true | 1.78 | FSA_F01-CHWR-102-DN020-I16C00_R0 |  | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-04 | 2025-03-11 |  | 2025-03-12 | 2025-03-14 | Office 26/05/2025 | 2025-03-28 |  | 2025-03-14 | 2025-05-16 | 2025-05-16 | 2025-05-27 | 2025-05-27 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System CHW and LTHW GROUND FLOOR
93445 | FSA_F01-CHWR-103-DN020-I16C00_R0 | 0 | true | 2.35 | FSA_F01-CHWR-103-DN020-I16C00_R0 |  | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-04 | 2025-03-11 |  | 2025-03-12 | 2025-03-19 | Office 24/05/2025 | 2025-03-28 |  | 2025-03-21 | 2025-05-19 | 2025-05-19 | 2025-05-26 | 2025-05-26 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System CHW and LTHW GROUND FLOOR
93446 | FSA_F01-CHWR-104-DN020-I16C00_R0 | 0 | true | 3.31 | FSA_F01-CHWR-104-DN020-I16C00_R0 |  | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-04 | 2025-03-11 |  | 2025-03-12 | 2025-03-19 | Office 27/05/2025 | 2025-03-28 |  | 2025-03-21 | 2025-05-20 | 2025-05-20 | 2025-05-29 | 2025-05-29 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System CHW and LTHW GROUND FLOOR
93447 | FSA_F01-CHWR-105-DN020-I16C00_R0 | 0 | true | 2.33 | FSA_F01-CHWR-105-DN020-I16C00_R0 |  | 1129 | FSA Corridor | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-14 | 2025-03-13 |  | 2025-03-18 | 2025-03-21 | Office 26/05/2025 | 2025-03-28 |  | 2025-03-27 | 2025-05-20 | 2025-05-20 | 2025-06-19 | 2025-06-19 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-200 | System CHW and LTHW GROUND FLOOR
93448 | FSA_F01-CHWR-106-DN050-I16C00_R0 | 0 | true | 31.5 | FSA_F01-CHWR-106-DN050-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-14 | 2025-03-13 |  | 2025-03-18 | 2025-04-03 | Office 26/04/2025 | 2025-04-09 |  | 2025-04-04 | 2025-04-17 | 2025-04-26 | 2025-04-26 | 2025-05-30 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-200, 1-125 | System CHW and LTHW GROUND FLOOR
93449 | FSA_F01-CHWR-107-DN040-I16C00_R0 | 0 | true | 1.67 | FSA_F01-CHWR-107-DN040-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-14 | 2025-03-13 |  | 2025-03-18 | 2025-03-31 | Office 09.06.2025 | 2025-04-09 |  | 2025-03-31 | 2025-06-05 | 2025-06-05 | 2025-06-05 | 2025-06-06 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-131 | System CHW and LTHW GROUND FLOOR
93450 | FSA_F01-CHWR-108-DN020-I16C00_R0 | 0 | true | 12.68 | FSA_F01-CHWR-108-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-04 | 2025-03-11 |  | 2025-03-12 | 2025-03-19 | Office 20/05/2025 | 2025-03-28 |  | 2025-03-21 | 2025-05-16 | 2025-05-16 | 2025-05-26 | 2025-05-26 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-201 | System CHW and LTHW GROUND FLOOR
93451 | FSA_F01-CHWR-109-DN020-I16C00_R0 | 0 | true | 8.65 | FSA_F01-CHWR-109-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-02-20 | 2025-02-24 |  | 2025-02-28 | 2025-03-07 | Office 15.05.2025 | 2025-03-28 |  | 2025-03-10 | 2025-05-09 | 2025-05-09 | 2025-05-20 | 2025-05-20 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-236 | System CHW and LTHW GROUND FLOOR
93452 | FSA_F01-CHWR-110-DN020-I16C00_R0 | 0 | true | 7.12 | FSA_F01-CHWR-110-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-04 | 2025-03-11 |  | 2025-03-12 | 2025-03-19 | Office 15.05.2025 | 2025-03-28 |  | 2025-03-21 | 2025-05-14 | 2025-05-14 | 2025-06-11 | 2025-06-11 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-200 | System CHW and LTHW GROUND FLOOR
93453 | FSA_F01-CHWR-111-DN015-I16C00_R0 | 0 | true | 3.56 | FSA_F01-CHWR-111-DN015-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-02-20 | 2025-02-24 |  | 2025-02-28 | 2025-03-19 | Office 21/05/2025 | 2025-03-28 |  | 2025-03-21 | 2025-05-19 | 2025-05-19 | 2025-05-23 | 2025-05-23 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-214 | System CHW and LTHW GROUND FLOOR
93454 | FSA_F01-CHWR-112-DN015-I16C00_R0 | 0 | true | 3.54 | FSA_F01-CHWR-112-DN015-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-05 | 2025-03-11 |  | 2025-03-12 | 2025-03-19 | Office 21/05/2025 | 2025-03-28 |  | 2025-03-21 | 2025-05-19 | 2025-05-19 | 2025-05-28 | 2025-05-28 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-214 | System CHW and LTHW GROUND FLOOR
93455 | FSA_F01-CHWR-114-DN020-I16C00_R0 | 0 | true | 3.21 | FSA_F01-CHWR-114-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-02-21 | 2025-02-24 |  | 2025-02-28 | 2025-04-02 | Office 29.05.2025 | 2025-04-09 |  | 2025-04-04 | 2025-05-12 | 2025-05-12 | 2025-05-27 | 2025-05-27 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-215 | System CHW and LTHW GROUND FLOOR
93456 | FSA_F01-CHWR-117-DN025-I16C00_R0 | 0 | true | 2.64 | FSA_F01-CHWR-117-DN025-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-04 | 2025-03-11 |  | 2025-03-12 | 2025-03-19 | Office 20/05/2025 | 2025-03-28 |  | 2025-03-21 | 2025-05-16 | 2025-05-16 | 2025-06-17 | 2025-06-17 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-240 | System CHW and LTHW GROUND FLOOR
93457 | FSA_F01-CHWR-118-DN032-I16C00_R0 | 0 | true | 7.59 | FSA_F01-CHWR-118-DN032-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-02-21 | 2025-02-24 |  | 2025-02-28 | 2025-04-03 | Office 30/04/2025 | 2025-04-09 |  | 2025-03-31 | 2025-04-24 | 2025-04-24 | 2025-04-30 | 2025-04-30 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-126 | System CHW and LTHW GROUND FLOOR
93458 | FSA_F01-CHWR-119-DN020-I16C00_R0 | 0 | true | 1.82 | FSA_F01-CHWR-119-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-02-21 | 2025-02-24 |  | 2025-02-28 | 2025-03-07 | Office 30/04/2025 | 2025-03-28 |  | 2025-03-10 | 2025-04-29 | 2025-04-29 | 2025-05-12 | 2025-05-12 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-125 | System CHW and LTHW GROUND FLOOR
93459 | FSA_F01-CHWR-120-DN020-I16C00_R0 | 0 | true | 4.21 | FSA_F01-CHWR-120-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-02-21 | 2025-02-24 |  | 2025-02-28 | 2025-03-06 | Office 30/04/2025 | 2025-03-28 |  | 2025-03-10 | 2025-04-29 | 2025-04-29 | 2025-05-01 | 2025-05-01 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-126 | System CHW and LTHW GROUND FLOOR
93460 | FSA_F01-CHWR-121-DN020-I16C00_R0 | 0 | true | 2.74 | FSA_F01-CHWR-121-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-04 | 2025-03-11 |  | 2025-03-12 | 2025-03-19 | Office 13/05/2025 | 2025-04-09 |  | 2025-03-21 | 2025-05-12 | 2025-05-12 | 2025-06-09 | 2025-06-09 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-235 | System CHW and LTHW GROUND FLOOR
93461 | FSA_F01-CHWR-122-DN020-I16C00_R0 | 0 | true | 7.03 | FSA_F01-CHWR-122-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-04 | 2025-03-11 |  | 2025-03-12 | 2025-03-19 | Office 13/05/2025 | 2025-03-28 |  | 2025-03-21 | 2025-05-12 | 2025-05-12 | 2025-06-06 | 2025-06-06 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-235 | System CHW and LTHW GROUND FLOOR
93462 | FSA_F01-CHWR-123-DN020-I16C00_R0 | 0 | true | 1.53 | FSA_F01-CHWR-123-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-02-21 | 2025-02-24 |  | 2025-02-28 | 2025-03-07 | Office 01.05.2025 | 2025-03-28 |  | 2025-03-10 | 2025-05-01 | 2025-05-01 | 2025-05-14 | 2025-05-14 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-124 | System CHW and LTHW GROUND FLOOR
93463 | FSA_F01-CHWR-124-DN020-I16C00_R0 | 0 | true | 4.56 | FSA_F01-CHWR-124-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-02-21 | 2025-02-24 |  | 2025-02-28 | 2025-03-06 | Office 01.05.2025 | 2025-03-28 |  | 2025-03-10 | 2025-05-01 | 2025-05-01 | 2025-05-14 | 2025-05-14 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-124 | System CHW and LTHW GROUND FLOOR
93464 | FSA_F01-CHWR-125-DN020-I16C00_R0 | 0 | true | 12.92 | FSA_F01-CHWR-125-DN020-I16C00_R0 |  | 1129 | FSA South Corridor | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-04 | 2025-03-11 |  | 2025-03-12 | 2025-03-19 | Office 26/05/2025 | 2025-03-28 |  | 2025-03-21 | 2025-05-16 | 2025-05-16 | 2025-06-12 | 2025-06-12 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-200 | System CHW and LTHW GROUND FLOOR
93465 | FSA_F01-CHWR-126-DN020-I16C00_R0 | 0 | true | 6.07 | FSA_F01-CHWR-126-DN020-I16C00_R0 |  | 1129 | FSA South | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-05 | 2025-03-11 |  | 2025-03-12 | 2025-03-19 | Office 11/04/2025 | 2025-03-28 |  | 2025-03-21 | 2025-04-08 | 2025-04-08 | 2025-04-11 | 2025-04-11 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-301 | System CHW and LTHW GROUND FLOOR
93466 | FSA_F01-CHWR-127-DN020-I16C00_R0 | 0 | true | 10.42 | FSA_F01-CHWR-127-DN020-I16C00_R0 |  | 1129 | FSA South | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-05 | 2025-03-11 |  | 2025-03-12 | 2025-03-19 | Office 11/04/2025 | 2025-03-28 |  | 2025-03-21 | 2025-04-08 | 2025-04-08 | 2025-04-11 | 2025-04-11 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-301
93467 | FSA_F01-CHWR-128-DN020-I16C00_R0 | 0 | true | 5.79 | FSA_F01-CHWR-128-DN020-I16C00_R0 |  | 1129 | FSA South | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-05 | 2025-03-11 |  | 2025-03-12 | 2025-03-19 | Office 14.04.2025 | 2025-03-28 |  | 2025-03-21 | 2025-04-11 | 2025-04-12 | 2025-04-14 | 2025-04-14 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-300 | System CHW and LTHW GROUND FLOOR
93468 | FSA_F01-CHWR-129-DN020-I16C00_R0 | 0 | true | 4.33 | FSA_F01-CHWR-129-DN020-I16C00_R0 |  | 1129 | FSA South | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-05 | 2025-03-11 |  | 2025-03-12 | 2025-03-21 | Office 24/04/2025 | 2025-03-28 |  | 2025-03-27 | 2025-04-18 | 2025-04-18 | 2025-06-18 | 2025-06-18 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-200 | System CHW and LTHW GROUND FLOOR
93469 | FSA_F01-CHWR-141-DN025-I16C00_R0 | 0 | true | 13.45 | FSA_F01-CHWR-141-DN025-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-05 | 2025-03-11 |  | 2025-03-21 | 2025-04-03 | Office 24/04/2025 | 2025-04-09 |  | 2025-03-31 | 2025-04-17 | 2025-04-24 |  | 2025-05-13 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-214 | System CHW and LTHW GROUND FLOOR
93470 | FSA_F01-CHWR-142-DN020-I16C00_R0 | 0 | true | 3.07 | FSA_F01-CHWR-142-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-02-21 | 2025-02-24 |  | 2025-02-28 | 2025-03-07 | Office 24/04/2025 | 2025-03-28 |  | 2025-03-10 | 2025-04-24 | 2025-04-24 | 2025-04-29 | 2025-04-29 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-214 | System CHW and LTHW GROUND FLOOR
93471 | FSA_F01-CHWR-143-DN020-I16C00_R0 | 0 | true | 2.03 | FSA_F01-CHWR-143-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-05 | 2025-03-11 |  | 2025-03-13 | 2025-03-19 | Office 24/04/2025 | 2025-03-28 |  | 2025-03-21 | 2025-04-23 | 2025-04-23 | 2025-04-29 | 2025-04-29 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-214 | System CHW and LTHW GROUND FLOOR
93472 | FSA_F01-CHWR-144-DN020-I16C00_R0 | 0 | true | 6.57 | FSA_F01-CHWR-144-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-05 | 2025-03-11 |  | 2025-03-13 | 2025-03-19 | Office 24/04/2025 | 2025-03-28 |  | 2025-03-21 | 2025-04-18 | 2025-04-18 | 2025-04-30 | 2025-04-30 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-214 | System CHW and LTHW GROUND FLOOR
93473 | FSA_F01-CHWR-145-DN020-I16C00_R0 | 0 | true | 1.89 | FSA_F01-CHWR-145-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-02-21 | 2025-02-24 |  | 2025-02-28 | 2025-03-07 | Office 22/05/2025 | 2025-03-28 |  | 2025-03-10 | 2025-05-21 | 2025-05-21 | 2025-06-24 | 2025-06-24 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-200 | System CHW and LTHW GROUND FLOOR
93474 | FSA_F01-CHWR-146-DN020-I16C00_R0 | 0 | true | 6.86 | FSA_F01-CHWR-146-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-02-21 | 2025-02-24 |  | 2025-02-28 | 2025-03-07 | Office 28.04.2025 | 2025-03-28 |  | 2025-03-10 | 2025-04-26 | 2025-04-28 | 2025-05-13 | 2025-05-13 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-215 | System CHW and LTHW GROUND FLOOR
93475 | FSA_F01-CHWR-148-DN025-I16C00_R0 | 0 | true | 13.92 | FSA_F01-CHWR-148-DN025-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-02-21 | 2025-02-24 |  | 2025-02-28 | 2025-03-07 | Office 30.05.2025 | 2025-03-28 |  | 2025-03-10 | 2025-05-26 | 2025-05-26 | 2025-05-26 | 2025-05-27 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-200 | System CHW and LTHW GROUND FLOOR
93476 | FSA_F01-CHWR-149-DN020-I16C00_R0 | 0 | true | 1.04 | FSA_F01-CHWR-149-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-02-21 | 2025-02-24 |  | 2025-02-28 | 2025-03-06 | Office 30.05.2025 | 2025-03-28 |  | 2025-03-10 | 2025-05-27 | 2025-05-27 | 2025-06-17 | 2025-06-17 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-200 | System CHW and LTHW GROUND FLOOR
93477 | FSA_F01-CHWR-150-DN020-I16C00_R0 | 0 | true | 6.6 | FSA_F01-CHWR-150-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-02-21 | 2025-02-24 |  | 2025-02-28 | 2025-03-07 | Office 30.05.2025 | 2025-03-28 |  | 2025-03-27 | 2025-05-30 | 2025-05-30 | 2025-06-16 | 2025-06-16 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-238 | System CHW and LTHW GROUND FLOOR
93478 | FSA_F01-CHWR-155-DN025-I16C00_R0 | 0 | true | 5.81 | FSA_F01-CHWR-155-DN025-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-02-24 | 2025-02-24 |  | 2025-02-28 | 2025-03-06 | Office 10/06/2025 | 2025-03-28 |  | 2025-03-10 | 2025-06-05 | 2025-06-09 | 2025-06-09 | 2025-06-09 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-238 | System CHW and LTHW GROUND FLOOR
93479 | FSA_F01-CHWR-156-DN015-I16C00_R0 | 0 | true | 1.96 | FSA_F01-CHWR-156-DN015-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-02-24 | 2025-02-24 |  | 2025-02-28 | 2025-03-13 | Office 10/06/2025 | 2025-03-28 |  | 2025-03-14 | 2025-06-10 | 2025-06-10 | 2025-06-13 | 2025-06-13 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-239 | System CHW and LTHW GROUND FLOOR
93480 | FSA_F01-CHWR-161-DN020-I16C00_R0 | 0 | true | 8.31 | FSA_F01-CHWR-161-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-02-24 | 2025-02-24 |  | 2025-02-28 | 2025-03-07 | Office 14.05.2025 | 2025-03-28 |  | 2025-03-10 | 2025-05-12 | 2025-05-14 | 2025-05-16 | 2025-05-16 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-236 | System CHW and LTHW GROUND FLOOR
93481 | FSA_F01-CHWR-162-DN040-I16C00_R0 | 0 | true | 31.49 | FSA_F01-CHWR-162-DN040-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-02-25 | 2025-02-24 |  | 2025-02-28 | 2025-03-10 | Office 18.04.2025 | 2025-03-28 |  | 2025-03-27 | 2025-04-14 | 2025-04-14 | 2025-04-17 | 2025-05-13 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-221 | System Loading Dock 01
93482 | FSA_F01-CHWR-168-DN025-I16C00_R0 | 0 | true | 11.85 | FSA_F01-CHWR-168-DN025-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-02-24 | 2025-02-24 |  | 2025-02-28 | 2025-03-07 | Office 28/04/2025 | 2025-03-28 |  | 2025-03-10 | 2025-04-23 | 2025-04-23 | 2025-04-23 | 2025-04-23 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-221 | System Loading Dock 01
93483 | FSA_F01-CHWR-173-DN015-I16C00_R0 | 0 | true | 4.06 | FSA_F01-CHWR-173-DN015-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-02-24 | 2025-02-24 |  | 2025-02-28 | 2025-03-07 | Office 26/05/2025 | 2025-03-28 |  | 2025-03-10 | 2025-05-21 | 2025-05-21 | 2025-07-21 | 2025-07-21 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-231 | System Loading Dock 01
93484 | FSA_F01-CHWR-174-DN032-I16C00_R0 | 0 | true | 26.16 | FSA_F01-CHWR-174-DN032-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-02-24 | 2025-02-24 |  | 2025-02-28 | 2025-04-02 | Office 17/06/2025 | 2025-04-09 |  | 2025-03-31 | 2025-06-10 | 2025-06-11 | 2025-06-16 | 2025-06-16 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-220 | System CHW and LTHW GROUND FLOOR
93485 | FSA_F01-CHWR-180-DN020-I16C00_R0 | 0 | true | 8.88 | FSA_F01-CHWR-180-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-02-24 | 2025-02-24 |  | 2025-02-28 | 2025-03-31 | Office 20/06/2025 | 2025-04-09 |  | 2025-03-31 | 2025-06-19 | 2025-06-20 | 2025-06-23 | 2025-06-23 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-227 | System CHW and LTHW GROUND FLOOR
93486 | FSA_F01-CHWS-100-DN032-I16C00_R0 | 0 | true | 14.94 | FSA_F01-CHWS-100-DN032-I16C00_R0 |  | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-05 | 2025-03-11 |  | 2025-03-21 | 2025-04-02 | Office 24/05/2025 | 2025-04-09 |  | 2025-03-31 | 2025-05-08 | 2025-05-09 | 2025-05-13 | 2025-05-13 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System CHW and LTHW GROUND FLOOR
93487 | FSA_F01-CHWS-101-DN020-I16C00_R0 | 0 | true | 4.06 | FSA_F01-CHWS-101-DN020-I16C00_R0 |  | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-05 | 2025-03-11 |  | 2025-03-13 | 2025-03-21 | Office 24/05/2025 | 2025-03-28 |  | 2025-03-27 | 2025-05-14 | 2025-05-14 | 2025-05-28 | 2025-05-28 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System CHW and LTHW GROUND FLOOR
93488 | FSA_F01-CHWS-102-DN020-I16C00_R0 | 0 | true | 1.82 | FSA_F01-CHWS-102-DN020-I16C00_R0 |  | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-05 | 2025-03-11 |  | 2025-03-13 | 2025-03-21 | Office 26/05/2025 | 2025-03-28 |  | 2025-03-27 | 2025-05-16 | 2025-05-16 | 2025-05-27 | 2025-05-27 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System CHW and LTHW GROUND FLOOR
93489 | FSA_F01-CHWS-103-DN020-I16C00_R0 | 0 | true | 2.65 | FSA_F01-CHWS-103-DN020-I16C00_R0 |  | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-05 | 2025-03-11 |  | 2025-03-13 | 2025-03-21 | Office 24/05/2025 | 2025-03-28 |  | 2025-03-27 | 2025-05-19 | 2025-05-19 | 2025-05-26 | 2025-05-26 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System CHW and LTHW GROUND FLOOR
93490 | FSA_F01-CHWS-104-DN020-I16C00_R0 | 0 | true | 3.63 | FSA_F01-CHWS-104-DN020-I16C00_R0 |  | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-05 | 2025-03-11 |  | 2025-03-13 | 2025-03-19 | Office 27/05/2025 | 2025-03-28 |  | 2025-03-21 | 2025-05-20 | 2025-05-20 | 2025-05-29 | 2025-05-29 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System CHW and LTHW GROUND FLOOR
93491 | FSA_F01-CHWS-105-DN020-I16C00_R0 | 0 | true | 1.29 | FSA_F01-CHWS-105-DN020-I16C00_R0 |  | 1129 | FSA Corridor | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-17 | 2025-03-13 |  | 2025-03-18 | 2025-03-20 | Office 26/05/2025 | 2025-03-28 |  | 2025-03-21 | 2025-05-20 | 2025-05-20 | 2025-06-19 | 2025-06-19 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-200 | System CHW and LTHW GROUND FLOOR
93492 | FSA_F01-CHWS-106-DN050-I16C00_R0 | 0 | true | 31.83 | FSA_F01-CHWS-106-DN050-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-17 | 2025-03-13 |  | 2025-03-18 | 2025-04-03 | Office 26/04/2025 | 2025-04-09 |  | 2025-04-04 | 2025-04-17 | 2025-04-26 | 2025-04-26 | 2025-04-26 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-200, 1-125 | System CHW and LTHW GROUND FLOOR
93493 | FSA_F01-CHWS-107-DN040-I16C00_R0 | 0 | true | 1.82 | FSA_F01-CHWS-107-DN040-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-17 | 2025-03-13 |  | 2025-03-18 | 2025-03-31 | Office 09.06.2025 | 2025-04-09 |  | 2025-03-31 | 2025-06-06 | 2025-06-06 | 2025-06-06 | 2025-06-06 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-131 | System CHW and LTHW GROUND FLOOR
93494 | FSA_F01-CHWS-108-DN020-I16C00_R0 | 0 | true | 12.64 | FSA_F01-CHWS-108-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-10 | 2025-03-11 |  | 2025-03-13 | 2025-03-19 | Office 20/05/2025 | 2025-03-28 |  | 2025-03-21 | 2025-05-16 | 2025-05-16 | 2025-05-26 | 2025-05-26 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-201 | System CHW and LTHW GROUND FLOOR
93495 | FSA_F01-CHWS-109-DN020-I16C00_R0 | 0 | true | 8.99 | FSA_F01-CHWS-109-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-02-24 | 2025-02-24 |  | 2025-02-28 | 2025-03-11 | Office 15.05.2025 | 2025-03-28 |  | 2025-03-12 | 2025-05-09 | 2025-05-09 | 2025-05-20 | 2025-05-20 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-236 | System CHW and LTHW GROUND FLOOR
93496 | FSA_F01-CHWS-110-DN020-I16C00_R0 | 0 | true | 7.17 | FSA_F01-CHWS-110-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-10 | 2025-03-11 |  | 2025-03-13 | 2025-03-19 | Office 15.05.2025 | 2025-03-28 |  | 2025-03-21 | 2025-05-14 | 2025-05-14 | 2025-06-11 | 2025-06-11 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-200 | System CHW and LTHW GROUND FLOOR
93497 | FSA_F01-CHWS-111-DN015-I16C00_R0 | 0 | true | 4.06 | FSA_F01-CHWS-111-DN015-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-10 | 2025-02-24 |  | 2025-02-28 | 2025-03-28 | Office 21/05/2025 | 2025-04-09 |  | 2025-03-31 | 2025-05-19 | 2025-05-19 | 2025-05-23 | 2025-05-23 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-214 | System CHW and LTHW GROUND FLOOR
93498 | FSA_F01-CHWS-112-DN015-I16C00_R0 | 0 | true | 4.03 | FSA_F01-CHWS-112-DN015-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-10 | 2025-03-11 |  | 2025-03-13 | 2025-03-21 | Office 21/05/2025 | 2025-03-28 |  | 2025-03-27 | 2025-05-19 | 2025-05-19 | 2025-05-28 | 2025-05-28 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-214 | System CHW and LTHW GROUND FLOOR
93499 | FSA_F01-CHWS-114-DN020-I16C00_R0 | 0 | true | 3.77 | FSA_F01-CHWS-114-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-02-24 | 2025-02-24 |  | 2025-02-28 | 2025-03-19 | Office 29.05.2025 | 2025-03-28 |  | 2025-03-21 | 2025-05-12 | 2025-05-12 | 2025-05-27 | 2025-05-27 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-215 | System CHW and LTHW GROUND FLOOR
93500 | FSA_F01-CHWS-117-DN025-I16C00_R0 | 0 | true | 2.35 | FSA_F01-CHWS-117-DN025-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-04 | 2025-03-11 |  | 2025-03-13 | 2025-03-28 | Office 20/05/2025 | 2025-04-09 |  | 2025-03-31 | 2025-05-16 | 2025-05-16 | 2025-06-17 | 2025-06-17 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-240 | System CHW and LTHW GROUND FLOOR
93501 | FSA_F01-CHWS-118-DN032-I16C00_R0 | 0 | true | 7.86 | FSA_F01-CHWS-118-DN032-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-02-24 | 2025-02-24 |  | 2025-02-28 | 2025-04-03 | Office 30/04/2025 | 2025-04-09 |  | 2025-03-31 | 2025-04-29 | 2025-04-29 | 2025-04-30 | 2025-04-30 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-126 | System CHW and LTHW GROUND FLOOR
93502 | FSA_F01-CHWS-119-DN020-I16C00_R0 | 0 | true | 1.5 | FSA_F01-CHWS-119-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-02-24 | 2025-02-24 |  | 2025-02-28 | 2025-03-14 | Office 30/04/2025 | 2025-03-28 |  | 2025-03-14 | 2025-04-29 | 2025-04-29 | 2025-05-12 | 2025-05-12 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-125 | System CHW and LTHW GROUND FLOOR
93503 | FSA_F01-CHWS-120-DN020-I16C00_R0 | 0 | true | 4.1 | FSA_F01-CHWS-120-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-02-24 | 2025-02-24 |  | 2025-02-28 | 2025-03-26 | Office 30/04/2025 | 2025-03-28 |  | 2025-03-27 | 2025-04-29 | 2025-04-29 | 2025-05-01 | 2025-05-01 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-126 | System CHW and LTHW GROUND FLOOR
93504 | FSA_F01-CHWS-121-DN020-I16C00_R0 | 0 | true | 2.5 | FSA_F01-CHWS-121-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-03 | 2025-03-11 |  | 2025-03-13 | 2025-03-19 | Office 13/05/2025 | 2025-03-28 |  | 2025-03-21 | 2025-05-12 | 2025-05-12 | 2025-06-09 | 2025-06-09 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-235 | System CHW and LTHW GROUND FLOOR
93505 | FSA_F01-CHWS-122-DN020-I16C00_R0 | 0 | true | 7.26 | FSA_F01-CHWS-122-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-03 | 2025-03-11 |  | 2025-03-13 | 2025-03-20 | Office 13/05/2025 | 2025-03-28 |  | 2025-03-21 | 2025-05-12 | 2025-05-12 | 2025-06-06 | 2025-06-06 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-235 | System CHW and LTHW GROUND FLOOR
93506 | FSA_F01-CHWS-123-DN020-I16C00_R0 | 0 | true | 1.86 | FSA_F01-CHWS-123-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-02-24 | 2025-02-24 |  | 2025-02-28 | 2025-03-19 | Office 01.05.2025 | 2025-03-28 |  | 2025-03-21 | 2025-05-01 | 2025-05-01 | 2025-05-14 | 2025-05-14 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-124 | System CHW and LTHW GROUND FLOOR
93507 | FSA_F01-CHWS-124-DN020-I16C00_R0 | 0 | true | 4.73 | FSA_F01-CHWS-124-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-02-24 | 2025-02-24 |  | 2025-02-28 | 2025-03-10 | Office 01.05.2025 | 2025-03-28 |  | 2025-03-27 | 2025-05-01 | 2025-05-01 | 2025-05-14 | 2025-05-14 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-124 | System CHW and LTHW GROUND FLOOR
93508 | FSA_F01-CHWS-125-DN020-I16C00_R0 | 0 | true | 13.04 | FSA_F01-CHWS-125-DN020-I16C00_R0 |  | 1129 | FSA South Corridor | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-05 | 2025-03-11 |  | 2025-03-13 | 2025-03-19 | Office 26/05/2025 | 2025-03-28 |  | 2025-03-21 | 2025-05-16 | 2025-05-16 | 2025-06-12 | 2025-06-12 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-200 | System CHW and LTHW GROUND FLOOR
93509 | FSA_F01-CHWS-126-DN020-I16C00_R0 | 0 | true | 5.75 | FSA_F01-CHWS-126-DN020-I16C00_R0 |  | 1129 | FSA South | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-06 | 2025-03-11 |  | 2025-03-13 | 2025-03-19 | Office 11/04/2025 | 2025-03-28 |  | 2025-03-21 | 2025-04-08 | 2025-04-08 | 2025-04-11 | 2025-04-11 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-301 | System CHW and LTHW GROUND FLOOR
93510 | FSA_F01-CHWS-127-DN020-I16C00_R0 | 0 | true | 10.19 | FSA_F01-CHWS-127-DN020-I16C00_R0 |  | 1129 | FSA South | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-06 | 2025-03-11 |  | 2025-03-13 | 2025-03-19 | Office 11/04/2025 | 2025-03-28 |  | 2025-03-21 | 2025-04-08 | 2025-04-08 | 2025-04-11 | 2025-04-11 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-301 | System CHW and LTHW GROUND FLOOR
93511 | FSA_F01-CHWS-128-DN020-I16C00_R0 | 0 | true | 5.87 | FSA_F01-CHWS-128-DN020-I16C00_R0 |  | 1129 | FSA South | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-06 | 2025-03-11 |  | 2025-03-13 | 2025-03-19 | Office 14.04.2025 | 2025-03-28 |  | 2025-03-21 | 2025-04-11 | 2025-04-12 | 2025-04-14 | 2025-04-14 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-300 | System CHW and LTHW GROUND FLOOR
93512 | FSA_F01-CHWS-129-DN020-I16C00_R0 | 0 | true | 4.61 | FSA_F01-CHWS-129-DN020-I16C00_R0 |  | 1129 | FSA South | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-06 | 2025-03-11 |  | 2025-03-13 | 2025-03-19 | Office 24/04/2025 | 2025-03-28 |  | 2025-03-21 | 2025-04-18 | 2025-04-18 | 2025-06-18 | 2025-06-18 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-200 | System CHW and LTHW GROUND FLOOR
93513 | FSA_F01-CHWS-141-DN025-I16C00_R0 | 0 | true | 12.86 | FSA_F01-CHWS-141-DN025-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-06 | 2025-03-11 |  | 2025-03-13 | 2025-03-28 | Office 24/04/2025 | 2025-04-09 |  | 2025-03-31 | 2025-04-17 | 2025-04-24 |  | 2025-05-13 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-214 | System CHW and LTHW GROUND FLOOR
93514 | FSA_F01-CHWS-142-DN020-I16C00_R0 | 0 | true | 2.81 | FSA_F01-CHWS-142-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-02-24 | 2025-02-24 |  | 2025-02-28 | 2025-03-19 | Office 24/04/2025 | 2025-04-09 |  | 2025-03-21 | 2025-04-24 | 2025-04-24 | 2025-04-29 | 2025-04-29 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-214 | System CHW and LTHW GROUND FLOOR
93515 | FSA_F01-CHWS-143-DN020-I16C00_R0 | 0 | true | 2.24 | FSA_F01-CHWS-143-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-06 | 2025-03-11 |  | 2025-03-13 | 2025-03-21 | Office 24/04/2025 | 2025-03-28 |  | 2025-03-27 | 2025-04-23 | 2025-04-23 | 2025-04-29 | 2025-04-29 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-214 | System CHW and LTHW GROUND FLOOR
93516 | FSA_F01-CHWS-144-DN020-I16C00_R0 | 0 | true | 6.76 | FSA_F01-CHWS-144-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-06 | 2025-03-11 |  | 2025-03-13 | 2025-03-19 | Office 24/04/2025 | 2025-03-28 |  | 2025-03-21 | 2025-04-18 | 2025-04-18 | 2025-04-30 | 2025-04-30 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-214 | System CHW and LTHW GROUND FLOOR
93517 | FSA_F01-CHWS-145-DN020-I16C00_R0 | 0 | true | 1.36 | FSA_F01-CHWS-145-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-02-24 | 2025-02-24 |  | 2025-02-28 | 2025-03-19 | Office 22/05/2025 | 2025-03-28 |  | 2025-03-21 | 2025-05-21 | 2025-05-21 | 2025-06-24 | 2025-06-24 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-200 | System CHW and LTHW GROUND FLOOR
93518 | FSA_F01-CHWS-146-DN020-I16C00_R0 | 0 | true | 6.34 | FSA_F01-CHWS-146-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-02-24 | 2025-02-24 |  | 2025-02-28 | 2025-03-19 | Office 28.04.2025 | 2025-04-09 |  | 2025-03-21 | 2025-04-26 | 2025-04-28 | 2025-05-13 | 2025-05-13 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-215 | System CHW and LTHW GROUND FLOOR
93519 | FSA_F01-CHWS-148-DN025-I16C00_R0 | 0 | true | 14.79 | FSA_F01-CHWS-148-DN025-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-02-24 | 2025-02-24 |  | 2025-02-28 | 2025-03-10 | Office 30.05.2025 | 2025-03-28 |  | 2025-03-27 | 2025-05-24 | 2025-05-26 | 2025-05-26 | 2025-05-27 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-200 | System CHW and LTHW GROUND FLOOR
93520 | FSA_F01-CHWS-149-DN020-I16C00_R0 | 0 | true | 1.16 | FSA_F01-CHWS-149-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-02-24 | 2025-02-24 |  | 2025-02-28 | 2025-03-19 | Office 30.05.2025 | 2025-03-28 |  | 2025-03-21 | 2025-05-27 | 2025-05-27 | 2025-06-17 | 2025-06-17 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-200 | System CHW and LTHW GROUND FLOOR
93521 | FSA_F01-CHWS-150-DN020-I16C00_R0 | 0 | true | 6.89 | FSA_F01-CHWS-150-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-02-24 | 2025-02-24 |  | 2025-02-28 | 2025-03-10 | Office 30.05.2025 | 2025-03-28 |  | 2025-03-27 | 2025-05-30 | 2025-05-30 | 2025-06-16 | 2025-06-16 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-238 | System CHW and LTHW GROUND FLOOR
93522 | FSA_F01-CHWS-155-DN025-I16C00_R0 | 0 | true | 6.13 | FSA_F01-CHWS-155-DN025-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-02-24 | 2025-02-24 |  | 2025-02-28 | 2025-03-10 | Office 10/06/2025 | 2025-03-28 |  | 2025-03-27 | 2025-06-05 | 2025-06-09 | 2025-06-09 | 2025-06-09 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-238 | System CHW and LTHW GROUND FLOOR
93523 | FSA_F01-CHWS-156-DN015-I16C00_R0 | 0 | true | 1.99 | FSA_F01-CHWS-156-DN015-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-02-24 | 2025-02-24 |  | 2025-02-28 | 2025-03-13 | Office 10/06/2025 | 2025-03-28 |  | 2025-03-14 | 2025-06-10 | 2025-06-10 | 2025-06-13 | 2025-06-13 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-239 | System CHW and LTHW GROUND FLOOR
93524 | FSA_F01-CHWS-161-DN020-I16C00_R0 | 0 | true | 9.14 | FSA_F01-CHWS-161-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-02-24 | 2025-02-24 |  | 2025-02-28 | 2025-03-10 | Office 14.05.2025 | 2025-03-28 |  | 2025-03-27 | 2025-05-12 | 2025-05-14 | 2025-05-16 | 2025-05-16 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-236 | System CHW and LTHW GROUND FLOOR
93525 | FSA_F01-CHWS-162-DN040-I16C00_R0 | 0 | true | 31.99 | FSA_F01-CHWS-162-DN040-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-02-24 | 2025-02-24 |  | 2025-02-28 | 2025-03-11 | Office 18.04.2025 | 2025-03-28 |  | 2025-03-12 | 2025-04-14 | 2025-04-14 | 2025-04-17 | 2025-05-13 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-221 | System Loading Dock 01
93526 | FSA_F01-CHWS-168-DN025-I16C00_R0 | 0 | true | 11.95 | FSA_F01-CHWS-168-DN025-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-02-24 | 2025-02-24 |  | 2025-02-28 | 2025-04-02 | Office 28/04/2025 | 2025-04-09 |  | 2025-03-31 | 2025-04-23 | 2025-04-23 | 2025-04-23 | 2025-04-23 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-221 | System Loading Dock 01
93527 | FSA_F01-CHWS-173-DN015-I16C00_R0 | 0 | true | 3.77 | FSA_F01-CHWS-173-DN015-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-02-24 | 2025-02-24 |  | 2025-02-28 | 2025-03-14 | Office 26/05/2025 | 2025-03-28 |  | 2025-03-14 | 2025-05-21 | 2025-05-21 | 2025-07-21 | 2025-07-21 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-231 | System Loading Dock 01
93528 | FSA_F01-CHWS-174-DN032-I16C00_R0 | 0 | true | 26.7 | FSA_F01-CHWS-174-DN032-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-02-24 | 2025-02-24 |  | 2025-02-28 | 2025-04-02 | Office 17/06/2025 | 2025-04-09 |  | 2025-03-31 | 2025-06-10 | 2025-06-11 | 2025-06-12 | 2025-06-12 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-220 | System CHW and LTHW GROUND FLOOR
93529 | FSA_F01-CHWS-180-DN020-I16C00_R0 | 0 | true | 8.89 | FSA_F01-CHWS-180-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-02-24 | 2025-02-24 |  | 2025-02-28 | 2025-03-13 | Office 20/06/2025 | 2025-03-28 |  | 2025-03-14 | 2025-06-19 | 2025-06-20 | 2025-06-23 | 2025-06-23 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-227 | System CHW and LTHW GROUND FLOOR
93530 | FSA_F01-LTHWR-001-DN065-I16C00_R0 | 0 | true | 1.98 | FSA_F01-LTHWR-001-DN065-I16C00_R0 |  | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-14 | 2025-03-13 |  | 2025-03-17 | 2025-03-25 | Office 20/05/2025 |  |  | 2025-03-27 | 2025-04-29 | 2025-05-02 | 2025-05-13 | 2025-05-13 | 1360 | 193 | Working ISO delivered 14.04.25 - Spools to be checked |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System CHW and LTHW GROUND FLOOR
93531 | FSA_F01-LTHWR-002-DN065-I16C00_R0 | 0 | true | 2.14 | FSA_F01-LTHWR-002-DN065-I16C00_R0 |  | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-14 | 2025-03-13 |  | 2025-03-17 | 2025-03-25 | Office 20/05/2025 |  |  | 2025-03-27 | 2025-04-29 | 2025-04-30 | 2025-05-13 | 2025-05-13 | 1360 | 193 | Working ISO delivered 14.04.25 - Spools to be checked |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System CHW and LTHW GROUND FLOOR
93532 | FSA_F01-LTHWR-003-DN065-I16C00_R0 | 0 | true | 1.99 | FSA_F01-LTHWR-003-DN065-I16C00_R0 |  | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-14 | 2025-03-11 |  | 2025-03-13 | 2025-03-31 | Office 20/05/2025 | 2025-04-09 |  | 2025-03-31 | 2025-04-30 | 2025-04-30 | 2025-05-13 | 2025-05-20 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System CHW and LTHW GROUND FLOOR
93533 | FSA_F01-LTHWR-004-DN100-I16C00_R0 | 0 | true | 10.59 | FSA_F01-LTHWR-004-DN100-I16C00_R0 |  | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-14 | 2025-03-11 |  | 2025-03-14 | 2025-03-24 | Office 27/05/2025 |  |  | 2025-03-24 | 2025-05-03 | 2025-05-03 | 2025-05-13 | 2025-05-30 | 1360 | 193 | Working ISO delivered 14.04.25 - Spools to be checked |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System CHW and LTHW GROUND FLOOR
93534 | FSA_F01-LTHWR-005-DN065-I16C00_R0 | 0 | true | 2.97 | FSA_F01-LTHWR-005-DN065-I16C00_R0 |  | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-14 | 2025-03-11 |  | 2025-03-17 | 2025-03-25 | Office 27/05/2025 |  |  | 2025-03-27 | 2025-04-30 | 2025-04-30 | 2025-05-13 | 2025-05-30 | 1360 | 193 | Working ISO delivered 14.04.25 - Spools to be checked |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System CHW and LTHW GROUND FLOOR
93535 | FSA_F01-LTHWR-006-DN065-I16C00_R0 | 0 | true | 2.97 | FSA_F01-LTHWR-006-DN065-I16C00_R0 |  | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-14 | 2025-03-11 |  | 2025-03-17 | 2025-03-25 | Office 27/05/2025 |  |  | 2025-03-27 | 2025-04-29 | 2025-04-29 | 2025-05-13 | 2025-05-30 | 1360 | 193 | Working ISO delivered 14.04.25 - Spools to be checked |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System CHW and LTHW GROUND FLOOR
93536 | FSA_F01-LTHWR-007-DN100-I16C00_R0 | 0 | true | 13.52 | FSA_F01-LTHWR-007-DN100-I16C00_R0 |  | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-13 | 2025-03-11 |  | 2025-03-14 | 2025-03-25 | Office 20/05/2025 |  |  | 2025-03-27 | 2025-04-29 | 2025-04-29 | 2025-05-13 | 2025-05-30 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System CHW and LTHW GROUND FLOOR
93537 | FSA_F01-LTHWR-008-DN100-I16C00_1_R1 | 1 | true | 32.08 | FSA_F01-LTHWR-008-DN100-I16C00_1_R1 |  | 1129 | FSA South Corridor | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-02-27 | 2025-03-11 |  | 2025-03-14 | 2025-03-24 | Office 21/05/2025 |  |  | 2025-03-24 | 2025-04-15 | 2025-04-15 | 2025-04-17 | 2025-04-17 | 1360 | 193 | Working ISO delivered 14.04.25 - Spools to be checked |  |  | 194 | SEP | SEP | [5 empty] | 1-200 | System CHW and LTHW GROUND FLOOR
93538 | FSA_F01-LTHWR-010-DN015-I16C00_R0 | 0 | true | 11.77 | FSA_F01-LTHWR-010-DN015-I16C00_R0 |  | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-13 | 2025-03-11 |  | 2025-03-13 | 2025-04-03 | Office 30.05.2025 | 2025-04-09 |  | 2025-03-31 |  | 2025-05-13 | 2025-05-30 | 2025-05-30 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System CHW and LTHW GROUND FLOOR
93539 | FSA_F01-LTHWR-011-DN020-I16C00_R0 | 0 | true | 2.11 | FSA_F01-LTHWR-011-DN020-I16C00_R0 |  | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-13 | 2025-03-11 |  | 2025-03-13 | 2025-03-18 | Office 30.05.2025 | 2025-03-28 |  | 2025-03-21 | 2025-05-30 | 2025-05-30 | 2025-05-30 | 2025-05-30 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System CHW and LTHW GROUND FLOOR
93540 | FSA_F01-LTHWR-100-DN025-I16C00_R0 | 0 | true | 17.12 | FSA_F01-LTHWR-100-DN025-I16C00_R0 |  | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-06 | 2025-03-11 |  | 2025-03-13 | 2025-03-25 | Office 24/05/2025 | 2025-03-28 |  | 2025-03-27 | 2025-05-07 | 2025-05-13 | 2025-05-13 | 2025-05-13 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System CHW and LTHW GROUND FLOOR
93541 | FSA_F01-LTHWR-101-DN020-I16C00_R0 | 0 | true | 2.51 | FSA_F01-LTHWR-101-DN020-I16C00_R0 |  | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-06 | 2025-03-11 |  | 2025-03-13 | 2025-03-18 | Office 24/05/2025 | 2025-04-09 |  | 2025-03-21 | 2025-05-14 | 2025-05-14 | 2025-05-28 | 2025-05-28 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System CHW and LTHW GROUND FLOOR
93542 | FSA_F01-LTHWR-102-DN020-I16C00_R0 | 0 | true | 1.79 | FSA_F01-LTHWR-102-DN020-I16C00_R0 |  | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-06 | 2025-03-11 |  | 2025-03-13 | 2025-03-21 | Office 26/05/2025 | 2025-03-28 |  | 2025-03-27 | 2025-05-16 | 2025-05-16 | 2025-05-27 | 2025-05-27 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System CHW and LTHW GROUND FLOOR
93543 | FSA_F01-LTHWR-103-DN020-I16C00_R0 | 0 | true | 1.72 | FSA_F01-LTHWR-103-DN020-I16C00_R0 |  | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-06 | 2025-03-11 |  | 2025-03-14 | 2025-03-21 | Office 24/05/2025 | 2025-03-28 |  | 2025-03-27 | 2025-05-19 | 2025-05-19 | 2025-05-26 | 2025-05-26 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System CHW and LTHW GROUND FLOOR
93544 | FSA_F01-LTHWR-104-DN020-I16C00_R0 | 0 | true | 2.99 | FSA_F01-LTHWR-104-DN020-I16C00_R0 |  | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-06 | 2025-03-11 |  | 2025-03-14 | 2025-03-19 | Office 27/05/2025 | 2025-03-28 |  | 2025-03-21 | 2025-05-20 | 2025-05-20 | 2025-05-29 | 2025-05-29 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System CHW and LTHW GROUND FLOOR
93545 | FSA_F01-LTHWR-105-DN020-I16C00_R0 | 0 | true | 2.38 | FSA_F01-LTHWR-105-DN020-I16C00_R0 |  | 1129 | FSA Corridor | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-17 | 2025-03-13 |  | 2025-03-18 | 2025-03-20 | Office 26/05/2025 | 2025-03-28 |  | 2025-03-21 | 2025-05-20 | 2025-05-20 | 2025-06-19 | 2025-06-19 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-200 | System CHW and LTHW GROUND FLOOR
93546 | FSA_F01-LTHWR-106-DN050-I16C00_R0 | 0 | true | 32.26 | FSA_F01-LTHWR-106-DN050-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-17 | 2025-03-13 |  | 2025-03-18 | 2025-04-03 | Office 26/04/2025 | 2025-04-09 |  | 2025-04-04 | 2025-04-17 | 2025-04-26 | 2025-04-26 | 2025-04-26 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-200, 1-125 | System CHW and LTHW GROUND FLOOR
93547 | FSA_F01-LTHWR-107-DN040-I16C00_R0 | 0 | true | 1.35 | FSA_F01-LTHWR-107-DN040-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-17 | 2025-03-13 |  | 2025-03-18 | 2025-04-01 | Office 09.06.2025 | 2025-04-09 |  | 2025-03-31 | 2025-06-06 | 2025-06-06 | 2025-06-06 | 2025-06-06 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-131 | System CHW and LTHW GROUND FLOOR
93548 | FSA_F01-LTHWR-108-DN020-I16C00_R0 | 0 | true | 13 | FSA_F01-LTHWR-108-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-17 | 2025-03-11 |  | 2025-03-14 | 2025-03-19 | Office 20/05/2025 | 2025-03-28 |  | 2025-03-21 | 2025-05-16 | 2025-05-16 | 2025-05-26 | 2025-05-26 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-201 | System CHW and LTHW GROUND FLOOR
93549 | FSA_F01-LTHWR-109-DN020-I16C00_R0 | 0 | true | 2.37 | FSA_F01-LTHWR-109-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-02-24 | 2025-02-24 |  | 2025-03-06 | 2025-03-18 | Office 15.05.2025 | 2025-03-28 |  | 2025-03-21 | 2025-05-12 | 2025-05-12 | 2025-05-20 | 2025-05-20 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-236 | System CHW and LTHW GROUND FLOOR
93550 | FSA_F01-LTHWR-110-DN020-I16C00_R0 | 0 | true | 7.77 | FSA_F01-LTHWR-110-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-06 | 2025-03-11 |  | 2025-03-14 | 2025-03-19 | Office 15.05.2025 | 2025-03-28 |  | 2025-03-21 | 2025-05-14 | 2025-05-14 | 2025-06-11 | 2025-06-11 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-200 | System CHW and LTHW GROUND FLOOR
93551 | FSA_F01-LTHWR-111-DN015-I16C00_R0 | 0 | true | 2.9 | FSA_F01-LTHWR-111-DN015-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-02-24 | 2025-02-24 |  | 2025-03-06 | 2025-03-14 | Office 21/05/2025 | 2025-03-28 |  | 2025-03-14 | 2025-05-19 | 2025-05-19 | 2025-05-23 | 2025-05-23 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-214 | System CHW and LTHW GROUND FLOOR
93552 | FSA_F01-LTHWR-112-DN015-I16C00_R0 | 0 | true | 2.88 | FSA_F01-LTHWR-112-DN015-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-10 | 2025-03-11 |  | 2025-03-14 | 2025-03-24 | Office 21/05/2025 | 2025-03-28 |  | 2025-03-24 | 2025-05-19 | 2025-05-19 | 2025-05-28 | 2025-05-28 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-214 | System CHW and LTHW GROUND FLOOR
93553 | FSA_F01-LTHWR-114-DN015-I16C00_R0 | 0 | true | 2.1 | FSA_F01-LTHWR-114-DN015-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-02-24 | 2025-02-24 |  | 2025-03-06 | 2025-03-28 | Office 29.05.2025 | 2025-04-09 |  | 2025-03-31 | 2025-05-12 | 2025-05-12 | 2025-05-27 | 2025-05-27 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-215 | System CHW and LTHW GROUND FLOOR
93554 | FSA_F01-LTHWR-117-DN015-I16C00_R0 | 0 | true | 3.4 | FSA_F01-LTHWR-117-DN015-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-06 | 2025-03-11 |  | 2025-03-14 | 2025-03-28 | Office 20/05/2025 | 2025-04-09 |  | 2025-03-31 | 2025-05-16 | 2025-05-16 | 2025-06-17 | 2025-06-17 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-240 | System CHW and LTHW GROUND FLOOR
93555 | FSA_F01-LTHWR-118-DN020-I16C00_R0 | 0 | true | 7.21 | FSA_F01-LTHWR-118-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-02-24 | 2025-02-24 |  | 2025-03-06 | 2025-03-10 | Office 30/04/2025 | 2025-03-28 |  | 2025-03-27 | 2025-04-29 | 2025-04-29 | 2025-04-30 | 2025-04-30 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-126 | System CHW and LTHW GROUND FLOOR
93556 | FSA_F01-LTHWR-119-DN015-I16C00_R0 | 0 | true | 2.48 | FSA_F01-LTHWR-119-DN015-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-02-24 | 2025-02-24 |  | 2025-03-06 | 2025-03-14 | Office 30/04/2025 | 2025-03-28 |  | 2025-03-14 | 2025-04-29 | 2025-04-29 | 2025-05-12 | 2025-05-12 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-125 | System CHW and LTHW GROUND FLOOR
93557 | FSA_F01-LTHWR-120-DN015-I16C00_R0 | 0 | true | 4.37 | FSA_F01-LTHWR-120-DN015-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-02-24 | 2025-02-24 |  | 2025-03-06 | 2025-03-21 | Office 30/04/2025 | 2025-03-28 |  | 2025-03-27 | 2025-04-29 | 2025-04-29 | 2025-05-01 | 2025-05-01 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-126 | System CHW and LTHW GROUND FLOOR
93558 | FSA_F01-LTHWR-121-DN015-I16C00_R0 | 0 | true | 3.47 | FSA_F01-LTHWR-121-DN015-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-06 | 2025-03-11 |  | 2025-03-14 | 2025-03-20 | Office 13/05/2025 | 2025-03-28 |  | 2025-03-21 | 2025-05-12 | 2025-05-12 | 2025-06-09 | 2025-06-09 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-235 | System CHW and LTHW GROUND FLOOR
93559 | FSA_F01-LTHWR-122-DN015-I16C00_R0 | 0 | true | 2.66 | FSA_F01-LTHWR-122-DN015-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-06 | 2025-03-11 |  | 2025-03-14 | 2025-03-21 | Office 13/05/2025 | 2025-03-28 |  | 2025-03-27 | 2025-05-12 | 2025-05-12 | 2025-06-06 | 2025-06-06 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-235 | System CHW and LTHW GROUND FLOOR
93560 | FSA_F01-LTHWR-123-DN015-I16C00_R0 | 0 | true | 1.47 | FSA_F01-LTHWR-123-DN015-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-02-24 | 2025-02-24 |  | 2025-03-06 | 2025-03-28 | Office 01.05.2025 | 2025-04-09 |  | 2025-03-31 | 2025-05-01 | 2025-05-01 | 2025-05-14 | 2025-05-14 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-124 | System CHW and LTHW GROUND FLOOR
93561 | FSA_F01-LTHWR-124-DN015-I16C00_R0 | 0 | true | 4.46 | FSA_F01-LTHWR-124-DN015-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-02-24 | 2025-02-24 |  | 2025-03-06 | 2025-03-28 | Office 01.05.2025 | 2025-04-09 |  | 2025-03-31 | 2025-05-01 | 2025-05-01 | 2025-05-14 | 2025-05-14 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-124 | System CHW and LTHW GROUND FLOOR
93562 | FSA_F01-LTHWR-125-DN020-I16C00_R0 | 0 | true | 14.21 | FSA_F01-LTHWR-125-DN020-I16C00_R0 |  | 1129 | FSA South Corridor | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-06 | 2025-03-11 |  | 2025-03-14 | 2025-03-19 | Office 26/05/2025 | 2025-03-28 |  | 2025-03-21 | 2025-05-19 | 2025-05-19 | 2025-06-12 | 2025-06-12 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-200 | System CHW and LTHW GROUND FLOOR
93563 | FSA_F01-LTHWR-126-DN020-I16C00_R0 | 0 | true | 6.06 | FSA_F01-LTHWR-126-DN020-I16C00_R0 |  | 1129 | FSA South | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-06 | 2025-03-11 |  | 2025-03-14 | 2025-03-19 | Office 11/04/2025 | 2025-03-28 |  | 2025-03-21 | 2025-04-08 | 2025-04-08 | 2025-04-11 | 2025-04-11 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-301 | System CHW and LTHW GROUND FLOOR
93564 | FSA_F01-LTHWR-127-DN020-I16C00_R0 | 0 | true | 10.39 | FSA_F01-LTHWR-127-DN020-I16C00_R0 |  | 1129 | FSA South | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-06 | 2025-03-11 |  | 2025-03-14 | 2025-03-19 | Office 11/04/2025 | 2025-03-28 |  | 2025-03-21 | 2025-04-10 | 2025-04-10 | 2025-04-11 | 2025-04-11 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-301 | System CHW and LTHW GROUND FLOOR
93565 | FSA_F01-LTHWR-128-DN015-I16C00_R0 | 0 | true | 5.94 | FSA_F01-LTHWR-128-DN015-I16C00_R0 |  | 1129 | FSA South | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-06 | 2025-03-11 |  | 2025-03-14 | 2025-03-26 | Office 14.04.2025 | 2025-03-28 |  | 2025-03-27 | 2025-04-12 | 2025-04-14 | 2025-04-14 | 2025-04-14 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-300 | System CHW and LTHW GROUND FLOOR
93566 | FSA_F01-LTHWR-129-DN020-I16C00_R0 | 0 | true | 3.83 | FSA_F01-LTHWR-129-DN020-I16C00_R0 |  | 1129 | FSA South | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-06 | 2025-03-11 |  | 2025-03-14 | 2025-03-21 | Office 24/04/2025 | 2025-03-28 |  | 2025-03-27 | 2025-04-18 | 2025-04-18 | 2025-06-18 | 2025-06-18 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-200 | System CHW and LTHW GROUND FLOOR
93567 | FSA_F01-LTHWR-141-DN020-I16C00_R0 | 0 | true | 14.28 | FSA_F01-LTHWR-141-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-06 | 2025-03-11 |  | 2025-03-14 | 2025-03-20 | Office 24/04/2025 | 2025-03-28 |  | 2025-03-21 | 2025-04-15 | 2025-04-24 |  | 2025-05-13 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-214 | System CHW and LTHW GROUND FLOOR
93568 | FSA_F01-LTHWR-142-DN015-I16C00_R0 | 0 | true | 3.71 | FSA_F01-LTHWR-142-DN015-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-02-24 | 2025-02-24 |  | 2025-03-06 | 2025-03-18 | Office 24/04/2025 | 2025-03-28 |  | 2025-03-21 | 2025-04-24 | 2025-04-24 | 2025-04-29 | 2025-04-29 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-214 | System CHW and LTHW GROUND FLOOR
93569 | FSA_F01-LTHWR-143-DN015-I16C00_R0 | 0 | true | 1.69 | FSA_F01-LTHWR-143-DN015-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-06 | 2025-03-11 |  | 2025-03-14 | 2025-03-25 | Office 24/04/2025 | 2025-03-28 |  | 2025-03-27 | 2025-04-23 | 2025-04-23 | 2025-04-29 | 2025-04-29 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-214 | System CHW and LTHW GROUND FLOOR
93570 | FSA_F01-LTHWR-144-DN015-I16C00_R0 | 0 | true | 6.22 | FSA_F01-LTHWR-144-DN015-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-06 | 2025-03-11 |  | 2025-03-14 | 2025-03-24 | Office 24/04/2025 | 2025-03-28 |  | 2025-03-24 | 2025-04-18 | 2025-04-18 | 2025-04-30 | 2025-04-30 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-214 | System CHW and LTHW GROUND FLOOR
93571 | FSA_F01-LTHWR-145-DN020-I16C00_R0 | 0 | true | 2.92 | FSA_F01-LTHWR-145-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-02-24 | 2025-02-24 |  | 2025-03-06 | 2025-03-18 | Office 22/05/2025 | 2025-04-09 |  | 2025-03-21 | 2025-05-21 | 2025-05-21 | 2025-06-24 | 2025-06-24 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-200 | System CHW and LTHW GROUND FLOOR
93572 | FSA_F01-LTHWR-146-DN020-I16C00_R0 | 0 | true | 7.59 | FSA_F01-LTHWR-146-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-02-24 | 2025-02-24 |  | 2025-03-06 | 2025-03-11 | Office 28.04.2025 | 2025-03-28 |  | 2025-03-12 | 2025-04-26 | 2025-04-28 | 2025-05-13 | 2025-05-13 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-215 | System CHW and LTHW GROUND FLOOR
93573 | FSA_F01-LTHWR-148-DN032-I16C00_R0 | 0 | true | 13.71 | FSA_F01-LTHWR-148-DN032-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-02-24 | 2025-02-24 |  | 2025-03-06 | 2025-04-02 | Office 30.05.2025 | 2025-04-09 |  | 2025-03-31 | 2025-05-23 | 2025-05-26 | 2025-05-26 | 2025-05-27 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-200 | System CHW and LTHW GROUND FLOOR
93574 | FSA_F01-LTHWR-149-DN020-I16C00_R0 | 0 | true | 1.15 | FSA_F01-LTHWR-149-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-02-24 | 2025-02-24 |  | 2025-03-06 | 2025-03-18 | Office 30.05.2025 | 2025-03-28 |  | 2025-03-21 | 2025-05-27 | 2025-05-27 | 2025-06-17 | 2025-06-17 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-200 | System CHW and LTHW GROUND FLOOR
93575 | FSA_F01-LTHWR-150-DN020-I16C00_R0 | 0 | true | 6.03 | FSA_F01-LTHWR-150-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-02-24 | 2025-02-24 |  | 2025-03-06 | 2025-03-13 | Office 30.05.2025 | 2025-03-28 |  | 2025-03-14 | 2025-05-30 | 2025-05-30 | 2025-06-16 | 2025-06-16 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-238 | System CHW and LTHW GROUND FLOOR
93576 | FSA_F01-LTHWR-155-DN020-I16C00_R0 | 0 | true | 7.08 | FSA_F01-LTHWR-155-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-02-24 | 2025-02-24 |  | 2025-03-06 | 2025-03-13 | Office 10/06/2025 | 2025-03-28 |  | 2025-03-14 | 2025-06-05 | 2025-06-09 | 2025-06-09 | 2025-06-09 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-238 | System CHW and LTHW GROUND FLOOR
93577 | FSA_F01-LTHWR-156-DN020-I16C00_R0 | 0 | true | 1.83 | FSA_F01-LTHWR-156-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-02-24 | 2025-02-24 |  | 2025-03-06 | 2025-03-18 | Office 10/06/2025 | 2025-03-28 |  | 2025-03-21 | 2025-06-10 | 2025-06-10 | 2025-06-13 | 2025-06-13 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-239 | System CHW and LTHW GROUND FLOOR
93578 | FSA_F01-LTHWR-161-DN020-I16C00_R0 | 0 | true | 9.86 | FSA_F01-LTHWR-161-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-02-24 | 2025-02-24 |  | 2025-03-06 | 2025-03-18 | Office 14.05.2025 | 2025-04-09 |  | 2025-03-21 | 2025-05-12 | 2025-05-14 | 2025-05-16 | 2025-05-16 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-236 | System CHW and LTHW GROUND FLOOR
93579 | FSA_F01-LTHWR-173-DN020-I16C00_R0 | 0 | true | 2.09 | FSA_F01-LTHWR-173-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-02-24 | 2025-02-24 |  | 2025-03-06 | 2025-03-18 | Office 26/05/2025 | 2025-03-28 |  | 2025-03-21 | 2025-05-21 | 2025-05-21 | 2025-07-21 | 2025-07-21 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-231 | System Loading Dock 01
93580 | FSA_F01-LTHWR-174-DN032-I16C00_R0 | 0 | true | 25.11 | FSA_F01-LTHWR-174-DN032-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-02-24 | 2025-02-24 |  | 2025-03-06 | 2025-04-02 | Office 17/06/2025 | 2025-04-09 |  | 2025-03-31 | 2025-06-11 | 2025-06-13 | 2025-06-16 | 2025-06-16 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-220 | System CHW and LTHW GROUND FLOOR
93581 | FSA_F01-LTHWR-180-DN015-I16C00_R0 | 0 | true | 9.02 | FSA_F01-LTHWR-180-DN015-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-02-24 | 2025-02-24 |  | 2025-03-06 | 2025-04-02 | Office 20/06/2025 | 2025-04-09 |  | 2025-04-04 | 2025-06-19 | 2025-06-20 | 2025-06-23 | 2025-06-23 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-227 | System CHW and LTHW GROUND FLOOR
93582 | FSA_F01-LTHWR-250-DN015-I16C00_R0 | 0 | false | 12.03 | FSA_F01-LTHWR-250-DN015-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | [13 empty] | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-202
93583 | FSA_F01-LTHWR-252-DN015-I16C00_R0 | 0 | false | 8.05 | FSA_F01-LTHWR-252-DN015-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | [13 empty] | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-011
93584 | FSA_F01-LTHWR-253-DN015-I16C00_R0 | 0 | false | 6.74 | FSA_F01-LTHWR-253-DN015-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | [13 empty] | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-204
93585 | FSA_F01-LTHWR-255-DN015-I16C00_R0 | 0 | true | 14.19 | FSA_F01-LTHWR-255-DN015-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-02-24 | 2025-02-24 |  | 2025-03-06 | 2025-03-28 | Office 27.05.2025 | 2025-04-09 |  | 2025-03-31 | 2025-05-12 | 2025-05-13 | 2025-05-23 | 2025-05-26 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-233 | System CHW and LTHW GROUND FLOOR
93586 | FSA_F01-LTHWR-256-DN015-I16C00_R0 | 0 | true | 10.33 | FSA_F01-LTHWR-256-DN015-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-02-24 | 2025-02-24 |  | 2025-03-06 | 2025-03-25 | Office 09.06.2025 | 2025-03-28 |  | 2025-03-27 | 2025-06-05 | 2025-06-06 | 2025-06-06 | 2025-06-06 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-234 | System Loading Dock 01
93587 | FSA_F01-LTHWR-257-DN015-I16C00_R0 | 0 | true | 13.56 | FSA_F01-LTHWR-257-DN015-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-02-24 | 2025-02-24 |  | 2025-03-07 | 2025-03-26 | Office 10/06/2025 | 2025-03-28 |  | 2025-03-27 | 2025-06-02 | 2025-06-06 | 2025-06-09 | 2025-06-09 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-012 | System Loading Dock 01
93588 | FSA_F01-LTHWS-001-DN100-I16C00_R0 | 0 | true | 9.81 | FSA_F01-LTHWS-001-DN100-I16C00_R0 |  | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-13 | 2025-03-11 |  | 2025-03-13 | 2025-03-25 | Office 26/04/2025 |  |  | 2025-03-27 | 2025-04-24 | 2025-04-25 | 2025-04-25 | 2025-04-26 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System CHW and LTHW GROUND FLOOR
93589 | FSA_F01-LTHWS-002-DN065-I16C00_R0 | 0 | true | 1.38 | FSA_F01-LTHWS-002-DN065-I16C00_R0 |  | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-17 | 2025-03-11 |  | 2025-03-14 | 2025-03-25 | Office 26/04/2025 |  |  | 2025-03-27 | 2025-04-24 | 2025-04-25 | 2025-04-25 | 2025-04-26 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System CHW and LTHW GROUND FLOOR
93590 | FSA_F01-LTHWS-003-DN065-I16C00_R0 | 0 | true | 1.38 | FSA_F01-LTHWS-003-DN065-I16C00_R0 |  | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-13 | 2025-03-11 |  | 2025-03-17 | 2025-03-25 | Office 26/04/2025 |  |  | 2025-03-27 | 2025-04-25 | 2025-04-25 | 2025-04-26 | 2025-04-26 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System CHW and LTHW GROUND FLOOR
93591 | FSA_F01-LTHWS-004-DN100-I16C00_R0 | 0 | true | 4.16 | FSA_F01-LTHWS-004-DN100-I16C00_R0 |  | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-13 | 2025-03-11 |  | 2025-03-13 | 2025-03-31 | Office 20/05/2025 | 2025-04-09 |  | 2025-03-31 | 2025-04-19 | 2025-04-29 | 2025-05-13 | 2025-05-13 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System CHW and LTHW GROUND FLOOR
93592 | FSA_F01-LTHWS-005-DN100-I16C00_R0 | 0 | true | 2.44 | FSA_F01-LTHWS-005-DN100-I16C00_R0 |  | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-13 | 2025-03-11 |  | 2025-03-13 | 2025-03-31 | Office 20/05/2025 | 2025-04-09 |  | 2025-03-31 | 2025-04-28 | 2025-04-28 | 2025-05-13 | 2025-05-13 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System CHW and LTHW GROUND FLOOR
93593 | FSA_F01-LTHWS-006-DN100-I16C00_R0 | 0 | true | 11.41 | FSA_F01-LTHWS-006-DN100-I16C00_R0 |  | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-11 | 2025-03-11 |  | 2025-03-13 | 2025-03-31 | Office 20/05/2025 | 2025-04-09 |  | 2025-03-31 | 2025-04-29 | 2025-04-30 | 2025-05-13 | 2025-05-20 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System CHW and LTHW GROUND FLOOR
93594 | FSA_F01-LTHWS-007-DN100-I16C00_R0 | 0 | true | 3.5 | FSA_F01-LTHWS-007-DN100-I16C00_R0 |  | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-11 | 2025-03-11 |  | 2025-03-13 | 2025-03-31 | Office 20/05/2025 | 2025-04-09 |  | 2025-03-31 | 2025-04-18 | 2025-04-30 | 2025-05-13 | 2025-05-13 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System CHW and LTHW GROUND FLOOR
93595 | FSA_F01-LTHWS-008-DN100-I16C00_1_R2 | 2 | true | 32.59 | FSA_F01-LTHWS-008-DN100-I16C00_1_R2 |  | 1129 | FSA South Corridor | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-02-27 | 2025-03-11 |  | 2025-03-14 | 2025-03-24 | Dejan Todorovski 14.04.2025 |  |  | 2025-03-24 | 2025-04-16 | 2025-04-17 | 2025-04-17 | 2025-04-17 | 1360 | 193 | Working ISO delivered 14.04.25 - Spools to be checked |  |  | 194 | SEP | SEP | [5 empty] | 1-200 | System CHW and LTHW GROUND FLOOR
93596 | FSA_F01-LTHWS-009-DN065-I16C00_R0 | 0 | true | 1.37 | FSA_F01-LTHWS-009-DN065-I16C00_R0 |  | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-13 | 2025-03-11 |  | 2025-03-17 | 2025-03-25 | Office 20/05/2025 |  |  | 2025-03-27 | 2025-05-05 | 2025-05-06 | 2025-05-13 |  | 1360 | 193 | Working ISO delivered 14.04.25 - Spools to be checked |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System CHW and LTHW GROUND FLOOR
93597 | FSA_F01-LTHWS-010-DN020-I16C00_R0 | 0 | true | 1.09 | FSA_F01-LTHWS-010-DN020-I16C00_R0 |  | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-13 | 2025-03-11 |  | 2025-03-14 | 2025-03-21 | Office 30.05.2025 | 2025-03-28 |  | 2025-03-27 | 2025-05-30 | 2025-05-30 | 2025-05-30 | 2025-05-30 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System CHW and LTHW GROUND FLOOR
93598 | FSA_F01-LTHWS-011-DN032-I16C00_R0 | 0 | true | 1.58 | FSA_F01-LTHWS-011-DN032-I16C00_R0 |  | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-13 | 2025-03-13 |  | 2025-03-18 | 2025-03-27 | Office 08.05.2025 | 2025-03-28 |  | 2025-03-27 | 2025-05-07 | 2025-05-07 | 2025-05-07 | 2025-05-07 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System CHW and LTHW GROUND FLOOR
93599 | FSA_F01-LTHWS-012-DN032-I16C00_R0 | 0 | true | 0.6 | FSA_F01-LTHWS-012-DN032-I16C00_R0 |  | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-13 | 2025-03-13 |  | 2025-03-18 | 2025-03-24 | Office 08.05.2025 | 2025-03-28 |  | 2025-03-24 | 2025-05-07 | 2025-05-07 | 2025-05-07 | 2025-05-07 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System CHW and LTHW GROUND FLOOR
93600 | FSA_F01-LTHWS-013-DN032-I16C00_R0 | 0 | true | 2.89 | FSA_F01-LTHWS-013-DN032-I16C00_R0 |  | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-13 | 2025-03-13 |  | 2025-03-18 | 2025-04-03 | Office 22/05/2025 | 2025-04-09 |  | 2025-03-31 | 2025-05-06 | 2025-05-06 | 2025-05-06 | 2025-05-07 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System CHW and LTHW GROUND FLOOR
93601 | FSA_F01-LTHWS-014-DN020-I16C00_R0 | 0 | true | 1.21 | FSA_F01-LTHWS-014-DN020-I16C00_R0 |  | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-13 | 2025-03-11 |  | 2025-03-14 | 2025-03-25 | Office 08.05.2025 | 2025-03-28 |  | 2025-03-27 | 2025-05-07 | 2025-05-07 | 2025-05-08 | 2025-05-08 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System CHW and LTHW GROUND FLOOR
93602 | FSA_F01-LTHWS-100-DN025-I16C00_R0 | 0 | true | 16.71 | FSA_F01-LTHWS-100-DN025-I16C00_R0 |  | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-06 | 2025-03-11 |  | 2025-03-14 | 2025-04-01 | Office 24/05/2025 | 2025-04-09 |  | 2025-03-31 | 2025-05-08 | 2025-05-08 | 2025-05-13 | 2025-05-13 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System CHW and LTHW GROUND FLOOR
93603 | FSA_F01-LTHWS-101-DN020-I16C00_R0 | 0 | true | 2.82 | FSA_F01-LTHWS-101-DN020-I16C00_R0 |  | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-07 | 2025-03-11 |  | 2025-03-14 | 2025-03-21 | Office 24/05/2025 | 2025-03-28 |  | 2025-03-27 | 2025-05-14 | 2025-05-14 | 2025-05-28 | 2025-05-28 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System CHW and LTHW GROUND FLOOR
93604 | FSA_F01-LTHWS-102-DN020-I16C00_R0 | 0 | true | 1.7 | FSA_F01-LTHWS-102-DN020-I16C00_R0 |  | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-07 | 2025-03-11 |  | 2025-03-14 | 2025-03-21 | Office 26/05/2025 | 2025-03-28 |  | 2025-03-27 | 2025-05-16 | 2025-05-16 | 2025-05-27 | 2025-05-27 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System CHW and LTHW GROUND FLOOR
93605 | FSA_F01-LTHWS-103-DN020-I16C00_R0 | 0 | true | 2.06 | FSA_F01-LTHWS-103-DN020-I16C00_R0 |  | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-07 | 2025-03-11 |  | 2025-03-14 | 2025-03-19 | Office 24/05/2025 | 2025-03-28 |  | 2025-03-21 | 2025-05-19 | 2025-05-19 | 2025-05-26 | 2025-05-26 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System CHW and LTHW GROUND FLOOR
93606 | FSA_F01-LTHWS-104-DN020-I16C00_R0 | 0 | true | 3.02 | FSA_F01-LTHWS-104-DN020-I16C00_R0 |  | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-07 | 2025-03-11 |  | 2025-03-14 | 2025-03-19 | Office 27/05/2025 | 2025-03-28 |  | 2025-03-21 | 2025-05-20 | 2025-05-20 | 2025-05-29 | 2025-05-29 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System CHW and LTHW GROUND FLOOR
93607 | FSA_F01-LTHWS-105-DN020-I16C00_R0 | 0 | true | 2.19 | FSA_F01-LTHWS-105-DN020-I16C00_R0 |  | 1129 | FSA Corridor | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-17 | 2025-03-13 |  | 2025-03-18 | 2025-03-21 | Office 26/05/2025 | 2025-03-28 |  | 2025-03-27 | 2025-05-20 | 2025-05-20 | 2025-06-19 | 2025-06-19 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-200 | System CHW and LTHW GROUND FLOOR
93608 | FSA_F01-LTHWS-106-DN050-I16C00_R0 | 0 | true | 32.42 | FSA_F01-LTHWS-106-DN050-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-17 | 2025-03-13 |  | 2025-03-18 | 2025-04-01 | Office 26/04/25 | 2025-04-09 |  | 2025-03-31 | 2025-04-17 | 2025-04-26 | 2025-04-26 | 2025-04-26 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-200, 1-125 | System CHW and LTHW GROUND FLOOR
93609 | FSA_F01-LTHWS-107-DN040-I16C00_R0 | 0 | true | 1.35 | FSA_F01-LTHWS-107-DN040-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-17 | 2025-03-13 |  | 2025-03-18 | 2025-03-27 | Office 09.06.2025 | 2025-03-28 |  | 2025-03-27 | 2025-06-06 | 2025-06-06 | 2025-06-06 | 2025-06-06 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-131 | System CHW and LTHW GROUND FLOOR
93610 | FSA_F01-LTHWS-108-DN020-I16C00_R0 | 0 | true | 13.04 | FSA_F01-LTHWS-108-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-10 | 2025-03-11 |  | 2025-03-14 | 2025-03-19 | Office 20/05/2025 | 2025-03-28 |  | 2025-03-21 | 2025-05-16 | 2025-05-16 | 2025-05-26 | 2025-05-26 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-201 | System CHW and LTHW GROUND FLOOR
93611 | FSA_F01-LTHWS-109-DN020-I16C00_R0 | 0 | true | 2.27 | FSA_F01-LTHWS-109-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-02-24 | 2025-02-24 |  | 2025-03-07 | 2025-03-19 | Office 15.05.2025 | 2025-03-28 |  | 2025-03-21 | 2025-05-12 | 2025-05-12 | 2025-05-20 | 2025-05-20 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-236 | System CHW and LTHW GROUND FLOOR
93612 | FSA_F01-LTHWS-110-DN020-I16C00_R0 | 0 | true | 7.38 | FSA_F01-LTHWS-110-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-07 | 2025-03-11 |  | 2025-03-14 | 2025-03-20 | Office 15.05.2025 | 2025-03-28 |  | 2025-03-21 | 2025-05-14 | 2025-05-14 | 2025-06-11 | 2025-06-11 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-200 | System CHW and LTHW GROUND FLOOR
93613 | FSA_F01-LTHWS-111-DN015-I16C00_R0 | 0 | true | 2.86 | FSA_F01-LTHWS-111-DN015-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-02-24 | 2025-02-24 |  | 2025-03-07 | 2025-03-14 | Office 21/05/2025 | 2025-03-28 |  | 2025-03-14 | 2025-05-19 | 2025-05-19 | 2025-05-23 | 2025-05-23 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-214 | System CHW and LTHW GROUND FLOOR
93614 | FSA_F01-LTHWS-112-DN015-I16C00_R0 | 0 | true | 2.77 | FSA_F01-LTHWS-112-DN015-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-10 | 2025-03-11 |  | 2025-03-14 | 2025-03-24 | Office 21/05/2025 | 2025-03-28 |  | 2025-03-24 | 2025-05-19 | 2025-05-19 | 2025-05-28 | 2025-05-28 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-214 | System CHW and LTHW GROUND FLOOR
93615 | FSA_F01-LTHWS-114-DN015-I16C00_R0 | 0 | true | 2.65 | FSA_F01-LTHWS-114-DN015-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-02-24 | 2025-02-24 |  | 2025-03-07 | 2025-03-14 | Office 29.05.2025 | 2025-03-28 |  | 2025-03-14 | 2025-05-12 | 2025-05-12 | 2025-05-27 | 2025-05-27 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-215 | System CHW and LTHW GROUND FLOOR
93616 | FSA_F01-LTHWS-117-DN015-I16C00_R0 | 0 | true | 3.11 | FSA_F01-LTHWS-117-DN015-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-10 | 2025-03-11 |  | 2025-03-14 | 2025-03-24 | Office 20/05/2025 | 2025-03-28 |  | 2025-03-24 | 2025-05-16 | 2025-05-16 | 2025-06-17 | 2025-06-17 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-240 | System CHW and LTHW GROUND FLOOR
93617 | FSA_F01-LTHWS-118-DN020-I16C00_R0 | 0 | true | 7.49 | FSA_F01-LTHWS-118-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-02-24 | 2025-02-24 |  | 2025-03-07 | 2025-03-14 | Office 30/04/2025 | 2025-03-28 |  | 2025-03-14 | 2025-04-29 | 2025-04-29 | 2025-04-30 | 2025-04-30 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-126 | System CHW and LTHW GROUND FLOOR
93618 | FSA_F01-LTHWS-119-DN015-I16C00_R0 | 0 | true | 2.19 | FSA_F01-LTHWS-119-DN015-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-02-24 | 2025-02-24 |  | 2025-03-07 | 2025-03-24 | Office 30/04/2025 | 2025-03-28 |  | 2025-03-24 | 2025-04-29 | 2025-04-29 | 2025-05-12 | 2025-05-12 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-125 | System CHW and LTHW GROUND FLOOR
93619 | FSA_F01-LTHWS-120-DN015-I16C00_R0 | 0 | true | 4.27 | FSA_F01-LTHWS-120-DN015-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-02-24 | 2025-02-24 |  | 2025-03-07 | 2025-03-19 | Office 30/04/2025 | 2025-03-28 |  | 2025-03-21 | 2025-04-29 | 2025-04-29 | 2025-05-01 | 2025-05-01 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-126 | System CHW and LTHW GROUND FLOOR
93620 | FSA_F01-LTHWS-121-DN015-I16C00_R0 | 0 | true | 3.16 | FSA_F01-LTHWS-121-DN015-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-10 | 2025-03-11 |  | 2025-03-14 | 2025-03-20 | Office 13/05/2025 | 2025-03-28 |  | 2025-03-21 | 2025-05-12 | 2025-05-12 | 2025-06-09 | 2025-06-09 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-235 | System CHW and LTHW GROUND FLOOR
93621 | FSA_F01-LTHWS-122-DN015-I16C00_R0 | 0 | true | 2.8 | FSA_F01-LTHWS-122-DN015-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-10 | 2025-03-11 |  | 2025-03-14 | 2025-03-19 | Office 13/05/2025 | 2025-03-28 |  | 2025-03-21 | 2025-05-12 | 2025-05-12 | 2025-06-06 | 2025-06-06 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-235 | System CHW and LTHW GROUND FLOOR
93622 | FSA_F01-LTHWS-123-DN015-I16C00_R0 | 0 | true | 1.73 | FSA_F01-LTHWS-123-DN015-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-02-24 | 2025-02-24 |  | 2025-03-07 | 2025-03-24 | Office 01.05.2025 | 2025-03-28 |  | 2025-03-24 | 2025-05-01 | 2025-05-01 | 2025-05-14 | 2025-05-14 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-124 | System CHW and LTHW GROUND FLOOR
93623 | FSA_F01-LTHWS-124-DN015-I16C00_R0 | 0 | true | 4.65 | FSA_F01-LTHWS-124-DN015-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-02-24 | 2025-02-24 |  | 2025-03-07 | 2025-03-19 | Office 01.05.2025 | 2025-03-28 |  | 2025-03-21 | 2025-05-01 | 2025-05-01 | 2025-05-14 | 2025-05-14 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-124 | System CHW and LTHW GROUND FLOOR
93624 | FSA_F01-LTHWS-125-DN020-I16C00_R0 | 0 | true | 13.1 | FSA_F01-LTHWS-125-DN020-I16C00_R0 |  | 1129 | FSA South Corridor | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-10 | 2025-03-11 |  | 2025-03-14 | 2025-03-20 | Office 26/05/2025 | 2025-03-28 |  | 2025-03-21 | 2025-05-16 | 2025-05-19 | 2025-06-12 | 2025-06-12 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-200 | System CHW and LTHW GROUND FLOOR
93625 | FSA_F01-LTHWS-126-DN020-I16C00_R0 | 0 | true | 5.38 | FSA_F01-LTHWS-126-DN020-I16C00_R0 |  | 1129 | FSA South | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-10 | 2025-03-11 |  | 2025-03-14 | 2025-03-19 | Office 11/04/2025 | 2025-03-28 |  | 2025-03-21 | 2025-04-08 | 2025-04-10 | 2025-04-11 | 2025-04-11 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-301 | System CHW and LTHW GROUND FLOOR
93626 | FSA_F01-LTHWS-127-DN020-I16C00_R0 | 0 | true | 9.78 | FSA_F01-LTHWS-127-DN020-I16C00_R0 |  | 1129 | FSA South | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-10 | 2025-03-11 |  | 2025-03-14 | 2025-03-19 | Office 11/04/2025 | 2025-03-28 |  | 2025-03-21 | 2025-04-10 | 2025-04-10 | 2025-04-11 | 2025-04-11 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-301 | System CHW and LTHW GROUND FLOOR
93627 | FSA_F01-LTHWS-128-DN015-I16C00_R0 | 0 | true | 5.42 | FSA_F01-LTHWS-128-DN015-I16C00_R0 |  | 1129 | FSA South | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-10 | 2025-03-11 |  | 2025-03-14 | 2025-03-20 | Office 14.04.2025 | 2025-03-28 |  | 2025-03-21 | 2025-04-12 | 2025-04-14 | 2025-04-14 | 2025-04-14 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-300 | System CHW and LTHW GROUND FLOOR
93628 | FSA_F01-LTHWS-129-DN020-I16C00_R0 | 0 | true | 3.55 | FSA_F01-LTHWS-129-DN020-I16C00_R0 |  | 1129 | FSA South | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-10 | 2025-03-11 |  | 2025-03-14 | 2025-03-21 | Office 24/04/2025 | 2025-03-28 |  | 2025-03-27 | 2025-04-18 | 2025-04-18 | 2025-06-18 | 2025-06-18 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-200 | System CHW and LTHW GROUND FLOOR
93629 | FSA_F01-LTHWS-141-DN020-I16C00_R0 | 0 | true | 14.14 | FSA_F01-LTHWS-141-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-10 | 2025-03-11 |  | 2025-03-14 | 2025-03-21 | Office 24/04/2025 | 2025-03-28 |  | 2025-03-27 | 2025-04-15 | 2025-04-24 |  | 2025-05-13 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-214 | System CHW and LTHW GROUND FLOOR
93630 | FSA_F01-LTHWS-142-DN015-I16C00_R0 | 0 | true | 3.46 | FSA_F01-LTHWS-142-DN015-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-02-24 | 2025-02-24 |  | 2025-03-07 | 2025-03-14 | Office 24/04/2025 | 2025-03-28 |  | 2025-03-14 | 2025-04-24 | 2025-04-24 | 2025-04-29 | 2025-04-29 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-214 | System CHW and LTHW GROUND FLOOR
93631 | FSA_F01-LTHWS-143-DN015-I16C00_R0 | 0 | true | 1.87 | FSA_F01-LTHWS-143-DN015-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-10 | 2025-03-11 |  | 2025-03-14 | 2025-03-24 | Office 24/04/2025 | 2025-03-28 |  | 2025-03-24 | 2025-04-23 | 2025-04-23 | 2025-04-29 | 2025-04-29 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-214 | System CHW and LTHW GROUND FLOOR
93632 | FSA_F01-LTHWS-144-DN015-I16C00_R0 | 0 | true | 6.39 | FSA_F01-LTHWS-144-DN015-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-10 | 2025-03-11 |  | 2025-03-14 | 2025-03-20 | Office 24/04/2025 | 2025-03-28 |  | 2025-03-21 | 2025-04-15 | 2025-04-15 | 2025-04-30 | 2025-04-30 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-214 | System CHW and LTHW GROUND FLOOR
93633 | FSA_F01-LTHWS-145-DN020-I16C00_R0 | 0 | true | 2.71 | FSA_F01-LTHWS-145-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-02-24 | 2025-02-24 |  | 2025-03-07 | 2025-03-19 | Office 22/05/2025 | 2025-03-28 |  | 2025-03-21 | 2025-05-21 | 2025-05-21 | 2025-06-24 | 2025-06-24 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-200 | System CHW and LTHW GROUND FLOOR
93634 | FSA_F01-LTHWS-146-DN020-I16C00_R0 | 0 | true | 7.53 | FSA_F01-LTHWS-146-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-02-24 | 2025-02-24 |  | 2025-03-07 | 2025-03-13 | Office 28.04.2025 | 2025-03-28 |  | 2025-03-14 | 2025-04-26 | 2025-04-28 | 2025-05-13 | 2025-05-13 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-215 | System CHW and LTHW GROUND FLOOR
93635 | FSA_F01-LTHWS-148-DN032-I16C00_R0 | 0 | true | 14.16 | FSA_F01-LTHWS-148-DN032-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-02-24 | 2025-02-24 |  | 2025-03-07 | 2025-04-02 | Office 30.05.2025 | 2025-04-09 |  | 2025-03-31 | 2025-05-23 | 2025-05-26 | 2025-05-26 | 2025-05-27 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-200 | System CHW and LTHW GROUND FLOOR
93636 | FSA_F01-LTHWS-149-DN020-I16C00_R0 | 0 | true | 1.08 | FSA_F01-LTHWS-149-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-02-24 | 2025-02-24 |  | 2025-03-07 | 2025-03-19 | Office 30.05.2025 | 2025-03-28 |  | 2025-03-21 | 2025-05-27 | 2025-05-27 | 2025-06-17 | 2025-06-17 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-200 | System CHW and LTHW GROUND FLOOR
93637 | FSA_F01-LTHWS-150-DN020-I16C00_R0 | 0 | true | 6.3 | FSA_F01-LTHWS-150-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-03 | 2025-02-24 |  | 2025-03-07 | 2025-03-19 | Office 30.05.2025 | 2025-03-28 |  | 2025-03-21 | 2025-05-30 | 2025-05-30 | 2025-06-16 | 2025-06-16 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-238 | System CHW and LTHW GROUND FLOOR
93638 | FSA_F01-LTHWS-155-DN020-I16C00_R0 | 0 | true | 6.98 | FSA_F01-LTHWS-155-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-03 | 2025-02-24 |  | 2025-03-07 | 2025-03-13 | Office 10/06/2025 | 2025-03-28 |  | 2025-03-14 | 2025-06-05 | 2025-06-09 | 2025-06-09 | 2025-06-09 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-238 | System CHW and LTHW GROUND FLOOR
93639 | FSA_F01-LTHWS-156-DN020-I16C00_R0 | 0 | true | 1.85 | FSA_F01-LTHWS-156-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-03 | 2025-02-24 |  | 2025-03-07 | 2025-03-19 | Office 10/06/2025 | 2025-03-28 |  | 2025-03-21 | 2025-06-10 | 2025-06-10 | 2025-06-13 | 2025-06-13 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-239 | System CHW and LTHW GROUND FLOOR
93640 | FSA_F01-LTHWS-161-DN020-I16C00_R0 | 0 | true | 9.97 | FSA_F01-LTHWS-161-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-03 | 2025-02-24 |  | 2025-03-07 | 2025-03-13 | Office 14.05.2025 | 2025-03-28 |  | 2025-03-14 | 2025-05-12 | 2025-05-13 | 2025-05-16 | 2025-05-16 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-236 | System CHW and LTHW GROUND FLOOR
93641 | FSA_F01-LTHWS-173-DN020-I16C00_R0 | 0 | true | 2.48 | FSA_F01-LTHWS-173-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 |  | 2025-02-24 |  | 2025-03-07 | 2025-03-13 | Office 26/05/2025 | 2025-03-28 |  | 2025-03-14 | 2025-05-21 | 2025-05-21 | 2025-07-21 | 2025-07-21 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-231 | System Loading Dock 01
93642 | FSA_F01-LTHWS-174-DN032-I16C00_R0 | 0 | true | 25.64 | FSA_F01-LTHWS-174-DN032-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-03 | 2025-02-24 |  | 2025-03-07 | 2025-04-02 | Office 17/06/2025 | 2025-04-09 |  | 2025-03-31 | 2025-06-11 | 2025-06-12 | 2025-06-16 | 2025-06-16 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-220 | System CHW and LTHW GROUND FLOOR
93643 | FSA_F01-LTHWS-180-DN015-I16C00_R0 | 0 | true | 9.05 | FSA_F01-LTHWS-180-DN015-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-03 | 2025-02-24 |  | 2025-03-07 | 2025-04-03 | Office 20/06/2025 | 2025-04-09 |  | 2025-04-04 | 2025-06-19 | 2025-06-20 | 2025-06-23 | 2025-06-23 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-227 | System CHW and LTHW GROUND FLOOR
93644 | FSA_F01-LTHWS-250-DN015-I16C00_R0 | 0 | false | 11.63 | FSA_F01-LTHWS-250-DN015-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | [13 empty] | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-202
93645 | FSA_F01-LTHWS-252-DN015-I16C00_R0 | 0 | false | 7.74 | FSA_F01-LTHWS-252-DN015-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | [13 empty] | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-011
93646 | FSA_F01-LTHWS-253-DN015-I16C00_R0 | 0 | false | 6.82 | FSA_F01-LTHWS-253-DN015-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | [13 empty] | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-204
93647 | FSA_F01-LTHWS-255-DN015-I16C00_R0 | 0 | true | 13.76 | FSA_F01-LTHWS-255-DN015-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 |  | 2025-02-24 |  | 2025-03-07 | 2025-03-20 | Office 27.05.2025 | 2025-03-28 |  | 2025-03-21 | 2025-05-12 | 2025-05-13 | 2025-05-23 | 2025-05-26 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-233 | System CHW and LTHW GROUND FLOOR
93648 | FSA_F01-LTHWS-256-DN015-I16C00_R0 | 0 | true | 9.61 | FSA_F01-LTHWS-256-DN015-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 |  | 2025-02-24 |  | 2025-03-07 | 2025-03-26 | Office 09.06.2025 | 2025-03-28 |  | 2025-03-27 | 2025-06-05 | 2025-06-06 | 2025-06-06 | 2025-06-06 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-234 | System Loading Dock 01
93649 | FSA_F01-LTHWS-257-DN015-I16C00_R0 | 0 | true | 13.27 | FSA_F01-LTHWS-257-DN015-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 |  | 2025-02-24 |  | 2025-03-07 | 2025-03-24 | Office 10/06/2025 | 2025-03-28 |  | 2025-03-24 | 2025-06-02 | 2025-06-06 | 2025-06-09 | 2025-06-09 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-012 | System Loading Dock 01
93650 | FSA_F02_1-LTHWR-008-DN100-I16C00_R2 | 2 | true | 60.58 | FSA_F02_1-LTHWR-008-DN100-I16C00_R2 |  | 1129 | FSA_South Side | F02 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2024-11-30 | 2024-12-03 |  | 2024-12-08 | 2025-01-07 | Office 11.03.2025 | 2025-01-29 |  | 2025-01-09 | 2025-02-26 | 2025-02-26 | 2025-02-27 | 2025-03-22 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-200 | System CHW and LTHW FIRST FLOOR
93651 | FSA_F02_1-LTHWS-008-DN100-I16C00_R2 | 2 | true | 60.57 | FSA_F02_1-LTHWS-008-DN100-I16C00_R2 |  | 1129 | FSA_South Side | F02 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2024-11-30 | 2024-12-03 |  | 2024-12-08 | 2025-01-07 | Office 11.03.2025 | 2025-01-29 |  | 2025-01-09 | 2025-02-26 | 2025-02-26 | 2025-02-27 | 2025-03-22 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-200 | System CHW and LTHW FIRST FLOOR
93652 | FSA_F02_2-LTHWR-008-DN100-I16C00_R3 | 3 | true | 28.44 | FSA_F02_2-LTHWR-008-DN100-I16C00_R3 |  | 1129 | FSA Corridor | F02 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2024-12-16 | 2024-12-19 |  | 2025-01-22 | 2025-02-03 | Office 02.04.2025 | 2025-02-05 |  | 2025-02-06 | 2025-03-22 | 2025-03-24 | 2025-04-26 | 2025-05-30 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-320 | System CHW and LTHW FIRST FLOOR
93653 | FSA_F02_2-LTHWR-270-DN015-I16C00_R0 | 0 | true | 8.74 | FSA_F02_2-LTHWR-270-DN015-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-03 | 2025-02-24 |  | 2025-03-07 | 2025-03-18 | Office 01/05/2025 | 2025-03-28 |  | 2025-03-21 | 2025-04-29 | 2025-04-29 | 2025-04-29 | 2025-05-30 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-012 | System CHW and LTHW FIRST FLOOR
93654 | FSA_F02_2-LTHWS-008-DN100-I16C00_R1 | 1 | true | 27.14 | FSA_F02_2-LTHWS-008-DN100-I16C00_R1 |  | 1129 | FSA Corridor | F02 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2024-12-08 | 2024-12-10 |  | 2025-01-07 | 2025-01-26 | Office 02.04.2025 | 2025-01-29 |  | 2025-01-27 | 2025-03-22 | 2025-03-22 | 2025-03-24 | 2025-05-30 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-320 | System CHW and LTHW FIRST FLOOR
93655 | FSA_F02_2-LTHWS-270-DN015-I16C00_R0 | 0 | true | 8.38 | FSA_F02_2-LTHWS-270-DN015-I16C00_R0 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2025-02-07 | 2025-02-06 | 2025-03-03 | 2025-02-24 |  | 2025-03-07 | 2025-03-19 | Office 01/05/2025 | 2025-03-28 |  | 2025-03-21 | 2025-04-29 | 2025-04-29 | 2025-04-30 | 2025-05-30 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-012 | System CHW and LTHW FIRST FLOOR
93878 | CUB4_CWR-001-DN450-GFSDR17_R1 | 1 | true | 18.93 | CUB4_CWR-001-DN450-GFSDR17_R1 |  | 1272 | CUB4 | F01 | N/A | TBH-ZAT-2025-02-14 | 2025-02-13 |  | 2025-02-17 |  |  |  | Adrijan Vuckovic 16.04.2025 |  |  |  | 2025-04-17 | 2025-03-22 | 2025-06-19 |  | 1629 | 193 |  |  |  |  | SEP | SEP | [5 empty] | CUB4 | NO TESTING REQUIRED
93879 | CUB4_CWR-005-DN450-GFSDR17_R1 | 1 | true | 12.57 | CUB4_CWR-005-DN450-GFSDR17_R1 |  | 1272 | CUB4 | F01 | N/A | TBH-ZAT-2025-02-14 | 2025-02-13 |  | 2025-02-17 |  |  |  | Adrijan Vuckovic 16.04.2025 |  |  |  | 2025-04-17 | 2025-03-22 | 2025-06-19 |  | 1629 | 193 |  |  |  |  | SEP | SEP | [5 empty] | CUB4 | NO TESTING REQUIRED
93880 | CUB4_CWR-005-DN500-GFSDR17_R1 | 1 | true | 20.44 | CUB4_CWR-005-DN500-GFSDR17_R1 |  | 1272 | CUB4 | F01 | N/A | TBH-ZAT-2025-02-14 | 2025-02-13 |  | 2025-02-17 |  |  |  | Adrijan Vuckovic 16.04.2025 |  |  |  | 2025-04-17 |  | 2025-03-22 | 2025-06-16 | 1629 | 193 |  |  |  |  | SEP | SEP | [5 empty] | CUB4 | NO TESTING REQUIRED
93881 | CUB4_CWR-026-DN020-GFSDR11_R1 | 1 | true | 1.31 | CUB4_CWR-026-DN020-GFSDR11_R1 |  | 1273 | CUB4 | F01 | N/A | TBH-ZAT-2025-02-14 | 2025-02-13 |  | 2025-02-17 |  |  |  | Adrijan Vuckovic 16.04.2025 | [7 empty] | 1629 | 193 |  |  |  |  | SEP | SEP | [5 empty] | CUB4 | NO TESTING REQUIRED
93882 | CUB4_TWMU-001-DN200-GFSDR11_R1 | 1 | true | 11.76 | CUB4_TWMU-001-DN200-GFSDR11_R1 |  | 1273 | CUB4 | F01 | N/A | TBH-ZAT-2025-02-14 | 2025-02-13 |  | 2025-02-17 |  |  |  | Adrijan Vuckovic 16.04.2025 |  |  |  |  | 2025-04-17 | 2025-03-22 |  | 1630 | 193 |  |  |  |  | SEP | SEP | [5 empty] | CUB4 | NO TESTING REQUIRED
93883 | CUB5_CWR-001-DN500-GFSDR17_R1 | 1 | true | 20.7 | CUB5_CWR-001-DN500-GFSDR17_R1 |  | 1272 | CUB5 | F01 | N/A | TBH-ZAT-2025-02-14 | 2025-02-13 |  | 2025-02-17 |  |  |  | Adrijan Vuckovic 16.04.2025 |  |  |  |  | 2025-03-22 | 2025-06-16 |  | 1629 | 193 |  |  |  |  | SEP | SEP | [5 empty] | CUB5 | NO TESTING REQUIRED
93884 | CUB5_TWMU-001-DN200-GFSDR11_R1 | 1 | true | 17.1 | CUB5_TWMU-001-DN200-GFSDR11_R1 |  | 1273 | CUB5 | F01 | N/A | TBH-ZAT-2025-02-14 | 2025-02-13 |  | 2025-02-17 |  |  |  | Adrijan Vuckovic 16.04.2025 |  |  |  |  | 2025-04-17 | 2025-03-22 |  | 1630 | 193 |  |  |  |  | SEP | SEP | [5 empty] | CUB5 | NO TESTING REQUIRED
93885 | FSA_F01-CHWR-274-DN050-I16C00_R0 | 0 | true | 16.72 | FSA_F01-CHWR-274-DN050-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-14 | 2025-02-13 | 2025-03-10 | 2025-03-11 |  | 2025-03-17 | 2025-04-02 | Office 15.05.2025 | 2025-04-09 |  | 2025-03-31 | 2025-04-29 | 2025-05-01 | 2025-05-13 |  | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-215 | System CHW and LTHW GROUND FLOOR
93886 | FSA_F01-CHWS-019-DN020-I16C00_R1 | 1 | true | 5.31 | FSA_F01-CHWS-019-DN020-I16C00_R1 |  | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-02-14 | 2025-02-13 | 2025-03-15 | 2025-03-13 |  | 2025-03-18 | 2025-03-28 | Office 29.05.2025 | 2025-04-09 |  | 2025-03-31 | 2025-05-26 | 2025-05-26 | 2025-05-26 | 2025-05-26 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System CHW and LTHW GROUND FLOOR
93887 | FSA_F01-CHWS-274-DN050-I16C00_R0 | 0 | true | 18.77 | FSA_F01-CHWS-274-DN050-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-14 | 2025-02-13 | 2025-03-10 | 2025-03-11 |  | 2025-03-17 | 2025-04-03 | Office 15.05.2025 | 2025-04-09 |  | 2025-04-04 | 2025-04-29 | 2025-05-13 | 2025-05-14 | 2025-05-14 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-215 | System CHW and LTHW GROUND FLOOR
93888 | FSA_F01-LTHWR-008-DN100-I16C00_2_R0 | 0 | true | 76.08 | FSA_F01-LTHWR-008-DN100-I16C00_2_R0 |  | 1129 | FSA Corridor | F01 | FoamInside | TBH-ZAT-2025-02-14 | 2025-02-13 | 2025-03-03 | 2025-03-11 |  | 2025-03-14 | 2025-03-24 | Office 16.05.2025 |  |  | 2025-03-24 | 2025-04-18 | 2025-04-24 | 2025-05-05 | 2025-05-15 | 1360 | 193 | Working ISO delivered 14.04.25 - Spools to be checked |  |  | 194 | SEP | SEP | [5 empty] | 1-200 | System CHW and LTHW GROUND FLOOR/System CHW and LTHW FIRST FLOOR
93889 | FSA_F01-LTHWR-251-DN020-I16C00_R0 | 0 | true | 1.21 | FSA_F01-LTHWR-251-DN020-I16C00_R0 |  | 1129 | FSA_South Side | F01 | FoamInside | TBH-ZAT-2025-02-14 | 2025-02-13 | 2025-03-10 | 2025-03-11 |  | 2025-03-17 | 2025-03-21 | Office 26/05/2025 | 2025-03-28 |  | 2025-03-27 | 2025-05-22 | 2025-05-22 | 2025-05-22 | 2025-05-22 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-200 | System CHW and LTHW GROUND FLOOR
93890 | FSA_F01-LTHWR-252-DN015-I16C00_R1 | 1 | true | 8.05 | FSA_F01-LTHWR-252-DN015-I16C00_R1 |  | 1129 | FSA_South Side | F01 | FoamInside | TBH-ZAT-2025-02-14 | 2025-02-13 | 2025-03-10 | 2025-03-11 |  | 2025-03-17 | 2025-04-01 | Office 12.06.2025 | 2025-04-09 |  | 2025-03-31 | 2025-06-06 | 2025-06-06 | 2025-06-06 | 2025-06-06 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-011 | System CHW and LTHW GROUND FLOOR
93891 | FSA_F01-LTHWR-253-DN015-I16C00_R1 | 1 | true | 6.74 | FSA_F01-LTHWR-253-DN015-I16C00_R1 |  | 1129 | FSA_South Side | F01 | FoamInside | TBH-ZAT-2025-02-14 | 2025-02-13 | 2025-03-10 | 2025-03-11 |  | 2025-03-17 | 2025-03-28 | Office 26/05/2025 | 2025-04-09 |  | 2025-03-31 | 2025-05-22 | 2025-05-22 | 2025-05-23 | 2025-05-23 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-204 | System CHW and LTHW GROUND FLOOR
93892 | FSA_F01-LTHWS-008-DN100-I16C00_2_R0 | 0 | true | 74.28 | FSA_F01-LTHWS-008-DN100-I16C00_2_R0 |  | 1129 | FSA Corridor | F01 | FoamInside | TBH-ZAT-2025-02-14 | 2025-02-13 | 2025-03-03 | 2025-03-11 |  | 2025-03-24 |  | Office 16.05.2025 | 2025-04-09 |  | 2025-04-07 | 2025-04-17 | 2025-04-24 | 2025-05-06 | 2025-05-15 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-200 | System CHW and LTHW GROUND FLOOR/System CHW and LTHW FIRST FLOOR
93893 | FSA_F01-LTHWS-251-DN020-I16C00_R0 | 0 | true | 0.72 | FSA_F01-LTHWS-251-DN020-I16C00_R0 |  | 1129 | FSA_South Side | F01 | FoamInside | TBH-ZAT-2025-02-14 | 2025-02-13 | 2025-03-10 | 2025-03-11 |  | 2025-03-17 | 2025-03-20 | Office 26/05/2025 | 2025-03-28 |  | 2025-03-21 | 2025-05-22 | 2025-05-22 | 2025-05-22 | 2025-05-22 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-200 | System CHW and LTHW GROUND FLOOR
93894 | FSA_F01-LTHWS-252-DN015-I16C00_R1 | 1 | true | 7.74 | FSA_F01-LTHWS-252-DN015-I16C00_R1 |  | 1129 | FSA_South Side | F01 | FoamInside | TBH-ZAT-2025-02-14 | 2025-02-13 | 2025-03-10 | 2025-03-11 |  | 2025-03-17 | 2025-03-28 | Office 12.06.2025 | 2025-04-09 |  | 2025-03-31 | 2025-06-09 | 2025-06-09 | 2025-06-09 | 2025-06-09 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-011 | System CHW and LTHW GROUND FLOOR
93895 | FSA_F01-LTHWS-253-DN015-I16C00_R1 | 1 | true | 6.82 | FSA_F01-LTHWS-253-DN015-I16C00_R1 |  | 1129 | FSA_South Side | F01 | FoamInside | TBH-ZAT-2025-02-14 | 2025-02-13 | 2025-03-10 | 2025-03-11 |  | 2025-03-17 | 2025-03-26 | Office 26/05/2025 | 2025-03-28 |  | 2025-03-27 | 2025-05-22 | 2025-05-22 | 2025-05-23 | 2025-05-23 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-204 | System CHW and LTHW GROUND FLOOR
93896 | FSA_F01-PHTGR-009-DN100-I16C00_R0 | 0 | true | 142.32 | FSA_F01-PHTGR-009-DN100-I16C00_R0 |  | 1129 | FSA Corridor | F01 | N/A | TBH-ZAT-2025-02-14 | 2025-02-13 | 2025-03-11 | 2025-03-13 |  | 2025-03-24 | 2025-03-24 | Office 02.06.2025 | 2025-03-28 |  | 2025-03-24 | 2025-04-01 | 2025-04-09 | 2025-06-02 | 2025-06-02 | 1368 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-200, 1-238, 1-221 | System PHTG underground/System PHTG
93897 | FSA_F01-PHTGR-013-DN020-I16C00_R1 | 1 | true | 3.09 | FSA_F01-PHTGR-013-DN020-I16C00_R1 |  | 1129 | FSA Mech Wet Room | F01 | N/A | TBH-ZAT-2025-02-14 | 2025-02-13 | 2025-03-15 | 2025-03-13 |  | 2025-03-18 | 2025-04-01 | Office 20/05/2025 | 2025-04-09 |  | 2025-03-31 | 2025-05-16 | 2025-05-16 | 2025-05-16 | 2025-05-16 | 1368 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System PHTG
93898 | FSA_F01-PHTGS-012-DN100-I16C00_R0 | 0 | true | 142.29 | FSA_F01-PHTGS-012-DN100-I16C00_R0 |  | 1129 | FSA Corridor | F01 | FoamInside | TBH-ZAT-2025-02-14 | 2025-02-13 | 2025-03-11 | 2025-03-11 |  | 2025-03-24 | 2025-03-24 | Office 02.06.2025 | 2025-04-09 |  | 2025-03-24 | 2025-04-01 | 2025-04-03 | 2025-06-02 | 2025-06-02 | 1368 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-200, 1-238, 1-221 | System PHTG underground/System PHTG
93899 | FSA_F01-PHTGS-026-DN020-I16C00_R1 | 1 | true | 2.81 | FSA_F01-PHTGS-026-DN020-I16C00_R1 |  | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-02-14 | 2025-02-13 | 2025-03-15 | 2025-03-13 |  | 2025-03-18 | 2025-03-21 | Office 20/05/2025 | 2025-03-28 |  | 2025-03-27 | 2025-05-16 | 2025-05-16 | 2025-05-16 | 2025-05-16 | 1368 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System PHTG
93900 | FSA_F01-PHTGS-027-DN015-I16C00_R1 | 1 | true | 19.76 | FSA_F01-PHTGS-027-DN015-I16C00_R1 |  | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-02-14 | 2025-02-13 | 2025-03-14 | 2025-03-13 |  | 2025-03-17 | 2025-03-27 | Office 24/05/2025 | 2025-03-28 |  | 2025-03-27 | 2025-05-19 | 2025-05-19 | 2025-05-19 | 2025-05-19 | 1368 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System PHTG
93901 | FSA_F01-PHTGS-028-DN025-I16C00_R1 | 1 | true | 5.94 | FSA_F01-PHTGS-028-DN025-I16C00_R1 |  | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-02-14 | 2025-02-13 | 2025-03-14 | 2025-03-13 |  | 2025-03-21 | 2025-04-02 | Office 20/05/2025 | 2025-04-09 |  | 2025-03-31 | 2025-05-15 | 2025-05-15 | 2025-05-15 | 2025-05-15 | 1368 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System PHTG
93902 | FSA_F01-PHTGS-029-DN020-I16C00_R1 | 1 | true | 4.26 | FSA_F01-PHTGS-029-DN020-I16C00_R1 |  | 1129 | FSA Mech Wet Room | F01 | FoamInside | TBH-ZAT-2025-02-14 | 2025-02-13 | 2025-03-14 | 2025-03-13 |  | 2025-03-17 | 2025-03-25 | Office 20/05/2025 | 2025-03-28 |  | 2025-03-27 | 2025-05-15 | 2025-05-15 | 2025-05-15 | 2025-05-15 | 1368 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-308 | System PHTG
95161 | FSA_F01-CHWR-147-DN020-I16C00_R0 | 0 | true | 9.68 | FSA_F01-CHWR-147-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-21 | 2025-02-20 | 2025-03-11 | 2025-03-11 |  | 2025-03-17 | 2025-03-20 | Office 20/05/2025 | 2025-03-28 |  | 2025-03-21 | 2025-05-13 | 2025-05-19 | 2025-06-10 | 2025-06-10 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-241 | System CHW and LTHW GROUND FLOOR
95162 | FSA_F01-CHWS-147-DN020-I16C00_R0 | 0 | true | 9.46 | FSA_F01-CHWS-147-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-21 | 2025-02-20 | 2025-03-11 | 2025-03-11 |  | 2025-03-17 | 2025-03-21 | Office 20/05/2025 | 2025-03-28 |  | 2025-03-27 | 2025-05-16 | 2025-05-19 | 2025-06-10 | 2025-06-10 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-241 | System CHW and LTHW GROUND FLOOR
95163 | FSA_F01-FT-CHW-101_Spool_R0 | 0 | true | 0 | FSA_F01-FT-CHW-101_Spool_R0 |  | 1129 | FSA Mech Wet Room | F01 | N/A | TBH-ZAT-2025-02-21_Special | 2025-02-20 | 2025-03-18 | 2025-03-11 |  | 2025-03-13 | 2025-03-24 | Office 18.04.2025 |  |  | 2025-03-24 | 2025-04-18 | 2025-04-18 | 2025-04-18 | 2025-04-18 | 1859 | 193 | Working ISO delivered 14.04.25 - Spools to be checked |  |  | 194 | SEP | SEP | [5 empty] | Spool pieces not for Calc | System CHW and LTHW GROUND FLOOR
95164 | FSA_F01-LTHWR-147-DN020-I16C00_R0 | 0 | true | 9.92 | FSA_F01-LTHWR-147-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-21 | 2025-02-20 | 2025-03-11 | 2025-03-11 |  | 2025-03-17 | 2025-03-20 | Office 20/05/2025 | 2025-03-28 |  | 2025-03-21 | 2025-05-16 | 2025-05-20 | 2025-06-10 | 2025-06-10 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-241 | System CHW and LTHW GROUND FLOOR
95165 | FSA_F01-LTHWR-162-DN080-I16C00_R0 | 0 | true | 31.04 | FSA_F01-LTHWR-162-DN080-I16C00_R0 |  | 1129 | FSA North Corridor | F01 | FoamInside | TBH-ZAT-2025-02-21 | 2025-02-20 | 2025-03-12 | 2025-03-11 |  | 2025-03-17 | 2025-03-24 | Office 18.04.2025 |  |  | 2025-03-24 | 2025-04-16 | 2025-04-16 | 2025-04-16 | 2025-05-13 | 1360 | 193 | Working ISO delivered 14.04.25 - Spools to be checked |  |  | 194 | SEP | SEP | [5 empty] | 1-221 | System Loading Dock 01
95166 | FSA_F01-LTHWR-168-DN080-I16C00_R0 | 0 | true | 28.51 | FSA_F01-LTHWR-168-DN080-I16C00_R0 |  | 1129 | FSA North Corridor | F01 | FoamInside | TBH-ZAT-2025-02-21 | 2025-02-20 | 2025-03-12 | 2025-03-11 |  | 2025-03-24 | 2025-03-31 | Filip Gronjak 17.04.2025 | 2025-04-09 |  | 2025-03-31 | 2025-04-25 | 2025-04-26 | 2025-04-26 | 2025-04-26 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-221 | System Loading Dock 01
95167 | FSA_F01-LTHWR-249-DN032-I16C00_R0 | 0 | true | 10.17 | FSA_F01-LTHWR-249-DN032-I16C00_R0 |  | 1129 | FSA North ODH | F01 | FoamInside | TBH-ZAT-2025-02-21 | 2025-02-20 | 2025-03-11 | 2025-03-11 |  | 2025-03-17 | 2025-04-03 | Office 26/05/2025 | 2025-04-09 |  | 2025-03-31 | 2025-05-12 | 2025-05-12 | 2025-05-13 | 2025-05-13 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-235 | System CHW and LTHW GROUND FLOOR
95168 | FSA_F01-LTHWR-250-DN015-I16C00_R1 | 1 | true | 12.07 | FSA_F01-LTHWR-250-DN015-I16C00_R1 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-21 | 2025-02-20 | 2025-03-12 | 2025-03-11 |  | 2025-03-21 | 2025-03-31 | Office 14.05.2025 | 2025-04-09 |  | 2025-03-31 | 2025-05-13 | 2025-05-13 | 2025-05-13 |  | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-202 | System CHW and LTHW GROUND FLOOR
95169 | FSA_F01-LTHWR-259-DN032-I16C00_R0 | 0 | true | 6.22 | FSA_F01-LTHWR-259-DN032-I16C00_R0 |  | 1129 | FSA North ODH | F01 | FoamInside | TBH-ZAT-2025-02-21 | 2025-02-20 | 2025-03-13 | 2025-03-11 |  | 2025-03-17 | 2025-03-21 | Office 27/05/2025 | 2025-03-28 |  | 2025-03-27 | 2025-05-21 | 2025-05-21 | 2025-05-21 | 2025-05-22 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-231 | System Loading Dock 01
95170 | FSA_F01-LTHWR-260-DN032-I16C00_R0 | 0 | true | 2.28 | FSA_F01-LTHWR-260-DN032-I16C00_R0 |  | 1129 | FSA North ODH | F01 | FoamInside | TBH-ZAT-2025-02-21 | 2025-02-20 | 2025-03-12 | 2025-03-11 |  | 2025-03-17 | 2025-04-02 | Office 26/05/2025 | 2025-04-09 |  | 2025-03-31 | 2025-05-19 | 2025-05-19 | 2025-05-19 | 2025-05-19 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-221 | System Loading Dock 01
95171 | FSA_F01-LTHWR-261-DN032-I16C00_R0 | 0 | true | 3.03 | FSA_F01-LTHWR-261-DN032-I16C00_R0 |  | 1129 | FSA North ODH | F01 | FoamInside | TBH-ZAT-2025-02-21 | 2025-02-20 | 2025-03-12 | 2025-03-11 |  | 2025-03-17 | 2025-03-25 | Office 27/05/2025 | 2025-03-28 |  | 2025-03-27 | 2025-05-15 | 2025-05-15 | 2025-05-15 | 2025-05-15 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-221 | System Loading Dock 01
95172 | FSA_F01-LTHWR-262-DN032-I16C00_R0 | 0 | true | 3.03 | FSA_F01-LTHWR-262-DN032-I16C00_R0 |  | 1129 | FSA North ODH | F01 | FoamInside | TBH-ZAT-2025-02-21 | 2025-02-20 | 2025-03-12 | 2025-03-11 |  | 2025-03-17 | 2025-04-01 | Office 16.05.2025 | 2025-04-09 |  | 2025-03-31 | 2025-05-15 | 2025-05-15 | 2025-05-15 | 2025-05-30 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-221 | System Loading Dock 01
95173 | FSA_F01-LTHWR-263-DN032-I16C00_R0 | 0 | true | 3.03 | FSA_F01-LTHWR-263-DN032-I16C00_R0 |  | 1129 | FSA North ODH | F01 | FoamInside | TBH-ZAT-2025-02-21 | 2025-02-20 | 2025-03-12 | 2025-03-11 |  | 2025-03-17 | 2025-03-27 | Office 15.05.2025 | 2025-03-28 |  | 2025-03-27 | 2025-05-14 | 2025-05-14 | 2025-05-14 | 2025-05-30 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-221 | System Loading Dock 01
95174 | FSA_F01-LTHWR-264-DN032-I16C00_R0 | 0 | true | 2.54 | FSA_F01-LTHWR-264-DN032-I16C00_R0 |  | 1129 | FSA North ODH | F01 | FoamInside | TBH-ZAT-2025-02-21 | 2025-02-20 |  | 2025-03-11 |  | 2025-03-17 | 2025-04-01 | Office 14.05.2025 | 2025-04-09 |  | 2025-03-31 | 2025-05-13 | 2025-05-13 | 2025-05-14 | 2025-05-14 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-221 | System Loading Dock 01
95175 | FSA_F01-LTHWR-265-DN032-I16C00_R0 | 0 | true | 3.04 | FSA_F01-LTHWR-265-DN032-I16C00_R0 |  | 1129 | FSA North ODH | F01 | FoamInside | TBH-ZAT-2025-02-21 | 2025-02-20 | 2025-03-12 | 2025-03-11 |  | 2025-03-17 | 2025-03-27 | Office 14.05.2025 | 2025-03-28 |  | 2025-03-27 | 2025-05-12 | 2025-05-12 | 2025-05-12 | 2025-05-13 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-221 | System Loading Dock 01
95176 | FSA_F01-LTHWR-266-DN032-I16C00_R0 | 0 | true | 2.56 | FSA_F01-LTHWR-266-DN032-I16C00_R0 |  | 1129 | FSA North ODH | F01 | FoamInside | TBH-ZAT-2025-02-21 | 2025-02-20 | 2025-03-12 | 2025-03-11 |  | 2025-03-17 | 2025-04-02 | Office 12.05.2025 | 2025-04-09 |  | 2025-03-31 | 2025-05-09 | 2025-05-09 | 2025-05-12 | 2025-05-12 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-221 | System Loading Dock 01
95177 | FSA_F01-LTHWR-267-DN032-I16C00_R0 | 0 | true | 3.04 | FSA_F01-LTHWR-267-DN032-I16C00_R0 |  | 1129 | FSA North ODH | F01 | FoamInside | TBH-ZAT-2025-02-21 | 2025-02-20 | 2025-03-12 | 2025-03-11 |  | 2025-03-17 | 2025-04-01 | Office 09.05.2025 | 2025-04-09 |  | 2025-03-31 | 2025-05-08 | 2025-05-08 | 2025-05-08 | 2025-05-09 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-221 | System Loading Dock 01
95178 | FSA_F01-LTHWR-268-DN032-I16C00_R0 | 0 | true | 2.78 | FSA_F01-LTHWR-268-DN032-I16C00_R0 |  | 1129 | FSA North ODH | F01 | FoamInside | TBH-ZAT-2025-02-21 | 2025-02-20 | 2025-03-12 | 2025-03-11 |  | 2025-03-21 | 2025-05-30 | Office 02.06.2025 | 2025-05-30 |  | 2025-05-30 | 2025-05-30 | 2025-05-30 | 2025-05-30 | 2025-06-02 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-221 | System Loading Dock 01
95179 | FSA_F01-LTHWS-147-DN020-I16C00_R0 | 0 | true | 10.14 | FSA_F01-LTHWS-147-DN020-I16C00_R0 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-21 | 2025-02-20 | 2025-03-12 | 2025-03-11 |  | 2025-03-17 | 2025-03-19 | Office 20/05/2025 | 2025-03-28 |  | 2025-03-21 | 2025-05-16 | 2025-05-19 | 2025-06-10 | 2025-06-10 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-241 | System CHW and LTHW GROUND FLOOR
95180 | FSA_F01-LTHWS-162-DN080-I16C00_R0 | 0 | true | 31.67 | FSA_F01-LTHWS-162-DN080-I16C00_R0 |  | 1129 | FSA North Corridor | F01 | FoamInside | TBH-ZAT-2025-02-21 | 2025-02-20 | 2025-03-12 | 2025-03-11 |  | 2025-03-17 | 2025-03-24 | Office 18.04.2025 |  |  | 2025-03-24 | 2025-04-16 | 2025-04-16 | 2025-04-17 | 2025-05-13 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-221 | System Loading Dock 01
95181 | FSA_F01-LTHWS-168-DN080-I16C00_R0 | 0 | true | 27.92 | FSA_F01-LTHWS-168-DN080-I16C00_R0 |  | 1129 | FSA North Corridor | F01 | FoamInside | TBH-ZAT-2025-02-21 | 2025-02-20 | 2025-03-12 | 2025-03-11 |  | 2025-03-17 | 2025-03-25 | Office 26/04/2025 |  |  | 2025-03-27 | 2025-04-23 | 2025-04-24 | 2025-04-25 | 2025-04-26 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-221 | System Loading Dock 01
95182 | FSA_F01-LTHWS-249-DN032-I16C00_R0 | 0 | true | 9.56 | FSA_F01-LTHWS-249-DN032-I16C00_R0 |  | 1129 | FSA North ODH | F01 | FoamInside | TBH-ZAT-2025-02-21 | 2025-02-20 | 2025-03-12 | 2025-03-11 |  | 2025-03-17 | 2025-04-03 | Office 26/05/2025 | 2025-04-09 |  | 2025-03-31 | 2025-05-12 | 2025-05-12 | 2025-05-13 | 2025-05-13 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-235 | System CHW and LTHW GROUND FLOOR
95183 | FSA_F01-LTHWS-250-DN015-I16C00_R1 | 1 | true | 11.58 | FSA_F01-LTHWS-250-DN015-I16C00_R1 |  | 1129 | FSA North | F01 | FoamInside | TBH-ZAT-2025-02-21 | 2025-02-20 | 2025-03-12 | 2025-03-11 |  | 2025-03-21 | 2025-04-01 | Office 14.05.2025 | 2025-04-09 |  | 2025-04-04 | 2025-05-13 | 2025-05-13 | 2025-05-13 |  | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-202 | System CHW and LTHW GROUND FLOOR
95184 | FSA_F01-LTHWS-259-DN032-I16C00_R0 | 0 | true | 4.81 | FSA_F01-LTHWS-259-DN032-I16C00_R0 |  | 1129 | FSA North ODH | F01 | FoamInside | TBH-ZAT-2025-02-21 | 2025-02-20 | 2025-03-13 | 2025-03-11 |  | 2025-03-17 | 2025-03-25 | Office 27/05/2025 | 2025-03-28 |  | 2025-03-27 | 2025-05-21 | 2025-05-22 | 2025-05-23 | 2025-05-23 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-231 | System Loading Dock 01
95185 | FSA_F01-LTHWS-260-DN032-I16C00_R0 | 0 | true | 0.42 | FSA_F01-LTHWS-260-DN032-I16C00_R0 |  | 1129 | FSA North ODH | F01 | FoamInside | TBH-ZAT-2025-02-21 | 2025-02-20 | 2025-03-13 | 2025-03-11 |  | 2025-03-17 | 2025-04-01 | Office 26/05/2025 | 2025-04-09 |  | 2025-03-31 | 2025-05-18 | 2025-05-18 | 2025-05-18 | 2025-05-18 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-221 | System Loading Dock 01
95186 | FSA_F01-LTHWS-261-DN032-I16C00_R0 | 0 | true | 0.04 | FSA_F01-LTHWS-261-DN032-I16C00_R0 |  | 1129 | FSA North ODH | F01 | FoamInside | TBH-ZAT-2025-02-21 | 2025-02-20 | 2025-03-13 | 2025-03-11 |  | 2025-03-17 | 2025-04-01 | Office 27/05/2025 | 2025-04-09 |  | 2025-03-31 | 2025-05-21 | 2025-05-21 | 2025-05-21 | 2025-05-21 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-221 | System Loading Dock 01
95187 | FSA_F01-LTHWS-262-DN032-I16C00_R0 | 0 | true | 0.04 | FSA_F01-LTHWS-262-DN032-I16C00_R0 |  | 1129 | FSA North ODH | F01 | FoamInside | TBH-ZAT-2025-02-21 | 2025-02-20 | 2025-03-13 | 2025-03-11 |  | 2025-03-17 | 2025-04-01 | Office 16.05.2025 | 2025-04-09 |  | 2025-03-31 | 2025-05-15 | 2025-05-15 | 2025-05-15 | 2025-05-30 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-221 | System Loading Dock 01
95188 | FSA_F01-LTHWS-263-DN032-I16C00_R0 | 0 | true | 0.04 | FSA_F01-LTHWS-263-DN032-I16C00_R0 |  | 1129 | FSA North ODH | F01 | FoamInside | TBH-ZAT-2025-02-21 | 2025-02-20 | 2025-03-13 | 2025-03-11 |  | 2025-03-17 | 2025-04-01 | Office 15.05.2025 | 2025-04-09 |  | 2025-03-31 | 2025-05-14 | 2025-05-14 | 2025-05-14 | 2025-05-30 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-221 | System Loading Dock 01
95189 | FSA_F01-LTHWS-264-DN032-I16C00_R0 | 0 | true | 0.04 | FSA_F01-LTHWS-264-DN032-I16C00_R0 |  | 1129 | FSA North ODH | F01 | FoamInside | TBH-ZAT-2025-02-21 | 2025-02-20 | 2025-03-13 | 2025-03-11 |  | 2025-03-17 | 2025-04-01 | Office 14.05.2025 | 2025-04-09 |  | 2025-03-31 | 2025-05-13 | 2025-05-13 | 2025-05-13 | 2025-05-13 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-221 | System Loading Dock 01
95190 | FSA_F01-LTHWS-265-DN032-I16C00_R0 | 0 | true | 0.05 | FSA_F01-LTHWS-265-DN032-I16C00_R0 |  | 1129 | FSA North ODH | F01 | FoamInside | TBH-ZAT-2025-02-21 | 2025-02-20 | 2025-03-13 | 2025-03-11 |  | 2025-03-17 | 2025-04-01 | Office 14.05.2025 | 2025-04-09 |  | 2025-03-31 | 2025-05-12 | 2025-05-12 | 2025-05-12 | 2025-05-13 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-221 | System Loading Dock 01
95191 | FSA_F01-LTHWS-266-DN032-I16C00_R0 | 0 | true | 0.05 | FSA_F01-LTHWS-266-DN032-I16C00_R0 |  | 1129 | FSA North ODH | F01 | FoamInside | TBH-ZAT-2025-02-21 | 2025-02-20 | 2025-03-13 | 2025-03-11 |  | 2025-03-17 | 2025-04-01 | Office 12.05.2025 | 2025-04-09 |  | 2025-03-31 | 2025-05-09 | 2025-05-09 | 2025-05-09 | 2025-05-09 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-221 | System Loading Dock 01
95192 | FSA_F01-LTHWS-267-DN032-I16C00_R0 | 0 | true | 0.05 | FSA_F01-LTHWS-267-DN032-I16C00_R0 |  | 1129 | FSA North ODH | F01 | FoamInside | TBH-ZAT-2025-02-21 | 2025-02-20 | 2025-03-13 | 2025-03-11 |  | 2025-03-17 | 2025-03-20 | Office 09.05.2025 | 2025-03-28 |  | 2025-03-21 | 2025-05-08 | 2025-05-08 | 2025-05-08 | 2025-05-08 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-221 | System Loading Dock 01
95193 | FSA_F01-LTHWS-268-DN032-I16C00_R0 | 0 | true | 1.54 | FSA_F01-LTHWS-268-DN032-I16C00_R0 |  | 1129 | FSA North ODH | F01 | FoamInside | TBH-ZAT-2025-02-21 | 2025-02-20 | 2025-03-13 | 2025-03-11 |  | 2025-03-17 | 2025-03-24 | Office 02.06.2025 | 2025-03-28 |  | 2025-03-24 | 2025-05-30 | 2025-05-30 | 2025-05-30 | 2025-05-30 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-221 | System Loading Dock 01
95194 | FSA_F02_1-PICV-PCW-001_Spool_R0 | 0 | true | 0 | FSA_F02_1-PICV-PCW-001_Spool_R0 |  | 1129 | CCNR AHU Room | F02 | FoamInside | TBH-ZAT-2025-02-21_Special | 2025-02-20 |  | 2025-03-11 |  | 2025-03-13 | 2025-03-14 | Office 31.03.2025 | 2025-03-19 |  | 2025-03-14 | 2025-03-28 | 2025-03-29 | 2025-03-29 |  | 1859 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | Spool pieces not for Calc | System PCW 02
95195 | FSA_F02_1-PICV-PCW-002_Spool_R0 | 0 | true | 0 | FSA_F02_1-PICV-PCW-002_Spool_R0 |  | 1129 | CCNR AHU Room | F02 | FoamInside | TBH-ZAT-2025-02-21_Special | 2025-02-20 |  | 2025-03-11 |  | 2025-03-13 | 2025-03-14 | Office 31.03.2025 | 2025-03-19 |  | 2025-03-14 | 2025-03-28 | 2025-03-29 | 2025-03-29 | 2025-05-30 | 1859 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | Spool pieces not for Calc | System PCW 02
95196 | FSA_F02_1-PICV-PCW-003_Spool_R0 | 0 | true | 0 | FSA_F02_1-PICV-PCW-003_Spool_R0 |  | 1129 | CCNR AHU Room | F02 | FoamInside | TBH-ZAT-2025-02-21_Special | 2025-02-20 |  | 2025-03-11 |  | 2025-03-13 | 2025-03-14 | Office 31.03.2025 | 2025-03-19 |  | 2025-03-14 | 2025-03-28 | 2025-03-29 | 2025-03-29 | 2025-05-30 | 1859 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | Spool pieces not for Calc | System PCW 02
95197 | FSA_F02_1-PICV-PCW-004_Spool_R0 | 0 | true | 0 | FSA_F02_1-PICV-PCW-004_Spool_R0 |  | 1129 | CCNR AHU Room | F02 | FoamInside | TBH-ZAT-2025-02-21_Special | 2025-02-20 |  | 2025-03-11 |  | 2025-03-13 | 2025-03-14 | Office 31.03.2025 | 2025-03-19 |  | 2025-03-14 | 2025-03-28 | 2025-03-29 | 2025-03-29 | 2025-05-30 | 1859 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | Spool pieces not for Calc | System PCW 02
95198 | FSA_ROF-CHWR-193-DN025-I16C00_R0 | 0 | true | 17.79 | FSA_ROF-CHWR-193-DN025-I16C00_R0 |  | 1129 | FSA Penthouse | Roof | FoamInside | TBH-ZAT-2025-02-21 | 2025-02-20 | 2025-03-17 | 2025-03-13 |  | 2025-03-21 | 2025-03-27 | Office 09.05.2025 | 2025-03-28 |  | 2025-03-27 | 2025-05-02 | 2025-05-02 | 2025-05-03 | 2025-05-05 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | Penthouse no No. | System CHW and LTHW FIRST FLOOR
95199 | FSA_ROF-CHWR-206-DN020-I16C00_R0 | 0 | true | 0.54 | FSA_ROF-CHWR-206-DN020-I16C00_R0 |  | 1129 | FSA Penthouse | Roof | FoamInside | TBH-ZAT-2025-02-21 | 2025-02-20 | 2025-03-17 | 2025-03-13 |  | 2025-03-14 | 2025-03-24 | Office 15.05.2025 | 2025-03-28 |  | 2025-03-24 | 2025-05-14 | 2025-05-14 | 2025-05-15 | 2025-05-15 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | Penthouse no No. | System CHW and LTHW FIRST FLOOR
95200 | FSA_ROF-CHWR-207-DN020-I16C00_R0 | 0 | true | 4.42 | FSA_ROF-CHWR-207-DN020-I16C00_R0 |  | 1129 | FSA Penthouse | Roof | FoamInside | TBH-ZAT-2025-02-21 | 2025-02-20 | 2025-03-15 | 2025-03-13 |  | 2025-03-12 | 2025-03-20 | Office 06.06.2025 | 2025-03-28 |  | 2025-03-21 | 2025-05-21 | 2025-05-21 | 2025-05-21 | 2025-05-21 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | Penthouse no No. | System CHW and LTHW FIRST FLOOR
95201 | FSA_ROF-CHWR-208-DN020-I16C00_R0 | 0 | true | 16.86 | FSA_ROF-CHWR-208-DN020-I16C00_R0 |  | 1129 | FSA Penthouse | Roof | FoamInside | TBH-ZAT-2025-02-21 | 2025-02-20 | 2025-03-17 | 2025-03-13 |  | 2025-03-12 | 2025-03-20 | Office 06.06.2025 | 2025-03-28 |  | 2025-03-21 | 2025-05-13 | 2025-05-13 | 2025-05-28 | 2025-05-28 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | Penthouse no No. | System CHW and LTHW FIRST FLOOR
95202 | FSA_ROF-CHWS-193-DN025-I16C00_R0 | 0 | true | 18.24 | FSA_ROF-CHWS-193-DN025-I16C00_R0 |  | 1129 | FSA Penthouse | Roof | FoamInside | TBH-ZAT-2025-02-21 | 2025-02-20 | 2025-03-17 | 2025-03-13 |  | 2025-03-21 | 2025-03-27 | Office 09.05.2025 | 2025-03-28 |  | 2025-03-27 | 2025-05-02 | 2025-05-02 | 2025-05-03 | 2025-05-05 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | Penthouse no No. | System CHW and LTHW FIRST FLOOR
95203 | FSA_ROF-CHWS-206-DN020-I16C00_R0 | 0 | true | 0.54 | FSA_ROF-CHWS-206-DN020-I16C00_R0 |  | 1129 | FSA Penthouse | Roof | FoamInside | TBH-ZAT-2025-02-21 | 2025-02-20 | 2025-03-17 | 2025-03-13 |  | 2025-03-18 | 2025-03-28 | Office 15.05.2025 | 2025-04-09 |  | 2025-03-31 | 2025-05-14 | 2025-05-14 | 2025-05-15 | 2025-05-15 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | Penthouse no No. | System CHW and LTHW FIRST FLOOR
95204 | FSA_ROF-CHWS-207-DN020-I16C00_R0 | 0 | true | 4.72 | FSA_ROF-CHWS-207-DN020-I16C00_R0 |  | 1129 | FSA Penthouse | Roof | FoamInside | TBH-ZAT-2025-02-21 | 2025-02-20 | 2025-03-15 | 2025-03-13 |  | 2025-03-18 | 2025-03-21 | Office 06.06.2025 | 2025-03-28 |  | 2025-03-27 | 2025-05-21 | 2025-05-21 | 2025-05-21 | 2025-05-21 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | Penthouse no No. | System CHW and LTHW FIRST FLOOR
95205 | FSA_ROF-CHWS-208-DN020-I16C00_R0 | 0 | true | 16.98 | FSA_ROF-CHWS-208-DN020-I16C00_R0 |  | 1129 | FSA Penthouse | Roof | FoamInside | TBH-ZAT-2025-02-21 | 2025-02-20 | 2025-03-17 | 2025-03-13 |  | 2025-03-18 | 2025-04-03 | Office 06.06.2025 | 2025-04-09 |  | 2025-03-31 | 2025-05-13 | 2025-05-13 | 2025-05-28 | 2025-05-28 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | Penthouse no No. | System CHW and LTHW FIRST FLOOR
95206 | FSA_ROF-LTHWR-193-DN020-I16C00_R0 | 0 | true | 16.87 | FSA_ROF-LTHWR-193-DN020-I16C00_R0 |  | 1129 | FSA Penthouse | Roof | FoamInside | TBH-ZAT-2025-02-21 | 2025-02-20 | 2025-03-17 | 2025-03-13 |  | 2025-03-18 | 2025-03-26 | Office 09.05.2025 | 2025-03-28 |  | 2025-03-27 | 2025-05-02 | 2025-05-02 | 2025-05-03 | 2025-05-05 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | Penthouse no No. | System CHW and LTHW FIRST FLOOR
95207 | FSA_ROF-LTHWR-206-DN015-I16C00_R0 | 0 | true | 0.88 | FSA_ROF-LTHWR-206-DN015-I16C00_R0 |  | 1129 | FSA Penthouse | Roof | FoamInside | TBH-ZAT-2025-02-21 | 2025-02-20 | 2025-03-17 | 2025-03-13 |  | 2025-03-21 | 2025-04-02 | Office 15.05.2025 | 2025-04-09 |  | 2025-04-04 | 2025-05-14 | 2025-05-14 | 2025-05-15 | 2025-05-15 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | Penthouse no No. | System CHW and LTHW FIRST FLOOR
95208 | FSA_ROF-LTHWR-207-DN015-I16C00_R0 | 0 | true | 4.6 | FSA_ROF-LTHWR-207-DN015-I16C00_R0 |  | 1129 | FSA Penthouse | Roof | FoamInside | TBH-ZAT-2025-02-21 | 2025-02-20 | 2025-03-17 | 2025-03-13 |  | 2025-03-21 | 2025-04-01 | Office 06.06.2025 | 2025-04-09 |  | 2025-04-04 | 2025-05-22 | 2025-05-22 | 2025-05-22 | 2025-05-22 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | Penthouse no No. | System CHW and LTHW FIRST FLOOR
95209 | FSA_ROF-LTHWR-208-DN015-I16C00_R0 | 0 | true | 16.46 | FSA_ROF-LTHWR-208-DN015-I16C00_R0 |  | 1129 | FSA Penthouse | Roof | FoamInside | TBH-ZAT-2025-02-21 | 2025-02-20 | 2025-03-17 | 2025-03-13 |  | 2025-03-21 | 2025-04-02 | Office 06.06.2025 | 2025-04-09 |  | 2025-04-04 | 2025-05-13 | 2025-05-27 | 2025-05-28 | 2025-05-28 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | Penthouse no No. | System CHW and LTHW FIRST FLOOR
95210 | FSA_ROF-LTHWR-271-DN015-I16C00_R0 | 0 | true | 0.28 | FSA_ROF-LTHWR-271-DN015-I16C00_R0 |  | 1129 | FSA Penthouse | Roof | FoamInside | TBH-ZAT-2025-02-21 | 2025-02-20 | 2025-03-17 | 2025-03-13 |  | 2025-03-21 | 2025-04-03 | Office 12.05.2025 | 2025-04-09 |  | 2025-04-04 | 2025-05-12 | 2025-05-12 | 2025-05-12 | 2025-05-12 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-012 | System CHW and LTHW FIRST FLOOR
95211 | FSA_ROF-LTHWS-193-DN020-I16C00_R0 | 0 | true | 17.32 | FSA_ROF-LTHWS-193-DN020-I16C00_R0 |  | 1129 | FSA Penthouse | Roof | FoamInside | TBH-ZAT-2025-02-21 | 2025-02-20 | 2025-03-18 | 2025-03-13 |  | 2025-03-18 | 2025-03-26 | Office 09.05.2025 | 2025-03-28 |  | 2025-03-27 | 2025-05-02 | 2025-05-02 | 2025-05-03 | 2025-05-05 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | Penthouse no No. | System CHW and LTHW FIRST FLOOR
95212 | FSA_ROF-LTHWS-206-DN015-I16C00_R0 | 0 | true | 0.74 | FSA_ROF-LTHWS-206-DN015-I16C00_R0 |  | 1129 | FSA Penthouse | Roof | FoamInside | TBH-ZAT-2025-02-21 | 2025-02-20 | 2025-03-18 | 2025-03-13 |  | 2025-03-21 | 2025-04-01 | Office 15.05.2025 | 2025-04-09 |  | 2025-04-04 | 2025-05-14 | 2025-05-14 | 2025-05-15 | 2025-05-15 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | Penthouse no No. | System CHW and LTHW FIRST FLOOR
95213 | FSA_ROF-LTHWS-207-DN015-I16C00_R0 | 0 | true | 4.79 | FSA_ROF-LTHWS-207-DN015-I16C00_R0 |  | 1129 | FSA Penthouse | Roof | FoamInside | TBH-ZAT-2025-02-21 | 2025-02-20 | 2025-03-15 | 2025-03-13 |  | 2025-03-21 | 2025-04-01 | Office 06.06.2025 | 2025-04-09 |  | 2025-04-04 | 2025-05-22 | 2025-05-22 | 2025-05-22 | 2025-05-22 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | Penthouse no No. | System CHW and LTHW FIRST FLOOR
95214 | FSA_ROF-LTHWS-208-DN015-I16C00_R0 | 0 | true | 17 | FSA_ROF-LTHWS-208-DN015-I16C00_R0 |  | 1129 | FSA Penthouse | Roof | FoamInside | TBH-ZAT-2025-02-21 | 2025-02-20 | 2025-03-18 | 2025-03-13 |  | 2025-03-21 | 2025-04-02 | Office 06.06.2025 | 2025-04-09 |  | 2025-04-04 | 2025-05-13 | 2025-05-27 | 2025-05-28 | 2025-05-28 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | Penthouse no No. | System CHW and LTHW FIRST FLOOR
95215 | FSA_ROF-LTHWS-271-DN015-I16C00_R0 | 0 | true | 0.29 | FSA_ROF-LTHWS-271-DN015-I16C00_R0 |  | 1129 | FSA Penthouse | Roof | FoamInside | TBH-ZAT-2025-02-21 | 2025-02-20 | 2025-03-18 | 2025-03-13 |  | 2025-03-21 | 2025-04-03 | Office 12.05.2025 | 2025-04-09 |  | 2025-04-04 | 2025-05-12 | 2025-05-12 | 2025-05-12 | 2025-05-12 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 1-012 | System CHW and LTHW FIRST FLOOR
95216 | FSA_ROF-TCV-CHW-306_Spool_R0 | 0 | true | 0 | FSA_ROF-TCV-CHW-306_Spool_R0 |  | 1129 | FSA Roof | Roof | N/A | TBH-ZAT-2025-02-21_Special | 2025-02-20 |  | 2025-03-11 |  | 2025-03-17 | 2025-03-24 | Office 10.05.2025 | 2025-04-09 |  | 2025-03-24 | 2025-06-12 | 2025-06-12 | 2025-06-12 | 2025-06-12 | 1859 | 193 | Working ISO delivered 14.04.25 - Spools to be checked |  |  | 194 | SEP | SEP | [5 empty] | Spool pieces not for Calc | System CHW and LTHW FIRST FLOOR
95217 | FSA_ROF-TCV-PHTG-306_Spool_R0 | 0 | true | 0 | FSA_ROF-TCV-PHTG-306_Spool_R0 |  | 1129 | FSA Roof | Roof | N/A | TBH-ZAT-2025-02-21_Special | 2025-02-20 |  | 2025-03-11 |  | 2025-03-13 | 2025-03-14 | Office 16.05.2025 | 2025-03-19 |  | 2025-03-14 | 2025-05-07 | 2025-05-07 | 2025-05-07 | 2025-05-07 | 1859 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | Spool pieces not for Calc | System PHTG
95218 | FSA_ROF-TCV-PHTG-307_Spool_R0 | 0 | true | 0 | FSA_ROF-TCV-PHTG-307_Spool_R0 |  | 1129 | FSA Roof | Roof | N/A | TBH-ZAT-2025-02-21_Special | 2025-02-20 |  | 2025-03-11 |  | 2025-03-17 | 2025-03-24 | Office 10.05.2025 | 2025-04-09 |  | 2025-03-24 | 2025-06-12 | 2025-06-12 | 2025-06-12 | 2025-06-12 | 1859 | 193 | Working ISO delivered 14.04.25 - Spools to be checked |  |  | 194 | SEP | SEP | [5 empty] | Spool pieces not for Calc | System PHTG
95219 | FSA_ROF-TCV-PHTG-308_Spool_R0 | 0 | true | 0 | FSA_ROF-TCV-PHTG-308_Spool_R0 |  | 1129 | FSA Roof | Roof | N/A | TBH-ZAT-2025-02-21_Special | 2025-02-20 |  | 2025-03-11 |  | 2025-03-13 | 2025-03-14 | Office 16.05.2025 | 2025-03-19 |  | 2025-03-14 | 2025-05-07 | 2025-05-07 | 2025-05-07 | 2025-05-07 | 1859 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | Spool pieces not for Calc | System PHTG
95220 | FSA_ROF-TCV-PHTG-309_Spool_R0 | 0 | true | 0 | FSA_ROF-TCV-PHTG-309_Spool_R0 |  | 1129 | FSA Roof | Roof | N/A | TBH-ZAT-2025-02-21_Special | 2025-02-20 |  | 2025-03-11 |  | 2025-03-17 | 2025-03-24 | Office 10.05.2025 | 2025-04-09 |  | 2025-03-24 | 2025-06-12 | 2025-06-12 | 2025-06-12 | 2025-06-12 | 1859 | 193 | Working ISO delivered 14.04.25 - Spools to be checked |  |  | 194 | SEP | SEP | [5 empty] | Spool pieces not for Calc | System PHTG
95221 | FSA_ROF-TCV-PHTG-310_Spool_R0 | 0 | true | 0 | FSA_ROF-TCV-PHTG-310_Spool_R0 |  | 1129 | FSA Roof | Roof | N/A | TBH-ZAT-2025-02-21_Special | 2025-02-20 |  | 2025-03-11 |  | 2025-03-13 | 2025-03-14 | Office 16.05.2025 | 2025-03-19 |  | 2025-03-14 | 2025-05-07 | 2025-05-07 | 2025-05-07 | 2025-05-07 | 1859 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | Spool pieces not for Calc | System PHTG
95322 | FSA_F02_2-CHWR-244-DN025-I16C00_R1 | 1 | true | 0.51 | FSA_F02_2-CHWR-244-DN025-I16C00_R1 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2025-02-28 | 2025-02-27 | 2025-01-09 | 2025-01-14 |  | 2025-01-19 | 2025-01-29 | Office 03.04.2025 | 2025-02-05 |  | 2025-01-30 | 2025-04-01 | 2025-04-01 | 2025-04-01 | 2025-04-01 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-320 | System CHW and LTHW FIRST FLOOR
95323 | FSA_F02_2-CHWR-245-DN020-I16C00_R1 | 1 | true | 2.36 | FSA_F02_2-CHWR-245-DN020-I16C00_R1 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2025-02-28 | 2025-02-27 | 2025-01-09 | 2025-01-14 |  | 2025-01-19 | 2025-01-29 | Office 03.04.2025 | 2025-02-05 |  | 2025-01-30 | 2025-04-03 | 2025-04-03 | 2025-04-15 | 2025-04-15 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-320 | System CHW and LTHW FIRST FLOOR
95324 | FSA_F02_2-CHWR-246-DN025-I16C00_R1 | 1 | true | 9.27 | FSA_F02_2-CHWR-246-DN025-I16C00_R1 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2025-02-28 | 2025-02-27 | 2025-01-09 | 2025-01-14 |  | 2025-01-19 | 2025-01-27 | Office 03.04.2025 | 2025-02-05 |  | 2025-01-27 | 2025-04-01 | 2025-04-01 | 2025-04-15 | 2025-04-15 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-209 | System CHW and LTHW FIRST FLOOR
95325 | FSA_F02_2-CHWS-244-DN025-I16C00_R1 | 1 | true | 0.86 | FSA_F02_2-CHWS-244-DN025-I16C00_R1 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2025-02-28 | 2025-02-27 | 2025-01-08 | 2025-01-14 |  | 2025-01-21 | 2025-01-29 | Office 03.04.2025 | 2025-02-05 |  | 2025-01-30 | 2025-04-01 | 2025-04-01 | 2025-04-01 | 2025-04-01 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-320 | System CHW and LTHW FIRST FLOOR
95326 | FSA_F02_2-CHWS-245-DN020-I16C00_R1 | 1 | true | 2.24 | FSA_F02_2-CHWS-245-DN020-I16C00_R1 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2025-02-28 | 2025-02-27 | 2025-01-08 | 2025-01-14 |  | 2025-01-21 | 2025-01-29 | Office 03.04.2025 | 2025-02-05 |  | 2025-01-30 | 2025-04-03 | 2025-04-03 | 2025-04-15 | 2025-04-15 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-320 | System CHW and LTHW FIRST FLOOR
95327 | FSA_F02_2-CHWS-246-DN025-I16C00_R1 | 1 | true | 9.31 | FSA_F02_2-CHWS-246-DN025-I16C00_R1 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2025-02-28 | 2025-02-27 |  | 2025-01-14 |  | 2025-01-21 | 2025-01-29 | Office 03.04.2025 | 2025-02-05 |  | 2025-01-30 | 2025-04-01 | 2025-04-01 | 2025-04-15 | 2025-04-15 | 1359 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-209 | System CHW and LTHW FIRST FLOOR
95328 | FSA_F02_2-LTHWR-244-DN025-I16C00_R1 | 1 | true | 1.06 | FSA_F02_2-LTHWR-244-DN025-I16C00_R1 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2025-02-28 | 2025-02-27 | 2024-12-16 | 2024-12-22 |  | 2025-01-02 | 2025-01-12 | Office 03.04.2025 | 2025-01-29 |  | 2025-01-12 | 2025-04-01 | 2025-04-01 | 2025-04-01 | 2025-04-01 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-320 | System CHW and LTHW FIRST FLOOR
95329 | FSA_F02_2-LTHWR-245-DN020-I16C00_R1 | 1 | true | 2.56 | FSA_F02_2-LTHWR-245-DN020-I16C00_R1 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2025-02-28 | 2025-02-27 | 2024-12-16 | 2024-12-22 |  | 2025-01-02 | 2025-01-12 | Office 03.04.2025 | 2025-01-29 |  | 2025-01-12 | 2025-04-02 | 2025-04-02 | 2025-04-15 | 2025-04-15 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-320 | System CHW and LTHW FIRST FLOOR
95330 | FSA_F02_2-LTHWR-246-DN020-I16C00_R1 | 1 | true | 9.61 | FSA_F02_2-LTHWR-246-DN020-I16C00_R1 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2025-02-28 | 2025-02-27 |  | 2024-12-22 |  | 2025-01-02 | 2025-01-12 | Office 03.04.2025 | 2025-01-29 |  | 2025-01-12 | 2025-04-01 | 2025-04-01 | 2025-04-15 | 2025-04-15 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-209 | System CHW and LTHW FIRST FLOOR
95331 | FSA_F02_2-LTHWS-244-DN025-I16C00_R1 | 1 | true | 1.1 | FSA_F02_2-LTHWS-244-DN025-I16C00_R1 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2025-02-28 | 2025-02-27 | 2024-12-15 | 2024-12-19 |  | 2025-01-06 | 2025-01-29 | Office 03.04.2025 | 2025-02-05 |  | 2025-01-29 | 2025-04-01 | 2025-04-01 | 2025-04-01 | 2025-04-01 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-320 | System CHW and LTHW FIRST FLOOR
95332 | FSA_F02_2-LTHWS-245-DN020-I16C00_R1 | 1 | true | 2.54 | FSA_F02_2-LTHWS-245-DN020-I16C00_R1 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2025-02-28 | 2025-02-27 | 2024-12-15 | 2024-12-19 |  | 2025-01-06 | 2025-01-29 | Office 03.04.2025 | 2025-02-05 |  | 2025-01-29 | 2025-04-02 | 2025-04-03 | 2025-04-15 | 2025-04-15 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-209 | System CHW and LTHW FIRST FLOOR
95333 | FSA_F02_2-LTHWS-246-DN020-I16C00_R1 | 1 | true | 9.14 | FSA_F02_2-LTHWS-246-DN020-I16C00_R1 |  | 1129 | FSA North | F02 | FoamInside | TBH-ZAT-2025-02-28 | 2025-02-27 |  | 2024-12-19 |  | 2025-01-06 | 2025-01-30 | Office 03.04.2025 | 2025-02-05 |  | 2025-01-29 | 2025-04-01 | 2025-04-01 | 2025-04-15 | 2025-04-15 | 1360 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | 2-209 | System CHW and LTHW FIRST FLOOR
95334 | FSA_ROF-CHWS-023-DN080-I16C00_Spool_R0 | 0 | true | 1.06 | FSA_ROF-CHWS-023-DN080-I16C00_Spool_R0 |  | 1129 | FSA Roof | Roof | FoamInside | TBH-ZAT-2025-02-28_Special | 2025-02-27 | 2025-03-18 | 2025-03-11 |  | 2025-03-24 | 2025-03-31 | Office 10.05.2025 | 2025-04-09 |  | 2025-03-31 | 2025-05-12 | 2025-05-12 | 2025-05-12 | 2025-05-30 | 1859 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | Spool pieces not for Calc | System CHW and LTHW FIRST FLOOR
95335 | FSA_ROF-PHTGR-016-DN080-I16C00_Spool_R0 | 0 | true | 1.21 | FSA_ROF-PHTGR-016-DN080-I16C00_Spool_R0 |  | 1129 | FSA Roof | Roof | FoamInside | TBH-ZAT-2025-02-28_Special | 2025-02-27 | 2025-03-18 | 2025-03-11 |  | 2025-03-17 | 2025-03-25 | Office 10.05.2025 |  |  | 2025-03-27 | 2025-05-02 | 2025-05-10 | 2025-05-10 | 2025-05-10 | 1859 | 193 | Working ISO delivered 14.04.25 - Spools to be checked |  |  | 194 | SEP | SEP | [5 empty] | Spool pieces not for Calc | System PHTG
95336 | FSA_ROF-PHTGR-017-DN100-I16C00-Spool_R0 | 0 | true | 1.11 | FSA_ROF-PHTGR-017-DN100-I16C00-Spool_R0 |  | 1129 | FSA Roof | Roof | FoamInside | TBH-ZAT-2025-02-28_Special | 2025-02-27 | 2025-03-18 | 2025-03-11 |  | 2025-03-13 | 2025-03-24 | Office 10.05.2025 |  |  | 2025-03-24 | 2025-04-16 | 2025-04-18 | 2025-04-18 | 2025-04-18 | 1859 | 193 | Working ISO delivered 14.04.25 - Spools to be checked |  |  | 194 | SEP | SEP | [5 empty] | Spool pieces not for Calc | System PHTG
95337 | FSA_ROF-PHTGR-018-DN080-I16C00_Spool_R0 | 0 | true | 1.66 | FSA_ROF-PHTGR-018-DN080-I16C00_Spool_R0 |  | 1129 | FSA Roof | Roof | FoamInside | TBH-ZAT-2025-02-28_Special | 2025-02-27 | 2025-03-18 | 2025-03-11 |  |  |  | Office 03/07/2025 |  |  |  | 2025-04-03 | 2025-04-03 | 2025-04-03 | 2025-04-03 | 1859 | 193 |  |  |  | 194 | SEP | SEP | [5 empty] | Spool pieces not for Calc | System PHTG
95338 | FSA_ROF-PHTGS-015-DN150-I16C00_Spool_R0 | 0 | true | 0.81 | FSA_ROF-PHTGS-015-DN150-I16C00_Spool_R0 |  | 1129 | FSA Roof | Roof | FoamInside | TBH-ZAT-2025-02-28_Special | 2025-02-27 | 2025-03-18 | 2025-03-11 |  | 2025-03-13 | 2025-03-24 | Office 10.05.2025 |  |  | 2025-03-24 | 2025-05-12 | 2025-05-12 | 2025-05-12 | 2025-05-12 | 1859 | 193 | Working ISO delivered 14.04.25 - Spools to be checked |  |  | 194 | SEP | SEP | [5 empty] | Spool pieces not for Calc | System PHTG
95339 | FSA_ROF-PHTGS-018-DN100-I16C00_Spool_R0 | 0 | true | 1.11 | FSA_ROF-PHTGS-018-DN100-I16C00_Spool_R0 |  | 1129 | FSA Roof | Roof | FoamInside | TBH-ZAT-2025-02-28_Special | 2025-02-27 | 2025-03-18 | 2025-03-11 |  | 2025-03-13 | 2025-03-24 | Office 10.05.2025 |  |  | 2025-03-24 | 2025-05-12 | 2025-05-12 | 2025-05-12 | 2025-05-12 | 1859 | 193 | Working ISO delivered 14.04.25 - Spools to be checked |  |  | 194 | SEP | SEP | [5 empty] | Spool pieces not for Calc | System PHTG